## Table 1
|  |  |  | ASPHALT CONSTRUCTION INSPECTION AND TEST PLAN |  |  | Responsibilities
[7 empty] | Role Key |  | Name | Initial
[7 empty] | RM | Renewals manager | Reina Schmidt | RS
Project Number: |  | GT0550 | Project Name: | Bay of Plenty East NOC SH33 Maniatutu Rd Int |  |  | PE | Project engineer | Gemma Nieuwpoort | GN
[7 empty] | SE | Site engineer | Shivang Vyas | SV
Client: |  |  |  |  | Contract Number: | 2/14-001/601 | SP | Supervisor | tbc
ITP Description: | [6 empty] | QA | Quality assurance technician | tbc
Specification: | [6 empty] | FP | Foreperson | tbc
Drawings: |  | 033-0000-10160-10204-Maniatutu Rd Int-Rev3 |  |  |  |  | PM | Plant manager | Wayne Hardman | WH
ITP No. |  | Version No. | Reviewed Date | Reviewed By | Approved Date | Approved By | QM | Quality manager | Venely Bonita | VB
Written/Reviewed By: |  | Name: Gemma Nieuwpoort | Signature: |  | Date: 26/09/2025 |  | AM | Asset Manager | Ian Smit | IS
Approval by: |  | Name: | Signature: |  | Date: |  | QC | Quality Controller | Kobus Du Toit | KDT
Maintenacnce Contract Manager : |  | Name: | Signature: |  | Date: |  | CR | Client Representative (NZTA) | Steve Elvy | SE
Item No. | Task/Activity/ Description | Inspection/Test |  |  |  | Acceptance Criteria | Specification/ Contract Clause Reference | Verification Record Documents | Responsibilities | Comments/ Verification | Checked by
|  | Detail of Activity | Action (H/W/M/C) | Frequency | Inspection / Test method | [5 empty] | Printed Name | Company Name | Initial/ Date
1 | ASPHALT CONSTRUCTION INSPECTION AND TEST PLAN
1.1 | Contractor checklist | Obtain necessary Consents and Permits, and ensure differet lines of information are aligned | Check | Prior to commencement | Review | Items in checklist completed or send out for action | — | Contractor checklist | RM, PE, SE | —
1.2 | Previous lots completed | Confirm ITP items for underlying works have got confirmation and sign off received from client | Hold Point | Per site prior to commencement | Review | Sign off received | Project Specification | Copy of signed ITP | RM, CR | —
1.2 | Design | Ensure that the design is approved and drawings are of the latest revision | Hold Point | Prior to commencement and as required for revisions during the works | Review | Design document with principal approval signature | — | Design report | RM, CR | —
1.3 | Renewal Quality Plan | Quality plan for the site that looks at site specific requirements | Hold point | Prior to commencement | Review | RQP with principal approval signature | — | RQP | RM, CR | —
2 | Material Conformance Inspection
2.1 | Material Procurement
2.1.1 | Asphalt mix | Confirm compliant Mix design is in place | Hold Point | Prior to commencement with revision uploaded when it reaches expiry date; per mixtype and plant | Review | Dates valid and performance aligns with requirements SMA12.5 PG64V AC20 PG64V | NZTA M10 & M27 Mix design report submitted to NZTA | Approved JMF | RM | Approval of Contract Administrator &/or Design Engineer
2.1.2 | Material compliance | Confirmation of compliant materials used in mix | Hold Point | Prior to commencement with revision uploaded when it reaches expiry date; per mixtype and asphalt plant | Review | IANZ accredited test reports that meet relevant specification | M01 - A NZTA M10: 2020: sec 2 | Checklist | PE | All individual test reports need to be available for review by client as requested
2.1.3 | Lay down trial | review lay down trial records | review | Prior to commencement per mix | Review | Mix design results achieved | — | — | Sup, PE | —
2.2 | Material Production
2.2.1 | Production testing | Binder and Grading Testing - Particle Size Distribution and Binder Content | Check / Monitor | Minimum of 1 test for every 200T produced, per mixtype and asphalt plant | Field / Lab Testing | For individual tests: 1.18mm sieve and larger: ±8 0.600, 0.300 mm sieves: ±6 0.150, 0.075 mm sieves: ±3 For mean of 3 tests: 1.18mm sieve and larger: ±5 0. 600, 0.300 mm sieves: ±4 0.150, 0.075 mm sieves: ±2 | NZTA M10: 2020: 5.1-5.3 ; M27 | IANZ accredited test report | PE | When 3 or more tests are required for a project a rolling average can be calcuated. Tolerances are the maximum allowable on the JMF.
2.2.2 | Production testing | Volumetrics Testing - Maximimum Specific Gravity and Airvoids | Check / Monitor | Minimum 1 test for every 600Tproduced, per mixtype and asphalt plant | Field / Lab Testing | For individual tests: Binder content, percent by mass: ±0.5 Air voids: +2,-1 For mean of 3 tests: Binder content, percent by mass: ±0.3 Air voids: +1.2,-0.6 | NZTA M10: 2020: 5.1-5.3 ; M27 | IANZ accredited test report | PE | When 3 or more tests are required for a project a rolling average can be calcuated. Tolerances are the maximum allowable on the JMF.
3 | Construction process
3.1 | Site Setup
3.1.1 | Pre AC construction site checklist | Ensure everything is in place for works to go ahead and outstanding Items from contractor checklist have been actioned | Check/Monitor | week prior to paving | Review | Complete Pre AC construction site checklist | — | Pre AC construction site checklist attached | PE | —
3.1.2 | Go/No Go checklist | Ensure everything is in place and all outstanding items and previous holdpoints have been actioned or released. | Hold point | within 24 hours | Review | Complete go/no go checklist | — | Complete go/no go checklist | PE | —
3.2 | Paving Preparation
3.2.1 | Milling Depth | The existing road surface and underlying pavement shall be milled to the specified AC depth and area covered | Hold Point | 20m left right and centre behind the milling machine | Field Testing /Survey | SMA12.5 design thickness = 50mm AC20 = Design Thickness 100mm Minimum milling depth = 155mm | — | stringline sheet from QA pack Pictures for verification | QA Site Engineer | dipchecks behind the mill can be completed instead or in addition to stringlines
3.2.3 | Proofrolling | Proofrolling to be done on milled surface Use PTR or loaded Asphalt truck, to proofrol milled area's. If it shows movement or has loose material please contact renewals or cotracts manager. | Witness Point | Full surface area | Field testing | Surface finish shall present a tightly consolidated surface after sweeping. | — | Pictures or video Written communication if any additional instructions received | QA Site Engineer | —
3.2.5 | Membrane (Subbase Material only) | G4 or 5 Memberane | Witness Point | Prior to paving on exposed Sub Base | Visual Inspection | 1.0 l/m² residual binder minimum | NZTA M10: 9.3.2; | Spraysheet with RP's and pictures for verification | QA Site Engineer | Looks for stripping or any other damages. Spray vertical faces and transverse joints as well.
3.2.6 | Tackcoat (Asphalt) | An emulsion tack coat must be sprayed between all Asphalt Layers. | Witness Point | Prior to paving on top of existing Asphalt layer | Visual Inspection | 0.2-0.6 L/m2 | NZTA M10: 9.3.1; | Spraysheet(s) or pictures for verification | QA Site Engineer | Spray vertical faces and transverse joints as well
3.2.7 | Joint Preparation | Transverse joints to be milled/cut back to provide a square edge and emulsion must be handsprayed on the vertical face. Succesive transverse joints must be staggered by a minimum of 2m | Witness Point | All transverse joints | Visual Inspection | — | — | Pictures for verification | QA Site Engineer | —
3.3 | Asphalt Paving
3.3.0 | Structural Layer
3.3.1 | Temperatures | Delivery and compaction temperatures to be monitored throughout the paving process | Check / Monitor | Each truckload that arrives on site prior to paving | Infrared Thermometer | A minimum of -30 degrees from the recommended mixing temperature of 160-175°C To be recorded when mix is tipped into the paver. Manager to be notified if temperature falls below: AC20 PG64V 130°C | NZTA M10: 2020: Notes; Higgins asphalt bitumen guide, NZTA M1A 2019 | Mix tracking sheet from QA pack; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp on AC | QA Site Engineer | It is critical to ensure a temperature representative of the full load and not surface temperatures of the mix are measured.
3.3.2 | Layer thickness / Structural Asphalt | Monitor layer thickness throughout paving process. By keeping track of the spreadrates and performing dipchecks behind the paver. | Check / Monitor | For each truckload that gets paved, 1 mix tracking sheet per shift and a site diagram per layer | Survey, Field / Lab Testing | a minimum of 90% specified layer thickness to be achieved, but maximum minus 10mm of Specified layer thickness from design, with a minimum of 80mm per layer for AC20 PG64V. MINIMUM Thickness = 100mm as per design | NZTA M10: 2020: 9.7 and table 3.1 | Mix tracking sheet and site diagram in QA pack and photographic evidence to prove dipchecks have been performed | QA | These are deemed operational checks and will get verified through cores as specified in items 3.3.6 and 3.4.6
3.3.3 | Compaction | Plateau testing to be performed to set rolling pattern | Check/monitor | for each mix type | Field / Lab Testing | completed/not completed |  | Asphalt plateau density test sheet from QA pack | QA site engineer | —
3.3.4 | Compaction | Monitor compaction throughout paving process for quality control by the use of a NDM gauge | Check / Monitor | Minimum of 1 test per 20 linear meters per run and minimum 1 every 100m on Longitudinal Joints | Field / Lab Testing | Asphalt shall be uniformly compacted to the standards specified in clause 9.9.1 as soon as the asphalt has cooled sufficiently to support the compaction equipment without undue displacement. | NZTA M10: 9.9.1 - 9.9.2 | NDM sheet in QA pack Pictures for verification | Super Site Engineer Foreman PS QA | These are operational quality control checks and will be formally verified through cores as specified in items 3.3.5 .
— | — | — | — | As the Deeplift on this site is less than 30T it does not count as a lot and therefore no AC20 cores are required as per M10. | — | — | — | — | — | If there is any concearn for the AC20 having failed, contact manager prior to continue paving surface layer. To get additional instruction on whether or not to continue or postpone
3.4 | Paving - Surfacing Layer
3.4.1 | Temperatures | Delivery and compaction temperatures to be monitored throughout the paving process | Check / Monitor | Each truckload that arrives on site prior to paving | Field / Lab Testing | A minimum of -30 degrees from the recommended mixing temperature of 155-170°C To be recorded when mix is tipped into the paver. Manager to be notified if temperature falls below: SMA12.5 PG64V 125°C | NZTA M10: 2020: M27 Notes; Higgins asphalt bitumen guide, NZTA M1A 2019 | Mix tracking sheet from QA pack; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp on AC | QA Site Engineer | It is critical to ensure a temperature representative of the full load and not surface temperatures of the mix are measured.
3.4.2 | Layer thickness / Structural Asphalt | Monitor layer thickness throughout paving process. By keeping track of the spreadrates and performing dipchecks behind the paver. | Check / Monitor | For each truckload that gets paved, 1 mix tracking sheet per shift and a site diagram per layer | Survey, Field / Lab Testing | Average depth > min specified depth As per M10 for layer thicknesses below spec. an LCV of -5mm of specified thickness is allowed. Thickness Req: 50mm as per design | NZTA M10: 2020: 9.7 and table 3.1; M27 | Layer sheet and site diagram in QA pack and photographic evidence to prove dipchecks have been performed | QA | These are deemed operational checks and will get verified through cores as specified in items 3.3.6 and 3.4.6
3.4.3 | Compaction | Plateau testing to be performed to set rolling pattern | Check/monitor | for each mix type | Field / Lab Testing | completed/not completed | — | Asphalt plateau density test sheet from QA pack | QA site engineer | —
3.4.4 | Compaction | Monitor compaction throughout paving process for quality control by the use of a NDM gauge | Check / Monitor | Joint: 1 per 100m /minimum. 3 per Lot Mat: 1 per 300m2 / minimum. 8 per Lot | Field / Lab Testing | Asphalt shall be uniformly compacted to the standards specified in clause 9.9.1 as soon as the asphalt has cooled sufficiently to support the compaction equipment without undue displacement. | NZTA M10: 9.9.1 - 9.9.2 M27 | NDM sheet in QA pack Pictures for verification | Super Site Engineer Foreman PS QA | These are internal quality control checks and will be formally verified through cores as specified in items 3.4.5
3.4.5 | Cores | Cores to be taken post construction to prove layer thickness and air voids. | Check / Monitor | Joint: 1 per 100m /minimum. 3 per Lot Mat: 1 per 300m2 / minimum. 8 per Lot | Field / Lab Testing | Layer thickness testing :4no. core thickness tests to be taken before trimming. with a picture of each measurement. Accepted Airvoids = 2 - 7 % - Matt; 2 - 9 % Joint | NZTA M10: 2020: 9.7, 9.9, 10.3 M27 | IANZ Accredited Test Report Picture of each Core Coring Site Diagram in AC QA Pack | Site Engineer QA Foreman Paving Supervisor | —
3.4.6 | Overbanding/Joint Filling | Joints between new asphalt and existing surfacings are to be over banded with a suitable bituminous filler to prevent water ingress. | Monitor | Between Joints of Existing and new Asphalt | Visual Verification | Satisfactorily completed | — | Mention quantities of Bandage Seal in AC QA Pack Pictures uploaded into Site Diary of Procore | — | —
4 | Post construction
4.1 | Post seal inspection | Ensure the shape and levels of finished surface is acceptable | check/monitor | at completion of paving | visual verification/ field testing | Roughness - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Not more than 5mm under a 3m Straight Edge. Level - -0 < +5mm from Specified Level Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC. | NZTA M10 9.8 and M27 10.2 | Pictures and completion checklist | SE Sup | —
4.3 | QA Handover | — | — | For each site on the project | — | Over milled and Deep lift extents recorded and verified by Contract Engineer / QA Spray sheets for membrane area received by Contract Engineer from Sealing Team. Surfacing layer extents recorded and verified by Contract Engineer. | NZTA M10, M27 as appropriate and contract drawings | Evidence provided demonstrating full compliance with specified design | QA Site Engineer PE RM | —
4.4 | Linemarking and RRPM reinstated Matches previous linemarking - within 48 hours of sealing | On completion of surfacing pavement markings and reflective raised pavement markers are to be reinstated | Check Point | at completion of site | visual verification | Everything reinstated | MOTSAM | Pictures for verification | SE Sup PE | —
4.5 | Collec RAMM data | RAMM update to be completed | Check Point | at completion of site | Verification | completed/not completed | — | — | Surveyor CPM SE | —
5 | Final Sign Off
Client Final Inspection: The signature below verifies that this ITP has been completed in conformance with the contract requirements and and other relevant specifications.
Contractor's Rep Name: |  |  | Signature: |  |  | Date:
Contract Administrator: |  |  | Signature: |  |  | Date:
Project Manager Name: |  |  | Signature: |  |  | Date:
Quality Manager Name: |  |  | Signature: |  |  | Date:

## Contractor checklist
Contractor checklist
| Responsible | yes | no | N/A | comment - date started | initial
TMP
TMP request process started | PE
Design
Design review completed | PE
Design submitted for approval | RM
RQP set up | PE
RQP submitted for approval | RM
ITP set up | PE
ITP submitted for approval | RM
Comms
Draft Program send out | PE
Program checked against any events in the area | RM
Preseal inspection completed
Preseal inspection completed | Sup/SE
Site properly marked and aligned with design | Sup/SE
Any underlying concearns idetified? (further investigation required?) | Sup/SE
Trees to cut? | Sup/SE
Any lids needing adjustments? | Sup/SE
Are there traffic light loops going to be impacted? | sup/SE
other
Drainage
Are there any catchpits within the site that need protecting | Sup/SE

## Material compliance checklist
2.1.2 | Material compliance | Confirm binder compliance | Hold Point | once per shipment | Review | Binder grade | NZTA M01: 2022 | IANZ accredited test report/ NTC from WSP
2.1.3 | Chip | Source property coarse aggregate | Hold Point | 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009) | Review | Crushing resistance: <10% fines @200kN Weathering quality index: AA or BA Single Broken faces: 98%min Two broken faces: 60% min Bulk specific gravity and Density: Report only Absorption: Report only | NZTA M10: 2020: 2.1.2, table 2.1 | IANZ accredited test report/ NTC from WSP | Non compliant material can be approved by engineer when it comes from a source of proven performance
2.1.4 | Chip | Source aggregate fine aggregate | Hold Point | 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009) | Review | Crushing resistance: <10% fines @200kN Sand equivalent: 35 min OR Clay index: 3 max Bulk specific gravity and Density: Report only Absorption: Report only | NZTA M10: 2020: 2.1.3, table 2.2 | IANZ accredited test report/ NTC from WSP

## Pre AC construction checklist
Pre AC construction site checklist (week prior)
| Responsible | yes | no | N/A | comment | initial
TMP
Approved, dates correct and suitable for works | PE
Approved and notified | RM
Before you dig
Before you dig completed and all info received (valid 1 month) | PE/SE
Unison plans applied for and received | PE/SE
close approach first Gas applied for | SE
close approach power applied for (overhead or underground) | SE
Location services required? Who has been organised | SE
Any other close approaches applied for? | SE
Comms
Program send out | PE/SE
Letter drop completed | RM
Buisnesses notified; and high impacted buisnesses spoken to in person? | RM
Do program and tracker align? | RM
Do program and public notifications align? | RM
Do TMP and public notification align? | RM
Weather forecast looking acceptable? | PE
Preseal inspection completed
All required contractor checklist items actioned? | Sup/SE
Confident on resource availability? | Sup/SE
No change from design report | RM/PE
All holdpoints in ITP have been released | PE

## Go-No go checklist
Go/No go checklist (24hr)
| Responsible | yes | no | N/A | comment | initial
Weather
Rainforecast for duration of work (or first week) acceptable | Sup/SE
Temperature forecast for duration of work(or first week) acceptable | Sup/SE
Wind forecast for duration of work(or first week) acceptable | Sup/SE
If no to any of the above, please list impact on program or methodology change:
Before you dig
Close approaches received or booked in prior to requirement? | SE
Cable locate/GPR booked in | SE
Dig permit organised | SE
Comms
Comms requirements met | RM
Jobbrief send out | SE
Mix availability confirmed | SE
Gear on site or transport plan in place | Sup
Trucks confirmed | Sup
Membrane resources confirmed | SE
TM resources confirmed | SE
Milling resources confirmed | SE
Service cover adjustment resources confirmed | SE
Operational
Gear parking/toolbox area confirmed | Sup/SE
VMS in place | Sup/SE
No roadclosures/big TM delays expected on route to site | Sup/SE
Milling dumpsite organised | Sup/SE
All hold points in ITP have been released | PE

## Specifications
P11 | This specification describes the required properties of open graded porous asphalt for use as a surfacing course for road pavements.
M27 | The M27 stone mastic asphalt specification (version 1) and notes (version 1) cover stone mastic asphalt used as a pavement surfacing layer for roads and related applications.
M01-A | specification sets out the performance characteristics to be met by the binders used for asphalt manufacture.
M10 | The M10 dense graded asphalt specification (version 6) and notes (version 4) cover dense graded asphaltic concrete for roads and related applications.

## Sheet1
Document Information
Document Name: |  |  | 033-0000-10160-10204-Maniatutu Rd Int-Rev2-1 | [5 empty] | Status & Description: |  |  | Revision 2.1
Document Guarantor: |  |  | John Bezuidenhout | [8 empty] | Preliminary Version for Higgins Review
Document Patron: |  |  | John Bezuidenhout | [5 empty] | Written By: |  |  | Rosalie Collins-Gargan Date: 12 Jun 2024
Pavement Designer: |  |  | N/A | [5 empty] | Reviewed By: |  |  | Robert Tutty Date: 17 Jul 2025
Pavement Design Reviewer: |  |  | N/A | [5 empty] | Approved By: |  |  | Date:
SITE DETAILS | [7 empty] | Visual Observations |  |  |  |  | Design Traffic Volume
Site Name: |  | SH33 Maniatutu Rd Int
[8 empty] | Surface Defects: |  |  | Cracking Fretting / Scabbing |  | AADT (2024) | 7547
Lanes To Be Treated: |  | L1 L2 R2 R1 | [10 empty] | Heavy Vehicles | 13.2%
Site Type: |  | Intersection Signalised | [8 empty] | Flushing |  | Growth Rate | 4.7%
|  | Roundabout Steep Gradient | [8 empty] | Shoving |  | LDF / DF | 1 / 0.5
|  | Small Radius Curve | [5 empty] | Pavement Defects: |  |  | Rutting |  | NHVAG | 2.94
|  | Other Turning bay, very low volume | [8 empty] | Fatigue Cracking |  | NDT | 6620000
Posted Speed Limit: |  | 100 km/h | [8 empty] | Failure |  | ESA / HVAG | 0.544
T/10 Skid Resistence: |  | IL: 0.4 & 0.45 | [8 empty] | Pothole |  | DESA 10 Year | 3600000
Existing Surfacing: |  | Date: 9/02/2010 | [5 empty] | Other: |  |  |  |  | Comments:
Material: SMA
Depth: 100mm, based one one pit
Pavement Curvature (mm)
0.50 0.40 0.30 0.20 0.10 0.00 L1 R1 90th%ile Curvature Curvature Threshold
Pavement Deflection & Curvature Data
| L1 |  |  |  |  | R1 |  |  |  | Curvature Threshold¹: 0.23 (mm)
| d0 |  |  | Curv |  | d0 | Curv |  |  | Comments:
Minimum (mm) | 0.59 |  |  | 0.14 |  | 0.4 | 0.11 |  |  | This site has localised areas of high curvature.
Mean (mm) | 0.79 |  |  | 0.21 |  | 0.9 | 0.22
Maximum (mm) | 0.95 |  |  | 0.25 |  | 1.34 | 0.3
90th%ile (mm) | 0.92 |  |  | 0.24 |  | 1.3 | 0.29
95th%ile (mm) | 0.93 |  |  | 0.25 |  | 1.32 | 0.29
Standard Deviation | 0.12 |  |  | 0.04 |  | 0.38 | 0.08
1Thin Asphalt Surfacing Life Analysis and Guidelines (2017), Waka Kotahi NZTA
Older pit taken a few years back provided here for info
Pavement Test Pits
TP1 10165 R1 RWP 0 100 200 300 400 CBR 4% @ 500 mm 500 600 Surfacing Basecourse Subbase Subgrade
Design Notes
Design approach: - Evaluate the FWD pavement surface curvature, undertake field inspection, and consider strengthening the existing pavement where the curvature exceeds the selected threshold for the site, whilst also taking into account the current surface condition and the achieved life to date of that surfacing. Proposed Surfacing Treatments - Mill and Inlay: - Mill and replace 50mm of the existing surface with SMA12.5 on a waterproofing seal where indicated on the Treatment Plan. Proposed Strengthening - Mill and Inlay: - Mill an additional 100mm and replace with AC20 prior to SMA12.5 if indicated on the Treatment Plan. The nominated 100mm thick AC 20 strengthening depth, has not been formally ‘designed’, but has been provided as a practical option, based on design experience, practitioner input, and suitability relative to the AC20 maximum aggregate size. Formal asphalt designs using detailed materials testing and analysis using Circly or similar, generally provide significant depths of AC strengthening, (eg 150-170mm strengthening, plus the 50mm top surface). These are considered conservative, and excessive, given NZTA’s funding constraints. The report requires the milled surface to be proof rolled prior to the laying of any structural layer, and provides additional guidance if/where that ‘foundation’ may be found to be unsuitable. 100mm AC 20 strengthening depth, is considered a suitable cost effective treatment, and has been used successfully in EW NOC for the past few seasons.
Materials & Construction
Surfacing Materials
• SMA12.5 - PG64V binder • Grade 4 or 5 waterproofing seal where exposed milled surface is granular • Bitumen emulsion tack coat where exposed milled surface is asphalt and between asphalt layers • Skid and Texture requirements (T/10) - Refer to Treatment Plan for skid category site locations.
Strengthening Materials
• Structural layer - AC20 PG64V • Grade 4 or 5 bitumen emulsion membrane seal underneath AC20 layer
Construction Considerations
General • All works to be carried out in accordance with NZTA Specifications and the NOC contract requirements. • Construction quality control requirements are detailed in the Surfacing Renewal Quality Plan for this site and is approved separately to this document; however, it must be read in conjunction with this design report. Re-Surfacing (Mill & Fill) • The milled surface shall be inspected and proof rolled prior to placing of any asphalt layer. Proof rolling of the entire exposed area to be undertaken with a rubber-tyred roller or loaded aggregate / asphalt truck. Areas showing movement under proof rolling or having loose materials on the surface, shall be marked out for Strengthening Treatment as described below. • Where no strengthening treatment is required, the milled surface shall receive a waterproofing seal if granular (Grade 4 or 5 with at least 1.0 l/m2 residual bitumen) or a tack coat if there is already a waterproof surface prior to placing the new asphalt surfacing layer. Strengthening Treatment (Mill & Fill) • Strengthening Treatment shall be carried out if indicated on the Treatment Plan. • The milled surface shall be inspected and proof rolled prior to placing the structural asphalt layer as described above. Areas showing movement under proof rolling or having loose materials on the surface, shall receive Additional Strengthening Treatment - refer to details below. • Where no additional strengthening is required, the milled surface shall receive a membrane seal of at least 1 l/m2 residual bitumen prior to placing the asphalt strengthening layer. Additional Strengthening Treatment (Mill & Fill - 80mm AC20) • Locations determined on site. • Additional Strengthening includes the removal of an additional 80mm of pavement and replacement with AC20 on a membrane seal of at least 1 l/m2 residual binder prior to placing the asphalt strengthening layer.
Risks and Mitigation
Special features and requirements of the resurfacing that introduce or mitigate risk are identified below. Mitigations proposed as part of our resurfacing solution are also described.
Risk Identified |  |  |  |  | Potential Consequences | [6 empty] | Mitigation Proposed
Surface shape not meeting the specified requirements (Shape irregularities shall be no greater than 5mm under a 3m straight edge when measured transversely and longitudinally across the finished surface). |  |  |  |  | If there are shape irregularities in the adjacent pavement of greater than 5mm, and it is not practical to extend the treatment to a point where there are no shape irregularities, it is unlikely that either the specified rutting or roughness will be able to be achieved, at the tie-ins. | [6 empty] | Ignore tie-in shape for first and last 20m of site.
Roughness - The post construction determination of the roughness must consider the geometry of the site. In some cases, it is impossible due to changes in levels and constraints such as intersections and services to obtain the specified roughness levels. e.g where the site is an overlay treatment, or has tight geometric curves, or is too short, or is an in-lane treatment, or constrained by kerb. |  |  |  |  | Unable to meet PCDAR roughness requirements. Short site less than 50m long, so unable to get a 100m rolling average, and also includes a side road with incoming side road geometrics. | [6 empty] | Disregard PCDAR roughness performance. Capture straight edge shape measurements at time of construction.
Rutting |  |  |  |  | PCDAR rut measurement is unreliable for a short site. | [6 empty] | Ignore PCDAR rut measure. Capture straight edge shape measurements at time of construction.
Skid resistance |  |  |  |  | Insufficient skid resistance. Inability of the new asphalt surfacing to meet the Equilibrium SCRIM Coefficient. Loss of control & Crash risk. | [6 empty] | Site is on a slight hill with a low volume side road. A standard SMA aggregate (eg Taotaoroa) has been shown to be sufficient for skid in this environment. Site is very short, in any case
Cracking, pavement strength |  |  |  |  | There are areas on site where a thin asphalt surface (without any strengthening) will be insufficient to accommodate the existing pavement deflections/curvature. | [6 empty] | If any required strengthening is not undertaken, then the surface life will be severely compromised. If that is the case, NZTA accept the risk for cracking, rutting and roughness.
APPENDIX A - SITE LAYOUT PLAN
APPENDIX B - SITE PHOTOGRAPH
Figure 1: Cracking, ravelling, surface deterioration of the decreasing lane.