## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Asphalt | itp |  |  |  |  | ITP - Asphalt
section | 1.0 ASPHALT CONSTRUCTION INSPECTION AND TEST PLAN
checkpoint | 1.1 - Contractor checklist
label | Detail of Activity - Obtain necessary Consents and Permits, and ensure differet lines of information are aligned
label | Action (H/W/M/C) - Check
label | Frequency - Prior to commencement
label | Inspection / Test method - Review
label | Acceptance Criteria - Items in checklist completed or send out for action
label | Verification Record Documents - Contractor checklist
label | Responsibilities - RM, PE, SE
checkpoint | 1.2 - Previous lots completed
label | Detail of Activity - Confirm ITP items for underlying works have got confirmation and sign off received from client
label | Action (H/W/M/C) - Hold Point
label | Frequency - Per site prior to commencement
label | Inspection / Test method - Review
label | Acceptance Criteria - Sign off received
label | Specification/ Contract Clause Reference - Project Specification
label | Verification Record Documents - Copy of signed ITP
label | Responsibilities - RM, CR
holdpoint | HOLD POINT
checkpoint | 1.2 - Design
label | Detail of Activity - Ensure that the design is approved and drawings are of the latest revision
label | Action (H/W/M/C) - Hold Point
label | Frequency - Prior to commencement and as required for revisions during the works
label | Inspection / Test method - Review
label | Acceptance Criteria - Design document with principal approval signature
label | Verification Record Documents - Design report
label | Responsibilities - RM, CR
holdpoint | HOLD POINT
checkpoint | 1.3 - Renewal Quality Plan
label | Detail of Activity - Quality plan for the site that looks at site specific requirements
label | Action (H/W/M/C) - Hold point
label | Frequency - Prior to commencement
label | Inspection / Test method - Review
label | Acceptance Criteria - RQP with principal approval signature
label | Verification Record Documents - RQP
label | Responsibilities - RM, CR
holdpoint | HOLD POINT
section | 2.0 Material Conformance Inspection (2.1 Material Procurement)
checkpoint | 2.1.1 - Asphalt mix
label | Detail of Activity - Confirm compliant Mix design is in place
label | Action (H/W/M/C) - Hold Point
label | Frequency - Prior to commencement with revision uploaded when it reaches expiry date; per mixtype and plant
label | Inspection / Test method - Review
label | Acceptance Criteria - Dates valid and performance aligns with requirements SMA12.5 PG64V, AC20 PG64V
label | Specification/ Contract Clause Reference - NZTA M10 & M27 Mix design report submitted to NZTA
label | Verification Record Documents - Approved JMF
label | Responsibilities - RM
label | Comments/ Verification - Approval of Contract Administrator &/or Design Engineer
holdpoint | HOLD POINT
checkpoint | 2.1.2 - Material compliance
label | Detail of Activity - Confirmation of compliant materials used in mix
label | Action (H/W/M/C) - Hold Point
label | Frequency - Prior to commencement with revision uploaded when it reaches expiry date; per mixtype and asphalt plant
label | Inspection / Test method - Review
label | Acceptance Criteria - IANZ accredited test reports that meet relevant specification
label | Specification/ Contract Clause Reference - M01 - A NZTA M10: 2020: sec 2
label | Verification Record Documents - Checklist
label | Responsibilities - PE
label | Comments/ Verification - All individual test reports need to be available for review by client as requested
holdpoint | HOLD POINT
checkpoint | 2.1.3 - Lay down trial
label | Detail of Activity - review lay down trial records
label | Action (H/W/M/C) - review
label | Frequency - Prior to commencement per mix
label | Inspection / Test method - Review
label | Acceptance Criteria - Mix design results achieved
label | Responsibilities - Sup, PE
section | 2.0 Material Conformance Inspection (2.2 Material Production)
checkpoint | 2.2.1 - Production testing
label | Detail of Activity - Binder and Grading Testing - Particle Size Distribution and Binder Content
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - Minimum of 1 test for every 200T produced, per mixtype and asphalt plant
label | Inspection / Test method - Field / Lab Testing
label | Acceptance Criteria - For individual tests: 1.18mm sieve and larger: ±8
label | ○ 0.600, 0.300 mm sieves: ±6
label | ○ 0.150, 0.075 mm sieves: ±3
label | For mean of 3 tests: 1.18mm sieve and larger: ±5 0.
label | ○ 600, 0.300 mm sieves: ±4
label | ○ 0.150, 0.075 mm sieves: ±2
label | Specification/ Contract Clause Reference - NZTA M10: 2020: 5.1-5.3 ; M27
label | Verification Record Documents - IANZ accredited test report
label | Responsibilities - PE
label | Comments/ Verification - When 3 or more tests are required for a project a rolling average can be calcuated.
label | ○ Tolerances are the maximum allowable on the JMF.
checkpoint | 2.2.2 - Production testing
label | Detail of Activity - Volumetrics Testing - Maximimum Specific Gravity and Airvoids
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - Minimum 1 test for every 600Tproduced, per mixtype and asphalt plant
label | Inspection / Test method - Field / Lab Testing
label | Acceptance Criteria - For individual tests: Binder content, percent by mass: ±0.5 Air voids: +2,-1
label | ○ For mean of 3 tests: Binder content, percent by mass: ±0.3 Air voids: +1.2,-0.6
label | Specification/ Contract Clause Reference - NZTA M10: 2020: 5.1-5.3 ; M27
label | Verification Record Documents - IANZ accredited test report
label | Responsibilities - PE
label | Comments/ Verification - When 3 or more tests are required for a project a rolling average can be calcuated.
label | ○ Tolerances are the maximum allowable on the JMF.
section | 3.0 Construction process (3.1 Site Setup)
checkpoint | 3.1.1 - Pre AC construction site checklist
label | Detail of Activity - Ensure everything is in place for works to go ahead and outstanding Items from contractor checklist have been actioned
label | Action (H/W/M/C) - Check/Monitor
label | Frequency - week prior to paving
label | Inspection / Test method - Review
label | Acceptance Criteria - Complete Pre AC construction site checklist
label | Verification Record Documents - Pre AC construction site checklist attached
label | Responsibilities - PE
checkpoint | 3.1.2 - Go/No Go checklist
label | Detail of Activity - Ensure everything is in place and all outstanding items and previous holdpoints have been actioned or released.
label | Action (H/W/M/C) - Hold point
label | Frequency - within 24 hours
label | Inspection / Test method - Review
label | Acceptance Criteria - Complete go/no go checklist
label | Verification Record Documents - Complete go/no go checklist
label | Responsibilities - PE
holdpoint | HOLD POINT
section | 3.0 Construction process (3.2 Paving Preparation)
checkpoint | 3.2.1 - Milling Depth
label | Detail of Activity - The existing road surface and underlying pavement shall be milled to the specified AC depth and area covered
label | Action (H/W/M/C) - Hold Point
label | Frequency - 20m left right and centre behind the milling machine
label | Inspection / Test method - Field Testing /Survey
label | Acceptance Criteria - SMA12.5 design thickness = 50mm
label | ○ AC20 = Design Thickness 100mm
label | ○ Minimum milling depth = 155mm
label | Verification Record Documents - stringline sheet from QA pack
label | ○ Pictures for verification
label | Responsibilities - QA Site Engineer
label | Comments/ Verification - dipchecks behind the mill can be completed instead or in addition to stringlines
holdpoint | HOLD POINT
checkpoint | 3.2.3 - Proofrolling
label | Detail of Activity - Proofrolling to be done on milled surface
label | ○ Use PTR or loaded Asphalt truck, to proofrol milled area's. If it shows movement or has loose material please contact renewals or cotracts manager.
label | Action (H/W/M/C) - Witness Point
label | Frequency - Full surface area
label | Inspection / Test method - Field testing
label | Acceptance Criteria - Surface finish shall present a tightly consolidated surface after sweeping.
label | Verification Record Documents - Pictures or video
label | ○ Written communication if any additional instructions received
label | Responsibilities - QA Site Engineer
checkpoint | 3.2.5 - Membrane (Subbase Material only)
label | Detail of Activity - G4 or 5 Memberane
label | Action (H/W/M/C) - Witness Point
label | Frequency - Prior to paving on exposed Sub Base
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - 1.0 l/m² residual binder minimum
label | Specification/ Contract Clause Reference - NZTA M10: 9.3.2;
label | Verification Record Documents - Spraysheet with RP's and pictures for verification
label | Responsibilities - QA Site Engineer
label | Comments/ Verification - Looks for stripping or any other damages.
label | ○ Spray vertical faces and transverse joints as well.
checkpoint | 3.2.6 - Tackcoat (Asphalt)
label | Detail of Activity - An emulsion tack coat must be sprayed between all Asphalt Layers.
label | Action (H/W/M/C) - Witness Point
label | Frequency - Prior to paving on top of existing Asphalt layer
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - 0.2-0.6 L/m2
label | Specification/ Contract Clause Reference - NZTA M10: 9.3.1;
label | Verification Record Documents - Spraysheet(s) or pictures for verification
label | Responsibilities - QA Site Engineer
label | Comments/ Verification - Spray vertical faces and transverse joints as well
checkpoint | 3.2.7 - Joint Preparation
label | Detail of Activity - Transverse joints to be milled/cut back to provide a square edge and emulsion must be handsprayed on the vertical face. Succesive transverse joints must be staggered by a minimum of 2m
label | Action (H/W/M/C) - Witness Point
label | Frequency - All transverse joints
label | Inspection / Test method - Visual Inspection
label | Verification Record Documents - Pictures for verification
label | Responsibilities - QA Site Engineer
section | 3.3 Asphalt Paving (3.3.0 Structural Layer)
checkpoint | 3.3.1 - Temperatures
label | Detail of Activity - Delivery and compaction temperatures to be monitored throughout the paving process
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - Each truckload that arrives on site prior to paving
label | Inspection / Test method - Infrared Thermometer
label | Acceptance Criteria - A minimum of -30 degrees from the recommended mixing temperature of 160-175°C To be recorded when mix is tipped into the paver.
label | ○ Manager to be notified if temperature falls below: AC20 PG64V 130°C
label | Specification/ Contract Clause Reference - NZTA M10: 2020: Notes; Higgins asphalt bitumen guide, NZTA M1A 2019
label | Verification Record Documents - Mix tracking sheet from QA pack; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp on AC
label | Responsibilities - QA Site Engineer
label | Comments/ Verification - It is critical to ensure a temperature representative of the full load and not surface temperatures of the mix are measured.
checkpoint | 3.3.2 - Layer thickness / Structural Asphalt
label | Detail of Activity - Monitor layer thickness throughout paving process. By keeping track of the spreadrates and performing dipchecks behind the paver.
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - For each truckload that gets paved, 1 mix tracking sheet per shift and a site diagram per layer
label | Inspection / Test method - Survey, Field / Lab Testing
label | Acceptance Criteria - a minimum of 90% specified layer thickness to be achieved, but maximum minus 10mm of Specified layer thickness from design, with a minimum of 80mm per layer for AC20 PG64V.
label | ○ MINIMUM Thickness = 100mm as per design
label | Specification/ Contract Clause Reference - NZTA M10: 2020: 9.7 and table 3.1
label | Verification Record Documents - Mix tracking sheet and site diagram in QA pack and photographic evidence to prove dipchecks have been performed
label | Responsibilities - QA
label | Comments/ Verification - These are deemed operational checks and will get verified through cores as specified in items 3.3.6 and 3.4.6
checkpoint | 3.3.3 - Compaction
label | Detail of Activity - Plateau testing to be performed to set rolling pattern
label | Action (H/W/M/C) - Check/monitor
label | Frequency - for each mix type
label | Inspection / Test method - Field / Lab Testing
label | Acceptance Criteria - completed/not completed
label | Specification/ Contract Clause Reference -
label | Verification Record Documents - Asphalt plateau density test sheet from QA pack
label | Responsibilities - QA site engineer
checkpoint | 3.3.4 - Compaction
label | Detail of Activity - Monitor compaction throughout paving process for quality control by the use of a NDM gauge
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - Minimum of 1 test per 20 linear meters per run and minimum 1 every 100m on Longitudinal Joints
label | Inspection / Test method - Field / Lab Testing
label | Acceptance Criteria - Asphalt shall be uniformly compacted to the standards specified in clause 9.9.1 as soon as the asphalt has cooled sufficiently to support the compaction equipment without undue displacement.
label | Specification/ Contract Clause Reference - NZTA M10: 9.9.1 - 9.9.2
label | Verification Record Documents - NDM sheet in QA pack
label | ○ Pictures for verification
label | Responsibilities - Super Site Engineer, Foreman, PS QA
label | Comments/ Verification - These are operational quality control checks and will be formally verified through cores as specified in items 3.3.5 .
checkpoint-no-status | As the Deeplift on this site is less than 30T it does not count as a lot and therefore no AC20 cores are required as per M10. If there is any concearn for the AC20 having failed, contact manager prior to continue paving surface layer. To get additional instruction on whether or not to continue or postpone
section | 3.4 Paving - Surfacing Layer
checkpoint | 3.4.1 - Temperatures
label | Detail of Activity - Delivery and compaction temperatures to be monitored throughout the paving process
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - Each truckload that arrives on site prior to paving
label | Inspection / Test method - Field / Lab Testing
label | Acceptance Criteria - A minimum of -30 degrees from the recommended mixing temperature of 155-170°C To be recorded when mix is tipped into the paver.
label | ○ Manager to be notified if temperature falls below: SMA12.5 PG64V 125°C
label | Specification/ Contract Clause Reference - NZTA M10: 2020: M27 Notes; Higgins asphalt bitumen guide, NZTA M1A 2019
label | Verification Record Documents - Mix tracking sheet from QA pack; contains delivery temperature, temp when in paver, temp inside the screed and rolling temp on AC
label | Responsibilities - QA Site Engineer
label | Comments/ Verification - It is critical to ensure a temperature representative of the full load and not surface temperatures of the mix are measured.
checkpoint | 3.4.2 - Layer thickness / Structural Asphalt
label | Detail of Activity - Monitor layer thickness throughout paving process. By keeping track of the spreadrates and performing dipchecks behind the paver.
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - For each truckload that gets paved, 1 mix tracking sheet per shift and a site diagram per layer
label | Inspection / Test method - Survey, Field / Lab Testing
label | Acceptance Criteria - Average depth > min specified depth
label | ○ As per M10 for layer thicknesses below spec. an LCV of -5mm of specified thickness is allowed.
label | ○ Thickness Req: 50mm as per design
label | Specification/ Contract Clause Reference - NZTA M10: 2020: 9.7 and table 3.1; M27
label | Verification Record Documents - Layer sheet and site diagram in QA pack and photographic evidence to prove dipchecks have been performed
label | Responsibilities - QA
label | Comments/ Verification - These are deemed operational checks and will get verified through cores as specified in items 3.3.6 and 3.4.6
checkpoint | 3.4.3 - Compaction
label | Detail of Activity - Plateau testing to be performed to set rolling pattern
label | Action (H/W/M/C) - Check/monitor
label | Frequency - for each mix type
label | Inspection / Test method - Field / Lab Testing
label | Acceptance Criteria - completed/not completed
label | Verification Record Documents - Asphalt plateau density test sheet from QA pack
label | Responsibilities - QA site engineer
checkpoint | 3.4.4 - Compaction
label | Detail of Activity - Monitor compaction throughout paving process for quality control by the use of a NDM gauge
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - Joint: 1 per 100m /minimum. 3 per Lot Mat: 1 per 300m2 / minimum. 8 per Lot
label | Inspection / Test method - Field / Lab Testing
label | Acceptance Criteria - Asphalt shall be uniformly compacted to the standards specified in clause 9.9.1 as soon as the asphalt has cooled sufficiently to support the compaction equipment without undue displacement.
label | Specification/ Contract Clause Reference - NZTA M10: 9.9.1 - 9.9.2 M27
label | Verification Record Documents - NDM sheet in QA pack
label | ○ Pictures for verification
label | Responsibilities - Super Site Engineer, Foreman, PS QA
label | Comments/ Verification - These are internal quality control checks and will be formally verified through cores as specified in items 3.4.5
checkpoint | 3.4.5 - Cores
label | Detail of Activity - Cores to be taken post construction to prove layer thickness and air voids.
label | Action (H/W/M/C) - Check / Monitor
label | Frequency - Joint: 1 per 100m /minimum. 3 per Lot Mat: 1 per 300m2 / minimum. 8 per Lot
label | Inspection / Test method - Field / Lab Testing
label | Acceptance Criteria - Layer thickness testing :4no. core thickness tests to be taken before trimming. with a picture of each measurement.
label | ○ Accepted Airvoids = 2 - 7 % - Matt; 2 - 9 % Joint
label | Specification/ Contract Clause Reference - NZTA M10: 2020: 9.7, 9.9, 10.3 M27
label | Verification Record Documents - IANZ Accredited Test Report
label | ○ Picture of each Core
label | ○ Coring Site Diagram in AC QA Pack
label | Responsibilities - Site Engineer, QA Foreman, Paving Supervisor
checkpoint | 3.4.6 - Overbanding/Joint Filling
label | Detail of Activity - Joints between new asphalt and existing surfacings are to be over banded with a suitable bituminous filler to prevent water ingress.
label | Action (H/W/M/C) - Monitor
label | Frequency - Between Joints of Existing and new Asphalt
label | Inspection / Test method - Visual Verification
label | Acceptance Criteria - Satisfactorily completed
label | Verification Record Documents - Mention quantities of Bandage Seal in AC QA Pack
label | ○ Pictures uploaded into Site Diary of Procore
section | 4.0 Post construction
checkpoint | 4.1 - Post seal inspection
label | Detail of Activity - Ensure the shape and levels of finished surface is acceptable
label | Action (H/W/M/C) - check/monitor
label | Frequency - at completion of paving
label | Inspection / Test method - visual verification/ field testing
label | Acceptance Criteria - Roughness - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape.
label | ○ Not more than 5mm under a 3m Straight Edge.
label | ○ Level - -0 < +5mm from Specified Level
label | ○ Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC.
label | Specification/ Contract Clause Reference - NZTA M10 9.8 and M27 10.2
label | Verification Record Documents - Pictures and completion checklist
label | Responsibilities - SE, Sup
checkpoint | 4.3 - QA Handover
label | Frequency - For each site on the project
label | Acceptance Criteria - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA
label | ○ Spray sheets for membrane area received by Contract Engineer from Sealing Team.
label | ○ Surfacing layer extents recorded and verified by Contract Engineer.
label | Specification/ Contract Clause Reference - NZTA M10, M27 as appropriate and contract drawings
label | Verification Record Documents - Evidence provided demonstrating full compliance with specified design
label | Responsibilities - QA Site Engineer, PE, RM
checkpoint | 4.4 - Linemarking and RRPM reinstated - Matches previous linemarking - within 48 hours of sealing
label | Detail of Activity - On completion of surfacing pavement markings and reflective raised pavement markers are to be reinstated
label | Action (H/W/M/C) - Check Point
label | Frequency - at completion of site
label | Inspection / Test method - visual verification
label | Acceptance Criteria - Everything reinstated
label | Specification/ Contract Clause Reference - MOTSAM
label | Verification Record Documents - Pictures for verification
label | Responsibilities - SE, Sup, PE
checkpoint | 4.5 - Collect RAMM data
label | Detail of Activity - RAMM update to be completed
label | Action (H/W/M/C) - Check Point
label | Frequency - at completion of site
label | Inspection / Test method - Verification
label | Acceptance Criteria - completed/not completed
label | Responsibilities - Surveyor, CPM, SE
section | 5.0 Final Sign Off
checkpoint | Client Final Inspection: The signature below verifies that this ITP has been completed in conformance with the contract requirements and and other relevant specifications.
textbox | Contractor's Rep Name:
textbox | Contract Administrator:
textbox | Project Manager Name:
textbox | Quality Manager Name:
signoff | Signatures: