## CHK-CIV-RSS Pre-cast panel
ConQA Team Notes:
Document Title: |  | CHK-14-CIV-MSS-RSS Walls-Pre-cast Panel Installation
ITP Description: |  | RSS Walls - Panel Installation
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 02/10/2025
ITP created by: |  | Matthew Dib
ITP approved for use by: |  | Romualdo Magpantay
Special Notes to ConQA Team : |  | CHK to be used at Maidstone ONLY
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Panels survey set out tolerance | VR 682.20 IFC Drawings MRP-122-C-RFL-DRG-31-NPT-CSW-5101 | - Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations) | Measure | Base course panels | IP | Surveyor/PE | This Checklist Signed-off
2 | Mark-up panel for construction team | IFC Drawing: MRP-122-C-RFL-DRG-31-NPT-CSW-5121 to 5137 | - Mark number of strips per row on the back of each panel. - Mark design location (Wall number, row and column) as per elevation drawings on the back of each panel | Visual | Each panel | IP | SE | This Checklist Signed-off
3 | Panel installation | IFC Drawings | RSS Panels are to be installed as per IFC Drawings and specified schedule. - Check for correct architectural pattern - Check for Weephole Locations - Check the 1 in 40 slope is to be maintained - Check the 19mm nominal gap to be maintained / 25mm gap at slip joint location | Visual Measure | Each panel | WP | SE | This Checklist Signed-off
4 | Bearing Pad Installation | IFC Drawing: MRP-122-C-RFL-DRG-31-NPT-CSW-5103 | 3 x bearing pads must be installed per panel - Centre of the outer bearing pads must be 200mm+/-10mm from the edge of the panel - Install 3 Bearing Pads at rear on top of panels - Above must be checked with Surveyor prior to backfill - Note bearing pads shall not be installed under base row panels | Visual | Each panel | WP | SE | This Checklist Signed-off
5 | Panel installation - Abutment interfaces | IFC Drawings MRP-122-C-RFL-DRG-31-NPT-CSW-5115 RP-122-C-RFL-DRG-31-NPT-CSW-5116 | Panel installation and abutment interface: - 275 x 6 HD galvanised folded plate, drill and fix 150mm leg to abutment with Galv. M12x75 excalibur screwbolts at 500 crs - 600mm wide Bitac tape located centrally - RSS panel to be attached to abutment wall with anchor connection | Measure | Where applicable | IP | SE/PE | This Checklist Signed-off
6 | Panel Installation - Slip Joint Detail | IFC Drawings: MRP-122-C-RFL-DRG-31-NPT-CSW-5121 | Install slip joint detail - M16 Ferrule and grade 4.6/S M16x75 long bolt at 500 crs & Grade 250 6mm galvanised plate RW01 - Column 34 RW02 - Column 2 RW03 - Column 55 RW04 - Column 1 | Visual | Where applicable | IP | SE/PE | This Checklist Signed-off
6 | Filter fabric -Installation | IFC Drawings MRP-122-C-RFL-DRG-31-NPT-CSW-5103 VR682.11 | Install Filter Fabric against all vertical and horizontal joints | Visual | Each course of panel installation | IP | SE | This Checklist Signed-off
7 | Drainage-Strip Drain | VR682.11 | Install 300mm wide strip drain between precast wall panel vertical joints. Strip drain to be encapsulated by nonwoven geotextile in accordance with section 682.11 At every vertival joint between panels in RSS wall, ensure no gap is formed bewteen strip drian and RSS panels | Visual | Each course of panel installation | IP | SE | This Checklist Signed-off
8 | Panel installation-Survey reference points | VR 682.20 | To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS | Visual | Each course of panel installation | IP | Surveyor/SE | This Checklist Signed-off
9 | Traceability of precast units and records | VR 620.09 | Unique ID of precast panel is recorded. - ATTACH: marked-up elevation drawings or installation record with reference to panel ID | Visual | Each panel | IP | SE/PE | This Checklist Signed-off
10 | Panels installation-Conformance Survey | IFC Drawings VR 682.06 VR 682.17 VR 682.20 | The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions - Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall - Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm - Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full length of the gap - The wall level shall not deviate from the specified level by more than ±20mm - The tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height - The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V) Attach: Survey Report | Survey Measure | Each course of panel installation | HP* | Surveyor/PE | This Checklist Signed-off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /