## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
e3d53e95-f578-4f0b-a655-1aa84b32d151 | checklist | CHK-003-Civil-Material delivery inspection-Precast Pits and RCPs Rev 0 |  | CHK-003-Civil-Material delivery inspection-Precast Pits and RCPs
0185b4d9-ca54-478d-bfd6-11b9f7fa3ed3 | section | Details
2b64a5a4-b8ba-4c36-9cdc-0cfa9bfd5f87 | checkpoint-no-value | Referenced Documentation
875b1ce8-2c8c-575d-a77a-c2c9eecfdd3c | note | Document Title: CHK-003-Civil-Material delivery inspection-Precast Pits and RCPs
c351b7ca-7d86-53a4-8585-554c2da1576a | note | Checklist Description: Material delivery inspection-Precast Pits and RCPs
4f77f138-36c5-530c-976d-a9a5bda081af | note | Discipline (e.g. CIV/STR/RAIL): 003-Civil
1deae571-a919-51cc-b9f7-b46a10f7197b | note | Revision Number: 0
56c99700-742b-53c9-84e6-59b9136ee966 | note | Revision Date: 6/12/2023
d88fbe70-c8b2-593f-8719-600a0e9abd89 | note | ITP created by: Victor Mira
8f132e27-72bd-5cab-ab3b-a219151ab5be | note | ITP approved for use by: Victor Mira
da61488f-e3b7-4e85-96bd-11ff4ace40fd | checkpoint | 1 - Delivery Details
d42260c0-df66-565e-ac8e-bbd5a4f732e4 | note | Reference -
a3cbf84f-2072-539c-9ccf-1a94019c5b1b | note | Acceptance Criteria - Enter: Delivery Docket Number: [Free text box]:
42d5759a-059f-58fd-a84b-29ff6f8b8098 | textbox | Enter: Delivery Date:
fec7fca9-c8ac-5863-a369-061f9066f40e | textbox | Enter: Element ID (s):
63b0ba05-1797-5047-b034-0683cbf65ef1 | note | ○ Attach: Delivery Docket and packaging Slip
4b2b152a-0e32-554d-94de-676773854644 | note | Method - Document Review, Visual
da486c01-8d98-5ed7-8723-95573fad0b4f | note | Frequency - Each Delivery
19d1fdad-5cd1-58de-ae2f-a6df9c5960a7 | note | Category - IP
2d294c13-612f-5072-9958-b19eeb8933b2 | note | Responsibility - PE/SE
69b6330e-60d4-5d6a-a075-37650a935709 | note | Verifying Documents - This Checklist
8c10e752-9e88-55ce-af73-ef1025633284 | date | Date Completed:
fa573758-39f8-4c13-8cde-a10cd85b2c50 | checkpoint | 2 - Packaging Inspection-Quantity
3280434c-664f-5b17-8b41-5ffc244d35ac | note | Reference -
ce6d3483-0d12-5170-bff2-fca73ce0e70f | note | Acceptance Criteria - Does the number of packages in the delivery match that listed on the freight list/packaging slip?
4df00599-81ad-554b-9f8a-299ec7f2c4c2 | note | Method - Visual
66ffb5b4-8c54-512e-97a1-c615875f1db5 | note | Frequency - Each Delivery
1ddc245d-a04a-5566-a4a0-57784af2a1bf | note | Category - IP
29509a83-7022-58b3-9a61-2864d5c0c865 | note | Responsibility - PE/SE
2edac38b-76d8-5913-bea9-ad933c0b1515 | note | Verifying Documents - This Checklist
ea9f39ed-a883-5eb0-a7a9-240896416243 | date | Date Completed:
7d3215c9-f223-4123-8424-efd2289394e3 | checkpoint | 3 - Packaging Inspection-Delivery Contents
9faba7d5-f123-523e-a403-eed394ea6167 | note | Reference -
1d1ef1a3-fa68-5166-84c0-ced3d2cc1baf | note | Acceptance Criteria - Do the contents of the delivery match the freight list/packaging slip?
20f9578f-21ac-5bdb-a6f5-07eb813c4e7c | note | Method - Document Review, Visual
6a3b6257-5b72-556d-b783-7556806e55a7 | note | Frequency - Each Delivery
0210b7a7-66ff-5731-affe-c898fd5703ae | note | Category - IP
4bc70d62-7b30-5622-b5da-a7e2d270711e | note | Responsibility - PE/SE
451d4602-2339-55d0-8d39-4e2ee263e71a | note | Verifying Documents - This Checklist
29251626-c892-558a-b089-33d3edc48ba4 | date | Date Completed:
ff62109b-9a82-4802-987a-ce65030d65f1 | checkpoint | 4 - Packaging Inspection-Birth Certificate
36dd4061-06bd-5b79-bad6-b440e12c0c21 | note | Reference -
c13fc6f9-3340-583d-ad33-92084d7de150 | note | Acceptance Criteria - Is the delivery accompanied by Precast items Birth Certificates?
3bf1ed09-c45a-5e6b-9482-4b4a34dcaab5 | note | ○ Precast components are to be marked on the birth certificate.
2659ad95-67ca-5334-a877-90bae700eb4c | note | ○ Cast date and lot are to be marked on the birth certificate.
2b4fd31f-55aa-5521-b67b-9737c3b987bf | note | Method - Document Review
885f63f5-d2cd-5ee6-a2bc-195d127d7855 | note | Frequency - Each Delivery
a9bcefe5-24b6-5a94-a215-0f81b1264626 | note | Category - IP
632b1642-4afb-5c6d-ab27-fbb15c8c6e87 | note | Responsibility - PE/SE
11874622-f9c8-52fc-8100-16fb3ff03143 | note | Verifying Documents - This Checklist
b8a71fb1-d8af-583d-b505-86ffa77d080c | date | Date Completed:
436ae6b4-f3ed-41af-ad89-2277b6d3941d | checkpoint | 5 - Packaging Inspection-Transport
b12ff482-0b62-5b60-bcd2-e8f80c770e6b | note | Reference -
a224ef95-123c-59c9-8174-58ecce3549e5 | note | Acceptance Criteria - Is the condition of packaging acceptable.
2177435d-ddd7-504a-b307-3ebc320a4c0c | note | ○ Precast items are protected from damage during the transport
385c3d17-174a-5f2e-a6f7-5e09940f6d0b | note | Method - Visual
e89bd68f-04db-59a6-8d51-68b39e16eea1 | note | Frequency - Each Delivery
9f8cff80-15ef-558c-859d-a8cbcf2cc12c | note | Category - IP
76eab21d-31c4-5e51-ad7b-5f72ef91abac | note | Responsibility - PE/SE
2622d2a5-7f28-55e4-a754-c047cbf8c1e3 | note | Verifying Documents - This Checklist
b5661c5d-f832-50ae-9579-a256eb20f7d8 | date | Date Completed:
bde8ca9e-1d9f-419b-9e59-4a8cc527848a | checkpoint | 6 - Fault IDs:
347340ff-cc39-577c-9c5f-048fff320c60 | note | Reference -
89b99d54-ab4a-5a8d-8d03-18bbf03f657d | note | Acceptance Criteria - For each precast type delivered, check for the following:
febc8b1c-da88-5dac-abb8-ebcac9bbcc13 | note | 1 - Identification markings match the Precast type
e6d35934-8641-5663-b0eb-1e79e7fa21e5 | note | 2 - Precast Pit fabricated as per drawings - inverts size.
6b1c5a48-8156-53b6-86bb-4c512b9aced7 | note | 3 - Precast Pit Fabricated as per drawings - Inverts position (Distance from the bottom and edges).
a6d08161-2d38-5661-95ef-0d135850a4e3 | note | 4 - Precast Pit Fabricated as per Drawings - Invers Position - Correct Wall (orientation).
ab9a697d-1aad-5ce6-90f3-e61935d09113 | note | 5 - Precast Pits - Inverts coliding.
9f4b0523-f2f5-5064-8883-d19c80e9a0b7 | note | 6 - Precast Pits and RCPs - Inspect for Cracks.
bdae63f5-82ea-55df-b0ec-13b2f319a0d9 | note | 7 - Precast Pits and RCPs - Inspect for Spalling/Damage to concrete surface.
69ccffab-7c56-5abb-be4f-58c979e19864 | note | 8 - Precast Pits and RCPs - Inspect for Exposed Reinforcement.
6b138135-6cc0-5fdc-ab94-55cecbeaa8d3 | note | 9 - Precast Pits and RCPs - Inspect for correct Lifting mechanism.
efe614f5-0895-5b4a-8c37-a4271cc7ee5c | note | 10 - RCPs - Inspect rubber rings
139b7bb1-dc06-55d3-b1be-ef2233922398 | note | 11 - Precast Pits and RCPs - Inspect for other fabrication defects (specify on the following lines)
c12ab59a-63c3-5482-9e75-2c8099c3ca71 | note | Method - Visual, Measure
0b3174b4-510b-5e05-b269-1413b2314765 | note | Frequency - Each Delivery
98a0ac3d-19bf-5a85-add6-24157f51bdda | note | Category - IP
9789921f-d9fb-5c91-b399-b5774b370a9c | note | Responsibility - PE/SE
21023909-7708-506e-ae1e-b846f0457628 | note | Verifying Documents - This Checklist
33099aba-4b18-5c03-9949-93cfccafd2c4 | date | Date Completed:
19ae6607-ee93-4832-bca7-e5a68356d625 | checkpoint | 7 - Check for Faults - 1
5d5a82c1-b6ab-53b3-bd56-ebcfdc45544b | note | Reference - Item 6 on this Checklist
88d2b393-7566-5f86-a829-7d2b5dd496a9 | note | Acceptance Criteria - For Each Precast type delivered:
a0b91d07-7667-5484-837c-8eafb20a5dce | textbox | Enter: Panel Identification:
e4c64cf0-9150-5d10-b1a8-56d8862a5808 | textbox | Enter: Quantity:
e05aed2c-3f27-55a7-a426-8abfc1c09249 | textbox | Enter: Fault ID if any:
173158fd-5d09-55d8-8067-94ac23ba35f0 | note | Method - Visual, Measure
3b6b061d-2a5c-5b3a-8068-8b228b29f7a6 | note | Frequency - Each precast type delivered
cdfb7b42-3ba1-5da2-a850-9248af30dd01 | note | Category - IP
b41b7bd6-b026-5443-bdd4-a8db2de623ea | note | Responsibility - PE/SE
ed8e7c07-8f61-5535-96fb-98f636367909 | note | Verifying Documents - This Checklist
060484cc-0a19-58ef-9900-c698d3d06fdd | date | Date Completed:
b1fffe04-b798-40b5-9d38-fc8866361bb0 | checkpoint | 7 - Check for Faults - 2
c0b43eed-9c75-5cfd-bfdb-15087425d1de | note | Reference - Item 6 on this Checklist
9b4adef8-82c9-59bb-a1f6-9ffe48bdfc2e | note | Acceptance Criteria - For Each Precast type delivered:
6184592e-49f0-5541-b173-aed03c574ead | textbox | Enter: Panel Identification:
690d1921-59f4-5b8b-a6a9-975f1f0bee60 | textbox | Enter: Quantity:
b9ca90af-6ce5-5a1e-a3fc-9186d1540aef | textbox | Enter: Fault ID if any:
a1f7a7b9-f93b-5829-84f6-d9b7d6ec4890 | note | Method - Visual, Measure
1a6726b5-4349-51d8-b0cf-1af50da4b951 | note | Frequency - Each precast type delivered
8147d376-4b16-5a56-9b18-ea79d38e6c6e | note | Category - IP
6638ec9a-772c-5401-a78a-4c3b29d095de | note | Responsibility - PE/SE
2f4ad40a-f9b5-5de4-bc79-f6fa2645c648 | note | Verifying Documents - This Checklist
57e6daab-b9e8-5b6f-8884-e3dbd12d75fd | date | Date Completed:
ab08fc55-a293-46c6-8d0d-f74ce9d4a8b7 | checkpoint | 7 - Check for Faults - 3
72080c10-1d99-59b7-80fc-96904456f8e3 | note | Reference - Item 6 on this Checklist
9e7191f8-469c-59c3-a61d-9b270768087d | note | Acceptance Criteria - For Each Precast type delivered:
b34155e5-99c6-5848-a6f1-0fb01d7025de | textbox | Enter: Panel Identification:
24a965b4-e4e3-5469-a027-af07641cf6a1 | textbox | Enter: Quantity:
a8f23341-c17d-5115-b05e-0c3f3576d56f | textbox | Enter: Fault ID if any:
77720c75-1237-539f-b79a-bc9b6851ea08 | note | Method - Visual, Measure
db14efe1-ceae-5fda-b200-ebf394dec791 | note | Frequency - Each precast type delivered
2fd24d5c-262e-5b31-9321-f1930e4f236b | note | Category - IP
6f4b239f-d083-50c8-9a65-29be093235c6 | note | Responsibility - PE/SE
ac4b0d88-f91b-575f-bdd5-c354e5a6ce82 | note | Verifying Documents - This Checklist
941c4d10-f666-59f6-b381-e91e2ea4a636 | date | Date Completed:
f93b4060-6cee-4b9b-9085-0e218f0ed446 | checkpoint | 7 - Check for Faults - 4
8ef39548-9e8a-5178-886a-c22f11029de5 | note | Reference - Item 6 on this Checklist
cb20668e-3405-5dfc-9f61-434488caf1b9 | note | Acceptance Criteria - For Each Precast type delivered:
61b9380a-5932-51db-ae25-58780cbe011a | textbox | Enter: Panel Identification:
14955b34-b91a-52a3-bbf2-2bc16a1f1af2 | textbox | Enter: Quantity:
36c303f2-488a-56fa-82e0-738202f05a05 | textbox | Enter: Fault ID if any:
2ecd06d2-5084-5fe6-a89b-f8083917f6de | note | Method - Visual, Measure
5ea5b9fe-df04-5b9b-aca3-4129026839db | note | Frequency - Each precast type delivered
f79029bb-ad48-5498-8e64-fe112e45a9df | note | Category - IP
a906cace-81ef-5d6d-8935-15ddc33e7237 | note | Responsibility - PE/SE
82d0e298-3a41-5517-bb0d-187c467970ec | note | Verifying Documents - This Checklist
54957289-3d7f-5612-b89e-7e96b4b89a63 | date | Date Completed:
ca12dd9f-2491-49e2-a48e-13b261a7d356 | checkpoint | 7 - Check for Faults - 5
37a2933a-c444-5db5-baab-f49a6f71f37f | note | Reference - Item 6 on this Checklist
f39785ac-ea7e-5eb5-bcc4-6d811a01f35b | note | Acceptance Criteria - For Each Precast type delivered:
c2dc97ec-04c2-5a52-ac98-778839421149 | textbox | Enter: Panel Identification:
c5e1d5b6-d793-55d0-9dc2-04ff437c1e1c | textbox | Enter: Quantity:
6425cf0d-d437-5f86-9a54-9d8c034e98ab | textbox | Enter: Fault ID if any:
78835fb9-8267-5435-bc4c-a17d12092849 | note | Method - Visual, Measure
f3895bee-7d03-511c-b33f-04d47fe81681 | note | Frequency - Each precast type delivered
2967ab88-16de-58d8-8b01-b851483d4288 | note | Category - IP
1b747d03-eaae-514a-b1a2-7d66f0f177f8 | note | Responsibility - PE/SE
a6d2cb1d-02f8-5b7e-ac11-97019e6aaa7a | note | Verifying Documents - This Checklist
c60a427b-855c-5c35-87cf-2204f9206131 | date | Date Completed:
73866b9f-980e-4eac-9f7d-334d97b3349a | checkpoint | Final Inspection
9a6c6abc-75b6-5f9e-8751-0e50fb14d912 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
ac4f9ec9-218a-5434-b9f8-56376c74f867 | textbox | Name:
094d6312-5721-57ef-b53b-b34ed0d04ceb | textbox | Position:
6b276d8c-8481-514e-ad13-85fe8b586d32 | date | Date Completed:
a8f0d196-86b2-45e5-b3d8-a32f7f1fec9c | signoff | Sign ITP
1a7e3373-f520-4fa7-b0ca-eaced959f382 | checklist | CHK-017-CIV-ADL-Stormwater Drainage Pipes Installation Rev 0 |  | CHK-017-CIV-ADL-Stormwater Drainage Pipes Installation
0c92049d-ace4-4d94-9a69-148fa3ca802f | section | 1. Referenced Documentation
b8be57f1-6752-4367-a9fa-f2884f88e82b | checkpoint-no-value | Referenced Documentation
23430a07-718b-54bb-b09e-e72631aa7bed | note | Document Title: CHK-017-CIV-ADL-Stormwater Drainage Pipes Installation
e47e5cd5-16b7-5d15-a70e-34ed277540c0 | note | Checklist Description: ADL-Stormwater Drainage Pipes Installation
e3fd2e3d-5316-55dc-8a46-0821992aa148 | note | Discipline (e.g. CIV/STR/RAIL): 017-CIV
c44607b3-441e-56bb-81b0-50f14831d193 | note | Revision Number: 0
06696043-7020-5f79-805b-fb169a9711f5 | note | Revision Date: 12/06/2025
b74b1423-01eb-5b25-b0d2-3c63fae6257c | note | ITP created by: Abhi Patel
fc1d9e2e-1137-5c8d-91a4-0bda0cc58c90 | note | ITP approved for use by: Aldrin Guinchoma
7e51c832-75fc-5c30-991f-2ab4069f3daf | note | 1.1 - Non Dependent
cf28f398-4798-5350-926f-043289d84753 | note | Reference - VR 701
fac18fa3-04c9-5064-a328-fe1b1717a7bb | note | 1.2 - Main ITP
e8b287fe-ac9e-524b-9536-edf85479635c | note | Reference - ITP-284-CIV-ADL-Stormwater Drainage ITP
849e984e-c264-5fb7-85bf-28f7e1bab70e | note | Acceptance Criteria - This ITP Should be used in Conjunction with ITP-284-CIV-ADL-Stormwater Drainage ITP
e50c2eb4-601e-5037-bc71-dd0c8d5272e8 | textbox | Enter: Main ITP Teambinder Lot Number
5717e051-9b6d-464c-9e46-03f2e0d55852 | section | 2. Preliminaries - Materials
cec340a2-038b-4305-a09f-0fee9f590296 | checkpoint | 2.1 - Bedding
dd7d3163-1517-58bc-84dd-0ee0f740b9f5 | note | Reference - VR 701
df6888dd-e4e9-5ff2-a12b-20e673bc5927 | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
d2d07ac7-ad2b-51d4-8d90-fbc8fb5c477d | note | Method - Document Review
d249e61d-c57a-5aed-8a20-7fb3ca1d98a5 | note | Frequency - Each Lot
062ecdca-192b-5e87-b6ca-089c83cde6a8 | note | Category - HP*
02a7c44e-cf84-53ac-80ba-d0d9565bf6ad | note | Responsibility - SE
e5755a22-94cd-5198-ab19-b4d4b6f56cba | note | Verifying Documents - Material Delivery Docket
98d69033-89de-5246-84d9-40a8119d94af | date | Date Completed:
c9ef817e-01e9-4245-85cb-9be413014d4e | checkpoint | 2.2 - Backfill Material
e2b6ba2b-e5b8-5a85-837b-6d8dc4b06e70 | note | Reference - VR 701
ae2c4960-3ed6-5f8b-a5f8-367b1aafe092 | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
feca33fb-85d9-54e3-b340-8324c23ee7df | note | Method - Document Review
d3bc30aa-8bff-5df4-9f26-b32a9153109a | note | Frequency - Each Lot
e4e01f4e-2ec9-51a3-8062-53c449f50d4c | note | Category - HP*
63e6034f-0606-54b7-944b-876aef684826 | note | Responsibility - SE
7a12e0fa-c9af-5346-b3b2-ec4ecccfa1ea | note | Verifying Documents - Material Delivery Docket
2b2ae87f-d084-5ac3-ad5b-c18d242acac7 | date | Date Completed:
f2c3987b-9b52-457a-a59e-fa3593053970 | checkpoint | Stabilized Sand
f4d74a72-cfc9-5b49-b782-912843778b9b | note | Reference - VR 701
1ac93a6d-a414-5710-a0b8-4f6022b68aa5 | note | Acceptance Criteria - Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe
25dd98cb-bb81-57e9-acdf-bb9e9848e621 | note | Method - Document Review
bcf195b9-eedd-50e6-8b42-d0f59bcd9195 | note | Frequency - Each Lot
d92087e5-49ef-5c80-8348-8091f9143a46 | note | Category - HP*
c436c266-520b-5198-8a77-f2374a0b0d9a | note | Responsibility - SE
7c68e4b0-05bd-518d-a38a-308383d7524c | note | Verifying Documents - Material Delivery Docket
6e7a8b2a-217b-5526-b0ef-40b34b994b7d | date | Date Completed:
9e93b01e-118a-4b1f-955a-902934924182 | section | 3. Preliminaries - Procedures & Documentation
761fbd9a-dd98-4de4-a06f-280c27c836a2 | checkpoint | 3.1 - Subcontractor QA Submissions and ITP
45230073-b0fb-5ded-b15b-de697b4beb85 | note | Reference - ITP-284-CIV-ADL-Stormwater Drainage ITP
43f49943-a496-55bb-8e81-b40dc6cd8ad4 | note | Acceptance Criteria - Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
ac93cb56-06d0-5547-80eb-2c1f576f3250 | note | ○ ATTACH: Subcontractor Signed ITP
ddac949f-44c1-5e1b-ad49-abf962d3d8de | note | Method - Document Review
395d97d0-d0fa-5595-81f3-f79e300e9aba | note | Frequency - Each Lot (in case undertaken by subcontractor)
a113a7e6-d63a-5760-92eb-6b23d4ad4536 | note | Category - HP*
557bc6da-b1b4-5d3c-8d69-2207166e2778 | note | Responsibility - SE
12fca977-a623-54d7-836e-1819972060f1 | note | Verifying Documents - ConQA Hold Point Release
89bb555b-d91c-5747-8961-e9ab1aefb8d6 | date | Date Completed:
b164afba-e56e-40d0-a78d-4e98e90b3e1e | section | 4. Pre-construction Activities
5b6df943-5dca-404c-8816-7a45e7e129b5 | checkpoint | 4.1 - Survey Set-Out-
67f3a234-f06a-5756-b2dc-6d00e96c5447 | note | Reference - 710.1
1eb9d903-99fc-5703-95dc-15e54499a7b1 | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
bf5e333f-930a-517a-82a2-6ea506f43f41 | note | ○ The culverts constructed shall be constructed true to line and level.
acdaa5ec-23af-5035-95b6-41fe70bdc499 | note | ○ MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
2f298ff8-7254-5f62-b4cf-ce18da822442 | note | Method - Survey, Measure
0c4e77c8-83d0-52c1-9353-39a925c7fb37 | note | Frequency - Each Lot
9b7e2d38-49bf-5a6b-b801-f35893a9cfa8 | note | Category - HP*
5efd9385-fa5d-57f9-b118-978d2621e13e | note | Responsibility - SE
814e2c35-44a2-5f0f-aca4-dda156606a5f | note | Verifying Documents - This ITP, Main Lot Map
a1ad8bb5-52ca-5055-a0e8-5f2ff07ec97b | date | Date Completed:
a673f65c-9168-4ebd-9105-f77e7503e15d | section | 5. Construction Activities
d642809b-4c9b-4a60-93f4-0374f992a3c4 | checkpoint | 5.1 - Trench Excavation
3b0e3a12-cc68-5770-9d64-70118bd23326 | note | Reference - VR 701.15
dd61594d-d733-5c84-a1bb-7bd27310726c | note | Acceptance Criteria - For box culverts, the width of the trench shall be such that the clearance from the outside of the culvert to the wall of the trench is in the range 0.5 to 1.0 times the overall height of the culvert.
90188ba2-ef33-5fa1-9535-7bc9cc35f707 | note | ○ Horizontal Clearance to wall of trench
b32e2c6a-6799-556e-88ea-74de882bf09b | note | Pipe Culverts:
4d54318e-6169-5e97-a48e-f2e3e6071062 | note | ○ 300mm<Horizontal clearance for corrugated metal culverts<1000mm
8fdbc0b4-1a13-5cc9-ba1a-ba54a1786ed4 | note | ○ 300mm<Horizontal clearance for other Pipe culverts<600mm
00f3fb4e-ba85-5e3b-9843-e42349dddf35 | note | Box Culverts:
151c080b-82a5-5e05-ba88-c2bce4b16186 | note | ○ 0.5 times the height of the culvert<Horizontal clearance<overall height of the culvert
4504d7e0-84ec-52e1-8823-0e6196027437 | note | Method - Measure
4f765936-ba8f-5cec-a14a-c74b757d5800 | note | Frequency - Each Lot
d296fc91-a26d-51df-b631-8bd6f104b732 | note | Category - IP
639da4bd-eac7-5141-877c-43b2c01adc7d | note | Responsibility - SE
efb9b652-1e30-54ae-814e-af9cddc01856 | note | Verifying Documents - This ITP
68e63e28-b89f-58fb-bd27-04a5d17c386e | date | Date Completed:
d951a85d-647e-4057-b954-169482ab5bbe | checkpoint | 5.2 - Trench Base
fe3b0b70-b65d-54a7-b38c-e43b3397e310 | note | Reference - VR 701.15
0a0adaf0-bd0a-5ba9-a6cc-baa87ecc46cf | note | Acceptance Criteria - The base of the trench shall be compacted to refusal using mechanical plant
ce8338ec-3b55-5e61-84f6-79a8e07c3309 | note | Method - Visual
6e8a5267-9c8b-5a69-9224-40209f25994a | note | Frequency - Each Lot
f2f90537-b5e6-5609-b597-eadd4b425134 | note | Category - SP
820c4035-c9cc-51bf-8f76-b75cdba73c9f | note | Responsibility - SE
6c4ab3ba-ff7d-5b65-984c-00c567b0a382 | note | Verifying Documents - This ITP
27051211-773a-5ca9-a538-9ecefc8a197a | date | Date Completed:
81a2aa83-4da6-4582-9a72-b8ac7eae0f70 | checkpoint | 5.3 - Bedding-Placement and compaction
9716c6fa-51c6-5169-b298-5a084f114703 | note | Reference - VR 701.16, VR 701.20 (a)
a3e2f4d6-0e17-5648-aa3d-4be6b1f159b2 | note | Acceptance Criteria - Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be not less than:
5bbd6c06-e859-5aef-805d-b000f8a75f6f | note | — 100 mm where D < 1500 mm
55f601bc-83da-5b93-9cd8-ea465720ea50 | note | — 200 mm where D ≥ 1500 mm
d44ccc01-574a-5de3-96a6-2a55b9220efb | note | ○ Bedding materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer
6c5cd708-761f-5d8c-92d8-a786e36df80f | note | Method - Visual, Measure
a6d3a4b4-c48d-5d1c-9a6d-6b5969e2ad0b | note | Frequency - Each Lot
85a83922-27dd-56e2-82ed-7dc4b24cb1ca | note | Category - SP
c849aac7-a406-5cb2-ba69-e8748602c674 | note | Responsibility - SE
ca903861-ba6a-5124-9b61-fa2c88df6538 | note | Verifying Documents - This ITP
0b8bddd7-7e9a-5f7f-b8dc-96247885f852 | date | Date Completed:
c15d25ed-b623-4728-983e-96e02dabbd3a | checkpoint | 5.4 - Laying pipes-Bedding conformity
4d79191e-3070-596c-a97c-005464f49de6 | note | Reference - VR 701.17
1a92341c-a118-5def-973d-7e113086035e | note | Acceptance Criteria - Laying of pipes or box culverts shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and that box culverts and pipes are not damaged.
20b060cb-80b7-568e-a773-7c82cbd3f55d | note | ○ Laying of pipes or box culverts shall commence from the downstream end.
49970587-2a40-51d0-b747-a113511a7a22 | note | Method - Visual
b38aef81-cac8-5f8c-8a88-48b92970a66b | note | Frequency - Each Lot
fa9d8fac-d6c9-55ca-bcf0-e44dbdea836e | note | Category - HP*
b864aa3d-fc87-5c70-a323-e6969cd2aca4 | note | Responsibility - SE
cd6c3ddc-1557-519f-b836-29a5dcb317a2 | note | Verifying Documents - This ITP
a2716996-f0ed-512c-955e-78b74f10a89e | date | Date Completed:
905ee30e-e8d1-4197-98dd-ec4108e16f6f | checkpoint | 5.5 - Pipe Laying
1ca5dec3-78df-56e3-bb31-3e2938284873 | note | Reference - VR 701.16, VR 701.17
019f993e-6599-554a-9648-7e3665a4bb21 | note | Acceptance Criteria - Laying of pipes or box culverts shall commence from the downstream end.
9706b725-395f-54e9-a967-f86616f51ec1 | note | ○ Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered.
05daa6a8-8fea-526e-8ddb-dace4a5cb935 | note | ○ The lower portion of the pipe shall be in contact with the bedding for the full length of each section.
cc8f83dd-afc5-54b3-ad2e-ae61e6d846ad | note | ○ The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
821673f2-d9fd-5b33-9f94-c83acb224736 | note | ○ When the sections are in position, an additional layer of bedding material shall be placed to a height equal to 30% of the nominal pipe diameter or culvert height
ee2aa1ed-be36-5cd5-9316-0ebfb234e80e | note | Method - Visual
f0d1be5d-5457-5064-800f-8409c67b8240 | note | Frequency - Each Pipe
f601dae6-1a26-5c8a-a358-c13e0ad3618b | note | Category - SP
041e0fb7-3748-5ba3-bbda-6d0ee84e9048 | note | Responsibility - SE
a04118bf-3a7e-5441-b3e7-1f5506f219e4 | note | Verifying Documents - This ITP
1764afe1-29fd-53e8-8d22-42c6a7f4f10f | date | Date Completed:
76c619bd-ec16-447d-a6b7-d750c37d36fb | checkpoint | 5.6 - Pipe Joints and rotation
2e8c5d48-9edf-5524-b0a2-bfa1ca4a4ad9 | note | Reference - VR 70.18
89d680e5-832d-54e4-b9bb-371e054a0ce8 | note | Acceptance Criteria - All interlocking RCP shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
e6bc4823-0075-5fec-9fe5-9f9a68d915ae | note | ○ Pipes shall be laid with lifting holes uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. .
edd63bcb-c6a5-5af6-80e3-b521fb5fa101 | note | Method - Visual
4d24513e-0310-596b-a06b-95fc2625c679 | note | Frequency - Each Pipe
a435f594-c276-5cc2-98e2-711a5cb07bf9 | note | Category - SP
6d5cfd28-5100-54fe-bc70-b4877efb1100 | note | Responsibility - SE
1a260d4e-c583-59b1-8ef9-1a0a9ea11552 | note | Verifying Documents - This ITP
d0bd4003-cd95-533d-990d-709b98810100 | date | Date Completed:
d890ecd9-6688-4719-81ba-c1c3379f5cdc | checkpoint | 5.7 - Conformity with drawings
707a4926-c956-5b7a-9fbb-82d0ed7587d4 | note | Reference - VR 701.10
2ea08427-e72e-5d0e-bbb6-898007213c89 | note | Acceptance Criteria - The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
5941f08b-466d-5410-956f-dca51c9459ce | note | ○ Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
7e0e957d-c547-5d43-b24a-eba1f54694d0 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
8dd64e4b-1ed3-5cdf-880c-d81ecd365cd4 | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
8da693d6-724f-52e4-9489-45a3e4d44b13 | note | (c) invert level of pipes at pits ±50 mm
71d4d610-acac-56ed-983e-f4422f1967c4 | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
eac8e392-c653-5196-8965-6bc2c2a106a8 | note | ○ ATTACH: Survey Report
a365d964-17ed-545b-a721-6f5e061ce437 | note | Method - Measure
65e3dde7-aa7a-580c-8324-e09d6b0aa7b0 | note | Frequency - Each Lot
af4db3cf-e029-54d6-bdc6-b5919df02ff9 | note | Category - HP*
3dfb614e-bbc7-5036-8d53-224a19eacaeb | note | Responsibility - SE
59d39290-d143-5c67-8195-3a718db83efa | note | Verifying Documents - Survey Report
ffb46bea-1b73-5a89-98b3-5b268091e6f9 | date | Date Completed:
f7baf61f-2268-4aeb-90dc-771ca490e6bb | checkpoint | 5.8 - Backfill-Under area to be paved
2c94c389-c62e-5733-96e8-696644d1c2dc | note | Reference - VR 701.19 (a) i
d0cff7c5-6328-5320-b2d1-a45375c5f984 | note | Acceptance Criteria - Culvert under area to be paved
b98333f2-2ad9-578d-93f3-2970f7d7f893 | note | ○ Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
a14b8c42-1131-5759-bd8b-113bacb8dba9 | note | ○ Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material.
1216d5f3-e854-5bec-a000-1a54727b7672 | note | Method - Visual
1d80c36d-9a60-5d11-b6c4-b952fe1edf6c | note | Frequency - Each Lot
cc328865-1e92-5e8a-9a5c-7cb946e68221 | note | Category - SP
3cea2e32-04d7-5f14-9e5a-544d0a521887 | note | Responsibility - SE
e0253636-6519-58a5-8c6e-29df312df22c | note | Verifying Documents - This ITP
93b61925-e3d1-55a6-8d77-920d51149493 | date | Date Completed:
2788a8b3-0544-41f1-9489-17576f4f6c7c | checkpoint | 5. 9 - Backfill-Under area not to be paved
e7fa6617-2ec1-595d-8126-499d7caa2556 | note | Reference - VR 701.19 (a) ii
b9c3154c-2813-5daa-a0c9-4005fe517889 | note | Acceptance Criteria - The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level
c79f549d-1290-5623-9e31-fa25ea73ed9a | note | Method - Visual
fc4d6084-2882-5392-8904-9fc949cda4b3 | note | Frequency - Each Lot
dc4efda8-2647-5e75-9de8-5e70d2aac97a | note | Category - SP
105e3c6d-2af1-579c-89e1-e2f7b6a3717c | note | Responsibility - SE
b87b5c3b-41f2-5ba2-ac92-4ef75b3544b9 | note | Verifying Documents - This ITP
9d49013f-198f-5b47-b33f-b4b103f47784 | date | Date Completed:
75f1e8f6-cb7d-4dfe-95fd-5a5ea6355c40 | checkpoint | 5.10 - Backfilling with cement stabilised sand
eb1754b5-d460-5df8-ad67-59cf1a5d76f7 | note | Reference - VR 701.19 ( c)
4d9a99ac-ef1a-54d6-8cae-4da425c21014 | note | Acceptance Criteria - Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height
e6e952af-0efa-595f-8db2-68f2b063b179 | note | Method - Visual
2198ce44-4d24-5417-897a-49d995384040 | note | Frequency - Each Lot
fde2660f-5e9f-5db5-b489-107888d7e92a | note | Category - SP
cae9084a-8eb8-5358-b3a1-0ed5892189aa | note | Responsibility - SE
146fa201-c577-5f37-8457-c871853de33b | note | Verifying Documents - This ITP
7e1caf71-cd80-50a3-9362-2cf96ba19031 | date | Date Completed:
17b9c0de-b489-4a89-8dd1-8680efe4ef56 | checkpoint | 5.11 - Backfill Placement
61132126-e79a-5fae-b4eb-8bdadc95901b | note | Reference - VR 701.20
b6a308c8-76e9-5f54-8028-01d7dad49e5b | note | Acceptance Criteria - backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
a0fe64a3-9f11-5b42-8923-dc4893d87646 | note | Method - Visual
bad43252-f414-599f-9471-9064019dbdc2 | note | Frequency - Each Lot
938e449b-5fb9-565d-9d8e-a6ae50e76624 | note | Category - SP
0180cdb1-e178-5250-8421-f2775f13cdc2 | note | Responsibility - SE
c8b83e7b-30db-51e7-a9f0-0e13e8ad9759 | note | Verifying Documents - This ITP
c5945f2c-7ef7-50eb-92c7-fd0a4868833f | date | Date Completed:
2fa785d9-00c4-4398-88c1-7144e0e226e5 | checkpoint | 5.12 - Backfill Compaction
3a61fd20-f9f1-54d6-a971-2023b4edd009 | note | Reference - VR 701 (b)
9985f311-078b-575f-af12-a6dc2425211f | note | Acceptance Criteria - 20% of all bedding/Backfill layers for each culvert shall be tested.
8a176df4-4516-56b3-af5a-b682dab6da6a | note | ○ Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%.
4749771e-c8af-54f7-8db1-bc959276d0cc | note | ○ Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
27089db6-ea06-5d72-af15-a1a61d0272af | note | Method - Test
c697534f-a0ce-57c9-a3f6-8a59eb9e1b4e | note | Frequency - Each Lot
b60fffff-ac19-542b-91cb-f28039b15bc2 | note | Category - HP*
2cd62205-c6c5-5024-9b07-ecda63103b4a | note | Responsibility - PE
c10ebe33-788e-57e8-9595-bd22fb03ff0c | note | Verifying Documents - This ITP
23ee3d24-378f-56da-907e-d72e11e835a0 | date | Date Completed:
3a3908ce-f9fa-4f77-a5e0-c1b046049899 | section | 6. Post-construction Activities
0930a950-7950-467e-8db0-cf940559d491 | checkpoint | 6.1 - Compaction and Moisture content tests
53844d67-6d7b-54c9-8dec-e00c069b3d14 | note | Reference - VR 701.20
7f724a07-a6f2-5459-a889-a8d9fe57a9c4 | note | Acceptance Criteria - Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls.
3ca62449-9721-53b2-bd18-bc0beac2b0a9 | note | ○ Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
61a2ca3b-39eb-5736-952f-962b18e8906e | note | ○ ATTACH: Compaction and Moisture content test results:
9dc4d190-2c5d-51ee-9e8b-86c92ef17c4f | note | Method - Document Review
e6aa6551-41da-5943-9e52-c13f592d89bc | note | Frequency - Each Lot
14b1c3ff-153b-5688-b5aa-fb87bb42002b | note | Category - IP
789a7d00-9f33-52d3-8288-2bad742f8ab5 | note | Responsibility - SE/PE
953ea86b-e40c-5f0a-8c32-de4d10f1575b | note | Verifying Documents - Test Results
0c0a9bd4-c4cd-5442-891e-19f66d164a78 | date | Date Completed:
ea1c71df-0458-43c8-aa86-3f45809b45aa | checkpoint | Final Inspection
f872c0ae-c0cd-5f85-a8a9-ee319cf4b7c1 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c2c6175c-1b9d-5004-b635-c87231bdd05f | textbox | Name:
29629098-b238-55d7-8201-5dc097724cfc | textbox | Position:
8fa12c4b-703d-5651-814c-8d4386eeda75 | date | Date Completed:
4377beeb-fc26-4a25-8e9c-39874c93a88e | signoff | Sign ITP
e29ea96f-2017-4f02-8394-f27c7ca5ccfd | checklist | CHK-018-CIV-ADL-Stormwater Drainage Pits Installation Rev 0 |  | CHK-018-CIV-ADL-Stormwater Drainage Pits Installation
8e132aed-efd4-4368-9e11-baa460ba1745 | section | 1. Referenced Documentation
0cb17564-a9ed-40ed-bc0f-3f06903aaa47 | checkpoint-no-value | Referenced Documentation
5d455c7e-93f4-5ce8-8001-877a46669e71 | note | Document Title: CHK-018-CIV-ADL-Stormwater Drainage Pits Installation
eec8db0e-259e-5f7f-89bb-ac5a1865df2a | note | Checklist Description: ADL-Stormwater Drainage Pits Installation
903844ed-78f8-5c1d-9c91-54228d9d630d | note | Discipline (e.g. CIV/STR/RAIL): 018-CIV
0424176a-73c7-5415-9cec-ab93da8d8a88 | note | Revision Number: 0
0cf034df-e9b4-58a5-b42d-573050484f6a | note | Revision Date: 12/06/2025
954c033a-b16d-55d5-9e4c-6f908f9e9cfa | note | ITP created by: Abhi Patel
64d87d62-a9fa-5cff-a367-41ca98d1e453 | note | ITP approved for use by: Aldrin Guinchoma
42221807-93d1-5d97-ba98-fe6743dbdeec | note | 1.1 - Non Dependent
005ebed4-0a0d-5bdd-bc3a-6f5edb3738f0 | note | Reference - VR 701
0ade695e-9143-51b8-8760-159440d7cb01 | note | 1.2 - Main ITP
348ade3e-c503-5662-ae6d-c64568a73010 | note | Reference - ITP-284-CIV-ADL-Stormwater Drainage ITP
7c69279b-6d8b-51f2-adc2-b20105326934 | note | Acceptance Criteria - This ITP Should be used in Conjunction with ITP-284-CIV-ADL-Stormwater Drainage ITP
df91cc4e-3701-5674-bbf1-aefced9dd45d | textbox | Enter: Main ITP Teambinder Lot Number
9edf0ad4-4adb-4217-a01b-a4ecebe2b35b | section | 2. Preliminaries - Materials
55892f3c-ad06-4fc9-b336-a2fc98f8e361 | checkpoint | 2.1 - Bedding
cecacedf-b9e2-5f1a-b02b-4e85418c875d | note | Reference - VR 701
7bd7bc9a-3df6-5026-9808-4406bf325375 | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
0563dd18-a618-5ef8-99c0-8f85884ee5a9 | note | Method - Document Review
d5c9e034-8e94-580b-9d56-6d40cd76a030 | note | Frequency - Each Lot
46a7d1d6-efff-5f92-8a19-f2a634dd5327 | note | Category - HP*
16de8cf0-ed36-5f16-ad27-0d7035e6851d | note | Responsibility - SE
ab92d990-95fc-5a91-bb0c-aa17e5320f72 | note | Verifying Documents - Material Delivery Docket
1634fea5-2f5d-5229-83ac-e13112e00981 | date | Date Completed:
1ab873a7-4eed-4ed3-95bd-a139e706623b | checkpoint | 2.2 - Backfill Material
edf3dc55-da77-579b-bba7-b60595ed3026 | note | Reference - VR 701
75ef1475-eddb-5501-9926-25ad597445c7 | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
d150a3a8-001f-54e8-a9ad-b8f711db1312 | note | Method - Document Review
f08d0cc8-3871-5407-88c5-4d93430ff95d | note | Frequency - Each Lot
505e3c14-f48a-5a08-b013-22c54b52ddac | note | Category - HP*
a94ca157-4e36-5e4f-bde7-f08634a8feb7 | note | Responsibility - SE
f828fad9-e127-5d8c-aa3d-33a1e56ef5aa | note | Verifying Documents - Material Delivery Docket
776e92a3-3273-5d1c-a6b8-e74fbfaaf8d2 | date | Date Completed:
14a08841-9175-45e5-ad86-75578391e557 | section | 3. Preliminaries - Procedures & Documentation
6a4c161c-a6c2-4971-99f3-f262c712de74 | checkpoint | 3.1 - Subcontractor QA Submissions and ITP
b4eb0d03-09e9-523e-8f71-0af990c49334 | note | Reference - ITP-284-CIV-ADL-Stormwater Drainage ITP
fa17cf1c-4d50-5e51-9e8f-3703b4f46191 | note | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications..
7e3c1993-87dd-51d3-916b-a3dde540e5c8 | note | ○ ATTACH: Subcontractor Signed ITP
c3a5de8e-4fbe-5f28-8293-e872cd56252d | note | Method - Document Review
01b9e592-9b86-5b9e-aae9-1f61b9e0ef28 | note | Frequency - Each Lot (in case undertaken by subcontractor)
43380ace-f4d7-5393-a5a6-3b488e831d81 | note | Category - HP*
4b571863-595c-5193-8486-844a7f5511e2 | note | Responsibility - SE
24ad12e3-b7b1-5a85-8c0f-c4b528c2759d | note | Verifying Documents - ConQA Hold Point Release
a4382a72-9149-5d61-987f-fa9fd4c7e087 | date | Date Completed:
a08a4476-efb6-4d04-b303-b692c04f6a3e | section | 5. Construction Activities
00862958-6b83-43d5-ba4f-27b4c9c68907 | checkpoint | 3.1 - Survey Set Out
0a3d7990-735f-580c-90a0-619f940554c9 | note | Reference - VR 701.10
2351f980-917a-5b69-bd3a-60bdef4b84f3 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10
dd003b6c-c275-52ce-9c86-7b6bd18daf66 | note | Method - Visual inspection
678f6068-732c-50fc-82c8-d683380bea1a | note | Frequency - Each Lot
b08e11bc-2252-5567-a6dc-ab5ff9ed81b7 | note | Category - HP*
719db574-fd38-5433-bc78-e7d538e8eed1 | note | Responsibility - SE
703984ba-2d94-534f-aea8-52724cab076e | note | Verifying Documents - This ITP
e6a48d7a-f894-5eaf-b12c-a33a5097328c | date | Date Completed:
2529f659-3f22-49a2-a99f-5226aa78701c | checkpoint | 3.2 - Pit Excavation
1daa434d-72d6-5f11-8d8d-70ff58654926 | note | Reference - VR 705.05
6096ab4d-6fe6-54b7-937b-6b05ca44b01f | note | Acceptance Criteria - Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
5ea31f81-f3fe-5f5b-b69f-ca5e35611a67 | note | Method - Visual inspection
19227ace-77b4-5f16-b36f-d441e4ab4e4b | note | Frequency - Each Lot
0cb504c2-1cbb-5b2a-b908-0e8f740b1ed0 | note | Category - IP
87f75f51-15ac-5bc0-8f0b-cc13c2eb55d5 | note | Responsibility - SE
5316d25d-3ffc-5d4c-b7f0-50c1803245e2 | note | Verifying Documents - This ITP
00cb4ee3-100e-55cb-b6d1-29d5f325918b | date | Date Completed:
afbd3c75-87c1-4d48-8af7-2e9a70a2d1d0 | checkpoint | 3.3 - Excavation Foundation
c979deb8-9ef0-504d-97bd-7086948f6bd9 | note | Reference - VR 705.05
6b384119-a860-57cb-bb2b-a696d55672f0 | note | Acceptance Criteria - Bedding conforming to to 710.09 shallbe supplied, placed and compacted to a thickness:
2224f032-0c6c-5e1c-b190-47258eaf03d6 | note | ○ > 80mm for clay foundations
8a6ede6b-98eb-51be-a0e4-851eb5880639 | note | ○ > 150mm for rock foundations
c42bc58a-c9cd-5920-9812-78a030d72e68 | note | Method - Visual inspection
434dffb4-ddb2-563f-9a13-328c2d936cbc | note | Frequency - Each Lot
a8ca552e-73e4-5167-8002-a77ec2c021d0 | note | Category - IP
0de0371b-9925-5f27-b0e1-d54619909e92 | note | Responsibility - SE
2fca786b-6491-5f1b-8b55-b12efb633e51 | note | Verifying Documents - This ITP
a2de2fd5-2506-54fb-a780-15f3422bced1 | date | Date Completed:
531e7554-bac3-472a-ab85-77c363d9629e | checkpoint | 3.4 - Jointing
3dfbcd9d-91fa-529f-98ed-e6d8a99a701a | note | Reference - VR 705.11
bf9cf9ef-5bf0-55ca-bdc6-b6308a3e0ca5 | note | Acceptance Criteria - All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
5868fde4-242b-53c7-b1d2-59b8f52b7b13 | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment
13587863-eee7-5dab-b143-74ed45c17635 | note | Method - Visual inspection
86ba42ab-6e47-5052-8578-8a9f0aece924 | note | Frequency - Each Lot
eeb7701c-7615-59d6-a6bb-42721d7f973e | note | Category - IP
ff1291aa-7432-538c-b0cb-857a5dfcaf2f | note | Responsibility - SE
da48086f-a355-574d-8150-dea9c8245262 | note | Verifying Documents - This ITP
1b53dcf5-3edd-5bb5-81a7-1710389fa690 | date | Date Completed:
22ac7669-445e-4680-b314-04398e5b566b | checkpoint | 3.5 - Shaping of Floor
92fe2ca4-f614-557c-a9ec-b6cf4e80414f | note | Reference - VR 705.13
64d2b67f-bed2-5d31-a8ce-1e97be39fc59 | note | Acceptance Criteria - Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
c9e9e069-29a1-5408-a6f3-0ba62bee3a95 | note | Method - Visual inspection
d62d28b7-62e4-51ca-8de2-ce6cb5097e25 | note | Frequency - Each Lot
ff84feaa-bc2c-50bf-a8d3-b6c718a06354 | note | Category - IP
4c9e0442-5a22-5d89-809d-6244dec121ef | note | Responsibility - SE
029647c6-9c03-5ac9-82ec-94bfd1b88e12 | note | Verifying Documents - This ITP
2b6032df-0851-5774-b026-58fbf2a97e7d | date | Date Completed:
c32f2274-3220-4d0b-9834-62b3536deb51 | checkpoint | 3.6 - Step Irons
8fa04a6d-208f-5b45-89ac-5626ef8ba223 | note | Reference - VR 705.12
12d93738-bf9d-538c-83ad-30a5fa3dc8cb | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder rungs shall not obstruct openings and that water does not discharge on them.
c6190189-e054-58b2-bea7-f35fbae6b3cb | note | Method - Visual inspection
430c4514-7638-54fc-93cc-db5abf73b6c8 | note | Frequency - Each Lot
756fc0ff-6cdb-5c71-8728-03cc28e9608c | note | Category - IP
3917398d-61d6-5495-80f2-0f99580ebc8a | note | Responsibility - SE
7f49f517-cc9c-5b9d-87e3-ac09f9e25a61 | note | Verifying Documents - This ITP
808e3dbb-03a6-59e9-b70d-88ec45135a79 | date | Date Completed:
a2286366-8ba7-44f3-ac02-a74a7fb7b721 | checkpoint | 3.7 - Fitting of Covers
8d9b09f0-235e-5a91-8b97-ea5699eade46 | note | Reference - VR 705.17
4f45d000-3e24-507d-8c70-e7b7fb74d116 | note | Acceptance Criteria - Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
f20d0c56-7236-5141-a4e9-11290b9731f1 | note | ○ Height shall be within 10mm of the design level
b1697fc7-16e1-54e8-af0c-cd0bd9b125fa | note | Method - Visual inspection
8afdced9-f8be-57bb-82cf-a6e9cdf932e6 | note | Frequency - Each Lot
b1dd339b-0603-550b-abb1-21d4d859d354 | note | Category - IP
84add1c5-9389-5234-a4eb-c7bb0e1285d7 | note | Responsibility - SE
e2723e9d-b9d7-5efc-9e45-bb07bbf609c1 | note | Verifying Documents - This ITP
4c463f8f-6bf5-5c5c-a711-38c18de8272f | date | Date Completed:
c8a9c20d-a90b-4b4d-82b6-8c7ca53ab553 | checkpoint | 3.8 - Backfilling Around Drainage Pits
b887dae2-434f-5b06-bd08-de6411bcd7f1 | note | Reference - VR 705.18
de30232a-7ec0-58e1-a720-0197b857cb86 | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal
205a1842-ee58-57b1-b091-a74ad24c8916 | note | Method - Visual inspection
3a551164-3a91-59c0-b626-7592f3f790d2 | note | Frequency - Each Lot
e1ac4057-da34-5a63-8ab7-fcb2c31616f0 | note | Category - IP
b7284fa0-7916-5009-9fe6-f192a20c566f | note | Responsibility - SE
b1bcfdd9-3667-5c94-be28-637080b16dbf | note | Verifying Documents - This ITP
df0a0990-e0d6-5f73-85f8-c2aae1b770fa | date | Date Completed:
562f8152-b166-44c2-96ff-c99dcf675ff8 | section | 6. Post-construction Activities
d741856c-be48-4982-a8c6-c4247fdff7c9 | checkpoint | 6.1 - Placement of Pit-Conformity with drawings
f7daf13f-a89d-5d61-bc52-84b2bc0fa47e | note | Reference - VR 701.10
97e0d0fa-1970-523c-b0ef-360a40665a4c | note | Acceptance Criteria - The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
d63ed77d-7603-54e1-9df8-80378d473069 | note | ○ Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
4ed54c6b-6058-56eb-99b5-df3fa589b198 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
8e730b81-0e0b-5fcc-82a5-6f6a1fb73c6a | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
5d57076d-d88b-575f-8191-b2fb8c5f509a | note | (c) invert level of pipes at pits ±50 mm
98e35553-f1e5-5a1d-af65-82072ca7cdc1 | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
60f92289-b3c3-5413-a81d-5906a077eafd | note | ○ ATTACH: Survey Report
38b4e9fb-674f-5d6e-aed6-295165772d06 | note | Method - Measure
d057dbfa-1175-5684-ad74-11fb17915fb8 | note | Frequency - Each Lot
e7e7dbd2-9ce4-5358-868e-5c37670c78b6 | note | Category - HP*
3ae32538-4ed5-5d66-848d-e94f21cd087d | note | Responsibility - SE
5c1235ed-7dbf-5f69-80df-5397aee49700 | note | Verifying Documents - Survey Report
8e4da822-5f79-5ed8-9e3d-6f6f0b78f306 | date | Date Completed:
4c3f9735-01b4-45d5-aed2-e7084092f17d | checkpoint | Final Inspection
e080d8dc-e6fa-50c8-8dc1-86eeb4e3b843 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
6fa8cbe8-3c1d-5e57-a575-62d6164a518a | textbox | Name:
5fe46054-5f0e-5c8b-abc0-9ecd76568174 | textbox | Position:
2f6d3d38-6db4-5447-b715-d5b04ac9b85e | date | Date Completed:
7daba98a-ce75-4c93-96c5-33b162b1dd69 | signoff | Sign ITP
9e24f68d-f5c5-4ae1-9989-bf0272ff87f7 | checklist | Handover Walkthrough Report |  | Handover Walkthrough Report
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
274f55ef-7d8f-4e7a-84c3-54ddd23c7a88 | checkpoint-no-value | Project Details
4bc67576-c36b-5624-a0d6-330765d434ad | note | Alliance Name: Metropolitian Roads Program Alliance (MRPA)
93ffa6a4-d095-518d-9233-521eb10035a9 | textbox | Project Name
15fe2c86-5b48-527d-ade8-a4fa5a514e48 | textbox | Package Code
298ed052-a3f0-5b9c-8bfb-737f27a1282b | textbox | Project Background
afb6c258-08bf-47fd-9dd6-8c468cbe6e90 | checkpoint-no-value | Walkthrough Details
8199bff5-13cd-57a1-8fd5-078eb31c12a9 | date | Handover Walkthrough Date
5226efe2-cd0b-5a99-b00b-28111118603a | textbox | Walkthrough Discpline
89e6a0be-1ba1-5e41-9351-24cce3e1cf67 | textbox | Detailed Description of Works
e42d319d-a6e1-5fed-93d1-5bf4a69a6491 | textbox | Reference Drawings
49ac1c48-1497-4e8d-8aca-e8493f0b4228 | checkpoint | Walkthrough complete
bc0d4648-6422-5d90-aa1c-cb64df512215 | note | Attendee signatures
d1e97f69-2159-4763-82ce-6f53852aa510 | checklist | ITP-258-CIV-MSS-Rail Delineation Temporary Fencing Rev 0 | itp | ITP-258-CIV-MSS-Rail Delineation Temporary Fencing
b30d5927-aa2a-4175-9daa-a1c419f916b9 | section | 1. Referenced Documentation
e5ec234d-1b1d-42a3-bd1c-3a10dca10cb7 | checkpoint-no-value | Referenced Documentation
a8e7e741-f040-53d6-b884-e7eb519ef698 | note | Document Title: ITP-258-CIV-MSS-Rail Delineation Temporary Fencing
5daf2d2e-70bf-57cf-8826-495db92c3874 | note | ITP Description: Rail Delineation Temporary Fencing for Maidstone St
74ebf3ff-1bb9-5e94-930c-6fdf286d80bd | note | Discipline (e.g. CIV/STR/RAIL): CIV
b0795da0-301f-5bc0-b808-a22e646e127c | note | Revision Number: 0
a96b066d-3712-5ac7-a862-b449f6be2df8 | note | Revision Date: 1/05/2025
04c1c6fe-a5cb-5e17-82ca-1d291b52c1d2 | note | ITP created by: Dan O'Brien
d14fb9ac-5528-55e9-9522-d8f106736f9d | note | ITP approved for use by: Aldrin Guinchoma
ba769a3c-ef1f-55a7-892c-33fe9e8a6d75 | note | 1.1 - Non Dependent
a4f65d4f-4495-505e-82e9-d8e8cc3aa71d | note | Reference - IFC Drawings L1-CHE-STD-005, L1-CHE-STD-025
301f92e4-91d1-46ce-a32d-dc6d99e8f675 | section | 2. Preliminaries-Materials
7d3893ae-ce4b-4572-93ad-920e6f3d6bc3 | checkpoint | 2.1 - Concrete
967bddab-989a-58ff-a014-d3743906042c | note | Reference - IFC Drawings
0e22a410-778b-5489-9550-0eee8a45933c | note | Acceptance Criteria - 32MPa concrete to be used as per IFC drawings.
463d1ef1-255c-5bfe-9550-dd8421c26165 | note | Method - Document Review
1b716367-f4ed-5bee-a233-f7f36098ee35 | note | Frequency - Each Mix
c7af3906-0ae0-5057-b4ed-080c26ebba39 | note | Category - HP*
8189423d-5812-5b4d-891a-bf0702722c51 | note | Responsibility - PE
a9938361-823c-5d27-9eaa-879a388a5076 | note | Verifying Documents - This ITP
c6c1c15e-dbd4-5706-a6ed-3c09c80df184 | date | Date Completed:
cd8d2ab8-a0d4-4a6f-8251-6eaecdd47937 | checkpoint | 2.2 - Steel components
f61ace2e-494f-5f41-87f6-b42e49869546 | note | Reference - IFC Drawings AS41000, AS1163
e2ebe6c4-3578-531b-8dce-0e3b6f4c979b | note | Acceptance Criteria - All Steel must comply with Australian Standards.
cde41fe9-275b-5748-a29d-dbc4e4fc31fa | note | ○ Steel section sizes must be checked on site.
f47932f1-206d-5f98-b799-146125e2d135 | note | ○ Steel posts to be CHS with a grade of C250
6dae5f91-b7b5-5aa8-bb79-543683b02433 | note | Method - Document review, Visual and Measure
728d77b2-40be-572c-8582-fe774106e235 | note | Frequency - All elements
c98bffb7-175a-55b1-a07b-7fb6ff871f97 | note | Category - IP
914b4262-0cf3-5cbb-b2f8-052bebf1f2c5 | note | Responsibility - SE/Site Supervisor
4a7450c0-a084-5359-990f-450b81a9919d | note | Verifying Documents - Delivery Dockets
5fefe35e-b7c1-54a8-b9cb-6ff4f707dad1 | date | Date Completed:
b8eda38d-1e6a-458a-9493-800c896ca93e | section | 3. Preliminaries-Documentations
b54abd41-d0ce-4699-9ec5-4874b33118ca | checkpoint | 3.1 - Excavation works
c2e494dd-26a2-567b-8bf0-611c1fe3e96f | note | Reference - IFC Drawings L1-CHE-STD-005
424ba696-9b01-58af-acb2-bba3b291f099 | note | Acceptance Criteria - Excavation for post foundation must not undermine track and comply with PTDT requirements.
43e3c5c9-6bad-55b5-a5ac-eeb35a820977 | note | ○ Follow asset owners guidelines for work around their service.
3b724dee-872e-5039-8265-4a56d7178f04 | note | ○ Excavation must use Non Distructive Digging in close proximity to services
8c06b442-ae56-570a-89c0-52ffbe827d4c | note | Method - Visual
f81bb348-dbb8-5f5a-8041-05fb94dda9a3 | note | Frequency -
dfd44f2e-75b6-5a7c-a7b9-16c12b2b1ac7 | note | Category - IP
a9e0058e-a51f-5336-8918-e390bb6fe64f | note | Responsibility - SE/Site Supervisor
702e81e8-096f-57ce-9fcf-e71e0175a56a | note | Verifying Documents - This ITP
8fdf3b48-a006-50d8-9c20-f6b1900e78a1 | date | Date Completed:
b629eadc-5804-4580-9afc-381cf12b73d7 | section | 4. Pre-construction / Pre-installation Activities
a6cb935a-4aad-42bf-b3d2-95519b27e387 | checkpoint | 4.1 - Survey Set-out
32170596-9996-5e5c-b240-b7c5b900ef76 | note | Reference - IFC Drawings
bf3b2e30-38ec-51ea-a81c-18b91d949dde | note | Acceptance Criteria - Survey to set out the following but not limited to: existing services, post locations, refuge bays
f6491261-4bbf-5ea6-bdd9-0fce4671e946 | note | ○ Offset checked against the running edge prior to installation of posts.
51a2d371-a2b4-58c4-8c20-6938b657640b | note | ○ Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
279b33cc-2da8-5c70-9db2-0f100085d02d | note | ○ Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
34a5b179-e29b-5313-8fdc-ec11b4924a0d | note | Method - Measure, Visual inspect
6c09db2b-8528-51f7-9538-22a93b8c8553 | note | Frequency - Each element
11c34bc9-f08f-5732-8c9b-29b3ea46183d | note | Category - IP
b4c63114-1721-578b-a6fd-15f0ff98f679 | note | Responsibility - Surveyor, SE/PE/SPE
d6d49991-8a86-5c5b-80e3-3c805110d515 | note | Verifying Documents - This ITP
df47be1d-60b2-5ea3-845a-455e0e0f5b3a | date | Date Completed:
3053b6ed-d858-4294-9758-72f08ee38928 | checkpoint | 4.2 - Vibration Monitoring
b89d436c-ad3d-5037-8b85-72ab664b0b11 | note | Reference - Worley vibration monitoring plan
36002666-383e-5eff-8d92-4a426232894a | note | Acceptance Criteria - Vibration monitors installed as required in monitoring plan.
7cbf6c73-e611-581b-9b42-aadc811bc350 | note | ○ Vibration at VIVA pipelines not to exceed 10mm/s
d3705057-7652-54e8-93e1-6986bb219a4d | note | Method - Measure
00104225-2343-56a9-a26d-a5806c38835c | note | Frequency - Each element
927714c4-db1c-5465-99b0-9f5c4467dcf4 | note | Category - IP
fa0b1618-46ad-5fa3-aee8-e35e943053eb | note | Responsibility - SE/PE/SPE
ef6f6b0d-66bd-56c1-a830-390ec7cd4318 | note | Verifying Documents - This ITP
17c61e3c-ab59-552f-8d92-858c74b7f047 | date | Date Completed:
9c7a33c5-df87-417d-8cb9-d4ecb503cced | section | 5. Construction / Installation Activities
7b7ca035-54ad-4775-a6f3-1aa1b35c85ed | checkpoint | 5.1 - Ground Conditions
d558d455-9df2-5020-8955-37fcd753ecf5 | note | Reference - IFC Drawings
b84bfa7b-ba8c-500e-b301-8e38d3d11c8f | note | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
aa2871a2-9c77-57e5-b65c-5b06141e9aea | note | Method - Visual
2cb182c1-d573-568f-ac88-e5e5c51b6df1 | note | Frequency - Each post
b867af5d-fbac-5524-8601-8f13794f03e7 | note | Category - IP
3e09f592-e222-5796-9b31-1edd94c0daef | note | Responsibility - SE/Site Supervisor
098f7710-cae1-5ee3-a853-1f4ca223bc32 | note | Verifying Documents - This ITP
03b2c1e4-d873-53b5-b3be-6a048b936bf2 | date | Date Completed:
57c5f93c-c12b-4bfc-96f1-22df42bfd74d | checkpoint | 5.2 - Post Foundation
b3790331-f2b6-5ff9-9285-0f81be9db427 | note | Reference - IFC Drawings
cc8f33ea-6fb5-565b-a4eb-8a34f4185b35 | note | Acceptance Criteria - Concrete
a7af24e7-2da6-58fa-bc85-1a8e888c98ea | note | — 300mm Dia
865a1a67-1a5d-5e8b-80dc-0d29d9332b59 | note | — 800 mm Depth
6b8c44b4-b5ef-5637-b44f-1ab2c04de962 | note | CHS Sleeve:
0955d0be-52f6-5e0b-9320-f029d2ccf5b4 | note | — Depth 1400
76cee79d-3334-5932-9c1e-1c7fbba8b929 | note | — Other Dimensions as per IFC
7b2210aa-9ff2-52d6-8ac3-fdab18ab20b9 | note | Direct Driven:
98b5ee57-11e2-51e4-b761-505a06458eb6 | note | — 88.9x4 CHS
a20ef889-63ab-508e-aa79-fd2ca49fd281 | note | — Depth: 1400
96c0cb02-9c05-5467-96ff-8165f79c28df | note | Insulated fence near OLE posts:
089be3cb-93f8-5208-8734-04269c6fd94a | note | — 95x65 Truform LVL
30672cb4-320b-5eeb-a65e-e0b221683a09 | note | — Depth 800mm (post embedment 700mm)
139b792e-3a34-58c2-b6c5-63f28dc798c2 | note | — 300mm diameter
0d966fca-2b7d-563b-ba0e-9f409aa22746 | note | Spacings:
ec713574-0153-5eb6-b518-b03ce8243ee0 | note | — Typical: 2700 max
085c0be7-5a92-5160-9426-33268f0730d5 | note | — Gates: 1350
db01712f-ec6f-5c98-8a92-66e43bb237f6 | note | — Refuge: 1200
1f3b8249-290e-517b-9c71-8f40125ec563 | note | Method - Measure
44b5eb9a-11c8-56ac-87c7-0912faabbf58 | note | Frequency - Each footing
d2a47e23-3507-5fdd-b034-bb41d05f0d91 | note | Category - IP
c7ad1105-5372-5766-8829-ff1da28d2045 | note | Responsibility - SE/Site Supervisor
25d859a9-5e93-5561-844b-85b7f2629063 | note | Verifying Documents - Concrete Dockets
5eccd80f-37c8-59d9-8fbf-27fae94fc049 | date | Date Completed:
cab192f5-429d-4a50-80fa-3f3c83fb2b90 | checkpoint | 5.3 - Post Installation
cd681ce9-b967-58ae-903d-508c6ea51848 | note | Reference - IFC Drawings L1-CHE-STD-005
bf470028-e0ba-5511-a3cc-1f4d2a2625eb | note | Acceptance Criteria - Minimum offset 3000mm from centreline of track.
09c4a939-85a3-5d9d-9c84-0b2a88a1d3b4 | note | ○ Minimum 2m offset to existing OLE structures (insulated fence required)
a45969a5-823c-5213-aa0e-47bef95eb55b | note | ○ Maximum post spacing to be 3m
14d022a9-a93c-5430-82a5-aabaafb0cb33 | note | ○ Two spans at 1350CTRS at the end and at Refuge bays.
a73d14b9-3b2c-59f6-b7e9-8b8e49e50c1b | note | ○ Max. post height 1800mm above ground level.
49aff54a-6332-5886-b4ad-322491c0ab64 | note | ○ Vertical Tolerance: ±20mm from the design line.
1e8754a7-14e2-5d6c-98e8-63ccd499b2f2 | note | Method - Measure
307ba2c8-ec8c-599a-b934-18e1d79aae05 | note | Frequency - Each post
fd6ae2f1-621d-54a6-8d64-b8eb47fac034 | note | Category - IP
b94c280a-b1d9-598a-bae4-bdc0f09fdc5f | note | Responsibility - SE/Site Supervisor
27c9d2aa-66b6-5cd9-b4c0-fed2bbede3ad | note | Verifying Documents - This ITP
ef4f0635-e943-57d4-bccf-a823bbb7e024 | date | Date Completed:
0b3c0cbf-a5df-414b-a347-0973242bbcaf | checkpoint | 5.4 - Post Installation - insulated fence near OLE structure
5c7ba8e7-f806-5e33-af9d-5a1324be5d64 | note | Reference - IFC Drawings L1-CHE-STD-005
245fb2a8-4474-568c-9281-16ebfa224fde | note | Acceptance Criteria - Minimum offset 4000mm from centreline of track.
115cf64e-4c14-5055-b5cc-43781014d592 | note | ○ Minimum 1m offset to existing OLE structures
922cf335-b90a-56f3-8db7-8b345debab58 | note | ○ Maximum post spacing to be 2.7m
23c1c4cf-b39a-57bf-a0ee-d8ea3e39d1b2 | note | ○ Two spans at 1350CTRS at the end and at Refuge bays.
f6232f72-27ac-5b0e-a57a-f0d76943ddcc | note | ○ Max. post height 1800mm above ground level.
3a109598-c898-5eda-beee-1920a4558ea2 | note | ○ Vertical Tolerance: ±20mm from the design line.
0c51a0a1-5487-50df-afea-132f88163c4a | note | Method - Measure
ef0487e6-e81c-532a-8cd8-e857d0f6bb1d | note | Frequency - Each post
e055677a-b1d9-554a-8ce8-2e96a1dcce02 | note | Category - IP
9cd7f530-efe4-5579-a2d4-f19848ab61d7 | note | Responsibility - SE/Site Supervisor
bc58d52f-104b-55ff-902d-106cb217a91e | note | Verifying Documents - This ITP
02807b93-682d-586c-8d1d-93104a2ce8e4 | date | Date Completed:
735e7806-93c6-4b09-980d-97347cc97935 | checkpoint | 5.5 - Chain Wire Mesh Installation
3ad57d51-d4c1-53ad-accb-b890e04da40c | note | Reference - IFC Drawings
3276e5ee-3e98-50b5-97c0-e255863e10a2 | note | Acceptance Criteria - Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire.
6ddd682b-2b0b-5a46-ad5c-9ee3c3411920 | note | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
50179131-d959-5dee-8e6a-3b6f8ec47df6 | note | Method - Visual
c6aa8c93-3f94-5e1a-8c23-7683da055f4f | note | Frequency - Each element
1da61ce7-4827-5a00-b880-bf3e2de8b588 | note | Category - IP
1d5bc33a-1d8b-54b6-837d-7dac0beab93a | note | Responsibility - SE/Site Supervisor
33ab426b-20bb-5e99-9452-48d4d1861928 | note | Verifying Documents - This ITP
9cf3b7f0-4699-57a5-8617-33bf2c81e259 | date | Date Completed:
0c4f76cc-5706-42eb-867d-e6cf03e52e7e | checkpoint | 5.6 - Bracing
f5219dd5-2890-5a8d-82ef-41fc10b3c708 | note | Reference - IFC Drawings
0aeae59b-9001-5cf1-94da-caed533b03f8 | note | Acceptance Criteria - 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
7d56837e-dfb2-5f84-9090-4815f826af43 | note | ○ Bracing to be installed on both sides of the fence at the fence corners
59fcfbeb-243b-56ce-ba0a-afb4a36cd9d8 | note | Method - Visual
201672de-d408-5f68-9ce2-02ff936db4ca | note | Frequency - Each element
c0aa07e3-87fa-5e21-9367-edc3fcf1ed0a | note | Category - IP
6d30352e-d64b-5ea9-997f-69f189f617f6 | note | Responsibility - SE/Site Supervisor
afdabd39-16c6-5aea-9feb-93accdede224 | note | Verifying Documents - This ITP
4137af28-a1ff-5c56-b41f-9b111be13368 | date | Date Completed:
fdcde141-9138-4d89-b307-bea9ef6c8943 | checkpoint | 5.7 - Wire mesh and bracing at OLE posts (insulated fence)
46c6e66f-76d4-540d-a964-7d3f5d934b16 | note | Reference - IFC Drawings
6fe89efd-cdea-53d0-b023-53595842dcb6 | note | Acceptance Criteria - Mesh fence to be PVC coated
ad364aad-a92b-5af4-99cc-c7e22c369404 | note | ○ Bracing with 95x65 truform LVL - fix to post with 2x12G timber batten screws
8d7c4183-64bd-5353-a46f-5a34bf41d6c0 | note | ○ Tension wires to be PVC coated
953a035c-94a3-5fe1-90c2-3377ce7c6a10 | note | ○ Mesh fixed to posts using fence staples at max 200mm spacing
1cf522a5-3e2f-578b-afa6-c51bf1329bfd | note | Method - Visual
508340cf-1852-50bf-a7f4-272daa8c3735 | note | Frequency - Each element
e38b6a57-499a-5387-a3d2-f5612a405f6b | note | Category - IP
ee1e4638-46e0-504b-8908-9df873dee37a | note | Responsibility - SE/Site Supervisor
fc8591b1-5908-55c5-80d7-7ed4f4222444 | note | Verifying Documents - This ITP
7f235e0f-9231-51d2-84af-030ce2bc78d4 | date | Date Completed:
b252e649-e9e0-4cff-ab52-32871f2bf8a0 | checkpoint | 5.8 - Refuge Installation
fbf11d19-e1c4-544b-8e18-fb6273bb2d63 | note | Reference - IFC Drawings
a6d0b2d8-9888-5bcd-8124-f72723b2b825 | note | Acceptance Criteria - Refuge Access to only open from track side.
9661a4d3-1447-513d-b407-936e50ff533e | note | ○ No chain wire mesh to be installed at refuge access.
e4acd58c-37cd-563b-bcf2-3533c6a2fb88 | note | ○ Refuge Access to be located maximum 20m intervals
6cf48143-29db-50f5-9df6-4c99afbe49aa | note | ○ 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
0b4b8292-3965-5f40-aa80-6befb9d979ea | note | Method - Visual
2fb2cfb6-c5d3-5716-8d52-b73a565f5f3c | note | Frequency - Each element
af70bcae-543e-51d6-a358-074ff079ce7c | note | Category - IP
f3e0e1c9-c5b6-5df6-8236-548a374d53d5 | note | Responsibility - SE/Site Supervisor
95c2d7af-459f-5a8d-8c4d-c8cd87cc9320 | note | Verifying Documents - This ITP
0b4e2507-e355-51a8-b7f3-3a4e4fc61cab | date | Date Completed:
c34c7145-0600-419b-a5f1-5b1ecaf30215 | checkpoint | 5.9 - Refuge Signage
f6b1e182-f8d2-5e94-ade7-f3b3a220b70d | note | Reference - IFC Drawings
e87912b2-6464-5240-9d8b-53d65f327d1f | note | Acceptance Criteria - Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX)
4940ad9f-aa25-5018-9eb3-560582cea76a | note | Method - Visual
575ed73a-5b23-551e-9784-7f7f9f9351d5 | note | Frequency - Each element
fb9d979a-8e7d-51eb-b189-0271d3f78f5a | note | Category - IP
009dc2a9-cab4-5a48-b4b4-85aff8485da6 | note | Responsibility - SE/Site Supervisor
095d5d25-ca54-5225-a623-53359e2b2938 | note | Verifying Documents - This ITP
0d9d0a01-7eeb-5244-a6e3-a17ecbed5c76 | date | Date Completed:
a3a50805-960d-4b23-b4d3-449480bc6dc4 | section | 6. Post-construction / Post-installation Activities
141c2044-b4e7-4135-a104-641b66b910ed | checkpoint | 6.1 - Fence Height and Track Clearance
17b44d48-d8be-5ee6-8b3c-e64355d69195 | note | Reference - IFC Drawings
6edbf42c-143b-5812-bb94-d7ad2e41e36e | note | Acceptance Criteria - Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
3870fa3b-bbd0-5d32-8c90-21703c288f45 | note | Method - Measure
1899a64f-f296-5f1d-962d-1668817ce3fe | note | Frequency - Each lot
636e2600-6792-5dfb-89df-68b75b8a40d4 | note | Category - IP
5014919b-8412-57d5-851c-3d084025a4bf | note | Responsibility - SE/Site Supervisor
87eeaf9e-a5d4-54b3-9286-f6ffd07b527e | note | Verifying Documents - Survey report
d099666f-be94-51e4-90c9-cfe16c2caff5 | date | Date Completed:
27501c0c-0182-4b24-a1b9-cb7de41f4139 | checkpoint | Final Inspection
81fbc77a-b1d5-5188-b192-23125d1eac79 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
fb53e5d9-86ec-548f-8657-03ee7bb1307a | textbox | Name:
878d37e6-793f-5f2b-a526-d20747419764 | textbox | Position:
e453ea52-23ed-572f-93f0-86f2a74deb97 | textbox | Date Completed:
8d1ee2b7-8890-4ed8-acf0-60bfde425fef | signoff | Sign ITP
33e2818a-c0de-401b-a6f2-c588449fb9a5 | checklist | ITP-272-CIV-ADL-Site Clearing and Grubbing Rev 0 | itp | ITP-272-CIV-ADL-Site Clearing and Grubbing
1d481a1b-c2bb-44ce-92f4-59a4b63edfbe | section | 1. Referenced Documentation
2dcea1de-fecc-4c03-a9f8-b0b98b7cd827 | checkpoint-no-value | Referenced Documentation
0304228a-5c28-52c6-8c5a-4992de088a24 | note | Document Title: ITP-272-CIV-ADL-Site Clearing and Grubbing
5d9a7f04-6738-5ac8-aa88-ccace3de2240 | note | ITP Description: ADL-Site Clearing and Grubbing
803da310-8400-576b-bde4-a6ab73ec5996 | note | Discipline (e.g. CIV/STR/RAIL): 272-CIV
08ad79de-74a9-5136-ae18-1079306e0059 | note | Revision Number: 0
39c6eac0-69ba-592e-9beb-d63a72c2fcb1 | note | Revision Date: 20/05/2025
116fac49-f0c5-55d4-bc99-29b203e56c82 | note | ITP created by: Abhi Patel
39943b15-b0d8-5b53-84d4-4904845ad0a0 | note | ITP approved for use by: Aldrin Guinchoma
d077da54-0f62-5813-9714-cc2620af7fea | note | 1.1 - Non Dependent
821b2899-4747-541c-a7b7-b57f971495ad | note | Reference - VicRoads Section 201
deb70b6e-462a-5e29-adaf-5ad23885a2ba | note | 1.2 - Non Dependent
0f479653-1302-5206-a291-35295648d04b | note | Reference - VicRoads Section 204
6108435e-40ab-53be-ba11-765589bdeacf | note | 1.3 - Non Dependent
9c83fd1d-4fe4-5f0c-96de-d7c12f30d659 | note | Reference - IFC Drawings
141cdacc-af6f-4d74-bc7d-c5f06349548d | section | 3. Preliminaries - Documentations
9349d9eb-1146-4dd1-8beb-d6cb3f7a9883 | checkpoint | 3.1 - Environmental Controls
50232dad-5362-5d7c-b5e6-73ff7fc6ed59 | note | Reference - MRPA Environmental Management Plan
f1f10a09-f597-5441-832c-2db629906b7a | note | Acceptance Criteria - All environmental measures to be implemented as per current EMP and local authorities.
10593464-3a09-527a-b8f9-05f74972fd70 | note | ○ Sediment control measures to be installed and protected vegetation to be clearly identified.
655d3b36-9578-5d66-be08-e94dd2e51a28 | note | Method - Visual
c426a9ec-cfa7-5abb-aab1-e5c527fbf98c | note | Frequency - Where applicable, prior to starting Works
3dd5323f-6402-52a3-8135-2d07ab453f45 | note | Category - WP
ed1b9cb1-eaf4-550d-85cb-71feca85bf50 | note | Responsibility - Supervisor, SE/PE/SPE
83500836-972b-5935-9a91-2d49f5aee3bf | note | Verifying Documents - This ITP Signed-off
bdee3db5-15e9-52a7-8824-1791d7e5e795 | date | Date Completed:
190dfc21-ff0e-4fd0-95e4-238a55ee0078 | checkpoint | 3.2 - Vegetation Removal Permit
8b1e8ba8-ed4e-5e18-94ec-0ed4554176e6 | note | Reference - MRPA Environmental Management Plan
350be7b9-845f-50ca-af30-d0e58fc5e650 | note | Acceptance Criteria - Prior to removing any vegetation or habitat:
39778b84-7e11-5d7b-b84e-aeb4969a1eec | note | i. arrange an on-site inspection with the Nominated Authority and relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design Documents and any relevant permits.
601cacc9-8084-5a08-a955-a2461ed7653d | note | ○ A qualified ecologist with appropriate permits/licenses shall be present on site during removal of vegetation to identify possible locations of fauna, discovery of significant flora or fauna and to examine any habitats likely to be affected by Works.
4d0f6886-fd52-522b-8b09-defa226f41dc | note | ii. fence and sign all sites nominated as No-Go Zones.
ba1c5186-9e99-5104-b630-63feb42aa9fd | note | Method - Document Review, Visual
4b6a5b61-0c47-52e3-8b46-1d69d6b2c84b | note | Frequency - Where applicable, prior to starting Works
4a7364af-f103-5497-95db-d9470eb016a4 | note | Category - HP*
015b5f3a-b7d7-5701-9be9-fbf977c4f732 | note | Responsibility - Supervisor, SE/PE/SPE
13de2958-80a2-5f88-a965-4c59c2e3f92e | note | Verifying Documents - This ITP Signed-off, Ecologist's Report, Vegetation Removal Permit
3e5d1ccd-899c-5075-8fb4-59ad599c1083 | date | Date Completed:
ea6f5683-587d-42c3-bf67-9f476a9845d1 | section | 4. Pre-Construction Activities
6b75c730-b969-4587-8132-88c18e23b0ce | checkpoint | 4.1 - Survey Set-out / Limits of Work
bdaabaaf-0b68-55cf-be09-53a6e45b8eb1 | note | Reference - IFC Drawings Section 201.03
36cbc574-2e64-5250-98ef-33bd4dd0a4e6 | note | Acceptance Criteria - The limits of clearing and grubbing shall be:
cb153443-4cc1-5ca4-a873-6694f7b4ed8b | note | a. the limits defined on the IFC drawings
e40890de-577e-59e4-944f-ea51c2b89600 | note | b. the whole width between the outside edges of any batters, including any roundings, together with a further horizontal distance of 1m beyond the outside edges of batters but not beyond the road reserve boundary or, where catch drains are required, to the outside edges of catch drains
8732bfc7-8101-5657-99cd-a8bcc6b0477b | note | c. no more than the width required for completion of the Work under the Contract.
32760a7e-c66e-5744-844d-c115c363180f | note | Method - Measure, Visual
8a609701-09d1-55bf-917c-2b026da0da63 | note | Frequency - Once, prior to starting Works
6b5fa055-a8d4-53d9-9710-4c7363317d0d | note | Category - IP
d1e3f844-2c36-5519-b5b1-b6da74b4f1dc | note | Responsibility - Surveyor, SE/PE/SPE
2361863d-ad23-5f8b-ab2c-63c176c40d69 | note | Verifying Documents - This ITP Signed-off
17b44c63-33ee-53c6-8d0e-c97777077226 | date | Date Completed:
2c23d7c8-56c4-4c6e-803f-412b0bcd6940 | checkpoint | 4.2 - Cultural Heritage and Areas of Significance
dec0a27e-aa39-5a37-a2af-a6292d721c2b | note | Reference - MRPA Environmental Management Plan Section 201.10
990e9588-4d4b-51aa-8781-544b7436fb56 | note | Acceptance Criteria - Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
c80ccecc-6ef1-5499-8c9a-fc7b4f92e88d | note | ○ Immediately notify the Nominated Authority if any Cultural Heritage is discovered or identified during construction and work to be suspended.
17d35b8f-f4b8-5e51-a4a8-c3eb41ec3f6d | note | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
bf5bc31d-4f49-5018-b223-e8363e6479e5 | note | Method - Document Review, Visual
55b65ae9-686e-5810-a2ce-3753bf4e80ef | note | Frequency - Where applicable, prior to starting Works
3ca65e7e-e022-53f9-9dd7-92feba8120da | note | Category - HP*
3d70bfb1-b90c-5683-b0f4-180ddfe62a5f | note | Responsibility - Surveyor, SE/PE/SPE
6b41b017-4ffa-5872-a06d-0ef2d34ff0aa | note | Verifying Documents - This ITP Signed-off, Cultural Heritage Report
d8467764-eeae-5d4c-95a0-e6a39b76c4d9 | date | Date Completed:
cb4e7185-4004-4fac-9a5d-5d3333be6b23 | section | 5. Construction Activities
bf08cf07-2898-43ed-b8c8-2948e3396573 | checkpoint | 5.1 - Stripping of Topsoil
e8058611-e783-5d76-9c8e-bf6edf1ede53 | note | Reference - IFC Drawings Section 204.05
0512edc3-8448-55d8-b0bb-e14353814cd9 | note | Acceptance Criteria - Topsoil shall be stripped for the full width of the formation.
dca4e11a-0a2e-507f-8ae0-cc3dbdf7c45e | note | ○ Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
04811ce2-f6e3-52c5-bc07-489f37acdfc0 | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
0d8f3679-1593-5e50-8756-a4f0156ba2d8 | note | Method - Visual
6c46bf0b-4b6b-5621-88e9-e237538dfb12 | note | Frequency - Each Site
dc1347ca-09b4-50a0-baf0-63e2904fff7b | note | Category - IP
f093ab9e-ce43-5692-b781-d27a040396a1 | note | Responsibility - Supervisor, SE/PE/SPE
b53f1f37-879f-5f85-8e60-fa316c227a2e | note | Verifying Documents - This ITP Signed-off
3696a439-af98-5a51-801c-630363562062 | date | Date Completed:
b304f65b-2812-4269-b867-75f2e58e7859 | checkpoint | 5.2 - Stockpiling
10d0b188-1f72-5e89-8112-9ed75d76d328 | note | Reference - MRPA Environmental Management Plan Section 204.05
e96869e5-c4ef-5120-b35b-34a81fadef28 | note | Acceptance Criteria - Where soil is stock piled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways.
34e36a4a-1494-572b-aeb0-126ce574c9f8 | note | ○ If this clearance is not possible,additional protection shall be provided.
e38de41b-6fde-58e4-8217-cbcf7487870a | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water.
f3a4063b-444e-543a-9bcd-9360a6ca0c20 | note | ○ Topsoil shall be re-spread as soon as practicable.
8f2b3061-2c59-52e1-b142-129b3da25225 | note | Method - Visual
d4e1304b-955f-52f0-8e2e-4193a1900702 | note | Frequency - Where applicable, each Site
6a941ca9-dd97-5788-ae16-564c0abab26a | note | Category - IP
dba322b6-96f3-5017-bfc3-28ea516b48d5 | note | Responsibility - Supervisor, SE/PE/SPE
cbde1aaa-b1ed-5b64-b791-dd2cc888e2e4 | note | Verifying Documents - This ITP Signed-off
83001b0f-dc44-5afe-9297-8f779ad584e4 | date | Date Completed:
c80070ae-3d7a-4c60-a3ca-6d12aa5b7d2d | checkpoint | 5.3 - Abandoned Services
19e349f0-b4c9-5481-95b3-81cf353f4c2c | note | Reference - IFC Drawings Excavation Permit Section 201.05
d6dd85a5-bb24-5d7b-829f-516ca10233bf | note | Acceptance Criteria - Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works to be done.
3ff04773-2e9e-5ff6-b3c2-5ed020d71c52 | note | ○ Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
d8b11319-e95d-5f38-a942-0f20e6b0a992 | note | ○ Decommissioned services to be disposed of in a suitable manner.
c631cfe6-238e-5dbc-88d5-82108c5118c0 | note | ○ Decommissioned pits have been broken back to 0.3m below subgrade level. Remaining pipe openings shall be sealed with concrete.
df3de554-6f22-520f-9297-c010e83bc50c | note | Method - Visual
da52771e-e381-529d-996d-8cb2b423035a | note | Frequency - Where applicable, each Site
2a0eed87-beca-5398-8df2-2aa26fe51995 | note | Category - IP
fd12a5ba-206d-57f6-b411-2a9eb9fc0eb4 | note | Responsibility - Supervisor, SE/PE/SPE
7ba2db8d-94b1-5179-a703-954747038453 | note | Verifying Documents - This ITP Signed-off
d8e00862-00d0-5396-8342-371479eb970f | date | Date Completed:
65581f34-e9b8-45a9-aa94-43b9c5186ae0 | checkpoint | 5.4 - Clearing of Trees and Vegetation
f29c8fa6-1210-5a18-832b-0f6b96c81230 | note | Reference - IFC Drawings Section 201.04
a94490c3-a622-57ab-a59a-5b82a17a94ad | note | Acceptance Criteria - Clearing work shall not be undertaken outside of the specified limits of work.
9e4f9a45-e584-5fb8-9c13-1d3745aa7970 | note | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
53b041e4-49fc-5a81-8f3c-4512b0c2dab9 | note | Method - Visual
ae13d428-a88b-52f5-a046-23829b9d4a97 | note | Frequency - Where applicable, each Site
da482118-5634-5345-8102-428a756cbc2f | note | Category - IP
e9e44eba-9cad-5a5a-b171-48d6a32d9fec | note | Responsibility - Supervisor, SE/PE/SPE
df6408b2-5676-5b79-92c8-a0ccd20934c7 | note | Verifying Documents - This ITP Signed-off
ee0df769-2d36-5630-b489-ba59c9e89a15 | date | Date Completed:
93cc9b35-a4dc-4908-8f04-23c2667960fc | checkpoint | 5.5 - Grubbing of Vegetation
81140d34-fac4-5afd-8d25-2cb9cff1a7e8 | note | Reference - IFC Drawings Section 201.05, Section 201.06
f7d59364-ffeb-5665-aa23-aba692210aef | note | Acceptance Criteria - In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3m below the subgrade and batters, whichever is the lesser treatment.
94a78537-63b3-5896-aa5d-eaf595ca112a | note | ○ In areas to be covered by embankments, grubbing to be a depth of not less than 0.3m below the stripped surface or not less than 0.6m below the finished surface of the subgrade, whichever is the lesser treatment.
8c70d6fd-a9a8-500e-80dd-35acabdd6f21 | note | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material and not less than density ratio of 95% (standard compactive effort).
5f730986-8ebc-51c0-9417-503bfa415497 | note | ○ Unless otherwise shown on the drawings, trees and stumps within 10 m of any portion of a proposed bridge, or proposed culvert having a waterway area greater than 6 m2, shall be cleared and grubbed.
2d563ee8-7caf-575c-b180-493166f37294 | note | Method - Visual
8466bf8e-3070-583c-88dc-637f77e0f214 | note | Frequency - Where applicable, each Site
e44901fd-a67e-567e-8a16-7fdcc662e239 | note | Category - IP
092fafc4-4138-5453-8c49-95b88824dd05 | note | Responsibility - Supervisor, SE/PE/SPE
86e47296-3b72-53c7-b61f-498f23d96610 | note | Verifying Documents - This ITP Signed-off
1867753c-3a1f-50fe-9a44-1e913c8d45c0 | date | Date Completed:
e865c5c1-2de6-4052-ba68-fd28a5c11ca5 | section | 6. Post-construction Activities
cc9694a5-e125-42ce-8ade-a88c03a8aeb2 | checkpoint | 6.1 - Disposal of Materials & Vegetation
cd136eb4-493b-528b-8fd4-f92377535f94 | note | Reference - Section 201.07
17fd15d9-3110-59ec-9b42-21d11e29cd2c | note | Acceptance Criteria - Salvagable material to be used wherever possible, the remainder is to be remove from site.
e2908b28-30d3-5f41-928c-d05c05a65b43 | note | ○ Salvagable concrete and bituminous materials greater than 50 mm shall be disposed of at approved recycling establishments.
eef9689a-bf7a-531e-8b16-169d9292fded | note | ○ Tree trunks and large branches shall be removed from the site.
711e6a9b-e164-5d31-a694-8b3f54a88321 | note | ○ Small tree branches,shrubs and leaves; excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
0ecf6eae-fbe4-52b2-9d35-3408e3a0b3ae | note | ○ Attach: Delivery Dockets (for Items sent off Site)
2ddca178-19cf-52a4-9f19-9454dbac8f39 | note | Method - Visual
f26e030e-ce22-5b3a-8515-4f9a5e28cf07 | note | Frequency - Where applicable, each Site
dc43f60d-3013-5f9c-bd6e-6d577bd765b2 | note | Category - IP
95005841-82a2-5679-b5f4-f023623d788e | note | Responsibility - Supervisor, SE/PE/SPE
7faf3292-e1ae-557b-b3fc-4c89bc215f42 | note | Verifying Documents - This ITP Signed-off
286e5179-cac9-50ae-8393-a704f1d8d730 | date | Date Completed:
d6cf56b3-f0b8-413e-a41a-1472f7f2b002 | checkpoint | 6.2 - Non-conformance Report (NCR) Closure
19633775-6046-5f87-b36e-0a88f6883573 | note | Reference - MRPA Quality Management Plan
993c6894-f31c-59c4-bf72-78097faf7abc | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
2dd0f9d0-55f4-59c1-a992-e56269bb75fe | note | Method - Document Review
4cff97e3-c3c5-5d12-a681-699afb18302f | note | Frequency - Once, prior to closure of this lot / element / Work area
4043a6ea-620c-53e6-88d6-752237f2d38e | note | Category - HP*
62122b52-4018-545a-bd34-caa02decf478 | note | Responsibility - SE/PE/SPE
2202cfac-f70c-500f-8e55-2991a81e7604 | note | Verifying Documents - This ITP
2fd12520-acb8-53be-90e4-c660671f8e24 | date | Date Completed:
51c2f1dd-5cca-445d-9060-35a8b2a64cbd | checkpoint | Final Inspection
7518e5a7-78a2-5697-8f58-ae36ed3a0d54 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
2d5ee97f-d4ea-5365-80f1-835f976493fe | textbox | Name:
18babd2e-723b-521c-b42c-52317e7a4beb | textbox | Position:
2212ad70-7de5-5d1a-b0bc-ec03c823a613 | textbox | Date Completed:
778bb575-d48c-45eb-8edd-8c711f97c659 | signoff | Sign ITP
c51f959f-5e83-4e17-bff3-3284a14639f9 | checklist | ITP-273-CIV-ADL-Subgrade Preparation - Road Rev 0 | itp | ITP-273-CIV-ADL-Subgrade Preparation - Road
09dcb07a-8973-4bca-9067-e543401238c1 | section | 1. Referenced Documentation
353d9ccb-e890-4e08-9f76-1640db00d350 | checkpoint-no-value | Referenced Documentation
dd73eff8-f9e5-5c9f-ad8d-094277ca9ad3 | note | Document Title: ITP-273-CIV-ADL-Subgrade Preparation - Road
6b8824ce-1fa0-5bea-ab9a-a23aaecdaa8f | note | ITP Description: ADL-Subgrade Preparation - Road
25e11c32-9e88-5d2d-91e5-d66fb48a909a | note | Discipline (e.g. CIV/STR/RAIL): 273-CIV
ec4d66f9-cf25-5053-a2d8-66c915522cad | note | Revision Number: 0
af7f1121-429c-50bc-8688-c1831de41824 | note | Revision Date: 22/05/2025
9c9aedc7-e900-569f-b412-ae8052a1b34d | note | ITP created by: Abhi Patel
146f2023-6543-5a37-9863-a409add392e4 | note | ITP approved for use by: Aldrin Guinchoma
b4f54757-6daa-5e6b-afec-219505314848 | note | 1.1 - Non Dependent
a1d96ea8-4bea-53db-98d1-49b8d46f921e | note | Reference - VicRoads Section 204
9d1699e6-023c-5bea-b1fc-8b6ae4fbcda7 | note | 1.2 - Non Dependent
101c7c17-8eb0-5f23-bcb3-7ccfd11d0c31 | note | Reference - VicRoads Section 173
a4425afd-17b5-4ea1-8f49-d52972a48ef5 | section | 2. Preliminaries-Materials
7e63927a-923c-44dc-99cd-973137c02a17 | checkpoint | 2.1 - Material Approval
401ea3f0-e3cb-557b-a3ae-140ea64f59f4 | note | Reference - VR 204.04 (C)
9e8e3ce5-d5a1-50d5-973c-e9a18cd038df | note | Acceptance Criteria - Type B material shall be totally free of organic content, topsoil, deleterious and/or perishable matter.
5be372c0-ac7d-5982-b71d-3d961e955d75 | note | ○ Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20.N/A
6de095b9-276e-5453-b6d0-5a581dbc35d4 | textbox | Enter: Teambinder Material Approval number
563615e1-a1e2-5673-bceb-d0d674d38659 | note | Method - Document Review
67b7a7d3-006b-5669-ba24-2b7af89c6641 | note | Frequency - Once, for each mix material
1807d235-555f-5da7-a7e4-663d765f7fe6 | note | Category - HP*
cc9bef30-22fc-520b-860c-2ff3a2900dfc | note | Responsibility - Nominated Authority
cc4df168-3646-5800-bda5-7fa5e654bea8 | note | Verifying Documents - Teambinder Material Approval
391b00d8-65cb-5ffa-bd59-79b5cf1719b0 | date | Date Completed:
3e64166a-cc93-445e-a977-1d2bcd75998c | section | 3. Preliminaries-Documentations
c85e0726-c626-495a-9490-c3f523e2bfd9 | checkpoint-no-value | 3.1 - Non Dependent
71793db7-9512-4007-972c-61411aa8bb5f | section | 4. Pre-construction / Pre-installation Activities
4a897bd9-8e37-48f5-b988-95ac8530d249 | checkpoint | 4.1 - Survey Set-Out
95e5f64f-96cf-54d5-897f-9aab9a634901 | note | Reference - IFC Drawings
9872fa3a-670d-5919-a11c-1df3222368f0 | note | Acceptance Criteria - Area has been set out in accordance with the drawings
c4365c10-b811-5ea8-9107-7ce0cf79d2f6 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
cf6c600f-8d8b-5c8c-8858-cadccf334e33 | note | Method - Verify
82b64af2-36aa-5491-b63d-9d0e582cc22e | note | Frequency - Prior to commencement of excavation
ddbc0ba6-6861-58b6-ac37-acd5ae798d20 | note | Category - IP
d30a99e6-beb9-581a-b97c-324e3acff50c | note | Responsibility - SE/Surveyor
de7214b3-52fa-534a-aa2e-a8b29e856800 | note | Verifying Documents - This ITP
a12a8f39-ccb8-5876-b74d-8b374a68cc2d | date | Date Completed:
88230224-1661-42ed-843a-af4e0ba8feb0 | section | 5. Construction / Installation Activities
49fa9fb5-affa-480e-b861-769b656f8d5c | checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
277a8236-fa47-5abf-a13c-17ea63841617 | note | Reference - Section 204.06 (C), Section 204.06 (e) IFC Drawings
554b40ee-e934-52f2-807a-c4456c716319 | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
60953a9a-fd91-5268-aac4-8e527499ed1f | note | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
971cf373-dfe3-5493-9818-9ac2a0e0eb38 | note | ○ Assigned CBR ≥ 2.5%
179943fd-50bc-565b-88f8-8170abe65ea6 | note | ○ If parameters are met, rip and re compact to a depth of 150mm.
0628f244-e236-5bbd-a25f-864043592a94 | note | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
0837b73d-7bfc-5d6e-9de9-d1f9e0b6197f | note | ○ If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
c07b012c-5f40-509d-b50d-fb4e695e9c5d | note | ○ Attach: Laboratory testing Verification:
5ba6cbc8-261f-5159-a0b2-ee76af06aab6 | textbox | Enter: Type A fill Lot Number:
f4c66724-8290-5bc2-a06c-88664c5305a9 | note | Method - Verify-Document Review
8254bf9a-5dec-564b-8850-02aaf3d5b533 | note | Frequency - Each lot
145c758e-6fd2-57f8-a944-3274b8550fe7 | note | Category - HP
1fdde727-56a5-5ebc-a083-1a91bc83cbaf | note | Responsibility - Nominated Authority
0c7614f7-1daf-57aa-b704-bd66fdca6dbe | note | Verifying Documents - This ITP/Test Report/Referenced Lot number
8374593b-f874-56c6-8cbc-89341e6146fc | date | Date Completed:
e309c0f8-cb58-4e8e-9fd5-3f17f18d5daf | signoff | AUTHORITY HOLDPOINT
e8d1e764-d40e-4828-b6b7-91ced75ea20a | checkpoint | 5.2 - Material classified as silt
c21c4d96-721e-5fcf-b4c5-2b57222b24ec | note | Reference - Section 204.04 (b)
43ad4088-6c77-58d3-9f7a-fe303c84d7e1 | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
9cb35d49-1ab2-59c9-8b2b-c20450cec117 | note | Method - Document Review
57e8136c-97ad-5632-bb21-251d9adcce61 | note | Frequency - Prior to commencing
dd1ee55e-b89f-53e8-afc4-d1d730b91851 | note | Category - HP
2c7823e2-9c7f-59c1-b35f-c0de91ca06bb | note | Responsibility - Nominated Authority
7ef8a81d-8994-5803-9974-38f2ee02d1d9 | note | Verifying Documents - Superintendent satisfied with Stabilisation, Signed ITP/ records
65e16d0a-73bb-5cc3-a53a-b23843ee360e | date | Date Completed:
dfb4e3f7-35ba-481a-b35e-7db8d2cf4a27 | signoff | AUTHORITY HOLDPOINT
1b80955a-ad3f-4e45-ae76-223fbeff6939 | checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
4a7f018d-8ae6-5bcf-943e-519f7872018a | note | Reference - Section 204.06 (f)
5cce6b65-6efa-506d-ace0-4852b7d59468 | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
350c2cef-b316-5f4d-a86e-e984038c14ee | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
99cc2acd-6118-52a1-913c-f10dacc0be1f | note | Method - Site Inspection/ Document Review
5a35f4eb-a85b-5471-a199-2df2ddd64614 | note | Frequency - Prior construction of the regulating layer
66bcafad-e065-5a95-8a3c-7749046b4008 | note | Category - HP
f57eb615-ae9b-576f-8133-bec845a90a73 | note | Responsibility - Nominated Authority
54c42940-3163-5db9-abd8-29f9c470eeb0 | note | Verifying Documents - This ITP
24ccf69a-72b1-52e6-afd1-db2535981ac3 | date | Date Completed:
bb4a6ad9-c8c0-4af6-9615-05d638a70e42 | signoff | AUTHORITY HOLDPOINT
402eec62-32c4-47b1-a377-ec490ac58d07 | checkpoint | 5.4 - Unsuitable Material
20066514-5d00-55f2-a4b6-3d45da1f5006 | note | Reference - Section 204.07 (d)
47cd6f98-5066-5734-992d-a79f6de97a21 | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
48eb0ade-ce97-5fdd-ae8a-7641018aab78 | note | Method - Visual inspection
5af9ac17-d923-5362-abb3-c7d008423866 | note | Frequency - Each lot
f6c7fbeb-073d-5c79-a572-f21ac2dd986a | note | Category - HP
a3d1fb95-62c5-5038-9048-cf0774092955 | note | Responsibility - Nominated Authority
79bfd0ed-c17e-5a2b-bbdf-b53185ee71e0 | note | Verifying Documents - This ITP
11c2b495-fde8-5dd4-abd9-69c18590d41a | date | Date Completed:
5fdd4def-bd13-494d-ac56-6a9632393938 | signoff | AUTHORITY HOLDPOINT
db2e8e51-802d-4773-ae50-194d0fc0fc37 | checkpoint | 5.5 - Groundwater
a2bcf881-cb3a-5e4b-b78c-4771b141ed5a | note | Reference - Section 204.06 h)
faac3644-a61f-59f2-b37d-6727145cb4c4 | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
21080e1e-1b7f-5eb6-af18-d13db8274485 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
71e524e6-0d90-5bbe-99aa-0fa9a8d0f7b3 | note | Method - Visual inspection
4a338b20-2665-553a-8ac7-c950dc35c6af | note | Frequency - Each lot
220947a7-28ad-5c87-bd79-c34846b27fc9 | note | Category - HP
80d7e92a-de01-5613-b38d-5c29ca54af5a | note | Responsibility - Nominated Authority
aaf18eae-9f73-592f-9938-b61cd473e1fb | note | Verifying Documents - This ITP
b9a9163b-efc4-565c-bb28-3b6963c58075 | date | Date Completed:
dbc38a4b-af68-4f27-a745-ea35e8dce07d | signoff | AUTHORITY HOLDPOINT
adb32f4f-5e4d-4870-9bff-49a69b3b4f9d | checkpoint | 5.6 - Cut to Fill Zones
4f51c306-5033-548b-a790-dd5f61def9fe | note | Reference - Section 204.06 g)
b4254336-d112-5897-8544-44011fcfa945 | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
fd23b02b-8b72-550b-8f83-00785814e1fb | note | Method - Site Inspection
436d5b16-7171-5ff4-8865-876feac40239 | note | Frequency - Each lot
0f540ed0-8c65-5aa3-91f7-fadfc85f5686 | note | Category - IP
c0ef740b-a329-5da3-a753-137450861e9b | note | Responsibility - SE/Site Supervisor
ee0a9013-9c8c-55dc-8c13-cb21c8eb93de | note | Verifying Documents - Sign ITP
85505d1d-36c8-502c-bee2-7fbeff0097c7 | date | Date Completed:
71d2a16a-feae-4a72-949d-cb07f2b75b27 | checkpoint | 5.7 - Proof Roll
6817d6e3-ac9f-58e2-9e0b-141b20fdf5dc | note | Reference - Section 173
2e379c93-2b67-5f83-a37c-a12afa0e981c | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
cdcf98ed-1ed7-5e98-8a4f-2a22d6347c97 | note | Method - Visual inspection
cfce6d4a-56fc-5b0c-b4dd-9c19b20ebf16 | note | Frequency - Each lot
94fcb228-3945-5c7a-9272-ec1b16b9b660 | note | Category - HP
401d65b0-9e70-59cc-9489-2884412f5fcb | note | Responsibility - Nominated Authority
e66225e5-fd35-5f0c-916a-1910a413d304 | note | Verifying Documents - This ITP
99c7415c-1b39-522d-84e2-1b7851872b4c | date | Date Completed:
84c3217a-5be7-41be-9c6f-58e8db8ba844 | signoff | AUTHORITY HOLDPOINT
27caee17-76f6-49b6-9d3d-a53e25a8049f | checkpoint | 5.8 - Compaction Testing
adc517dc-9eae-5278-a185-43216197cfbe | note | Reference - Table 204.131
28025764-95c6-5c93-9a19-e52bdd08c316 | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
3281946c-27cc-50d1-8a3e-357bd8eca62e | note | ○ Ripped and re-compacted material below Cut Floor Level
c12cb1d3-9ce1-5359-862a-6a8981841002 | note | ○ Scale A: Characteristic Density Ratio 99%.
b4c2a007-9c7b-5141-97ec-ea61285a8d7e | note | ○ Scale B: Characteristic Density Ratio 98%.
998a5270-5f02-595c-b5b2-4da343ab181f | note | ○ Scale C: Mean Value of Density Ratio: 100%
a8dd6b73-6ada-52d8-bfd4-18d54b04a1a5 | note | ○ Attach: Compaction Test Result:
430bc580-e1ef-5dea-983a-b8c97796cbd7 | note | Method - Document Review
92f2960e-bc20-5157-9bc2-135fc56dfaa1 | note | Frequency - Each lot
b98f798d-602d-50f3-a018-6749deea3d92 | note | Category - IP
c19d1b18-fa0d-502d-af00-925e0af8ecba | note | Responsibility - PE/SE
557d34be-b86b-5abe-966e-6d38dcce97c7 | note | Verifying Documents - Sign ITP, Attach Test Report
9debf407-f104-5561-88f2-951f96d2812a | date | Date Completed:
1e64fe55-7aef-4c9e-b1a4-ec7d432bd401 | checkpoint | 5.9 - Post Compaction Material Property Testing
94b88f3e-5330-52de-9849-88719e8514e7 | note | Reference - Section 204.04 (C), Section 204.14 (a) and Table 204.141 For Scal A, Section 204.14 (b) for Scale B IFC Drawings
213ece8f-14d8-5a33-a2c4-e066da23611b | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
491e71bd-323e-52b6-a444-ba5f00286f69 | note | Scale A:
783c0188-8849-5764-bf5d-3f6aca99bfb5 | note | — CBR and Swell as per IFC for design packge:
60b85037-d86d-5e78-83f7-cdd51ca2a2ce | note | — MRP-DPK-087-00-CDR-0002-0
c3abf1ea-f7a2-5a47-bfa5-fc698a67817b | note | — as per table VR 204.141
460e207f-4e05-51eb-9ae8-e524e13ff2ef | note | Scale B:
1c90c618-e86a-5e94-bcb8-0cbd41bf76b1 | note | — CBR and Swell as per IFC for design packge:
26729c03-6f9c-51af-bda1-3bcc4963ce4a | note | — MRP-DPK-087-00-CDR-0002-0
67900d4a-00bb-518c-afc7-4e56dd647485 | note | First Lot for Max Particle Dimension:
89df4476-c4e2-5b1f-b831-c9ca23dda715 | note | — After compaction Type B material shall have a maximum particle dimension of not more than:
915a4c60-0c85-503f-bd48-ecfaad6705fe | note | — 150 mm within 400 mm of the top of Type B material and 400 mm at depths greater than 400 mm below the top of Type B material.
be39bb0b-e5a2-57c5-aa57-1eb32857c2f6 | note | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
a78136dc-3368-53f8-8aab-7e2b81e97c36 | note | ○ Attach: Post compaction test results:
5f4547b3-28dd-5987-ac63-06849e0be2cb | note | Method - Review Document
a809a2b1-a46c-57f4-b013-2869b9662448 | note | Frequency - Refer to Section 204
181eaece-e6a8-5bdd-b75a-029c8bc010ba | note | Category - IP
dc97c7bb-7a87-53a7-b931-753707f0dc6c | note | Responsibility - PE/SE
7201b939-c2e1-5ca2-a2a4-fa977a0fad1e | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
015a5371-5854-5451-aa46-39915541876c | date | Date Completed:
a05cb6bb-3ca7-4ac2-acaf-952af70bb34f | section | 6. Post Construction Activities
95e3c3b0-f72e-4b6b-85f9-0a7448432d7c | checkpoint | 6.1 - Survey Conformance
b27ea5df-064f-5eb5-be92-ce8f49f35436 | note | Reference - VicRoads 204.03f,g and h
638029b3-d4c5-5412-90b2-e6887dfcbdfd | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
050a1922-498f-55b5-8021-af0df7a77ed5 | note | Level tolerances (Scale A):
8017308e-fc44-5ff1-a67f-bf4a9fae2619 | note | — Range x = +5, -15mm
59239228-4857-5ba2-aa90-20df6c04ad3c | note | — Max S = 12 mm
2a350467-b9a6-5261-93b3-6bbcc2b61024 | note | — 80 measurements per lot
a13d987d-67b3-5a63-8996-63da65948161 | note | Level tolerances (Scale B):
e7e7c431-0754-5028-b6d6-224984b17783 | note | — Range x = +5, -25mm
e513662e-39bb-5ecd-9b9c-360552e4234f | note | — Max S = 15 mm
f724a1ae-8408-505e-8ebb-b3b607663d06 | note | — 40 measurements per lot
e3597c80-96e2-55e9-ac64-d38639473da1 | note | Level tolerances (Scale C):
0088500d-e7b9-5e34-8469-404cd700783a | note | — Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
0f69a527-db3e-572a-9751-d5f9c9bb435b | note | Method - Review Document
f8ed9129-e75d-5f49-b56c-1d7ccae75e34 | note | Frequency - Each lot
36ea462c-b60b-5b88-8925-9676c3a3e3da | note | Category - SCP
4c03fb61-cf9f-5c3e-b253-aea3eb615ff7 | note | Responsibility - SE/Surveyor
bb85935c-5f59-5ab5-b5a6-727463762666 | note | Verifying Documents - Sign ITP, Attach Survey Report
085979d8-bc45-5d74-bb4d-ec35c60fce72 | date | Date Completed:
0e3f5524-22f6-41c6-8c94-efe664b1b126 | checkpoint | 6.2 - Non-conformance Report (NCR) Closure
830383a5-2e93-53a2-8ebc-9a7601cb52e9 | note | Reference - MRPA Quality Management Plan
4eef6a52-0ed0-556d-9349-6af7339a32bb | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
53012d27-49c1-5773-8928-b6f4b9f20d4b | note | Method - Document Review
2a34738e-37e3-598a-846d-f6a740bc1dcf | note | Frequency - Once, prior to closure of this lot / element / Work area
5cb1a495-db76-57ee-a6ed-1063b011070b | note | Category - HP*
3fb07e5c-2dcb-5d6c-ac45-1533c281b376 | note | Responsibility - SE/PE/SPE
3b067177-c33b-5e19-9a0f-dae7cad63358 | note | Verifying Documents - This ITP
6d6fc070-d3e0-5dca-92ae-43d05ef97963 | date | Date Completed:
e4fd4f10-809b-433a-ada2-443787145b9f | checkpoint | Final Inspection
3dcb02a7-f241-5521-ba17-5e66126cdee6 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
03b8855f-d544-5048-9161-15eca2ce1754 | textbox | Name:
57bae9cb-a95a-5350-ae61-7fc2b36b0fc8 | textbox | Position:
f75c926d-e085-56c7-a192-0b66f21bc43f | textbox | Date Completed:
a8dad709-a2c0-4a76-b8db-b76042c49be4 | signoff | Sign ITP
ef1fd386-7fe5-4e65-8d0a-16adff7a9349 | checklist | ITP-274-CIV-ADL-Type A Fill - Road Rev 0 | itp | ITP-274-CIV-ADL-Type A Fill - Road
b255144d-456a-4b49-a127-b49e87dacde9 | section | 1. Referenced Documentation
5c04fd0b-8f67-4951-b06f-2abe83ba3e43 | checkpoint-no-value | Referenced Documentation
69d40f4a-f4eb-5362-8e8e-87b811015b80 | note | Document Title: ITP-274-CIV-ADL-Type A Fill - Road
e6f7b97c-0521-5180-a006-bfbb4d1cac9e | note | ITP Description: ADL-Type A Fill - Road
7524b109-bbf4-5d01-be4c-c41b750095cb | note | Discipline (e.g. CIV/STR/RAIL): 274-CIV
9dc1d6a5-80f6-5d32-9c98-71af2a967513 | note | Revision Number: 0
48abbf27-2e59-543c-893f-313bf8e3fe0b | note | Revision Date: 22/05/2025
c5ff1a73-7cb3-538f-b98b-dfc093e01eda | note | ITP created by: Abhi Patel
52ab9c68-e673-5af1-a7cb-387fd4bc4f0d | note | ITP approved for use by: Aldrin Guinchoma
dd758b6f-4221-58ec-9ba7-038198ae80e1 | note | 1.1 - Non Dependent
bf92bb9c-0b79-57de-b7d9-5ae3212cc247 | note | Reference - IFC Drawings
3dedf8d7-508e-5a5e-8aeb-c682afe3ccb3 | note | ○ VicRoads Standard Section 176
54685c05-fb4c-5463-8b7f-b946a778ba46 | note | ○ VicRoads Section 204
89524db5-1d8b-535f-8dd8-da157a5fd62f | note | ○ Code of Practice RC500.20
3b285dc1-20f4-5cc2-948d-8cc4ce11c985 | note | ○ Code of Practice RC500.5
28f09aa6-3215-4f17-a1cc-d6160c606d61 | section | 2. Preliminaries-Materials
b2023879-f5a8-481f-81ee-205f438692e9 | checkpoint | 2.1 - Material Conformance
25e3f916-dd85-5004-98a3-ee28309f7181 | note | Reference - Section 204.04 b) Table 204.041
07da9808-e588-5dd9-a8ca-65d513bb65af | note | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
7cdbba44-1e0f-5660-b9b6-1f3c091ca658 | note | Type A Material shall meet the followingPOST FIELD COMPACTION requirements as follows:
2db0c205-c362-5829-87cd-36922906e47e | note | ○ Assigned CBR≥ 6%
7e59fc7c-5ee3-5ed3-8eab-97e574da2252 | note | ○ Swell ≤ 1.5%
3c681f8f-4c93-5f67-a493-28a4aa065fb2 | note | ○ Permeability ≤ 5X10-9 m/s
0340d306-3f17-5df4-bd35-997d560d5aa6 | note | ○ Grading:
cad3fc56-0601-5423-9d94-96fae71a2126 | note | — 75.0mm 100%
e7acfa9b-d930-53b5-a652-df4176ed79ef | note | — 4.75mm 40-80%
0d6529c0-a4e1-5bee-80e7-2fbcda05943a | note | — 0.075mm 10-40%
f474ad2f-2f9a-5eb6-8087-17c9ac5bbf79 | note | ○ PI Range: 6 to 25
1d3fc829-3712-57ad-ab24-2484297e0561 | note | ○ PI x %passing o.425 mm: 1000 max
1773d91c-e4f8-50a9-b5e9-0091417c4844 | textbox | Reference: Material approval in Teambinder:
fb1f15b7-01d5-5827-916e-d561afd89b33 | note | Method - Document Review
d64f9b80-b081-541b-9022-540620abd294 | note | Frequency - Once, for each material type
cee71ede-5e53-5113-889f-1e2878801d1c | note | Category - HP*
d860668e-95ba-5fe7-9c14-fc19baffee62 | note | Responsibility - SE/Nominated Authority
0dc6d567-730e-5043-a8a9-4426668caa22 | note | Verifying Documents - Teambinder Material Approval
73892107-66b8-523b-b07f-bbad6b57170a | date | Date Completed:
d2e8517e-c3a3-4471-8644-15839e913df4 | section | 3. Preliminaries-Documentations
1ee92118-3cec-4997-b30a-bc9e24cdd9fe | checkpoint | 3.1 - Pre-Commencement of Fill Works
8413f968-2dfe-5f2f-bbd6-df5f9a3dfcd4 | note | Reference - Section 204.10 (b)
bc768997-fb07-509e-80a1-440c83dbb75b | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
ce0e6bb2-9610-5a56-a29b-520d30a8a861 | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
d99b3d56-048e-588c-a712-d91ac6bcdefa | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
a0ca7931-a39c-542e-91f1-9a43124e1c4f | textbox | Reference: Subgrade Preparation Lot Number:
37dc2bff-8bc2-54d8-85f6-5e71f6e6b383 | note | Method - Visual Inspection
26260b12-4f10-5cc9-b7a1-ede2bdf24fd6 | note | Frequency - Prior to commencement of fill works
0a188b95-8416-5997-8969-35d83eb8d962 | note | Category - HP
26f1578f-3dbf-5abf-9695-991eb97c391e | note | Responsibility - Nominated Authority
8bb38338-9015-5a5f-afea-27c3764eca12 | note | Verifying Documents - This ITP
efec891c-9fd5-5c8f-941d-ea76581cfde8 | date | Date Completed:
8b89ba69-61c0-48b2-8e82-ad30168e6017 | signoff | AUTHORITY HOLDPOINT
10be6132-444e-4d6e-aa65-9ac01df8a553 | section | 4. Pre-construction / Pre-installation Activities
381cb864-de16-4f7e-9a27-e2604718c047 | checkpoint | 4.1 - Survey Set Out
d5b2a507-4962-5bc8-a5dc-3e25e89c5a5f | note | Reference - Design Drawings
4dfea471-4c77-56ba-ba58-62225ea83191 | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
67ed877a-a3cc-58ea-974c-dfb3d1e30a60 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
dbf38148-395d-5021-aa7f-d6e660e47724 | note | Method - Visual Inspection
c4a3649e-7122-5ee0-b1c4-4bf6fb0e3e35 | note | Frequency - Each lot prior to commencement
3868e0b6-e248-5b01-ac61-71fd2c2ee616 | note | Category - HP*
f5a356f3-8f2b-57b0-9b5b-caac3da8b2b8 | note | Responsibility - PE
59f12a0b-2011-558f-8181-7e38fe76413e | note | Verifying Documents - Signed ITP, Lot Map
ac6b7ac8-a32b-533f-8674-a90592152114 | date | Date Completed:
efc42326-494a-49b6-be35-b23050065a7c | section | 5. Type A Fill/Verge Activities
5db8d518-4dc0-45c0-83b0-006359072682 | checkpoint | 5.1 - Placing of Fill
0a34e2dd-b48f-5ee8-a3a7-aea7cb9d44b7 | note | Reference - Section 204.10
cf188989-4903-5e8c-bed5-6a2b783bf2fd | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
590a8db8-2ab9-5582-9ced-cf2b44294447 | note | Method - Visual
3c71d492-51be-5c8a-8996-d0fac2877dc8 | note | Frequency - Each Lot
a9a047ab-1da5-57e9-ab7c-8552c384ce31 | note | Category - WP
17da9fa7-b4f0-540a-894c-6269c7b37b6e | note | Responsibility - SE/Site Supervisor
7dd1148c-63de-5582-9c24-289f46c95d4e | note | Verifying Documents - Sign ITP
b491327d-a46d-59e6-9c8a-3963a22b95c9 | date | Date Completed:
1afb1947-5e15-4393-bb6e-c358dd9ff7fc | checkpoint | 5.2 - Test Roll
d349d95b-0797-588b-a6c7-2bf807599b49 | note | Reference - Section 173.03, Section 204.12
ef33aea0-ae70-5af6-bcb4-f20ced431020 | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
207d8726-c8ad-5667-acf2-30fceba9f662 | note | Method - Test Roll as per 173.03
c6f6f299-4b55-5cbe-a049-bdad2b63271f | note | Frequency - Each Lot/Layer
78948789-addb-58e8-bff1-84f3a1cdcd8d | note | Category - HP
cde06611-d731-5bb6-8bc6-56d05d13d15a | note | Responsibility - Nominated Authority
61f3c70f-badf-5c2d-9131-b201eef9497f | note | Verifying Documents - Sign ITP
b8150c7a-d73c-54c9-bb7d-001bf47e7654 | date | Date Completed:
ce141adc-7179-41bd-9d87-84cc21ae5d7a | signoff | AUTHORITY HOLDPOINT
7f91f3f1-f5a1-4b4b-9392-6f665eb94544 | checkpoint | 5.3 - Compaction Testing
5876232a-95b3-5106-b032-58b075ffbeeb | note | Reference - Table 204.131, Section 204.14 c) Table 204.142
6e5f679f-5f9e-54dd-bfda-70f97dc56dea | note | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
4e4cd477-88e6-5d6b-8b76-f84777e10ee4 | note | ○ Standard Compactive Effort
e4b3285a-ffdd-505c-9de5-d35638d6e54d | note | — For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
694f8604-ad6b-527b-89aa-45d5c4d78b2a | note | ○ Compaction and Moisture content
a9edeb5c-a0aa-57f1-9d59-f931c3106cea | note | — Scale A: Characteristic Density Ratio 99%.
1f1ead93-5b42-5224-8ba6-17105e1d4161 | note | — Scale B: Characteristic Density Ratio 98%.
d24d3c9d-f20d-53fd-a67b-2521be404b89 | note | — Scale C: Mean Value of Density Ratio: 100%
59830395-80d9-50cd-810d-98a7b23fc473 | note | ○ Lot size - the leser of one day's production or 5,000sqm
c0ed5831-8f8a-5d99-b8b7-a07f1b89eef1 | note | ○ ATTACH: COMPACTION TEST RESULTS
2aa09247-598f-5cc2-99dc-f11c3975bbd8 | note | Method - Review Document
3c14dd10-a3b3-5dc8-a3d5-2ec3b6ba3176 | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
a88009a2-176f-5dc5-af62-4e3d719b8cf5 | note | Category - IP
d8f35a2f-c087-5e52-91bc-f36450ec2bfa | note | Responsibility - SE/Site Supervisor
53c06543-0074-51a4-b898-c5491eaa8fdd | note | Verifying Documents - Sign ITP, Attach Compaction Test Report
c8b578f9-d612-5575-94bd-aceec0ede687 | date | Date Completed:
09c26bbb-7c6b-4720-bbe6-959708bc825d | checkpoint | 5.4 - Preparation of final surface
b976650a-b2af-5c6a-b759-78f80564c9e7 | note | Reference - Section 204.15, 204.03 (g)
80ebf7d7-1a1a-5658-98c7-1a134ce9febc | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
5a4d791d-75cf-5358-bcd4-329ae9cdfdb1 | note | Method - Measure
05ccb54a-154f-5ac1-96a8-96610aca2997 | note | Frequency - Top layer
d8442e34-4a68-5844-a7a8-64422f6bc658 | note | Category - IP
e18d1329-2dc5-510a-8c98-3232a2ea071f | note | Responsibility - SE/Site Supervisor
59db97c1-d5aa-5b3c-b04a-eee6339cd112 | note | Verifying Documents - Signed ITP
1cfcc00d-0029-53a4-9b07-3a7eb40fbff9 | date | Date Completed:
9a2a2f0b-c560-417b-9b3e-4fc879f4bb41 | section | 6. Post-construction Activities
c888484e-9c63-44b7-a5d7-490dcd723dfd | checkpoint | 6.2 - Survey Conformance
af71c676-f0e1-5aa9-b98c-38c2f0832552 | note | Reference - VicRoads 204.03f,g and h
997a8af5-c284-58e5-a835-89d1723d0882 | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
ce132242-302d-5e96-91d7-2da31abaf8f1 | note | ○ Level tolerances Scale C: Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
17f0adfb-63ee-57ef-8301-b145ed4c1a5e | note | Method - Document Review
b76e1871-e357-5977-b51d-e69b224088f3 | note | Frequency - Top of Type A/Verge
f8e955e6-d5da-50b1-83ba-1ae0d3d823e3 | note | Category - IP
80b217e6-4e10-51f8-8bb6-b764c158e926 | note | Responsibility - Surveyor, SE/PE/SPE
16754cfc-22d9-5049-9a72-56e5661b17e2 | note | Verifying Documents - This ITP, Survey Conformance Report
37afd066-a92a-52e1-a648-92898e5eda3e | date | Date Completed:
f3c836f0-341a-45f0-a87d-b0f0a4984f6a | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
d6401255-312b-5a57-8a60-fda2e0dd80de | note | Reference - MRPA Quality Management Plan
c4244885-9f7b-58d0-8844-2a6dc8e37a3c | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
3d017004-de8c-5102-8cb9-8f3d4cd472d2 | note | Method - Document Review
6f1a76ea-1c7c-5465-ba2d-0dac163e9572 | note | Frequency - Once, prior to closure of this lot / element / Work area
8897ae7d-5c1f-5e13-a156-5b233813b2e2 | note | Category - HP*
324fef95-7474-588d-9e6e-764bfb35d4f5 | note | Responsibility - SE/PE/SPE
fcda5bf3-9325-54c6-8a73-0565dd2278b1 | note | Verifying Documents - This ITP
ad3f92d1-b71e-5869-ae19-37cf41d6b98f | date | Date Completed:
a363750a-b312-4572-85b3-b24bab0eee62 | checkpoint | Final Inspection
c4318869-28ab-5977-82be-5e99c25ce3b8 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
a7de28b7-e2d0-526f-91df-873727bb71d0 | textbox | Name:
b393fd46-a04a-52b6-8161-f3958e4cbaa5 | textbox | Position:
40049ab7-4d14-5bbb-b6bb-a6d5eac5c7c5 | textbox | Date Completed:
9ea54448-fdb6-4615-8efb-acbdfde340c3 | signoff | Sign ITP
34d01fba-4858-4d72-ada6-314994c4d336 | checklist | ITP-284-CIV-ADL-Stormwater Drainage Rev 0 | itp | ITP-284-CIV-ADL-Stormwater Drainage
cd06952d-9c1f-40ac-9824-0a62f90c7d9e | section | 1. Referenced Documentation
2e72469e-b11b-4416-9e9d-dda633d92da0 | checkpoint-no-value | Referenced Documentation
46b5bc56-ce98-5951-a6a2-1d4d3cb6d19b | note | Document Title: ITP-284-CIV-ADL-Storm water drainage ITP
1a9cee4b-3619-5d27-82db-d572aa171595 | note | ITP Description: ADL-Storm water drainage ITP
9b5d03c3-ee3d-57af-ab0e-43a9e517055f | note | Discipline (e.g. CIV/STR/RAIL): 284-CIV
e6d01d58-abc4-5d9c-8f22-522fdb4c6221 | note | Revision Number: 0
6842a560-e1e8-5a9b-bd21-0d83a82cc19c | note | Revision Date: 12/06/2025
1c5bf5f4-7aa5-5de6-9fef-8051b722e758 | note | ITP created by: Abhi Patel
20e4a723-ac64-5898-9fd8-2dc9fbc52caf | note | ITP approved for use by: Aldrin Guinchoma
91cc6cbc-3180-50fc-a20d-c545067f9f92 | note | 1.1 - Non Dependent
bd918f95-2e8d-52ec-95fd-25c330047e41 | note | Reference - VicRoads Section 701
0f77b24e-55ce-54d7-b44b-82fd1f3bf167 | note | 1.2 - Non Dependent
74ce8dc0-c671-57e7-8c91-eb739907add5 | note | Reference - VicRoads Section 705
d150e2d0-224b-5195-a03a-24b3ed8d552c | note | 1.3 - Non Dependent
d6c8a01e-ac25-54a5-8a04-4b2465860d17 | note | Reference - IFC Drawings
d3d99194-687e-4e23-9323-9835f577c17f | section | 2. Preliminaries-Materials
777d607c-089b-4cdd-a267-d7990ef11897 | checkpoint | 2.2 - Drainage Flexible Pipes
fbd01ab7-f7ef-5d15-b155-6bc11d6cc8ad | note | Reference - Section 701.08
6b057fea-710b-59a3-8344-64b287849638 | note | Acceptance Criteria - Flexible pipes shall be supplied in accordance with 701.08
469c8c89-8972-59fe-a4ac-7c83c59ba207 | textbox | Enter: Teambinder Material Approval number
8907238b-1b9c-5401-bd16-096415015372 | note | Method - Document Review
31f664db-2efa-51e9-8461-f56ba956d58e | note | Frequency - Each lot
79e2dec3-fe21-57bd-b5d7-b74ff1feca4a | note | Category - HP*
e60aa636-c678-527a-80a2-54df1a767f2f | note | Responsibility - Nominated Authority
33514c1d-db7c-5258-a047-a2d222a889d0 | note | Verifying Documents - Teambinder Material Approval
250bb49d-8e99-5310-8af7-746d0e53b612 | date | Date Completed:
b2cacf8e-8334-4c32-9f2e-4a9b8bcb3a8f | checkpoint | 2.3 - Precast Drainage Pit
5a6cc0e7-12fd-5475-ab42-f5266a744304 | note | Reference - Section 705.07, Section 705.04, Section 705.09
ee967f75-140b-5ff9-a990-03ac1373b585 | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
e56b8a9d-5b72-52d4-86c0-fff7503724b2 | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
1ac7dd6b-f5fe-518c-bb7f-54004002fa61 | textbox | Enter: Teambinder Material Approval number
bd024a08-ac0a-540a-994a-3d625ec8cb23 | note | Method - Document Review
fd159362-db77-5cf4-aa79-9be072abc704 | note | Frequency - Each lot
a0723edc-c85d-5d9b-a797-e74bad678ea5 | note | Category - HP*
6967a3c6-6d8a-5cf2-bb72-a8ace698bf07 | note | Responsibility - Nominated Authority
17209c9b-8a05-5076-a92d-e2239ec7017c | note | Verifying Documents - Teambinder Material Approval
d1e77364-6a74-5f8a-9a33-26a5a3364601 | date | Date Completed:
a3052aac-70cd-4515-a361-d745d8e74ada | checkpoint | 2.4 - Cast in Place Drainage Pit
3bd31697-56e1-57c1-aadc-22d6c9e91a3f | note | Reference - Section 705.06 IFC Drawings
f0674aa0-0553-555e-bccf-adbde05b4ebb | note | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
55a8b08c-959c-5318-814c-1204f3337b3e | note | Method - Document Review
c955a1f6-e5d9-5cc1-873a-b4af04b0e0bb | note | Frequency - Each lot
00b86ba4-7346-5a75-a946-2d1f3f003da7 | note | Category - HP*
0d2628ad-609b-5aa5-8565-2384809feed3 | note | Responsibility - Nominated Authority
53bcc7f4-3d4c-565a-8fe1-6d0b2a148292 | note | Verifying Documents - Teambinder Material Approval
338660cd-94d4-550e-9b1c-c8e4762b2f2c | date | Date Completed:
88a72648-44fc-4d3c-994f-0041a29e5566 | checkpoint | 2.5 - Drainage Pit - Step Irons
cdfaab5e-b594-5101-8728-217799b89745 | note | Reference - Section 705.04, Section 705.12
f285b4e2-951c-5fcc-97e1-3ab2e21e8629 | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
02960a30-02e5-56c2-b0f8-29b3c060c287 | note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
fcd2c6d5-680d-5fd4-9330-d17831e48282 | textbox | Enter: Teambinder Material Approval number
1e955220-7533-5438-8c44-7ac2d289ba5a | note | Method - Document Review
b388e9a8-5ed7-5693-9027-705d37d01540 | note | Frequency - Each lot
13013716-d658-5e11-8902-85d35b8c175b | note | Category - HP*
e8ec8349-1385-5390-b003-39b57f201b81 | note | Responsibility - Nominated Authority
a531147a-a04b-54d0-9445-6d66e9a39980 | note | Verifying Documents - Teambinder Material Approval
8a94efbd-999b-5ec4-8f11-8e22142bd017 | date | Date Completed:
aa75e470-e0a8-4cda-bea6-9df4912e14fc | checkpoint | 2.6 - Drainage Bedding Material
48c0ffc5-7797-5abb-8ef4-47cf8ea9c929 | note | Reference - Section 701.09
df0e90eb-96c6-52d1-b4b8-662009b0cb61 | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
ebf4eca8-907d-567a-ae01-62828aa6e267 | textbox | Enter: Teambinder Material Approval number
ae26a3e0-b092-5c10-aed9-5640c88b2e0b | note | Method - Document Review
3f03f8cd-4cee-5fe0-89c7-96f7976d2119 | note | Frequency - Each lot
4c787bae-9e5a-50bc-aacf-c27eac779f08 | note | Category - HP*
fba2e00c-5f6b-5b69-95ca-589039e8fde7 | note | Responsibility - Nominated Authority
b55a812b-62fb-51cd-b81a-4963f1411d2f | note | Verifying Documents - Teambinder Material Approval
e6d7e29a-8074-5db9-b6d4-9736e35585fc | date | Date Completed:
fe11ff88-60dc-454c-87ac-5e37d8bb620a | checkpoint | 2.7 - Drainage Backfill Material
808cbde2-c380-5339-93c2-626632010e6c | note | Reference - Section 701.09, Section 701.19
ddc30952-b5de-558d-80b5-aafb7c35eab6 | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
a0291222-79e3-50b6-af35-64296e9d0cf6 | note | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
d08d13b8-3eff-59da-a650-1ee0698eece6 | textbox | Enter: Teambinder Material Approval number
aebc55ba-29cf-53a8-90f2-a65c19220bf5 | note | Method - Document Review
d22803de-b2b4-5d68-9a61-48690f3d90ff | note | Frequency - Each lot
476bbea8-fb37-590c-8f65-2c4efe3ef313 | note | Category - HP*
8dfceebd-62f7-50ab-8307-8a23726db746 | note | Responsibility - Nominated Authority
12964f12-dfb3-50b6-980f-7bd82eaf8a13 | note | Verifying Documents - Teambinder Material Approval
ffdb0744-ed59-57dc-92e6-c39e56d89357 | date | Date Completed:
1738d718-00d3-4066-8c94-5b95cbfe4dc7 | section | 5. Construction / Installation Activities
c5aa2ac3-4617-470f-a6ee-d26a5d1e53d3 | checkpoint | 5.1 - Pits - installation
a5829353-7ab9-5110-9c46-fa6bc62b757a | note | Reference - IFC Drawings VR 701, VR 705
5470640b-213b-586f-b0a2-ccca787f2d7a | note | Acceptance Criteria - All the pits for this separable package are installed and respecting Lots are closed
eea95f9e-aead-585f-96d0-234dff62c855 | note | Method - Document review
3d4a5f38-34ad-51d0-b439-d02c905b7a2b | note | Frequency - Eachdrainage separable package
b2a60d20-93b1-5303-b07c-62b9aacab7d0 | note | Category - IP
0d61c52f-8576-5635-a29a-444d03f2cc85 | note | Responsibility - PE
9355429b-797e-5c83-b93e-c7b0327ca9c0 | note | Verifying Documents - CHK-017-CIV-ADL-Stormwater Drainage Pipes Installation
e695feef-7581-5847-be9a-fd0dd8932591 | date | Date Completed:
2b30f87a-f4da-4dbc-80be-55db0c41d22b | checkpoint | 5.1 - Pipes - installation
8c68666a-50a2-5606-8528-e0d24934a142 | note | Reference - IFC Drawings VR 701, VR 705
3eafb165-7b15-5c4d-b6ec-1fe13e703000 | note | Acceptance Criteria - All the pipe runs for this separable package are installed and respecting Lots are closed
1d53917d-4819-5e04-80c1-ee58df114023 | note | Method - Document review
832f6ec7-4cdb-5436-a164-7ffdf2bd2c86 | note | Frequency - Each drainage separable package
271a50d2-b021-5209-8766-302c817c6422 | note | Category - IP
06757a56-2296-581a-9289-c8afe2a51774 | note | Responsibility - PE
3f204bc7-0f22-59e3-9254-f421194f1719 | note | Verifying Documents - CHK-018-CIV-ADL-Stormwater Drainage Pits Installation
d702a511-9df4-5782-bc48-e61c602c79dc | date | Date Completed:
9b71fb10-1100-4a35-98a6-8c8c578a2b80 | section | 6. Post-construction / Post-installation Activities
3d752f54-b44d-4879-a2ed-5667737a0d41 | checkpoint | 6.1 - Flushing & CCTV
e9eea1e1-2d0e-52bd-9469-bd4417dbd7a1 | note | Reference - Section 701.28, Section 701.30
f96afa70-3f57-52c9-bb39-012e4977b911 | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
9e2ba83b-525c-53cf-8c05-8af0af734fc8 | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
04c9d10f-e15e-5eef-808c-ca524dffced1 | note | Method - Record Review
a0f8af4b-a914-516b-b438-fd3c862f45e2 | note | Frequency - Each lot
558bb0f3-cad6-5b18-93da-d5a2daeb5a91 | note | Category - HP
5295ecd3-02ea-5e73-8fb5-265b9727256d | note | Responsibility - Nominated Authority
2a58bd29-d057-5d43-9e62-58101686d8f2 | note | Verifying Documents - This ITP, CCTV Reports
effa00c4-a8a7-547f-9614-f92460958346 | date | Date Completed:
599ab5ed-e022-4d62-959e-17708a3c2ad2 | signoff | AUTHORITY HOLDPOINT
13549660-26d3-4488-892a-75b1f2279ee1 | checkpoint | 6.2 - As Built Survey
982b3cad-96d7-5a2e-af07-b31e686a76c7 | note | Reference - Section 701.10
9953a23d-0c0c-553a-b955-53f8f09f92e3 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
3b7b1d53-4a15-5971-85f2-b37574ee8388 | note | Method - Document Review
bfd90593-eeea-5ece-b2fb-4f1e9f29b0fd | note | Frequency - Each lot
25f8445e-70f2-5b46-b358-ef18fa96e8aa | note | Category - IP
589bd7f9-83c4-57b3-b904-15bdb6877bf3 | note | Responsibility - SE
c5bbf102-4ed4-574b-b409-5de4c4d99681 | note | Verifying Documents - This ITP, As Built Survey Report
bd9477bf-0f58-5adf-bed9-eaba7dfcfd07 | date | Date Completed:
d9cad5e6-5302-4226-ad9b-c9dbb1f9f858 | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
948a13f3-93ec-547d-8ff0-a1640569db22 | note | Reference - MRPA Quality Management Plan
1bf6908a-6159-5a73-9900-9beffab0cc88 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
1cc07766-50eb-582d-b221-da39ef52b7d3 | note | Method - Document Review
b19ade9a-c5cd-5c13-bf7d-32e7b5a76657 | note | Frequency - Once, prior to closure of this lot / element / Work area
3888f4e4-2cfe-5832-b91b-6053bf1d7c7f | note | Category - HP*
783d7dc4-9a2b-51de-8469-4ae7da8a9476 | note | Responsibility - PE
7163de31-d4ec-502e-9a0d-839d2ecc5c94 | note | Verifying Documents - This ITP
ced07f6e-1081-5d48-ad24-6f456efe8368 | date | Date Completed:
159164c7-b34d-4aa5-a931-200c73b50df1 | checkpoint | 6.3 - Repairs to Damaged Pipes
796dd5e7-9153-5a6d-8aa9-d722de1589f2 | note | Reference - Section 701.31
4a60bd24-aa23-5e66-842e-d9da337d30fa | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
5dc12a9e-e267-5e67-a746-5e76990910db | note | — cracks wider than 0.5 mm
3575f3ce-bedd-51a6-af6e-96f63a780a6d | note | — spalling of concrete
97de406c-b986-5988-9828-6f854dc84dd2 | note | — exposed reinforcement
cda3834b-f57e-5930-a5bf-3ba9235f91c9 | note | — joints that are not fully engaged.
f615e218-a803-560a-8fdd-d9c1b6b94e52 | note | ○ Any pipes with defects greater than the following limits shall be removed and replaced:
1e434a2e-04c6-5db2-af03-3c552cad766d | note | — longitudinal cracks greater than 2 mm
c58dcb21-0f54-5ba0-8505-095d983d98c8 | note | — circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
7c679d4f-c2b6-577f-98d5-04f1131caf15 | note | — circumferential cracks around part of the circumference with width greater than 4 mm
4e9efb97-572f-5dc1-9b6e-b88a93535477 | note | — penetrations with area greater than 400 mm2
2f95123b-90f8-5558-b079-bcccb5e88d9b | note | — pipe joints that are separated.
5d2c1f9b-701c-592e-bb12-79b3b22293c1 | note | ○ The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
a4b76e20-2808-57fa-af48-a66e762a6842 | note | — hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
2710c214-2d53-5b0e-a855-d170309b4ccc | note | — fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
619ec9d8-ccfe-5f20-ad7b-9d5b59e105c7 | note | — spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
b3d8ea14-1c22-5b5f-81d4-f8846d26cb0c | note | ○ The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
92baa907-7b4e-5da2-a236-735a777e5e67 | note | ○ No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
7666f42b-98aa-5d5e-a51d-a61b8c5589a8 | note | ○ All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
997fcacc-1bd9-5d97-af94-90c31c6e69e7 | note | Method - Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
8a7ec94f-0ef3-5a8e-a06c-b19ffb5b3fa4 | note | Frequency - Each lot
c5ad1fb6-e5fe-509f-a76a-f913dfbaa681 | note | Category - HP
612a0508-3929-52d4-922e-f9225a7d78a8 | note | Responsibility - Nominated Authority
bf50d0e0-7118-590d-97fb-88c4c57c4b5e | note | Verifying Documents - This ITP, Approved Repair Procedure, Post Repair CCTV Report
43cada80-ef8f-5b34-8dcc-11957ca44718 | date | Date Completed:
ecfdb17e-341c-4697-9823-99f5d73be25c | signoff | AUTHORITY HOLDPOINT
ccf6a924-a023-4d66-9419-0e0a8e5ed7b5 | checkpoint | Final Inspection
f7cb8f98-f0e1-5e9b-a5d5-f30f1131755b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
52d4bad0-9144-5a0c-9d0d-4b1aae72bbb7 | textbox | Name:
7a1e52c2-806f-5f38-aa0a-cf34f80e0d6d | textbox | Position:
7a034ec8-326d-50ec-b60e-d9d96ece8b48 | textbox | Date Completed:
997c6c05-acb7-4af3-a7aa-63d2532e39bd | signoff | Sign ITP
5be6aa5f-ee1e-4fe9-a705-cc39d5aa59ae | checklist | ITP-286-CIV-ADL-Unbound Flexible Pavement-Scale C Rev 0 | itp | ITP-286-CIV-ADL-Unbound Flexible Pavement-Scale C
42779cb4-66d3-4394-a5d2-f5abeb060d82 | section | 1. Referenced Documentation
f44850b0-9f21-498a-b55c-807795640710 | checkpoint-no-value | Referenced Documentation
4d4b02e4-ef20-5d66-b61c-7a785fdbb520 | note | Document Title: ITP-286-CIV- ADL-Unbound Flexible Pavement-Scale C
c1e279c9-cc59-580d-a810-7d33887b08ae | note | ITP Description: ADL-Unbound Flexible Pavement-Scale C
0eb935c5-0e70-550b-8d20-a78e61413a63 | note | Discipline (e.g. CIV/STR/RAIL): 286-CIV-
4413bbd0-5b43-54e3-a7ad-e567c3605671 | note | Revision Number: 0
9c9e9b79-9afc-5aca-840c-b28178bacf4e | note | Revision Date: 20/06/2025
0b1ba540-69b4-5442-a60b-4b2a78cd6887 | note | ITP created by: Abhi Patil
05411262-be92-574a-9a8f-c10e8a47ed0e | note | ITP approved for use by: Aldrin Guinchoma
66c4fe28-4cef-5d7d-916e-5db007de52e1 | note | 1.1 - Non Dependent
167f66ae-772b-576c-8a33-7bb72c255b88 | note | Reference - Reference Documents: IFC Drawings
e63c9613-7ae9-5a92-9225-938f50161a4f | note | 1.2 -
0e4fa3c6-b5b1-54ea-8276-0c00dea48221 | note | Reference - VicRoads Section 173
ecadf879-f1a4-5403-89f5-7cb3dce3c391 | note | 1.3 -
47c780c5-6cae-5461-9fd3-863535c376d0 | note | Reference - VicRoads Section 304
53d297a5-2ac7-5d12-8b73-bc9474801430 | note | 1.4 -
ca7517ce-dc09-5c11-8608-56fceb750bbf | note | Reference - VicRoads Section 801
8dfc1a9c-b1c6-53d7-9db7-6d236baeee9b | note | 1.5 -
8d2b2e21-935e-57ee-9982-068d97c5c9ba | note | Reference - VicRoads Section 812
32c8be1b-1b04-408b-a766-5e7cbcdaa2aa | section | 2. Preliminaries-Materials
4233d6bf-e198-4e9c-b74a-016ce686bec5 | checkpoint | 2.1 - Crushed Rock Mix Design
36257de4-4b11-5f8a-a762-50618b555c02 | note | Reference - Section 304.04, Section 304.05, Section 812.04 Table 812.121 IFC Drawings
33274067-051e-53cb-ab19-b3e7f8aa7d0c | note | Acceptance Criteria - All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
85a45ebf-23c6-573b-9650-b2304269b85f | textbox | Enter: Teambinder Material Approval number
3fbf2424-158b-594f-920d-83787ec055c9 | note | Method - Document Review
0639d968-b855-5b2a-ad38-7e96ed69a765 | note | Frequency - Material conformance as per Table 812.121
f39cce3f-f59d-5999-82a3-5e872010cb73 | note | Category - HP*
17e6031e-0d67-5e47-a75e-75793a77d4c9 | note | Responsibility - NA
8676c3a0-b506-5077-b7e5-2f2d33e1a291 | note | Verifying Documents - TeamBinder Material Approval Number
6ff5a8a0-44f6-57df-b363-9a32662dbaa0 | date | Date Completed:
27356614-3fff-4342-be3c-b436d3704c36 | section | 3. Preliminaries-Documentation
688c71c3-df9b-4459-bd53-e5340c774702 | checkpoint | 3.1 - Subgrade Preparation
bcf13046-c5bb-54df-8de4-72bf59d15b27 | note | Reference - 304.05
bd0a763a-6987-51a3-8b2d-22316133e0c2 | note | Acceptance Criteria - Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
2bb8f264-e1c0-592b-a93d-76a26f10d8b4 | textbox | Enter Subgrade Lot No:
56ff61e8-3c8e-5260-b7c1-7df781600ea1 | note | Method - Document Review
ee44a94d-ce8c-534d-afd3-7985fce382ac | note | Frequency - Each Lot
a81e8283-edf7-5b92-91e0-9e166902dab1 | note | Category - HP*
2c1daed4-e3b4-5c12-9358-c0781e9d703e | note | Responsibility - PE
0b4e383d-93cc-5d37-93f6-51711349b74a | note | Verifying Documents - Underlying layer Lot number
6c1d38c8-c346-589e-b180-b6d13c2b89b5 | date | Date Completed:
5e5c33e3-e56e-4176-82be-15beb65c54e1 | section | 4. Pre-construction / Pre-installation Activities
21ed9d2f-1aed-4433-bf81-82efd748537f | checkpoint | 4.1 - Survey Set-out and Lot size
2e5c9b84-e1e7-55fc-81e0-8e874a5a1f82 | note | Reference - IFC Drawings Section 304.07
77bb14e4-08f0-5f63-8e0a-9ad9332141ae | note | Acceptance Criteria - Lot size shall be the lesser of 4000sqm or a days production.
0b94e0c8-bfd4-5ca5-838b-435b31386632 | note | ○ Clearly mark out limits of works as per IFC Drawings and VR 304.07.
67e07c98-2f93-55d8-8b38-e19b116030c4 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
092de049-7cad-5990-a8ed-00e1639d3f17 | note | Method - Survey, Document Review, Measure
07996402-ce3e-51b5-b700-7edbd12d2555 | note | Frequency - Each lot
ae7a6314-a0c2-522a-a5bd-781c14390a9e | note | Category - IP
5b9160b2-de10-5cd7-98e2-1d1d3fb43479 | note | Responsibility - Surveyor, SE
b56c052c-e8d3-5efe-9b7e-0e8e7a917880 | note | Verifying Documents - Sign ITP
2a410873-1a9f-5dc5-ad33-7b8b4516416a | date | Date Completed:
c202c82c-df0a-49e1-bc1f-a5c8b8ef044d | section | 5. Construction / Installation Activities
9e0f8add-f079-46c0-8b58-a901d3b937b4 | checkpoint | 5.1 - Placement of Material
65e2e152-8dc3-5d7e-b9b1-2ee2aae9d68d | note | Reference - Section 304.08
f20fd815-9e49-57d4-92d6-b90a9adf7491 | note | Acceptance Criteria - Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
31fba38e-3c49-5f21-ae2d-4640d611bc0b | note | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
7cf1765b-c38e-5bfa-94ac-a96445062302 | note | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
0389f629-8c3b-51b7-bc8d-99c6fe54cc68 | note | Method - Visual and Measure
c00906ed-1282-5396-b1bc-c38dc6615613 | note | Frequency - Each lot
d0a941ca-dd18-595f-8450-42fa87743a74 | note | Category - IP
3292e2c6-981d-5d62-8050-b7bffbfc2b41 | note | Responsibility - SE/Site Supervisor
d5eb089a-ab70-56e3-9d8f-628e0457bd3a | note | Verifying Documents - Sign ITP
d36acc31-103e-57b9-ab65-b6628456712e | date | Date Completed:
d0eadaaf-0353-4703-a236-1ca20c11a218 | checkpoint | 5.2 - Construction - Jointing
8e46eb34-f1cd-5339-a61f-9b861f7be1cb | note | Reference - Section 304.08
ffc28a52-441f-5506-ab11-38388bda21a7 | note | Acceptance Criteria - The layout of joints shall conform to the following requirements:
1419bfa8-a9f3-5260-823d-7c8af86eb5c6 | note | (a) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
660b991e-f718-5c3e-8e22-d5411d8ad7ae | note | (b) transverse joints shall be offset from one layer to the next by not less than 2 m;
b4effc79-b5d4-5b17-b0c7-df9c2abb2dfc | note | (c) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
c5fd583a-dd9e-5a9a-a45c-460062f4ad3c | note | (d) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
c3b9fb00-08f8-52c2-bcb2-50141bc09632 | note | Method - Visual and Measure
bf41961a-2e1a-5c15-a232-d145e5cb7ccc | note | Frequency - Each lot
7738c8d4-820d-5e8f-accd-199d8d22dca0 | note | Category - IP
9f15ba7c-249d-51b8-a1ee-653483069c24 | note | Responsibility - SE/Site Supervisor
d9b84563-4af9-517c-b1e9-252eab440151 | note | Verifying Documents - Sign ITP
e2573251-f3e0-5a73-b66b-347b03662962 | date | Date Completed:
581d68c5-52e9-4c7b-bd33-bdfb51cf891f | checkpoint | 5.3 - Compaction test (Frequency)
ff1ea210-d45f-5953-9391-7f4db99cae5e | note | Reference - 304 .09 (b)
37a98044-4d1b-5c9d-93f4-42e91fdac989 | note | Acceptance Criteria - The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
5cbb0164-9428-5297-8803-a73993ed9e48 | note | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
bcee1c92-135d-5a59-bb69-42af354f1fb2 | note | ○ Scale C: 3 samples
edd5b538-c582-5896-9f1d-1fa48e07c9c8 | textbox | Enter: last tested lot number
1cf7c365-51f0-5a2f-8e20-b01a71755936 | note | Method - Visual
4c04914a-a34e-57bf-9a7c-3af00ea31bda | note | Frequency - Each Lot Where applicxable
957f1c4a-eb07-54bb-8859-4bd472df3753 | note | Category - IP
2cf91b28-284c-524a-81ac-11fce3bb17db | note | Responsibility - SE
46c497ba-fdf5-5bb6-9d62-8ddc4ac5b899 | note | Verifying Documents - Sign ITP
e5ee2f7d-8974-59cb-ae9d-70ca5369653a | date | Date Completed:
b846a639-5913-4411-b362-40d70ae6bd1b | checkpoint | 5.4 - Post Compaction Materials Testing (Frequency)
c64e9eed-bb6d-5b7b-8c71-eb1ef2ced6b9 | note | Reference - 304.11
c6056a83-6379-51d4-896b-d36b0623a7c4 | note | Acceptance Criteria - SCALE C: Atterberg Limits and Grading
9eeebde6-e76c-564e-bee4-737667f7b712 | note | Method - Visual
3bfaa809-b731-5200-a171-09ffbd2a3df7 | note | Frequency - Each Lot Where applicxable
35758695-f763-51ec-9e2d-4f520e0edde1 | note | Category - IP
9ff873fb-83f3-5787-8b88-87ccfc477564 | note | Responsibility - SE
5e8ba609-6e5e-5b33-b1da-104d55fd9528 | note | Verifying Documents - Sign ITP
548ba973-f0e1-5307-bb2d-f91d49976280 | date | Date Completed:
2e945b60-8e6c-4921-8b14-98614a699860 | checkpoint | 5.5 - Proof Roll
9fac54c9-b450-5cdb-96cb-7be43c8e7cbe | note | Reference - Section 304.09
cc2ca2ff-e5de-5880-8ebd-fc1f32b470a2 | note | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
708918b1-2c39-5551-a80e-c40249b63bd1 | note | Method - Visual
e59c866b-4bf0-58c5-9613-f2741a131e60 | note | Frequency - Each lot
0fe6229b-a70a-58e9-b096-2611aa95d8fb | note | Category - HP
67b78268-c5e7-53a8-a773-25bda0dc6ec9 | note | Responsibility - Nominated Authority
3019776c-6cbc-582d-9a1f-1c896e40fcbe | note | Verifying Documents - Sign ITP
4df6c903-0230-5cd9-be31-cd66940c8a0f | date | Date Completed:
a5cdd3e3-f0ec-447f-853e-59b898ab1f16 | signoff | AUTHORITY HOLDPOINT
9eae96f9-6896-4c05-84e9-73c420436124 | checkpoint | 5.6 - Protection of compacted layer
c0b921fc-c065-5f19-b54e-2bcfc0e4a501 | note | Reference - Section 304.10
a59cbf71-30e3-5e60-a0d4-b61435ec1863 | note | Acceptance Criteria - The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
07446ea6-b8ad-56a2-bb23-cf8684c6ba33 | note | Method - Visual
6f82d288-2bd2-5923-8d14-914a61192af7 | note | Frequency - Each lot
0943f563-63d8-5099-a715-df20b520c9f9 | note | Category - IP
8c82e632-5b50-5f7f-9d90-1c3c6df2b78e | note | Responsibility - SE/Site Supervisor
e03896bc-a57b-5e22-a46c-26ad78314806 | note | Verifying Documents - Sign ITP
bee7b0c8-3f42-539b-930d-2ec041e5331f | date | Date Completed:
63b2761b-1570-4901-a2b3-dac9d7be523d | section | 6. Post-construction / Post-installation Activities
bb408391-76ef-4627-9f23-aecd2699bad4 | checkpoint | 6.1 - Compaction Testing (results)
8217c44f-c730-58b1-98bf-451a624f7a33 | note | Reference - Section 173, Section 304.09 Table 304.091
31316666-8f5e-5482-8e5c-f2e8aadff2c0 | note | Acceptance Criteria - During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
629e715d-4e4a-51a8-8e30-cf33abf209d0 | note | ○ Density Ratio to be based on tests performed with Modified Comp active Effort.
2642f632-c32a-5764-b028-7d2947048322 | note | ○ Scale C:
f40b509b-2ad8-524a-b369-e576a6702083 | note | — Subbase Layer CDR ≥ 98%
b52a7054-f09e-5c11-bd36-9d1881bdd7a6 | note | — Base Layer CDR ≥ 100%
2cd0a7c3-c767-5a0e-9133-ec250d0885b1 | note | ○ 3 tests per lot
53798202-fc2c-513d-9442-d2d27182beec | note | ○ ATTACH: Compaction Test Results
d68e769e-9190-5d62-8ea4-490ea0eb5af7 | note | Method - Document Review
051f107b-a4fc-5a77-8519-7bae08e1b6ef | note | Frequency - Each Lot Where applicxable
c49ed077-aa8c-5cda-b423-c98ba5270b9c | note | Category - IP
bb02a174-e701-5129-a880-2377b41d297b | note | Responsibility - PE
fd78be75-61e9-5fa9-b0c6-bfd505bcf8da | note | Verifying Documents - Compaction Test Rersults
661ec649-1702-548a-9a1e-0c5a93429eb4 | date | Date Completed:
00e7e106-c8f2-44b7-8af1-0160740dc46e | checkpoint | 6.2 - Post Compaction Materials Testing (Results)
3308ea8f-0823-5bf7-99ea-4a21ce9b0171 | note | Reference - Section 304.10, Section 304.11 RC 500.02
9f8933e5-f9ec-50bb-bc11-1daca60f0ae3 | note | Acceptance Criteria - Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
a1079418-7f17-5877-9358-5da54cf1862e | note | 20mm Class 3:
10e7d7c3-c239-531f-b717-c63db4dea420 | note | Grading
cdae8dc0-981d-5c7b-9e70-3bcb1871dc5a | note | ○ 26.5mm 100%
e4484177-2ab6-54f5-9221-06e1fb5609e3 | note | ○ 19.0mm 95-100%
143fa684-8589-5884-96e1-7d55e235839c | note | ○ 13.2mm 75-95%
b6f8b1ac-8357-5d74-ad38-b4222421faee | note | ○ 9.5mm 60-90%
062d4fc3-d184-500d-b0e7-6033e56f3daa | note | ○ 4.75mm 42-76%
b0cdb435-11cf-5e90-a5f4-10df7946f16d | note | ○ 2.36mm 28-61%
3e4527d5-124f-5e72-984a-97bb0e586950 | note | ○ 0.425mm 14-29%
3859ae57-92ca-5c6c-8f75-ef08245349a0 | note | ○ 0.075mm 6-14%
e885b52d-5412-5b94-b196-b9420001aada | note | PI between 0 to 10
4acccf1f-e174-5af7-9484-85ebcf35c8c6 | note | 20mm Class 4:
a565e08e-45b8-5144-a5ae-87777cd96deb | note | Grading
7a64b99f-f528-5329-b2d3-3572205987ce | note | ○ 26.5mm 100%
289bf61d-3c51-59c2-ad66-268b3615585f | note | ○ 4.75mm 42-76%
b308e6b0-fc2e-5cc2-bdb6-824d336886a1 | note | ○ 0.425mm 10-28%
2455b50c-2f14-5986-93a0-27457d9f1b18 | note | ○ 0.075mm 2-14%
92ea1770-1a56-5859-bad2-109e1332ccbb | note | ○ PI between 0 to 20
90b24778-0e1f-5681-b97b-f9bfbd919b93 | note | ○ PI x % passing 0.425 mm sieve (max) 450
c2c34fe8-81ec-581a-b8af-354aee257472 | note | Scale C: Post compaction material testing is not required (Choose NA)
e531f342-84e5-5986-a71d-c586fb7f679a | note | Method - Document Review
c787a246-9219-50aa-b901-2fcda2a388d2 | note | Frequency - Each Lot Where applicable
79210cb5-231b-5496-a42c-19d3101981f9 | note | Category - IP
59611245-5aa2-5c32-ac77-bab1463da3d6 | note | Responsibility - PE
b44aef57-a9b6-58d3-aee1-145c4fa111f8 | note | Verifying Documents - Compaction Test Rersults
1c1f8fd2-b248-563f-beea-ed41c2e89091 | date | Date Completed:
f5ed849a-fede-4124-af03-efe5e442b63e | checkpoint | 6.3 - Survey As-Built - Width and alignment
701ba4ab-c42e-58b4-8f76-218ef1df01a0 | note | Reference - 304.07 (a)
ecd79cca-bb83-53ac-9d28-8d271c0ea56c | note | Acceptance Criteria - The width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
bafe5ebf-1e2d-574a-8a2f-fba47fd6a197 | note | ○ Attach: Survey Report
43fb7307-bcdb-5d6a-b64a-a2c0bca793aa | note | Method - Document Review
ed4245aa-40a1-5867-b476-ecee9491ed61 | note | Frequency - Each lot
bf7dbbce-52c5-54a2-9706-7ec8ddee4fbe | note | Category - IP
a66b5ecd-9855-5187-ab0c-9ed1db7467ab | note | Responsibility - PE/Surveyor
420516a2-0328-5dd0-9911-f5cd1e7e907b | note | Verifying Documents - Survey Conformance Report
6372231a-fc4c-5f21-b988-5ad06caa967a | date | Date Completed:
eefcf55b-197a-4f81-985c-96a70c4b1c44 | checkpoint | 6.4 - Survey As-Built Thickness of Pavement Layers - CARPARK PAVEMENT
8a2c8235-f7e3-513f-afeb-847ecc973662 | note | Reference - 304.07 (c )
1e8abef6-e305-5209-a360-b88818e5b719 | note | Acceptance Criteria - Subbase course shall be not less than the specified thickness by more than 15 mm.
ac612b73-3f5d-5b2b-a7ad-d694291be05c | note | ○ Base Course shall be not less than the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be less than specified thickness.
c9facc08-41e6-59fa-992e-b662828a29c4 | note | ○ The combined thickness of subbase and base courses shall be not be less than the specified thickness by more than 15 mm.
ccdc7b40-975d-58ed-b578-1cd73a122f13 | note | ○ Attach: Survey Report
39b14d7b-9937-5aa6-98f6-aea875a96cd8 | note | Method - Document Review
91b5bc0e-3b2c-5294-97ed-d85c573665cd | note | Frequency - Each lot
d123fc8b-7511-5f1b-aba8-85a993701a81 | note | Category - IP
b8e73348-ef9c-585d-b56f-5bf53b3746f6 | note | Responsibility - PE/Surveyor
cf241f68-e8cc-5d46-8c8c-5f9e8d16276c | note | Verifying Documents - Survey Conformance Report
183dbb7e-9461-5f7d-9582-29ec415a8982 | date | Date Completed:
4ff42b25-1084-4980-afbb-37e7c171c8dc | checkpoint | 6.5 - Survey As-Built - Surface Level - MAIN ALIGNMENT ONLY
e0c0ef56-8b44-5647-9479-c2679e7a2f17 | note | Reference - IFC Drawings Section 304.07 (b), VR 304.07 (d) Table 304.071, Table 304.072
aa6cead6-d83b-5407-a654-e234d3723db4 | note | Acceptance Criteria - - No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
6e07cfc2-108c-5576-bf0f-5489ad811bcc | note | — At no location shall water pond on the surface of any pavement layer.
aa74ed12-360c-50ee-8f85-1122360e9d3d | note | ○ Scale B: A minimum of 40 measurements per lot
aa8341ca-bb05-594d-816b-99275f396144 | note | ○ Subbase: mean range +8mm to -16mm, maximum Standard Deviation of 15mm
e3af192c-ca36-5c9e-829a-2b5ae12321a1 | note | ○ Base: mean range ±8mm, maximum Standard Deviation of 10mm
612006e2-bc5d-55d6-868e-b1f680e72636 | note | ○ Attach: Survey Report
34d65c32-0c3d-5d32-b770-d9bbcff16dbb | note | Method - Document Review
89e4fd06-2604-5543-a9eb-20167dd896e3 | note | Frequency - Each lot
eca38ab7-56a1-5e06-aa49-3558b967d983 | note | Category - IP
d4a38ca2-560b-5b91-ae55-c65e7d4fa254 | note | Responsibility - PE/Surveyor
382be2da-3dd0-5414-b8c8-ec29b05c0e25 | note | Verifying Documents - Survey Conformance Report
98baf3da-2ab5-5dcd-849c-111103503c86 | date | Date Completed:
022ed2c1-76c2-4c4a-9e89-0ddc9455775e | checkpoint | Final Inspection
548cc930-d8ca-5582-a864-7569fdb7d42f | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
38a9224a-485d-5897-b10f-c9fa955ec39b | textbox | Name:
6401c245-7ee1-5ed1-8419-d1fa8f45415c | textbox | Position:
9d6b2524-dda7-57ad-8564-225e68c1dda5 | textbox | Date Completed:
c5fa05ec-d5a5-4f16-86ae-0a3c19ae6667 | signoff | Sign ITP
dee6e990-ec2d-407b-93ba-1fedbed6c7af | checklist | ITP-289-CIV-ADL-Heavy Duty Vehicle Crossing, Shared Use Path and Footpath Rev 0 | itp | ITP-289-CIV-ADL-Heavy Duty Vehicle Crossing, Shared Use Path and Footpath
6b00d0d5-7af0-4ac4-aadb-5dee462194c7 | section | 1. Referenced Documentation
690590cd-ac87-473c-b37e-20d104c9c2f1 | checkpoint-no-value | Referenced Documentation
9dfa3c68-5d26-5c36-b171-0f25bce59210 | note | Document Title: ITP-286-CIV- ADL-Unbound Flexible Pavement-Scale C
1f25bf63-c343-5044-bca3-4aa61c07ec6e | note | ITP Description: ADL-Unbound Flexible Pavement-Scale C
afbdac83-e61b-56b1-8a86-625db1176447 | note | Discipline (e.g. CIV/STR/RAIL): 286-CIV-
c58ebd29-562b-578b-80b0-fc20bf76d113 | note | Revision Number: 0
ec0b2b14-c404-5559-8b71-a2279fe761be | note | Revision Date: 20/06/2025
9061e500-c7e4-5637-800d-f41ce79ee336 | note | ITP created by: Abhi Patil
6b8707dc-37c8-5683-a4b0-6352ac9644ad | note | ITP approved for use by: Aldrin Guinchoma
a84fbb89-f429-5b02-bdb2-bffa27371947 | note | 1.1 - Non Dependent
e0e1080a-0ef4-5276-8c00-5927a3138b60 | note | Reference - VicRoads Section 304 August 2013
16151eeb-3a3f-5dfa-b81b-c36b2bcc6672 | note | 1.2 - Non Dependent
bd51c458-c0d2-5ddb-8dee-5e1db529e51a | note | Reference - VicRoads Section 703 April 2019
2102c728-55ae-51bb-ac3b-fbf32011b7a3 | note | 1.3 - Non Dependent
0ad8f28d-4356-52a5-93be-79f09c913d3e | note | Reference - Council IDM SD 250, IDM SD 236, IDM SD 205
72fed05f-51bb-5fdc-8f6e-20b5e8609670 | note | 1.4 - Non Dependent
48ddd0de-40c9-51bb-bc0d-1f192ba20bf6 | note | Reference - AS 1379-2007
b1e37c28-bbb5-5cdf-a753-c06daa30ca47 | note | 1.5 - Non Dependent
bb762a5e-a316-574e-8f15-74010cec1676 | note | Reference - VicRoads Section 812 July 2016
cb477870-46ba-5b36-97c3-631694daf9bb | note | 1.6 - Non Dependent
ca0070a9-66f9-595e-961c-f400be398621 | note | Reference - IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012
0d6f7a0a-89d1-4cbc-a6e5-6372da8006b9 | section | 2. Preliminaries - Materials
679fc1f6-90f6-47bb-8220-ba6259d0a281 | checkpoint | 2.1 - Bedding Material Placement & Compaction
c1365c5f-129d-5a56-a40c-01ffd89ad6c8 | note | Reference - IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012
345f1459-8abe-5a40-9ac6-d4832eae8a66 | note | ○ 812.04, 703.21
8ee7064f-80c1-5711-8226-45ad03fd3de0 | note | Acceptance Criteria - Footpaths: SIZE 20mm CLASS 3 CRUSHED ROCK
8ce0395d-aeb7-54b2-8a5e-f230b1881aea | note | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.3
ae3a2712-65cb-5ee0-8424-11bb5c68b0b4 | textbox | Enter: Teambinder Material Approval number
e5ceb974-61a6-591f-a115-2c225c76390c | note | Method - Document Review
3d4109b0-966c-5f17-8261-53a7fd2d7f51 | note | Frequency - Each Lot
36a5927f-2579-5395-9bee-01c15d939d52 | note | Category - HP
0bf824c6-3fe5-504f-a9b9-9736d14cebb0 | note | Responsibility - Nominated Authority
1c207ad1-9cf6-555f-8a66-10d6641d976d | note | Verifying Documents - ConQA Hold Point Release
b2947b53-87ef-5169-8552-e256c5393c9b | date | Date Completed:
6ea24a7b-e028-47c9-9df7-0fe1e6f6598a | signoff | AUTHORITY HOLDPOINT
fe225bc9-95b7-49e7-8f36-0b8b1675dc95 | checkpoint | 2.2 - Concrete Mix
e541e858-8f82-5223-97c3-6ed2fc2745a2 | note | Reference - IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012
aedd9853-c60c-5029-9f5d-104e4f507f23 | note | ○ 703.05 (a), 703.07
82cb5e43-c79c-52cd-91a8-6f9441105d91 | note | Acceptance Criteria - Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings:
e83fe8af-0c98-5849-a5df-7899051933dd | note | ○ Heavy Duty Vehicle Crossing (PA1):
4fa31fff-4ead-5c87-86d5-ca6e24505d60 | note | — Concrete Strength: 32Mpa
7432715a-885d-5570-b8dc-6321f4b8a2f0 | note | ○ Shared Use Path (F1):
4e4c7d76-b242-52b4-825c-12abbec81c87 | note | — Concrete Strength: 32MPa
6b91751b-b9d4-54a2-9cbe-d8d121432f8e | note | — Min 30% SCM
ae22dd9a-dfba-51a2-a514-44543a22ecc2 | note | ○ Footpath (F2)
f259620c-5a90-5b7b-93d3-730c9c088ccc | note | — Concrete Strength: 32MPa
d5f88bee-47a3-50d8-b41e-ced4f800f5e0 | note | — Min 30% SCM
12de84b5-5f19-5a97-a183-ae5f721a6a0b | note | — Macro-Synthetic Fibre Reinforced Concrete can be used in lieu of steel reinforcing path given council approval
d1306ff5-a31a-5bda-8e4d-667cd9218f43 | textbox | Enter: Teambinder Material Approval number
158e6c2f-f179-542c-983e-510265775ede | note | Method - Document Review
ecb4d208-65ce-526e-a49f-81bfa5e53c31 | note | Frequency - Each Lot
b5769535-becd-556b-ad51-948cb899dd2b | note | Category - HP
f973339d-a48b-58d2-9e3a-ed1f3987300c | note | Responsibility - Nominated Authority
d13025d5-54f5-562b-a08f-45ae84947c1e | note | Verifying Documents - ConQA Hold Point Release
8b68eba2-274f-548f-b63f-edd4ed9ec2d1 | date | Date Completed:
c665615b-cea4-4ec0-a93f-794d01b82616 | signoff | AUTHORITY HOLDPOINT
41c4ffa2-9293-41cf-a435-ef8e4cb497c2 | checkpoint | 2.3 - Reinforcement
c9d9c342-25ee-5405-9b0b-d302e59c319e | note | Reference - IFC Drawings
1851c03c-a9ad-5ab1-99c5-57fb56f40219 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
57979344-64d2-51ef-b5c2-3e462627d3fa | note | — 703.16
773c0b6a-0fcb-5bfe-89fd-dda5fd6e05ac | note | Acceptance Criteria - Reinforcement shall comply with AS4671. Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
2698c9cc-81a9-580a-a441-1d7e8347ae8b | note | Following steel mesh requirements shall apply as per IFC Drawings:
b8ee2045-a66e-58cb-ba1e-080e28cd2a78 | note | ○ Heavy Duty Vehicle Crossing (PA1):
65b4df25-1d6c-5374-8291-b72984c78e9b | note | — Two layers of SL82 Mesh (Top Cover Min 60mm)
23ef6b84-3e00-5551-afb9-93c2ffdadf8c | note | ○ Shared Use Path (F1):
09c409d2-44b3-52ee-ad4b-c84eb6f99dea | note | — SL82 Mesh Placed Centrally
d46bd227-554e-5607-a4cc-2eb53a8bf1db | note | ○ Footpath (F2)
2bad65e4-9421-59a9-a4e6-1c185c8b56fd | note | — SL72 Mesh (Min 50mm Cover to All Edges)
472e31f7-51f7-5062-8426-0d92ffe95146 | textbox | Enter: Teambinder Material Approval number
df2d5e42-59bd-5cf5-80a9-2774b71c1d71 | note | Method - Document Review
24463e2b-657c-58d8-bb75-1535fa278350 | note | Frequency - Each Lot
7f9e5954-d59a-5589-953f-91e7d567a3a3 | note | Category - HP
4ca8ff9b-f22d-5d07-b2d5-75e26698a6d0 | note | Responsibility - Nominated Authority
e682a6a4-756d-5623-a381-e41625dabe2d | note | Verifying Documents - ConQA Hold Point Release
194475fd-dce9-5052-a855-64b949dd94c2 | date | Date Completed:
2d3d4e0a-eca9-44bd-9071-3bb3d941fe16 | signoff | AUTHORITY HOLDPOINT
57b6a59a-6540-405a-884c-2568c89ae18d | checkpoint | 2.4 - Evaporative Retardant
90f51e9d-5935-549a-91a4-1ba451b8ad61 | note | Reference - 703.09, 610.17 (f)
8ba06c18-3bba-5770-a41e-61a039715e1a | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
95095497-e35e-5722-83fc-4d49911c836e | textbox | Enter: Teambinder Material Approval number
91b35a8b-16af-5e29-b272-5b198c389f7a | note | Method - Document Review
3bd9995a-febf-5e14-9412-0e8df09ec750 | note | Frequency - Once, for each product, prior to placement of concrete
8f811458-c201-5ebd-8e05-18d46eea640e | note | Category - HP
a979980a-bb12-5de0-906b-8b4bc78893de | note | Responsibility - Nominated Authority
000c0642-3449-50b5-bdfb-f05a0e1648ae | note | Verifying Documents - This ITP
e9b0328e-7613-5541-9eef-03c7bff90550 | date | Date Completed:
17a59767-c3f1-4205-95e5-f9e1be82e1f3 | signoff | AUTHORITY HOLDPOINT
0478264b-c4be-465e-96a9-b77646857561 | checkpoint | 2.5 - Curing Compound
ea237233-27f3-5adb-a7c8-0dce7f2ab2a3 | note | Reference - 703.10 (a), 610.23 (d)
21259750-46a0-5987-90e5-267727b67937 | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
469fd15c-5557-52e3-8af5-9666a511312d | textbox | Enter: Teambinder Material Approval number
330a2339-7f26-5a7c-8172-bda79bd77ae5 | note | Method - Document Review
0fdc0cbe-9eaf-57b2-a3e9-c637431b4193 | note | Frequency - Once, for each product, prior to placement of concrete
83dbbbd9-fd16-5555-9719-60e42104d2a5 | note | Category - HP
f977cf4d-5278-5122-8c63-6eab1db5c087 | note | Responsibility - Nominated Authority
cad6e33e-8073-5604-ad59-3cc56beabcb5 | note | Verifying Documents - This ITP
e4d6ee3c-c91b-555a-b2cb-b6cbc6d73558 | date | Date Completed:
de91bbed-99f6-4c7f-8443-5da64bb61f83 | signoff | AUTHORITY HOLDPOINT
2fcb1973-fc24-48f2-9c35-6170718ec19d | section | 3. Preliminaries - Documents
bd4d7054-1348-4bd8-9b5c-76263da8b75f | checkpoint | 3.1 - Survey Set-out
18c3bf35-7461-5235-9a94-689cd3721fc9 | note | Reference - IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012
4f3d89c7-bbec-5f18-b52b-8468aa274990 | note | ○ 703.17
190d957e-d67d-58d1-9bfa-808c4537f2a3 | note | Acceptance Criteria - The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
20906e1d-d987-5ac8-8f23-7778ac5da3ea | note | ○ The Nominated Authority will review and confirm the set out.
614f9d31-02f0-5117-a236-8dc240debf7b | note | ○ Attach: Survey Report
04dc3e29-4734-597a-b1a1-a2496b2651d5 | note | Method - Document Review, Measure, Visual
0e23622a-0a27-5828-87a5-6256e539f173 | note | Frequency - Each lot
05a62350-5aaa-5fad-a36e-d0803d22ec52 | note | Category - HP
550c3874-3be2-5d19-8376-29e59e7ad986 | note | Responsibility - Nominated Authority
8fdd3ec7-2fe1-578f-a62a-0b2c4db31dbf | note | Verifying Documents - ConQA Hold Point Release
2f3a7633-9476-5583-82af-4be4a38eaa10 | date | Date Completed:
c7b5a64e-97f1-4ced-a6ed-028b37a5e708 | signoff | AUTHORITY HOLDPOINT
7aee4994-bd4a-42b0-9453-519cfce3bb70 | checkpoint | 3.2 - Lot Map
4ee6a3ef-fb16-5012-86b6-df1502bac0ab | note | Reference - MRPA Lot Management Plan
b5b376bd-da38-5017-891c-5ebf61effcde | note | Acceptance Criteria - Attach Marked drawing indicating the location of this Lot
4aaee557-1225-5300-b2ff-f67da43312c3 | note | ○ Attach: Lot Map
716af710-373d-5499-868b-f504af9e9b2c | note | Method - Document
f94735b8-68df-535d-baa2-c55cb26f1b08 | note | Frequency - Each Lot
6ddf328a-7826-502b-9f99-4ba6e6aa91d6 | note | Category - HP*
1a04ae3d-5274-5723-b22c-285ea140ba32 | note | Responsibility - SE/PE
ea61569f-9909-5c9b-ab3d-624cd6349ffe | note | Verifying Documents - Attached Lot Map
1d9a4e6d-960e-5260-859a-a2911b5740be | date | Date Completed:
97f44105-030c-496a-ab68-94451d5ab741 | section | 4. Pre-Construction Activities
69c1b18c-de04-4bfa-9086-b2467e6694bc | checkpoint | 4.1 - Site Clearing & Grubbing
47676e0a-41f3-54a2-81e0-6769f7551489 | note | Reference - IFC Drawings
d5035978-f9ec-54d9-854c-ae440940bd55 | note | Acceptance Criteria - If not completed during the site establishment, the work area needs to be cleared and grubbed.
03baf9b4-6ee9-570c-8274-9700b3e1a67f | note | ○ Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.
bb94737b-4088-5bc9-953e-abc6e0e76680 | note | Method - Visual
581352f4-9f52-50e5-bee0-c73385c0fcca | note | Frequency - Where applicable
11e76ddd-e0f4-50bd-88fb-7ef6338b6359 | note | Category - IP
195b0a22-b988-5408-bd35-53ee6bde5c15 | note | Responsibility - SE/PE/SPE
1c5a3638-b210-589c-8215-a49f5411254f | note | Verifying Documents - This ITP
ea5b3091-331b-5a79-840d-26e577aa0e45 | date | Date Completed:
7969f56c-e711-4d90-a3de-3c7b969a5b9a | checkpoint | 4.2 - IFC Drawings
cf0a6b13-7401-538c-8835-565da90ba6a6 | note | Reference - MRPA Quality Management Plan
6ab8063b-7710-5412-97a4-0fce447e2198 | note | Acceptance Criteria - Ensure that all employee and sub contractors are:
28a6f09d-ca11-5670-bf56-19a431068f30 | note | ○ Using the correct and complete set of drawings
cb3d7efa-1c56-5961-92fa-770167b051cc | note | Method - Document Review
e8d55265-af1d-5d13-964f-1762679257d5 | note | Frequency - Prior to starting Works and at regular intervals
3d9d9947-6bb0-5dab-8fbd-b7601fc1195a | note | Category - HP*
475c555b-553c-5be4-8ffb-6ed7671e9dd3 | note | Responsibility - SE/PE/SPE
930e2c83-b98e-5970-bf9a-a27038d22426 | note | Verifying Documents - This ITP
6a70bf84-734d-5a59-b97c-9d6759127de6 | date | Date Completed:
df8a68fa-bfb2-4885-af99-c97e2b8130b6 | section | 5. Construction Activities
d748097f-23f5-4c7e-828e-fb7089572f36 | checkpoint | 5.1 - Excavation
6fb09a30-26ac-595e-b970-5eb424dd1b19 | note | Reference - 703.20
0e70024b-c29e-5329-a241-862378e78d64 | note | ○ IFC Drawings
adf31466-b97b-5ae4-bd8e-40a28e50b249 | note | — IDM SD 250
6ab2b016-c388-56cb-aa6a-22a1fd92da54 | note | — IDM SD 236
e25ba1c1-477b-53b7-8d1d-c13f27f6a517 | note | — IDM SD 205
0240102c-0839-5519-a4ef-3315ed10ef5e | note | Acceptance Criteria - Where the new vehicle crossing is proposed at exostomg vehicle crossing locations, the existing granular subbase can be compacted and retained under the new base.
bd690a47-6d29-5c0e-8a6a-2b3ad2a66707 | note | ○ Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
81e7964d-ece8-56b7-bcc8-6ad67c37ff89 | note | ○ Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
1bc6e722-1feb-5f39-9f3b-675fd83d2793 | note | ○ Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
0df3e917-533f-507a-9266-063f78536529 | note | Method - Visual, Measure
470763bc-a3fc-5461-911a-25f984f0ef1d | note | Frequency - Each lot
2fa65bbc-1aac-5772-96f5-a6c6201feae0 | note | Category - IP
4f0dd5eb-94cd-536a-9c41-545a8b424e13 | note | Responsibility - SE/PE/SPE
53a1ba19-4edb-5e8f-828b-380308199c2f | note | Verifying Documents - This ITP
15e7919a-f8a7-54b5-94a1-f2cbcaaf671e | date | Date Completed:
e1a84d0c-fc27-47a2-b9ab-c2193f44ff10 | checkpoint | 5.2 - Excavation-Pavement Thickness Increases for Crossings
f6060537-a179-55b3-b402-e1c9d4c93c00 | note | Reference - 703.21
4db253b4-313a-566c-8cb2-5b1942bbe46d | note | ○ IFC Drawings:
e16ecbbd-00c4-5f40-92f2-461cf0644ec1 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
4586cfae-f2e4-5a96-a8d7-8889bbf7b3ff | note | ○ Relevant Council drawings:
f0abec57-f2d5-509f-92f0-5bcabf7ebf09 | note | — IDM SD 250
a6d48346-3207-5581-94c4-3d708b4b1407 | note | — IDM SD 236
9ccd7351-a9de-5921-95ac-c5e32cefe570 | note | — IDM SD 205
ac2be723-5af0-5711-8174-6e31eed6e1fe | note | Acceptance Criteria - Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing.
f7b7782b-62ad-5e7a-a0f6-4ec1b74270ce | note | ○ Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
5df437b7-306f-5cc1-af9e-91cb1355e728 | note | Method - Visual, Measure
47d10e58-c7ca-5fb7-ac83-eb1329e72bd9 | note | Frequency - Where applicable, each lot
3d46da93-296f-59d9-a424-74da925b22bd | note | Category - IP
63025b69-046e-5a6a-b128-20d3c1c9dbd9 | note | Responsibility - SE/PE/SPE
d0812f53-2c90-5ad8-a9da-b74c8adf34bc | note | Verifying Documents - This ITP
7fd994e4-a27d-5c98-8c77-ed5d6316eb12 | date | Date Completed:
86477289-9bdf-4fc7-a24b-b43df4296d17 | checkpoint | 5.3 - Bedding Material Placement & Compaction
3e057b27-46bc-598f-a6e1-86f0fa6dbb47 | note | Reference - 703.21
d406d886-75e1-5ede-81ec-a5cc2066280f | note | ○ IFC Drawings:
0b2e3fab-1aaf-5653-b1de-0923acb0ffce | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
2164a054-13df-5bb0-8f7b-eb8fab55c565 | note | ○ Relevant Council drawings:
99d1d0b9-d5d5-5a9f-86a3-fa2a634348fa | note | — IDM SD 250
94ab9661-1e92-5dc9-bd71-036f0629cdd0 | note | — IDM SD 236
bfc12e37-d489-5277-8d4c-765028b6fcc6 | note | — IDM SD 205
c81a00f2-a791-5ae8-a8cb-14df2b3c6374 | note | Acceptance Criteria - Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings:
79634473-36bd-5e45-94fa-695c4af8a466 | note | ○ Heavy Duty Vehicle Crossing (PA1):
f4068e8a-00d8-540f-966c-5c18c6f7bc0f | note | — 20mm Class 3 Crushed Rock (Min 100mm Compacted Thickness)
16a1d7fe-5a6c-5ff5-a7b0-1d1246593692 | note | ○ Shared Use Path (F1):
552695ac-a508-58b4-a94f-1bd544278ed8 | note | — 20mm Class 3 Crushed Rock (Min 100mm Compacted Thickness)
c2b3906e-1777-540a-a6b1-ad735f8ce5b9 | note | ○ Footpath (F2)
b63d37b5-0ae1-5389-bd6d-a23800482a5d | note | — 20mm Class 3 Crushed Rock (Min 100mm Compacted Thickness)
02c51d2f-6a18-504f-860e-d47fcbf3f2a4 | note | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
c75658f1-cbc1-5c68-ac01-f11da7374838 | note | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
477b91e8-0cfe-5976-909f-951772149c10 | note | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
97a2324b-4d38-5407-ac1b-b62dc8ff6a27 | note | ○ Attach: Bedding Material Delivery Dockets
9f68d7cf-596f-5a49-8b7e-fd775c089522 | note | Method - Visual, Measure
94261dea-55c6-5f39-9844-25d2b8c88820 | note | Frequency - Each lot
c0f8fc5f-7dc7-5c1e-af99-6ec336c4b78c | note | Category - IP
dbbdd297-799f-5050-82b4-7afe8ef678a8 | note | Responsibility - SE/PE/SPE
789d0dfd-3396-5397-8e0f-1556dd429a04 | note | Verifying Documents - This ITP
d5e0b586-7f9a-5fbf-8db7-543f97fad880 | date | Date Completed:
105ca73a-d7bd-4d28-ba63-523ce3f518e9 | checkpoint | 5.4 - Compaction Testing
32a7889a-186f-5532-aef0-ee67cb1aa620 | note | Reference - 703.21
dc625e7e-736d-527b-83fd-8b7ca6c49ce4 | note | ○ 304.08 (a) & (b)
af110688-5f42-5ac0-9176-4c5ca5a7aa15 | note | ○ 304.11 (a)
8324ca0e-e676-5755-ba37-f4e5b331536b | note | ○ IDM SD 250
cb3e2385-1a5a-5dc1-9122-e4a97d883438 | note | ○ IDM SD 236
063ff10a-8b22-5289-9582-531c7241cee4 | note | ○ IDM SD 205
5d645444-66c9-5ff7-ad86-ae44a5441a26 | note | Acceptance Criteria - Compaction shall meet the following requirements:
50b522e6-2732-5cf2-b953-827cbefd778c | note | — Scale of Surface Level Measurement = Scale C
716b3d6f-e226-5097-b277-4efd7f668f8e | note | — Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test)
8218b975-628d-5d06-9cd8-e4c5951771a7 | note | — Mean Value of Density Ratio % (3 tests) not less than 100%
a93ec91e-e9da-5b36-8788-0c5871618988 | note | — Modified Maxmumum Dried Density (3 tests) not less than 97%
dc98e188-6fe6-5f7d-88b3-5b22785814d2 | note | ○ Attach: Mean Value of Density Ratio or Modified Maximum Dried Density
69743d81-5cd5-5f00-8c78-d6258e94a251 | note | Method - Document Review, Visual
e3bb1c7c-62ec-53dc-b58a-854aac840fe0 | note | Frequency - Where applicable, each lot
49efd976-362f-5e1f-8caf-8504add3ce7d | note | Category - IP
091db48a-1c05-5336-8f88-72d18cb1b133 | note | Responsibility - SE/PE/SPE
0d3b52ad-9f6d-5e33-937c-bb8327ff5289 | note | Verifying Documents - This ITP
05e39ba8-c0e6-5b7b-8bf5-a09f3ba2d181 | date | Date Completed:
27b31762-ed3b-48e1-855f-56f4d65b0f69 | checkpoint | 5.5 - Formwork Construction & Placement
c8acedec-5097-5912-bb1a-1b20e3040155 | note | Reference - IFC Drawings: MRP-120-C-SME-DRG-12-NPT-CPT-0012
74acfc57-6657-5dad-ae61-007c2d5b71db | note | ○ 703.12
d9cd6afc-ed58-532a-8528-0b28b4697eaf | note | Acceptance Criteria - Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete.
b7cfb45c-3d16-5584-8c1f-feecd929aa92 | note | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
58cfe98b-7de2-5b8f-9541-1286b2cc4e63 | note | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
23a3658f-c7e2-5698-9ea9-adb78c0b085c | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
75ae6ae4-919f-52cb-b847-47071e91e569 | note | Method - Visual, Measure
7324c31a-0dd7-5b0e-902c-31483f14a149 | note | Frequency - Each lot
5a06b00d-bb89-57f0-939d-dd2d2fa552e5 | note | Category - IP
133b15d4-7198-52d5-af40-b727333f1292 | note | Responsibility - SE/PE/SPE
c1c2309e-7927-55db-bc50-c83b15e74c92 | note | Verifying Documents - This ITP
2a7cee75-642b-5f72-9eba-1ea41555cf3e | date | Date Completed:
8eda80d4-8649-4063-9ebf-f947c617e9f8 | checkpoint | 5.6 - Construction Joints & Matching Existing Surfaces
5dfcac81-7815-5f24-830a-be117f93238a | note | Reference - IFC Drawings
362ea7c6-28f6-5402-b15a-08ff47cba1a7 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
9b91cf49-343b-5f18-937f-7b4e99fa6779 | note | — 703.24
753c37a7-24df-59d9-8ab6-c62c1d70d11f | note | ○ Relevant Council Standard Drawings
d93f1ba0-1a95-5e4f-bc62-0be0eb11616c | note | ○ Relevant Council drawings:
47738c57-60b8-5225-b8c6-a21aa3bef072 | note | — IDM SD 250
ada5ac54-4af3-56ef-af47-9f6dd07c11b6 | note | — IDM SD 236
f46ce00b-59b1-5e47-a1a6-2bd12a5525ee | note | — IDM SD 205
21cebdc3-e942-5fc3-9013-9a4a920a2f88 | note | Acceptance Criteria - Where applicable, construction joints shall be placed where the new construction ties into existing structures.
fa27517c-d0da-5045-96fe-21e734996e75 | note | ○ Consult the relevant Council Standard drawings for the joint detail, these may require:
69b5f6d2-a796-595b-9671-8ca3d9d8dfb7 | note | i. Concrete cutting of a shear-key
223864b5-ca86-5b52-85ca-1a698229636a | note | ii. Surface roughening
a12fb1f4-bba2-5fd7-8b62-91274961d2d2 | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
b45032d0-ca3f-5474-aab6-e78ad8a04ee2 | note | iv. Cutting a groove for sealant
b53214f9-b81a-5df0-9584-03d8590a8cdb | note | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
027545b0-e691-59d5-824e-f76c6fe62c46 | note | ○ Transitions between different profiles shall be made in accordance with the drawings.
4616f8df-aa7b-5eb3-b811-7adff169a674 | note | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
b517570b-bb24-5ea8-a9d7-cea2193e14e4 | note | Method - Visual, Measure
48270baa-efc5-539b-ae2c-d099571e37fd | note | Frequency - Where applicable, each lot
4b28b43c-5383-5255-89c3-c9fbebc628f2 | note | Category - IP
d574cae7-453a-55fe-af6d-22c3233000ee | note | Responsibility - SE/PE/SPE
022c11f7-420a-59fb-8145-c56b38edd8a8 | note | Verifying Documents - This ITP
8ed7855a-3212-53f1-9f75-f7b39786a3ec | date | Date Completed:
5d6d9b92-718d-4745-8043-edd772f60d0f | checkpoint | 5.7 - Isolation Joints
7ac5a57c-27af-5670-b8e6-9e87b27473e4 | note | Reference - IFC Drawings
b045ad23-08e6-5c0d-90bc-b1b8767a1913 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
2299ce11-1003-5e8f-8a5f-b396e602a17a | note | — 703.26 (c)
89094ebd-d06b-5819-a45b-cb0bb0565457 | note | ○ Relevant Council Standard Drawings
6195cd2d-3c9f-5267-9c05-98ccd5e08fe2 | note | — IDM SD 250
b728355f-cf8b-5aaf-9c75-9487bc424ea5 | note | — IDM SD 236
65ff3c7e-8fb1-5b1d-a736-39d8159e2c19 | note | — IDM SD 205
427384b6-c766-5ee8-b9c4-b3ff2c6fc4d3 | note | Acceptance Criteria - Where applicable, isolation joints shall be placed:
28fe6e13-69ae-5c5b-8b9e-64938d0ed43f | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
d39b375c-c52c-5979-bf34-41dc8f7fc9d3 | note | ii. at any location marked on the drawings
167e2f93-9b2a-5558-8bc5-ccf9a5880391 | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
284f49b6-51c7-5d2d-80a7-eb23006a826b | note | Method - Visual, Measure
878f24df-3e21-5e34-8788-f01a97c8629f | note | Frequency - Where applicable, each lot
7e4f9b93-75fa-5868-8dfc-c8ffb87c317e | note | Category - IP
e481473d-cc1a-5ea3-8df2-814fb6f4a11c | note | Responsibility - SE/PE/SPE
c2c9c114-2fa1-5c0f-91b0-821f0656c424 | note | Verifying Documents - This ITP
2bf0116a-712e-504e-b39c-3d2d97404a92 | date | Date Completed:
ee6149a7-212c-48ac-b083-d517c0598988 | checkpoint | 5.8 - Expansion Joints
2da2f4e4-826c-5a06-84a1-4584d6a6f118 | note | Reference - IFC Drawings
e7ae094f-d21d-5cbe-8917-78e5de87be99 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
4b14457e-0d09-59dd-9f88-02955bfb2599 | note | — 703.26 (a) (ii) & (b) (i)
ee62e3a6-de27-5225-8f07-f0d9311059ab | note | ○ Relevant Council Standard Drawings
d4bc075b-fbfa-554e-bb69-ce62c3c30d23 | note | — IDM SD 250
4979d237-bcb1-5543-a88d-02ded12e54a5 | note | — IDM SD 236
1b2c4b72-5723-577a-b736-835eea17b3f7 | note | — IDM SD 205
821a9b5a-3885-5948-bd79-880d5b6aab07 | note | Acceptance Criteria - Where applicable, expansion joints shall be placed:
11741bb7-3448-5fb7-a08e-5c1646f7e793 | note | i. on either side of vehicle crossings
c13b92bc-5e91-5221-a234-559fe409b7a6 | note | ii. at junctions with existing footpaths and shared use paths
b8fde9ff-cf01-512f-aeba-ff962f3b44d6 | note | iii. at junctions with bridges
fcd1ce76-be93-55a8-a870-e3ee2da220d4 | note | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
00e64f7c-b7af-56bc-8a81-13d74502d846 | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
1512e746-13e9-50de-8a8b-2ef9f17e925b | note | ○ Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
eff02cba-fda2-55fd-9f9f-bf28b5f1c8d1 | note | ○ Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
a0e40574-c4ed-5fa3-bd05-4489369d8a19 | note | Method - Visual, Measure
71d6e00b-e586-5b3a-bde4-f7f9babcbd79 | note | Frequency - Where applicable, each lot
6e035bdf-57d8-5c59-9eb9-b7d1f25c8246 | note | Category - IP
1c5841ab-8ac9-5a13-8da4-c15bcd3ca3bf | note | Responsibility - SE/PE/SPE
89eb804b-bf70-5a78-8ada-9b6c0bf6858e | note | Verifying Documents - This ITP
719590dc-f74e-58e3-aa8d-6b8f3174646d | date | Date Completed:
7210277b-8371-4e49-b1a8-8e89e258b2e6 | checkpoint | 5.9 - Reinforcement Placement
dc4585b3-d170-52e1-ba3f-89a1163b9ed9 | note | Reference - IFC Drawings
93e29170-ba1d-5f45-b634-4f19fcf4adef | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
aa041474-93c3-5f33-b8e1-ef06058a7635 | note | — 703.13
4e2ca409-dcd0-5225-ad8f-4428a76512e7 | note | ○ Relevant Council Standard Drawings
ba48bb13-19f1-505a-bd57-4b4639ea0435 | note | — IDM SD 250
0a973945-41e9-5249-8923-130d8fa8d020 | note | — IDM SD 236
2729adc8-0880-53fc-b645-1ac7b2e6d9ce | note | — IDM SD 205
2bd0f193-39c1-5d98-864b-8c0db7f93231 | note | Acceptance Criteria - The correct mesh type and location as shown on the IFC drawings.
d7be0f75-3d34-5a65-b8e5-29a8de753c06 | note | ○ Heavy Duty Vehicle Crossing (PA1):
4407d6dd-6f46-5d99-9a09-b8c43e20075f | note | — Two layers of SL82 Mesh (Top Cover Min 60mm)
8d8aaa69-d458-5cac-9805-c1c66da85863 | note | ○ Shared Use Path (F1):
0a350650-9011-5393-b5e6-53b5d7f77c61 | note | — SL82 Mesh Placed Centrally
1d7119a6-1cc0-57f0-9409-cf77ebfc1a16 | note | ○ Footpath (F2)
588c39ba-083f-58d0-9f6e-ed43ab4195cb | note | — SL72 Mesh (Min 50mm Cover to All Edges)
04753973-d273-529f-be6a-7f2e1d951e50 | note | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
0f7704b5-97a4-52a7-8e97-edd6af03a968 | note | ○ Any splice lengths achieve the minimum length and are in contact for this length.
efc666a0-5666-52f5-891e-013ab21ab707 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
c9e7777a-0ba2-5daa-9c4e-4f7233788655 | note | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
dfa7e829-5b78-5a4b-af5f-af96d78efb9c | note | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement.
93755c6b-d475-51c4-9016-88360b130fc4 | note | Method - Measure, Visual
d2afd590-d469-5b34-9afb-8eeaca9ef189 | note | Frequency - Each element
097fd99f-b03f-5d5c-b507-8d4336c36cf8 | note | Category - IP
6d63826a-f1c5-5e4a-b24b-fac4cee68644 | note | Responsibility - Foreman, SE/PE/SPE
ab5e5ee1-f7bf-59c9-a4b7-42b50d3c7c1e | note | Verifying Documents - This ITP
d364d9bd-60f9-578b-8d1f-2de7ac363784 | date | Date Completed:
c1ec3578-4b1f-47f2-83b4-98d60ecf4570 | checkpoint | 5.10 - Pre-pour Survey
dda77c5e-4591-514b-bfb3-4defc38d5b2d | note | Reference - IFC Drawings
73d28cfd-f8ed-5fb0-bfd3-796883898813 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
6fdd67c8-a150-57c1-8c42-a9634c9f9262 | note | — 703.15
d1855de5-6e8c-50f9-af74-89fe98bbc091 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
1565d85c-3e7a-58ba-b777-ef38cff0c457 | note | ○ Erected formwork and base layer within the tolerances below:
669636fb-3c42-58e0-a71d-7f7086c9fcca | note | — Departure from RL = ±10mm
a27555ac-f0d7-5cf1-b981-edba5141af40 | note | — Departure from alignment = ±10mm
2929fe68-b383-5f02-aa43-0a89f25951a2 | note | — Rate of change of deviation from RL or alignment = 10mm in 10m
8438a581-1df2-58c5-a03d-9ee24348a9fd | note | — Irregularities in alignment = 5mm in 3m
c10c4fe7-72cf-51f6-abab-51e4589f07ae | note | — Section dimensions = ±5mm
7f0d5c9b-41d3-5f62-a15b-f9d8049132be | note | — Section dimensions (less than 25mm) = ±3mm
127bf911-db91-5579-bc9d-842135b74c43 | note | — Width of pavement = -5mm, +15mm
1d23dcdf-b038-59a7-9309-1ec9c5c8707c | note | ○ Attach: Survey Report
aa2712ed-6ca1-5295-86f0-10c1a74b4027 | note | Method - Measure, Visual
f7d434d8-6449-51d6-9035-924f5d2aeb8a | note | Frequency - Each lot
a74d193e-1932-5e8f-ae19-0c1bb9509f3d | note | Category - HP*
0859d350-4003-5527-aa07-81ccc15b259a | note | Responsibility - Surveyor, SE/PE/SPE
0253f853-3f80-53d8-a105-e265f5eb8ee6 | note | Verifying Documents - This ITP
655bf98a-37c0-5868-b3f6-64d729d34e08 | date | Date Completed:
01c09d0a-8df7-45fd-a44f-1899662dd9bf | checkpoint | 5.11 - Pre-pour Inspection
ed814cae-221f-51ef-8077-e3d5ba809942 | note | Reference - Section 703.09, Section 703.21 Section 610.17a), b) & c)
3aee96cd-1e89-51a6-a3d3-039de42524a3 | note | Acceptance Criteria - Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
2ddbba63-666b-57e9-ab93-322d8ecf7181 | note | ○ Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
e52e8dc0-49a3-537b-b00c-0cead8fc7c3d | note | Method - Measure, Visual
1b12f4e1-8b9b-53f0-a2ca-095282b8c7c1 | note | Frequency - Each lot
3be67e0e-5c31-51e0-8999-ae1ef35e6060 | note | Category - HP*
1adc0953-5ab9-5e29-901e-3d2b12bbaf36 | note | Responsibility - SE/PE/SPE
2a514a18-1be4-56c5-a1bb-47e0cb8b3ab9 | note | Verifying Documents - This ITP
ec36c4a0-578f-5900-b505-0b7ea47fda7c | date | Date Completed:
106b20b6-380f-4bb8-8195-e0acdac20503 | checkpoint | 5.12 - Weather Conditions & Evaporation Limits
64059af9-de74-5270-bcca-a929e31f62f1 | note | Reference - 703.09, 610.17 (a - f) Table 610.171
d97ff5e7-ae56-5edc-9e21-d02315c0f487 | note | Acceptance Criteria - Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
4875c1b6-66d2-5ff3-bd51-93aca68a1252 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
afe9bfe2-6d6e-56cc-ad75-8937ccb758b3 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
678e3a2f-b88d-585f-a8c6-70df7090d775 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
a539226e-9023-5aaa-8e3c-98b60ea75d5a | note | ○ Record: Required information on the Concrete Pour Record.
2da371d6-8771-51b4-bb14-c1d3928cd0ff | note | Method - Measure, Visual
8443f6b4-f7cf-550a-992a-24fdd2435925 | note | Frequency - Each lot
45644eb3-cdf3-5883-a79d-e52606f5ccaa | note | Category - IP
897f4bc3-68a1-582f-a933-4b74fe3b05e2 | note | Responsibility - Foreman, SE/PE/SPE
50a090a7-339c-5899-9338-807bbaaae84a | note | Verifying Documents - This ITP
a5661be4-9a8b-511f-a657-9057d566a19d | date | Date Completed:
0f707b0d-40f9-4c27-867e-82321462c7b5 | checkpoint | 5.13 - Concrete Testing - Sampling Frequencies - Footpath, Industrial Driveway, Traffic Island
7f083d90-8462-5c5b-ab4c-db1262523490 | note | Reference - 703.11, 610.16 (b), AS 1379-2007 Cluse 6.2
203a2ecc-746d-5341-b2f4-eb32c403a359 | note | Acceptance Criteria - The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade
2fc021f6-f74f-5233-889f-9bae1b1db408 | note | ○ Correct quantity of cylinders manufactured per sample.
e4f06785-22d2-5eeb-a3f2-1eccd2991b3d | note | ○ Correct quantity of cylinders manufactured per sample.
17421e71-f540-5017-a5d1-396d6210dbb5 | note | ○ Record: Required information on the Concrete Pour Record.
aff39707-4324-5a25-817e-932c6e98de3c | note | Method - Test
cffe3b55-918d-5c1e-98d4-c45d91c04216 | note | Frequency - Each lot
e2a21433-bb25-50f4-abc6-b653553e5e4a | note | Category - IP
ddeeaa40-be1b-546e-9577-e5271400ba8d | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
eba01b0a-ca4a-51d8-8091-f353edbb129d | note | Verifying Documents - This ITP
0720fc72-734f-57bd-bd1a-4fd53512ce42 | date | Date Completed:
75de23d6-4470-49c1-953d-2510adb6ae68 | checkpoint | 5.14 - Concrete Testing - Slump
17dd4b7e-86ad-51bf-a03e-5579c51a4a4c | note | Reference - 703.11, 610.16 (c)
5ab2bf85-edcf-5791-807a-e7f9b403dca4 | note | Acceptance Criteria - Slump testing tolerances =
b78fa946-9c05-51a6-9002-e4fc84a278ae | note | <60mm = ±10mm
4ee8fb37-350a-50ff-b0ba-0f217264ce72 | note | ≥60mm to ≤80mm = ±15mm
851b6c16-825a-58a6-8653-c0b476143d13 | note | >80mm to ≤110mm = ±20mm
c44ab2e6-0a4a-52e1-a9e1-0dda70f3fdc5 | note | >110mm to ≤150mm = ±30mm
ea8917ef-66cf-5de1-94ab-6a3d507efd83 | note | >150mm = ±40mm
d5976835-b3d3-5f79-95f0-25186fe92beb | note | ○ Record: Required information on the Concrete Pour Record.
bb032942-6be7-5c42-ae0d-0e92ac52d55f | note | Method - Test
7cf259e4-13ec-52c5-a9c7-875f7c9bc0ac | note | Frequency - Each sample
6c94d8ca-e474-52fb-8e06-ce67c2693a23 | note | Category - IP
a7497985-6163-57f7-92c4-9e48363e145c | note | Responsibility - Concrete Tester
46936f8a-8532-5931-ac2e-74ba29bc070c | note | Verifying Documents - This ITP
2cfc416b-a1be-51b2-98e9-6622b3e6054d | date | Date Completed:
116584f7-1cfa-4cfb-945c-92106cfae85b | checkpoint | 5.15 - Placement & Compaction
8de465a2-edef-5551-b2be-218fd6a04b05 | note | Reference - 703.08
001af3fa-3bce-5672-bd46-afb9c9ae1a06 | note | Acceptance Criteria - All concrete batches are traceable.
e5e08fb3-3271-50d5-a97b-6616e0ae1b85 | note | ○ Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
78181ebb-b434-5082-b8b2-2585da82b137 | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
ad79081c-7b05-5932-966d-66ab88a8d4a2 | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
caace30f-6266-5b0e-8b6a-32e48b9a774d | note | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
69dbfaf9-2031-549a-9357-1b428c9d1e56 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
bb3d151c-6215-54f7-9442-5da943f58e69 | note | ○ Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
9943a7c9-ac77-58d9-98ac-37b6afb12114 | note | ○ Record: Required information on the Concrete Pour Record.
f2bcc7da-5cb2-594a-b8cc-bffac91f5ba8 | note | ○ Attach: Concrete Pour Record
625ea765-6d6d-5767-9325-5a3c7fe7477c | note | ○ Attach: Concrete Dockets
cba461cf-f7a1-51aa-bff0-612a8dfafb47 | note | Method - Visual
35713094-5975-58a2-af4f-444b51f52caa | note | Frequency - Each load
a5346427-9899-5dc9-9bb0-5c4494b7add5 | note | Category - SP
87a75593-86db-51ee-ae56-dd904cdeec7e | note | Responsibility - Foreman, SE/PE/SPE
c1277c21-cf66-5272-b47b-2c714fa028ea | note | Verifying Documents -
0acd3936-d60a-50af-b401-f6cb3e6f3e25 | date | Date Completed:
a7c5fe30-5ec2-4ef6-9bc0-7a3627196370 | checkpoint | 5.16 - Surface Finishes
0d395e63-7de3-5c63-9a65-70b68c91532b | note | Reference - IFC Drawings
b91fbaf6-4e59-5e2b-87b2-04eb1e805391 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
5d810729-e093-561d-ae6e-557d3c05ca7e | note | ○ Relevant Council Drawings
d5c7b10e-85b5-5179-a4bf-1f12a06de75a | note | — IDM SD 250
79099fe7-cc0b-548b-8701-faeeedf2a250 | note | — IDM SD 236
a4a482cc-6948-54fa-a871-7f81539bd2bf | note | — IDM SD 205
be9d104f-a6c4-5ff1-aab9-70fc8cceaa44 | note | — 703.25
e0fa3f96-bb9f-5e88-9698-1195eaf78996 | note | Acceptance Criteria - Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top. It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool.
1294120b-a0b1-5feb-aad8-10bb48ef6296 | note | ○ After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
f3bf106b-74d0-5299-9ef3-b41d404c7bed | note | ○ Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610.
5b37b35b-9d68-5dda-b918-6ca5e03b3d06 | note | ○ All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces
553a4fc0-0b94-5cff-8612-e312d15d1d80 | note | Method - Visual
a7bfdcb5-ba7d-5e25-85bb-c14c4f851633 | note | Frequency - Each lot
582b28a0-3f88-554d-95b7-ea95bd887761 | note | Category - IP
3295050e-07d1-504e-bf49-1978c9016dd9 | note | Responsibility - Foreman, SE/PE/SPE
02b9454f-5b42-518f-ac46-abadce0498b1 | note | Verifying Documents - This ITP
9e016af7-1e3c-5033-aa71-e8ea88e19673 | date | Date Completed:
d078a269-d0ee-4f1c-92b2-84dba599b978 | checkpoint | 5.17 - Crack-control Joints / Weaken Plane Joints
395e04ac-46fb-5617-b4c8-c5fb45cc84e2 | note | Reference - IFC Drawings
266c799e-8587-56b0-a3b3-7774e8740202 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
03961830-e9e4-5927-a549-36aab2922270 | note | ○ Relevant Council Drawings
8ac1b815-e310-5f78-bb2b-f9d4332b2078 | note | — IDM SD 250
084b800a-51f5-5534-aa11-5498e5f825be | note | — IDM SD 236
68c1f413-8c7f-5bc1-8145-a025fabf087a | note | — IDM SD 205
7243bc91-77d5-5d8b-a11c-9600305f7904 | note | — 703.26 (b) (ii)
ee4cda49-f6b6-577c-91b9-b23cbf0d0937 | note | Acceptance Criteria - Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
f79311c5-dde2-5418-a44a-6e20b2d938d9 | note | Method - Visual
29cfc5aa-5d17-55bb-af94-4e0c0db6155e | note | Frequency - Where applicable, each lot
78ff3feb-23ee-576e-bbd3-9df52960ca9c | note | Category - IP
8d98325f-0412-5ca9-8f23-e8b3b4fc2dfe | note | Responsibility - Foreman, SE/PE/SPE
976507c9-bd39-5f03-acd2-314ab24a717a | note | Verifying Documents - This ITP
3a8fcbd3-f31f-519a-8989-893287bf967c | date | Date Completed:
d977e315-686c-4fe0-a859-f1c0111843c7 | checkpoint | 5.18 - Curing
01cd18a7-3ba3-52c2-b947-0ec9aa969b0f | note | Reference - 703.1
b69d912e-cc16-54e2-b586-20049a8905fb | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
832a7862-34a4-5a74-83d7-eb5b13ed1409 | note | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
c2304ed3-97cd-59aa-9af7-fa32917bf764 | note | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
039809d3-96da-5dde-a25f-6d6db266b9dd | note | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
051dc7a7-ada1-5e89-a97f-25a23a11e05c | note | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
475a0072-534b-5125-acee-acacba7cc867 | note | Method - Visual
4ee0392d-478b-525d-b04b-b971538a00f9 | note | Frequency - Each lot
2136425d-7ed9-5ea8-bea6-4f52920a57de | note | Category - IP
fe0454b7-d2f3-55bb-bdea-0649769dd085 | note | Responsibility - Foreman, SE/PE/SPE
3fedd4d0-ef86-5758-876b-c4827e8469bc | note | Verifying Documents - This ITP
5986733d-69b6-5dcc-92ae-52673635caaf | date | Date Completed:
0f55904e-6f67-4d82-bd7a-6e653ce2d86b | section | 6. Post-construction Activities
2141ebfb-17fa-43a1-bca2-6439ab3e96b1 | checkpoint | 6.1 - Crack-control Joints / Weaken Plane Joints
5e29e77a-007f-5e56-b363-bfe240c0cefc | note | Reference - IFC Drawings
1c79a1b0-8929-5f51-b5e3-bf178605997f | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
d1a9cfcc-4534-5667-83e2-f5014abb895d | note | ○ Relevant Council Drawings
064eb192-0555-5690-b819-01322f151949 | note | — IDM SD 250
ddb81a6a-f910-5283-baec-4ee822f29ad9 | note | — IDM SD 236
011111d2-3efc-5ea8-8323-22fb2b58c83d | note | — IDM SD 205703.26 (b) (ii)
f436f206-f417-58b3-b386-de4f2f80e329 | note | Acceptance Criteria - Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
4575b321-0941-5bce-ab8b-d23ad1648e14 | note | <20°C = within 24 hours of finishing operations
60bb5a57-5c4a-5c34-a402-d2383e5dbd1c | note | ≥20°C - 35°C = within 4 hours of finishing operations
88410e01-de43-511f-b8d0-a10786af1f44 | note | Method - Visual
c6796d6d-f5a5-58c0-a199-6ca11b4738fc | note | Frequency - Where applicable, each lot
69fed1d0-a3aa-5bbc-802e-89a2cb296f1d | note | Category - IP
4ee0f2f8-41b9-5ddb-8bd8-d6b4542f6acd | note | Responsibility - Foreman, SE/PE/SPE
0c3b556c-4492-564c-abb0-2e3730cf80e0 | note | Verifying Documents - This ITP
b112d7d7-52ef-541b-a0e2-111c3c3eab49 | date | Date Completed:
85f0331d-643d-4628-885c-d5f88ffe74a6 | checkpoint | 6.2 - Protection of Newly Poured Concrete
48449f3d-414a-5bcd-b0d0-fa3f0754a0b3 | note | Reference - 703.27
3de0d4f0-07c5-5ea5-84fd-95c3c6114e31 | note | Acceptance Criteria - All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
25b264bb-a4ec-533c-8047-9aedc913c973 | note | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
586c6048-81de-55d5-9b87-4645f8984079 | note | Method - Visual
345d927f-51d5-518c-a318-60d1f2c6e54a | note | Frequency - Where applicable, each lot
521af398-1021-5d0b-865b-f1f8b51a8ea4 | note | Category - IP
34a8e3bc-23a3-50df-bb8e-0cf6a8d2a97d | note | Responsibility - Foreman, SE/PE/SPE
2f38a874-006b-551e-9a8c-56b95b88ebc6 | note | Verifying Documents - This ITP
87012ffa-36f5-5059-b94d-74f24a92969e | date | Date Completed:
0e7569e9-3f05-47ac-8e34-8c2c02274239 | checkpoint | 6.3 - Stripping Formwork
86acbcfa-f0dc-565a-af93-d9150e52449f | note | Reference - 703.12, AS3610 Table C2
5016f042-8831-53f2-afd2-51663dd48e7e | note | Acceptance Criteria - Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
c66e6e0d-ec59-5b36-91f0-1c5ebc3dc4d2 | note | i. 2 days for vertical formwork on external surfaces; and
b29992ed-b641-5f41-b366-91e6af736709 | note | ii. 1 day for vertical forms on permanently hidden surfaces
2288a16b-33ed-5d9c-ae98-6dcb900410e6 | note | Method - Visual
2111e6c7-5bae-5ecd-b4a9-1ecf27ea176a | note | Frequency - Each lot
675b8f77-9e7d-5242-be7c-45f2723f6fcd | note | Category - IP
1df21cf6-1c06-5cbb-a468-53a304171759 | note | Responsibility - Foreman, SE/PE/SPE
33db9bdf-6f88-5a07-9d69-7c0b7819a09a | note | Verifying Documents - This ITP
d6e9263e-bed6-512a-98b2-20550f46b834 | date | Date Completed:
4a063afc-8210-4ed9-ad87-a27fe87b171e | checkpoint | 6.4 - Backfilling & Pavement Restoration
3c1a5b71-e25a-5018-8b0d-893abe56c8dc | note | Reference - 703.29
8cfdcaad-88f8-5ae4-9746-c7f62c7fa7b9 | note | Acceptance Criteria - At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
b9624318-82b3-5dbb-a272-e38f7537932c | note | Method - Visual, Measure
28cab7f5-d65e-50ca-a3e7-9c70b271f70d | note | Frequency - Each lot
c0744259-830a-5e23-8e5d-dd64f16225bb | note | Category - IP
51ef797f-483d-5906-ad25-cecb80fe907f | note | Responsibility - Foreman, SE/PE/SPE
ca804119-e0c7-5f81-b1fd-541d5aaa8719 | note | Verifying Documents - This ITP
17aee34f-aa56-5b83-b9a4-6c2e81ce6478 | date | Date Completed:
6ed80ef8-9fca-44b7-aacc-d7bec4bae69f | checkpoint | 6.5 - Surface Inspection - Cracks
e07752cd-3d57-51c2-9fd2-45d9c7a0e2c0 | note | Reference - 703.3
dea6d92a-76dc-550d-b672-9a2dffeaec37 | note | Acceptance Criteria - No cracks greater than 0.2mm.
4c28b0bc-04a8-5ba2-a31f-6a843cfd3842 | note | ○ If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
f3beaec1-17b6-5d7d-8c2c-14c8be1bf632 | note | Method - Visual, Measure
314f559e-8db5-52c2-a606-500402f060fc | note | Frequency - Where applicable, each lot
d789c63a-e21e-5764-b142-44fb83cdd7cb | note | Category - IP
7823594a-ae84-56b7-84d8-d8b1cca75557 | note | Responsibility - SE/PE/SPE
d6bace36-8a29-5b3b-9156-96042c832191 | note | Verifying Documents - This ITP
0c963a69-b6fe-5aa7-bb96-2facaeb2a5db | date | Date Completed:
83d48e79-0193-48e0-a5b9-a5e6a54af037 | checkpoint | 6.6 - Surface Inspection - Surface Finish
ba39a52d-5afa-5f3d-88c0-ac079cda4311 | note | Reference - IFC Drawings
08032dc7-a2cc-588d-bef6-43011da2d387 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
26bd390d-d702-5d64-9e19-0fa623a88256 | note | ○ Relevant Council Drawings
aecd6425-46d3-529d-9c3f-0b45ea427feb | note | — IDM SD 250
e6dc0c07-d4a6-5aec-9683-ab4208767160 | note | — IDM SD 236
e3870dc8-b0a2-516d-b8e1-bcf8f3ccf01d | note | — IDM SD 205
879693f7-f387-538e-823c-cb2e41cf9860 | note | — 703.25
3cf5dd55-6837-59ee-9027-27d4f066f875 | note | — 703.10 (a)
7326f244-670b-5c82-b12e-e697ba316677 | note | — AS3610 Clause 3.2
7c4613ed-15a7-5aed-8cba-60504f4b2333 | note | Acceptance Criteria - After finishing, all work shall present a consistently neat appearance of uniform colour.
e9fcb3e7-5bfd-5705-aca6-d8a255c77cd9 | note | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
e4132a05-43e9-5c41-9825-129b285d0908 | note | ○ Class of finish:
2f55bedf-9922-5c5e-ad40-bf3d6cee8b6b | note | — Permanently hidden surfaces = Class 4
6e248fba-f7de-5562-8ff1-0b58c1000b2a | note | — All other surfaces = Class 3
bfa0b11e-0364-5c0d-9870-a4c73ad5cc23 | note | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
27366ddc-c95e-5c15-8252-96c41d1bff99 | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
5da815b1-4b88-513e-b17f-db13271b233f | note | Method - Visual
2d24a72b-6234-5d16-adda-2ff77e88aa73 | note | Frequency - Each lot
02cc790f-c1a6-5f4f-8119-579249da074e | note | Category - IP
e88791fb-7a4e-5815-9d4d-2481007f947e | note | Responsibility - SE/PE/SPE
38ef48e7-e3ec-555c-90f3-be4387db3452 | note | Verifying Documents - This ITP
3c893c9a-d962-5861-99da-50bf3dcc112d | date | Date Completed:
92d52c14-e80a-47c3-b001-6cc11ca25956 | checkpoint | 6.7 - Compressive Strength Test Results
134faccd-0dd8-578e-9291-eca73e75777b | note | Reference - IFC Drawings
248fe39c-9909-5e49-8c4c-4e8c3e4a8c07 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
9ca12349-0495-561c-8fd0-c629e4df6b68 | note | ○ Relevant Council Drawings
8faa8bfc-dcfe-5737-ba0b-6d6d1552aae1 | note | — 703.11 Table 703.111
2b5728bc-c925-5079-ac6f-65826c05a889 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
67214a5a-04a3-5b26-af65-7480cbae98ac | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
d333641a-7f71-5a4a-90ea-87191b34b965 | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
7fc72417-d07b-5a7e-99e1-806e29f5a0e3 | note | ○ Attach: Compressive Strength Test Results
ffd6f37b-d2ec-53d3-b507-3b649aa72a2d | note | Method - Document Review
93e8be78-376c-53c6-9387-70e5e82bd0cf | note | Frequency - Each cylinder
736eb35a-1779-576a-a702-cc34d2bd285c | note | Category - IP
8efc96f7-1411-5d2e-9241-84a638144632 | note | Responsibility - SE/PE/SPE
96f16f05-4ae1-5bad-9b02-509595e610d8 | note | Verifying Documents - This ITP
5b254200-9463-5791-a26f-62d811db00c1 | date | Date Completed:
a7536efa-69f2-4761-a486-10e3b57f1a80 | checkpoint | 6.8 - As-built Survey
aa20041f-82ed-5b85-b659-492054924398 | note | Reference - IFC Drawings
75fbaaed-39c3-5fad-8378-602fc7ebf625 | note | — MRP-120-C-SME-DRG-12-NPT-CPT-0012
d5c0eb49-45e8-50ff-b90b-5ce011e97909 | note | — 703.15
9ef5668f-1836-5117-a7fa-cc4fb0866861 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
ececf87a-d386-5d39-bb58-b058c5b03e8d | note | — Departure from RL = ±10mm
3c905fbb-37aa-5a41-8135-df7119d23e85 | note | — Departure from alignment = ±10mm
57ca0656-acd1-529b-a29e-f6ec2482577c | note | — Rate of change of deviation from RL or alignment = 10mm in 10m
2793c90c-0bab-50e0-a378-15a31438b8ff | note | — Irregularities in alignment = 5mm in 3m
169febaa-af7f-56ca-9f51-62588869e375 | note | — Section dimensions = ±5mm
835a0e20-1942-552c-b56b-dfb235d8e6f5 | note | — Section dimensions (less than 25mm) = ±3mm
dd4c5d5b-ae5d-582e-aee3-c871fab312b6 | note | — Width of pavement = -5mm, +15mm
d60fa11b-4063-56e5-95a3-fe2676168442 | note | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a cross fall between 1% and 3% towards the edges.
efcbb82f-aa99-5bf9-ab3f-c4970ad287b4 | note | ○ Attach: Survey As-builts / Survey Report
c47718e6-cbc0-5080-974a-a66f40ebf4ea | note | Method - Document Review
eedd817b-089d-5fad-a292-d22111f301ea | note | Frequency - Each lot
9d5a9c86-10d8-5486-80ca-08effe575228 | note | Category - IP
19f52d6d-c840-531c-8001-775f4f9011a1 | note | Responsibility - Surveyor, SE/PE/SPE
8b873771-d0a1-5b90-a86d-3f843ec92367 | note | Verifying Documents - This ITP
c2dff475-6267-5bc6-ad58-77af182b05e3 | date | Date Completed:
42e4a03a-97eb-4704-a694-d171a20f4359 | checkpoint | 6.9 - Non-conformance Report (NCR) Closure
c1e465e0-3bff-51f2-8076-d88495c01c0b | note | Reference - MRPA Quality Management Plan
f331935d-f2ee-5f9e-a27e-31c31e1f1aeb | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
bdd6654d-2938-5311-b0b7-7e011c273914 | note | Method - Document Review
d03b2b74-271c-508b-90e6-9ea23b0d9a6f | note | Frequency - Once, prior to closure of this lot / element / Work area
bb59af41-6e0b-5fda-9211-cc716a49766f | note | Category - HP*
d86f9455-272c-5c0c-8520-b334823b9ae3 | note | Responsibility - SE/PE/SPE
4d9a8c63-d79d-5d06-a19d-fb1672609a15 | note | Verifying Documents - This ITP
1d79146c-84e3-5c33-8a2a-4c39b5079104 | date | Date Completed:
739ec113-8b5f-48d3-a63c-ec0f69ace02d | checkpoint | Final Inspection
46b56c0d-4ac1-5543-8c0b-2d32b094756c | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
fbf8e859-f71a-50c1-8506-f1bda86315c0 | textbox | Name:
e7d383f3-a6c9-5136-95e3-776122529ffb | textbox | Position:
0c806a69-86d1-5c9e-8576-622bb6a36eea | textbox | Date Completed:
2fbdd468-8e0a-4bdb-958b-5b72b0635160 | signoff | Sign ITP
d8d5d221-ad02-4f05-bf7f-a93609b77666 | checklist | ITP-292-CIV-ADL-Kerb Channel (Supply and Install) Rev 0 | itp | ITP-292-CIV-ADL-Kerb Channel (Supply and Install)
41b24c6d-9dde-4b1a-8e60-282d8d984c54 | section | 1. Referenced Documentation
12e488ed-6015-49df-a776-6a4b04a50381 | checkpoint-no-value | Referenced Documentation
8a8bf20c-bbcc-599d-9dcb-d45b4651a597 | note | Document Title: ITP-292-CIV-ADL-Kerb and Channel (Supply and Install)
69b7bb75-5f83-5aaf-8c30-69d7c17c038c | note | ITP Description: ADL-Kerb and Channel (Supply and Install)
62decb48-5b18-5323-9670-a22d61d6b6fb | note | Discipline (e.g. CIV/STR/RAIL): 292-CIV
fc21044d-2bde-572f-a599-119975798bc7 | note | Revision Number: 0
13879a1f-e4fc-5781-861a-166a23a0d1e1 | note | Revision Date: 1/06/2025
56cf1d1b-0451-5f52-af2e-646b014ffa76 | note | ITP created by: Abhi Patil
e97df966-be1d-52f7-8884-e0a635ea896e | note | ITP approved for use by: Romualdo Magpantay
5ab6b9cb-90a0-51a7-80ad-3d2d4f878054 | note | 1.1 - Non Dependent
ec309afa-8063-57fd-8079-ca20c83b38e4 | note | Reference - VicRoads Section 703 (August 2021)
7d64d712-df38-58e0-a1f2-12a567249355 | note | ○ VR SD2001
5c2c609c-739a-50c6-b9a5-bb22247e29f8 | note | ○ VR SD2102
ab8fd2e2-4a9b-5651-b914-f5568d6709b1 | note | ○ AS 2876
ea08031e-b6d4-58ce-b91c-b1969bb907d5 | note | ○ AS1379
ace09f23-86ac-4169-afb3-dacddf43828d | section | 2. Preliminary - Materials
21db3fb3-4787-4603-baec-897a1b700046 | checkpoint | 2.2 - Mix design
c944270d-5ca5-5a4d-8391-2e9fc8b5405c | note | Reference - SD2001, AS1379 Section 703.05, 703.06, 703.07
ff4ab938-8e56-51a2-bc09-68885d691330 | note | Acceptance Criteria - Approved VR mix design to be used.
865aae95-5f9b-5467-b02e-8c3b0c3ce83b | note | ○ Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
e90d3ba6-7f1e-5244-9fe0-bb2bda5e6eb3 | note | ○ Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
31002104-0c0f-52ba-ac23-a544e16cdc8b | note | ○ Attach: TeamBinder Material Approval Ref No.
59441e1a-53bb-5a91-b39e-b45f86736ce4 | note | Method - Verify, Document Review
62a73c0e-a42b-5b63-9605-0160c5df881e | note | Frequency - Prior to commencing any activity
82cbbf03-5cbb-5b6d-b70d-253c5ce113bf | note | Category - HP
cff8a1cb-2a99-5889-9cee-b3000d7329ea | note | Responsibility - Nominated Authority
7dd7c27b-0e73-5ab3-8aa4-91e4aaba82ca | note | Verifying Documents - Conqa HP Release
4238d639-1dc7-595d-b9be-0f8552840c05 | date | Date Completed:
0e2f4caa-3b83-4436-8541-e53e06336d83 | signoff | AUTHORITY HOLDPOINT
b0573f9a-6181-413b-a9ca-f8dca0130044 | checkpoint | 2.3 - Bedding Material
a9b27c6e-de44-59e4-a296-ba82bd756838 | note | Reference - Section 703.21 IFC Drawings
5650eb93-c5ee-5848-95fb-3188e4762b05 | note | Acceptance Criteria - Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
cafa0e59-4f00-5553-a04d-ed15a5d5cb4c | note | ○ Attach: TeamBinder Material Approval Ref No.
24d525bd-881d-5538-8999-5cd9d3c0bfad | note | Method - Verify, Document Review
58a8c329-9597-539c-800b-a01039c76628 | note | Frequency - Prior to commencing any activity
fb0b892e-348d-5aa7-9665-2e43cee206e2 | note | Category - HP
6446f4ca-2c44-598b-a10a-cc395b98d6dc | note | Responsibility - Nominated Authority
13d9698f-fac1-562a-ae74-fda593137347 | note | Verifying Documents - Conqa HP Release
0c23ca89-e507-50ac-b344-68e4149bef7f | date | Date Completed:
a79d05be-71b5-442a-bfb4-f83c722e7ae9 | signoff | AUTHORITY HOLDPOINT
a2af8dc5-2048-46e9-81bc-8cec6f85abcb | checkpoint | 2.4 - Curing Compound
023929ba-f007-57db-b24a-6a8536e8b1ee | note | Reference - Section 703.10
260fd231-a442-56f2-ba9c-ec6b86e8724c | note | Acceptance Criteria - Curing compound shall comply with AS3799
210c0a14-020e-590d-9c5f-7e17a1a1998b | note | ○ Attach: TeamBinder Material Approval Ref No.
a3149643-3e27-58e9-a64f-a5cfa239c926 | note | Method - Verify
632da26d-e25a-5d1d-888b-e9b8749139b3 | note | Frequency - Prior to commencing any activity
2af01229-9699-5360-bae3-ba53c1a4fd06 | note | Category - HP
ffed3b0f-b99f-5c2a-a94d-9514bf89bdef | note | Responsibility - Nominated Authority
c2a0b249-024a-5064-a2ee-044b2225b515 | note | Verifying Documents - Conqa HP Release
c52e4b5d-dbd4-5e99-b3fa-e4d6ea829879 | date | Date Completed:
13720e50-dee3-4dd2-8480-5f09305631c8 | signoff | AUTHORITY HOLDPOINT
fed0ab85-2e20-4857-bba8-fed5a5680cb7 | section | 3. Preliminary - Documentation
654e5434-b081-4299-a512-1fcd6e438f3d | checkpoint | 3.1 - Check for correct documentation
2bab44ca-0a18-5aac-884f-0cb7017bb389 | note | Reference - IFC Drawings
469b0a68-1704-5283-9bd1-79e9a6681361 | note | Acceptance Criteria - Ensure that all employee and sub contractors are:
37f5a406-3440-564b-8fb6-c43779cca676 | note | — Using the correct and complete set of drawings
98569bf5-0306-5a75-986e-ae5e0528ab72 | note | — All drawings are the latest version
d87967aa-7571-57f1-b2d3-ede885b6e4b1 | note | Method - Visual inspection
f6135d86-9fc2-5b20-9f5b-35ea8f5e96e7 | note | Frequency - Prior to commencing any activity
921b6cde-73fe-5051-80e3-1c5ad8e665b4 | note | Category - HP*
e955ee35-6656-5f51-bb4e-3dda291f38e3 | note | Responsibility - SE/Site Supervisor
97358bb4-169d-5aa3-80c8-59a862036c07 | note | Verifying Documents - ITP Signed
e2e5a311-b446-5140-88a9-2b58f0116b89 | date | Date Completed:
49086ba4-4adb-4740-a0e6-03c23bcb1f61 | section | 4. Pre-construction / Pre-installation Activities
22e62f9a-d142-4d24-8669-e4d80352cdec | checkpoint | 4.1 - Setting out
12784118-9e02-55b1-a0e4-8258eebb33fc | note | Reference - Section 703.17 IFC Drawings
9cab28a6-edac-54f5-89aa-57e1395b2a5e | note | Acceptance Criteria - Set out work in accordance with IFC Drawings.
12eaee67-2a01-5e36-a4c1-ea42693fe8d7 | note | ○ The superintendent will review and confirm set out.
8f821c52-cd7f-51f5-8f86-9a4c60a34d87 | note | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
caeef032-f59c-53b3-9d06-f1044150007b | note | ○ Attach: Lot Map-Marked up drawing to indicate the location of the Lot
43755f09-fd38-576d-9aa6-e2e3cdbc138e | note | Method - Verify
a2620d8e-6835-52d6-ac50-6aa08f698492 | note | Frequency - Prior to start
9bbffab4-c61d-5bdb-bffc-75d95c869d42 | note | Category - HP
44c93a18-a154-583d-bfaf-63061e11f1ab | note | Responsibility - Surveyor/Nominated Authority
ca61e474-efb8-5d01-a060-6e0d85ac9993 | note | Verifying Documents - Conqa HP Release
adb6515d-0650-5bcc-8f46-9dd543d348cc | date | Date Completed:
a5b654f1-78c0-4dd0-87e8-78c71c1303bd | signoff | AUTHORITY HOLDPOINT
9cccadb9-62ec-4d80-ac2d-69516d880977 | checkpoint | 4.2 - Temporary drainage provisions
ce5772f5-a641-5774-9a40-4f9c57439e55 | note | Reference - Section 703.18 CEMP
846ece53-ce5e-5a1d-9a5a-a891274772ad | note | Acceptance Criteria - If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
d25613f2-fa4c-5423-afa9-a9335f340e60 | note | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
ce9369a1-976c-5c92-9226-b53f902aac61 | note | ○ Attach: relevant written approval from relevant stakeholder.
350fa3cc-c21e-5a00-9f64-e69dcd22e5fc | note | Method - Visual inspection, Document Review
ba055a70-18e5-5599-b637-2b81083d6bdb | note | Frequency - Prior to start (where required)
f0da8d8f-cdc6-5f0a-89ae-2c9c921aa30d | note | Category - HP*
95c140bd-4b57-5ab7-8717-d8d2bc944f58 | note | Responsibility - SE/PE/Site Supervisor
f235d5ae-f135-5997-b4eb-b49550a2acad | note | Verifying Documents - ITP Signed
f4dc087d-62ba-5f79-9837-f27a28c2d57a | date | Date Completed:
be2e817e-45ce-470f-9afc-de803113f62c | section | 5. Construction / Installation Activities
cddc9843-6b86-4763-937a-9c8fdb4cefb5 | checkpoint | 5.1 - Bedding
ad5262dd-28aa-5022-b682-634847396fca | note | Reference - Section 703.21
59064a9c-66c1-5e35-abb3-e624a8b9e054 | note | Acceptance Criteria - Bedding to be compacted to a thickness of not less than 100mm.
a0756f07-1943-58e6-ad39-394b4c10eaeb | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
85c8a42f-6065-566b-8a21-8761b07784d1 | note | Method - Visual inspection
ee225932-6f7a-5b25-9402-3201f2f567bd | note | Frequency - Each lot
94d9babb-4f70-5932-b17c-af536191a9cc | note | Category - WP
d60c4e83-362a-531e-b447-2eb846bfe53c | note | Responsibility - SE/Site Supervisor
3c1eb766-5767-5d17-af4d-02311175cf3e | note | Verifying Documents - ITP Signed
200c21c4-2438-5d66-828f-7a4a0fa4eb36 | date | Date Completed:
27fca514-d8bc-4a49-bf6c-e6290e2dec26 | checkpoint | 5.2 - Formwork
ab8fb6b3-bba0-5594-b827-b309d187f7b2 | note | Reference - Section 703.12 AS3610
86bcae6c-c277-5099-b7dc-73541ae0e116 | note | Acceptance Criteria - Joints in formwork shall be constructed such that loss of mortar is prevented.
1b601e8b-751c-58f0-bad7-33d8742db250 | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
8b3b72d9-acac-5ebd-a00a-af490d6764b9 | note | Method - Visual inspection
889ae981-64d8-5ff1-95a2-bcc5e5407e2b | note | Frequency - Each lot
fd450281-6c03-5029-82d0-280d8283b8df | note | Category - WP
267161cb-91e9-5675-a46b-09e82d91717f | note | Responsibility - SE/Site Supervisor
c315d35b-ac83-5fae-a89a-45ad97537b5f | note | Verifying Documents - ITP Signed
6784e982-f6c5-5133-b450-1c592e0ce825 | date | Date Completed:
f1e70e86-f0eb-456b-ad41-98ddddf79bb1 | checkpoint | 5.3 - Pre Pour Check
6ffc18f8-651e-5dd5-866e-8afd938cb77e | note | Reference - Section 703.09, Section 703.2, Section 610.17 (a,b,c)
1e2a55eb-373d-5f81-9a8f-9bef61b2013f | note | Acceptance Criteria - Bedding shall be moist but shall have no free water on the surface .
5b72ac75-b971-5d91-8e5e-bd28445bca3f | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
8ff42e4f-83ff-56a4-80c3-3994917594b1 | note | ○ Attach: Pre-pour Inspection Record
25f52f5d-141f-5890-a055-359ebf2d6f4f | note | Method - Verify
0762638f-98b4-5e26-bbe5-9ad53b291712 | note | Frequency - Each lot
b9b80c20-0def-5df6-ae9c-110a1e149ad2 | note | Category - HP*
f56c6eea-3369-5b88-9ffc-451478ed8150 | note | Responsibility - SE/Nominated Authority
0fc02bdb-fa0c-527c-8f5b-d798c3dd929f | note | Verifying Documents - ITP Signed
a6e73743-f455-54bd-9748-a723e568755b | date | Date Completed:
aef4e000-4490-40b6-9a84-d2874e21b966 | checkpoint | 5.4 - Concrete placement
1fea84b6-2083-5b94-8cb4-c980c91d0710 | note | Reference - Section 703.08, Section 703.23
b4c38adc-5a09-5962-bce2-9d9fca128f73 | note | Acceptance Criteria - Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
1b95fe29-0f4a-5a12-9993-a991b58997bc | note | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
b249b788-01cc-5f95-939a-043ff4795b64 | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
bd72e0d3-7843-5316-ad3e-36ccb77521bf | note | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
36b90355-6bad-5166-a9a4-ffb661ab3def | note | ○ Attach: Concrete Pour Records
85facca1-4d50-50cc-9574-974e23d196ab | note | Method - Site inspection
fad3433f-f1b1-509b-b4a5-755a4859370e | note | Frequency - Each lot
023b8467-7bc3-5b0e-b544-83f932920e8c | note | Category - IP
01deebd4-a3e8-598f-9e3d-2d9c6be7eee6 | note | Responsibility - SE
c55ac425-1b43-5f65-aa61-2d398026a4a9 | note | Verifying Documents - ITP Signed
383f8b23-dc4c-5cd2-84eb-f1657c2ebe00 | date | Date Completed:
9110fdc5-f469-48df-9c21-2bf0d95f4ee6 | checkpoint | 5.5 - Transitions
bf3e3101-58ce-5152-8acf-52e2c73c3fb8 | note | Reference - Section 703.24
0e0dca17-1a1a-5e92-99eb-c2247698930a | note | Acceptance Criteria - Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
eade9436-351a-5a2d-8353-8d90310e6e08 | note | Method - Site inspection
1ce3a9f7-36cf-5c3d-a43f-18b8c1d44677 | note | Frequency - Each lot
8879cda7-b109-5d1b-b0f8-303eef3b38dc | note | Category - IP
1dbc481d-d489-53b0-ac70-727ac4e57343 | note | Responsibility - SE
fb6217c1-f724-5c09-beab-9b3c70f24809 | note | Verifying Documents - ITP Signed
6521960e-31c1-5068-b509-1cf1c4e70eb0 | date | Date Completed:
e49aa3de-64f1-4f3d-bc53-aef7cdd89bbd | checkpoint | 5.6 - Surface Finish
0f0e9b32-fc93-551e-ad6a-7d57bc26d03e | note | Reference - Section 703.25
2deb9319-eec6-5bc6-b140-e834148e46a9 | note | Acceptance Criteria - All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
33fba777-3029-5c6a-92c2-4af22eac91a7 | note | ○ Renderings shall be applied within 30 minutes of extrusion.
78488366-73b6-5bbc-a853-8d61b8a4d4bc | note | ○ Concrete to have a neat appearance and uniform colour.
73fac3b3-15d1-51a3-ae64-8d313967d601 | note | ○ Class 3 finish required for external surfaces.
35b1bf50-554a-5923-8bab-cc1b9a40fb82 | note | ○ Class 4 finish required for permanently hidden surfaces.
487a5d41-6637-59a6-a117-0b6c12b86ca2 | note | Method - Visual inspection
f6cc12a3-eed9-56b7-8f13-ac80f0aff223 | note | Frequency - Each lot
c43cdcc8-168b-5f0c-b9d8-64f19ffcddd5 | note | Category - IP
24cac554-4543-5dac-a800-fad86eb5d636 | note | Responsibility - SE/ Site Supervisor
895ce5eb-da62-5232-acc5-6927e5008987 | note | Verifying Documents - ITP Signed
2afba734-7a8f-59cc-8efb-58d9a458e87b | date | Date Completed:
ce0443fe-cf18-4c82-8cc8-60b116250e10 | checkpoint | 5.7 - Formwork Stripping
679ff832-6e30-55df-bf0c-4c2a82f44c14 | note | Reference - Section 703.12 AS3610
f62351c7-691e-56f7-9e2a-6b3aadad031b | note | Acceptance Criteria - Formwork shall not be stripped before the minimum time of:
5c2d28be-e356-53e8-ad45-e39faa12c798 | note | — External faces 2 days
96c9a77a-e980-5c60-ad98-977a5208333c | note | — Permanently hidden faces 1 day
2fb6a320-4f31-51b9-9a64-25cff9f7bd4a | note | Method - Visual inspection
546340b2-f521-5d40-a7ad-2cacdbc1d774 | note | Frequency - Each lot
5f043000-2de3-5977-b780-af3a750ef4de | note | Category - HP*
f64eccca-0701-551c-8fcf-3b55b897aa7b | note | Responsibility - SE/ Site Supervisor
c7300dd4-1c5f-5768-a53c-c9e2c07590b8 | note | Verifying Documents - ITP Signed
e4af147b-60a0-5348-9f74-173a6229473c | date | Date Completed:
02921d77-f346-4f34-9402-407c3d78f8aa | checkpoint | 5.8 - Tolerance
28c7e97e-628c-5c5c-887a-9f83472c8427 | note | Reference - Section 703.15
45ea9153-4cf1-5649-96cd-b8fe56067c65 | note | Acceptance Criteria - Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
8f091b68-0291-55f6-8161-d9d2fa60a218 | note | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
2f17671c-4228-52b4-9f21-dd562033f288 | note | ○ Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
bf51c627-fe72-58ac-b0c0-3cb9460cfd5f | note | ○ Attach: Post-pour Inspection Records
2cfe95fb-9894-55e5-803f-6d783ec2ce9f | note | Method - Verify
58e04620-e7d2-58ee-ae28-b9c73bd4eb09 | note | Frequency - Each lot
1695f99d-f174-5c69-824f-dd727317e9b3 | note | Category - IP
e52847e8-efad-5236-af87-1a8e330ba26f | note | Responsibility - SE/Surveyor
36737fbb-ca7d-5dd7-a892-b728b46b237d | note | Verifying Documents - ITP Signed
e69432de-ddd1-52a5-a7c6-a0768f277ba2 | date | Date Completed:
9d811b6e-d2fc-432c-b418-3c664b9c6045 | checkpoint | 5.9 - Curing
49f2353c-ecf9-5467-bf33-3160274a4fec | note | Reference - Section 703.10
e583a81d-53e5-5eda-a2a0-abcd78f73376 | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
e250a720-aa17-5fe1-929b-74471408445c | note | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete
066c085d-c829-5a66-9f86-31b4bf57cd3d | note | Method - Visual inspection
57fc17cb-9f42-504f-9d2b-a034abbd9225 | note | Frequency - Each lot
aac37e40-8b8b-5a59-bcf3-e9ad1178e75a | note | Category - IP
799f5f2f-20d7-51c8-b08a-a9de985649ed | note | Responsibility - SE/Site Supervisor
10cdfa7d-4595-5cd3-9e99-5a92dd07b9a9 | note | Verifying Documents - ITP Signed
1f83296e-f95c-56ea-bc1d-f03cfbb51e16 | date | Date Completed:
3c99b5d1-7d67-4062-a7e7-91e3b659e531 | checkpoint | 5.10 - Joints
e000539f-cc53-5f79-8d54-61591072da78 | note | Reference - Section 703.26
8cda6387-95d9-5215-a552-3d361acd9af3 | note | Acceptance Criteria - Transverse joints constructed at intervals not exceeding 2.5m.
8b73aae7-c2fe-5074-a3b3-159d7d64458a | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
5517c01d-7816-5e0f-bce4-29f1f0058ead | note | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
816ae395-dbc9-5991-bb8a-b82b4e3554b6 | note | Method - Verify
9afb2d1c-1363-5952-83bd-0d2843e76690 | note | Frequency - Each joint
fce917c5-013a-5537-856e-007b0d37571c | note | Category - IP
43e1d16a-4230-5d4d-b6b9-93b131f0ad6a | note | Responsibility - SE / Site Supervisor
64baea37-494f-5fde-844d-78752fa63775 | note | Verifying Documents - ITP Signed
f56e85af-d4e5-5a42-9f80-dca880c45201 | date | Date Completed:
d5bf06f6-a22f-4088-9b4e-cbc6a9f4de4d | checkpoint | 5.11 - Protection of Concrete
dd73873b-85f1-58bb-87bd-c4d215c026d4 | note | Reference - Section 703.27
adf8a517-cee5-56e1-880a-28958f0ba8e0 | note | Acceptance Criteria - All concrete shall be protected from damage from early loading.
dc864bab-002e-53d9-be14-c459b944b94c | note | Method - Visual inspection
143b3bd0-0bf5-5e8e-953c-192eeb112c79 | note | Frequency - Each lot
4b03d0e3-49ab-557a-8208-cc52d2b6875e | note | Category - IP
63311496-2eaa-5710-bda8-4f2b4f502755 | note | Responsibility - SE
810327f4-a671-57a6-a92b-3b7fa0c1cbf3 | note | Verifying Documents - ITP Signed
1ac94a1b-a8d7-5cb7-9812-8f013c10c2f9 | date | Date Completed:
0cb9269d-d346-4eb8-8920-4a75e10e113f | checkpoint | 5.12 - Bus Stop Kerb Height
47b0b6e8-3656-552b-ac0d-b58fd60f015b | note | Reference - DoT Handover Process
666a8cf4-c59b-533d-a36a-f75031fe06c8 | note | Acceptance Criteria - Height of the Bus Stop Barrier Kerb to be between 150mm and 180mm.
61cbe7d7-6ebd-546d-94bc-b542e6577ccb | note | ○ Note: Capture this in pre-pour checks i.e. formwork and post-pour checks
24210ff6-fc18-58b0-a6c7-d31d23cb28be | note | Method - Visual Inspection
0170d329-cd6e-58f9-9c26-58bae9a974ba | note | Frequency - Each lot
1ba353b1-5ed0-5b24-a255-4a08a1b7b698 | note | Category - HP*
92a9f12a-84c8-57d6-a7da-82bb49a85258 | note | Responsibility - SE
30250e55-bc25-5911-9c13-4018d87b856d | note | Verifying Documents - ITP Signed
8416ea5d-aed9-59b9-a701-98e481750611 | date | Date Completed:
c38c2658-336c-4ef5-82db-355ba6fa9986 | section | 6. Post-construction / Post-installation Activities
ec2d37e4-2ccd-4ddb-8b2a-877bd96e6f6d | checkpoint | 6.1 - Backfilling
be1c90d5-885f-5ee7-9e43-c9001cee4572 | note | Reference - Section 703.29
dbfdbefe-7075-5785-a54b-ac428dd48f7a | note | Acceptance Criteria - No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
d4339554-7fa1-5c30-8ce1-e5ac63b6dc60 | note | Method - Verify
3a15009b-c74a-5de3-bd8b-a91b96945727 | note | Frequency - Each lot
2daae748-b6a9-5092-a823-04cacb63986d | note | Category - IP
21bf1e5d-8e8d-5f9b-b64e-f4430f55f642 | note | Responsibility - SE
f4aeb131-9fbc-5fb5-8210-dec1de171088 | note | Verifying Documents - ITP Signed
500e7670-fc4a-5b49-8f35-4faf811b62b4 | date | Date Completed:
3e2fea04-863b-4d1b-953c-43263c793c8a | checkpoint | 6.2 - Cracking of Concrete
b82b02d7-2e65-5e6a-a2e1-6b5c859ccdae | note | Reference - Section 703.30
984cfbe0-d985-585a-b22d-2ff3fa7dfec3 | note | Acceptance Criteria - The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
54faa997-5ba1-5b88-94e4-693e0befb029 | note | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
add575f8-2c2e-541e-a700-bac48ce85b8b | note | ○ Attach: Pot-pour Inspection Record
b464952d-dfb6-5e58-9da3-b59537bb1bac | note | Method - Visual inspection
90134277-19f3-5517-addf-f75ea4180131 | note | Frequency - Each lot
6ab5337f-b356-566b-ab38-b288a1117d3b | note | Category - IP
ea9211ee-2471-5ef5-9aea-edd5817b8782 | note | Responsibility - SE
7716ed08-c8bc-5bfc-98d1-6d3bf9ac34d1 | note | Verifying Documents - ITP Signed
a4ed1f7b-0b6d-569a-aaa0-43b1ed3a876d | date | Date Completed:
c2dcc45f-9290-41ad-912c-2a86206c6b3c | checkpoint | 6.3 - Survey Conformance
0e66c7c2-1fb5-5a21-9ef1-4eda9e2e65c1 | note | Reference - Section 703.15
dc98f890-ac7d-59e1-9b9c-9a0bb58fea94 | note | Acceptance Criteria - Survey to as built the works and to confirm the works are within the specified tolerances.
71afe6f8-0d6a-548c-bf3a-ece865885aa5 | note | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
de757ed0-fbae-5e6f-9390-a84f9b38b681 | note | Method - Document Review
d43ee5b2-938f-5883-b08e-718b19c3eedc | note | Frequency - Completion of each lot
26112cf0-1400-5712-9baa-85bcdc757c4f | note | Category - WP
90e16df2-c2b5-5643-a52f-cb1c2508a316 | note | Responsibility - Project Engineer/ Surveyor
45387c71-4eec-5152-9cc6-0071165b6827 | note | Verifying Documents - As-built survey records
6a3bafed-6193-5f58-b1da-60afd614f1af | date | Date Completed:
371cd95c-3f4d-4d46-ad1d-e1010b36a19c | checkpoint | 6.4 - Non-conSupervisorce Report (NCR) Closure
1cc47107-d3d0-5f42-99b7-e26f8a643efe | note | Reference - MRPA Quality Management Plan
202fddeb-466d-5bb8-a6b8-37d4a1a56219 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
0349c763-0603-5ba1-9120-2b1a5651a5c2 | note | Method - Document Review
b6c466f2-ad03-5a1f-8649-4b8633171a66 | note | Frequency - Once, prior to closure of this lot / element / Work area
08c35714-f026-512b-91ab-c4e4d406904e | note | Category - HP*
d6613723-f111-5d27-a117-6107e4f35143 | note | Responsibility - SE/PE/SPE
d055903f-19bf-5f6b-ab26-d12fae1a1b79 | note | Verifying Documents - This ITP
82f4db77-4235-53bc-a088-fc6905383712 | date | Date Completed:
27942f24-5ac8-4390-bd8a-4dea3316600f | checkpoint | Final Inspection
df6b5651-b058-5ba5-bb6b-8818ee247e0a | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
771158d3-d103-5a04-8599-4e0f17eb8088 | textbox | Name:
0e2dd523-8b91-5f5c-9a82-4cfaf8d09ada | textbox | Position:
dbce6ec0-3d6f-5711-9649-3d587b4a5f85 | textbox | Date Completed:
9276009f-80e9-44af-a150-943439f7b87d | signoff | Sign ITP
8f1e39a5-81ab-4a4d-a00a-937250d24fd7 | checklist | ITP-295-CIV-MSS-Conduit & Pits-Rail (Supply & Install) Rev 0 | itp | ITP-295-CIV-MSS-Conduit & Pits-Rail (Supply & Install)
b910fed3-0553-4d36-af4c-e000382da8b9 | section | 1. Referenced Documentation
c2a2bfb4-9781-4d03-8667-70b9f61c22ad | checkpoint-no-value | Referenced Documentation
82898b00-bc44-593f-8f63-c70138cc3d58 | note | Document Title: ITP-295-CIV-MSS-Conduit & Pits-Rail (Supply & Install)
36221661-a04c-5955-b04e-a53dee1c821c | note | ITP Description: Conduit & Pits - Rail (Supply and Install)
32f1fbb8-1335-5486-8d29-a6a458fe548e | note | Discipline (e.g. CIV/STR/RAIL): CIV
f22752c7-50ae-5c4f-85f0-7c8de77b1878 | note | Revision Number: 0
0961167b-5d05-5897-ac3b-894b23a7a2e3 | note | Revision Date: 24/07/2025
8c48ee3b-a88b-5777-8eb9-4b659fa01af7 | note | ITP created by: O'BRIEN, Dan
974de8de-41f5-5efa-b068-a8add583df69 | note | ITP approved for use by: Romualdo Magpantay
77e367a7-e64c-50f7-8614-e1e47d689a0f | note | 1.1 - Non Dependent
d590d99f-3111-5f46-aa4a-832118674524 | note | Reference - IFC Drawings
8fda9d78-402f-5a19-adfb-827b0bc77533 | note | ○ L1-CHE-STD-043 (VRIOGS 012.2.1)
7a695439-8620-5396-948f-eb7b240fd5ae | note | ○ L1-CHE-SPE-0703
ac9429a8-9d9e-51dc-8400-a60aa7cbd358 | note | ○ Australian Standards
61a0873a-8302-53fc-b158-17b9cdb0fe0e | note | ○ MRPA Standards
acb16382-01e5-41be-a5d6-ead06cf2b498 | section | 2. Preliminaries - Materials
ec5b5360-4598-42d6-811d-79207736c517 | checkpoint | 2.1 - Conduits
bce7ca92-51cf-5657-a6fa-8bb933583351 | note | Reference - HV Conduit: AS 2053
76c2a0ba-7d3e-58f6-9ff2-438424027687 | note | ○ HV Conduit (boring): AS 4130
f4463a89-e969-58eb-be66-be82e1af8248 | note | ○ Comms Conduit: AS/ACIF S008:2006
7266746f-9b46-53df-bb52-de245655b753 | note | ○ LV Conduit: AS/NZS 3000 - 2000.
a90c784f-a741-57c6-a50f-e015c691e873 | note | ○ L1-CHE-STD-043
89ed8a91-1473-542c-9154-ab57ec68e126 | note | ○ L1-CHE-SPE-070
66f83312-c59d-5073-8156-cecc2c2d8674 | note | Acceptance Criteria - LV & Signalling: 100Ø (114mm OD), orange electrical heavy duty 5.9mm wall thickness
076bb1f5-af23-5d6e-90b9-9c75cabe5f3b | note | ○ LV & COMMS CONDUITS TO HAVE A MIN 600mm BENDING RADIUS
b78e03ba-50f6-5c42-aa05-000c7946439d | note | ○ Inspect materials upon delivery and attached delivery dockets.
e01baed0-3cd4-5d2e-a57b-46405a03d4e3 | note | Method - Visual, Document Review
8e8aa226-ac95-502a-b2cc-f2c0188c0ad5 | note | Frequency - Each Material Type, Each Delivery
66f12ebf-a3fd-5879-a46e-c616d55881fd | note | Category - IP
2531e596-e75b-5ffd-aef0-f7edfbd10524 | note | Responsibility - SE/PE
d384b5c0-9b2c-527f-a221-97285d92ca9e | note | Verifying Documents - Attach Material Conformance Certs
9289b9af-d544-59ad-9a2a-415279d5b25e | note | ○ Attach delivery dockets
91971d92-1899-5d11-a721-5b6640383c3d | date | Date Completed:
6dd56d80-4845-46fb-84ed-4df8cbb5ab18 | checkpoint | 2.2 - Pits and Pit Lids
13692ad9-af25-5987-b609-002b1b7c91ef | note | Reference - IFC Drawings
ead524c8-0313-556f-a38b-59a84f090edf | note | ○ VRIOGS 012.2.1 Section 6.15-16
e795108b-aa0d-5803-8eab-2189f4ae9d2c | note | ○ VRIOGS 012.2.1 Section 6.9
7d1174f3-b534-5eda-b619-ba5df76389c8 | note | ○ VRIOGS 012.2.1 Cl. 6.7 (c)
c277b0ae-9d78-529a-a785-ff831071a651 | note | ○ L1-CHE-SPE-070 Cl. 10 AS1289
b584c88c-6a6e-5970-9ec2-a3b087ffbd5b | note | Acceptance Criteria - Pits:
fbd088bc-38a8-5f98-82c7-d9fe0fad844d | note | — Pits located within 1.5m of nearest rail, pit to be 300LA Railway loading
7ac3d11a-dd91-5563-b816-55bb198f56bd | note | — Pits 900x900mm or greater, multipart pits lids to be used.
271d695a-a0c4-55df-937c-a5a97d5b21e3 | note | ○ Pit Lids:
8fee99b2-d527-5250-85d6-86bf3af23826 | note | — Pit Covers shall comply with AS3996-2006
4dd51396-ea00-54e7-b10e-bf1fa986063c | note | — Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class C.
d79ee908-58b9-5d5a-8cd8-c6eb9475e1c6 | note | — LV, Comms Cover: pit covers shall be labelled with the words “RAILWAYS SIGNALS & COMMUNICATIONS” (L1-CHE-STD-043 14.6)
36fb7326-e4bf-5c26-9a2f-d84480181c2b | note | — Inspect materials upon delivery and attached delivery dockets.
50573bce-c81a-5206-9bf7-47aa1c437397 | note | Method - Visual, Document Review
d503ff21-dae0-580e-b856-b43a497d3820 | note | Frequency - Each Material Type, Each Delivery
eef0e0f2-0d90-53e4-8a17-0af0da0ffb4b | note | Category - IP
52214c9d-dee8-5551-8497-7f36704264d7 | note | Responsibility - SE/PE
78af6589-639c-55a3-b5ae-c0eea10081be | note | Verifying Documents - Attach Material Conformance Certs
000d89ba-797c-5757-a95d-1d7a81f0c773 | note | ○ Attach delivery dockets
a39529c0-6f08-5518-bf48-b8cac340c3dd | date | Date Completed:
53637946-77e0-4898-bd5e-e9da4861e3e4 | checkpoint | 2.3 - Warning/Marker Tape
a7247791-b91a-5cf7-b555-e84af4aefaaa | note | Reference - IFC Drawings
6bee9940-39a0-5f2f-b74e-da0d0566868b | note | ○ AS/NZ 2648.1
2240eb7b-f002-557a-b045-8cf65a0d6dc6 | note | ○ TS-SP-013
229a68b0-2bc8-5ce8-97cc-dfe89f555c54 | note | ○ L1-CHE-STD-043 6.4
8fd3f90e-b7ed-57be-8928-e6b1fb2b1ab7 | note | Acceptance Criteria - Warning/Marker Tape:
8a80a190-3b74-50d9-8b23-aa1bfc92b9d1 | note | ○ Above LV:
af946bf2-9e7b-5b91-ac2e-d87fc3d8f8f7 | note | — 150mm minimum wide orange coloured PVC
f3bd9bf7-b020-5831-9d93-ec8520cc631c | note | — ‘DANGER RAILWAY SIGNALLING CONDUITS’
ee78020a-d061-548d-adc7-124514210413 | note | ○ Above Comms:
c2f7a3bf-af4d-5d4d-8b78-36c07adc2157 | note | — 75mm minimum wide white coloured PVC
21887afd-0640-5ac8-847f-b8fdca6886ea | note | — ‘WARNING COMMUNICATIONS CABLES’ with an embedded stainless steel trace wire to be laid directly above trenched VicTrack assets
8c406cd3-28e3-592c-8f3e-82bb4150944a | note | ○ Above HV:
8d3a7f5a-6a52-5c84-8921-d6ccce83083d | note | — 300mm minium width orange coloured PVC 'Danger - Electrical Cable Below'
e7475a6a-ffbb-5dca-a7a0-8498d4028baf | note | ○ Inspect materials upon delivery and attached delivery dockets.
1dd2465f-400a-5696-8d68-36afd8e5d613 | note | Method - Visual, Document Review
aef3c22a-0d81-59b5-b051-fc9088d7e973 | note | Frequency - Each Material Type, Each Delivery
8ae06038-725f-5d3b-bc48-ac5da53d8674 | note | Category - IP
a6f62993-c35e-5bcf-9d72-7e67462e9ed1 | note | Responsibility - SE/PE
3a54b8b1-f8ac-5044-98a0-c952e2c71beb | note | Verifying Documents - Attach Material Conformance Certs
93d53784-ecca-5104-8de2-06a49f4bcee5 | note | ○ Attach delivery dockets
0148aa6d-5ee8-5828-a4ea-e4b3106adfd9 | date | Date Completed:
0b428970-aa5f-46fd-9324-6671899551fb | checkpoint | 2.4 - Protection Barriers
ffcb2237-0dff-5360-bb27-8ab940eec9ae | note | Reference - IFC Drawings L1-CHE-STD-070 10.3.3 AS4702
dd5da2a6-7524-5bc5-ba11-05491bc8270a | note | Acceptance Criteria - Protection barriers shall be polymeric cable protection covers complying with AS4702 OR a min. 40mm thick concrete barriers (pavers) not less than 15MPa at 28 days
e51f8806-2cef-5f5b-bfa0-1b4ef083ebd9 | note | ○ Inspect materials upon delivery and attached delivery dockets.
13b1553f-daee-5bee-b501-40d6a1a80c01 | note | Method - Visual, Document Review
81e2670c-e014-55eb-b94e-8f8b5ba4e61c | note | Frequency - Each Material Type, Each Delivery
2f637692-e9ef-54af-b5a7-df74a8a89dc0 | note | Category - IP
4bbb394e-9630-5cc3-97ef-a52938ffb0ae | note | Responsibility - SE/PE
71b56bc0-3f2d-5634-b3fa-6ae3f61e8e95 | note | Verifying Documents - Attach Material Conformance Certs
8f50947e-b391-5b29-9cef-6ec2b2f8c863 | note | ○ Attach delivery dockets
5ab5b17c-6833-5703-9631-5abae23f28d1 | date | Date Completed:
6d0a86eb-628f-4e34-81ad-c309acbf7d67 | checkpoint | 2.5 - Backfill Material (stabilised sand)
481a60a3-35d9-541d-b4d9-4ca29ce69d8a | note | Reference - IFC Drawings L1-CHE-STD-043 Section 2 Table 1
1fd41a66-2b7c-541e-be9c-25f8f75329e5 | note | Acceptance Criteria - Material free of rocks that will not pass a 30mm sieve. The material shall be free or organic matter or anything that could dmanage the conduits.
0c88e456-0c16-5d49-91bd-da5271d209ff | note | ○ Inspect backfill material.
89bff0ae-5425-5d0c-986e-b43afa911536 | note | ○ Attached delivery dockets (if applicable).
64f7da1d-f8ee-5643-a5df-0d2046db6b5b | note | Method - Visual, Document Review
76e957b0-5977-5e31-bccb-1ca862f14372 | note | Frequency - Each Material Type, Each Delivery
370c56aa-ceb4-5726-8876-03c4181d087d | note | Category - IP
0583a03d-49a2-5f23-9694-7837e00537c5 | note | Responsibility - SE/PE
c5723b7d-fa63-5338-933b-bf3336ba8e4c | note | Verifying Documents - Attach Material Conformance Certs
823a5051-c11c-5ef7-9109-a28eb3f36711 | note | ○ Attach delivery dockets
49e15549-4941-5848-acf6-66122b9459ab | date | Date Completed:
41f4cb2e-c06e-4fe2-9253-a0573c8f1e91 | checkpoint | 2.6 - Bedding Sand
96a7e7af-e351-5f62-9d8e-5cd1379b43bb | note | Reference - IFC Drawings AS2758.1
972c7ee0-b4c1-5e1d-b462-eb05bb49854e | note | Acceptance Criteria - Bedding Sand shall be a clean sand that is an uncrushed fine aggregate to AS2758.1 and shall have a thermal resistivity ≤ 1.2 °Cm/W at 5% moisture content.
9f54f606-b07e-57ed-8647-c9a4bd000160 | note | Method - Visual, Document Review
8fbdcd40-eec6-5807-ae5d-00123ac072c9 | note | Frequency - Each Material Type, Each Delivery
017f80c1-2bdc-56d3-88c3-c8bcfe5bc83b | note | Category - IP
34863ce3-02a0-584f-9a54-62c08857446b | note | Responsibility - SE/PE
aa396874-d3aa-590f-a8e9-bd126de94830 | note | Verifying Documents - Attach Material Conformance Certs
ad98ef5b-7cbd-5f43-9c5b-d4b15408cb3c | note | ○ Attach delivery dockets
38d907bd-a019-59c6-b202-e754de2b7847 | date | Date Completed:
1160e1fa-97eb-49bd-bee7-af592007c6dc | checkpoint | 2.7 - Draw Wires
2c77d85c-36a6-53b3-abc1-76e3df9ae935 | note | Reference - TS-SP-013, AS 4142
d7d787be-00bb-5126-b440-71b66e88b1d4 | note | Acceptance Criteria - 6 mm diameter polypropylene blue/yellow
9dcda93d-4666-5c3d-8838-b3f20030c96a | note | Method - Document Review
2634ef27-afc9-5226-9395-3c48277973e3 | note | Frequency - Each Material Type, Each Delivery
f7bfec02-8f22-52f1-9000-fcd69430fb67 | note | Category - IP
8d3fae95-36df-59cb-8c3d-5638fd557e40 | note | Responsibility - SE/PE
4d144260-00ba-5651-b9ab-f4da96fb7b24 | note | Verifying Documents - Attach Material Conformance Certs
ab823b9b-0305-5184-a7e9-9ffb3aa8d35d | note | ○ Attach delivery dockets
1a0f022b-2741-5168-a735-e87542afea43 | date | Date Completed:
a1faf77e-a6bb-413d-9f3e-a0bbd900551a | checkpoint | 2.8 - Concrete Mix - Trench
5d4790e4-76f8-5d38-ac6f-a48c22d208db | note | Reference - L1-CHE-STD-043
22db14e6-cedb-505f-bf7c-48e3289897b5 | note | Acceptance Criteria - Concrete strength at 28 days shall be not less than 25MPa.
285d1d55-75cf-5d0b-a9b6-f0f22bed02ec | note | ○ Chemical admixtures or fly ash shall not be used
f13007b1-cc11-5ac5-a0f3-cb311521e572 | note | Method - Document Review
c8a5b2ed-5c8e-5a29-9a27-e05c863a4590 | note | Frequency - Each Material Type, Each Delivery
8c141ae3-5db8-56d5-8df2-9e6e573854d0 | note | Category - IP
6c5c8d46-b336-59de-a593-5e063b16c25a | note | Responsibility - SE/PE
4d93f8ac-f619-5d7b-8cbb-0aec5dc52718 | note | Verifying Documents - Attach Material Conformance Certs
74c5bb45-b03a-5d67-8265-e069a72a42a5 | note | ○ Attach delivery dockets
c6a7c4cf-edd7-52e1-aab4-169ced06c907 | date | Date Completed:
64cf718a-c6f1-4f2a-a852-4a2be340a3b2 | section | 3. Prelimnaries - Procedures & Documentation
6dbd6ca8-36f1-4394-b0a8-d68f6fc0043a | checkpoint | 3.1 - Services
d9ecb74e-777b-58dc-b8ea-64433bd3df7f | note | Reference - Services CAD file
d3bb710f-239b-5287-bac8-f4d15e214ac5 | note | Acceptance Criteria - All services within 5m of Excavation location have been identified and appropriate control in place (refer to MRPA Excavation Permit).
cb8d6b05-2994-5e61-b47b-39f13824f0ee | note | ○ Survey to mark out existing services.
8df5666d-bc8a-5ef6-916a-bc940e75015a | note | Method - Visual
7ade4213-dc41-5b8e-8885-12cf2cc1a2a6 | note | Frequency - Prior to commencement of works
7faf454f-e15f-5e85-ab35-28d66f25b119 | note | Category - IP
4afe9d94-209b-5a9b-bf6b-efce48b4ed37 | note | Responsibility - SE/Site Supervisor
47d959ec-fcf5-5b8c-b009-dd7bee30d643 | note | Verifying Documents - This ITP
36983994-e730-5fa6-98f4-fe15fc4834a8 | date | Date Completed:
38d7ac9b-c3e8-44ef-b24f-956b70601444 | checkpoint | 3.2 - CSR Works Procedure
39e8b4b3-db68-586e-8cc2-33ca888b3cef | note | Reference - WAP_BRU_201
ee03bbf2-7396-5d75-9348-c5107571f595 | note | Acceptance Criteria - WAP to be reviewed and signed by all relevant stakeholders along with Rail Safety highlighting works proedure with in the Rail Corridor
87e9fe93-7fec-57a4-be9b-fdb9c5f883cf | note | Method - Document Review
add27901-faf4-512f-9d09-a9c13dd2b9d1 | note | Frequency - Prior to commencement of works
bab03395-929d-5bf2-a584-426f780c7ecb | note | Category - HP*
a57a2d0f-8666-543f-8487-8dfb9148519d | note | Responsibility - SE/Site Supervisor
a7dbfab8-b41d-5190-93e8-4ba6ca6f1652 | note | Verifying Documents - This ITP
700db065-1a7c-5de3-aa7c-8edd68a4a81d | date | Date Completed:
e6da6b8a-22ac-4905-96a2-f7c0dfa131bd | section | 4. Pre-Construction Activities
0393f1a4-6f7a-47ad-bddc-6bca14774451 | checkpoint | 4.1 - Survey Set-out
7661664b-e8e6-5780-bc25-da9c4ae1c021 | note | Reference - IFC Drawings
f038059c-7fcd-5ddd-b689-04ec80ad88af | note | Acceptance Criteria - Survey to set out trench alignment and pits, and establish construction control (alignment and level).
77622b0d-370d-57d8-aebe-34fce123538d | note | Method - Measure, Visual
0bfac141-4bd6-597c-ade2-56553c4c20db | note | Frequency - Each element
eed39e91-af8c-52a6-9ede-65d51edb2eff | note | Category - IP
a457cb26-9c18-582c-b2b1-450b361901ed | note | Responsibility - Surveyor, SE/Site Supervisor
d294c055-6ae9-55bb-9420-7a784d7b2c1d | note | Verifying Documents - This ITP
9aaced14-0de3-5dad-83e3-eba928356625 | date | Date Completed:
a74b6a9e-d901-4727-a446-91eb682ec855 | checkpoint | 4.2 - IFC Drawings
16114ca5-b703-5fb3-aab2-77f04fd22fae | note | Reference - IFC Drawings
e6ba1090-7aa9-57f5-8a86-853ee7364b08 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
99aebc85-9ccf-5da1-86b2-3fd6b5c33031 | note | Method - Document Review
4f891ea1-e3ec-5523-9585-77ee836b85d8 | note | Frequency - Prior to commencement of works and at regualr intervals
0999dbf3-de48-5ca8-97fa-542b18b1c453 | note | Category - IP
46a5ebd6-044f-57b9-8d3a-ae917621813a | note | Responsibility - SE/Site Supervisor
e886bddd-eea5-583d-9efa-7a526aab6abb | note | Verifying Documents - This ITP
91a50509-1e38-59d6-b3ec-479c465acb1a | date | Date Completed:
5b4ee4cc-dff9-4afe-bdec-245937e3f35b | section | 5. Construction Activities
a016dbf0-9ab7-4573-b1c4-899153e502bf | checkpoint | 5.1 - Trench Excavation
bc3f8d78-0cfc-5599-9509-cf0a2b74d51f | note | Reference - IFC Drawings
13d11978-db63-52fe-8d49-08c200c5b2d9 | note | ○ L1-CHE-SPE-070 7.3 Table 2
f7ed0a35-9830-5534-b5a1-1a8dd96a09c4 | note | ○ L1-CHE-STD-043
de602a7d-54d5-578c-99e5-cee5c819c890 | note | ○ L1-CHE-STD-070 7.1c
ebf8531d-b0e5-554f-9b6d-ae4d0b948600 | note | Acceptance Criteria - Trench profile and depth as per IFC drawings.
fff247cc-b53d-5f2d-95b5-3cf75d6903ce | note | ○ Edge of trenching to be a min. 2m from strucutres/pile foundation (unless it is mounting the structure) and a min. 4m from the rail for HV and 3m from the rail for LV & Comms
3d2797c2-2f23-522c-81c1-ac78d70c7fae | note | ○ The bottom of the cable trench shall be level across its width and free from any protrusions and rubble that could cause damage to the conduits.
1b0ef45c-fb2f-5a45-9743-c3e8f10e9241 | note | ○ The width of the trench shall be not less than 200 mm (chain or bucket excavation) or 300 mm (backhoe and other).
ef7e102e-89ef-513c-afd1-cecc7abeb46e | note | Method - Measure, Visual
1e9f09f8-47ff-5302-aa9d-ae5e0803ef77 | note | Frequency - Each lot
17de76f4-dfc6-5ee0-8e6d-750b2471a164 | note | Category - IP
477857d8-8d01-501e-bb4d-738e58d386b6 | note | Responsibility - SE/Site Supervisor
c3364a14-37d4-5f34-a657-73dfdc7184a2 | note | Verifying Documents - This ITP
4037df9b-40d8-5c2c-92b1-579eb8d34ff1 | date | Date Completed:
68baeb56-0f3a-4b44-b62a-d3fd251f15c2 | checkpoint | 5.2 - Trench Stability
7d391e24-788f-59a7-8afd-394e0ca6fe13 | note | Reference - L1-CHE-SPE-070
f42400e9-dc90-5cb3-8589-aedcea09f6ad | note | ○ L1-CHE-STD-043
606ecec6-6c19-5388-a798-49d541f571ea | note | ○ L1-CHE-STD-070
64a0d046-d91a-556d-8ee9-adf4771d089d | note | ○ IFC Drawings
77a1c7e3-4a66-5ff6-a1af-9ba53f83e31e | note | ○ MRPA Standards
4a98ceb6-8278-5e4e-b471-80953be3ebb0 | note | Acceptance Criteria - Trench stability check:
359b695f-7ebb-5f7c-9969-659f9c1cf10f | note | — Shoring,
2e8057d4-28e8-56e1-82a1-c054b5920db2 | note | — benching
a46a9417-71c9-5d0d-9bf1-b55902511368 | note | — geotech signoff
773dc372-bb9e-521f-98c4-847e4f8f6460 | note | ○ Attached Geotech Report
ba61381b-1af2-5737-9b13-9cf33a541c0f | note | Method - Visual, Document Review
07f5cebe-f896-5dd2-9eda-f9ffc93cd1ee | note | Frequency - Each lot
cda8be39-26e6-57bb-bc80-2133fc51c7d0 | note | Category - IP
a93d5a06-93dd-5e6d-83d9-8fbc80c38f1a | note | Responsibility - SE/Site Supervisor
9353e388-9276-5674-a355-94514a74f38a | note | Verifying Documents - This ITP
7124eeef-061b-5ffb-8bee-be1999a4d5ae | date | Date Completed:
d0e79c50-a353-477d-8af9-81387c52fead | checkpoint | 5.3 - Placement of Bedding Sand for Conduits
a4e6aad7-0d03-567c-a425-a2ff86fb3152 | note | Reference - IFC Drawings
dc5008c4-d266-5880-8308-bdf69fe38321 | note | ○ L1-CHE-SPE-070
381401c4-e562-5754-a0a4-e09c950f1652 | note | ○ L1-CHE-STD-043
f80171c4-1068-5c06-a16e-9418b1af8ef5 | note | ○ L1-CHE-STD-070
92c90e6f-2c0a-5fa3-87d0-4fad8959d681 | note | Acceptance Criteria - 100mm of bedding sand/crusher dust to be places at the base of trench.
75eb00b1-3ce9-5d4f-b6ec-bbed90a8e2c0 | note | Method - Measure, Visual
d4b5448a-e2e8-56f2-8873-1309943e1b23 | note | Frequency - Each lot
b6e6d70e-2bdc-5291-a8d5-4dc0764583f6 | note | Category - IP
fce7493d-1340-5a3a-8684-cd6b745ca24a | note | Responsibility - SE/Site Supervisor
23b32353-0cbe-590c-b29a-89552bfc452e | note | Verifying Documents - This ITP
6a112ee7-55db-5273-a789-b6cc69d7cd00 | date | Date Completed:
941b1b84-cd2e-4c94-ae9e-d7c21a90cf91 | checkpoint | 5.4 - Conduit Placement & Configuration
5f3e2185-15c7-5587-b535-9b4f52237e39 | note | Reference - IFC Drawings
96b375c3-f61e-52d0-8ac8-5211aeadbf74 | note | ○ L1-CHE-SPE-070
cba569a0-a08a-50ab-b1dc-3f7efe763c7a | note | ○ L1-CHE-STD-043
d7848823-320d-5d46-b670-287539afb93b | note | ○ L1-CHE-STD-070
4b019817-56ef-5170-9ea2-8d4513c15366 | note | ○ L1-CHE-STD-077
b48a47ca-6dfd-57be-93b6-27751d7da041 | note | Acceptance Criteria - Conduits are configured in accordance with IFC drawings and meet cable separation requirements.
e25eda21-a467-5f7d-990d-d769d2a53d23 | note | Min Cover
805a4649-f218-524f-bb36-94e51810d033 | note | — HV: 1000mm
b1bd85b8-0321-56bd-9047-0d328132f393 | note | — VicTrack: 650mm
fa40d421-b231-59a5-8c37-402613de1220 | note | — Signalling: 800mm
174f3a14-c3f5-5019-b2d6-02e6ebe605e1 | note | — LV: 800mm
f5eb6705-97a4-5768-9767-29dd4fb6a73d | note | — Electrolysis: 800mm
966224eb-b94c-5ac9-af8c-5fe1a7f7139a | note | — SCADA: 800mm
96e212c2-9688-5044-951b-bb0a69b1938b | note | — MTM Comms: 600mm
d48e28a0-b9a1-5098-9a30-f17320c6ee6b | note | — 800mm below water coarses (stab sand encasement)
dd1a12f6-93e6-511f-9558-778feb647613 | note | — 1200mm Under VicRoads Roads & top of Rail
1b358c87-17ed-57ca-bc0f-cdb9f6ea0fc2 | note | — 900mm below council roads
37c84e17-0f5c-5ed5-baf1-5651cba73648 | note | Method - Measure, Visual
9012bbdc-a878-58c1-b066-b480704250da | note | Frequency - Each lot
1cb825a2-5d62-5c2f-a564-248a690da643 | note | Category - IP
b91eb76c-44ce-51ab-819f-90eab6769cd2 | note | Responsibility - SE/Site Supervisor
842456f5-46b3-5673-b27c-5f8e45c7b8c2 | note | Verifying Documents - This ITP
e1e7207f-f16e-5145-98c8-71249bdab952 | date | Date Completed:
5df90427-41e1-469f-b590-35aa3cb647fe | checkpoint | 5.5 - Separation of Services
4ded7c0d-6705-544e-bded-2e5a7cffc204 | note | Reference - L1-CHE-SPE-070
5d689d97-40be-5c79-8d6b-31b233291cd8 | note | ○ L1-CHE-STD-043
ffa8a5d9-0c92-5500-afc2-ec4929046910 | note | ○ L1-CHE-STD-070
efe8791c-1899-56a6-b825-625810fe2ca9 | note | ○ L1-CHE-STD-077
4d7d873f-3d5a-5492-9f33-e25273372f6e | note | ○ IFC Drawings
cf3b24c6-5ba1-5eb9-82d1-148e3f93ee0a | note | Acceptance Criteria - Separation of services
3630fa3d-8739-52ff-b705-29f493b4235b | note | — HV: Min. seperation distance between HV conduits at least 50mm
e4a0b8df-55ca-54a8-90d5-e54d1b752a56 | note | — VicTrack: fiber 300mm from HV
29c52f71-bc99-517c-807c-b803da454255 | note | — Utility: 300mm to utilities
2faf230e-4f13-5eb8-9f05-13e031b86c09 | note | — Rail: When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
0c6ea2ae-2701-5549-a0c6-4c7c674e0a3a | note | Method - Measure, Visual
3c507d74-c804-5ade-a9bc-0f00e91b71a6 | note | Frequency - Each lot
1715bb81-bda3-5c00-874c-5264b2703e68 | note | Category - IP
1477bff5-a7d6-5cdd-a56a-946894e07209 | note | Responsibility - SE/Site Supervisor
9dee18e1-63fb-5c76-b871-0cd6edaa5c8e | note | Verifying Documents - This ITP
5abf2b44-cda4-5def-9aa2-e5540a954cd8 | date | Date Completed:
446fb29c-0fa7-44e9-89e2-37a5a196c7f0 | checkpoint | 5.6 - Joints
d6dde3ae-f807-5f6e-ab50-fe6ba308f713 | note | Reference - L1-CHE-SPE-070
8fc43af6-7a8f-54d2-b0f2-35c2b6ec1353 | note | ○ L1-CHE-STD-043
c33d1ad8-9127-57e2-b6f6-91adbe1ba318 | note | ○ L1-CHE-STD-070
48369a7f-8224-5e78-a2c4-f6b1db621260 | note | ○ IFC Drawings
1e02f7a6-5c50-5b8f-8e7f-a243393c8de8 | note | Acceptance Criteria - All conduit joints shall be made by utilising the spigot and socket ends.
ebf99f25-112d-514c-a180-7377b7150ac2 | note | ○ Ends to be joined shall be thoroughly cleaned using a solvent approved by the conduit manufacturer.
eeead95d-f9d7-52c3-8c67-3d7ab5bfa3f6 | note | ○ The joint shall be impervious to water and shall be glued with an adhesive approved by the conduit manufacturer.
3f3b66e5-a0cf-5f16-9088-49e5d03271af | note | ○ Socket ends to be placed firmly into the spigots then hit with a mallet to ensure a sound connection
cbd6706f-6500-5088-ac19-38d69ff13a31 | note | Method - Visual
f4a5973f-a969-542f-972e-9809e4592919 | note | Frequency - Each Joint in each trench
ab838061-ec74-5db5-b40e-98d04aaf7850 | note | Category - IP
3887e0cf-5fa2-547d-87c1-8a594837347d | note | Responsibility - SE/Site Supervisor
2c6a823b-638d-51e4-83dd-80dda93b87c7 | note | Verifying Documents - This ITP
8b4bac07-5943-5e95-88db-40137cdbf29f | date | Date Completed:
e1c24470-d15a-4483-9e52-0111e03834ad | checkpoint | 5.7 - Conduit Inspection
544e0039-d2dc-53aa-b2a3-d20a03135d65 | note | Reference - L1-CHE-STD-070 16
fb216f31-27e0-5a67-af7f-47ed8ed8cb45 | note | Acceptance Criteria - Provision shall be made for inspection of cable routes by NA, MTM/VicTrack representatives prior to backfilling.
279fd09c-bb4a-5fc1-8081-743c6d8b17c8 | note | Method - Visual
77c68c47-a316-50f1-8ab4-0e06ec30ea8c | note | Frequency - Each lot
50b1d5a6-6648-53e6-8465-b266f0695819 | note | Category - HP*
71e9e545-9a25-503d-a042-6ded3515dd3c | note | Responsibility - SE/PE MTM / VicTrack Rep.
b4b02094-6681-52b6-ab60-56c4353d7ee3 | note | Verifying Documents - This Itp
5769f6ea-2b57-5706-9b54-f2f9391eb86b | date | Date Completed:
1158a2c7-ec09-4a40-9382-3384625e8769 | checkpoint | 5.8 - Bedding Sand Installation
347ff0fb-0eaf-5142-b186-6513a7f91628 | note | Reference - L1-CHE-SPE-070
43fd87e4-614d-56db-80e4-cb8a538943e8 | note | ○ L1-CHE-STD-043
57d7c67e-b137-5e43-b6d8-7468afcf8fe8 | note | ○ L1-CHE-STD-070 CL13.1
521837f8-fd91-5972-96fc-9b1eadbaa8d5 | note | ○ IFC Drawings
802c3930-e4e1-5cad-8d43-9517759f12d5 | note | Acceptance Criteria - Bedding sand/crusher dust extends 50mm past edge of conduits.
af9733b8-d1d4-579c-859c-d0d51c233034 | note | ○ Bedding sand/crusher dust extends 100mm above conduits.
44375ce4-6d84-5123-a54c-61708953d80c | note | ○ Attach Delivery Dockets
8c480ab6-a032-5b84-8953-bbb8acb09c5c | note | Method - Visual
c738d6f7-fd32-5491-a110-1239dbb1335a | note | Frequency - Each lot
ac7dfe85-4743-5108-99ae-66c0d8621b3a | note | Category - IP
e4f50f3e-feff-58e5-a477-63bf315d8a96 | note | Responsibility - SE/Site Supervisor
e7234e01-e9dc-5287-9327-8e8be73a4d3f | note | Verifying Documents - This ITP
8edf3bc2-dc76-58e1-8957-b3d3ff6087e9 | date | Date Completed:
53d898b4-c253-434d-b275-49c2f7d2805a | checkpoint | 5.9 - Marker Tape
b98e535c-e521-59c5-b8cf-c8a30de519af | note | Reference - L1-CHE-SPE-070
3aa821fe-a0c7-5fe9-a798-5cec51fa75b1 | note | ○ L1-CHE-STD-043
fd87549b-7af0-53cc-a3f5-2226b7cd1c19 | note | ○ L1-CHE-SPE-070 Cl10.3.3
8d02e763-a0f8-5708-b86d-e36859e6dc4e | note | Acceptance Criteria - Warning Tape installed a min. 300mm above top conduit or a min. 300mm above HV protection barrers.
a48bea42-77d8-5de1-bc6b-19741f05b914 | note | ○ Tape to be one continuous length.
d2447c33-b016-53e6-92b2-8be8e80c1312 | note | ○ VicTrack to inspect the Marker Tape placement..
82a689be-6a3f-5fac-ae19-0491f91447a6 | note | Method - Visual
01ce6b5f-4375-505a-b888-d812845b97e3 | note | Frequency - Each lot
fcf19e1b-21aa-5024-90d9-60502395d731 | note | Category - HP*
c532559d-cd0c-56ce-a54f-15493b21ab44 | note | Responsibility - SE/PE, MTM / VicTrack Rep
b9efcb46-0b0f-5bca-af81-42d91b562ded | note | Verifying Documents - This ITP
0b31646a-8e61-5f7c-b6a5-0600fc696ef1 | date | Date Completed:
6d25b95f-1a46-4cbc-8ed6-108797f2a02e | checkpoint | 5.10 - Backfill Installation for Conduits
2a05fcd8-84e0-5dfd-a150-2b421f83ebf0 | note | Reference - IFC Drawings L1-CHE-STD-043 clauses 6.15 and 6.16
a696d314-d932-5274-bbaf-7ab51a4c9054 | note | Acceptance Criteria - Backfill per trench profile:
9e138a1a-7808-5429-9d81-53826aa0cb40 | note | — 150mm layers of 3% stabe sand
8b8c9015-8fd4-5a80-9339-0e067f4626e7 | note | — conduits under water ways to have 800mm cover from base of water way and backfilled with 3% stab sand
c03579f2-81cf-526d-8921-110b7b85edb5 | note | ○ The trench shall be finished with a slight mound, height equal to approximately 25% of trench width, to provide for further settlement.
7543fe6c-ea3f-57f6-9de5-cabc7b42228c | note | ○ Trenches under road pavement - backfill to be same material as the road formation material.
d4dd66be-51aa-54ca-8bf3-72ae64b3202e | note | ○ Trenches immediately adjacent to footing shall be 3% stab sand. To be thoroughly placed to fill all voids without placing undue strain on or cause displacement of conduits.
157fd622-6529-5c24-a713-1e6091614bfc | note | ○ When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
ea282d14-530c-5146-b773-68586a83fedc | note | ○ VicTrack to be notified and witness the first layer of backfilling.
26a6da18-ce73-57a9-8a75-c567c3e7b758 | note | ○ Attached Delivery Dockets
190fd874-aae3-5042-b9b2-f50f2aeb7587 | note | Method - Visual
f74b2428-f662-5f56-ad13-0e3308431a1d | note | Frequency - Each lot
310dcfe7-5072-587d-960c-828740f4e619 | note | Category - HP*
8bc9a8a4-ea28-51ea-9815-44d6fa0adc4d | note | Responsibility - SE/PE, MTM / VicTrack Rep
a473fa66-d804-55b8-8fe2-83754ac85890 | note | Verifying Documents - This ITP
9c215b2f-44cc-518d-ac91-dc07b0df1d32 | date | Date Completed:
02ba215b-188f-4a2f-9cd0-e90e2bd7752c | checkpoint | 5.11 - Signalling Pits, LV Pits, Electrolysis Pits, SCADA Pits, MTM Comms Pits
917177da-adb0-5497-ab11-f7671cd46af6 | note | Reference - L1-CHE-STD-043 Cl7.14.o, Cl7.14.g
24231afa-cd0f-5452-aaf3-308652dfdd41 | note | Acceptance Criteria - intervals no greater than 400m (electrolysis 190m)
14fb04be-6c72-5a14-8c9c-9b23cddc171d | note | — 3m from rail
63be3294-aefe-5cfa-b310-cbbcf8fadb6b | note | — Access Roads, Class D lids
a8deef1e-c2d6-5ea9-aeeb-483631460358 | note | — Footpaths and non traffiacl areas, Class C Lids
95fda06b-521c-5b2d-a78f-3c001f1c779e | note | Method - Visual, Measure
4d197e1e-d60e-57cf-9127-3107f6b35455 | note | Frequency - Each Pit
db7df531-aaf8-504b-b8b8-7d279d9a2f24 | note | Category - IP
ed01296a-5ce2-57f3-bd65-622993ff8138 | note | Responsibility - SE/Site Supervisor
84b01b05-d288-514a-9f67-48640b09c4bd | note | Verifying Documents - This ITP
4ace52eb-5723-5d7f-bb53-0dafa402a7e4 | date | Date Completed:
3529be7d-104c-468f-bad7-85d39dcbf741 | checkpoint | 5.12 - Additional Considerations
46afd207-5bae-5378-9bb1-c497d0bc2b4a | note | Reference - IFC Drawings
27bee4d1-7059-536e-a5a7-56e4b880aa38 | note | Acceptance Criteria - Access tracks to pits
f8801b68-2001-50de-9011-7847a0c2d06d | note | ○ Safe access and egress (i.e. lid doesn't open up with workers back to the rail)
89915c75-5bee-5db5-b418-6b691d89d39c | note | ○ Hand rail & retaining wall installed as required
3e94da1a-bee2-550d-bcb5-7cd8ae92f961 | note | Method - Viual
c8daa94e-a8e3-59f1-93e7-546b75bf2a2d | note | Frequency - Each Pit
c5255049-337a-5c6a-a7c6-c10f84c953aa | note | Category - IP
66422e07-5076-562b-af32-5a40c79370e6 | note | Responsibility - SE/Site Supervisor
6d6b3d42-0bbe-5ab0-8f73-185f4edc82e6 | note | Verifying Documents - This ITP
0f865af3-8c03-5b1f-a99c-a886c569afdc | date | Date Completed:
9cae01b0-27e6-45b9-abd0-1b21d0980da4 | checkpoint | 5.13 - Bedding for Pit Installation
4ee2ac9c-952a-5928-a628-c511506943b0 | note | Reference - L1-CHE-STD-070 Cl 7.21.u, L1-CHE-STD-043
061156d0-42e6-5a58-b35b-4187d91a94a3 | note | Acceptance Criteria - 150mm of crushed rock under pit extending 500mm past the pit
dd83127b-0cd4-5aab-bfd8-39c30ea83eef | note | ○ Drainage arrangements shall be provided at the base of each pit.
55aed04e-c475-59c0-bbdb-1d5cf0921cf8 | note | ○ Attach Delivery Dockets
611ee798-dd7e-5179-9ae0-f9b35fadfe87 | note | Method - Viual, Measure
dc93a60b-23c7-5bb5-bb36-a165e5fcc770 | note | Frequency - Each Pit
1c05de7e-bddc-530a-a003-e4195ce12880 | note | Category - IP
0930bd37-9df9-5a2a-91b4-fa94f5457f1c | note | Responsibility - SE/Site Supervisor
149c9ba3-638c-5542-b2f5-e117ec6dc511 | note | Verifying Documents - This ITP
cf126e72-43af-5749-ad88-0598aeeb5795 | date | Date Completed:
933c9d3e-b24b-4310-9b99-5a13ce416f06 | checkpoint | 5.14 - Pit Orientation
8883f002-1e24-5be7-afe5-6587cd1c1ba3 | note | Reference - IFC Drawings
8b347707-2555-5018-bfd6-4b19bcb88f77 | note | Acceptance Criteria - Pit to be parallel to track and parallel to conduit route.
acbb966b-3f42-58de-a7b5-0de2394fb2d9 | note | Method - Viual
a61476fc-0097-51d3-8de8-3ec6cf693d90 | note | Frequency - Each Pit
c2d2e964-83d7-5c85-b18e-07d60bcf9175 | note | Category - IP
293da53e-3fc9-584c-ba59-a7bd93292814 | note | Responsibility - SE/Site Supervisor
08ca53c3-4ece-5e1c-8a70-743fac27a8c1 | note | Verifying Documents - This ITP
2ec34f2e-e773-5864-9c7a-c9a2553ed984 | date | Date Completed:
f75b046f-3348-42e0-a998-89a8eac813a6 | checkpoint | 5.15 - Pit Installation
b91a6d5d-ef2c-5cf7-974c-4b27aa9e3f0c | note | Reference - IFC Drawings
33f3d29a-4676-5973-a28c-d78746c486b7 | note | Acceptance Criteria - Pit installed to design specifications
8924f2a9-b709-5549-847b-74832b9e6d5f | note | ○ Pit chamber floor to be 100mm lower than the underside of the lowest conduit.
319a8b7a-b020-5a7a-a670-372e7a4bbe4d | note | Method - Viual
ffe5cf5d-42c2-5f5e-bd19-4ce8d9ce2797 | note | Frequency - Each Pit
646d267f-e56f-5d32-a28a-71aa0e2b3ee8 | note | Category - IP
4662e283-da7e-5c14-b150-888fa5ba2373 | note | Responsibility - SE/Site Supervisor
d752af78-c53b-5b9f-842e-9a300b568d4e | note | Verifying Documents - This ITP
b5129d0e-3f29-5e19-a6db-d7dcd9ec1fba | date | Date Completed:
e3c21023-411d-4a0e-a7e4-c6fd2783b32b | checkpoint | 5.16 - Conduit Entry onto Pits
d907deed-bcea-592e-af85-7accc9278a07 | note | Reference - L1-CHE-SPE-070
2dec45f2-d103-5f77-bbf7-0d7258629dfb | note | ○ L1-CHE-STD-043
06329ea9-b6d8-52f7-854f-549c94f4e014 | note | ○ L1-CHE-STD-070
b01e2e45-cd75-5589-8d62-8cc8de60ce06 | note | ○ IFC Drawings
d36c282f-325f-5c2a-92b7-765e6ec35ed0 | note | Acceptance Criteria - Lowest conduit 100mm from the pit chamber floor.
bddebfd1-587f-546c-887a-130171709611 | note | Method - Visual, Measure
2464309a-faf1-5b8a-bd3c-d602f43c6514 | note | Frequency - Each Pit
67800750-4fdb-59f8-bb57-6ab895858899 | note | Category - IP
18c6252d-6078-5dd5-a33f-7df2b20496e6 | note | Responsibility - SE/Site Supervisor
103e5b46-09b2-5f63-bf91-3bd65d5e1ccf | note | Verifying Documents - This ITP
decfd31e-fcb7-57fc-9fd2-368d691f037c | date | Date Completed:
44fc683c-f009-48ae-8a74-fe7e647a932f | checkpoint | 5.17 - Tracer Wire
ad68440d-1cc4-5d13-8b11-48a138ba46b5 | note | Reference - L1-CHE-SPE-070
bffd7118-4db9-5b35-a2ec-d331777ae1b1 | note | ○ L1-CHE-STD-043
30aa3630-ce9c-55b4-963c-e817fdb31ff5 | note | ○ L1-CHE-STD-070
fa218cab-6a62-56e8-9457-8aeb51c22e8c | note | ○ IFC Drawings
fd682759-895a-583c-8cce-513e043a3386 | note | Acceptance Criteria - Warrning tracer wire for Vic Track routes to be drilled into pits and crimped off.
4b9750de-fc4a-512f-91f0-a98a7b3102df | note | ○ If tracer wire broken needs to Crimped
b0f15fd3-3619-53e1-ae21-531f1bac5c74 | note | Method - Visual
65689207-6216-5795-a9a4-5f8c218decdb | note | Frequency - Each VicTrack Pit
ae0368d9-8371-5870-be02-e52a3fe19fee | note | Category - HP*
198c07f9-36dd-50ca-b871-ec5cd05a5d3c | note | Responsibility - SE/PE, MTM / Vic Track Rep
0443319c-b56c-5f00-846e-9dcbbea930a8 | note | Verifying Documents - This ITP
20287418-f4f6-530c-8143-410cb5bd2d5a | date | Date Completed:
296f30ee-7d36-4dac-bc20-1642324b0ff5 | checkpoint | 5.18 - Spigots and Bell Mouths
863eebed-41ec-56d5-8cc7-43df250f7cfa | note | Reference - L1-CHE-SPE-070_9.3.4
40a19118-e515-59ee-bbce-a994a300a1ec | note | Acceptance Criteria - All conduit ends in pits are to be correctly fitted with spigots to ensure that there are no sharp edges on the conduit; they are to be mounted flush with the pit wall and not touching any other spigots.
c60830a1-fe60-5c30-aa3a-0c3b946a2d98 | note | ○ HV Conduit entering the pit shall extend a minimum of 150mm beyond the edge of the excavation and be fitted with Bell Mouths.
a755b64f-f53d-5852-ba57-78ce12cf3bc8 | note | Method - Visual, Measure
dca3ce3e-5714-5c03-aaa0-4b7bb8e178aa | note | Frequency - Each Pit
d08b3553-8ee4-5e2f-8ecd-9d83473c9061 | note | Category - IP
04ea5099-128a-5eb3-969c-75d7608ecbcb | note | Responsibility - SE/Site Supervisor
58b759d5-ba1a-59e3-9d4c-00496cb31821 | note | Verifying Documents - This ITP
bcadec9b-a1d3-5fc5-a954-ae5f23cc36ed | date | Date Completed:
de626973-f964-4263-a235-f9b80b1df669 | checkpoint | 5.19 - Draw Ropes
bfc34f1c-3a43-5820-8084-d415c13a5682 | note | Reference - VRIOGS 012.2.1
9c938d8c-79eb-5163-96dd-3cf72f48095f | note | Acceptance Criteria - The draw wire shall be continuous for the complete length of the conduit run.
e5f3a52a-2cb8-5163-91c1-29acea9d6c6f | note | ○ The draw wire shall have a minimum of 2 metres of slack within every pit.
c7d2445c-7b94-5e27-8f44-2b1de8bb758f | note | Method - Visual
c6ada36a-904b-5031-9b05-05c3113a5aee | note | Frequency - Each Pit
41308785-1612-5606-91a8-ef0e65fff39e | note | Category - IP
6aa7023d-42e1-57db-a0e8-9cdaef5d6128 | note | Responsibility - SE/Site Supervisor
ad3c398b-61d2-5420-88ff-983d50ec9e9a | note | Verifying Documents - This ITP
9a3e8b95-1d9d-595e-9a98-0b3cad362715 | date | Date Completed:
092df6c2-b330-4d8b-a288-b3233aae6c08 | checkpoint | 5.20 - Backfill and Compaction Testing (if applicable) arouns Pits
c0958d5d-0e70-5304-86f6-89626e4d97a3 | note | Reference - L1-CHE-SPE-070
a5efeddf-9ca2-5a6e-97c3-ef18ab3b75b4 | note | ○ L1-CHE-STD-043
7f745a75-3c6b-5ae2-8dff-c30e61427325 | note | ○ L1-CHE-STD-070
c3657dd6-aa20-5c43-b2d0-2170a5d5ad14 | note | ○ IFC Drawings
96ca558a-b9e0-597b-b669-6bd63c672eb1 | note | Acceptance Criteria - Backfill used around pit & pit lid to achieve 95% standard compaction in layers no more than 150mm layers
aa135849-7752-5c29-82dd-067d52d2f2ce | note | ○ Sand within sand pits to be compacted in layers no more than 250mm layers
0ec734f7-433a-5580-80ea-e50e030ca750 | note | ○ Backfill shall be compacted and level with the collar and surrounds for Trafficable Pits.
2819986f-7153-5c65-a911-9bfc72d4dd92 | note | ○ Attach Test Report
6735465f-5b4a-5f37-ab71-b2d146136712 | note | Method - Document Review, Visual
c3f866ef-7499-5412-878c-38771b947e9f | note | Frequency - Each Pit
ac0b746e-995c-5ae5-8b57-f44387757e04 | note | Category - IP
b3c57318-8d7b-5745-986a-41f19a50e0e8 | note | Responsibility - SE/Site Supervisor
7474a51f-c3a9-5dcb-b3d6-2278025c3536 | note | Verifying Documents - This ITP
e86996f2-3e1c-5e8c-8903-12b3f2b0ddb0 | date | Date Completed:
b0033168-8136-4d5b-98be-a596353a1d65 | checkpoint | 5.21 - Spare Conduits
496f7ffd-05fd-59dd-b587-97ab185f3afc | note | Reference - L1-CHE-SPE-070
55286ada-c1c9-52a5-be6a-49715d7848b9 | note | ○ L1-CHE-STD-043
505a071d-0d89-5f94-ad97-86e591f6fbf0 | note | ○ L1-CHE-STD-070
4773c37b-183a-5609-8bf7-af8480bf81e6 | note | ○ IFC Drawings
d555ba29-1993-5539-b466-de7cc978997a | note | Acceptance Criteria - Spare conduits to be sealed and to be included on survey report.
f345e299-5800-5033-a338-d5c74dd565ab | note | Method - Visual
fda68f12-9506-5704-8607-8e0aba7ebe6f | note | Frequency - Each Pit
da1d8015-6f73-5bce-88c7-f58f293a0310 | note | Category - IP
8621d87b-b55a-58b8-aabf-47bfdc1e62db | note | Responsibility - SE/Site Supervisor
253cf55d-aaaf-523a-90ec-cf68931c85b3 | note | Verifying Documents - This ITP
0ba0c18d-b771-5c47-99f0-186cedc40c3a | date | Date Completed:
5b25f5c1-45ba-43eb-8867-10826b33a77c | checkpoint | 5.22 - Pit Lables
09875e99-dd5b-5f5a-b4c2-00e2a7dd6cf2 | note | Reference - L1-CHE-SPE-070
e20c6a09-e518-5e8b-9867-4706a3e03310 | note | ○ L1-CHE-STD-043
7032d6ed-08da-5085-bd6f-d79b74b18e88 | note | ○ L1-CHE-STD-070
1866a252-462d-55bf-8c45-87b5b028c914 | note | ○ IFC Drawings
cce4ccf1-eabb-550d-b189-c896885dbe1c | note | Acceptance Criteria - Pit labels Brass Label (30mm x 150mm)
b28d2183-d72a-5e17-bb41-bca20c9ea5bd | note | — HV: DANGER - Railway High Voltage
9641edb9-891b-54a0-900f-ca1562553bb1 | note | — VicTrack: Victrack Comms
80334646-2183-5afa-b5f7-778fb1fe680c | note | — Signalling: Rail Sign Comms
3cfdbfa2-65d9-5f7e-a220-221b00b898c0 | note | — LV Pits: Electrical
56a0a2e6-a38e-5d8d-9b85-3457c2fe98d3 | note | — Electrolysis: Electrolysis
3e8d1eff-bef1-5c93-b7d8-906978dadfef | note | — SCADA: Rail Sign Comms
899be3b3-669b-598e-84ad-4cf4a71b37c0 | note | — MTM Comms: Rail Sign Comms
aa3a6121-7d0f-524f-a77a-e0ff5b8d79cd | note | Method - Visual
d929137d-6bab-52c3-8ec4-0fc0ebafe738 | note | Frequency - Each Pit Lid
02334225-e0f5-5833-9d5c-8b3419f8848f | note | Category - IP
f130ea3d-bef7-523f-b561-7314782dac9c | note | Responsibility - SE/Site Supervisor
60557c1c-c324-55bd-b9d5-ba4652bf646d | note | Verifying Documents - This ITP
2bbb784f-56f7-5981-a95c-9f64ab4b18b9 | date | Date Completed:
8021885b-23b9-457e-b73c-847ddeb8414f | checkpoint | 5.23 - Pit Numbers
5ee559c4-7f89-5620-9fbb-5500801aa6c0 | note | Reference - L1-CHE-SPE-070
bb210b91-8030-56c4-b40e-ca036b09ba50 | note | ○ L1-CHE-STD-043
4fa6832a-a353-5504-8ba6-3445fc1f0474 | note | ○ L1-CHE-STD-070
9d0f70e8-7547-5fa8-a295-deda7a4adda8 | note | ○ IFC Drawings
7c9b16fd-345f-5c59-9785-1e0d9738930c | note | Acceptance Criteria - Pit Number Brass Label (30mm x 150mm)
d7f73663-0c4d-577a-aa46-3f20e6c8003d | note | — HV (22kVV Feeders): ###HV
ee89a42f-ea0c-5016-a32c-059762fccba7 | note | — DC (HV Feeders for OHLE): ###DC
6ba0ebb9-e1fa-57e0-83ff-e43d3ad01c42 | note | — VicTrack: ###C
6be5d7d3-cb32-55d0-a871-d4adea0f25d3 | note | — Signalling LV: ###SL
b620ee3c-8591-5356-a4a9-f43422ffeee9 | note | — Signalling HV (2.2 or 3.3kv): ###SH
aa271322-52d8-5112-8580-31b41d0ca307 | note | — LV Pits: ###L
40575d2e-373e-5c49-b89e-257217f5f85f | note | — Electrolysis: ###E
f6e3e1e6-e719-5333-bac6-40b9632c304f | note | — SCADA: ###MS
b8c58dd5-eeea-56ee-809f-f37d202a2201 | note | — MTM Comms: ###M
444ab24a-a39e-59af-9d85-a72445d30c0f | note | Method - Visual
724df23c-beb0-5adb-a5b8-9dd59bfe585c | note | Frequency - Each Pit Lid
28272fa2-1ca7-59e2-8b0d-352311cccefc | note | Category - IP
49acdf21-36de-5f48-8887-8259002b6fac | note | Responsibility - SE/Site Supervisor
d4158129-366d-5402-b0ac-69395460d6d4 | note | Verifying Documents - This ITP
7b44625d-e8d8-538e-8101-f96d08a71ebd | date | Date Completed:
3a1ccc03-5543-43f8-9d11-84d7ccd3f9dd | checkpoint | 5.24 - Cable Route Markers
3d799d66-c1c2-5a22-9829-67200efba9d4 | note | Reference - L1-CHE-SPE-070_13.2
c05bd66f-4dd9-5ac7-9ce8-90655674688d | note | ○ STD_E0169 and STD_E0170
a27cdade-fabc-5686-b8e4-9d541805aede | note | ○ AS 4799
65a2312a-92ec-5fb9-92dd-64b6807d7e08 | note | ○ STD G0003 and STD G0004
060a7b52-d052-50b0-b3dc-bb2c677cafa6 | note | Acceptance Criteria - Cable Route Markers
af1d36a6-8d30-5842-ba0f-4ff59025ec3a | note | — points entering & leaving the rail corridor
35fbf1da-64f0-5264-ae60-4ffebf8ef08e | note | — no greater than 100m spacing
903123af-3276-5c5c-aa91-6c2078f5479e | note | — Change of direction (more than 5 degrees)
521c2ce3-f599-5f83-9998-9e59259e39a8 | note | — White posts with marker plates for conduit runs
5fece27c-4af6-57de-81ed-3683e9766306 | note | Method - Visual
61f932f2-334c-5bd6-ab8e-8f43d2e4d9b1 | note | Frequency - Per Cable Route
9ddd1ae8-720d-5ddd-b7d5-8554d542b4b5 | note | Category - IP
ea3b43ca-ede6-5709-b642-49d79ba007af | note | Responsibility - SE/Site Supervisor
c98d59d7-fb4f-5182-bf68-004a8367121a | note | Verifying Documents - This ITP
a0ffc263-0906-5580-a548-616fd25182cf | date | Date Completed:
e4ab54de-cfd2-4034-ab02-305a04b82585 | checkpoint | 5.25 - Cable Pulling
1989b2b5-f5da-51ff-a6b7-4cb1e17c8443 | note | Reference - L1-CHE-SPE-070
6d8e38b7-a7a7-5a7b-9bda-a5bf1f7995fe | note | ○ L1-CHE-STD-043
5261c9fd-c569-57e3-9032-6b281fe16492 | note | ○ L1-CHE-STD-070
d5d473a5-4edc-57d6-aa1f-bbe3ff16efba | note | ○ IFC Drawings
a0e55fa8-7aba-5fd1-9cb2-fb0810756cd4 | note | Acceptance Criteria - Cable pulling to be witnessed by MTM/Vic Track and to be signed off.
e16d4981-3f4e-5649-89fb-6ad69ca42902 | note | Method - Visual
90937978-0fa0-5b56-ab50-fa42ab4a0410 | note | Frequency - Per Cable
c2938fcd-ee2a-5a9f-8051-593ec65b509b | note | Category - HP*
3692b393-71f0-5c5f-80e1-692aed353986 | note | Responsibility - PE, MTM/VicTrack Rep
ce408a92-64ae-5386-85ae-8d898a278de2 | note | Verifying Documents - This ITP
b075057e-b2fb-5cb8-8db3-ff70a10f7852 | date | Date Completed:
ab1231eb-2e64-4cd5-a7b8-bc2e72f59c8c | checkpoint | 5.26 - Cable Labels
7736fddb-8e82-5820-98a0-a2d8a206b874 | note | Reference - L1-CHE-SPE-070 Section 13.3
6eedaf40-ee2f-53d0-a9cf-ad971f43dcec | note | Acceptance Criteria - All installed High Voltage Cables shall be legibly and indelibly marked with an appropriate identifying label at each end of the cable, and at any cable joints.
df272dcd-3c0c-57a4-8eb4-79587db88452 | note | ○ The label shall state the destination points of the cable and the name of the cable relevant to appropriate drawings
3a8e6e12-72a7-54d4-b0c9-7f1d7ad3aec1 | note | Method - Visual
c0324c29-56cc-5f0d-947d-0bdf6173aded | note | Frequency - Per Cable
adb43a5e-9ed5-5bde-a359-659964c3a272 | note | Category - HP*
112f7b80-6405-5825-8232-1fe2bfa7cd1d | note | Responsibility - PE, MTM/VicTrack Rep
2bc6b472-5e86-5f48-b963-9f0320f7ff7a | note | Verifying Documents - This ITP
edf7d595-f7f2-50d5-a5cc-c68cc19e1493 | date | Date Completed:
5edc89b6-264f-42fa-9fdf-f4cbf425f7dd | checkpoint | 5.27 - Cable Joints
24ee56ed-cad0-57cb-9322-10a7519b66e4 | note | Reference - L1-CHE-SPE-070
7b0b5d6c-7f93-5842-a8bd-f4b75d16d122 | note | ○ L1-CHE-STD-043
75d2fd8f-d4eb-5ac7-bdbf-29dde62cb565 | note | ○ L1-CHE-STD-070
104bc220-f536-5890-bbb7-b4f71cb2276c | note | ○ IFC Drawings
b9b8efa0-42d4-548d-bdf8-c5821b5cade5 | note | Acceptance Criteria - Cable joints are installed correctly, with sufficient fault loops lengths & supported correctly in pits.
7d00489c-1d73-51a2-8776-d9954e867963 | note | Method - Visual
8360adce-70a7-5d40-bdfe-0181739a8d0c | note | Frequency - Per Joint / Termination
5b24dc69-b58b-58b9-a93c-59fc42856b23 | note | Category - HP*
927f2a9c-3c85-5897-850a-b9006e6842a6 | note | Responsibility - PE, MTM/VicTrack Rep
dea12e58-b9ac-5df9-b2b1-c312be0ea749 | note | Verifying Documents - This ITP
d9ed94ea-361a-5a62-9701-1bda625a5266 | date | Date Completed:
76c04f1c-eb6e-4f6c-95a9-b35bce8dd4e0 | section | 6. Post-construction / Post-installation Activities
59691746-963c-4be1-8943-b8fb56ae8738 | checkpoint | 6.1 - As-built Survey
40a3c7ee-21ca-50c1-a170-5c1ddb6fb52a | note | Reference - IFC Drawings L1-CHE-SPE-070 Section 13.1
0eb9fc93-287f-58c4-b7b8-8433a43526b4 | note | Acceptance Criteria - Survey report to include but not limited to:
b4d2dfbc-b976-5bed-bb68-5fe7f4bc6b27 | note | — Cable joint locations.
994e2ff4-cc86-56ee-b687-16466bf589df | note | — Cable pit locations (Corners)
96d42fbe-fd29-56d6-97d7-66dcf30d8524 | note | — Pit dimensions & pit lid type
0cbe5798-1138-5397-bb07-40adda30b3b9 | note | — Under line crossings
c32076f3-2d7e-5726-af3f-ae742797c631 | note | — Under road crossings
c2d48861-a7b5-5f3e-84b9-d0bd3335d266 | note | — Changes of direction
61adde5c-026a-5128-a0a6-8fa1179b9d9d | note | — Spare Conduits
d74fa2e0-23bf-5ac1-bdd5-0eca45217f3d | note | — Conduits labelled as per trench profile
aa6d5370-bde0-5b34-b388-80e15abd4737 | note | — every 10m
3e648e67-ad27-518f-9716-193040b92785 | note | — Other significant points of the cable route
e30feaeb-3b15-51d4-bb1f-7f5d26a567c3 | note | ○ Attached Survey Report
fa77b9f6-8eb0-5f92-8170-3645705a6069 | note | Method - Document Review
c01d39ec-b9e1-57fe-a465-3eb908c441b8 | note | Frequency - Each Lot
0953857b-ccc6-571d-9eea-12943d7d7e09 | note | Category - IP
540db516-d0ee-5484-b03d-d4391620af48 | note | Responsibility - SE/PE
7d50c981-c97a-5243-bbbb-9b494809a17d | note | Verifying Documents - This ITP
de56849a-b389-5e16-a5b6-1c6a21623a9b | date | Date Completed:
3bfbc328-2a19-402b-9174-b23414c03b42 | checkpoint | 6.2 - Handover Check
ae98041f-277f-5aee-bd9b-6f795572e614 | note | Reference - IFC Drawings
f7b5a273-e96e-580a-9fca-91461e87dfd6 | note | Acceptance Criteria - Handover check completed for Testing and Commisioning.
a2f220cc-6151-5565-b6ec-a0a09c3daa61 | note | ○ Attach MTM/Vic Track Check Sheet (Signed-off)
67c97a9e-712b-50f3-938d-8db637d16998 | note | Method - Document Review
c2bd2794-893e-507d-94fc-ac834db87c48 | note | Frequency - Each Lot
b7a18a7b-279f-578a-81b7-641b876c1482 | note | Category - HP*
e0a64ebe-aa49-596a-8372-6c9f92f69240 | note | Responsibility - PE, MTM/VicTrack Rep
a1ed8cf5-61b5-50b9-a049-a9dec9c7ebc4 | note | Verifying Documents - This ITP
5fcea59a-e164-59b3-9657-741d8304bd52 | date | Date Completed:
316e8a0f-625d-4ae7-8658-924866d55980 | checkpoint | 6.3 - Testing and Commissioning
8fd80972-b9e2-585d-9a8d-a75c456ef361 | note | Reference - IFC Drawings
7aebf57c-fe1b-5fcc-86fd-2f280bd6e393 | note | Acceptance Criteria - Testing and Comminsiong to be completed
759f3500-a53c-5796-a9ad-5f25f736847f | note | ○ Attach Testing and Comminsiong Report
dce92ece-a49f-5200-a22a-e99cfe4c6902 | note | Method - Document Review
239258d2-8b5c-5587-87cf-7f8c042865fa | note | Frequency - Each Lot
9029ab14-06b5-513d-adcf-30c3034d526d | note | Category - HP*
5316b438-289e-5bc3-86e4-909a24488bff | note | Responsibility - PE, MTM/VicTrack Rep
1a390e46-640f-5e67-bea4-626a812af27d | note | Verifying Documents - This ITP
b270bf6d-b43f-514f-8ab2-fa85756b0c44 | date | Date Completed:
a47f2804-d570-43fd-9e30-9e4d5ce3bb30 | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
ebf31bea-e34e-5488-a3f4-9d1eb8e68b49 | note | Reference - MRPA Quality Management Plan
5865cb46-23ec-5f35-831a-1bec7421def4 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
655ece0d-c9d2-5b43-b29d-d3602137c679 | note | Method - Document Review
6c10890b-afb9-5b9b-bd75-51f1fa6d9d63 | note | Frequency - Once, prior to closure of this lot / element / Work area
3240f32b-ab58-50e8-983e-72d85e8d64ee | note | Category - HP*
549062a8-6f05-5b17-985d-05b2a41b8d83 | note | Responsibility - SE/PE/SPE
55baabf8-53ab-5bd6-b8cc-31df8d1b83b0 | note | Verifying Documents - This ITP
ea905992-eaa9-5a7e-81bd-a164db36f213 | date | Date Completed:
dc6c9ce8-cae6-407e-b3bb-56854f0ae554 | checkpoint | Final Inspection
cad8e5a6-dd64-5772-817f-719181277305 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
80bdd11d-035e-55e1-bb8a-4f959e45185a | textbox | Name:
f7e317d4-ded4-548b-8502-f31abd2eab38 | textbox | Position:
67c7f60f-bb41-58aa-a4b7-8551134b3fbb | textbox | Date Completed:
5dd898b4-563f-4f79-a645-668da204b37f | signoff | Sign ITP
8ecc0bf8-955f-4244-820c-dc1a9bb344f5 | checklist | ITP-300-CIV-ADL-Hot Mix Asphalt Rev 0 | itp | ITP-300-CIV-ADL-Hot Mix Asphalt
a756c9a4-d6fc-445e-b501-95a767dd4d83 | section | 1. Referenced Documentation
8706a4a2-dab2-41c6-980e-cceb062c6ee3 | checkpoint-no-value | Referenced Documentation
32d282da-a047-508e-85dc-68c2d6ec6e14 | note | Document Title: ITP-300-CIV-ADL- Hot Mix Asphalt
cabb1f01-81e8-595f-9820-1093bb81554a | note | ITP Description: ADL-Hot Mix - Asphalt
4a5b0748-5208-52fb-bb5b-2b076823a732 | note | Discipline (e.g. CIV/STR/RAIL): 300-CIV
67059bae-2cbf-5334-99fd-e437ff902da5 | note | Revision Number: 0
ed1bc311-ab2c-5827-89d6-392a7b09e1ab | note | Revision Date: 7/08/2025
47001e78-68b9-509d-9a73-2c87dabbe38b | note | ITP created by: Tyler Alphonso
c4e969e0-e16d-5dab-a023-48be67cfef9b | note | ITP approved for use by: Romualdo Magpantay
781ee0a8-2700-53d2-9613-23325391c74f | note | 1.1 - Non Dependent
b206c9a3-77ef-53b6-ab2d-0bdaab4b4067 | note | Reference - VR 407 - July 2022
b4b27a0a-d7ab-5e31-8a95-e6fefb47a1a5 | note | 1.2 - Non Dependent
c2c611db-0ec4-5ddc-94d2-1d65335c825a | note | Reference - VR 173 - Oct 2008
6606cbe3-f3a2-4057-99da-a55314db6b63 | section | 2. Preliminaries - Materials
0d20a53e-ec52-4b64-b646-4d5744b1d27d | checkpoint | 2.1 - Mix Design
023cd987-a6b0-5229-9ff4-c8624ace42d7 | note | Reference - VR 407.09
2b4adac1-9e34-530b-841e-0202f30ffcdc | note | Acceptance Criteria - All asphalt mixes proposed for use in the works shall have a mix design registered by Department of Transport as ‘General’, unless otherwise approved by the Department of Transport. The registration for all mixes incorporated into the works shall be current at the time of their use.
98fd23fa-ae7f-5fdf-87d7-a2d94485cb13 | textbox | Enter: Teambinder Approval number
750e2b57-e619-5829-a7d7-0a0868747153 | note | Method - Document Review
9bd6d0a3-295e-570c-95bd-a748c98c84b4 | note | Frequency - Each Mix
89bd5acc-2a89-5789-87d8-8b0be3944117 | note | Category - HP
4d7f8e5b-eafa-539e-9363-730b64f91c62 | note | Responsibility - PE/Nominated authority
a8afd216-f8b3-58af-b135-b33eeb0f5be6 | note | Verifying Documents - This ITP, TeamBinder Approval
54131fda-d8d7-5c57-a87e-02562ec93f04 | date | Date Completed:
9fcbde68-17ae-42b8-a410-8a84881012ff | signoff | AUTHORITY HOLDPOINT
205c18b3-870f-4c40-83d7-5a0e428789d6 | checkpoint | 2.2 - Bituminous Materials-Tack Coat
ec9a046c-a33b-5dbd-9a50-9068304519b9 | note | Reference - VR 407.08 (d)
426c4998-aba1-5d38-ab06-8d0229d57ec3 | note | Acceptance Criteria - Tack coat shall consist of a bituminous based binder.
f8cbd17c-373c-5748-abea-3300a4f8dbac | note | ○ Only trackless tack coat or a tack coat application system that prevents pickup of the tack coat must be used.
584ae20f-f1ad-5abb-8ad5-37cf4a8eb621 | note | ○ The Contractor shall submit the details of the trackless tack coat proposed to be used in the works.
d06e1dce-1afe-585d-8257-7a29b70184d7 | textbox | Enter: Teambinder Approval number
39f75e0a-43cc-54f3-84d0-597cc357d5d3 | note | Method - Document Review
01cca8d6-57de-5bad-9c60-60006430eebf | note | Frequency - Each Material
f6a22a92-7949-546e-907b-ae80324a7890 | note | Category - HP
80a397d1-ac91-56e5-af6f-b58cedf22829 | note | Responsibility - PE/Nominated authority
a0b253da-7c92-5353-b697-b84d71b25d5c | note | Verifying Documents - This ITP, TeamBinder Approval
c6d64fa5-4d2b-58ee-bdd4-bdb4e9d77033 | date | Date Completed:
9cf56d43-cc80-44bd-b505-d47082a6aa40 | signoff | AUTHORITY HOLDPOINT
275a7312-2ed1-4adc-90ea-0c548e3832de | section | 3. Preliminaries - Procedures & Documentation
ad7f5d73-7918-409c-8d0d-5091195f8064 | checkpoint | 3.1 - Asphalt Quality Plan
e2ba6177-8a0e-586d-adfd-14d647b59126 | note | Reference - VR 407.04, VR 407.11
631e9b82-9189-5843-a1bf-16ebd27bc200 | note | Acceptance Criteria - the Contractor shall provide an asphalt quality plan that addresses the following requirements:
3daf754f-4da4-50de-8ff9-58d8a49712ca | note | — RAP Management plan (Approved by DTP)
88f94242-b982-589f-a0bd-c8e0aeae2431 | note | — asphalt loading and transportation to minimise segregation and achieve adequate mix temperature on delivery to site
c7ee6c02-915e-5523-9f29-a57b5326d8ea | note | — measuring and recording of pavement temperature, wind speed and weather conditions
7db70449-a8ac-54df-9502-67ca0a2d118b | note | — achieving a uniform application of tack coat
0b2cc465-12d5-536c-8e5c-c58a19d5fdcf | note | — achieving uniform asphalt placement including determination of paving speed and paving plans
162f01ac-fbd9-5e4c-9b13-da41c8903274 | note | — determination of appropriate compaction equipment, number of rollers and rolling patterns required to achieve density
5545c647-3d66-5b16-a64e-822f569a65f6 | note | — procedures to maximise density at joints.
a9f8dc93-c239-54aa-857c-b83e67b3561b | note | ○ Production, storage, discharge and compaction temperature ranges for warm mix asphalt shall be included in the Contractor’s asphalt quality plan.
c2c857a1-b1ea-505b-8c9c-1f1fbb88e77e | textbox | Enter: Teambinder Approval number
529b9091-4abb-527e-89f2-278b1009ec2f | note | Method - Document Review
4e99ff3b-46d9-58b3-85c4-b9ef0ebeeaf2 | note | Frequency - Each Lot
2ae8a53f-9e55-52f0-af09-0c6b0b3dc081 | note | Category - HP
4e1b3d2c-0a1d-54d1-8d43-bdbf4685fd7a | note | Responsibility - PE/Nominated authority
9eed097b-b0a2-55d3-afe3-f76191f0dc63 | note | Verifying Documents - This ITP, TeamBinder Approval
369438f7-ce02-5239-93c0-efe40c360552 | date | Date Completed:
51cac56c-fa42-46d6-84a4-2bf763513d61 | signoff | AUTHORITY HOLDPOINT
a3785eef-8bfb-4424-8e86-b9a2a586d438 | checkpoint | 3.2 - RAP Management Plan
820b4360-fb52-558e-a3bf-afc46194e2cd | note | Reference - VR 407.13 (f)
87c0f032-8fd0-541d-aff2-7210f68a0433 | note | Acceptance Criteria - No asphalt containing RAP shall be supplied until the Department of Transport approved RAP Management Plan has been submitted at least 14 days prior to the asphalt works commencing and approval to proceed is given by the Superintendent.
afa278c8-d835-5945-a5b6-9b50d622812b | textbox | Enter: Teambinder Approval number
7165dbac-5d8c-505b-a39c-6d17b0f0b2fd | note | Method - Document Review
d4c04a00-7e82-525b-82f9-3cc871859223 | note | Frequency - Each Lot
d2b32c96-2d81-51e1-9835-d1aad45f1c09 | note | Category - HP
7164af26-f90a-52ec-bdb7-7cf3ac426dd6 | note | Responsibility - PE/Nominated authority
2ca6e723-3da6-5e2e-ad72-5b628c881ea7 | note | Verifying Documents - This ITP, TeamBinder Approval
864dc735-c39f-5373-b3ba-0ad47e78d4a6 | date | Date Completed:
6789d441-bcde-42fa-9e27-fefa007c4f4b | signoff | AUTHORITY HOLDPOINT
1b2bad9e-cd68-44e0-8b67-f6855ca984de | checkpoint | 3.3 - Cold weather placement
8f8cee22-2b92-5ea0-944b-34bf8a21bb18 | note | Reference - VR 407.17 (b)
5f61af6f-04dc-5e8d-bdf7-e4374ed5d798 | note | Acceptance Criteria - Where approved by the Superintendent placement of dense graded asphalt in layers 35 mm or greater may take place at pavement temperatures up to 5ºC below the minimum temperatures specified in Table 407.171.
a09184f8-70ca-5661-a893-2602434d327c | note | ○ Prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review.
5f68173c-a2f0-5335-9d5f-77b1e3cf6f35 | textbox | Enter: Teambinder Approval number
1b9f6df0-7f9c-5453-90df-b09493af65ab | note | Method - Document Review
70d48eb4-cfb0-51ed-9b62-313e1189840c | note | Frequency - Each Lot
b6b50b2b-e7b1-5f2b-8b64-d7b8385be772 | note | Category - HP
cea19f6a-9f50-51b3-a9b0-4f45bc78c7d6 | note | Responsibility - PE/Nominated authority
bc96e0d3-cb3b-51bc-9b63-0fedec989a2e | note | Verifying Documents - This ITP, TeamBinder Approval
0961db73-642e-512b-bc12-632f1b07807a | date | Date Completed:
0e4ad2bd-da8e-4556-9b52-ca0a003bb3d4 | signoff | AUTHORITY HOLDPOINT
dbaf5273-7a40-415f-a817-3c010baf6726 | section | 4. Pre-construction Activities
60cf4b48-f01e-4d8f-bedf-bd5c15df2e96 | checkpoint | 4.1 - IFC Drawings
cb3c5efc-a4f7-55d6-b813-e7da6a4edd5a | note | Reference - MRPA Quality Management Plan
1b4aa64a-f70f-5c19-928a-fecff3f223c8 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
37112a2a-6d9b-5d74-84ac-f85eb2f1e7e7 | note | Method - Document Review
c2c1f70f-e1ee-58e7-95b4-708f988ab8e7 | note | Frequency - Prior to starting Works and at regular intervals
46886ce9-efb7-594b-986c-9892f4197cef | note | Category - HP*
06b936d4-0cfc-5267-82f3-8f41ba149929 | note | Responsibility - PE/SE
f09e13ea-b069-52a7-899f-8649ed63b9c1 | note | Verifying Documents - This ITP
d6ddde4d-fb03-53b9-9c31-930b1885f867 | date | Date Completed:
3035d808-fd71-4ed2-a757-a67e86997297 | checkpoint | 4.2 - Lot Map-and Lot size
8402612d-12cf-5929-8c69-9bd18d329bfb | note | Reference - VR 407.21 (a), VR 407.27 (b) (i)
b5c975ca-806d-5750-aaa3-ada908a99677 | note | Acceptance Criteria - A lot presented for testing shall consist of an asphalt layer which is placed in one shift under uniform conditions and is essentially homogeneous in respect to placement methods, materials and appearance.
4cee68f3-494a-5da6-8118-3cb134618193 | note | ○ The location of all joints shall be planned prior commencement to achieve the specified offsets between layers and the position of joints in the wearing course.
a526de68-6c5e-5eca-b9f6-1b13f05179c7 | note | ○ ATTACH: Lot Map with planned location of Joints
003dcce1-a299-51ca-83a5-7a06d5cf3c59 | note | Method - Document review
c107fb44-50dd-5048-9851-d091fea5dd95 | note | Frequency - Each Lot
2d8ce000-55de-5f81-92d2-ab7a48248e90 | note | Category - HP*
ac7ef76c-11e0-5540-a63b-9f1f0521414a | note | Responsibility - PE/SE
dba371bd-b3c0-521c-b5e1-804afd75e6af | note | Verifying Documents - attached Lot Map
34effb79-fe25-52d7-beea-7608bec7b5f0 | date | Date Completed:
431ed5e7-2eab-4ffe-bbdf-b35b5f6cd960 | section | 5. Construction Activities
9f9d0a06-3521-4d9e-8c91-aee9b9f9846d | checkpoint | 5.1 - Ambient Conditions-Surface conditions
dfd5613d-3e23-5d8d-bdba-8028ffb76fcd | note | Reference - VR 407.17 (a), VR 407.18
23624ddb-98b2-5311-ac51-25aa23e8333a | note | Acceptance Criteria - The surface on which asphalt is to be placed shall be essentially dry and free from surface water. Asphalt shall not be placed when the pavement surface is wet, or rain is imminent.
94b0f060-0cf6-5fff-832a-da043bde30a7 | note | ○ The Contractor shall remove all loose and deleterious material and sweep clean the area upon which asphalt is to be placed.
054e1573-6fdb-5a2d-82c3-72fd09acfc24 | note | Method - Visual
b61f8f49-3124-59cc-bf0e-8fbd76540728 | note | Frequency - Each Lot
fa791afa-472e-5ebc-8f23-06ed12aad7f3 | note | Category - IP
8d47e877-8a1f-58a3-8fb0-2cdc702952d0 | note | Responsibility - PE/SE
8d92f234-5cea-5e77-9e07-bc1b553198ac | note | Verifying Documents - This ITP
9ee67d77-7094-525c-a74e-f810ef5b32da | date | Date Completed:
449f4fe6-0e6b-43a5-a1de-df3ba67bc63b | checkpoint | 5.2 - Ambient Conditions-Surface Temperature
00aa904c-8d91-5fb0-b4e3-81244d630fa9 | note | Reference - VR 407.17 (a)
0728db2b-9542-5ed6-87a5-99bf1b4a1c33 | note | Acceptance Criteria - Asphalt shall not be placed when the majority of the area to be paved has a surface temperature less than that detailed in Table 407.171 and as below:
08cb2670-0390-5781-8deb-a2b045cdea25 | note | ○ Specified binder class of C170 or C320:
2d77627b-0791-552b-9929-1cd80f8db616 | note | — Wearing course: 10°C
973ccbeb-b943-59c5-bf90-c15636f424d1 | note | — Other courses: 5°C
5e036527-7ffb-5253-9c8e-d77f0bd7a111 | note | ○ Specified binder class of C600 or containing a PMB:
c5160391-97ee-53b8-ae0e-cdb9d3519f9f | note | — Wearing Course 15°C
acd8a903-f8eb-54a4-8a19-00d153d12ab8 | note | — Other courses 10°C
1ccf37e1-09b7-583d-abd3-beffed8ed692 | note | Method - Measure
ce7952c0-2870-5e39-a00b-645ea7bb3e64 | note | Frequency - Each Lot
3673cc80-183a-52ae-a7e0-3910d7981d58 | note | Category - IP
8367d83a-50ee-5be6-882e-4e6894dd8718 | note | Responsibility - PE/SE
2c507f62-455a-5795-b90f-247e7d698f45 | note | Verifying Documents - This ITP
85957fb4-1d6f-5959-a3a9-0334e9638f87 | date | Date Completed:
61179383-42f4-45a0-bf08-dff10565017a | checkpoint | 5.3 - Joints and Junctions-Layer by Layer-Transverse Joints
0fcd5708-0edc-5583-9c94-18183b35c0fb | note | Reference - VR 407.21 (b)
b9eb0d71-0312-5213-b969-b2e5f16b19cf | note | Acceptance Criteria - Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
b34286fd-b980-5aa3-8b7a-e6573b571518 | note | ○ All transverse joints shall be offset from layer to layer by not less than 2 m.
80b7dd76-1df7-52d0-b546-076595eca00e | note | Method - Visual, Measure
f9ea6ae9-6c3e-5995-bd66-729a398988b0 | note | Frequency - Each Lot
67752e01-dbcc-5d35-836e-aa5feebc2925 | note | Category - IP
9927ccb6-4017-5231-9c27-696d027943f4 | note | Responsibility - PE/SE
073e14bf-00c2-52de-a042-bfc3b18eff53 | note | Verifying Documents - This ITP
fb8b80dd-2316-50d5-a7ae-b90f43e4d7de | date | Date Completed:
3f966e44-5ccb-4dc7-8468-eac068bdd50d | checkpoint | 5.4 - Joints and Junctions-Layer by Layer-Longitudinal Joints
5e2d5133-a925-53aa-b213-caa482f36fa2 | note | Reference - VR 407.21 (c)
16399ce9-05a0-5786-aa17-64229774ac4b | note | Acceptance Criteria - Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
793219ac-8cea-5fbb-a74c-900cb177f3d8 | note | ○ Longitudinal joints in the wearing course shall coincide with the location of intended traffic lane lines.
78462f72-da62-50c7-8478-ebbfc3f68a8d | note | ○ Longitudinal joints shall be parallel to the traffic lanes.
617b94dd-1b36-53b7-9b26-aaec3dd9f9ac | note | ○ Longitudinal joints in intermediate and base courses shall be offset from layer to layer by not less than 150 mm and shall be within 300 mm of the traffic lane line or the centre of traffic lane.
2ee80e10-7595-5b65-9376-ba27b529fe12 | note | Method - Visual, Measure
2aefdc08-79cb-5819-9cee-1dcd04a0cf88 | note | Frequency - Each Lot
ac57701f-3fc7-586a-a8a1-c784d10c8eee | note | Category - IP
d45a94dc-1fdc-53fc-b09a-620333ad7cbe | note | Responsibility - PE/SE
d17264f3-2654-5115-b771-4383814c583a | note | Verifying Documents - This ITP
dd87ad66-ce01-5d16-923d-3fd957879907 | date | Date Completed:
788169da-3303-4a85-b56a-0e7ad506c615 | checkpoint | 5.5 - Joints and Junctions-Abutting existing pavement
dcf25a9a-55ea-5e9c-bcbd-9d868a87dfde | note | Reference - VR 407.21 (c)
4cf67395-ad7f-5dfd-a795-f75ec17382a1 | note | Acceptance Criteria - Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm.
878de885-8089-5cd0-86c3-a96173a73564 | note | ○ At the wearing surface where the new and existing pavement join, a hot applied bituminous crack sealant shall be applied.
28736828-dcbd-50df-9c11-1da9355b4956 | note | Method - Visual, Measure
4ad2c396-e790-56d6-b1d7-5e0a9f938da2 | note | Frequency - Where applicable
a9ae4fef-c731-565e-81f1-9f47fbbdb63c | note | Category - IP
bf935dbe-2dc4-5927-8e63-e05153eb30c0 | note | Responsibility - PE/SE
e4cdbeb5-dc61-5e2d-827e-1246b87fb0f7 | note | Verifying Documents - This ITP
47723eec-389f-5d5e-af3c-ea2c147de675 | date | Date Completed:
48771303-05da-4b04-87d3-436f1adbd14e | checkpoint | 5.6 - Joints and Junctions-Junctions at limits of works
bbe8b476-4709-5d61-a9ad-f5705f974a69 | note | Reference - VR 407.21 (d), VR 402
fc760bd0-43b5-555c-a8eb-0b734088f941 | note | Acceptance Criteria - At junctions where the new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planing as specified in Section 402.
34ebff03-67fe-5cb9-806c-45aa71490f3f | note | ○ The chase shall be cut by removal of a wedge of asphalt tapering from zero to a depth of 2.5 times the nominal size of the asphalt from the existing pavement to the minimum length as follows:
4cd4e413-9532-577a-bffb-1fb500ace14a | note | (i) at side streets and median openings – 600 mm
cc561426-d758-5e2e-b65e-d8176c8157f5 | note | (ii) on through carriageways with a speed limit of 80 km/h or less – 3 m
5697433b-0a0c-57e6-87b8-828d7a1fdfbe | note | (iii) on through carriageways with a speed limit of more than 80 km/h – 6 m.
a6f219cd-d64b-5ecb-a0b8-f7a51c08bced | note | Method - Visual, Measure
f128c150-bf4a-5074-a912-dcac8bba7944 | note | Frequency - Where applicable
ad9d3aba-773a-520a-93a3-d13984f4c846 | note | Category - IP
b2c0053f-66cf-56d7-99b1-d90d165f9c3d | note | Responsibility - PE/SE
a06fab1c-21d1-51e6-9498-d2cba1620544 | note | Verifying Documents - This ITP
ef7d45d9-656b-5f51-a172-c4a21e47f7bd | date | Date Completed:
42884b36-c27e-4c16-ac6b-32914d6437f1 | checkpoint | 5.7 - Application of Tack Coat
35ac715a-3771-5655-9c06-b044cb0f3694 | note | Reference - VR 407.19
5a7776c9-dd9b-5b89-9d58-95ac24ba7a5c | note | Acceptance Criteria - A tack coat shall be applied to all asphalt, concrete or sprayed seals on which asphalt is to be placed.
698c2a3b-1a0d-5fdf-9a10-ccaff9d19b46 | note | ○ The application rate for the tack coat shall be 0.15 to 0.30 L/m2 of residual bitumen
89ec2dd8-5846-5f94-8989-4f0ba286cf65 | note | ○ For joints and chases rates shall be doubled.
df0939a8-a953-580a-a2dc-85ecb5eecdb4 | note | ○ The Contractor may omit the tack coat where asphalt is to be spread over
941fdb60-ef36-5a5c-9207-79a328cd531e | note | — A clean, un-trafficked, freshly laid asphalt, or
46f9bcce-404b-5185-9da6-d6bf83395e1a | note | — A clean primed surface, or
1529f107-89b8-5ef7-bee9-4db3acbc2565 | note | — Granular material where the overall asphalt depth is 150mm or greater.
2995210c-7a6d-5bc9-973f-a09657fe8c24 | note | ○ PHOTOGRAPHIC EVIDENCE shall be supplied to show that tack has been applied.
5cdc2bfb-70dc-5970-a59c-d140c7f5cedd | note | ○ ATTACH: Photographic Evidence
ff0a68d5-623d-570d-ba84-8afec6274462 | note | Method - Visual
016b0701-1764-5388-be63-087e41df2335 | note | Frequency - Where applicable
c7c7439b-9a5f-56ba-b499-5f77ff80c0df | note | Category - SP
1d819d8c-a390-5b26-808d-954f26d5cc70 | note | Responsibility - PE/SE
3ce141ee-5366-53e0-9c2b-a6da5e216d5b | note | Verifying Documents - This ITP
66de6976-5de1-5605-b5b3-43ca663e7015 | date | Date Completed:
87daa021-47ec-43c7-8722-ef0ae063a96e | checkpoint | 5.8 - Joints and Junctions
bbeeb0ff-2490-557a-8196-c7419af4f609 | note | Reference - VR 407.21 (a)
eb9056a8-03ef-5da9-94b0-0d7a550885ff | note | Acceptance Criteria - All joints shall be well bonded and sealed
29585c31-b16f-56ec-9553-c0ec1b6ef76f | note | ○ All cold joints and abutting concrete edges shall be tack coated
74abe5f6-112d-5d00-8fd2-138ed4e20651 | note | Method - Visual
52192bc4-9460-5e58-b369-184493515e7c | note | Frequency - Where applicable
d9851c87-c40a-573e-ae55-3dbf640fcd8e | note | Category - SP
42e4401c-b8f5-5cd5-a593-9f2c476d15b6 | note | Responsibility - PE/SE
54d79946-2e11-5cec-986d-ff7f2ca470d6 | note | Verifying Documents - This ITP
606e0107-d1a8-5b98-b929-a7e518f1dc10 | date | Date Completed:
8d0be222-4806-4d33-bad3-d14a62a52c5e | checkpoint | 5.9 - Delivery Dockets
b22b47e9-1dc0-5869-8aa2-c878d833e62c | note | Reference - VR 407.20
c356888f-433e-54bf-9be5-8819b307cc2a | note | Acceptance Criteria - Asphalt delivered to the site, which is segregated, has been overheated, is too cold, contains separated binder, uncoated particles or which does not comply with the Specification shall be removed from the site.
9217564f-c714-5e7f-985c-afaf754a60f1 | note | ○ Maximum Asphalt temperature at discharge from the plant is 175°C
6982d2dd-f568-5de3-9140-8cd61b4c2005 | note | ○ ATTACH: Mix Delivery Docket3
1f139656-4000-52cd-a263-45e3e07780ae | note | Method - Document review
260e06e4-949e-54bf-9dc5-209b2092330d | note | Frequency - Each Lot
63943f16-1457-58e4-b983-2e5084307c3a | note | Category - IP
c4a4bf19-43fe-5c19-8823-3154e5a6b3d3 | note | Responsibility - PE/SE
154c5baf-448e-5057-a224-4a6ac6fb3f9d | note | Verifying Documents - This ITP
4498e6e1-a156-5c46-8305-0282173a8b9d | date | Date Completed:
fccbc893-1190-48be-a1ee-0cc855060dec | checkpoint | 5.10 - Commencement of Placement
0ba905f6-acaf-5384-9b63-ab2e8403a526 | note | Reference - VR 407.23
9e268b8d-f74c-50b8-b5e3-0ac0abbc3039 | note | Acceptance Criteria - The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from the Superintendent.
1404b53e-7187-5018-abd3-d32aab219bae | note | Method - Visual
ca23ec18-c3bf-5d0d-b24e-f41e55306bed | note | Frequency - Each Lot
5b05db25-cf0e-565d-b3b5-b582153a68df | note | Category - HP
1d80ff0b-f4c8-5da9-b7e3-487628ddfd58 | note | Responsibility - SE/Nominated authority
d15f9228-c774-5cd7-813a-95826f6f04e7 | note | Verifying Documents - This ITP
f5db294b-76f2-581d-9de0-6d664c15c523 | date | Date Completed:
283f7160-5097-4f27-b1e7-f9745fda1d1d | signoff | AUTHORITY HOLDPOINT
4694e23f-b426-4636-8be0-fa5ac55f5305 | checkpoint | 5.11 - Paving of Asphalt
cd63bbc0-b29b-5a43-9b16-7f708ebb1dbe | note | Reference - VR 407.25
61fee9d9-93cd-5297-bc1b-b8100ac613d0 | note | Acceptance Criteria - Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings.
4d9642d7-48de-5278-a6ad-04f26c7ac561 | note | ○ All asphalt shall be spread with paving machine (or by hand if not accessible by Paver) to form a smooth asphalt mat without segregation, tearing or gouging.
7daf2ea6-43c9-5123-9cab-62d40f6e9de8 | note | Method - Visual
a359b01e-c4aa-5a07-b90b-71d76469466e | note | Frequency - Each Lot
b2cc3b5b-7feb-5069-8fda-90221c424246 | note | Category - SP
8330ea2b-6f56-56a1-aaf2-002517b44113 | note | Responsibility - SE/PE
8546e5c6-732e-5da2-a874-5f217dc98e5a | note | Verifying Documents - This ITP
52133045-9712-519d-b6e9-f3865cf66d72 | date | Date Completed:
89a0e0e8-45f6-45ee-9c0d-7adf2e9da22b | checkpoint | 5.12 - Paving of Asphalt
e7a10f67-4433-5dbc-a56b-6aa14cfc0b78 | note | Reference - VR 407.25
63655576-13b6-5156-9529-8b965502263d | note | Acceptance Criteria - If the paver is required to stop and asphalt in front of the screed cools to below 120°C, a transverse joint shall be constructed.
924adaa4-1879-58b9-a30d-75875f2637b1 | note | Method - Measure
58f57ab2-92f0-5e18-a4a0-5fece4dd4df0 | note | Frequency - Where applicable
c29fe8a1-0567-5b71-8b0b-ca9562162c26 | note | Category - IP
3c7cbe6a-482a-5ac0-b6a5-e1076f22b580 | note | Responsibility - SE
93ad02ba-a033-5af4-9d84-44eeb6c1297a | note | Verifying Documents - This ITP
a26f1351-ea8a-5561-b838-bc3449760ccb | date | Date Completed:
a2ff29f7-0cfc-4030-8cf1-ed0916f9428d | checkpoint | 5.13 - Compaction
ccfe0fe8-bee9-5ad3-974d-b7e30fa882ba | note | Reference - VR 407.26
d339a36a-82b9-5b59-a1aa-b0747ebbf1bf | note | Acceptance Criteria - Asphalt shall be uniformly . Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement.
e4eee921-8011-53dc-8f09-5156bd65a9dc | note | ○ Vibratory rolling shall not be used to compact asphalt on bridge decks.
88e55139-2287-504b-ba2d-af76669ecb3d | note | Method - Visual
e697a396-6ad1-5cf4-80e4-dde56f61d886 | note | Frequency - Each Lot
3225fdcd-b938-50ee-9e03-7f3455a6ab94 | note | Category - SP
05744ec8-bf35-55f0-914a-0028b859fe57 | note | Responsibility - SE
2b500683-45b7-5dcf-a6ff-13fffebe7497 | note | Verifying Documents - This ITP
f9b83059-de1f-5fa1-988f-f7775e3ac3e8 | date | Date Completed:
faed4b04-ea54-41d1-91a3-68a92750c83f | section | 6. Post-construction Activities
169283d4-b159-4bb5-bab7-ccaa26cdce91 | checkpoint | 6.1 - Compaction test-Lots larger than 500 sqm
1f26d953-bd59-5d2b-9a5e-9afdd1028c25 | note | Reference - VR 407.27 (b) (i)
fe0329dd-d726-5f11-9c92-c03921460c57 | note | Acceptance Criteria - The work (excluding longitudinal edge strips) represented by a lot of six tests shall be assessed as shown in Table 407.271.
e4f2267a-8c18-5250-b495-17b425795e40 | note | ○ For lots exceeding 500 m2 density testing of the longitudinal edge strips (200 mm from the longitudinal joint) for the wearing course shall be undertaken and results reported as a separate lot.
a3976bab-e508-56f8-99bf-56d4835bca2b | note | ○ The Characteristic Value of the Density Ratio determined for the longitudinal edge strips within the lot shall be submitted for report only
fbc57e48-4f77-5235-a1dc-a47cb9c5aeac | note | ○ ATTACH: Compaction test report
831805e0-6939-5d5d-9bf9-5b2a9fc7e4ea | note | ○ ATTACH: Wearing course joint strip compaction test results
8be0793d-7574-543f-b595-641d71954299 | note | Method - Document Review
e1d7cfa7-bd18-5d07-8cb4-c8722eaa924b | note | Frequency - Each Lot Where Applicable
1b2cc688-3b43-50da-9fff-93aba8ee3af5 | note | Category - HP
03f04a79-9952-59c6-8dd3-797a3811e6d4 | note | Responsibility - Nominated authority
5af8030b-47af-5284-8e7b-c325504599b9 | note | Verifying Documents - This ITP
c5d8b689-f7db-5458-984d-19d6a38d5717 | date | Date Completed:
8e6ee053-4203-41be-86cc-866076f5f7df | signoff | AUTHORITY HOLDPOINT
14b9efba-35a8-4ea9-be7e-e80dd5cf7402 | checkpoint | 6.2 - Compaction test frequency-Lots smaller than 500 sqm
f128c6ad-ff18-5d4a-a375-8ae48440b257 | note | Reference - VR 407.27 (b) (ii), VR 173.04 (d)
63ee30d4-8961-56a2-aa7a-fd957b244098 | note | Acceptance Criteria - acceptance of the lot shall be based on the mean values of 3 individual tests. The lot will be accepted if the mean value of the individual tests exceeds by 2.0% or more the appropriate compaction scale requirement for the characteristic value of density ratio for a lot of six tests.
89fea52c-e152-57b0-9110-2ad7849d703e | note | ○ ATTACH: Compaction test results
0e376a04-3073-5569-91fb-43084ba79f74 | note | Method - Document Review
c789c625-afa0-54d9-849c-fa86d899c7b0 | note | Frequency - Each Lot Where Applicable
fa38217c-b348-5a1a-aa34-3652a15004cd | note | Category - HP
da70c7b4-2579-5f3c-8b84-0cc920b72c45 | note | Responsibility - Nominated authority
c689dce1-4842-56fa-8e70-bd4bbd67b588 | note | Verifying Documents - This ITP
7453ba6a-b9fd-51e8-a48a-ad231f8d004e | date | Date Completed:
c18c77f8-0ecb-4e7c-b5eb-dfdec53756f6 | signoff | AUTHORITY HOLDPOINT
16b3e05f-5b07-4888-8ebe-df69ccd554bc | checkpoint | 6.3 - Surface finish and conformity with drawings-Surface Finish and shape
2e47cfdb-94e2-5f4d-a2b7-1092abc451ed | note | Reference - VR 407.29 (a) (i), VR 407.29 (a) (ii), VR 407.29 (a) (iii)
156b6e7d-9ef1-5c85-aacf-566d8cd4a94d | note | Acceptance Criteria - The finished surface of any asphalt course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks.
62f2723f-e60c-5a3a-a8ec-42906ea0b293 | note | ○ No point on the finished surface of the wearing course:
9d3bfeec-8c5f-5e93-8970-e99080404bd2 | note | — shall lie more than 4 mm below a 3 m straight edge
4845751d-fbf4-5663-9107-62d2fb49d517 | note | ○ For intermediate and base course layers:
f2524afd-631b-565f-b51f-31db47113377 | note | — the distance below the straight edge shall not exceed 6 mm and 10 mm respectively.
a417d689-c241-5562-80ee-e6dfc45b599b | note | ○ Where asphalt is placed against kerb and channel the surface at the edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel
dc0b672d-1203-5af5-a178-48680a6135e2 | note | Method - Measure
c89f0ed6-f355-543b-a892-1471795c937c | note | Frequency - Each Lot Where Applicable
506de518-6c54-50a4-803a-62b834633170 | note | Category - IP
08e4f759-b4a4-5290-b7ad-f53b7568b95e | note | Responsibility - SE/PE
784ae513-b161-55ff-8687-3c3d77ae4e52 | note | Verifying Documents - This ITP
103c93a3-f0d4-59d8-801f-9d274d59456f | date | Date Completed:
b6db2b06-d2a1-466c-95ea-eb06d405cf37 | checkpoint | 6.4 - Surface finish and conformity with drawings-Alignment and width
5e866c02-97b6-569c-84a9-8a923e87ec35 | note | Reference - VR 407.29 (a) (iv), VR 407.29 (a) (v)
905502c0-15d4-5d3c-9cdf-df0fa4866e3f | note | Acceptance Criteria - Where asphalt pavement is not placed against a concrete edging:
5f262d2f-2ccb-50f1-86ab-d7f15ce7e7c0 | note | ○ the edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside,from design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25 mm in 10 m.
fb8149fc-ac51-5fb0-9413-c4c135ee101d | note | ○ the width of asphalt layers shall not be less than the design more than 50 mm or greater than the design by more than 100 mm. The average width over any 300 m shall not be less than the design.
89a585ca-c1a5-5cd6-b16b-020d30823858 | note | Method - Measure
401d9d4b-1486-51fe-89b4-52b8bff0bc9a | note | Frequency - Each Lot Where Applicable
48fa92a0-c666-53b7-82f7-4ee6e0b52874 | note | Category - IP
9ae18899-e68c-5396-a688-b02c9770795e | note | Responsibility - Surveyor/SE/PE
00659efe-382c-5a47-bec8-8b4dd6a92aa7 | note | Verifying Documents - This ITP
4763ced3-fa27-5e79-9b75-9102474c710a | date | Date Completed:
21d6c09f-e12c-44ff-86be-69e2e4263d8c | checkpoint | 6.5 - Conformity with drawings-Scale A and Scale B
7025db89-6ca7-5e79-acd0-15363941ab34 | note | Reference - VR 407.29 (b) (i), VR 407.292, VR 407.293, VR 173.05
fdb370b4-0cbe-5889-bc04-b3b3616e115f | note | Acceptance Criteria - the surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.05
319d9b8c-927f-553d-bb2a-e1342b898f1d | note | ○ Number of measurements and acceptable tolerances are to be as per tables VR 407.292 and VR 407.293
b290344a-534b-5b90-8318-c6ed1f3565c2 | note | Method - Measure
90c208e3-eae2-5493-b936-c2377bece22d | note | Frequency - Each Lot Where Applicable
6f6f97af-caea-5a6c-b690-ff8bb81db3d9 | note | Category - IP
5136677a-c583-5b1f-94fd-774ff6fc0fcc | note | Responsibility - Surveyor/SE/PE
19337138-d97c-5210-a57b-b73cad840e20 | note | Verifying Documents - This ITP
e93f306d-e083-5ce4-8107-390dfa22a6ff | date | Date Completed:
155c95f5-d477-42dd-bd1d-8f212854ac2b | checkpoint | 6.6 - Conformity with drawings-Scale C
381e2030-160d-537e-bea1-cf8939df716f | note | Reference - VR 407.29 (b) (ii), VR 173.06 (c), VR 173.06 (d)
b7e8efc3-ada1-5e29-9a20-edaf5e87a336 | note | Acceptance Criteria - the surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.06
ef40a135-615b-54f9-8b88-3d717c4dad93 | note | ○ The level of the top of each asphalt course shall not differ from the specified level by more than 15 mm for intermediate and base courses and 10 mm for wearing course.
af256a27-3564-5801-a74d-aec69650113e | note | ○ For the purpose of this clause, the maximum lot size shall not be more than 4,000 m2 of pavement area.
4b3f1584-81f4-582c-880e-9455f1164b7f | note | Method - Measure
40cd026c-fdfa-5da6-b021-458e63e4554b | note | Frequency - Each Lot Where Applicable
73820499-3b64-5207-9925-d1895efc6f43 | note | Category - IP
a859cd6a-ef14-59ea-9eec-f5efaa0d1567 | note | Responsibility - Surveyor/SE/PE
768d225c-5ac7-571f-aad5-6df7f7bbc0ca | note | Verifying Documents - This ITP
45a84b1e-db26-5010-ae34-6d942a6f5bce | date | Date Completed:
475203d7-4924-4e19-bf1f-138e1cce04e2 | checkpoint | Final Inspection
502e35ad-2c05-54aa-91c6-35d09786e062 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
f447b3b0-a50b-586c-b712-483c0ec308d5 | textbox | Name:
730c5339-4832-5ecd-822b-5bb5c66aa1f9 | textbox | Position:
70d5ce70-3429-5f1b-bc78-a0a0348ff9a3 | textbox | Date Completed:
4e7f9a04-f225-472e-a0aa-cba0e5221e9f | signoff | Sign ITP
653201d0-bebe-448c-8979-d973b6964fb5 | checklist | ITP-307-STR-MSS-Bored Piling Rev 0 | itp | ITP-307-STR-MSS-Bored Piling
fadc8327-d98c-4cf3-94b2-b2ec5aee1c67 | section | 1. Referenced Documentation
3b3cc706-22dd-4ac6-a157-2e827191a99d | checkpoint-no-value | Referenced Documentation
b48af03f-d828-5e11-a444-1534e79613c1 | note | Document Title: ITP-307-STR-MSS-Bored Piling
b655fe2b-f1ef-5d2b-bfb5-c40852d8f4fc | note | ITP Description: MSS-Bored Piling
1c16ab7d-656b-554d-899f-47981f1b96b9 | note | Discipline (e.g. CIV/STR/RAIL): 307-STR
beba0483-7c45-5395-af6a-7a59b8ff49e7 | note | Revision Number: 0
61a9551f-2a61-5d5c-900b-b6ab9ef5bf97 | note | Revision Date: 27/08/2025
b52d6e9c-b857-5ea2-b184-adf1ae9cd6ec | note | ITP created by: Andrew Carlini
fb6a5744-62d8-593f-95d1-b10061e984f7 | note | ITP approved for use by: Romualdo Magpantay
623c7b85-413c-5e1b-971c-a4444fa0eb9c | note | 1.1 - Non Dependent
56963743-f072-5387-adb5-00ef6d746117 | note | Reference - DTP Section 606 July 2017
a0b2bd5f-4590-5af0-a3b5-9718b56e8e18 | note | 1.2 - Non Dependent
2b0c129d-6394-5f8a-9499-7f4752067934 | note | Reference - DTP Section 610 Feb 2020
c0a8f06f-5a4d-55f2-88f9-252bc1a02700 | note | 1.3 - Non Dependent
480d6584-29eb-5c42-a6e8-db7911889c3c | note | Reference - DTP Section 611 November 2018
1f99bcbc-9803-57a6-b270-86644011cc8c | note | 1.4 - Non Dependent
b2a02963-a5aa-587a-8cf0-f92cb7178289 | note | Reference - AS2159-2009
4c3d9ab8-a268-589a-97e7-67921358c6c4 | note | 1.5 - Non Dependent
37ff9cc2-7c16-5be7-89cc-fc3a47b04732 | note | Reference - AS3810.1 2018
342b5635-dbcf-5f8c-9c8b-53081316b178 | note | 1.6 - Non Dependent
e4a0fd77-fb9c-582a-ab3b-71d9ab001ec2 | note | Reference - AS5100.3-2017
1636809c-3aab-4a40-a717-67a2da7ff716 | section | 2. Preliminaries - Materials
1966faff-0ee2-400a-b127-aaec1e09f629 | checkpoint | 2.1 - Concrete Mix
f1655c3e-7cba-5d8b-ac84-474fbbc83249 | note | Reference - 610.07 Table 610.071
1a8769f0-5916-50cc-bd5a-1f19fe58d1ff | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
71f9bc3e-8e38-52eb-bca4-b24c12a7e186 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
99fe0163-70b4-5309-9968-ca2995d07b1f | textbox | Enter: Teambinder Material Approval number
76fd0901-fc41-5691-9159-6fd2e457732b | note | Method - Document Review
7c3adcef-51d5-5403-a96f-3bf446b52be5 | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
be79ac3c-83c5-5312-9af1-b7c246a481da | note | Category - HP
16de0310-7caa-5893-a5ca-e608af045d72 | note | Responsibility - Nominated Authority
5296f6dc-78d6-5c57-b339-14821708ae60 | note | Verifying Documents - ConQA Hold Point Release
85a9355a-0a37-513a-979c-af2b680457a8 | date | Date Completed:
2614f42b-fcc2-489f-ad40-33099a6296b9 | signoff | AUTHORITY HOLDPOINT
a1b63b3d-9698-4531-9a2a-9bdfbb400c15 | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
dc46131c-53c3-565b-9483-17a181872599 | note | Reference - 611.05 (a)
baaa1323-56f1-5372-a630-b4d86bcf79c5 | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
d6ec007d-beef-5510-8c39-7549b6d223c3 | note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
a2c69ac4-a793-57cf-9562-cb6b001b3f16 | note | Enter: Teambinder Material Approval number
7bd70eb1-1cb7-5495-9f71-6dc980a5e88c | note | Method - Document Review
6c25d9fd-ffcd-566f-869a-ee91da4b3655 | note | Frequency - Once for each supplier, 14 days of award of contract
68668f2d-aed4-5a15-ab4c-eda6ab17bcf4 | note | Category - HP
bf6e2c54-afba-5e9f-87f4-b2631f696849 | note | Responsibility - Nominated Authority
2f304f91-557f-5e50-862c-48bd04eb4e72 | note | Verifying Documents - This ITP
56345cf2-1b08-57de-b3d0-2aa2fa404202 | date | Date Completed:
279fb4e7-2c38-49d4-9a70-3b38ec420679 | signoff | AUTHORITY HOLDPOINT
1cfb225e-6778-4ae4-95c7-38f1bf11ad70 | checkpoint | 2.3 - Bar Chairs/Aspros/wheels Certification
cb402f25-f95f-5f20-bbfc-2dd37391b32a | note | Reference - 610.26 (a)
d5d99d65-78e7-5d65-bf60-7b2872fba1a5 | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
5fdfe15a-0ad3-5e2c-a8e9-214197e7675e | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
eee4bcdc-2147-56af-aaaa-56be5db89ee4 | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
3604a3bf-a97b-5758-b174-22c255b078b7 | textbox | Enter: Teambinder Material Approval number
9f683a2b-8e53-5da5-94e4-5c6572d28648 | note | Method - Document Review
e2b89865-3779-5394-a21c-0b4d6707313f | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
0ac64c6a-884c-5366-bd0f-4f2adc010eb2 | note | Category - HP
20e11a95-77f6-5511-841e-720e16bb11b9 | note | Responsibility - Nominated Authority
ff1f8104-e7ee-5f68-a4ec-cd1c2aec6da7 | note | Verifying Documents - This ITP
0919a2ec-05ed-5d35-94c0-14a76c819bab | date | Date Completed:
cd5f3b9e-8baa-4d59-b90c-ffba955dd782 | signoff | AUTHORITY HOLDPOINT
9b830049-b5d8-411d-ab2c-7675d728dba0 | section | 3. Preliminaries - Procedures & Documentation
8e4182d7-f983-4627-84ce-d8ad9c7889cc | checkpoint | 3.1 - Working Platform certification
a66da80c-29b4-5caf-adc2-478bd5bba03c | note | Reference -
49a80c46-9a49-569d-9aa8-f85dc92e8393 | note | Acceptance Criteria - Satisfies minimum plant bearing pressures requirement
ee0017dc-7e4a-5ff3-98de-81919d9e34b9 | note | Method - Document Review
ff66b974-3598-5426-bb33-73f35e34f88a | note | Frequency - Prior to works commencing & after rain event which there is >10mm in a 24hr period.
f119b2e9-a447-5e18-9631-b561afe536cd | note | Category - HP
759055c6-2f6c-55c9-a7f0-19a370c83e6e | note | Responsibility - Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
63e68586-f066-562c-b6f3-a62db81bdbe1 | note | Verifying Documents - This ITP
6f19b44a-36b7-5b8c-88c6-2f885b62f2a6 | date | Date Completed:
7c7c2524-b41b-4d7c-a5b3-54c88396b33c | signoff | AUTHORITY HOLDPOINT
9d2a70d4-e1ca-4e8c-a21e-a092a112b089 | checkpoint | 3.2 - Piling Operations Work Procedure
736bbbd9-39b9-50fe-b738-5445b2e0b492 | note | Reference - 606.03 (a)
04032ec6-53da-5a41-9ba2-ac551802b993 | note | Acceptance Criteria - Piling operations work procedure to be submitted for review to the Nominated Authority.
7615bfc5-1b98-5ffd-a749-7c8959c4200e | textbox | Enter: Teambinder Approval number
9b29d4d5-3774-519f-ab55-9e509a7c3887 | note | Method - Document Review
491b2b21-15df-5827-9d46-6c8a10cebff4 | note | Frequency - Once, 4 weeks prior to the commencement of piling
d84fffb4-0ff9-5936-8066-f09c7ad587d6 | note | Category - HP
2a7f8ee4-921d-57b9-b9c4-ac97f5c2a19f | note | Responsibility - Nominated Authority
0d3ead46-fd0d-5336-a7a2-caea67c760be | note | Verifying Documents - ConQA Hold Point Release
2dabe553-76aa-52c0-92b8-4198fac9af87 | date | Date Completed:
d07523ba-be0d-4aba-8ca9-1ab6252e038e | signoff | AUTHORITY HOLDPOINT
a24d1ba0-61f8-49a5-9d26-b655a2c6e01c | checkpoint | 3.3 - Temporary Steel Casings
d8a369de-1b9c-52e4-9262-d62e0a561558 | note | Reference - 606.03 (b)
be167445-9b87-5890-8352-23f86c273f2c | note | Acceptance Criteria - Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
91b40255-37c6-546e-b797-ace57a10f9c7 | note | ○ Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
ca8041bd-70c8-5a39-8f55-80f955ed9fd8 | note | ○ The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
cfc165f2-b301-5a5e-905a-73c679d9e179 | textbox | Enter: Teambinder Approval number
feb200dc-8727-5aa1-804a-18f96c88fc61 | note | Method - Document Review
e7387389-7135-5b5b-9ad7-9d3b3fdf4986 | note | Frequency - Where applicable, once, prior to use
c6d02372-ce7a-5d8e-b0b8-e3e308ca021d | note | Category - HP
c2974f8e-74cf-5209-b6e2-1b1aef7117cf | note | Responsibility - Nominated Authority
8841c5c7-4c38-5ee2-8c7f-730fd2a9eaa7 | note | Verifying Documents - This ITP
ef2f7e8a-779a-53a0-8663-f920f2f4ca19 | date | Date Completed:
75e34917-de73-4090-8312-36629ee53668 | signoff | AUTHORITY HOLDPOINT
41de8ac2-ca61-4b6a-8de2-cc298e34651f | checkpoint | 3.4 - Casting Under Water Procedure
f3d85c1b-86a7-5914-b497-0d3306fd6f54 | note | Reference - 606.06 (a)
ac47c3cf-25c0-53f1-b4dc-2e53efe5f789 | note | Acceptance Criteria - Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
9614f0b7-4490-5ed8-b1fe-d4cb9010eaf7 | textbox | Enter: Teambinder Approval number
fd085706-8bae-5464-b276-a28a5a037742 | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
85717341-0e23-5292-99a6-4670f426ccc8 | note | Method - Document Review
d6600efc-a881-5e4b-8186-0bfd6fd904c2 | note | Frequency - Where applicable, once, prior to placement of concrete
4a933432-80bd-5122-8b8d-d148d4332ca5 | note | Category - HP
d029afc2-a8c0-5706-bf7f-fc9ce9066594 | note | Responsibility - Nominated Authority
93c09432-63f2-5a4d-8614-8d40ab755c5d | note | Verifying Documents - This ITP
2c326999-f0ea-51a6-8de3-56d63cb91f3d | date | Date Completed:
b36bacd0-fe28-46f8-ac13-894e97217dbe | signoff | AUTHORITY HOLDPOINT
9a337fdb-21a2-4054-b236-65ba0fe88fad | checkpoint | 3.5 - Boring With Bentonite or Polymer Fluids
937a9486-c363-5f50-b3b0-b4e2df9f8f36 | note | Reference - 606.03 ( c)
0af15a57-c7c5-5d20-919d-bd9cd0472c70 | note | Acceptance Criteria - Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
22116def-b873-52ca-9f42-6db38411f069 | textbox | Enter: Teambinder Approval number
c0bf4b79-4a7e-5c1f-a0df-0e91fcb1f500 | note | ○ Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
cff970ba-d619-5557-888f-c59fc0aad309 | note | Method - Document Review
ba8e4a10-ea5e-5abe-8b59-fbb17914dc3f | note | Frequency - Where applicable, once, prior to commencement of boring
4682146e-d64d-5f6a-9935-c1cb8701581c | note | Category - HP
cd7bc474-65d2-580b-af86-248bb0bcc585 | note | Responsibility - Nominated Authority
7696f0a3-b363-5595-b39c-de5798326a1b | note | Verifying Documents - This ITP
c6e88247-27ac-59c7-920e-150db3948124 | date | Date Completed:
75a273ea-7563-416c-a47e-e7889439903d | signoff | AUTHORITY HOLDPOINT
d8f87053-1767-4f2f-a2bc-42d6c53b9b98 | checkpoint | 3.6 - Pre-qualified Pile Testing Consultant
8b89c9e1-062a-5121-9610-41df91d6f183 | note | Reference - 606.07
46547f3d-cdc6-5132-b587-82f9b4ec804c | note | Acceptance Criteria - All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
f23c394d-4c42-594f-b835-b448a5f6169d | note | Details of the consultant to be submitted for review to the Nominated Authority.
96296240-1c87-593e-a17e-ec645e1ab4cc | textbox | Enter: Teambinder Approval number
69c823f3-753f-5e5b-8bc9-f4dd04afee7e | note | Method - Document Review
8fea6b00-be8d-5a85-a73e-d4a4eb5d69fa | note | Frequency - Once, two weeks prior to testing
838725de-c063-50e8-8874-b632b4bc2fd9 | note | Category - HP
49e1b6ce-dfda-5d67-95bd-6b7e6a726524 | note | Responsibility - Nominated Authority
e2beaefc-07ec-5a3c-87fc-9f40ba3e1379 | note | Verifying Documents - ConQA Hold Point Release
d45af45b-bb55-5848-86f1-4aa31c42e995 | date | Date Completed:
66295409-0a94-42ba-9d6a-7f2bf4755e80 | signoff | AUTHORITY HOLDPOINT
49d37486-f78f-46f0-816a-1e9145df091c | checkpoint | 3.7 - Reinforcement Welding Specifications & Qualifications
4a900991-a40a-53f5-9568-c2189bca2683 | note | Reference - 611.13 (a), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
b8b1ef15-1210-5049-af8e-3d862023c9db | note | Acceptance Criteria - Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
9996f364-231f-54b0-ae09-79905fc2f57f | textbox | Enter: Teambinder Approval number
05bd11e1-db90-5b86-a3aa-7046d7649024 | note | Method - Document Review
9e5b7135-63a1-5baa-b51f-42c65dc9e5a4 | note | Frequency - Where applicable, once, prior to welding
d395f592-09c0-5fbc-9975-f9dc601da9d1 | note | Category - HP
45937685-e189-51be-a29e-448c4211eba9 | note | Responsibility - Nominated Authority
a33eb8cb-0dec-5914-b7cf-481cb34ca8fa | note | Verifying Documents - ConQA Hold Point Release
ad0e2c06-fc97-5b27-a7b7-0cb307b29c6b | date | Date Completed:
cdad8677-e274-4813-8f22-4780484635a4 | signoff | AUTHORITY HOLDPOINT
86205bad-7e3f-4396-8ce2-e1063be01385 | section | 4. Pre-construction Activities
da9670ee-4661-4718-94a4-1bfaff6c7fae | checkpoint | 4.1 - IFC Drawings
de01ce04-42a8-544f-924a-36b26e385d03 | note | Reference - MRPA Quality Management Plan
1f940b19-46c5-5a3d-b104-a107bdc78ba7 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
cac2f321-3070-592e-9318-e284375125fa | note | Method - Document Review
347bd1a2-0423-51a7-881c-1183f8bcc6b6 | note | Frequency - Prior to starting Works and at regular intervals
c2e94653-51d3-57b0-ad6d-a8173b09aca4 | note | Category - HP*
0e202cb4-9199-5cb8-8430-64f5f61819ae | note | Responsibility - All
5c6d5810-6472-54d0-b3f6-ffefae7fc461 | note | Verifying Documents - This ITP
1c57a517-db65-540d-a1e0-a99a5a141701 | date | Date Completed:
0f0a7f06-e2b6-4820-8145-cf5277301c05 | checkpoint | 4.2 - Survey Set-out
00f77a93-6b68-5215-a85c-22472f25fec5 | note | Reference - IFC Drawings 606.08 (a - c)
7bd702b8-ec24-56a4-8783-b004ecdd6817 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
a8c745fe-efd3-5bc6-9800-f0e8bf33c8d6 | note | ○ Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
f96e980e-70d6-5268-874c-d96052917ef0 | note | Method - Measure, Visual
09a224ee-0d8e-5073-9215-bc840668df2a | note | Frequency - Each pile
7418bdd2-8a2a-516d-8eb3-3803d3feffaf | note | Category - IP
748bc76c-bd9e-54f9-815b-880259ce42fd | note | Responsibility - Surveyor, SE
492e3266-4bc2-531d-83a7-e20a8ed596dd | note | Verifying Documents - This ITP
cb45ea88-6090-5a68-8ac5-2c860180c3f6 | date | Date Completed:
f81c28cd-4159-494b-a6d9-7a3323d59694 | checkpoint | 4.3 - Protection of Adjacent Piles
a2dc802a-4246-5f7a-8980-aaf54d459ecc | note | Reference - 606.04 IFC Drawings
eeccaaa2-df21-597f-aed2-be88fb063fc8 | note | Acceptance Criteria - Pile construction shall not:
fe8d7e3a-0f62-5521-a3ae-4d46e2e6a226 | note | i. result in damage to adjacent newly cast piles due to ground vibration.
a16f3928-e369-5394-b5d5-51afafe97024 | note | ii. commence within 3 piles diameter or 2.5m clear distace(Whichever is greater) from newly cast piles if that pile concrete strength <15MPa
70d7b24b-9eb4-589c-87a2-54a294f0fba5 | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
9ec6f0d3-5417-5d77-9b46-f822b236316c | note | Method - Measure, Visual
e458b3c9-0937-5bb9-9388-d712f1412e0c | note | Frequency - Each pile
c6092f0a-d41d-5841-9040-588a6ecc1048 | note | Category - HP*
7c67d166-a8f3-5764-b810-f0f5827ef222 | note | Responsibility - SPE/PE
0ead32a8-bb98-504e-bdfe-299028d11ff9 | note | Verifying Documents - This ITP
379785fd-4827-5ebc-8ef0-e06acb44a49d | date | Date Completed:
97ffe4ee-2c04-46f4-b0b1-5a0ddaf1e7c3 | section | 5. Construction Activities
31b740c6-bd28-4d8d-aa90-c38082ce7403 | checkpoint | 5.1 - Boring Operations
cf601e3f-7fbc-59d7-97f9-e7f90fdc71ef | note | Reference - IFC Drawings 606.03 (a)
448f39e8-a6eb-5e41-bd6c-822647a95b9f | note | Acceptance Criteria - Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
fd380a33-22ba-5f07-bd63-fea6ca5f600a | note | ○ Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
4ab8d814-110f-55a4-93c9-1f42db82238e | note | ○ Excavation clean and de-watered (where applicable) for inspection.
3bc4d9dd-76bf-5d0d-8dea-c3eec2f7e28a | note | ○ Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
5cae9cde-6cc3-5663-8440-ce2a21f4b896 | note | ○ Excavated material to be disposed of as appropriate to maintain a clean site.
d7e8fd78-e5de-5846-b205-493c6025439b | note | Method - Measure, Visual
56578fbe-648f-5e47-9894-292406c36352 | note | Frequency - Each pile
1eded23d-34a4-51b0-911c-5c5b2b2a58ac | note | Category - IP
c25c1312-78e7-5c4c-aa91-f52d57015da7 | note | Responsibility - Surveyor, SE/PE/SPE
727838cf-5f88-58a5-a92b-d51ce550d8d5 | note | Verifying Documents - This ITP
564b996c-e104-5783-a830-9228d47c2fae | date | Date Completed:
7ee3a710-426b-425f-be07-0f9033543fe0 | checkpoint | 5.2 - Formwork Extension
eaa0d347-0d6f-58b5-bdbe-7f8759e22cd3 | note | Reference - IFC Drawings
b1b145cf-6512-59fb-a04a-ed2d89801c64 | note | Acceptance Criteria - Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
6ec18138-a40d-5d58-bdc4-b4f32cf33eeb | note | Method - Measure, Visual
084e53b9-b4ab-5db4-a26b-26092ea91c13 | note | Frequency - Where applicable, each pile
428a2419-a09b-5260-a465-1669bf6b94c9 | note | Category - IP
296b6235-31f1-5406-881f-e9c62768a412 | note | Responsibility - Surveyor, SE/PE/SPE
bb12407a-d813-55fd-b4f7-2070dd0ee89a | note | Verifying Documents - This ITP
2b4f714b-39e2-525c-9e7b-c33affb16b1a | date | Date Completed:
3da965da-7a87-40a9-845f-8650f2ec330c | checkpoint | 5.3 - Inspection of Pile Excavation
8655c553-d512-5758-ac70-a92cb4cbd731 | note | Reference - 606.05
43492aef-8f12-56a2-9119-da5941c78b75 | note | Acceptance Criteria - Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
2abf8bea-f908-5937-ac1a-e85d5f8b002d | note | ○ Attach: Geotechnical Field Sheet or Report
4ce9aef7-ef62-5ba2-89b8-01b41125cfde | note | Method - Measure, Visual
10052d39-07d6-57de-afe2-85d1934028f6 | note | Frequency - Each pile
bb83df46-c790-506c-a3e3-a4c8ce87fc97 | note | Category - HP
407d41c9-acc2-5376-9739-98ef2de920d4 | note | Responsibility - Geotechnical Engineer
1b9b7ab8-cfeb-5abd-9090-21e5b0ccaad7 | note | Verifying Documents - ConQA Hold Point Release
da52fc49-472a-541a-a9a8-a3b853c4e27e | date | Date Completed:
b65e29f5-fcae-4cae-a1ae-45f18a394c12 | signoff | AUTHORITY HOLDPOINT
5f16a1fd-9944-44e1-ab79-f6d0996fb8c5 | checkpoint | 5.4 - Reinforcement - Placement
3df7c6d0-e8df-5828-b148-a8b2837b1346 | note | Reference - IFC Drawings
240f6e78-150f-58c0-8392-e59eb7e0acf4 | note | ○ 611.06
3e603fb2-fe56-5e86-af88-e69856c3ea5a | note | ○ 611.09
44584f58-4b58-55df-a194-0eb2d7332d0f | note | ○ 611.10
93a9e784-12d2-52b3-9f44-2d6fe455c3ed | note | ○ 611.11
45b3cad9-8353-5e4d-acd4-926b4212164d | note | ○ 611.12
f73689c1-0886-5509-8b23-64d62fd33fb0 | note | ○ 606.06 (a)
f270846c-794a-517a-8b79-523c099faf9e | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
27d91a52-8973-5164-8158-9681263fd491 | note | ○ Projecting reinforcement is the correct length and location.
a5241058-4118-59bd-a91a-d95da26e6d80 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
2c8a1562-9317-539d-803a-33b265597440 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
7ab758ee-13be-5c72-8604-a6ed2494914b | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
c0592fe4-f1a8-5a2b-a8a8-54551cb5c625 | note | ○ Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
1f58aac7-9e73-5657-ac25-bde097187565 | note | Method - Measure, Visual
8b70cd99-c576-57e7-ae74-5608a743cfb3 | note | Frequency - Each pile
ff4cb4d2-ccde-59cb-92ba-7a64f6d0f06e | note | Category - IP
9ff643b6-f697-5f66-bbc3-4dab086cbad0 | note | Responsibility - Foreman, SE/PE/SPE
444bd8d7-65f5-51cb-a97b-cb1f42e7262f | note | Verifying Documents - This ITP
b5fad0c8-aa93-5c9c-8afb-e800c77ec9d8 | date | Date Completed:
8f915a52-493c-4d9a-ab9b-6835932bbf89 | checkpoint | 5.5 - Reinforcement - Electrical Continuity
6bd055c8-06e6-5b6e-969e-7ae2932aa0af | note | Reference - IFC Drawings 610.29 (d), 610.43
cc31aa60-6d77-55bb-ba44-9ba2d2df17e1 | note | Acceptance Criteria - Pile reinforcement cage to be made electrically continuous by:
ec7d90b4-c0a0-5303-8691-015655bd1d59 | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
020c47b4-ddd6-576f-8928-d30ee7dc39af | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
2ba5fd23-d7dd-542a-a922-c4ab99a61024 | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
0a6bfe65-6c38-5be2-a457-b5296a5ef94d | note | ○ Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
ed472cb1-cd8c-5923-8948-b5e0a515e362 | note | ○ Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
154f187d-726d-56e5-a6f5-8ddaa40f25a8 | note | Method - Measure, Visual
8b5023aa-f312-5041-a74d-ac261765c9b3 | note | Frequency - Where applicable, each pile
05a23330-5213-5f2e-9f1d-2462b3dac297 | note | Category - IP
0bdacff7-f021-5769-87fb-aaa6d9b69487 | note | Responsibility - Earthing Engineer, SE/PE/SPE
682c0ff2-ed60-5cd1-8805-9215d8b86fa9 | note | Verifying Documents - This ITP
b4c00c44-9291-530e-b2b8-78ebc3ed0e4c | date | Date Completed:
f26cf190-1c23-4900-877b-d9ca7aacf037 | checkpoint | 5.6 - Cast-in Items
6793f706-6aec-57c1-bbb5-6ee8398a9083 | note | Reference - IFC Drawings
aa566d05-d6c1-5425-9a3f-ada8d0fc334f | note | ○ 610.46 (a), Table 610.462
087512f0-27c9-5507-95da-f960543c0d7e | note | ○ 610.47 (a), Table 610.472
fc57cff4-a705-52ed-80d3-141b0db0eb15 | note | ○ AS3810.1 Table 3.3.6.2
a86b4fea-0091-519e-a56c-3f167d1f35ed | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
8ce7dca0-c5e5-5f44-8949-1c05f4950adb | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
83378066-76a2-5d5c-af66-867cd195a588 | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
6f4a4f18-f449-52b9-a308-1efe448b1a5d | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
d7dc5338-10fe-5029-8287-960b3e1f6e4d | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
143d949c-ca56-5517-b1c7-1cd67244e733 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
7ef598b4-1891-5e7c-a460-828e874ad2ad | note | ii. Running dimensions of a group of the above = ±6mm
3703e411-f23b-5084-bfd0-f7c549c75c44 | note | iii. Ducts and conduit location = ±12mm
3714e5b3-61fe-5351-a2d1-77588b29442e | note | iv. Diameter of ducts and conduits = ±3mm
57ca043e-d479-57a8-aff4-954f2f2b7427 | note | Method - Measure, Visual
f84f7e94-8bcf-5340-848e-2676ab81c311 | note | Frequency - Where applicable, each pile
e0ba0695-3a57-541c-9d38-5758ba003415 | note | Category - IP
04871bd4-377e-5032-83cf-e41824b88603 | note | Responsibility - Foreman, SE/PE/SPE
d2f1abc1-1e5e-5a57-b423-ce7048a5db53 | note | Verifying Documents - This ITP
49c95465-b10b-5dfc-90f8-e05548bd9fec | date | Date Completed:
1a73816f-b9c1-4ab9-87e2-368cd978df0c | checkpoint | 5.7 - Pre-pour Inspection
a069a7e8-b190-5235-bbfc-8921bb7839fe | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
e521c152-91c1-556c-bda7-df5723d9e201 | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
3fb337ce-9d98-59d0-8caa-0cd91a3964a5 | note | ○ All foreign material has been completely removed from the excavation.
96619803-3fae-53c4-87a2-09352eaa9fb3 | note | Method - Measure, Visual
e3a9cbbf-240a-5a8d-a948-0f14d0cc235b | note | Frequency - Each pile
2b86f63b-fa45-52a2-b59d-6da2e96db568 | note | Category - HP
5a786186-eece-55b6-87c3-f411e439bae1 | note | Responsibility - Nominated Authority
d901510b-d250-5cd6-9f53-8624e9cd3cd6 | note | Verifying Documents - ConQA Hold Point Release
79607aa0-61d7-5765-a66a-e56bf357c97b | date | Date Completed:
cbf10c46-496c-482b-8604-1f4eb344c8a2 | signoff | AUTHORITY HOLDPOINT
7cf356c3-26a9-4de2-8e4b-2bf762fa926e | checkpoint | 5.8 - Weather Conditions & Evaporation Limits
f6cabc12-fd48-51d1-b549-2baab20bb752 | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
2adcc700-806a-5357-910b-7362a5d1472c | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
e99dae1c-51f7-5de2-8333-06e0c99749b8 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
ebaeb804-98f2-5523-b553-2cddaa514f33 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
f6a47176-766e-5a9d-886a-582d0682288d | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
6cefd5a6-6e39-52a8-9397-4f8d3b0af615 | note | ○ Record: Required information on the Concrete Pour Record.
cf701195-e00e-577e-baa7-91bde4c12645 | note | Method - Measure, Visual
f3b55245-db85-5779-9393-e178eef4444e | note | Frequency - Each pile
da72fe93-4b0a-5ac1-b178-b9344705ae77 | note | Category - IP
fe3f2652-edd9-5303-8bfb-e799df5e5243 | note | Responsibility - Foreman, SE/PE/SPE
700c6b15-3f08-5d43-a53b-5e925b1cda5f | note | Verifying Documents - This ITP
28079ee0-2f84-54b2-8afe-87f82641f78b | date | Date Completed:
240b3711-8707-424a-b19e-55d02a449caa | checkpoint | 5.9 - Concrete Testing - Sampling Frequency
03d146dd-892e-599c-923b-1e9d4d85c509 | note | Reference - Site Sampling & Testing Procedure 610.16 (b) Table 610.161
54e68843-b40a-5322-ac90-228068a46f96 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
969c5847-3adc-576b-910d-127b468e5963 | note | 0m³ to 10m³ = 1 sample
bf3600d1-8433-5909-a86f-f1062ca154a9 | note | 10m³ to 25m³ = 2 samples
086eb638-d9b1-5b67-b56c-9dc953e0d261 | note | 25m³ to 50m³ = 3 samples
a6c71201-848d-57f0-bff9-c691e8573224 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
98658eb8-00f3-5fca-a04c-70595f5496e4 | note | ○ For each additional 50m³ and additional sample shall be taken.
5cff1a1c-d8ee-5761-a66f-be85561e8746 | note | ○ Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
f2c5ff91-f9ec-5ec4-8272-84b158b2be21 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
500ec26e-6f5a-5eab-8040-321af51c8cf0 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
09fca4e2-0040-5bc9-82d8-ba0f54169729 | note | ○ Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
5ecb0b98-8031-584f-b78c-d57377872e4d | note | ○ Record: Required information on the Concrete Pour Record.
f7fea7fa-8b50-54bb-a450-a9ee67ce76be | note | Method - Test
fc3255ca-d15f-58bd-a88f-16514b02a595 | note | Frequency - Each pile
dc03f66f-e606-57cd-b729-b8f7f537016a | note | Category - IP
c446be2f-5ad0-5536-8210-6faedea58ab4 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
203c1994-b319-5d7b-a6a8-cfaf5bf5e11f | note | Verifying Documents - This ITP
cd385d6c-75f9-5157-9cb0-3d93ffeacba4 | date | Date Completed:
fd1e3cc6-20ff-407e-a3c7-ad82567f29b6 | checkpoint | 5.10 - Concrete Testing - Spread, Passability & Viscosity
5524f8b1-38cc-5675-bd3a-a791fa4de460 | note | Reference - 610.13 (b)
215406b1-f7d7-56e5-b9c0-754ae3e0d336 | note | Acceptance Criteria - Spread range = 550mm to 750mm
7ed59319-4518-59d8-a1ed-f66bb769233b | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
f51d0bfc-ebb6-5efa-8237-90b1bdd21fea | note | ○ Passability = ≤10mm (aggregate height differential)
60493dba-bad7-5f20-ae12-cd148719f6b7 | note | ○ Record: Required information on the Concrete Pour Record.
fa3cabe9-5cfd-5c80-b50d-9c8ce1493311 | note | Method - Test
99e6363c-8316-5d3a-b8e9-4c9c2a7211c3 | note | Frequency - Each sample of Self-compacting Concrete
cf5a218e-7227-5730-b610-7d9d0ab849c8 | note | Category - IP
56860af7-c455-5763-9767-70dc42e5b468 | note | Responsibility - Concrete Tester
550ee5fa-00a3-51c3-b848-04e679a02c2a | note | Verifying Documents - This ITP
e144cd3d-3107-5bf7-849b-68844901a45b | date | Date Completed:
d00e400d-a928-4bce-85ad-b6dc3840abd0 | checkpoint | 5.11 - Concrete Testing - Compressive Strength Cylinders
d7e11a5d-3560-5451-9625-1b40df201582 | note | Reference - Site Sampling & Testing Procedure 610.16
35a01607-9fbb-5908-a473-1a864dd9760c | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
a63dbd7f-dc11-5f10-b44f-3f0966a5ab75 | note | ○ Record: Required information on the Concrete Pour Record.
fe211f06-c32c-5e31-80d0-3380ab7578e5 | note | Method - Test
73716692-0aca-5e67-aadb-d7d59577c64d | note | Frequency - Each sample
3d7d0da6-d90f-50e1-97c9-ec8535abf68c | note | Category - IP
0e3cb82a-c0e5-578f-96b2-e18f39fb7db7 | note | Responsibility - Concrete Tester
e457119d-e912-5784-a380-4932a2f45290 | note | Verifying Documents - This ITP
c9648c6c-468c-5511-9d21-ca979ff81298 | date | Date Completed:
10803547-0fca-49ae-a436-27061b698fd7 | checkpoint | 5.12 - Placement & Compaction (Dry or Wet Excavation Conditions)
3154ec1c-1398-58f8-9616-7c68f599ddfd | note | Reference - Piling Quality Procedure 610.18 (a) & (b), 610.18 (d) (i), 606.06 (a & b)
3017fa97-5f52-55dc-9a0f-5d62b549203e | note | Acceptance Criteria - Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
a373b48e-9b43-59e3-bdbf-9e738753355b | note | ○ All concrete batches are traceable.
c8305b36-ecfd-5875-87fb-0b4c3c634284 | note | ○ Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
e498aea1-7d04-5e0e-91be-d848d484f5bd | note | ○ The initial discharge is pumped to waste until a consistent workable mix is discharged.
6351775c-23c5-5768-9c2c-8fe341c27cc0 | note | ○ The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
7772b4fa-7549-5065-897e-a165cb3ccf05 | note | ○ Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
439388e7-9c48-5630-a04c-97c96e17c10d | note | ○ Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
279b2c91-653b-5ac5-a2d0-c21ace1ba519 | note | ○ Record: Required information on the Concrete Pour Record.
72e0632a-6910-52dc-9919-a40fe31e51d2 | note | ○ Attach: Concrete Pour Record
774a5f60-512d-57df-8dd9-85c4ff6b0c91 | note | ○ Attach: Concrete Dockets
fb63ac46-f922-5f6f-9cae-ee331bfe9e64 | note | Method - Visual
97cfefe5-925d-52c7-a4ff-82b7ec865cdc | note | Frequency - Each load
088e80df-ccea-5b02-9912-829dabcfdd2d | note | Category - SP
aa932dc8-0f7c-514c-a653-09167d5906ae | note | Responsibility - Foreman, SE/PE/SPE
c672982b-3637-5554-a757-32c346c3b79b | note | Verifying Documents -
4e173637-0de0-5837-9e59-ed1fc99b09cc | date | Date Completed:
b2a75235-2de1-4331-b289-b5afa49c90a0 | checkpoint | 5.13 - Surface Finishes
882d567f-ae38-57f4-a7b0-ee3f7c34806c | note | Reference - IFC Drawings 610.31, 610.20
8534dc77-c7b8-5e94-b157-4d2dd1f83b0a | note | Acceptance Criteria - Surface finish as per IFC drawings.
9ebbc812-135d-5ff4-9d2c-52c26c464d57 | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
878bd62f-e664-520f-8f0a-7a8812990f01 | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
be04166b-b426-5a93-b010-91d94489350f | note | Method - Visual
76968ea8-6c99-5b95-913e-fe98def2d482 | note | Frequency - Each pile
b03aedd2-7ed3-52a5-9ffe-ff53fc5cc8f1 | note | Category - IP
c8dff89c-9755-5e4a-a0d9-05f9b9593115 | note | Responsibility - Foreman, SE/PE/SPE
4271c52c-7a9f-58d1-8582-0b89dfd7d22e | note | Verifying Documents - This ITP
ac9fe326-ffcf-52e8-a44a-2aee6f796231 | date | Date Completed:
080f32fe-57b0-4108-b6ac-66a7ffed6837 | section | 6. Post-construction Activities
06c707fe-32d1-47ce-96b2-3dfee5874d39 | checkpoint | 6.1 - Pile Trimming
912ab390-9e0d-5baa-9be9-d3e6864d07ce | note | Reference - IFC Drawings AS2159 Clause 7.2.2 - 3, 606.06 (a & b)
eee9bca5-1566-5b16-9d5f-e2e32846f58b | note | Acceptance Criteria - Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
3d4e5568-1541-52ed-8565-156c8e7adf01 | note | ○ Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
be34a95f-a8b7-57a3-8af7-434d79ac855b | note | ○ Any weak or damaged concrete shall be removed back to sound concrete.
c629983e-d1b0-5267-b825-9140ae2c6850 | note | Method - Measure, Visual
8bc9e02a-91c1-507e-a71f-166ca5e11310 | note | Frequency - Where applicable, each pile
d018ee46-ea70-5eb4-acce-85b2596485c3 | note | Category - IP
310427fe-697b-5625-9926-a004b7c0d433 | note | Responsibility - SE/PE/SPE
94328a38-fffe-5b29-8e3e-2d9590a27726 | note | Verifying Documents - This ITP
5ae42398-7948-52a9-9f17-4895c3448816 | date | Date Completed:
28ee0aa6-2494-4047-b76f-e3ef8eb3c633 | checkpoint | 6.2 - Compressive Strength Test Results
ebad6b28-af22-512e-911a-c247b149956a | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
ed28f54f-e193-5c0f-9699-4506696f91bd | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
1fd790b3-9e70-56bd-bbff-1148ff922679 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
250cc22b-091d-588e-8516-2c1a26430271 | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
154147bb-979b-52d5-80e2-ec519797cbdd | note | ○ Attach: Compressive Strength Test Results
65a56a88-6460-5c83-bdef-7c02b6f1cbf0 | note | Method - Document Review
09f86e99-ef79-5b02-b76e-adb6a09dd05a | note | Frequency - Each cylinder
7cbf7635-c975-54ce-9f65-063fe92a853c | note | Category - IP
58cd5ab7-1cdc-59e9-a7e2-19a33b0b84a9 | note | Responsibility - SE/PE/SPE
3e22dd16-cd81-530c-9ca5-f60c49335349 | note | Verifying Documents - This ITP
cf31b475-27b2-5e8a-927f-21ef67175962 | date | Date Completed:
4f15791d-d961-4e1c-84ee-b08cd69a43aa | checkpoint | 6.3 - Pile Integrity Testing
23e4cf74-79c3-5b86-a7b3-7a38e39fd2b3 | note | Reference - 606.07 (a, d & e) AS2159 Clause 8.8
01f36b79-d604-5a31-815c-ce9807ddfec2 | note | Acceptance Criteria - Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
f8df3cbf-5d2a-5afa-bbb0-ff952ccbc986 | note | ○ Cross-sectional area = ≥95%
11144b85-2a76-54d2-8b7d-6039840a7eee | note | ○ If any test fails, all piles shall be tested.
7191b589-d60b-5987-8b7b-8fc1718a1498 | note | ○ Attach: Pile Integrity Test Report
b325d18e-427b-5aec-8755-c9b8ce49cbfc | note | Method - Document Review
1b2fcac8-68e4-55df-aaed-2d92dddc4fc1 | note | Frequency - Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass.
a64c66ca-c9dc-5715-b813-98f52698e0c7 | note | Category - IP
dbaf942d-1569-5269-b72e-a6207828c3d0 | note | Responsibility - Testing Consultant, SE/PE/SPE
54c4d3e8-c7e1-53d5-9783-78f00e105db6 | note | Verifying Documents - This ITP
d20c7483-e18a-552a-93fd-548351a79044 | date | Date Completed:
d177dc8e-e7a5-4638-8a84-bce2534ebd71 | checkpoint | 6.4 - As-built Survey
c1857083-3a34-5d40-86c5-ea3aa6097f55 | note | Reference - IFC Drawings 606.08 (a - c) AS2159 Clause 7.2.2
b46e2e53-235d-59df-bc62-54a61e918c4f | note | Acceptance Criteria - The following tolerances apply to piles:
d2a4dc1d-9e93-579f-b1c6-3bda641a4460 | note | i. Pile head plan location = ±75mm
24f76a9f-caa6-58de-8b18-9ede28794067 | note | ii. Variance from vertical or rake = 1:100
0df62281-47f4-5ed9-ad7c-878142a85e1e | note | iii. Irregularities in straightness = 1:100
3ad5c9a5-7261-5a12-898b-358a0aeb36b6 | note | iv. RL = ±25mm
14a08fb5-a4e8-58f6-8b9a-e3e10bd6f51e | note | ○ Attach: Survey As-builts / Survey Report
5f8a3744-28d8-5ad8-8367-5795c2d7ab11 | note | Method - Document Review
da00ee21-46d5-559d-b613-2e841a2ac120 | note | Frequency - Each pile
8f2fdc42-17ca-52e1-adb8-65d2955202d2 | note | Category - IP
24b78e61-7596-578a-be05-a81477dbd608 | note | Responsibility - Surveyor, SE/PE/SPE
324f6598-2c1d-5961-9ba1-c557d5549fd2 | note | Verifying Documents - This ITP
f5ff138f-1296-5966-b800-3b5d06671105 | date | Date Completed:
ad9cb318-8639-4df6-a845-ca3b34b6b1dd | checkpoint | 6.5 - Non-conformance Report (NCR) Closure
35635b62-7ca1-5833-8723-098ff4741824 | note | Reference - MRPA Quality Management Plan
110f34b7-94e7-5701-b64b-49823bb2e8cd | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
57c27e2b-f0ba-50db-9d4f-661ac627ac53 | note | Method - Document Review
71dfb212-7cbd-5903-89be-cd7fe061c554 | note | Frequency - Once, prior to closure of this lot / element / Work area
534c5bfa-3333-5fb2-bf68-e795ef84ff92 | note | Category - HP*
ba6debef-08a3-5b9e-9e94-ea061d4e6c2f | note | Responsibility - SE/PE/SPE
733f9f11-386f-5d79-a2ee-bdd2bdcc6f82 | note | Verifying Documents - This ITP
2a648f33-82ec-529b-94c1-0fcece71c7d9 | date | Date Completed:
dfdeeae3-4094-4f5c-a54d-6615a88b64d2 | checkpoint | Final Inspection
e3ddfcec-bf7e-5f0d-a438-5c8ddee53a42 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
2e06820d-8873-59b5-9730-83d0461c4823 | textbox | Name:
bf6baf3a-0eb5-54a6-ae8a-01fc8edb282f | textbox | Position:
350b3e42-34dc-5237-9f6f-8b6d5e97ff00 | textbox | Date Completed:
38e90cd7-8541-4a20-b2e2-3d4eb96dd29e | signoff | Sign ITP
aed06526-4315-44b2-9b13-a6334788e82c | checklist | ITP-308-STR-MSS-Structural concrete Rev 0 | itp | ITP-308-STR-MSS-Structural concrete
ba5e384e-f50f-4186-a0bd-7db7d3506544 | section | 1. Referenced Documentation
7d8d1419-bf1e-4836-8535-d3de3a11f7e9 | checkpoint-no-value | Referenced Documentation
6a01a600-02f2-58f3-8a42-19af04b1f97d | note | Document Title: ITP-308-STR-MSS-Structural Concrete
96c43a37-4812-542f-b531-4e4e2a1638e3 | note | ITP Description: MSS-Structural Concrete
c7a0ec28-1bea-5854-8445-d18519b0beee | note | Discipline (e.g. CIV/STR/RAIL): 308-STR
4157e4a0-438e-599e-b4a5-259918d090a7 | note | Revision Number: 0
02ff18b6-821e-5394-a8ce-5c38f274dc80 | note | Revision Date: 28/08/2025
35d107eb-230a-5d8c-935b-f0a2f58a23bf | note | ITP created by: Andrew Carlini
644d2554-1085-53d1-b4b4-af235b1e1792 | note | ITP approved for use by: Romualdo Magpantay
f62df3ca-f172-5949-82fc-9644245e7b47 | note | 1.1 - Non Dependent
ced9daf0-bb6a-526e-b51c-e9a2f709194b | note | Reference - DTP Section 602 October 2007
f2e7b065-b9e7-5cb7-a095-a1127f2ed797 | note | 1.2 - Non Dependent
f9dd9ebd-8693-5051-98e9-d659a5fc726a | note | Reference - DTP Section 610 February 2020
e852c330-c575-580c-81d9-c5ef7e9db4f1 | note | 1.3 - Non Dependent
2f10058c-1e72-5940-9f33-2173d1a76e75 | note | Reference - DTP Section 611 November 2018
9a972fd7-21ee-5da6-be45-7476e2d62511 | note | 1.4 - Non Dependent
89a431ee-affe-58d6-9a78-8c0ea694d081 | note | Reference - DTP Section 614 June 2017
2f62b773-9348-567a-bce8-e33a89e2edb2 | note | 1.5 - Non Dependent
a00839cd-f283-5c10-9a36-a983db1066c5 | note | Reference - AS3810.1 2018
5b4436dc-6842-4790-8eee-b07a3289da85 | section | 2. Preliminaries - Materials
4997429c-6788-4573-9797-b3db8460b99f | checkpoint | 2.1 - Concrete Mix
252b6b3b-aad9-5a42-9db3-b99559282e40 | note | Reference - 610.07, Table 610.071 IFC Drawings
166e0978-b18c-504a-b23f-3ca7110427ba | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
06517b76-63eb-5899-9d1e-312c9bfba58c | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
c4d45773-a492-52c8-afef-0a7e2765de78 | textbox | Enter: Teambinder Material Approval number
5932a7ec-3af6-5cf4-b7e8-3b31c5f2ee0c | note | Method - Document Review
00ddadfe-b9c4-54a3-bd78-fe18d6bf050e | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
f4a636fe-3776-59a4-a146-60e3f84632ce | note | Category - HP
e610835e-9038-5504-8083-8cb217501943 | note | Responsibility - Nominated Authority
2a261822-6105-5bb4-9a80-afb6471999da | note | Verifying Documents - ConQA Hold Point Release
fbc93af7-9a52-5e78-9c20-eb214154a066 | date | Date Completed:
d1bf7f10-e0c3-4e7f-94da-5201ee48cbcb | signoff | AUTHORITY HOLDPOINT
d9b10eeb-75dd-457e-820a-a02840df66f0 | checkpoint | 2.2 - ACRS Certification (for Reinforcement) Bar Chairs/Aspros Certification
0c5a7944-6ee4-58bd-a693-42f2bf1012cb | note | Reference - 611.05 (a), 610.26 (a)
d5b4c103-b701-5403-a78c-01ee1491b2aa | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
b16d0b49-22a7-5b76-bb21-b117fa39c4a5 | note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
549e0a55-8908-58ce-b4d6-5fb80ff0aaed | note | ○ Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
0f79d101-1477-573f-a038-c721124a35b9 | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
594d7626-0c94-5a28-8e1c-021386e0bb30 | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
26ab8119-2dff-5a09-8a31-df1297689032 | textbox | Enter: Teambinder Material Approval number
383bfd6d-2309-54c0-99db-cc0342795df8 | note | Method - Document Review
31026620-be6a-53e8-b247-162b239d97c2 | note | Frequency - Once for each supplier, 14 days of award of contract
cdf581be-f305-5521-a5de-5572b5560fe4 | note | Category - HP
f05e6804-bf7f-5a12-b6ae-d335b5a1ca7d | note | Responsibility - Nominated Authority
239715d0-08fc-5436-98fc-a546a4160eb2 | note | Verifying Documents - This ITP
1a846a4c-aa36-5ae0-980f-3690fbb49cc9 | date | Date Completed:
9d647a2b-7ed9-4278-9e2d-4b84178c512c | signoff | AUTHORITY HOLDPOINT
eb95680f-4384-4375-b63f-47e19708f469 | checkpoint | 2.3 - Evaporative Retardant Curing Compound
8c8a887c-0b74-5aa1-bdea-5952e318fda3 | note | Reference - 610.17 (f), 610.23 (d)
7c016d77-762d-5f23-aaec-6d9c3798a92c | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
4c6912f8-5a22-52ad-ba3e-ece8c254243a | note | ○ Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
52a2cd95-cdb3-50be-ae5e-4b2bd2edadbf | textbox | Enter: Teambinder Material Approval number
7d6cbe10-cd10-5770-9fe0-3c74c1f13129 | note | Method - Document Review
ad74046e-e3be-576e-b53b-8663e61be743 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
c92009f1-4c5e-5c5c-8b37-e5db13fcb23f | note | Category - HP
87bbb4b8-1b1d-55c6-bbae-15736b91514b | note | Responsibility - Nominated Authority
6fc43390-e8e2-5ee4-8149-a1f00e64876a | note | Verifying Documents - This ITP
b135331a-62ef-578f-95d8-00b13ccb5e1b | date | Date Completed:
5cbccac3-cc61-4dbd-9eef-00b3ffdfc0c8 | signoff | AUTHORITY HOLDPOINT
7c4a361a-71b5-4ae1-b6b8-a5cfc8b48549 | section | 3. Preliminaries - Procedures & Documentation
daa61d96-fe39-4d3c-84f2-a8591f6024a6 | checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements (Concrete Sampling and Testing Procedure, Concrete Placement and Compaction Toolbox Meeting, Hot and/or Cold Weather Concreting Procedure, Curing Methodology (for Concrete and Grout)
07a69928-c5bb-5e39-866a-57748542bc3b | note | Reference - 610.18 (a) (i)
aaeb0272-9e5b-5986-8b53-aa759c4f865e | note | ○ 610.18 (a) (v)
a75479fe-7f77-5dc9-a4d7-5b1b780ee6c4 | note | ○ 610.18 (a) (iv)
7beffa2e-75eb-529d-a082-8e6db2935daf | note | ○ 610.17 (a)
b668a2b8-4ce3-5005-bca8-661e76402f53 | note | ○ 610.23 (a)
acdf5a5e-70d0-5222-844d-7e42922f022a | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
fc2f9bec-bb55-5773-ba21-1286460cee6f | note | ○ Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
b815955f-28d6-5e10-afc3-fe760a927ae0 | note | ○ Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
2d6b02c4-a305-581c-8d02-1d49360194eb | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
5989bf46-a02e-58cc-98c9-8cd4f89964cd | note | ○ Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
27a4c556-edad-5256-91e7-d115d31ca01e | note | ○ Curing methodology/procedure to be submitted for review to the Nominated Authority.
fa4847bd-1e1c-51cc-82c2-db0948a51c6c | textbox | Enter: Teambinder Approval number
bf104d4c-a836-5a89-8d6a-64f20545b151 | note | Method - Document Review
c3d966d2-12cc-5f4a-bc37-24019c97c9a6 | note | Frequency - Once, 4 weeks prior to placement of concrete
f50dde51-8c27-5af5-ab15-8264d02ee54f | note | Category - HP
2391a935-80fd-53cc-864e-9b433e8e6a8f | note | Responsibility - Nominated Authority
8c77a8c2-8fb8-5589-abd6-6ab5e0cd2690 | note | Verifying Documents - ConQA Hold Point Release
b366e728-8260-51ef-9e6e-45ca12790914 | date | Date Completed:
37bbdb3f-61d3-4fe4-a169-c53ba9b6c499 | signoff | AUTHORITY HOLDPOINT
008fddf3-1e33-4a38-b0ae-d5feae0637e2 | checkpoint | 3.2 - Concrete Drilling Procedure
301f5cc3-7838-5d46-bb69-0a1fc68c2f55 | note | Reference - 610.46
bc5eb14e-423c-5841-ac5b-c2b48b7575b2 | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
96e94444-8c4c-59f5-a37c-13263b262dbb | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
8424c855-8604-54fc-a2ba-72590b1f0965 | textbox | Enter: Teambinder Approval number
c20cb787-1463-5434-b11d-3208f2ae9a50 | note | Method - Document Review
6c554df6-a4df-5cf8-8416-6a54491843ae | note | Frequency - Where applicable, once, 2 days prior to drilling
fab38f77-b47c-554d-87ab-1a2c4814505f | note | Category - HP
6c79a7b3-3122-50d0-ba9b-ed82a8a33b65 | note | Responsibility - Nominated Authority
5d3d7c8c-0cfc-51e4-9c92-799ade9f6823 | note | Verifying Documents - ConQA Hold Point Release
2943a7e5-0620-545c-80d9-c1f968c899af | date | Date Completed:
2be75e82-6009-473c-826b-8e8861d64c1c | signoff | AUTHORITY HOLDPOINT
13e6b12c-c270-4d57-bae3-aee77ec7c18b | checkpoint | 3.3 - Temprature difference measuring-Calibration
b4d82dc9-1df3-5f00-a75e-0c9ab214daea | note | Reference - MRPA Quality Management Plan
03578302-237e-5478-80f4-49374104d628 | note | Acceptance Criteria - Calibration records are valid and up to date.
183e04f3-b85d-5b9d-a19a-69474f3fc1dc | note | ○ Attach: Calibration certificate
ae4a5f3e-b3dc-5b29-af71-1e69bfdf4711 | note | Method - Document review
904fd11c-6422-5c84-8f7c-4f2669422db6 | note | Frequency - Where applicable
eaf23428-4bcb-5a23-8c5f-f9c99d44c705 | note | Category - HP*
f1330f6c-544c-5fec-9830-3e38cccc583b | note | Responsibility - PE
17f9e6c6-67f4-56cb-86da-92ce6a59baad | note | Verifying Documents - This ITP, Attached calibration certificate
3d5dbc2d-c698-58c9-9558-afd81b594c8d | date | Date Completed:
bc674644-986d-443e-ac71-9742f97a6bc5 | section | 4. Pre-construction Activities
de66459f-28d7-4a55-990c-7d673126f85a | checkpoint | 4.1 - IFC Drawings
284f6524-b7e5-599f-a7d9-93502f796041 | note | Reference - MRPA Quality Management Plan
29f310cf-1183-54ef-8a44-1fdeffc77b70 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
064f1232-df56-53cb-9a80-e5fcc7773c47 | note | Method - Document Review
0af80382-0640-54c2-8d08-caac2d9a1e1c | note | Frequency - Prior to starting Works and at regular intervals
71ac3837-86b1-5e08-aab5-26ca3ec3b979 | note | Category - HP*
b3258a69-944f-56c3-b9d3-7cde23a7f4ee | note | Responsibility - All
bc0ddcfb-5263-53b7-bcf8-2732251dcf37 | note | Verifying Documents - This ITP
3c1d6bfb-4707-5ef9-893c-9fe5d7573f54 | date | Date Completed:
15269fdc-2cbf-4f63-8fc1-6ff6e7309ce2 | checkpoint | 4.2 - Survey Set-out
b760c67c-b522-5f7c-a0bd-a0c151ff3a3b | note | Reference - IFC Drawings 610.47 (a) Table 610.472
7e225052-8107-5643-83fb-e1055ce126c2 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
7fbd085e-6e52-5a11-bf12-5dbac37f1f49 | note | ○ Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
00ab5fd3-6abc-5c6e-9295-6ff0261d9997 | note | Method - Measure, Visual
4a4c7582-b514-5555-b43d-6da0e11cc26c | note | Frequency - Each element
bb9d619a-58ad-5dbf-9a66-820e2f8edf16 | note | Category - IP
c37e34ed-2f45-56ed-8cbf-4fefc23f72d8 | note | Responsibility - Surveyor, SE/PE
92ae5716-2f6c-5c73-a6dd-4b30522f8a31 | note | Verifying Documents - This ITP
0655d2b7-946d-5ca4-999f-7bc778b812eb | date | Date Completed:
005032a5-b78e-417b-a44e-395d843791dc | checkpoint | 4.3 - Excavation support
86fc8a4c-826c-5408-862c-dc63d5a3dffc | note | Reference - 602.02
7d997a1d-090a-53c0-93e5-3dddeb4a90c4 | note | Acceptance Criteria - For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
e70af64a-842c-5e68-abae-85fd153d624f | textbox | Enter: Teambinder Approval number
41acbc9c-771f-5365-985c-7fb19a3391c9 | note | Method - Document Review
cf804bba-587c-56f9-9d6e-fef8ca5a797e | note | Frequency - Where applicable, not less than 10 business days prior to excavation
7c20b604-842a-5ac3-b097-f924e76cb500 | note | Category - WP
76f779c8-79f4-54c2-9ff2-77e8d66c391d | note | Responsibility - SE/PE/SPE
62f7244d-7118-5422-9a5e-a1985df397ae | note | Verifying Documents - ConQA Hold Point Release
c02a19a0-5db7-5347-ad54-312de5a19f5b | date | Date Completed:
529aecce-1a75-4d6a-9b05-6e57e8bf90d2 | checkpoint | 4.4 - Excavation Inspection
b384176f-43ce-5e50-9fe6-ea71e355ca31 | note | Reference - 602.03
a523be06-3452-5439-8f49-e599b29f1c1b | note | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
aac61a22-2688-581c-88ff-166ccb0b5b7a | note | Method - Visual
13bc6c62-37c3-51e4-ab91-56f7d17e0ad8 | note | Frequency - Where applicable, prior to placing blinding concrete
b2a307a7-db91-5359-b45b-7f3bd1f22b07 | note | Category - HP
c1b06c4a-5360-5794-8fce-e42e2730e7ec | note | Responsibility - Nominated Authority
2ea2bd09-bdd1-5c3f-91b4-6c2e3046c921 | note | Verifying Documents - ConQA Hold Point Release
469b77e4-3bb1-544c-a312-67be8e96f069 | date | Date Completed:
5bb5b8fb-f1cc-4b39-95ce-665a2656d123 | signoff | AUTHORITY HOLDPOINT
3cb359c4-b273-45f9-90ac-5004747976aa | section | 5. Construction Activities
f954c9aa-7a6d-4d32-97f6-b0ec4d8a6246 | checkpoint | 5.1 - Formwork Design and Construction
438d62f3-e88b-5293-ae4f-ac448c510e7c | note | Reference - IFC Drawings 614.04, 614.05, 614.06
328857d4-e403-5f5b-a0a8-4622cdf49fff | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
e3d5b61c-af2a-5d4b-beb2-477243058152 | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
9caea330-1b88-533b-9b3d-7331affd68ba | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
2cfb7629-52fc-5baa-ae82-4cecc972ea64 | note | Method - Document Review, Visual, Measure
fad202fa-32ee-54a4-afe2-09c60443ad8c | note | Frequency - Each type of element
74c882d2-6be6-5531-9578-9e8e20c61cfc | note | Category - IP
3be996d7-b0e8-59c8-a38b-d2027528a9f2 | note | Responsibility - Temporary Works Designer, Proof Engineer, SE/PE/SPE
d3b65393-412d-5fc7-ad7a-e3bb09912c2e | note | Verifying Documents - This ITP
58420856-fec7-599d-97fc-4a5479667fad | date | Date Completed:
0fb00d7a-85cb-4b8c-a147-7e65a36cc8fc | checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
2766b93d-918e-5c5c-89ec-d40e16021d29 | note | Reference - 614.08
e591d00e-325e-53e3-9309-1a7a23251b2c | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
afa03d7a-5237-59fa-a1c0-5bdd3bf16f3d | note | ○ Walls with heights greater than 2.0 metres
7560fbb0-bb3b-55a4-a68f-47758e51bc0f | note | ○ Any member for which self-compacting concrete is proposed.
49be003b-9228-5cdb-9b0d-aa935faac49b | note | ○ Attach: Attachment A
5a79cfef-090d-51de-acd4-d8ce2fdb3c2c | note | ○ Attach: Attachment B
89a2e64c-7595-547b-b70f-3f45d7b3cb14 | note | Method - Document Review, Visual, Measure
539e7648-ad70-5aa1-b212-f05f0eddd980 | note | Frequency - Each element (where greater than 2m)
b73f9524-c96b-5dac-b767-98d46ac140d6 | note | Category - HP
bb001db5-1a62-57e8-8fdf-52edba5a29c6 | note | Responsibility - Temporary Works Designer, Proof Engineer
5bd852ed-18ec-5035-84f0-5458c083b4d1 | note | Verifying Documents - ConQA Hold Point Release
97451bc3-2ec4-5f5c-8e25-9e5150c7c6a6 | date | Date Completed:
d88880dd-e71a-48c3-b0ad-76fd8c5c0e17 | signoff | AUTHORITY HOLDPOINT
6cd73211-ee7c-4641-bfec-742bd28be2af | checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
da59e2ef-9173-52ca-92a5-69c618e147d4 | note | Reference - 614.08
87f5e10b-298f-5b56-a21d-d273948ad7fe | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
e7531e4d-5baf-5732-96ed-32ed3f329694 | note | ○ Walls with heights less than 2.0 metres
c8230c85-4dbc-54e8-9c7a-cf0bddb08f1e | note | ○ Attach: Attachment C
ae6fc42b-22dd-5bed-a640-6c2bcdd57c65 | note | Method - Document Review, Visual, Measure
6188c21a-c38c-530d-bc74-8a95a6252d6b | note | Frequency - Each element (where 2m or less)
6b8975e6-67eb-5f6b-95a6-97cd3abfcc71 | note | Category - HP
420992f2-b6a4-5c9d-8781-573f17580e5e | note | Responsibility - Temporary Works Designer, Proof Engineer
4c76597c-f817-510d-947a-2e2a2cfbfef6 | note | Verifying Documents - ConQA Hold Point Release
e6bc89a9-a4cd-5987-925b-bb7df2f31e55 | date | Date Completed:
2bf2c576-24d8-4f57-a2a7-7947c9e9a3ba | signoff | AUTHORITY HOLDPOINT
a745ed40-384a-41d1-a4f5-ec91ae68a605 | checkpoint | 5.4 - Pre-pour Survey
4e39af5e-5e9e-5ad1-91af-8ea2aca37537 | note | Reference - 610.47 (a), Table 610.472
1663ca13-6135-5bdb-b57c-e669a5b0aaf2 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
712e5983-dc78-54da-b87e-1b0608ae1913 | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
6510f15f-4289-543f-8a48-dbe55ba01bb1 | note | Method - Measure, Visual
5d37694e-d582-5304-9d1e-eaea05c8de5e | note | Frequency - Each element
af25b2f5-50d7-5d67-b824-936be57cde9d | note | Category - HP*
ff9c0654-7037-5635-9da0-4afd7403335a | note | Responsibility - Surveyor, SE/PE/SPE
f165c2e2-0de9-5266-9b30-6bf562f36ab0 | note | Verifying Documents - This ITP
28c6daf0-ca8f-5072-8b5b-3a72b5e86311 | date | Date Completed:
a4be2861-e2d1-404e-89ad-4b18436734e7 | checkpoint | 5.5 - Reinforcement Placement
3f9e19a0-74e7-533d-8a94-c4710b0e11a5 | note | Reference - IFC Drawings
ece7add2-0326-55f1-9d77-c4a1cf0486b7 | note | ○ 611.06
6175cf15-7e2c-5f95-8860-53710ee9885a | note | ○ 611.09
3fca57e0-a344-51a9-a8a5-ce470a126728 | note | ○ 611.10
1da0b7c3-d802-59f0-8f47-f8d361aa2c8c | note | ○ 611.11
fa6b1b74-a968-5625-a249-301530ff5ffb | note | ○ 611.12
51eceb4a-cb55-53cb-8e7d-77fb1fb21061 | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
db04fc5d-88c3-51e7-ba70-ca5dd20062e2 | note | ○ Projecting reinforcement is the correct length and location.
06549a0e-f505-5603-8596-385bbbaf8dca | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
d6332bc6-3533-5b90-8a80-794bd80053f1 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
d9dfe9cc-83cd-5bcd-bf46-df16977f2e99 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
9fb6245a-cca4-57cd-9c4a-78d9a10c0500 | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
3c4fece5-4b64-5878-8d7b-1673e74db84e | note | Method - Measure, Visual
b50d39dd-be12-5161-8b56-5e85acd99d67 | note | Frequency - Each element
6b39ddc8-47a6-5eee-9256-2f365c32fdca | note | Category - IP
67a158af-233d-5438-803f-5a192a6522b2 | note | Responsibility - Foreman, SE/PE/SPE
79a95081-46c3-54c0-87d7-171889384b52 | note | Verifying Documents - This ITP
8585ff0c-7239-59c6-8a45-8478b6baa6a0 | date | Date Completed:
8af6fd82-5c8c-49a1-93f2-1a4c4dd838d4 | checkpoint | 5.6 - Cast-in Items
31a78ea2-6d70-589a-8c14-849561a55e9f | note | Reference - IFC Drawings
5d8fde4c-fa07-5c5b-bd41-15c04bda7241 | note | ○ 610.47 (a), Table 610.472
438b1268-c0c4-5ee9-b4c1-cdb4c919ec43 | note | ○ AS3810.1 Table 3.3.6.2
653cfcdd-4458-57bc-b697-4157787f7031 | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
a46a93e0-021f-50b6-ba32-1bc6b11b957c | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
719b5a0d-82b2-55b9-a670-3b332c9bc06f | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
e3eaf736-f743-5089-8ae1-4d4bc26b7da5 | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
fff554b8-bbbd-590a-8fdb-83862bd381cc | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
8d7573ab-e7f8-5d44-9520-370b9430a050 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
9e767203-016d-571c-82aa-71f92c3d3724 | note | ii. Running dimensions of a group of the above = ±6mm
7ea8b8ec-8c2d-5c33-b218-3e494e4e5750 | note | iii. Ducts and conduit location = ±12mm
294be9b2-25fa-5ef8-b3fa-d959455c87ab | note | iv. Diameter of ducts and conduits = ±3mm
28bb7e4e-f67e-5cb6-9f94-d69cb038ee53 | note | Method - Measure, Visual
2fee6dcd-bf80-5eca-9426-80df7fef9788 | note | Frequency - Where applicable, each element
823f8e36-0eb2-5d02-baa4-ef2d166aeef9 | note | Category - IP
ddaeb365-321d-5f11-93d1-1e3879c5721b | note | Responsibility - Foreman, SE/PE/SPE
4ce5e71a-0574-514c-b8b0-3cbded8fea6a | note | Verifying Documents - This ITP
36613d1b-2d34-5199-8afb-670b213de9db | date | Date Completed:
5fbfc6d2-e686-4c09-9105-6331b201f3ae | checkpoint | 5.7 - Thermal Differential Monitoring
c28881f7-03c1-5898-9765-d10139d219f9 | note | Reference - 610.22
e48c55a1-4710-5e12-a737-fdb034089194 | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed.
bc332509-7395-59c6-aed3-2fc661df3096 | note | ○ Only applicable if the element has:
48f06a41-d569-58f5-894f-9c7aecf16493 | note | i. the smallest sectional dimension exceeding 500mm
985badf5-41e1-5182-8c03-b3d888ed8cfa | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
fc517e3f-e0c0-5f2f-b5e9-377375124acd | note | Method - Measure
ceb21219-9f8a-5578-987d-b50a8fac1ef8 | note | Frequency - Where applicable, each element
ad0ca0ba-dd3c-547e-85fb-ee9facd464a9 | note | Category - IP
3a896d27-86bb-5881-a969-c84fe78cad5b | note | Responsibility - Foreman, SE/PE/SPE
a445c097-8966-5d5c-b3eb-293bdc381c73 | note | Verifying Documents - This ITP
ea4dab84-8a59-5d6e-808a-0b820590d1f0 | date | Date Completed:
f3fa17e2-b8af-4873-8978-8aeb4a2f408f | checkpoint | 5.8 - Pre-pour Inspection
0692cdb7-6180-50e9-a864-2f6286a97211 | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
baca361d-8b15-50f0-ae8f-477a9012f9ff | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
6f600ecf-1ed3-56ab-bffa-7fb6280c0b16 | note | ○ All foreign material has been completely removed from the forms.
40bc5ba8-6874-5c0b-80e9-4ebbe7b7c846 | note | ○ ATTACH: Pre-Pour Checklist
5114c417-ec42-5362-a1f9-9a6750cc5d08 | note | Method - Measure, Visual
6fdf9d30-27cb-55d5-a8ba-42e2e44e6ec0 | note | Frequency - Each element
f06ecd02-facf-5a82-9134-d2c85a033b30 | note | Category - HP
36258b2f-637b-5c09-81fa-83f4ff2181c9 | note | Responsibility - Nominated Authority
16023bf5-96aa-56db-92b1-bc40706eb5cd | note | Verifying Documents - ConQA Hold Point Release Pre-pour checklist
61c38359-8134-5f1f-a4af-ebaf39a2e95d | date | Date Completed:
32c1471e-d943-4610-9f25-62a6166abd03 | signoff | AUTHORITY HOLDPOINT
721f173f-4cc0-4743-9c6b-d4494143a559 | checkpoint | 5.9 - Weather Conditions & Evaporation Limits
34800ac4-fefe-5ddc-bb62-1ec66a4d83fd | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
59a80fb2-defc-5432-9f06-2639b6b2e8df | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
d936d77c-c4fe-5117-b849-48642950fef8 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
dfc297f5-98d6-5839-85d5-41695877c4d3 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
517ef9b2-6478-50d6-b79f-fa9fc9a8d90d | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
7b75461f-dc4c-565e-9671-fbd01a5738e5 | note | ○ Record: Required information on the Concrete Pour Record.
e8585149-6c5c-5168-bfa5-609e1c3e7ac9 | note | Method - Measure, Visual
5d982d7d-4dec-53cd-93f0-1131a45c31cf | note | Frequency - Each element
b7ef3a4d-2a19-5727-b20e-3f5781c6a9d9 | note | Category - IP
976c686b-f36a-5c39-b422-fa57e5142168 | note | Responsibility - Foreman, SE/PE/SPE
02be46d6-9ee8-508e-90d7-857e6bacdc5c | note | Verifying Documents - This ITP, Concrete Pour Record
6edf328a-696e-5a0f-8dad-02c588a4e81c | date | Date Completed:
bb7abe0f-7ff8-4c54-a0fb-d36b5555740d | checkpoint | 5.10 - Concrete Testing - Sampling Frequency
c04f953a-3b2c-5f8f-9604-2d1968c9a9a7 | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
c9be9b1a-6e4a-581a-94ee-3db1d9f8bb98 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
a488043a-2d37-5f63-9b6f-d025bc5d0e80 | note | 0m³ to 10m³ = 1 sample
39933e3a-2615-50c4-b6d3-8056a7cc01ce | note | 10m³ to 25m³ = 2 samples
8d3d1f72-6e19-5196-8d95-d11373804a80 | note | 25m³ to 50m³ = 3 samples
0d76567b-b714-5074-a8e8-418bee8d16ef | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
8aac9d1b-5042-5370-9332-70bd0bb74efd | note | ○ For each additional 50m³ and additional sample shall be taken.
74204d9f-e3ea-5def-b4d3-42545fec471f | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
33b63dd9-7b96-5e0c-b7d1-5e9f2109c3c8 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
55d1ad91-3036-5da0-8c7d-361c119d8185 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
29126b71-0e24-58c7-abcb-52a336312028 | note | ○ Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
dcbf40c2-a5aa-5e06-8e4b-32fa67a54c69 | note | ○ Record: Required information on the Concrete Pour Record.
b35645fc-e6d0-5ccc-bbdf-86086204d907 | note | Method - Test
2b41a383-d98f-580c-8fce-1742b64bc621 | note | Frequency - Each element
a42bfce1-5013-51a5-a3ee-e477b6e9b8da | note | Category - IP
1d2f62fc-7cb4-5053-b2c5-aa44b0e655a4 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
1bb6efa1-7924-598d-ab09-859ecb2890b9 | note | Verifying Documents - This ITP, Concrete Pour Record
4d0dbfe7-97a2-573b-a145-01b483469533 | date | Date Completed:
9559e10e-b276-4015-847d-da7873d70e61 | checkpoint | 5.11 - Concrete Testing - Slump
b46f4c60-4b4d-585e-b1ec-4f80257c7096 | note | Reference - 610.16 (c)
8e6824dc-2a92-5eab-938d-c9f57906e4b8 | note | Acceptance Criteria - Slump testing tolerances =
f66d58e3-bd99-5dde-8df7-bd61f0debbf8 | note | <60mm = ±10mm
ba16149e-d075-5f35-a8c2-f06485b46b13 | note | ≥60mm to ≤80mm = ±15mm
2cbfa670-7b83-58a8-839d-e2b453a53464 | note | >80mm to ≤110mm = ±20mm
1eaa2a05-7eb9-5669-aae7-ac288054b88f | note | >110mm to ≤150mm = ±30mm
e25fdbb9-6a48-505d-8d8a-45c34b2ea59a | note | >150mm = ±40mm
c236f296-2b44-56d9-8086-146386ea4ee5 | note | ○ Record: Required information on the Concrete Pour Record.
cfadf853-c5f7-5084-95ef-e0636839fad9 | note | Method - Test
68199877-9d85-58b0-89a8-4aad2b73c59c | note | Frequency - Each sample of Standard or Superplasticised Concrete
9fd65426-deea-5fd4-bcec-85b86b49f450 | note | Category - IP
dc45a41c-eb65-5636-851d-179ea56c5b3d | note | Responsibility - Concrete Tester
979b8b0b-33bb-5724-ac45-52bdf02e8a5a | note | Verifying Documents - This ITP, Concrete Pour Record
d411c1ed-81d3-5452-b4c9-496915b0e285 | date | Date Completed:
6da39d2c-9ec7-442b-b5e9-463ae995f5c6 | checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
e77d90e3-5915-5991-ae78-cbc944a2128d | note | Reference - 610.13 (b)
78bb568a-2e61-535d-8257-29b980edaefd | note | Acceptance Criteria - Spread range = 550mm to 750mm
b457c5e0-e04e-5ddc-b021-127f4ba46e78 | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
6e72e782-f175-525c-9e4f-c81368200c4c | note | ○ Passability = ≤10mm (aggregate height differential)
394fee64-1661-5bb7-8ce0-0cc5e5ec3d24 | note | ○ Record: Required information on the Concrete Pour Record.
4c0e2c93-997c-52ab-b23c-5926c9226e35 | note | Method - Test
ae4902e5-09ce-56bd-b785-aae8ecdf76d1 | note | Frequency - Each sample of Self-compacting Concrete
d2cc3575-3aac-5492-acf3-92558b8d0a37 | note | Category - IP
c9bbe73b-dce3-513b-b6cf-b8876789c4ae | note | Responsibility - Concrete Tester
60de4fbb-6cf2-58c6-a272-0889a907a8d8 | note | Verifying Documents - This ITP, Concrete Pour Record
a01d5bad-cbc8-5d22-adfc-99efe65b3af6 | date | Date Completed:
c0b0ba98-9be1-458b-8306-5f87458a4813 | checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
5094753c-2bd7-54cc-b229-33144bfefaa8 | note | Reference - Site Sampling & Testing Procedure
37429e4b-f3bb-5907-a1e9-80eee92b585a | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
04c96c7e-b135-5e8c-9161-72d3872f2ef8 | note | ○ Record: Required information on the Concrete Pour Record.
5e0d3ee4-fc27-5fad-ab72-d07b6349129f | note | Method - Test
b92cf832-398f-5e5e-a70c-ec56e39ad783 | note | Frequency - Each sample
668c55a7-01c7-54aa-a0bc-29b96554d0f8 | note | Category - IP
b41fce5f-2da5-5b2a-9d85-5bd1f217bfeb | note | Responsibility - Concrete Tester
db68f3f2-bc01-5e6f-9cb8-ac932a4b2036 | note | Verifying Documents - This ITP
844bc600-dfa4-5e53-b4cb-29004f99477c | date | Date Completed:
2fbc01dd-e104-41f2-a64e-8d13dfe24ff1 | checkpoint | 5.14 - Supply & Discharge Rates
3852c263-71d9-5225-a6b3-4bd9768ad723 | note | Reference - 610.13 (a) & (f)
3d0287a3-7627-5067-9358-82d4e0458c69 | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
11355979-e9d5-56cc-8df1-488ed01742b6 | note | ○ No water is to be added once discharge commences.
cc8c997e-6589-5b5a-b81e-5b1fc10916d0 | note | ○ Maximum time between batching trucks is 25 minutes.
cba0dca8-0b5e-598f-8be2-0515b41a6155 | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
3708679f-9bd8-5824-b67b-65d170f656ee | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
85927518-c4f0-5e86-8fa2-d776e62273b6 | note | ○ Record: Required information on the Concrete Pour Record.
fa3997f3-f5dd-5dbf-b38b-b601c8f82727 | note | Method - Measure, Visual
da8dec8e-9396-5ac0-8527-0898e10b9d31 | note | Frequency - Each load
22d3d728-7d5a-55b4-b351-da142f57d946 | note | Category - IP
a16a4b9b-3f10-504c-a640-6011a2fa7bd9 | note | Responsibility - Foreman, SE/PE/SPE
4c05bca6-3df7-52b3-9cb4-5c7610253d60 | note | Verifying Documents - This ITP, Concrete Pour Record
72a4c8fe-382d-5319-89ee-aaeaf0c70399 | date | Date Completed:
a44587c9-63ba-42bb-81cb-d052af888678 | checkpoint | 5.15 - Placement & Compaction
8e170c90-0c0b-5e39-ad15-ce70fb6ae809 | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
8172a223-bb05-5821-9077-f4e4fcdee132 | note | Acceptance Criteria - All concrete batches are traceable.
ddf759fc-5904-5839-9309-8574e5fa0dad | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
04e42bdc-e27b-54e3-8ee0-0ef5a11421a9 | note | ○ Concrete is not dropped freely from a height exceeding 2m.
d6278100-e3eb-57a2-bf76-cb4e5246cc50 | note | ○ Concrete is not moved horizontally by use of vibrators.
1762b2f1-fb48-554f-8d7e-a376931dc79d | note | ○ Adequate compaction is ensured
edac2ff5-2e26-5de9-a173-8186b9afbc39 | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
ba47821b-9ba4-519a-8bfb-3e41ab181c56 | note | ○ Concrete layers are not more than 350mm
3e45272d-50c3-5190-8c6a-2cbcca0c8715 | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
d679ecd2-918b-51c4-8ecf-754e8efbd31f | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
69e9182d-6063-58d2-8521-9eccb4b800fb | note | ○ Record: Required information on the Concrete Pour Record.
556cb067-c8e4-5d22-b881-c44b382db878 | note | ○ Attach: Concrete Pour Record
5cf3c8ef-89f8-5ede-8129-a6be6268073d | note | ○ Attach: Concrete Dockets
50e2c511-e07e-5e5b-930b-60b487121ada | note | Method - Visual
6cf0d68b-2864-5538-9352-4d84a688f7b2 | note | Frequency - Each load
8200626e-fea4-527d-b1f3-9459416e90a1 | note | Category - SP
b44fa808-bf59-5786-813f-d43c68c31ce2 | note | Responsibility - Foreman, SE/PE/SPE
b449eb35-36e1-57db-bffd-38258f2d445d | note | Verifying Documents - This ITP, Concrete Pour Record
813173f5-55bf-5834-960e-e9479b4919c0 | date | Date Completed:
d5832b38-e2b4-4cfa-b26a-eb939dcab40e | checkpoint | 5.16 - Surface Finishes
d4ed880a-2234-5eac-84b8-d1076c0fb5ef | note | Reference - IFC Drawings 610.31, 610.20
59bdef61-0bc1-51c2-bbf0-1225d7c2c960 | note | Acceptance Criteria - Surface finish as per IFC drawings.
084f865e-f092-532f-a8a5-0f933c2d0816 | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
14736c09-7fe1-518f-8c32-4184ae2017a0 | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
30d7c1bb-18e3-5be2-adbc-2e4da3c9ee01 | note | Method - Visual
d14ec8d8-16fd-584f-a4d3-3d042a741848 | note | Frequency - Each element
d95a3535-2817-505e-9cda-a5aa036844d7 | note | Category - IP
e57a0f71-93d0-5546-b296-d1767ae00396 | note | Responsibility - Foreman, SE/PE/SPE
69d89c36-561d-5767-82e7-f8cdf1ff3430 | note | Verifying Documents - This ITP
bf5f2b16-7b37-50df-b907-f9d5e7dbd2f7 | date | Date Completed:
4ba0ffbd-5f9f-4441-99c1-5063544de380 | checkpoint | 5.17 - Curing-Top Surface
7f309a94-d297-5a2b-8bcd-a0ee71440a0d | note | Reference - IFC Drawings
1ff55efb-27b1-534a-a31e-581e90ae7534 | note | Acceptance Criteria - Top surface of the pier and abutment walls shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pier and abutment walls may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
15f77de9-1019-5c56-8d6e-dfc79e3df348 | note | Method - Visual
3385b4be-f468-5a0d-bc9d-8b52d6e8efa2 | note | Frequency - Each element
0f3221c7-b73a-593f-8980-77164c4fe554 | note | Category - IP
f3860a49-13e7-5627-ad11-9152497ea0d9 | note | Responsibility - Foreman, SE/PE/SPE
2a737e81-14a0-5bb3-b152-25177b416377 | note | Verifying Documents - This ITP
5eeb84c3-1b73-597e-9049-861f0baea448 | date | Date Completed:
d97fd515-4462-4157-abad-2878600e62bd | checkpoint | 5.18 - Curing after formwork removal
5c479828-d853-5eec-8dac-1d50f2b8e8d1 | note | Reference - IFC Drawings
8f1b0721-32bf-573e-91f8-c15f589a8f54 | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
dddb9c0f-c28e-565f-8cc2-a1d22fc7d2d2 | note | Method - Visual
81288d08-f284-5c62-8daa-bb3d1fad1251 | note | Frequency - Each element
28209dba-01df-5b2e-be28-88e98b52d9a1 | note | Category - IP
14f93049-fbe4-5635-9302-3f25be208305 | note | Responsibility - SE
8fecfe20-17c9-545b-a416-ee66a2d396d4 | note | Verifying Documents - Thip ITP
742e1670-cadb-5987-8a8d-912b2bc8ed67 | date | Date Completed:
e6bd0030-d2f8-4820-86bb-e27a65728328 | section | 6. Post-construction Activities
8f98ed3e-5745-47da-ae65-7b0b746721b0 | checkpoint | 6.1 - Thermal Differential Monitoring
1d9f3d8a-f6f6-57dd-9e37-20983a7d01d9 | note | Reference - 610.22
5ba73444-f00c-5e5c-8449-c75a3981ad2b | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
2259d541-311d-539d-8a1e-05a1dd1e49e2 | note | ○ Only applicable if the element has:
7beef71d-12ac-546f-99fa-65717a165a9b | note | i. the smallest sectional dimension exceeding 500mm
697444f3-660e-5dfe-a008-a2218c0723f1 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
390e52d2-a74f-5cde-9e5d-9eeed22d50b3 | note | ○ Attach: Thermal Monitoring Report
41eda216-b2c1-5e74-a161-b16977d14850 | note | Method - Document Review
15873c77-0e42-578e-a158-898177a4b737 | note | Frequency - Where applicable, each element
0acfd335-d864-58f8-a0db-47993fa18595 | note | Category - IP
f356d62d-f879-559a-bf96-89777ba04430 | note | Responsibility - Foreman, SE/PE/SPE
426686e2-5f75-5b33-b903-853634974734 | note | Verifying Documents - This ITP
02c9099f-df72-53ea-9ff3-476e1ce5eb34 | date | Date Completed:
8c60db46-cc98-4334-ae4e-c97ba157f582 | checkpoint | 6.2 - Early Age Compressive Strength Test Results - Removal of Formwork
81e99f2e-7730-5574-a19e-40dc5689f1d5 | note | Reference - IFC Drawings
c3ecaf6d-c9d6-5fd1-8f48-20b8088d3749 | note | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
b11057af-e6a5-5467-8081-f69ecb965fa2 | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
7bc47686-676c-5eac-a93c-36c0ecfc5922 | note | Method - Document Review
fdad2ae4-9c0d-5916-a312-0307dfe2e308 | note | Frequency - Where applicable, each element
4af9be77-f5e1-5625-83b7-e501218586bc | note | Category - IP
12404fd5-fbe3-5ff6-af84-a64d89f633fc | note | Responsibility - Foreman, SE/PE/SPE
932724c3-8f28-5ec1-86fa-96f1dd2a92c8 | note | Verifying Documents - This ITP
92c8de18-f82e-5695-9087-c1d531d6af06 | date | Date Completed:
0e26af55-5e8d-4f9d-a1c9-7c0626602878 | checkpoint | 6.3 - Surface Inspection - Cracks
e815b952-7fea-5d81-a4e4-49a8dfd573e3 | note | Reference - 610.24
a3bee56f-2f8c-5ff4-8eb9-850e70ac1d29 | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
5477e511-0470-5a7b-b9bf-ac6865ce25ec | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
b36ca01e-e945-5041-8246-363c21d8f685 | note | Method - Visual, Measure
c3abb3b5-b5e8-5755-86da-95ab159679ec | note | Frequency - Each element
ca6be0ce-2d98-5ed1-b49a-a2a0bc8b8ab2 | note | Category - IP
2ed54390-f218-5839-b06e-ae1ac07bd2a7 | note | Responsibility - SE/PE/SPE
d0f1698c-1128-59c2-b464-8050ab9ac85a | note | Verifying Documents - This ITP
e46087bf-1fc2-51fe-8735-dd6080d58b85 | date | Date Completed:
8bcaa524-652e-4718-9dda-7135e2116d24 | checkpoint | 6.4 - Surface Inspection - Surface Finish
34242976-1788-50c1-8daa-d8ae112bba5b | note | Reference - IFC Drawings 610.31 (a) - (n), 610.32
3ed39506-2737-5df6-ae22-846b30e5130a | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
ad5fa12c-5561-5ad5-8f99-258a1fbae25f | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
2bea37d1-2153-591c-b6ec-ef4a7acf65a1 | note | Method - Visual
267f17e9-ebf4-5743-8970-39d19d21fffb | note | Frequency - Each element
30361bfb-550f-585c-a4ca-dc81a14bded4 | note | Category - IP
03d9db34-42b5-57ca-9ed9-6ce11ea85448 | note | Responsibility - SE/PE/SPE
c2bf484a-bd24-57d5-8fa5-152d7c3febfe | note | Verifying Documents - This ITP
181f5a90-9ed1-5c40-972a-3e89293dbf7b | date | Date Completed:
4c2f83c8-ac7e-4158-829d-4f4058229ed5 | checkpoint | 6.5 - Measurement of Concrete Cover
02213efb-099d-54c5-893c-fefe1e27cfd3 | note | Reference - 610.34
1633f8d0-e0f3-5aee-9df1-4948666730b3 | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
aedd8b8f-08b0-5f9d-a743-b3bcf14fc4e3 | note | ○ Minimum 10 no. measurements recorded in each area.
9cc27299-ddad-53d5-88f9-ea8c9aef7866 | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
d0234b76-3d84-540b-906b-2f4f50cc34c3 | note | ○ Attach: Covermeter Check Record
b59ee70b-4f64-5f59-a4fd-a9ff2a62b8a5 | note | Method - Measure
e6c22414-c8a2-5441-8ae9-3ea1feb58f73 | note | Frequency - Each element
0f33c597-83a6-5556-968f-3e9010f6fa37 | note | Category - IP
dc898187-edd7-5df9-a0cd-c12a7861bc7c | note | Responsibility - SE/PE/SPE
2e084dfc-6d95-5c7a-9f5c-38bbba55df2d | note | Verifying Documents - This ITP
a253a706-797f-5391-a367-22925a5b11cc | date | Date Completed:
a8dfaab1-ba8c-4671-a0cf-c5bc1296a7f6 | checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
71912b10-06e5-5e92-aa91-60ff25e45d6e | note | Reference - Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
ba10c67e-6442-59c5-8f6c-4c35bf63e91b | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour.
afb7f9f3-ab42-5e66-937a-dbc163c7c2d0 | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
5d5832e6-fe7e-58ea-a4ed-2a7ffd7a8f4a | note | ○ Attach: Concrete Test Results or Maturity Test Results
da27c7d9-0eb7-5336-8f3a-b0b9d66cd2cf | note | Method - Document Review
a20a29d9-e7c7-5dc5-bd87-6a679eaf3f10 | note | Frequency - Where applicable, each substructure element
801f12bf-25cf-5a74-a6c0-51447633de86 | note | Category - SP
66d8784c-0d95-576f-a95b-12ea36bacbd3 | note | Responsibility - Foreman, SE/PE/SPE
349f3f4f-4c7c-5de6-a55a-76f9e3259e37 | note | Verifying Documents - This ITP
ca0cdcfd-52d7-5689-a3d1-fdbdf242e82f | date | Date Completed:
92aa32c2-3b68-4989-ae2a-5c0dee1e3d0d | checkpoint | 6.7 - Compressive Strength Test Results
1a22bdd6-e623-5869-b42f-7cf5b0b311a7 | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
51bdf8ad-7f06-5eb7-9b09-09eb9fb57d5b | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
321cbd41-5f7a-5ff0-9464-5650f855814d | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
c609fc5b-af67-55b7-b32e-042f79e38032 | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
99d064a6-3320-5adb-9d85-6b841ea1be41 | note | ○ Attach: Compressive Strength Test Results
0eb26967-c9a9-5b21-aa22-2a975d13c0d5 | note | Method - Document Review
7c9edcbd-6572-53b3-b872-1a3376092ce2 | note | Frequency - Each cylinder
08c6464b-1ea9-58f0-b4c3-939a70cff449 | note | Category - IP
64af92c9-331c-5a39-aa34-f68a1b9d90ad | note | Responsibility - SE/PE/SPE
cab1de28-f875-58d8-ab13-4aad7497d218 | note | Verifying Documents - This ITP
73867b47-26c5-5afb-881d-b02780446e85 | date | Date Completed:
a73f4d96-f294-492d-bd79-e364fdf66dd1 | checkpoint | 6.8 - As-built Survey
53fad8a5-4e6e-57a9-8a32-69ad3a9116e8 | note | Reference - IFC Drawings 610.47 Table 610.472
b3347fda-371a-542f-b891-34f5729ec34e | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
5ac6ba29-171f-5116-a83a-a4622db97c79 | note | ○ Attach: Survey As-builts / Survey Report
930f977c-67dc-5819-b82e-eb41cf97f618 | note | Method - Document Review
d38d9863-f77e-5de4-bf69-82eeda551f24 | note | Frequency - Each element
2d7148f1-06f6-5bde-b3e1-7265a24447c7 | note | Category - IP
8be5947a-6f3e-57da-a173-80aa1866c76e | note | Responsibility - Surveyor, SE/PE/SPE
c71ec465-e7b3-55d6-a6e1-745f57d02685 | note | Verifying Documents - This ITP
fd08d09c-8fa0-53d0-96bf-9138d04c843d | date | Date Completed:
a2bb5c8c-bab4-4dc5-bf08-a4557623635a | checkpoint | 6.9 - Non-conformance Report (NCR) Closure
d779c4a0-622e-56f5-b189-d06dae6adf76 | note | Reference - MRPA Quality Management Plan
407b7acb-5057-58b0-ab6a-b93bcab622e5 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
cadc2708-1327-5ca8-8f56-3ff5d90cef21 | note | Method - Document Review
c5636885-21a8-5599-a60f-31f1e65d26c7 | note | Frequency - Once, prior to closure of this lot / element / Work area
5ab2ac75-64e6-5cbf-bb4a-bea0a87447ab | note | Category - HP*
c2eda6d8-7d9a-5ab3-8e6f-c3c39ac2d8a9 | note | Responsibility - SE/PE/SPE
87e520ec-acc7-5b18-8028-018efeef1af5 | note | Verifying Documents - This ITP
b120c6b5-424a-58e9-ba30-0fb4550c0479 | date | Date Completed:
884e7b6a-6584-45c9-8432-1b9533b855c5 | checkpoint | Final Inspection
e71f5bcc-2316-5fc2-86a2-2552a9134b3e | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
9a846e71-b567-5108-947b-82e7c84184fd | textbox | Name:
2c9bbd1a-dc59-5acc-bd5b-33ac9b2ecaff | textbox | Position:
20f9c857-221e-54e1-abb9-39fd31a9dcf2 | textbox | Date Completed:
a1efeb6a-0470-41d6-8690-f498fe263185 | signoff | Sign ITP
ab1c69e3-aa1f-4b3b-9b74-be80b1461d6e | checklist | ITP-325-CIV-ADL Landscaping - Ground Preparation Rev 0 | itp | ITP-325-CIV-ADL Landscaping - Ground Preparation
e64f1985-6bd6-4a6d-982b-af5c07494a80 | section | 1. Referenced Documentation
017dd8cd-b458-4d41-9b79-b4aa10f5dd71 | checkpoint-no-value | Referenced Documentation
c6e224f5-6474-51fd-9f5a-61723aa80409 | note | Document Title: ITP-325-CIV Landscaping - Ground Preparation
b8ab0cb9-ed48-5164-86b2-fe5cee0aa5af | note | ITP Description: Landscaping - Ground Preparation
e7a54dd1-daf5-588b-ab2a-1cf9721802e7 | note | Discipline (e.g. CIV/STR/RAIL): CIV
b4628ce4-d2f5-5b83-a22f-188d86ba47aa | note | Revision Number: 0
ab07bf75-9843-536e-9e9e-399b957f0a26 | note | Revision Date: 2/10/2025
24f43505-15f8-5d9c-b25d-7943c3957f85 | note | ITP created by: Will McCuskey
42d9c631-8941-5806-a27c-17214c5f0d51 | note | ITP approved for use by: Romualdo Magpantay
b79a57d7-bcd4-5d2c-8f5d-103059a3e30b | note | Referenced Documentation: VicRoads 720 AS 4454, AS 4419 IFC Drawings
cfd61077-f99c-48d5-8d15-dc7ddb668abd | section | 2. Preliminaries
bd0290a3-6687-4ac2-8955-6b31f72cff45 | checkpoint | 2.1 - Check for correct documentation
c940038a-9cdf-596c-bc67-5e98aa4ddcd6 | note | Reference - Drawings and drawing registers
1af0bb77-2e54-5eb8-8d76-87f15917463e | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
c1d2c03f-7e2a-5a3f-958d-a6707690115a | note | — Using the correct and complete set of IFC drawings
0a38a38f-76c6-586b-98fd-275287255f64 | note | — All drawings are the latest revision
12ac42cb-b726-5daf-b040-8b8281d459ec | note | Method - Document Review
6e966097-ec9c-5545-8b22-503d7ff74f9c | note | Frequency - Prior to Commencement of works
846dc105-a6eb-5313-bb01-56f067098b88 | note | Category - IP
7c2f28e3-01e4-58db-9e22-4bac4613a009 | note | Responsibility - SE
50251484-f2cd-5672-aa0d-9fab83f9f564 | note | Verifying Documents - This ITP
f3c18405-e855-5350-9de8-eab1fbe9d4ec | date | Date Completed:
eaea6d11-ff8c-4a4a-99bf-a15ead7da6b1 | checkpoint | 2.2 - Submission and records
7faab33a-1d83-5c08-a112-e0e2066d1749 | note | Reference - Section 720.03
fa43915d-80e9-5b3f-b22f-15f296d9d649 | note | Acceptance Criteria - Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery.
56ba813f-92aa-5061-8534-4aa3ec73ac57 | note | Following information shall be provided to the NA:
5e8c9dd5-50c5-5f16-82dd-139a1cd64cf6 | note | ○ Samples
b4085dbe-c323-503f-8af6-f0031b83e52b | note | — Mulch
a1b0b038-0558-5099-9594-59fdfb663277 | note | — Imported topsoil
557c274e-86e7-5f82-8e81-f8682e96a97e | note | ○ Records
c7c04258-9e94-5a27-aec3-c8858a1bad39 | note | — Details of suppliers
1323f239-e9e0-5ef8-9c68-2ee36ff071a9 | note | — Soil tests on imported topsoil
496e2f82-90c3-5a89-99d3-7257aca91120 | note | — Copies/Photos of fertiliser labels
e9946c57-d298-5c89-94b0-06a6b69515bd | textbox | Enter: TeamBinder Approval No.
02047e68-ee44-5f7a-a7e5-b3c26dcddd6b | note | Method - Document Review
c098524a-6e68-5d94-9185-4365f2283686 | note | Frequency - Prior to Commencement of works
28cd6b1e-f772-5800-8894-b6b43f0276f3 | note | Category - IP
25e4fab4-1723-5742-a354-12dda15326be | note | Responsibility - SE, NA
9ac2ce40-3892-5ab7-b9ff-3821f91d5c9d | note | Verifying Documents - This ITP, Issue to TeamBinder: Records & certificates
7a8a9e06-f40a-5798-8449-72c2303b7e4f | date | Date Completed:
d9a58d26-545d-41a4-ab5c-c306fdeaee77 | checkpoint | 2.3 - Supply of topsoil
03d16ad4-5750-5733-ae8f-97279dfd7d22 | note | Reference - Section 720.04, Table 720.042 IFC Drawings
805eea4f-5d68-584b-bad1-14e11c1eafe3 | note | Acceptance Criteria - Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor.
24d5ab4e-2e91-5200-829a-8bc51a38afc2 | note | ○ Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings .
15204400-bde3-5833-9de2-960da7507b39 | dropdown | Type: | Site won top soil,imported
5f110af8-feee-5e88-a719-11ae1897c635 | textbox | Enter: TeamBinder Approval No.
5f34bf6a-bc42-5e84-b1d1-b7e6fed39d35 | note | Method - Verify, Doc. Review if applicable
56e8d952-c895-581f-a555-0e20186a2fd1 | note | Frequency - Prior to Commencement of works
90f0a87c-e98e-509c-87d5-165d4268b1e9 | note | Category - N/A
f5b72ea8-d666-5758-8da1-c3ee41112179 | note | Responsibility - SE
adf458b1-7078-5791-af1d-eaeb62a903f0 | note | Verifying Documents - This ITP, Issue to TeamBinder: material conformance docs or Test Report
7090a9da-da16-5b59-8c23-3b783b3cf5f6 | date | Date Completed:
1466babb-0c26-4eb0-8c8e-2b145c6a7ecd | checkpoint | 2.4 - Supply of Mulch
f46a5f6c-4a49-5c87-a78e-ccabe773dcc8 | note | Reference - Section 720.04, Table 720.044, AS4454 IFC Drawings
7296e37e-ccfc-5678-b0c7-c2dd09678d60 | note | Acceptance Criteria - Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings.
45c525be-be74-58cd-9ea7-3a0db3ab17dc | note | ○ All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings .
ffa5f225-2407-5246-82b4-b711fcb5bfb4 | note | ○ Imported Wood Mulch shall comply with Table 720.044.
39982fba-5c57-5410-9f15-11679783bafc | dropdown | Type: | Site won mulch,imported
5196b210-b12b-5a3e-a629-61d7f710dba1 | textbox | Enter: TeamBinder Approval No.
e2802317-55f9-5808-b2f3-78c0a41b123a | note | Method - Verify, Doc. Review if applicable
0abd0f2f-97bb-5837-8c4c-ed268e884b52 | note | Frequency - Prior to Commencement of works
6e27a768-eaef-5b47-bdfc-0ff5b13036d7 | note | Category - N/A
cc0fd01f-58aa-5b61-86c6-afe6d6feb559 | note | Responsibility - SE
bae977c9-d738-590a-8470-79854bcaa694 | note | Verifying Documents - This ITP, Issue to TeamBinder: material conformance docs (if applicable)
502df3d5-71f0-5ce1-83d6-26b765cfce73 | date | Date Completed:
5b53205d-f2ed-4e87-9f0f-6d8ee54378ca | section | 3. Site Preparation
a7337265-b5e8-4d13-921c-a40394824f4a | checkpoint | 3.1 - Set Out
ac8ad6ea-fd6d-5842-b1a8-a5b42780a885 | note | Reference - Section 720.06 IFC Drawings
a393f5f4-419a-5b25-9c70-174bbfa5bf0c | note | Acceptance Criteria - The Contractor shall set out the location and shape of planting areas in accordance with the Landscape Drawings.
fa7ae801-1324-5a07-9e55-465b7666a9e3 | note | Method - Inspection
6b729950-b552-5d24-994d-5db52b2f0960 | note | Frequency - Each Lot
858f38cc-33b5-53ea-a2fc-d197966efdee | note | Category - WP
98cc05a7-b49e-54b5-a809-151fd226d8b2 | note | Responsibility - SE/Site Supervisor
335905da-69a4-5936-92f8-08756b6323ec | note | Verifying Documents - This ITP
adef5803-85a5-542f-8874-83d2a576d311 | date | Date Completed:
9d35eec3-f67c-4a6b-82a8-28dead380ca4 | checkpoint | 3.2 - Soil Additives
bc337090-6979-522b-9e86-26f5c20b9ce7 | note | Reference - Section 720.07 AS 4419
05bbd45d-113c-5420-893d-24f5fe552d3d | note | Acceptance Criteria - Soil additives, including any material used to modify the chemical properties of the soil, shall be applied by the Contractor prior to physical ripping and cultivation and in accordance with results and recommendations from site topsoil analysis tests, if applicable.
b6070ab0-58f4-5647-8def-9c8772d4c3fa | note | Method - Document Review
eb59210b-1175-525b-9034-829dce11f419 | note | Frequency - Each Lot
430d41b4-5a07-5d6f-98b1-ba819449eebb | note | Category - IP
8e135c78-4868-55cf-8365-d986e811e9dd | note | Responsibility - SE
41dbea3d-3db2-5f83-bc0c-8aaa24d20af6 | note | Verifying Documents - This ITP, Attach Test Report
26e19b42-7362-518e-8f49-57ab4473c771 | date | Date Completed:
542b9349-aa57-4dad-acb8-39e806d6deac | checkpoint | 3.3 - Ripping of subsoil
54ca2416-1a4d-5f5f-aee0-7e35fa076c66 | note | Reference - Section 720.07 Table 720.071
06b48e9c-5ca9-560c-891d-5434b72e6001 | note | Acceptance Criteria - All ripping works shall conform to the requirements of 720.07
16cb6508-a0d1-5127-b9b7-afb7895e537a | note | ○ Situation- Ripping of subsoil
97711655-762f-5167-8d96-0244e5f8c52b | note | — Planting Areas in disturbed areas flatter than 3h:1v= min 400mm deep at a max of 500mm spacing
853c3bc9-8eee-5817-9e3c-ce86dc582b58 | note | — Planting Areas in disturbed areas steeper than 3h:1v= min 300mm at a max 500mm spacing
0836c9ed-2b23-5e85-8c50-0adf11992725 | note | — Planting Areas in undisturbed areas = Min 400mm deep at a max of 500mm spacing
b8695e3b-f347-5429-90c6-4d499e065836 | note | — Grassing in disturbed areas = Min 200 mm deep, 500 mm max spacing
7a98ee99-4ead-5638-9855-70ea5abd82b3 | note | — Individual Tree Planting within grassed areas = min 400mm deep at a max of 500mm spacing
a020c1da-0eaa-5568-ada8-6d637241519b | note | ○ Note: Ripping shall not occur within the extent of existing vegetation areas marked for protection or within the drip-line of existing woody plants.
4785734e-70aa-54b1-b951-3c83ea706c79 | note | ○ Do not proceed until the NA inspects and acknowledges requirements for ripping have been met.
1dc2a767-953b-59b9-bbe9-f3bbf95d975a | note | Method - Verify
bcf785e7-0b5f-5ca7-aca6-dfc8868678b8 | note | Frequency - Each Applicable Lot
4687c63f-e6e3-5eec-b66e-3018ccdd6723 | note | Category - HP
c0ee5a2a-f174-53ba-af66-3b2b7c78cf5d | note | Responsibility - SE, NA
e89932ac-5d18-5ace-a4c7-5e9a2a7b2608 | note | Verifying Documents - This ITP, Attach Lot Map/Marked Up Area Inspected
27d18b96-b51c-5348-990c-aed8deb28aa9 | date | Date Completed:
91a9f5c8-276e-43aa-a58f-fd1d151ade95 | signoff | AUTHORITY HOLDPOINT
eda1a599-51be-42f6-b1f2-6d16f1527fb3 | checkpoint | 3.4 - Edging
a616aa15-4a74-521f-a3c0-cad994885d3e | note | Reference - IFC Drawings
3f2bc6e3-dcb5-55b3-93c5-637772db11fb | note | Acceptance Criteria - The Contractor shall set out the location and shape of edging in accordance with the IFC Drawings.
82adb20c-ab5d-59c0-96e0-4853e2b6320d | note | Method - Verify
82a7d993-15fb-5946-b4f3-d846c539f6ea | note | Frequency - Each Applicable Lot
13f3c20c-440e-5295-8d20-00bb627b7342 | note | Category - IP
58231edc-eef4-5158-b93b-c2eea0784399 | note | Responsibility - SE/Site Supervisor
12f4e5c3-0796-5e98-b614-d4ed4af8cef8 | note | Verifying Documents - This ITP, Attach Delivery Dockets if applicable
5365b992-fa7d-5438-93c1-3beacc627ec8 | date | Date Completed:
9b02e5d6-df70-4ebb-9586-48bc1dc4c5ff | checkpoint | 3.5 - Topsoil application
fbb53508-d82f-57e0-9b82-aceedf03e5a8 | note | Reference - IFC Drawings Section 720.07
5a1eea5c-8684-5ab0-8858-a00fea6d3908 | note | Acceptance Criteria - Topsoil shall be spread on planting areas and grassed areas in accordance with minimum top soil depths stated in the IFC Drawings
8b140383-e125-5bba-8711-70bf7472a308 | note | Method - Verify
1b04d2d9-1624-5e60-b3f8-30b45a4a92e6 | note | Frequency - Each Applicable Lot
c3d5a805-daf4-55a7-936c-f96d4f87cfea | note | Category - HP
2a46fab7-27d0-52f5-8e34-dd86db847642 | note | Responsibility - SE, NA
8c543cc7-d992-5038-8922-1b85ee4094e1 | note | Verifying Documents - This ITP
e3f93351-c75d-5576-9147-29bef655c386 | date | Date Completed:
28e66aac-2cf6-4395-9704-9b221b42ba29 | signoff | AUTHORITY HOLDPOINT
48023dbb-e63d-428f-b8be-6146ddf9d636 | checkpoint | 3.6 - Cultivation
9595721f-b6b6-54fa-9153-91ac0a182147 | note | Reference - Section 720.07
2613f4e4-b0af-5abb-8ecd-e26d9ccac3ec | note | Acceptance Criteria - Cultivation will only take place if easy manual excavation cannot be achieved to 300mm or deeper.
6640a9bd-f2ae-509f-8e1e-05f1dc4ff25a | note | ○ If easy manual excavation is not achieved the following will take place
cc137377-168e-5ac5-b43a-3a8ca55cc6c8 | note | ○ Situation – Cultivate- Table 720.071
bac0545a-42d1-50db-8332-f0f5abeb2367 | note | — Planting Areas in disturbed areas flatter than 3h:1v = 150mm Minimum
956b7887-dfd1-543f-a5f7-665af4c9a86d | note | — Planting Areas in undisturbed areas=150mm Minimum
acde8ad3-71b2-545b-b5d9-feb317cec761 | note | — Grassing in undisturbed areas = 100mm Minimum
8b71e644-6250-560e-aab7-b6723ad0af44 | note | ○ Note: Cultivation shall not occur within the extent of existing vegetation areas marked for protection or the drip-line of existing woody plants. Hand cultivation shall be used within root zones of trees to be retained.
73701bdb-c8a0-5090-826a-e37f22d780c4 | note | Method - Verify
cba5e68c-a7c1-5aa3-8714-b89d64e14c29 | note | Frequency - Each Applicable Lot
f854a1d7-e0fc-5ef9-91f7-17dfbdb06eee | note | Category - HP
69b596f8-0f17-5a06-88d4-ba63a30f936d | note | Responsibility - SE, NA
45f858cd-6835-5ad8-ad1c-665cef29f6b8 | note | Verifying Documents - This ITP, Attach Lot Map/Marked Up Area Inspected
04828738-7c0e-5cdb-bbdf-d1bba63738e1 | date | Date Completed:
ef273cd8-7453-4732-a0e1-f6bc2877af53 | signoff | AUTHORITY HOLDPOINT
349a1f61-4c12-4bbe-8a7a-7688d33914fe | checkpoint | 3.7 - Topsoil FSL
a7496326-2548-51e6-b1f0-49e07d2d20e3 | note | Reference - Section 720.07
03b8626c-e787-5924-9cd6-d9f0b4a73d99 | note | Acceptance Criteria - After cultivation and trimming, the Contractor may lightly compress topsoil for stability on slopes.
79c30bda-1bcf-527d-8dc7-2743ad72ddc3 | note | — Vibrating plates shall not be used.
368c3bcb-cde4-59da-a857-cc0b1e13a787 | note | ○ The finished level of garden bed mulch and/or topsoil shall be tapered so that the finished mulch and/or topsoil levels meet flush with the adjacent surfaces.
bc80d215-e2c2-5e5b-8d3d-c407544c5bc5 | note | ○ The finished level of grassed areas shall be:
9b394ec1-bf52-5828-8eb4-815a1aa340a6 | note | — not higher than 125 mm below weep-holes or damp-proof courses in adjacent walls;
9d0c365d-1614-57bb-b500-a5d0eed7464e | note | — level with the bottom of fence plinths;
5f0334db-88b0-5abd-8ee7-8736d30991f7 | note | — level with adjacent pavements, kerbs, pits and other structures.
e575af95-0493-5b00-8f6d-e88a1eea8c31 | note | ○ Do not proceed until the NA inspects & acknowledges requirements for topsoiling and cultivation have been met
7ca47438-33bc-59a9-95d6-23b711fa6e25 | note | Method - Verify
ea2e247d-a318-53fc-8d5d-7f04971531a1 | note | Frequency - Each Applicable Lot
5b93dff1-046c-5914-b640-c62163ec8912 | note | Category - HP
b0594b99-6c9d-50d5-9d6a-8b529eaa7391 | note | Responsibility - SE, NA
404bf0e4-eb4a-5ad2-9ed3-5f3c5e9b29d9 | note | Verifying Documents - This ITP, Attach Lot Map/Marked Up Area Inspected
6a365f83-c5d5-56ac-96bf-e04826d1190d | date | Date Completed:
a4bbfcc9-a43c-421f-b737-4c182048795c | signoff | AUTHORITY HOLDPOINT
8494da5c-c10d-4280-9f91-d0ddca0525dd | checkpoint | 3.8 - Weed and Erosion Control Mat (if applicable)
eab9a860-4ef8-5020-8709-0962c288c7ac | note | Reference - IFC Drawings Section 720.04 i)
dd32bf15-9d7a-5dd2-8045-4b4d132fb715 | note | Acceptance Criteria - Jute or approved equivalent to be installed as indicated by the IFC drawing.
fe7a9162-ee76-5aa2-9a6f-867c0811727f | note | ○ Jute mat to be installed where specified on IFC drawings for planting areas steeper than 2:1 and in planting areas prone to flooding or within 2m of waterways, swales, wetlands and sedimentation ponds.
a17d802d-fb7c-5542-a4cc-1e7bbaebfaa0 | note | ○ Mat shall be laid and anchored in accordance with the manufacturer’s instructions.
7aebe136-e831-5d8d-b695-efcd35879f3c | textbox | Enter: TeamBinder Approval No.
7ee33a82-3a5d-5b3a-8fc7-08efbb2eb5fd | note | Method - Verify
30c1974e-8545-5e11-8e94-385c4b4aed81 | note | Frequency - Each Applicable Lot
181197f4-efbe-5bb3-ba2f-e6335ef6b3be | note | Category - IP
49c4853f-2924-5923-b983-55e7a5d898d5 | note | Responsibility - SE, Site Supervisor
d15fed53-fca1-53e8-9663-6d840b29aef3 | note | Verifying Documents - This ITP, Reference TeamBinder Material Approval No. if applicable, Attach Delivery Dockets
71c53807-a1ad-5c8a-9d44-2520481bf48c | date | Date Completed:
487f923f-e5a7-458d-a23b-687bec4fc99a | checkpoint | 3.9 - Mulching
87d2b2a6-de16-597b-9a6f-29beb8e3a35b | note | Reference - Section 720.08 a) IFC Drawings
312c6d83-965d-5925-8991-97e3cc748205 | note | Acceptance Criteria - Wood mulch to be placed at all planting areas unless specified.
add241bd-95b9-5566-ad13-feb8e7c30eb4 | note | ○ Mulch shall extend at least 1 metre beyond plant centres at the outer edges of all planting areas.
1daffa72-9041-54af-bb45-dd2972a45921 | note | ○ If space does not permit this, mulching shall extend to the back of kerb.
b77189ad-4819-5e48-be1e-54c24ed89882 | note | ○ Ecodynamics shall install mulch rings around individual tree plantings.
0dd8ba16-ec19-592c-823c-b1e456b0d7ea | note | ○ Mulch depths in all situations shall be a minimum 75mm and maximum 125mm.
c9043ea5-d3a3-51b5-ace1-c62c6f32f922 | note | ○ Mulch shall be raked to an even, neat appearance and kept clear of plant stems to avoid collar rot.
9fde8319-ab94-5d1a-bb1a-836ea92a5f2c | note | Method - Verify
472e28ae-c915-5287-88fa-00a52fe98dc9 | note | Frequency - Each Applicable Lot
992446b3-0985-52f1-ba4d-dfd796776555 | note | Category - IP
96a9552e-d206-5983-8d66-ec10a6243a15 | note | Responsibility - SE, Site Supervisor
a8a36f63-b5c6-52d3-b596-41a7fb30c427 | note | Verifying Documents - This ITP
abb5a945-175a-527f-83f3-d6d12096821c | date | Date Completed:
44d9d80c-651a-4947-9b06-86e0188920d8 | checkpoint | Final Inspection
b884f18c-aaa5-501e-82e6-d36774bb405f | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
d0070b11-e099-5e99-a95c-ce4a7acb3c15 | textbox | Name:
de76b6df-6fd8-5278-a7f0-f2b543dccaf4 | textbox | Position:
bb86abcc-5e3f-5489-8eb1-9f78cac01dbe | textbox | Date Completed:
0d8961e1-0256-42a1-a30c-4b740921c85e | signoff | Sign ITP
91aa65b3-edad-44b7-beb3-a72cd01e6176 | checklist | ITP-326-CIV-ADL-Landscaping-Planting Rev 0 | itp | ITP-326-CIV-ADL-Landscaping-Planting
a086cdcb-bd3b-4e0e-8a69-31bdb878a748 | section | 1. Referenced Documentation
b19c78d2-1013-4ab1-a641-a95954356257 | checkpoint-no-value | Referenced Documentation
f2bf475f-0d44-5ed4-9871-2b75598d5832 | note | Document Title: ITP-326-CIV-CPD-Landscaping-Planting
3e2b879d-420f-523a-babd-7fcc7ca290ec | note | ITP Description: Landscaping - Planting
e70e0011-236b-55c1-baa0-d8555e936b2f | note | Discipline (e.g. CIV/STR/RAIL): CIV
b67fe590-aee1-5b3b-b0ac-a4205e5ea1b2 | note | Revision Number: 0
134daed6-9f1a-50dc-bab4-270f4284c799 | note | Revision Date: 1/10/2025
3f6beacd-5a86-5d5d-bd75-dd3acc850e30 | note | ITP created by: Will McCuskey
4ca4669f-fad0-50a8-afe8-297a5809276a | note | ITP approved for use by: Romualdo Magpantay
2aa4daec-19e2-5bfa-b9a9-968aa4e85756 | note | Referenced Documentation: IFC Drawings Vic Roads Section 720 (Jul '24)
d0a9a349-6e5b-4b6b-b430-778ceabf442c | section | 2. Preliminaries
7df598ae-c08b-4a10-8c69-e525480ba96c | checkpoint | 2.1 - Check for correct documentation
d701cc4c-5013-5100-a341-24f93a8d3e76 | note | Reference - Drawings and Drawing Register
d80f1795-ab43-5570-b604-e6a739c4fc05 | note | Acceptance Criteria - Ensure that all employees and subcontractors are using:
88529cee-8b4b-5870-97dd-2b314202ccf8 | note | — The correct and complete set of drawings
7e6fd37d-edc5-5c45-8301-994bc46c227a | note | — All drawings are the latest revision
29d6343a-03b0-59ec-b281-edbe5617f6a2 | note | Method - Document Review
d2b8f00f-7b7a-5872-a756-493a5fe25427 | note | Frequency - Prior to Commencing works
4bad9abf-d8c0-51bb-8a93-d0008735f191 | note | Category - N/A
2210b623-c657-5d3c-a374-3b5ce2d087bb | note | Responsibility - SE
ca015b8a-2f3c-532a-a0c5-26b0c6031186 | note | Verifying Documents - This ITP
115cf146-b06c-5ebf-bec1-b1b2fd1aeb6c | date | Date Completed:
160b505d-abac-4886-a26a-35da28b5d7f5 | checkpoint | 2.2 - Submission and records
401f6a0b-0238-5173-bdda-83d3d20a7918 | note | Reference - VicRoads Spec. Cl.720.03
387e80cf-e4c4-55be-ad27-06495dee7392 | note | Acceptance Criteria - Inspections, Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery.
3ee97390-164b-51ec-b9e3-d8372213a60b | note | ○ Following information shall be provided to the superintendent:
feb14141-59cf-53f3-968d-182ddc46f92e | note | — Inspections of plant stock for all plant species
f5d99f1c-2e5f-5282-928b-3f727d2ad346 | note | ○ Records:
e7d27438-c6ab-5d3c-865d-b808d8da9fbd | note | — Evidence of origin of indigenous provenance plant material
cf253213-3892-54f7-b8a7-396945824c77 | note | — Analysis certificates for grass seed
428b8002-c484-522f-ac5d-3d400e58ce3e | note | — Details of suppliers
00414330-8b5c-5f20-8c74-bf54354a371a | note | — Copies/Photos of fertiliser labels
faf2336a-3e9d-53b0-ae29-f8e65075c20f | note | Method - Document Review
eafa98d9-7db9-5082-919a-ad0cc1c9476e | note | Frequency - Prior to Commencing works
4da595c4-81ec-57bb-a5d2-518a5fa3447f | note | Category - HP
5d2749c9-2c62-5960-bee4-5b969c75fb78 | note | Responsibility - SE,Superintendent
d0818052-50df-5429-8d14-6280b48e261b | note | Verifying Documents - This ITP, Attach Records to TeamBinder Approval Form
42e2700d-3afb-5737-9566-7d895a207852 | date | Date Completed:
79e59904-7201-463b-966c-1ccd26194ff3 | signoff | AUTHORITY HOLDPOINT
6a71988b-8ae0-40ec-a234-977c22cc15ca | checkpoint | 2.3 - Supply of Plant Stock
f1500ae3-47fa-5101-abc6-eb88c00f524b | note | Reference - VicRoads Spec. Cl.720.04, Table 720.041
35146e33-ec55-5da5-b50c-e6d9ee4ddea5 | note | Acceptance Criteria - All plants shall be of the type, height, container size and trunk caliper specified in the Plant Schedules, Specification and Planting Plans.
ab416920-1ae0-59f6-aed3-3918ba64b28e | note | — Plants are to conform to the supply properties specified in Table 720.041
09a5232b-b193-5ca5-ab21-3325caa63b1d | note | Method - Verify
8de05b80-af08-5670-a200-0256be6ec036 | note | Frequency - Prior to Commencing works
94b5f81a-e3b2-52a9-9005-f70430eabe4e | note | Category - N/A
ca17d9d0-26fd-5464-8932-78840a0a0a22 | note | Responsibility - SE
e6046f0e-c767-5202-a3d8-7ce077987c3e | note | Verifying Documents - This ITP
6f674b8a-eeb6-5e0f-832b-def999909d9c | date | Date Completed:
3615bc4d-b070-4e54-9801-f60319359ade | checkpoint | 2.4 - Supply of indigenous plant stock
eb1f3798-503d-51ac-a943-50e252ec318b | note | Reference - VicRoads Spec. Cl.720.04
34938114-9587-5d7d-a290-2702d182eed0 | note | Acceptance Criteria - A species listed on the planting schedule shall be classed as an indigenous plant if the plant is likely to have occurred within 10 km of the project site (pre 1750).
4cab1620-10d1-55fa-a6f9-327cc5786831 | note | ○ The Contractor shall submit documentation of origin of indigenous provenance plant material which shall include the following details for each seed lot:
4011296d-d7fa-513c-9676-91d8ffb269dd | note | — species name
2c694ef2-5972-56d9-b997-8ecff8c99cb1 | note | — storage code
dd3f1fc0-36ad-54cb-9f0d-691810d6f08e | note | — collection locality - Latitude/longitude or AMG
00fce1f6-53f2-59ed-9b28-54ee37cacbe7 | note | — approximate number of parent plants sampled
1061fc35-b081-5d9c-aacd-9255b005d023 | note | — approximate number of plants in that local population
b9f8253c-a7f3-57f8-871a-1ea321f8e5e2 | note | Method - Verify
4962e758-6cc9-5a6c-9472-d71f45ee80d6 | note | Frequency - Prior to Commencing works
82b2e3f9-3eaf-50a1-b9a0-6f08628850d4 | note | Category - N/A
f70c0dc7-b8b9-58ab-81c3-7abd1fc45a2c | note | Responsibility - SE
ecd8cb5d-4f68-522c-8c9b-29fc8f836761 | note | Verifying Documents - This ITP
3b6c56ab-3c29-59f7-953b-79c223a88b85 | date | Date Completed:
9f0d86ba-1416-49b0-b7e2-81b6264d0ef5 | checkpoint | 2.5 - Supply of grass seed
05251ca4-9d11-5f18-bb42-dcc13be0fe9d | note | Reference - VicRoads Spec. Cl.720.04, Table 720.045
d36809f8-54f9-5296-b7a9-ad1165c89a88 | note | Acceptance Criteria - Grass seed shall comply with Table 720.045
33576e61-e960-5d52-bbcb-8f27430b4efe | note | Method - Verify
c82d20fe-6d3c-54d3-a383-d3982540837e | note | Frequency - Prior to Commencing works
aad9c3ad-5b69-5f4f-9866-d435eead4d8e | note | Category - N/A
5ec7b702-bb26-5157-b9cd-f2ea91fb1649 | note | Responsibility - SE
62acbc35-fe23-5dae-98b0-2f9521849fd0 | note | Verifying Documents - This ITP
b65f4e41-3250-55cf-a8e9-83bbc91a972a | date | Date Completed:
ddc3a883-a08e-44fc-bec9-58b4be2aff91 | section | 3. Subcontractor ITP
29b205e1-cb9e-4818-bc71-f7e4eba0d5fb | checkpoint | 3.1 - Subcontractor ITP
307441e1-3bfe-5f50-a897-58fbbdce9fd2 | note | Reference - Subcontractor ITP
cfddfd0d-3c46-5a7c-9daa-0d61c79d6aff | note | Acceptance Criteria - Subcontractor ITP to be reviewed and approved by MRPA.
6e54de1e-f56f-5a6f-ac69-7eff1eab6b65 | note | Method - Document Review
f2ab1917-1121-513d-b454-132303360f4d | note | Frequency - Each Lot
ed88fb39-bee0-5498-b0b1-d4e546701b96 | note | Category - WP
7c7392f7-8ffc-5fcd-b360-a58b91fb5945 | note | Responsibility - SE/PE
07bee376-24b2-5a65-893c-fb8d816eab13 | note | Verifying Documents - Sign ITP
e84f05df-703d-5575-88bb-f58190366438 | date | Date Completed:
c8ac9a0c-2324-48d8-a70e-e9a3c2e8c398 | section | 4. Pre-Construction Activities
3432213e-1196-43c0-95df-53215ef316ff | checkpoint | 4.1 - Planting Section Approval
b3e3a137-a724-5965-a5c1-3f9f6c0adf92 | note | Reference - VicRoads Spec. Cl.720.06, Landscape Plus Planting ITP
e582688f-f276-532b-a895-3c494a50af55 | note | Acceptance Criteria - Trial planting sections have been approved by the Superintendent. These approved sections shall be used as a reference for the remaining planting works
55e74694-56b0-5e8c-9f33-6c05338c42e9 | note | Method - Verify
4e38917b-e5f4-5326-9ae4-a8ec1ae54ac9 | note | Frequency - Once
3f9daa2d-7a3c-56de-8d93-2f7b7fa3f4c4 | note | Category - HP
74a7d385-05f6-523e-8ee3-3303544a0546 | note | Responsibility - SE
8ec5d320-df21-5d85-9772-d67bdcb7a1db | note | Verifying Documents - This ITP
2fda3822-8217-587f-a8c8-439c8b0dbff8 | date | Date Completed:
2b89693b-b637-42ec-bd37-32176fb01ab7 | signoff | AUTHORITY HOLDPOINT
cbe2fef9-4ff3-427b-8113-b04533b01b6d | checkpoint | 4.2 - Pest and Weed Control
eaafb9f5-ee88-520b-a1cc-3904afbacd73 | note | Reference - Cl.720.05
db0d9dc9-b8e1-52a3-b3f5-db007735ae51 | note | Acceptance Criteria - The Contractor shall develop and implement site specific pest and weed management procedures to control pest and weed populations.
8c9fbb5a-baf6-5000-9242-6c58461948b5 | note | ○ Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing.
f46a4e9c-8551-54ea-87fa-fd4a70716127 | note | Method - Verify
c72f2e29-1fbc-5fa8-81e7-3c4148285be9 | note | Frequency - Once
6eb5b512-bdb3-53ec-8a79-04cc47e1aa23 | note | Category - HP*
34db027b-8a86-53ee-9ad5-58f0bccb7d40 | note | Responsibility - SE
51188618-0c1a-5590-815b-cf7e22209cdb | note | Verifying Documents - This ITP
57295200-95f7-5bf4-8acd-d3e5b54f4dd6 | date | Date Completed:
3f095502-7d49-4c4a-b892-8052a7e95e47 | checkpoint | 4.3 - Setting out planting areas
0a945467-5f05-5e2d-b533-95c5fcac5db7 | note | Reference - VicRoads Spec. Cl.720.06
56247ab3-7d3f-5d08-9aa3-c7caba1f5349 | note | Acceptance Criteria - Planting areas are to be set out to the location and shape specified in the landscape drawings.
7540c677-e21e-5ba4-86cf-209afea2f95e | note | ○ Plant density requiremens and planting offsets established in the plant schedule are to be adhered to.
057470d2-44fd-53da-b119-48bf44a0604e | note | ○ Individual plants shall be located in accordance with the drawings such that the mature form of the plant will be in accordance with VicRoads Road Design Guidelines, including clear zone and sight distance requirements.
34c19859-cc7d-52cc-ba99-73a3851aeb08 | note | Method - Verify
f610cfe1-9342-52d6-ba59-99757f35186e | note | Frequency - Each Applicable Lot
b9faee5d-0d61-5a55-b53c-ead01610dc7e | note | Category - N/A
ffc7fc0b-98d0-59ff-b50c-a1f7a624eddf | note | Responsibility - SE
b9187718-a866-5ec7-b7ab-35bc1d9aafa2 | note | Verifying Documents - This ITP
5f1bcec8-0a17-57cc-bf4b-4b57ba34c4f4 | date | Date Completed:
af67d3ed-4f55-44a1-a0f8-cf1d17e4fe44 | section | 5. Construction
67588359-8f0e-4986-9d6f-c3a366858bc6 | checkpoint | 5.1 - Planting
6cac052a-eaa9-5134-96dd-21d05556cd74 | note | Reference - VicRoads Spec. Cl.720.09, Landscape Plus Planting ITP
ed5ed9af-1ae6-5793-914e-1c5247f8564d | note | Acceptance Criteria - All planting will be undertaken in accordance to the contractors Planting ITP
865fb9ab-e613-59c9-940e-b04c4d0095e6 | note | Method - Verify
ac8a6905-c761-5424-8f18-3010aef6b37a | note | Frequency - Each Applicable Lot
bb4b9fb9-6bbc-5e14-8f18-1c5ef8f50ab0 | note | Category - NA
2380c57b-dc98-5d77-854d-59f543f058fd | note | Responsibility - SE,Foreman
3a946c40-0c8a-5cec-b5f1-66a1cff6e63f | note | Verifying Documents - This ITP
db358a06-35f5-5953-bded-2e54ea79e186 | date | Date Completed:
e939cd42-f4df-4ae2-9c46-5726642b6c95 | section | 6. Completion
71ee7d4b-62c3-4182-a829-6f4c80155255 | checkpoint | 6.1 - Site Final Inspection
ef7543b3-6487-5087-a5bc-88006a3d49c4 | note | Reference - Landscape Plus Planting ITP
79804c77-2903-5121-aeab-760ff36f6bff | note | Acceptance Criteria - Contractors ITP signed and completed
c2b4882a-5a1e-505d-b093-9986d5f89dd2 | note | Method - Document review & Site Inspection
7a3b0549-17d1-5f54-86b9-c47b7e6a3d6d | note | Frequency - Following completion of planting works
270e5eb6-de4a-540c-bdee-96298f6bafc0 | note | Category - N/A
0e615759-7847-5e90-b158-d914709c4ac9 | note | Responsibility - SE
4a9c46ce-0adf-5ce6-a44b-37f65794c72c | note | Verifying Documents - Sub-Contractor ITP completed, signed and to be attached
2439a41a-7328-5d5e-9695-86714cff3568 | date | Date Completed:
2c0a8792-3eeb-4dfa-be41-8afa8414a1ec | checkpoint | Final Inspection
281e1f58-98fa-51d1-b420-1d14bdc807b4 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
35f810ff-17dd-5625-aca4-500feb35e77f | textbox | Name:
a40cad67-a554-5648-bc26-c02829691042 | textbox | Position:
c49ab103-5a4e-5beb-a1cb-5d39ced67495 | textbox | Date Completed:
a85afe48-20e8-4d6f-853e-1fd0a11dc5f4 | signoff | Sign ITP
222e32c5-718b-4765-bb02-004eb4837a6d | checklist | ITP-327-CIV-ADL-Landscaping-Ground Preparation and Planting Rev 0 | itp | ITP-327-CIV-ADL-Landscaping-Ground Preparation and Planting
755ce2ec-2348-4677-8b59-963a92edcb6c | section | 1. Referenced Documentation
dad44777-133d-4464-b24a-d585edf159e2 | checkpoint-no-value | Referenced Documentation
4393bf72-2222-59b6-b1ab-f06d91c3c0e9 | note | Document Title: ITP-327-CIV-ADL-Landscaping-Ground Preparation & Planting
a3bdb91e-1774-58fc-9917-fc101be63e56 | note | ITP Description: Landscaping-Ground Preparation & Planting
2537dfd1-a2d6-5fef-95a6-b682e21edb3c | note | Discipline (e.g. CIV/STR/RAIL): CIV
3baf7a83-e2ed-5814-9689-c1d46c02ace1 | note | Revision Number: 0
f2b22726-e22a-5698-8d72-3e495f31767f | note | Revision Date: 2/10/2025
48437154-447e-5eab-98f5-f7fcad9f055e | note | ITP created by: Will McMuskey
48ff37e1-ce1e-5921-b985-cb25c3107ee2 | note | ITP approved for use by: Romualdo Magpantay
94ccea6a-6acc-55ba-906b-7fcc4c13bddb | note | 1.1 - Non Dependent
2d8c9c94-26a8-53c1-bc2e-744deafeeabe | note | Reference: VicRoads 720
f6b616ad-b53c-5251-b1d1-07a95dca7055 | note | 1.2 - Non Dependent
950d7ace-c9b6-519d-b928-8472ba802a5e | note | Reference: AS 4454
cccde030-0d5d-53c4-adf1-5e42dd2be80f | note | 1.3 - Non Dependent
1f63e4a2-a882-52a6-9ca0-86add223f122 | note | Reference: AS 4419
6304780c-0d5b-54ff-a306-876b8351cd7e | note | 1.4 - Non Dependent
fe4cb8a1-704c-5e7b-aacf-e15fe75e8181 | note | Reference: IFC Drawings
ad12e51d-7e38-48eb-8ddf-4afbe94f7be4 | section | 2. Preliminaries-Materials
1a9873b4-28cd-4ad3-8ea3-db9e0d82f640 | checkpoint | 2.1 - Submission and records
f3f61171-4e2f-56ae-903a-62487be74260 | note | Reference - VicRoads Spec: Cl. 720.03
fc60a87c-76ec-595a-9e0c-bbed62010eb5 | note | Acceptance Criteria - Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery.
99f5c84b-1de9-5288-a8b4-1b5184d73596 | note | Following information shall be provided to the NA:
6e05345f-4a00-59c2-a70b-468b5dcf0f58 | note | ○ Samples
f4850d0c-d665-53ae-88ea-29ff87b2ba1c | note | — Mulch
4de2e357-3888-5a40-9a10-f44e7c6c59ab | note | — Imported topsoil
765f88fd-a16c-540b-9f08-aba4de064304 | note | ○ Records
33fd7c5e-76d0-58dc-a8ef-de126b2c9c76 | note | — Details of suppliers
18a7f145-20ca-5dac-80ba-21c831bc479e | note | — Soil tests on imported topsoil
077eb3cc-c43a-509d-8b24-2cd8d08cfa55 | note | — Copies/Photos of fertiliser labels
05d97130-8552-5343-8c63-023b25242259 | note | ○ Attach: Records and Certs into Hold Point inTeamBinder and write the Reference No.
f8c5b156-4fc1-5781-8448-31d02ec473f1 | note | Method - Document Review
60c504de-2d39-5a4f-baff-0707e5c08230 | note | Frequency - Prior to Commencement of works
65d69f17-1f6a-567b-82b6-7fc8a4575b23 | note | Category - HP
398394b8-eb8a-5977-ad84-073cb1b37158 | note | Responsibility - NA
83ac1d52-cd1d-5e5d-9f22-01a7e0fef821 | note | Verifying Documents - ConQA HP Release
fef9a6d6-2f76-508e-b324-3b578ff4e20b | date | Date Completed:
9921e5c7-e722-4518-8064-5660d57cbdc9 | signoff | AUTHORITY HOLDPOINT
a333021d-a2cd-430c-89ee-c6930c633864 | checkpoint | 2.2 - Supply of topsoil
44490b99-ef65-5291-aebd-68255222232f | note | Reference - VicRoads Spec: Cl.720.04, Table 720.042 IFC Drawings
a71391bf-5b62-5419-82c3-39d968845721 | note | Acceptance Criteria - Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor.
3465ad0f-d49c-53bc-9437-86d723be99cc | note | ○ Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings.
75bdaafc-c1d3-5217-a9ce-06f4d6d60791 | note | ○ Attach: Material Conformance Docs / Test Reports as Material Approval onto TeamBinder and write the Reference No.
714e746d-e304-5668-a3f9-a409bc32a397 | note | Method - Verify, Doc. Review if applicable
22328e29-a248-5c92-a8e4-6c358f330af6 | note | Frequency - Prior to Commencement of works
1d6038a4-ccf1-5c5e-8f7b-14c6a3991732 | note | Category - HP
06f8c9f3-9717-5eed-ba3d-eabfe327a9bb | note | Responsibility - NA
806215c2-82c9-5f9a-9f18-8c424a7ca8cb | note | Verifying Documents - ConQA HP Release
7bf17b02-6231-577d-ae64-ab59fc7ecc81 | date | Date Completed:
48ce1ad7-4726-49ca-8f1e-b97481f8e7a2 | signoff | AUTHORITY HOLDPOINT
73dfbd40-8b1a-4c0e-a032-24bf46977aab | checkpoint | 2.3 - Supply of Mulch
edc8ad43-5e34-51c6-9347-77d0afee6113 | note | Reference - VicRoads Spec: Cl.720.04, Table 720.044, AS4454 IFC Drawings
101b266b-118c-596e-bdaa-00daf12f226b | note | Acceptance Criteria - Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings.
4eae3daa-f519-5fe8-9236-8181f5dc184b | note | ○ All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings .
d55b88de-0713-5ebc-86f7-a1ec8882c26a | note | ○ Imported Wood Mulch shall comply with Table 720.044.
d609836f-2f49-587e-9b62-fcdb916b72c5 | note | ○ Attach: Material Conformance Docs / Test Reports as Material Approvasl onto TeamBinder and write the Reference No.
c52d0131-c741-586c-b436-4eac451229d5 | note | Method - Verify, Doc. Review if applicable
ed562215-492f-5874-8c15-016c63961657 | note | Frequency - Prior to Commencement of works
24137c5c-c04d-56e7-a275-dc5ea521ad6b | note | Category - HP
d848d9ff-f83d-54df-8f86-5e0574354cd4 | note | Responsibility - NA
2c692776-e215-53c4-84b1-641732c11987 | note | Verifying Documents - ConQA HP Release
b321f333-9da4-5b02-a0cf-cc44180ef4ea | date | Date Completed:
8546beb3-c3c6-4fe2-ac98-efc7416a6bbf | signoff | AUTHORITY HOLDPOINT
bec12025-84c7-4f7f-b715-58e30987d486 | checkpoint | 2.4 - Supply of Plant
d47b16f2-3e76-508a-b267-d8c810317087 | note | Reference - VicRoads Spec: Cl.720.04, Table 720.041
bece23c5-7251-5c53-8817-39384ddb55ff | note | Acceptance Criteria - All Plants have been inspected and comply with Sec 720.041
2b8a7e8e-5c97-5b72-8e77-a59c3b023d25 | note | ○ Attach: Landscape Architect Approval
bba3c47e-adb9-5efe-9abc-b55d139a0550 | note | Method - Verify
f8dac6e6-19a8-59fe-bef2-b788f111e85e | note | Frequency - Each Lot
6497ffa6-9048-501d-abb9-c0126a18ae12 | note | Category - HP
1fac25a2-33ea-54e5-98ab-2179971a38ab | note | Responsibility - NA
5f2e8feb-e77a-55de-97cb-c60f1739629f | note | Verifying Documents - ConQA HP Release
6c64f78e-d4d7-5d6c-91c5-18a82495c3d6 | date | Date Completed:
196efb8e-798b-4adb-bb86-d5514c912359 | signoff | AUTHORITY HOLDPOINT
5ad903b5-32a4-4503-99a3-59a56e3cbfa5 | checkpoint | 2.5 - Supply of grass seed
1e60b5e5-f5f9-5af1-a372-dccaed3ed14a | note | Reference - VicRoads Spec. Cl.720.04, Table 720.045
a3f7b6a8-e73a-59c1-bdb8-ed7e62216875 | note | Acceptance Criteria - Grass seed shall comply with Table 720.045
b017b0e3-79c1-53de-ab08-11901aef3aef | note | ○ Attach: Material Conformance Docs / Test Reports as Material Approvasl onto TeamBinder and write the Reference No.
8992abcf-078f-5b05-bdb0-fb548972e218 | note | Method - Verify
57ba15ca-bc4a-52c9-872c-c0043da75495 | note | Frequency - Prior to Commencing works
ad5505d0-2d71-5185-8b0d-dadcab949b9a | note | Category - HP
3d5e96d7-ed3e-5484-9b03-d24e1bfd4b55 | note | Responsibility - NA
2151bddd-cfcf-537b-9e0f-caecf3c6a047 | note | Verifying Documents - ConQA HP Release
16cd73ff-1731-57b7-8f9e-84d703dd7cdd | date | Date Completed:
585db13d-a373-4f1c-a92d-c06898dca078 | signoff | AUTHORITY HOLDPOINT
15d7b4d5-6be4-4075-827e-1972e75d61f6 | section | 3. Preliminaries-Documents
a19d496a-dafb-4558-8adc-35a993aca7bb | checkpoint | 3.1 - Check for correct documentation
bc6fe210-bee5-5f56-8656-15ecddd0d3e8 | note | Reference - Drawings and drawing registers
b10c39cf-74bf-5075-a6d1-d3d5b6a149cb | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
de4e4c2c-9dd7-5774-903c-38fb66aaa569 | note | — Using the correct and complete set of IFC drawings
e02ee3c1-e48b-5888-b2be-d560a5d889a7 | note | — All drawings are the latest revision
08f5bb86-2dd0-5b45-a822-18ae7b9721a8 | note | Method - Document Review
34381fe2-d42b-56b0-b694-c1ff2ad81875 | note | Frequency - Prior to Commencement of works
855a975e-d3ee-57e5-8c76-47589eab77ea | note | Category - IP
292dea16-62c7-5b3d-b629-d648f8222f16 | note | Responsibility - SE/PE
2a974046-bf0d-53af-9b0e-c2e020108a2e | note | Verifying Documents - ITP Signed Off
5103e4d6-9635-55fc-813f-ebddf56cb435 | date | Date Completed:
4de3cf80-eff1-4b13-85ca-ad10aa99af24 | checkpoint | 3.2 - Subcontractor ITP
b573626c-ffdf-5619-83ad-88b8110f9b36 | note | Reference - Subcontractor ITP
af7dc314-4fe0-5a99-ab29-3b03b4757a1f | note | Acceptance Criteria - Subcontractor ITP to be reviewed and approved by MRPA.
fcd01efe-3916-57a9-b32e-b289f403114f | note | Method - Document Review
51315b90-0db4-588b-8403-73d6551b4008 | note | Frequency - Each Lot
ee341fc3-a724-569e-919f-e39a0dee4635 | note | Category - WP
3e9cd51f-f4ef-54af-8c8c-13d9b7ffd3bb | note | Responsibility - SE/PE
380c5741-61bc-5b6d-b6ad-dade9cd436e3 | note | Verifying Documents - ITP Signed Off
e2a7b0bd-ecf1-5862-a482-81fdaeb3f0e9 | date | Date Completed:
3e12ddaa-c06c-470c-bf79-4bf430ade10e | section | 4. Ground Preparation
2ad811dd-c3a5-4bb7-962c-c775fb418220 | checkpoint | 4.1 - Soil Additives
1e510e01-a997-5216-af83-d3ec7204fb11 | note | Reference - VicRoads Spec: Cl. 720.07 (a), AS 4419
17d0675c-4e78-50e6-995a-b57c38d07fe0 | note | Acceptance Criteria - Refer to Subcontractor ITP
dac3d0f3-81aa-51fc-b845-b19f4bb0cb06 | note | Method - Document Review
93ea440e-7123-5c34-a147-52aab396dbfe | note | Frequency - Each Lot
6d856bce-832e-5067-978a-d986d2df05d3 | note | Category - IP
1b3ad297-eae4-52c6-80cc-c38bb44bbaf4 | note | Responsibility - SE/PE
bec1d6f1-3917-5353-8f34-a7108d9566ad | note | Verifying Documents - Sign ITP
46cd8f8e-40e4-522e-b7d1-08242a4c6f20 | note | ○ Attach Test Report
aeb8edc9-2f77-509b-b971-d396e0c591bc | note | ○ Attached Delivery Docket (if applicable)
9dfa1a19-c9c0-5c55-8794-2fc8c4eff4e2 | date | Date Completed:
dba0489c-9927-44eb-b9dd-35da723b0bb7 | checkpoint | 4.2 - Ripping of subsoil
410931ee-008d-5e92-83f9-63c7e69dc8ce | note | Reference - VicRoads Spec: Cl. 720.07, Table 720.071
e9f0fd7a-cb84-5f7b-a68b-4962a5a242f6 | note | Acceptance Criteria - Rip Subsoil to min 250mm at 500mm spacing
5f1a3496-1911-55f8-9701-cfb72eb36eed | note | ○ Do not proceed until the NA inspects and acknowledges requirements for ripping have been met.
01e4dcac-9bde-524b-9757-ace632bd9d8f | note | Method - Verify
3e69cb03-5a2d-50e0-82f4-1b20fe997206 | note | Frequency - Each Applicable Lot
582fa167-e86e-54e6-a3ac-24e33dfa5dea | note | Category - HP
14143b29-378f-5a16-ae9f-a86229d31cea | note | Responsibility - SE/NA
d0860781-bc44-5a22-99ef-25017395b9d9 | note | Verifying Documents - Sign ITP, Attach Lot Map/Marked Up Area Inspected
5d5e2dfe-6079-5c02-9437-d90c4ac0c3a7 | date | Date Completed:
5b3fab35-e253-44ee-875b-65af08c11b18 | signoff | AUTHORITY HOLDPOINT
373f3f34-0838-482b-a682-2acf20c20e22 | checkpoint | 4.3 - Topsoil application
da401f02-d5f5-5c32-bfca-83ede871e823 | note | Reference - VicRoads Spec: Cl. 720.07
bfb99950-0612-514f-a1d7-2b1268800ca7 | note | Acceptance Criteria - Topsoil to be installed at 150mm depth with no air pockets, weeds, rocks, and other debris. Finish surface should be smooth and uniform
7f118a5b-2332-5c67-900d-3b35e1b4c072 | note | Method - Verify
98e5bff0-f86b-548f-88e6-69a98803bab8 | note | Frequency - Each Applicable Lot
1a407667-8c0f-5539-ab8a-57037ceafd30 | note | Category - IP
bd5e4299-6734-54de-b28f-7f72f082e95f | note | Responsibility - SE/Site Supervisor
8a2dd966-da8d-589c-ac33-f27254fcc053 | note | Verifying Documents - Subcontractor ITP
dc508948-3e41-56c8-88e1-97e74c65a943 | date | Date Completed:
616843cb-059b-42bd-8be8-e8c828ee7647 | checkpoint | 4.4 - Mulching
67d95cc9-0392-5977-823b-e083149d860d | note | Reference - IFC Drawings VicRoads Spec: Cl. 720.08(a)
ad33a045-f0aa-5630-9a1e-7d4d2d0b342e | note | Acceptance Criteria - Mulch to be installed at 100mm and to finish 50mm below pavement.
93e9787d-1420-548b-8b28-7a72ada8918c | note | Method - Verify
deaa7c52-6a8e-5680-9a4e-9c62c8dfab48 | note | Frequency - Each Applicable Lot
1b64ba04-4fa9-5345-8f93-098953c58c43 | note | Category - IP
60c72f73-ee56-52b4-abfa-d71c9e850a4a | note | Responsibility - SE/Site Supervisor
bf54768c-647f-5e4e-8b0b-57dce269d2ad | note | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
340730d1-e892-5f4c-bec4-c7c851ab74d8 | date | Date Completed:
13293915-1a0e-47a9-8095-efc9342f443d | checkpoint | 4.5 - Weed and Erosion Control Mat
0412d595-19bd-5cfd-83bf-776fa3986213 | note | Reference - IFC Drawings VicRoads Spec: Cl. 720.04(i)
378741fb-fe3b-5513-836a-5d447db579c7 | note | Acceptance Criteria - Refer to Subcontractor ITP
0fcb8aeb-4640-50a0-aac2-10323946fbde | note | Method - Verify
8471becd-ab9b-5bcf-879c-bb6de06e17cf | note | Frequency - Each Applicable Lot
e162e8e4-0005-5d75-bf62-6da124e30770 | note | Category - IP
82e99086-80bd-552f-80fc-e820abfe3328 | note | Responsibility - SE/Site Supervisor
9c6ba439-0885-52e0-88b5-96ac4fab645d | note | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
7e92fee5-e33a-5b2c-9c2e-4a194a9f073e | date | Date Completed:
3cd3e9e4-41f7-467e-9490-632ad3e5b5de | checkpoint | 4.6 - Jute Matting Installation
b21dd5fa-39e9-5c97-9527-3b57b8c86826 | note | Reference - IFC Drawings VicRoads Spec: Table 720.071
73adc2be-73d6-5b09-893b-2ac82e41bf7a | note | Acceptance Criteria - Pre-slit Jute Matt installed as per specification
0a8226a3-f90e-5726-a3b0-97210800f299 | note | ○ Lay Matting into a trench of min 150mm wide and depth, pin and backfill
08c47fef-05bd-5037-b1ea-616b74c0af97 | note | Method - Verify
786f9e7a-2d12-578c-8705-cb183852fb1c | note | Frequency - Each Applicable Lot
544446f0-682a-5003-9f64-cb216b71166b | note | Category - IP
82c2aa0c-036e-5638-8e7b-0b89d6801c96 | note | Responsibility - SE/Site Supervisor
6c8b1c43-3c5f-54e6-a0c3-179e530460b3 | note | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
7ad04904-6fcd-57d1-b512-e9b3d921bd82 | date | Date Completed:
9451bbd5-5494-4934-8806-770d548ddd37 | section | 5. Planting
393740f2-a01a-4ee3-a42d-0d9e478cb638 | checkpoint | 5.1 - Plant Installation
565c4ec3-5f8b-5310-ad69-e9eb8cec8fa5 | note | Reference - IFC Drawings VicRoads Spec: Table 720.041
695efe55-d0a7-537d-90a1-c5fe0120e265 | note | Acceptance Criteria - Plants to be removed from Pot and Roots Tickled
f44e97f8-0320-533b-b53f-01787d09ce9d | note | ○ Ensure Mulch does not overly cover stem of plant
19fda2b6-24af-56a6-9f14-c0af3f1e165b | note | ○ Ensure plants to be watered within the same day
d9efb6b3-a9ce-5ccf-8147-270c4451b7a6 | note | Method - Verify
b6280495-b772-5f09-ae09-728a85059f60 | note | Frequency - Each Applicable Lot
a0f6cc26-84ec-5fd9-9fce-64209cfad969 | note | Category - IP
9aabac0e-0b70-5d16-b8d1-63b6a6ae07bb | note | Responsibility - SE, Site Supervisor
abe846ab-d3a5-5e4d-babf-8aace5deda94 | note | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
594299b8-4466-5da6-a989-9fd502ad0280 | date | Date Completed:
7a1dceed-c842-4379-bb6a-ebf3d1fc5c9b | checkpoint | 5.2 - Fertiliser Application
2bbd90ef-0e0f-5594-8d2a-77a5d4e637a2 | note | Reference - IFC Drawings VicRoads Spec: Table 720.041
134a564d-2179-59d5-b74d-cdf7b8eb657e | note | Acceptance Criteria - Tubestock: 10gms (approx. 1 teaspoon) of fertiliser been added to base of plant
0caeee7e-cc31-5016-80c6-724f72aef8ea | note | ○ 15-30cm Pots: 40gms (approx. 4 teaspoons) of fertiliser been added to base of plant
9d980dff-ce02-5954-9398-420962742a2c | note | ○ 45L Trees: 80gms (approx. 8 teaspoons) of fertiliser been added to top of root ball
ed340300-41a9-5a67-8c9d-0bd4a18d3856 | note | Method - Verify
3f0a7435-e549-5e21-856b-6e61f79a061f | note | Frequency - Each Applicable Lot
ad5f0977-6478-57a8-80d9-fbf6e964c742 | note | Category - IP
0eb8bbb8-3f57-5926-b50c-7b76ad2ca913 | note | Responsibility - SE, Site Supervisor
a4271cf7-4fe0-5226-aefb-0ac35d849a38 | note | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
ef4625f9-ec7f-5fe6-963b-b5a97cde4143 | date | Date Completed:
f6d65495-478a-4f19-a8f6-6c34fc53ea26 | checkpoint | 5.3 - Tree Installation
f0c8ee56-0b8b-577b-81cd-ddc51b0bf234 | note | Reference - IFC Drawings VicRoads Spec: Table 720.041
121b8034-6821-5275-b98c-57373edb0488 | note | Acceptance Criteria - Installation on Grade:
1de66275-41dc-5723-8ee0-debe81b61dd1 | note | — Hole to be 100mm deeper and 600mm wider than pot size
619997c6-e3a8-597f-9314-b3f5105b5250 | note | — Three 50mm x 50mm x 2400mm Hardwood Stakes driven min 600mm into ground outside rootball
9fdbd84a-c0ce-5007-845f-9d6fca59944a | note | ○ Installation on Garden Beds/Turf:
863a3f80-407e-539c-ba29-783d8e6d33ca | note | — Tree Pit Inspected and Minimum 3 times the root ball width
b41c1006-b544-5777-83e4-1d026d685fc6 | note | — Three 50mm x 50mm x 2400mm Hardwood Stakes driven min 600mm into ground outside rootball
19ac0e07-1ed7-5524-85ef-69013f34db2c | note | Method - Verify
6dc949f4-7266-540f-92a0-59e62c483aaf | note | Frequency - Each Applicable Lot
f362e827-fbe5-5b6f-a470-049f7de22437 | note | Category - IP
892b0b00-9729-55f6-be73-a3567e67ce80 | note | Responsibility - SE, Site Supervisor
4ae53ad3-0932-53e3-a755-8eb768e4dae6 | note | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
3cf0c55d-565a-552b-a24a-6a6e189251c0 | date | Date Completed:
1bc99af6-74c6-4f25-b22f-75a46984261a | checkpoint | 5.4 - Soil Installation
3e709e7e-df0f-5a45-84f8-95e60f2878cf | note | Reference - IFC Drawings
b0ed66f1-c933-5b83-af8f-f02976586542 | note | Acceptance Criteria - 75mm depth topsoil & 100mm min in swales consolidated as approved
e8f4e6f2-a8c1-58a4-a762-fbe32c0aa95b | note | Method - Verify
78be70b1-e2fb-57e2-8d46-ac3c08e8575c | note | Frequency - Each Applicable Lot
31496a62-7c77-54f8-a67c-37fbb55461ce | note | Category - IP
25b8353f-dea4-5ea7-a2a5-0d752be02409 | note | Responsibility - SE, Site Supervisor
7684bc70-30ac-52b2-9a13-d13662e43cac | note | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
c5fda8a9-87a8-54d2-969a-9821c0c09427 | date | Date Completed:
bf75d4fd-e08c-478a-b8c0-19edb400093e | section | 6. Post Construction
d8a9cccf-701d-4f3c-a8d4-b7ffe3ca3801 | checkpoint | 6.1 - NCR Closeout
7bfa8468-614a-5864-a463-f550037fe522 | note | Reference - MRPA Quality Management Plan
9a13ebe5-bcc7-578c-9c52-7aa9f0ca29ae | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot/element/Work Area that this ITP covers, have been closed
27aaf5ba-2add-5bb2-b535-2e79ebdb62c6 | note | Method - Document Review
aa9266cc-2b3a-5720-b4d6-1410a5797d4e | note | Frequency - Once, prior to closure of this lot/element/work area
b55885dc-2989-53f2-90f8-c3327a20bebd | note | Category - HP*
96c719c4-be6e-5190-8c5b-dec959964acb | note | Responsibility - SE/PE/SPE
451c5230-e858-58b2-9336-56e70ab039d2 | note | Verifying Documents - ITP Signed Off
e589ff00-b163-5c1d-aa45-833e52fd6df0 | date | Date Completed:
442f44e0-d663-464f-b70a-1d3c42904dab | checkpoint | Final Inspection
bc37e326-1f7d-5269-8fae-65b3c95067ce | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
aa61cb93-0650-540f-9be0-7b2711f5e23c | textbox | Name:
caf5d3b0-b281-546d-9550-64ae783d3362 | textbox | Position:
52f191ea-702a-5eff-aabf-de9a1a78ccfb | textbox | Date Completed:
2345074b-d607-4051-83d2-780ec1b2d1c0 | signoff | Sign ITP
d58bd837-91f0-4656-9ceb-6f1f57ce146a | checklist | ITP-STR-296-ADL-Misc Structural Steel (Supply & Installation) Rev 0 | itp | ITP-STR-296-ADL-Misc Structural Steel (Supply & Installation)
9c438cdc-3252-4d6f-9052-d62ae4187309 | section | 1. Referenced Documentation
889d301b-9603-488a-80bd-cd06adb89118 | checkpoint-no-value | Referenced Documentation
89908a75-f470-5bda-8e27-e61f265b62f2 | note | Document Title: ITP-STR-296-ADL-Misc Structural Steel (Supply & Installation)
900d7e9d-9606-5690-acf8-f163349a0641 | note | ITP Description: 296-ADL-Misc Structural Steel (Supply & Installation)
446dceb0-1eee-5bfe-85a5-b2be8e5e2337 | note | Discipline (e.g. CIV/STR/RAIL): STR
7820a0a8-6546-5192-83ac-02f1ce117d0a | note | Revision Number: 0
249eda93-518c-5125-bd93-781eac5851fd | note | Revision Date: 24/07/2025
8d5aaf8c-851c-5d6d-8d60-83c92bf5d41f | note | ITP created by: J Ballard
cfb04abd-de81-518d-852a-ec6d66270506 | note | ITP approved for use by: Romualdo Magpantay
03f03713-834d-5dd3-8546-ff1ed01e5132 | note | 1.1 - Non Dependent
23b60de2-f7f8-5654-aa96-2a36195f5044 | note | Reference - MRP-120-C-SME-REP-91-NPT-CSW-0001
a1ca6289-8828-5b41-862e-a67706601ceb | note | 1.2 - Non Dependent
90f45d67-1cd7-559a-b293-a2dd3ecbe3f1 | note | Reference - AS 1252
4d0fa49c-7667-570f-adbf-a43786c01820 | note | 1.3 - Non Dependent
106045f6-de61-5a28-a94d-91050d995f54 | note | Reference - AS4100
89745374-cf8a-5fb6-99fa-6919bc079891 | note | 1.4 - Non Dependent
ab3b2ef8-ce4e-5f72-ad3c-f35f08380139 | note | Reference - AS5131
76fb5d36-5cfb-5451-92b8-f277b68d1c1e | note | 1.5 - Non Dependent
6315a861-2698-5ea1-b2fd-0c1c2440ba18 | note | Reference - AS4680
0253e433-f2f3-596f-ad7f-ae0fd33832cc | note | 1.6 - Non Dependent
e4655c91-df1e-5548-b4fa-0c8f3741d382 | note | Reference - AS 610
4bc965c0-5c3a-482b-a972-7f81f4c5ad44 | section | 2. Preliminaries - Materials
be8430a3-db41-46ca-a34e-e079ffb3708a | checkpoint | 2.1 - Structural Steel Components
ed9504a5-e1b0-52d0-b58d-1e5aa92e30f7 | note | Reference - IFC Drawings, MRPA Quality Management Plan
8f856002-31e6-5c37-8c61-a3162525be28 | note | Acceptance Criteria - Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
747cc3b4-afab-5570-afb0-d3f5c1de113a | note | Typically this consists of but not limited to:
65fe8114-ceb5-5313-8e72-b99eb4fcb34b | note | i. Certificate of Compliance
c1db1239-4ac2-5688-b16e-4d18b49c59df | note | ii. Completed ITP
9d74ed54-e8e1-59d0-8c9d-8b6fb30e7567 | note | iii. Weld Procedure Specifications
966c219d-1894-5645-b9af-6356dadc42e2 | note | iv. Weld Procedure Qualifications
fda1c83b-4593-5f87-8a8f-bc66ccc77d09 | note | v. Welder Qualifications
991930ed-3f42-58a5-8aec-fdfd9c43465b | note | vi. Material Certificates and traceability
030061a5-526c-58ea-b824-0fab85be8de3 | note | vii. Quality Assurance check sheets
0a468897-2788-50cd-8abd-b31bc73da398 | note | viii. Welding Consumable batch certificates
743b33c1-9aa3-53ba-87b5-f987605da169 | note | ix. Coating certificate(s)
4f885f71-6153-5961-bcfa-252490894bd6 | note | x. Non-destructive Testing (NDT) Reports
20109fbb-136b-5d02-a678-c56ab891e32d | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
3d5292cf-fca2-574b-aef3-6e39754c4c37 | note | ○ Collate: Structural Steel Quality Assurance Documentation and upload in a TeamBinder Lot.
bfda0850-3ee0-5891-9ebf-adb3f6c81d4a | textbox | Enter: Teambinder Material Approval number
fe3d0109-dd33-5c07-9bad-70cd981a5d9b | note | Method - Document Review
27b4b6b7-366a-5e9e-a9a0-d513f5de0926 | note | Frequency - Each component
34842dd3-41cc-54df-90fd-16581b4fdf43 | note | Category - IP
b5863367-bbe3-5325-a850-f9bc5f3202c8 | note | Responsibility - PE/SE/SPE
f3c78cb6-7e3e-52c8-92fd-d77068e95552 | note | Verifying Documents - This ITP
ab5ad0c7-cb99-5f1f-b814-6d887f97cfb3 | date | Date Completed:
d49607d7-216c-416c-ac94-30fb50650349 | checkpoint | 2.2 - Fasteners
04bf8da7-a264-56fe-b166-c5e499151ce5 | note | Reference - IFC Drawing
a51cd3a1-9c0d-5609-ace0-a412577f0953 | note | Acceptance Criteria - Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS 1252
e1b80e72-2d8c-5791-87c8-624a88351c8d | note | Method - Document review
adaeb448-2c72-5d28-bc55-eea172ad9663 | note | Frequency - Where applicable
5694b0aa-79a1-542e-a9ae-c1f85d40ada4 | note | Category - HP
ae87309d-dac1-5839-a769-82d31df8a53f | note | Responsibility - PE/SE/SPE
7ec0bcb7-903e-5017-90a8-1beaf358d80f | note | Verifying Documents - This ITP
dbde392b-171a-57ec-9145-fc310c3cd4d5 | date | Date Completed:
3ac6af83-9181-443f-a0c2-5cc5cd45befe | signoff | AUTHORITY HOLDPOINT
e6423446-3b02-4103-81ef-5987165cfdfb | section | 3. Pre-installation Activities
f28a0332-7a63-4195-862a-8f64f1df03e2 | checkpoint | 3.1 - IFC Drawings
18ad099c-417c-5d9c-8baf-cfcfbe95575b | note | Reference - MRPA Quality Management Plan
2e186661-d13a-50c1-afb4-0688126dab38 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
c79c06ad-3d59-5cf6-94f4-4a223da148ab | note | Method - Document Review
3a6e47c2-6d75-5be7-8e99-d145ad499445 | note | Frequency - Prior to starting Works and at regular intervals
f24f4355-8fbb-5b03-ae5d-7933501e92f5 | note | Category - HP*
6da98c81-6db0-51f1-894d-0ca51ba3df22 | note | Responsibility - All
6ddbfca7-e350-59fc-b495-d6bd78e82527 | note | Verifying Documents - This ITP
e2ad0e47-d003-5588-881e-4a0e36426508 | date | Date Completed:
5bc0b06c-a3b4-43f8-98b6-c40a1c57f16d | checkpoint | 3.2 - Materials Inspection
83ecc5b9-c927-5daa-a787-40b266a1c999 | note | Reference - IFC Drawings
33ff64cc-618a-545f-ae67-13ef1040ac6a | note | Acceptance Criteria - General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
ede0c9e5-e425-5a4f-b9be-e298680859e4 | note | Method - Visual
e6bdf9b8-5e93-57b4-a79e-e2798937bfce | note | Frequency - Each component
d0909b28-a4ce-5fa9-91e0-fc5ce5714b4f | note | Category - IP
dfd40a6a-6b82-5896-8392-e3037006618a | note | Responsibility - SE/PE/SPE
810e72b3-f933-5b8a-9524-99201d464c49 | note | Verifying Documents - This ITP
8f41785d-4841-54db-85d8-08ab819f0be2 | date | Date Completed:
370b85ed-fe3d-4beb-8dd3-1110291cb298 | checkpoint | 3.3 - Materials Inspection
df70cd4d-c553-5287-80b2-40995f385210 | note | Reference - IFC Drawings
732ec13b-62fa-5acc-ac75-7b1e03269f0a | note | Acceptance Criteria - Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
5efbe722-ee02-55cc-a344-a61958c4689d | note | ○ Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
bd001f16-c41b-5459-af9d-5ef433f2dada | note | Method - Visual
851761cd-8c33-5a4d-9bf1-1779f197a240 | note | Frequency - Each component
ff8d9f02-6d9f-5f68-87f7-1050559970cd | note | Category - IP
ca672c4e-b690-568a-b4c3-5e6cfb8a4017 | note | Responsibility - SE/PE/SPE
df4aa915-1fa5-5b57-a5f3-dac78abbd800 | note | Verifying Documents - This ITP
b9e40d95-ea5d-5430-8857-840593ae8bbd | date | Date Completed:
a3625e1b-f19b-45a9-94d8-fb9b052ed9a4 | checkpoint | 3.4 - Materials Inspection
31a33fbf-7775-5d12-9da1-6b46a03b6d49 | note | Reference - IFC Drawings
f0145acf-51e2-5298-aaec-5689e41ba814 | note | Acceptance Criteria - Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
1ffecbe2-bd07-55b6-9bba-50d2f9ae91fe | note | Method - Visual
6e6dc37b-041f-52d9-9ab5-1e93018a2e80 | note | Frequency - Each component
7c3ed030-7a00-5319-8dd1-928dde55581e | note | Category - IP
dd33fdef-b137-509f-ab96-5dcb5c547e72 | note | Responsibility - SE/PE/SPE
84dab39c-c938-5140-916c-82702b8901c4 | note | Verifying Documents - This ITP
ff452f6f-be7a-53d1-8975-952c1eb783b1 | date | Date Completed:
f117c373-60bb-4ee5-8185-03151271b927 | checkpoint | 3.5 - Materials Inspection
a532cfff-d406-543d-8f1f-40f5d5d85628 | note | Reference - IFC Drawings
581d33b4-ae9f-56db-8a57-241cfed3093c | note | Acceptance Criteria - Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
428a0dd7-abc8-5ea7-a37a-3b170af2e2f1 | note | Method - Visual
21d1f421-8276-5dec-a2fd-b096b6834666 | note | Frequency - Each component
a5f16720-767d-5466-822b-006707ee073f | note | Category - IP
d840a263-83dd-56b7-b2c1-0b66d19e96ef | note | Responsibility - SE/PE/SPE
25e6761e-53d0-5836-a2fc-3f9aba7eddc7 | note | Verifying Documents - This ITP
8c076100-dac0-5719-a7af-1ddb5e034c4b | date | Date Completed:
121e793d-7d9c-48ea-8636-9ca45929468d | checkpoint | 3.6 - Substrate inspection
aba66df8-b249-5c4d-834e-640e8a55edce | note | Reference - IFC Drawings
88c39b0a-0d8e-545a-bcd7-0e2e49102f12 | note | Acceptance Criteria - Substrate is clean and in good condition
c103b7ce-4f61-5678-9a6d-632dca272365 | note | Method - Visual
b4a1933c-5f68-56ce-81a0-b3af9dba885f | note | Frequency - Each component
1a019e26-6335-5d96-b6a8-0159005e5bb3 | note | Category - IP
9e27e5d7-72c1-5922-ad8a-453327292924 | note | Responsibility - SE/PE/SPE
e2ca2785-4de0-5bed-b689-da962ef5f955 | note | Verifying Documents - This ITP
9825a5f9-f49f-5925-bd27-2909d492121b | date | Date Completed:
72ba411f-b500-40b1-a461-f01cbe25a4bc | section | 4. Installation Activities
15141906-002d-4176-a998-a0fec0fb3df5 | checkpoint | 4.1 - Connection Point Installation
1c3d752c-e291-5c56-bfcd-1521c9065ee2 | note | Reference - IFC Drawings
e5380221-c479-5d79-8ff2-3abaa03d0526 | note | Acceptance Criteria - Install HILTI HST4 Stud Anchors with 90mm embedment as per manufactures installation instructions
2cc3fca9-b337-5b17-bfc4-871ace1c2170 | note | Method - Visual
a6976f0a-8fcf-51fb-bd90-ad7195f47f48 | note | Frequency - Each component
ae7d791d-3b27-5a0d-84c6-4093242d2a61 | note | Category - IP
b25cdf6e-6f50-53cc-a381-dafc91c64ff8 | note | Responsibility - SE/PE/SPE
e805fc2c-c8d3-5918-bdfc-bd45c9eac3f7 | note | Verifying Documents - This ITP
4106f132-ba4b-5c81-bcf3-2b893d61a5a7 | date | Date Completed:
090cda91-7319-4f9e-b175-333e19cf1c1f | checkpoint | 4.2 - Structural Steel Installation - Wall Ties and Brackets
c33f312b-cb3e-53e8-a586-66ca91e35b07 | note | Reference - AS4100 Clause 15.2.3, AS5131 Clause 11.5.7
621ba57b-37a8-5a49-adc3-9ea70036b8d5 | note | Acceptance Criteria - Place steel component into position,ensuring that it is plumb, level, square. Spacing and location as per plans (horizontal/vertical/height and around openings)
f5cc1f34-9272-55ef-a025-945dc6ea5a61 | note | ○ Where a misalignment is found, only rheaming, milling, drilling or machine flame or plasma cut are allowed. Internal surface of the hole to remain smooth and free from burrs.
00546203-b10e-567a-af36-80659c0027ac | note | Method - Measure, Visual
b3da284d-b1a0-51f0-be24-7db30a9a2624 | note | Frequency - Each component
30c1406b-675f-5f1e-8ce7-f82ba2aeea54 | note | Category - IP
739e2401-6197-5681-92ef-6edf3c12b753 | note | Responsibility - SE/PE/SPE
966a5793-7cb1-5787-9946-890b9219836a | note | Verifying Documents - This ITP
7152dd1f-1cbe-5ae7-a1dc-a69fedd5d3f0 | date | Date Completed:
7b3ec344-4a56-46de-9a9f-787424da1f23 | checkpoint | 4.3 - Fastener Tightening - Snug Tight Condition
4aa97c27-5607-58df-b538-db4be22bfcc6 | note | Reference - IFC Drawings
f62db421-5ac3-5add-98d9-beb9f4efeda5 | note | Acceptance Criteria - Place bolts, washers and nuts as detailed on the IFC Drawings.
97971704-aad4-5d13-9b47-08b2df636074 | note | — Washer as specified(Washers shall cover the hole or slotted hole completely by 0.5 x bolt diamter)
0a7c1dfc-0459-591d-bab2-1896cd50d719 | note | — Nut
492897a0-c527-5a32-82e1-5e91b89ef53b | note | — Bolt protrusion (2 clear tread)
9d00e06a-74e1-5717-8893-89465e7ef8b7 | note | Method - Visual
0ce258c8-8bff-56cc-bef3-478852b0a739 | note | Frequency - Where applicable, each bolted connection
c5dc2632-caf0-5cf0-bbbf-7c6c80b6fe5b | note | Category - IP
a8520241-398b-5de7-b3b5-4d482b8ed0db | note | Responsibility - SE/PE/SPE
f086e648-8223-520c-a462-c14cc92fc0ee | note | Verifying Documents - This ITP
4e0d49ab-2014-56bf-8a00-e6500f87ee4b | date | Date Completed:
e83601c2-1b21-4161-b40f-be2d80421197 | section | 5. Post-installation Activities
b44ab7d1-0157-477d-b68c-f6bba67d0a93 | checkpoint | 5.1 - Inspection of Coating/Surface treatment
e9aa634c-961b-5068-b0c5-28f37299996b | note | Reference - IFC Drawings AS4680
e566eda6-337d-5119-87d7-8142a819eff4 | note | Acceptance Criteria - After installation Works are complete, inspect the steel element for damage to the coatings.
62ea9020-f0a8-578e-9ad2-a3bd0bd8bf47 | note | ○ Where damage exists, it shall be repaired using an approved repair procedure
a9364894-9515-58c8-8db7-29cfacf2a687 | note | Method - Visual
8425de42-c0c8-53a6-b52b-a496f00baad3 | note | Frequency - Each component
f754940c-ec3b-55ed-907c-809375be9301 | note | Category - IP
c928abde-4fc7-5491-b8ec-4485fdd81d86 | note | Responsibility - SE/PE/SPE
56af80b5-c34b-5bc7-ab94-ec549f75ea4c | note | Verifying Documents - This ITP
17b4bd39-a12b-520e-8632-81c0c03f0450 | date | Date Completed:
91d877c2-629c-4a07-b619-91949b82e10a | checkpoint | 5.1 - As-built /Survey
73752344-ac06-5bb6-8e4d-612120cb6810 | note | Reference - IFC Drawings
f32e820f-0c0c-5864-8f8a-afd853a875fd | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
fbdacb3b-5458-5e00-a23a-ade6c122a0aa | note | Method - Document Review
a60de6e5-9aec-5a16-8374-8c209096e8a5 | note | Frequency - Each elemenmt
384db175-209f-5d3e-99ad-2edfb99eb529 | note | Category - IP
ac3b6232-6380-5aa7-8c99-7f7704018df4 | note | Responsibility - Surveyor, SE/PE/SPE
e2f0a32d-7342-5ec3-9a5a-ccfa4e4ebf73 | note | Verifying Documents - This ITP
d6e6774f-1d3c-5993-bfef-8b9a016cad11 | date | Date Completed:
dd10b616-ecf2-483c-98ac-40c090bff026 | checkpoint | 5.2 - Non-conformance Report (NCR) Closure
09251c4d-98fd-5611-95ff-fb8c4bf96085 | note | Reference - MRPA Quality Management Plan
39b50ce8-0717-5bf0-a0ca-3aebe0645ef3 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
e28f2202-cc40-5072-8d1d-86397cdb106b | note | Method - Document Review
a547532e-5216-509b-8c54-2d7d0d4dceee | note | Frequency - Once, prior to closure of this lot / element / Work area
27628867-7529-53f5-a84f-470dc5d4cd89 | note | Category - HP*
b07c9bbc-ce53-59e8-b23c-f37dc0706c82 | note | Responsibility - SE/PE/SPE
f0f4ce76-44dc-5b8e-8135-481ce35fdb13 | note | Verifying Documents - This ITP
ad586996-1290-549b-bfcd-836e46f892a4 | date | Date Completed:
e1f469cb-1f9b-4504-9a8f-6305116fa2d2 | checkpoint | Final Inspection
ba88f265-b2db-5271-9e60-badee46cfb8c | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
0d3b720e-96ea-508d-b0ad-cb031d4f3a92 | textbox | Name:
4f8fa123-85db-5361-bfa6-f3bbbb17c4c6 | textbox | Position:
8d9b97d0-e0e5-5f83-ba92-7cb9868d4cdc | textbox | Date Completed:
846e1d07-a8e7-4b6e-819b-290e642a2ff1 | signoff | Sign ITP