## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-329-STR-MSS-RSS Wall Main | itp |  |  |  |  | ITP-329-STR-MSS-RSS Wall Main Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-329-STR-MSS-RSS Wall Main
label | ITP Description: MSS-RSS Wall Main
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 01/10/2025
label | ITP created by: Matthew Dib
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 - Non Dependent
label | Reference: VicRoads Section 682 November 2018
label | 1.2 - Non Dependent
label | Reference: VicRoads Section 204 December 2015
label | 1.3 - Non Dependent
label | Reference: IFC drawings
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Concrete-Leveling Pad
label | Reference - IFC drawings
label | Acceptance Criteria - Concrete compressive strength grade must not be less than N25 for levelling course and backing blocks;
textbox | Reference: Teambinder MA number:
label | Method - Document Review
label | Frequency - Each element
label | Category - HP*
label | Responsibility - PE/Nominated Authority
label | Verifying Documents - Material approval
date | Date Completed:
checkpoint | 2.2 - Select fill
label | Reference - IFC Drawings VR 682
label | Acceptance Criteria - Select fill shall comply with the requirements of the RSS designer:
label | ○ UNIT WEIGHT (Max): 15-18 kN/m³
label | ○ COHESION (Min): ≥ 0 kPa
label | ○ EFFECTIVE FRICTION ANGLE (Min): ≥ 36°
label | Gradation:
label | ○ 150mm : 100% PASSING
label | ○ 37.5mm : 60 TO 100% PASSING
label | ○ 9.5mm : 25 TO 100% PASSING
label | ○ 2.36mm : 15 TO 100% PASSING
label | ○ 0.6mm : 10 TO 100% PASSING
label | ○ 0.075mm : 0 TO 15% PASSING
label | Electrochemical Properties:
label | ○ pH: 5 - 10
label | ○ RESISTIVITY >1000 Ω-cm
label | ○ CHLORIDES <200 mg/kg
label | ○ SULPHATES <200 mg/kg
label | ○ ORGANIC CONTENT 0%
label | Structural Properties:
label | ○ COEFFICIENT OF UNIFORMITY ≥ 5
label | ○ LIQUID LIMIT ≤ 30%
label | ○ PLASTICITY INDEX ≤ 12
label | The select backfill must meet the minimum requirements of Vicroads Type A filling
label | Reference: Material approval in Teambinder
label | Method - Document Review
label | Frequency - Each material specification
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Structural Type A Fill - Ground Improvement
label | Reference - IFC Drawings VR 204
label | Acceptance Criteria - Replacement of unsuitable foundation material shall be a Structural Type A fill adhering to DTP specification section 204 and the RSS Designer:
label | ○ COHESION (Min): 5 kPa
label | ○ EFFECTIVE FRICTION ANGLE (Min): 28°
label | PHYSICAL PROPERTIES:
label | ○ CBR (Min): 6%
label | ○ Swell: ≤ 1.5
label | ○ Permeability (Max): N/A
label | Gradation:
label | ○ 75.0mm : 100% PASSING
label | ○ 4.75mm : 40 TO 80% PASSING
label | ○ 0.075mm : 10 TO 40% PASSING
label | PI x % passing 0.425 mm Post Compaction (max): 1000
label | PI Range Post Compaction: 6 - 25
label | Method - Document Review
label | Frequency - Each material specification
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Perforated Pipe-material
label | Reference - IFC Drawings
label | Acceptance Criteria - 100mm dia perforated plastic pipe
textbox | Reference: Teambinder MA number:
label | Method - Document review, Measure
label | Frequency - Each wall
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries-Documents
checkpoint | 3.1 - RSS Panels
label | Reference - IFC drawings
label | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | i. Certificate of Compliance / Birth Certificate
label | — 1. Concrete strength;
label | — 2.Date of manufacture;
label | — 3.Unique Identification number;
label | — 4.Mass;
label | — 5.Confirmation of number, type and capacity of lifting inserts;
label | — 6.Quality assurance sign-off.
label | ii. Compressive strength test results
label | iii. Precast Lifting Design
label | iv. Pre-pour check sheet / ITP
label | v. Post-pour check sheet / ITP
label | vi. Covermeter check record
label | vii. Record of dimensional measurements
label | ○ Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here)
textbox | Reference: Precast panels MDR Lot in TeamBinder:
label | Method - Document Review
label | Frequency - Once for each type of panels
label | Category - HP
label | Responsibility - PE
label | Verifying Documents - Precast panels Birth certificates and MDR Lot
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Foundation
label | Reference - IFC Drawings
label | ○ MRP-122-C-SME-DRG-31-NPT-CSW-5004
label | ○ MRP-122-C-SME-DRG-31-NPT-CSW-5011
label | Acceptance Criteria - Foundation material under RSS shall adhere with minimum design bearing capacity and geotechnical parameters.
label | ○ RW01 (SW):
label | — CH 0 - 28 : 100 kPa
label | — CH > 28 : 150 kPa
label | ○ RW02 (NW):
label | — CH 0 - 40 : 200 kPa
label | — CH 40 - 80 : 150 kPa
label | — CH > 80 : 100 kPa
label | ○ RW03 (NE):
label | — CH 0 - 40 : 100 kPa
label | — CH 40 - 80 : 150 kPa
label | — CH > 80 : 200 kPa
label | ○ RW04 (SE):
label | — CH 0 - 40 : 150 kPa
label | — CH > 40 : 100 kPa
label | ○ Effective Cohesion (Min): 5 kPa
label | ○ Effective Friction Angle (Min) 28°
label | Method - Test, Document Review, Visual
label | Frequency - Each retaining Wall
label | Category - HP*
label | Responsibility - PE/Geotechnical Engineer, Foundation geotechnical assessment
label | Verifying Documents - This ITP Signed off, Test results
date | Date Completed:
checkpoint | 4.2 - Foundation
label | Reference - VR 204.12, VR 204.11
label | Acceptance Criteria - Areas upon which fills are to be constructed shall be test rolled in accordance with VR 173
label | ○ No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
label | Method - Visual
label | Frequency - Each retaining Wall
label | Category - HP
label | Responsibility - PE/Niminated Authority
label | Verifying Documents - This ITP Signed off
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Levelling Pad-Survey Set out
label | Reference - IFC Drawings VR 682.20
label | Acceptance Criteria - Survey to set up and validate all works meets levels and locations with the right tolerances as per IFC Drawings and Vicroads Specification.
label | ○ Levelling course level shall not deviate from the specified level by more than +/- 3mm
label | Method - Measure, Visual
label | Frequency - Each retaining Wall
label | Category - IP
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP Signed off
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Form Levelling pad
label | Reference - IFC Drawings MRP-122-C-RFL-DRG-31-NPT-CSW-5117 - 5120
label | Acceptance Criteria - Form timber shutters or Earth form to edge of levelling pad
label | ○ Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
label | Method - Measure, Visual
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed off
date | Date Completed:
checkpoint | 5.2 - Leveling Pad Concrete Pour
label | Reference - IFC Drawings VR610
label | Acceptance Criteria - Concrete to be placed in accordance with VR610.
label | ○ Attach: Concrete Delivery Docket
label | Method - Visual
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Concrete Pour record, Concrete Delivery Docket
date | Date Completed:
checkpoint | 5.3 - Leveling Pad Concrete Testing
label | Reference - IFC Drawings VR Section 610.16 (b)
label | Acceptance Criteria - Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
label | ○ Concrete strength (Min): N25 MPa
label | ○ Attach: Concrete test report
label | Method - Document Review
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - PE
label | Verifying Documents - Attach Concrete Test Report
date | Date Completed:
checkpoint | 5.4 - Levelling Pad-Post Pour Survey-Levelling Course
label | Reference - IFC Drawings VR682.20
label | Acceptance Criteria - Levelling course level shall not deviate from the specified level by more than ±3mm
label | ○ Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | Method - Measure, Visual
label | Frequency - Each retaining Wall
label | Category - IP
label | Responsibility - PE/Surveyor
label | Verifying Documents - Attach Survey Report
date | Date Completed:
checkpoint | 5.5 - Wall Panels Installation
label | Reference - VR682.17
label | Acceptance Criteria - The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions.
label | ○ Refer to checklist for each course of panels
label | ○ Attach: Lot map
label | Method - Visual Measure
label | Frequency - Each course of facing panel
label | Category - HP*
label | Responsibility - SE/PE
label | Verifying Documents - Precast Panel Installation Checklist
date | Date Completed:
checkpoint | 5.6 - Drainage-base of the Wall
label | Reference - MRP-122-C-SME-DRG-31-NPT-CSW-5021 - 5022
label | Acceptance Criteria - Install 300mm x 300mm granular backfill in geotextile BIDIM A24 around 100mm Dia.
label | — Geotextile BIDIM A24
label | — 300mmx300mm Granular backfill
label | — 100mm Dia. Perforted plastic pipe
label | Method - Visual
label | Frequency - Each wall
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed off
date | Date Completed:
checkpoint | 5.7 - Fill
label | Reference - VR682.16
label | Acceptance Criteria - The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
label | ○ Refer to checklist for each fill layer
label | ○ Attach: Lot map
label | Method - Visual, Test, Measure
label | Frequency - Each layer of fill
label | Category - HP*
label | Responsibility - SE/PE
label | Verifying Documents - Inspection record checklist: CHK-CIV-CPD-RSS Walls - Fill Placement
date | Date Completed:
checkpoint | 5.8 - Settlement Monitoring horizontal inclinometer
label | Reference - IFC drawings MRP-122-C-SME-DRG-31-NPT-CSW-5011
label | Acceptance Criteria - Seven horizontal inclinometers shall be installed at the Northern and Southern ramps. Inclinometers shall be installed on the prepared foundation at the base of the RSS wall embankment.
label | Method - Document Review
label | Frequency - Each Inclinometer
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - Teambinder approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - As-built Survey
label | Reference - MRPA Quality Management Plan, IFC Drawings
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances as per IFC drawings.
label | (a) Plan position shown on the drawings, at base of wall shall not exceed ±15 mm;
label | (b) Relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
label | (c) Local deviation of the wall face measured at any location with a 3m straight edge shall not exceed 15mm;
label | (d) The tolerance on position measured at the top of the wall face shall not exceed 5mm per 1m of wall height;
label | (e) The wall level shall not deviate from the specified level by more than ±20mm;
label | (f) Variation in gap width between facing panels shall not exceed 5mm per metre length and 10mm over the full length of the gap.
label | (g) The levelling course level shall not deviate from the specified level by more than ±3 mm;
label | (h) The vertical deviation of the soil reinforcement shall be within +1% (upwards) & -0.3% (downwards) of the soil reinforcement length, relative to the connection height unless noted otherwise
label | ○ Attach: Survey As-built / Survey Report
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - Survey Report
date | Date Completed:
checkpoint | 6.2 - Wall Post construction monitoring
label | Reference - IFC Drawings VR 682.20, VR 682.151
label | Acceptance Criteria - The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
label | Method - Measure, Survey
label | Frequency - Each wall
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - Survey Report
date | Date Completed:
checkpoint | 6.3 - Settlement Monitoring
label | Reference - IFC Drawings VR 682.15, VR 682.20
label | Acceptance Criteria - The settlement monitoring frequency shall be:
label | 1. Base reading immediately following installation of first RSS panel.
label | 2. Reading after each 1.0m of fill placement, however not less than 1 reading per week.
label | 3. Minimum 1 reading per week during construction and post construction until movement stabilises.
label | 4. Minimum of 1 reading per month until end of DLP.
label | The measured settlement from the settlement monitoring program is required to be assessed against the theoretical settlement:
label | TIME PHASE ACTIVITIES
label | ○ TIME A: START OF RSS WALL CONSTRUCTION (FOUNDATION)
label | ○ TIME B: END OF RSS WALL /EMBANKMENT CONSTRUCTION
label | ○ TIME C: END OF WEARING COURSE (PAVEMENT COMPLETION INCLUDING WEARING COURSE)
label | ○ TIME D: PC (PRACTICAL COMPLETION)
label | ○ TIME E: END OF DEFECTS LIABILITY PERIOD (EoDLP)
label | ○ TIME F: DESIGN LIFE
label | Method - Measure, Survey, Document Review
label | Frequency - 1m of fill
label | Category - HP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - Settlement monitoring results
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | CHK-013-CIV-MSS-RSS Walls-Fill Placement | [5 empty] | CHK-013-CIV-MSS-RSS Walls-Fill Placement Rev 0
section | Details
checkpoint-no-value | Referenced Documentation
label | Document Title: CHK-13-CIV-MSS-RSS Walls-Fill Placement
label | Checklist Description: RSS Walls-Fill Placement
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 02/10/2025
label | ITP created by: Matthew Dib
label | ITP approved for use by: Romualdo Magpantay
checkpoint | 1 - Soil reinforcement-Straps
label | Reference - VR682.08, VR682.17 IFC Drawings
label | Acceptance Criteria - Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels.
label | ○ Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
label | Method - Visual
label | Frequency - Each strap
label | Category - WP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 2 - Soil reinforcement-Straps
label | Reference - Installation manual
label | Acceptance Criteria - Correct number of reinforcing element shall be attached to each panel/wire facing units
label | Method - Visual
label | Frequency - Each panel
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 3 - Pre-cast Panel Soil reinforcements-Bolts Connections
label | Reference - IFC Drawings
label | ○ Schedule of lengths: MRP-122-C-RFL-DRG-31-NPT-CSW-5121, 5125, 5126, 5132, 5135
label | ○ Connections arrangement: MRP-122-C-RFL-DRG-31-NPT-CSW-5104 - 5106
label | Acceptance Criteria - Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel
label | ○ Finger tight nut or use a wrench so thread emerges from top of nut
label | Method - Visual
label | Frequency - Each Fill Layer
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 5 - Soil reinforcements-Plan arrangement
label | Reference - IFC Drawings
textbox | Arrangements:
label | Acceptance Criteria - Plan positions of Grid Strips are to be as IFC Drawings.
label | — Grid Strips to be placed perpendicular to back of panel where possible.
label | — Grid strips shall not overlap
label | Method - Visual
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 6 - Soil reinforcements-vertical/horizontal deviation
label | Reference - VR682.17
label | Acceptance Criteria - Soil reinforcement elements must be placed at the required level and position directly on top of the compacted fill material and connected to the facing panels in accordance with the design. Any twists, kinks, sags or deviations in the reinforcing elements must be removed. The level at the free end of the soil reinforcements must not deviate more than 1.0% along their length prior to the placement of fill material on the soil reinforcements. Wall construction must include provision of inserts where specified.
label | Method - Measure, Survey
label | Frequency - Each fill Layer
label | Category - IP
label | Responsibility - Surveyoe/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 7 - Soil reinforcements-clash with drainage
label | Reference - IFC Drawings MRP-122-C-RFL-DRG-31-NPT-CSW-5124, 5129
label | Acceptance Criteria - Avoid clash with stormawater pipe as per IFC drawings.
label | ○ Top layer/s of grid-strips to be shortened to avoid clash with storm water pipe and pits.
label | Method - Visual
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 8 - Fill-Placement
label | Reference - VR204.10
label | Acceptance Criteria - Select backfill shall be placed in accordance with Vicroads section 204.
label | ○ Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm.
label | ○ Fill dispensation to be granted by superintendent to increase thickness layers.
label | ○ All RSS fill layers to be spread from face of panel to tail of soil reinforcing straps.
label | Method - Measure, Visual
label | Frequency - Each fill layer
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 9 - Fill-Placement compaction
label | Reference - 204.111
label | Acceptance Criteria - 0 - 0.15 m Light weight hand operated DPU
label | ○ 0.15 - 0.30 m Less than 5T Roller
label | ○ 0.3 - 1.2 m Less than 10T Roller
label | ○ 1.2 - 2.4 m Less than 20T Roller
label | ○ >2.4 m Less than 35T Roller
label | Method - Visual
label | Frequency - Each fill layer
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 10 - Fill Test roll
label | Reference - VR 204.12
label | Acceptance Criteria - All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling
label | ○ Static Smooth drum roller with a mass >12T; or
label | ○ Tandem truck or water cart with a mass >20T.
label | ○ No visible deformation or springing during test roll.
label | ○ Unstable areas rectified as per agreed method.
label | Method - Visual
label | Frequency - Every Fill Layer
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This Checklist
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Select back fill-Compaction Testing
label | Reference - IFC Drawings VR 204.14, VR 682.16
label | Acceptance Criteria - Testing frequency shall be in accordance with Vicroad Specification section 204.14
label | ○ Moisture content shall achieve minimum characteristic value of density ratio: 98%
label | ○ Moisture content of backfill shall be maintained evenly at all times. Moisture content shall be +0%/-2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content must be allowed to dry.
label | ○ Attach: Compaction test results
label | Method - Documet review
label | Frequency - Each Fill Layer or every second layer as agreed
label | Category - IP
label | Responsibility - Nominated Authority/PE
label | Verifying Documents - Attached Test Results
date | Date Completed:
checkpoint | 12 - Select back fill-Test frequency
label | Reference - IFC Drawings VR 204.14, VR 682.16
label | Acceptance Criteria - After three consecutive lots of like material have achieved the specified requirement, reduce frequency of testing of subsequent lots to the minimum requirement specified in table 204.142:
label | Method - Documet review
label | Frequency - Each Fill Layer or every second layer as agreed
label | Category - IP
label | Responsibility - Nominated Authority/PE
label | Verifying Documents - Referenced Lots in This Checklist
date | Date Completed:
checkpoint | 13 - Survey Conformance Asbuilt
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
label | Method - Documet review
label | Frequency - Each Fill Layer
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - Attach: Survey Conformance As Built
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | CHK-014-CIV-MSS-RSS Walls-Pre-cast Panel Installation | [5 empty] | CHK-014-CIV-MSS-RSS Walls-Pre-cast Panel Installation Rev 0
section | Details
checkpoint-no-value | Referenced Documentation
label | Document Title: CHK-14-CIV-MSS-RSS Walls-Pre-cast Panel Installation
label | Checklist Description: RSS Walls - Panel Installation
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 02/10/2025
label | ITP created by: Matthew Dib
label | ITP approved for use by: Romualdo Magpantay
checkpoint | 1 - Panels survey set out tolerance
label | Reference - VR 682.20 IFC Drawings MRP-122-C-RFL-DRG-31-NPT-CSW-5101
label | Acceptance Criteria - Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | Method - Measure
label | Frequency - Base course panels
label | Category - IP
label | Responsibility - Surveyor/PE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 2 - Mark-up panel for construction team
label | Reference - IFC Drawing: MRP-122-C-RFL-DRG-31-NPT-CSW-5121 to 5137
label | Acceptance Criteria - Mark number of strips per row on the back of each panel.
label | — Mark design location (Wall number, row and column) as per elevation drawings on the back of each panel
label | Method - Visual
label | Frequency - Each panel
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 3 - Panel installation
label | Reference - IFC Drawings
label | Acceptance Criteria - RSS Panels are to be installed as per IFC Drawings and specified schedule.
label | — Check for correct architectural pattern
label | — Check for Weephole Locations
label | — Check the 1 in 40 slope is to be maintained
label | — Check the 19mm nominal gap to be maintained / 25mm gap at slip joint location
label | Method - Visual, Measure
label | Frequency - Each panel
label | Category - WP
label | Responsibility - SE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 4 - Bearing Pad Installation
label | Reference - IFC Drawing: MRP-122-C-RFL-DRG-31-NPT-CSW-5103
label | Acceptance Criteria - 3 x bearing pads must be installed per panel - Centre of the outer bearing pads must be 200mm+/-10mm from the edge of the panel
label | — Install 3 Bearing Pads at rear on top of panels
label | — Above must be checked with Surveyor prior to backfill
label | — Note bearing pads shall not be installed under base row panels
label | Method - Visual
label | Frequency - Each panel
label | Category - WP
label | Responsibility - SE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 5 - Panel installation - Abutment interfaces
label | Reference - IFC Drawings
label | ○ MRP-122-C-RFL-DRG-31-NPT-CSW-5115
label | ○ RP-122-C-RFL-DRG-31-NPT-CSW-5116
label | Acceptance Criteria - Panel installation and abutment interface:
label | — 275 x 6 HD galvanised folded plate, drill and fix 150mm leg to abutment with Galv. M12x75 excalibur screwbolts at 500 crs
label | —600mm wide Bitac tape located centrally
label | — RSS panel to be attached to abutment wall with anchor connection
label | Method - Measure
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 6 - Panel Installation - Slip Joint Detail
label | Reference - IFC Drawings: MRP-122-C-RFL-DRG-31-NPT-CSW-5121
label | Acceptance Criteria - Install slip joint detail - M16 Ferrule and grade 4.6/S M16x75 long bolt at 500 crs & Grade 250 6mm galvanised plate
label | ○ RW01 - Column 34
label | ○ RW02 - Column 2
label | ○ RW03 - Column 55
label | ○ RW04 - Column 1
label | Method - Visual
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 6 - Filter fabric -Installation
label | Reference - IFC Drawings MRP-122-C-RFL-DRG-31-NPT-CSW-5103, VR682.11
label | Acceptance Criteria - Install Filter Fabric against all vertical and horizontal joints
label | Method - Visual
label | Frequency - Each course of panel installation
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 7 - Drainage-Strip Drain
label | Reference - VR682.11
label | Acceptance Criteria - Install 300mm wide strip drain between precast wall panel vertical joints.
label | ○ Strip drain to be encapsulated by nonwoven geotextile in accordance with section 682.11
label | ○ At every vertival joint between panels in RSS wall, ensure no gap is formed bewteen strip drian and RSS panels
label | Method - Visual
label | Frequency - Each course of panel installation
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 8 - Panel installation-Survey reference points
label | Reference - VR 682.20
label | Acceptance Criteria - To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
label | Method - Visual
label | Frequency - Each course of panel installation
label | Category - IP
label | Responsibility - Surveyor/SE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 9 - Traceability of precast units and records
label | Reference - VR 620.09
label | Acceptance Criteria - Unique ID of precast panel is recorded.
label | ○ ATTACH: marked-up elevation drawings or installation record with reference to panel ID
label | Method - Visual
label | Frequency - Each panel
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | 10 - Panels installation-Conformance Survey
label | Reference - IFC Drawings
label | ○ VR 682.06
label | ○ VR 682.17
label | ○ VR 682.20
label | Acceptance Criteria - The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | — Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
label | — Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
label | —Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full length of the gap
label | — The wall level shall not deviate from the specified level by more than ±20mm
label | — The tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
label | — The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
label | ○ Attach: Survey Report
label | Method - Survey, Measure
label | Frequency - Each course of panel installation
label | Category - HP*
label | Responsibility - Surveyor/PE
label | Verifying Documents - This Checklist Signed-off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | CHK-015-STR-MSS-Precast Material Inspection | [5 empty] | CHK-015-STR-MSS-Precast Material Inspection Rev 0
section | Details
checkpoint-no-value | Referenced Documentation
label | Document Title: CHK-15-STR-MSS-Precast Material Inspection
label | Checklist Description: Precast Material Inspection
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 2/10/2025
label | ITP created by: Matthew Dib
label | ITP approved for use by: Romualdo Magpantay
checkpoint | 1 - Delivery Details
label | Acceptance Criteria - Enter: Delivery Docket Number: [Free text box]:
textbox | Enter: Delivery Date:
textbox | Enter: Element ID (s):
label | ○ Attach: Delivery Docket and packaging Slip
label | Method - Document Review, Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 2 - Packaging Inspection-Quantity
label | Acceptance Criteria - Does the number of packages/items in the delivery match that listed on the freight list and/or docket?
label | Method - Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 3 - Packaging Inspection-Delivery Contents
label | Acceptance Criteria - Have the correct precast elements been delivered? Check labels/markings, birth certificates and check actual dimensions against dwgs to make sure. Check that elements have the correct number of lifting points and hold-down brackets.
label | Method - Document Review, Visual
label | Frequency - Each Delivery
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 4 - Packaging Inspection-Birth Certificate
label | Acceptance Criteria - Is the delivery accompanied by Precast items Birth Certificates?
label | ○ Precast components are to be marked on the birth certificate.
label | ○ Cast date and lot are to be marked on the birth certificate.
label | ○ ATTACH: BIRTH CERTIFICATES
label | Method - Document Review
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - Birth Certificate
date | Date Completed:
checkpoint | 5 - Product Verification prior to delivery
label | Reference - VR620.08
label | Acceptance Criteria - Prior to delivery have the following evidence been provided:
label | 1 - Validation that the concrete strength is as per the 28-day strength in IFC (40MPa or 50MPa)
label | 2 - Validation that the precast elements are least 7 days (168 hours) old?
label | Method - Document Review
label | Frequency - Each Precast Item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - Concrete Test Reports Birth Certificate
date | Date Completed:
checkpoint | 6 - Packaging Inspection-Transport
label | Acceptance Criteria - Is the condition of packaging acceptable.
label | ○ Precast items are protected from damage during the transport. Check for cracking or damage around dunnage locations.
label | ○ Are the Ferrules capped with a protective cap
label | Method - Visual
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 7 - Product Inspection - Markings
label | Reference - VR620.06
label | Acceptance Criteria - Are markings of the element on each element and approximately 40mm high?
label | Method - Visual
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 8 - Product Inspection - Reinforcement & Cast-in items
label | Reference - VR620.04
label | Acceptance Criteria - 1 - Has any of the projecting reinforcement been damaged?
label | 2 - Are bars as per shop drawings and within tolerance (±3 mm)?
label | Method - Visual, Measure
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 9 - Product Inspection - Dimensional Tolerances
label | Acceptance Criteria - Have the dimensions of the item been verified?
label | 1 - Validation of dimensions
label | 2 - Validation of cast-in locatios
label | 3 - Validation of Hog (if referring to beams)
label | Method - Visual, Measure
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 10 - Pre-Lift Inspection-Transport
label | Acceptance Criteria - Are the elements stacked in the correct way to allow for lifting per the approved lift plan? Check lifting points for damage to concrete or lifters. Is there safe access to lifting points and elements can be lifted without damaging the element.
label | Method - Visual
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 11 - Fault IDs:
label | Acceptance Criteria - For each precast type delivered, check for the following:
label | 1 - Identification markings match the panel type
label | 2 - Element fabricated as per drawings
label | 3 - Cracks
label | 4 - Spalling/Damage to concrete surface
label | 5 - Exposed Reinforcement
label | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
label | 8 - Cast-in items incorrect or damaged inc bolts, hold-down brackets, conduits etc.
label | Method - Visual
label | Frequency - Each Precast item
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 12.1 - Check for Faults - 1
label | Reference - Item 7 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 12.2 - Check for Faults - 2
label | Reference - Item 7 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 12.3 - Check for Faults - 3
label | Reference - Item 7 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 12.4 - Check for Faults - 4
label | Reference - Item 7 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 12.5 - Check for Faults - 5
label | Reference - Item 7 on this Checklist
label | Acceptance Criteria - For Each Precast type delivered:
textbox | Enter: Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
label | Method - Visual, Measure
label | Frequency - Each precast type delivered
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP