## ITP Cover Page
Chipseal Maintenance strip Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 035 - Rev 0
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 035
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | IFC
ITP Description: |  |  | Chipseal Maintenance Strip |  |  |  |  | Revision: | 1000 |  | 0
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-PVS
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Contract Specifications, TCC IDC, TNZP/3
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft | 26/03/2025 |  | Cordelia Girdler-Brown & Chris Benson | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Chris Benson | [5 empty] | Downer PM
Downer QM |  | Cordelia Girdler-Brown |  |  |  |  | 28/03/2025 | Downer QM

## Master Body
Chipseal Maintenance Strip Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 035 - Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
3.1 | MATERIAL APPROVALS: Imported Material Testing - AP65-2 - Source Property Tests for Type A1 Imported Structural Fill - ALL TESTS TO BE NO OLDER THAN 3 MONTHS | [12 empty] | Final
3.1.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | NZS4407:2015 Test 3.10 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1.2 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | >60% | NZS4407:2015 Test 3.15 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1.3 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA,AB,AC,BA,BB,CB or CA | NZS4407:2015 Test 3.11 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1.4 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Sieve Percentage Passing 63.0 100% 37.5 68-90% 19 42-76% 9.5 26-58% 4.75 16-44% 2.36 10-33% 1.18 6-24% 0.425 3-14% 0.075 1-6% | NZS4407:2015 Test 3.8.1 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.1.5 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | NZS4402:1986 Test 4.1.2 | IANZ Accredited Report | 1 Test Per Material, PerSource | HP | ENG
on | Plasticity Index | NZS4407:2015, Test 3.4 Plasticity Index | <8 | NZS4407:2015 Test 3.4 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1.7 | Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent | >25 | NZS4407:2015 Test 3.6 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.2 | CHIPSEAL MATERIAL APPROVALS
3.2.1 | Chipseal Design | Peer review by WSP | Approval From WSP | Design meets requirements of P17 | Seal Design Report | Once | HP | ENG
3.2.2 | Cleanliness (Grades 2-6) | Lab Test | Cleanness value G2 = 89 G3 = 87 G4 = 85 G5 & G6 Report only | NZTA M/6 | IANZ Accredited Report | 1/500m3 | HP | ENG
3.2.3 | Compatibility (Multi Layered seals) | Comparison Of Chip ALD 6.84 3.62 |  | Chipsealing in New Zealand NZTA (NZTA 2005) | IANZ Accredited Report | ]1 Test Per Material, Per Source | HP | ENG
3.2.4 | Bitumen Distributor | Code of Compliance IANZ Lab E/2 Results | Speed Test(+-3% over 100m), Dipstick Test (+-50L over 2000L), Matt Test (app rate within 0.10L/m2, longitudinal within 10%, thirds within 5%, transverse within 20%) | Code of Compliance | RNZ E2 Certificate | 1 Test Per Material, Per Source | HP | ENG
3.2.5 | Emulsion / BitumenTesting | Manufacture Specification | Bitumen Content, ITM 11-01, Viscosity, ITM 10-02, PH ITM-08-02 | P/3 | Lab Testing | Per Emulsion/Bitumen Production Batch | HP | ENG
SECTION 4 - CONSTRUCTION - SUBBASE CONSTRUCTION - PREP GENERAL
5.1 | GENERAL
4.1 | Cut Subgrade Testing - Granular Soil Scala Penetrometer | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material | Minimum 3 blows per 100mm penetration | PS 27.4.2 | Scala Report | 4 test per 400M2 | I | SE
4.2 | Proof roll | Visual Inspection of Proof Roll | Visual Inspection of Proof Roll | Appendix XVIII | Visual inspection/ Photos | Across Whole are | I | ENG
4.3 | Compaction structural fill - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >98% of MDD Min >95% of MDD | NZTA B/02 7.6 | IANZ Accredited Report | 1 set (5 tests) 1000m2 | I | SE
SECTION 5 - CONSTRUCTION - CHIPSEAL CONSTRUCTION
5.1 | Pre Seal Survey | Survey to mark out setout | As per Design | Standard | Survey Records | Once - across Whole Zone | I | SE
5.2 | Pre seal Inspection | Pre Seal Inspection needs to be done by WSP. | Visual Inspection | Standard | Visual inspection/ Photos | Once - across Whole Zone | I | SE
5.3 | Road Furniture | Protect all road furniture in accordance with Crew Breifing Plan (Signs sockets Etc) | General | Standard | Crew Briefing Plan | continous - across whole Zone | I | SE
5.4 | Kerbs protected | Fabric & protect all kerb ande chanel where required | Visual Inspection | TNZ P/3 | Visual inspection/ Photos | continous - across Whole Zone | I | SE
5.5 | Spraying | Mark out start / Finish | Paper Start and Finish all runs | TNZ P/3 | Spray Sheet | continous - across Whole Zone | I | SE
5.6 | Removal of Surplus Chip | All sump and road furniture protection removed. | Visual Inspection | Standard | Visual inspection/ Photos | continous - across Whole Zone | I | SE
SECTION 6 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.1 | As-Builts Red Pen markup | Final inspection of All Work | All works meet project specifications and standards. Record Any Undercuts or change in Design | PS 16.7.6 | Survey Records Red Pen Mark up | During Earthworks | D | SV