## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-035 ITP Chipseal Maintenance Strip | itp |  |  |  |  | DN1210-035 ITP Chipseal Maintenance Strip Rev 0
section | SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 3.1.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - NZS4407:2015 Test 3.10
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - >60%
label | Standard / Specification - NZS4407:2015 Test 3.15
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA,AB,AC,BA,BB,CB or CA
label | Standard / Specification - NZS4407:2015 Test 3.11
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.4 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve ¦¦ Percentage Passing
label | 63.0 ¦¦ 100%
label | 37.5 ¦¦ 68-90%
label | 19 ¦¦ 42-76%
label | 9.5 ¦¦ 26-58%
label | 4.75 ¦¦ 16-44%
label | 2.36 ¦¦ 10-33%
label | 1.18 ¦¦ 6-24%
label | 0.425 ¦¦ 3-14%
label | 0.075 ¦¦ 1-6%
label | Standard / Specification - NZS4407:2015 Test 3.8.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.5 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4402:1986 Test 4.1.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, PerSource
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | on - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - <8
label | Standard / Specification - NZS4407:2015 Test 3.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.7 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - >25
label | Standard / Specification - NZS4407:2015 Test 3.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.1 - Chipseal Design
label | Detail - Peer review by WSP
label | Acceptance / Conformance Criteria - Approval From WSP
label | Standard / Specification - Design meets requirements of P17
label | Verifying Document - Seal Design Report
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - Cleanliness (Grades 2-6)
label | Detail - Lab Test
label | Acceptance / Conformance Criteria - Cleanness value
label | ○ G2 = 89
label | ○ G3 = 87
label | ○ G4 = 85
label | ○ G5 & G6 Report only
label | Standard / Specification - NZTA M/6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1/500m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.3 - Compatibility (Multi Layered seals)
label | Detail - Comparison Of Chip ALD 6.84, 3.62
label | Acceptance / Conformance Criteria - Two Coat Seal Aggregate Compatibility graph
label | Standard / Specification - Chipsealing in New Zealand NZTA (NZTA 2005)
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.4 - Bitumen Distributor
label | Detail - Code of Compliance, IANZ Lab E/2 Results
label | Acceptance / Conformance Criteria - Speed Test(+-3% over 100m), Dipstick Test (+-50L over 2000L), Matt Test (app rate within 0.10L/m2, longitudinal within 10%, thirds within 5%, transverse within 20%)
label | Standard / Specification - Code of Compliance
label | Verifying Document - RNZ E2 Certificate
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.5 - Emulsion / BitumenTesting
label | Detail - Manufacture Specification
label | Acceptance / Conformance Criteria - Bitumen Content, ITM 11-01, Viscosity, ITM 10-02, PH ITM-08-02
label | Standard / Specification - P/3
label | Verifying Document - Lab Testing
label | Testing Quantity Required (based from schedule qtys) - Per Emulsion/Bitumen Production Batch
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 - CONSTRUCTION - SUBBASE CONSTRUCTION - PREP GENERAL
checkpoint | 4.1 - Cut Subgrade Testing - Granular Soil Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
label | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
label | Standard / Specification - PS 27.4.2
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2 - Proof roll
label | Detail - Visual Inspection of Proof Roll
label | Acceptance / Conformance Criteria - Visual Inspection of Proof Roll
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Visual inspection/ Photos
label | Testing Quantity Required (based from schedule qtys) - Across Whole are
label | Verification Activity: Activity - I
label | Verification Activity: By - ENG
checkpoint | 4.3 - Compaction structural fill - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >98% of MDD
label | ○ Min >95% of MDD
label | Standard / Specification - NZTA B/02 7.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 - CONSTRUCTION - CHIPSEAL CONSTRUCTION
checkpoint | 5.1 - Pre Seal Survey
label | Detail - Survey to mark out setout
label | Acceptance / Conformance Criteria - As per Design
label | Standard / Specification - Standard
label | Verifying Document - Survey Records
label | Testing Quantity Required (based from schedule qtys) - Once - across Whole Zone
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2 - Pre seal Inspection
label | Detail - Pre Seal Inspection needs to be done by WSP.
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - Standard
label | Verifying Document - Visual inspection/ Photos
label | Testing Quantity Required (based from schedule qtys) - Once - across Whole Zone
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3 - Road Furniture
label | Detail - Protect all road furniture in accordance with Crew Breifing Plan (Signs sockets Etc)
label | Acceptance / Conformance Criteria - General
label | Standard / Specification - Standard
label | Verifying Document - Crew Briefing Plan
label | Testing Quantity Required (based from schedule qtys) - continous - across whole Zone
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.4 - Kerbs protected
label | Detail - Fabric & protect all kerb ande chanel where required
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - TNZ P/3
label | Verifying Document - Visual inspection/ Photos
label | Testing Quantity Required (based from schedule qtys) - continous - across Whole Zone
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.5 - Spraying
label | Detail - Mark out start / Finish
label | Acceptance / Conformance Criteria - Paper Start and Finish all runs
label | Standard / Specification - TNZ P/3
label | Verifying Document - Spray Sheet
label | Testing Quantity Required (based from schedule qtys) - continous - across Whole Zone
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.6 - Removal of Surplus Chip
label | Detail - All sump and road furniture protection removed.
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - Standard
label | Verifying Document - Visual inspection/ Photos
label | Testing Quantity Required (based from schedule qtys) - continous - across Whole Zone
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 6 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.1 - As-Builts Red Pen markup
label | Detail - Final inspection of All Work
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | ○ Record Any Undercuts or change in Design
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Survey Records, Red Pen Mark up
label | Testing Quantity Required (based from schedule qtys) - During Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature