## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: P11901-SOW-IEC-202 - Kaitoke CS Sump Remediation
| step |  |  | Tier 2: West Sump - T04010 Turret
| step |  |  | Tier 3: JB-04029
ITR-E-07 - Junction Box | checklist |  |  | Tier 4: Junction Box
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 4: 16 pair cable 0.5mm CU/PVC/CS/SWA/PVC
ITR-E-02B Cable Supports Above Ground | checklist |  |  | Tier 4: ITR-E-02B Cable Supports Above Ground
ITR-E-02A Conduit/Ducting Below Ground | checklist |  |  | Tier 4: 100mm Conduit from JB to T-04010 Turret
| step |  |  | Tier 3: PSH-04001
ITR-I-06 Instrument Installation | checklist |  |  | Tier 4: Pressure Switch
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 4: 1 pair cable 1.5mm CU/PVC/CS/SWA/PVC
ITR-I-02 Instrument Tubing Installation | checklist |  |  | Tier 4: Swagelok instrument tube and fittings
ITR-I-02 Instrument Tubing Installation | checklist |  |  | Tier 4: HV-040489
| step |  |  | Tier 3: PSH-04002
ITR-I-06 Instrument Installation | checklist |  |  | Tier 4: Pressure Switch
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 4: 1 pair cable 1.5mm CU/PVC/CS/SWA/PVC
ITR-I-02 Instrument Tubing Installation | checklist |  |  | Tier 4: Swagelok instrument tube and fittings
ITR-I-02 Instrument Tubing Installation | checklist |  |  | Tier 4: HV-040494
| step |  |  | Tier 3: PSH-04003
ITR-I-06 Instrument Installation | checklist |  |  | Tier 4: Pressure Switch
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 4: 1 pair cable 1.5mm CU/PVC/CS/SWA/PVC
ITR-I-02 Instrument Tubing Installation | checklist |  |  | Tier 4: Swagelok instrument tube and fittings
ITR-I-02 Instrument Tubing Installation | checklist |  |  | Tier 4: HV-040488
| step |  |  | Tier 3: LSH-04004
ITR-I-06 Instrument Installation | checklist |  |  | Tier 4: Level Switch
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 4: 2 pair cable 1.5mm CU/PVC/CS/SWA/PVC
ITR-I-02 Instrument Tubing Installation | checklist |  |  | Tier 4: Swagelok instrument tube and fittings
| step |  |  | Tier 3: FS-04006
ITR-I-06 Instrument Installation | checklist |  |  | Tier 4: Flow Switch
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 4: 2 pair cable 1.5mm CU/PVC/CS/SWA/PVC
| step |  |  | Tier 3: LIT-04004
ITR-I-06 Instrument Installation | checklist |  |  | Tier 4: Level Transmitter
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 4: 1 pair cable 1.5mm CU/PVC/CS/SWA/PVC
ITR-I-02 Instrument Tubing Installation | checklist |  |  | Tier 4: Bleed Ring - Wika 910.27 - 1/2 FNPT 316SS
ITR-I-02 Instrument Tubing Installation | checklist |  |  | Tier 4: Swagelok instrument tube and fittings
| step |  |  | Tier 3: LIT-04005
ITR-I-06 Instrument Installation | checklist |  |  | Tier 4: Level Transmitter
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 4: 1 pair cable 1.5mm CU/PVC/CS/SWA/PVC
ITR-I-02 Instrument Tubing Installation | checklist |  |  | Tier 4: Swagelok instrument tube and fittings
| step |  |  | Tier 3: Earthing
| step |  |  | Tier 4: E105
ITR-E-12 Electrical earthing | checklist |  |  | Tier 5: 70mm CU/PVC 1c 0.6/1KV
| step |  |  | Tier 4: ZR7
ITR-E-12 Electrical earthing | checklist |  |  | Tier 5: 12x14 Zinc Ribbon
| step |  |  | Tier 4: EB-04014
ITR-E-12 Electrical earthing | checklist |  |  | Tier 5: Earth Bar
| step |  |  | Tier 3: As Built Drawings Complete
Sign Off | checklist |  |  | Tier 4: Entec Supervisor
| step |  |  | Tier 3: COC, ESC, ROI
Certificate of compliance (COC) | checklist |  |  | Tier 4: COC
Electrical Safety Ceritificate (ESC) | checklist |  |  | Tier 4: ESC
Record of Inspection (ROI) | checklist |  |  | Tier 4: ROI
Test Equipment Details: | checklist |  |  | Tier 4: Test Equipment
| step |  |  | Tier 3: Workpack Completion Sign Off
Sign Off | checklist |  |  | Tier 4: Entec Supervisor
Sign Off | checklist |  |  | Tier 4: First Gas Construction Manager
Sign Off | checklist |  |  | Tier 4: First Gas Project Manager
| step |  |  | Tier 2: East Sump - A-04002 Turret
| step |  |  | Tier 3: JB-04030
ITR-E-07 - Junction Box | checklist |  |  | Tier 4: Junction Box
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 4: 4 pair cable 0.5mm CU/PVC/CS/SWA/PVC
ITR-E-02B Cable Supports Above Ground | checklist |  |  | Tier 4: ITR-E-02B Cable Supports Above Ground
ITR-E-02A Conduit/Ducting Below Ground | checklist |  |  | Tier 4: 100mm Conduit from JB to A-04002 Turret
| step |  |  | Tier 3: LIT-04002
ITR-I-06 Instrument Installation | checklist |  |  | Tier 4: Level Transmitter
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 4: 1 pair cable 1.5mm CU/PVC/CS/SWA/PVC
ITR-I-02 Instrument Tubing Installation | checklist |  |  | Tier 4: Bleed Ring - Wika 910.27 - 1/2 FNPT 316SS
ITR-I-02 Instrument Tubing Installation | checklist |  |  | Tier 4: Swagelok instrument tube and fittings
| step |  |  | Tier 3: LIT-04003
ITR-I-06 Instrument Installation | checklist |  |  | Tier 4: Level Transmitter
ITR-I-21A - Instrument and Control Cables | checklist |  |  | Tier 4: 1 pair cable 1.5mm CU/PVC/CS/SWA/PVC
| step |  |  | Tier 3: Earthing
| step |  |  | Tier 4: E105
ITR-E-12 Electrical earthing | checklist |  |  | Tier 5: 70mm CU/PVC 1c 0.6/1KV
| step |  |  | Tier 4: ZR7
ITR-E-12 Electrical earthing | checklist |  |  | Tier 5: 12x14 Zinc Ribbon
| step |  |  | Tier 4: EB-04003
ITR-E-12 Electrical earthing | checklist |  |  | Tier 5: Earth Bar
| step |  |  | Tier 3: As Built Drawings Complete
Sign Off | checklist |  |  | Tier 4: Entec Supervisor
| step |  |  | Tier 3: COC, ESC, ROI
Certificate of compliance (COC) | checklist |  |  | Tier 4: COC
Electrical Safety Ceritificate (ESC) | checklist |  |  | Tier 4: ESC
Record of Inspection (ROI) | checklist |  |  | Tier 4: ROI
Test Equipment Details: | checklist |  |  | Tier 4: Test Equipment
| step |  |  | Tier 3: Workpack Completion Sign Off
Sign Off | checklist |  |  | Tier 4: Entec Supervisor
Sign Off | checklist |  |  | Tier 4: First Gas Construction Manager
Sign Off | checklist |  |  | Tier 4: First Gas Project Manager