## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
73d8f2e1-5e24-469f-a500-9c738f392843 | checklist | ITC: 5 - Inground Conduit Installation (UPDATED) |  | Pour #
ae5b7970-7d5c-4c36-8106-9e7e376510de | section | Inground Conduit Installation
33779d1b-92dd-4b1f-bc59-a355571acbce | checkpoint | Correct location to drawing
1c5fb067-0030-5721-981b-c60c70cd79db | textbox | Drawing Number:
9dac69c0-a5f8-50c1-acd1-d61f7c85f7e8 | textbox | Revision:
02d87056-df72-4496-a9d9-df76a4722c57 | checkpoint | Correct size and type
86e26973-27fa-5060-8625-2e77c7492e25 | textbox | Conduit size & type required:
ff97890b-892e-5765-b5d8-3fbe9e04cc70 | textbox | Conduit size & type installed:
843a6385-61c4-47b2-bd0b-6ddad25999eb | checkpoint | Correct spacing in slabs
a58a39ac-a9bd-508a-ae06-a7f12a6cccc6 | textbox | Spacing required:
4ebabab6-ac8e-5b2f-ab9a-4414ceb760f6 | textbox | Spacing measured:
825588ce-5e35-4e42-adb3-9f36340075f9 | checkpoint | Correct alignment
91a50086-3977-4ff0-8ebc-d429e805c502 | checkpoint | Clear to other services
7f8a6d6f-c349-4255-9778-f139def2a2ad | checkpoint | Correct depth underground
59e0b636-9323-583e-a3f3-31d65f7e25c5 | textbox | Depth required:
04712e61-6ba7-5f89-bd4a-00aebb7f7213 | textbox | Depth measured:
b00bb701-41fd-43e0-aafb-35943f5266c0 | checkpoint | Correctly marked (tape or other)
934ce5fb-ba80-5f79-bd85-e76b8170b428 | textbox | Tape/cover used:
78f7e172-0850-51ac-8295-062eaccc324d | tickbox | Photo of marking tape/cover used
b720b61d-fa92-4525-b9a2-da7aff36347f | checkpoint | Correct fixing and safe
5941bc1e-5ce6-544b-889f-eae33f714167 | textbox | Fixing used:
ba5840fb-2c82-5a6d-b838-4719f440ad8f | tickbox | Photo of fixing used
461b1231-5d54-4e12-a677-0036b0248632 | signoff | HOLD POINT - SIGN OFF BY WATPAC & HEYDAY
9816de6c-887b-46bc-b0ee-aaee0c7b7496 | section | Trench Backfill
bd48bea3-dce7-429c-8261-2e870d4dffdf | checkpoint | Correct backfill and surfaces
64d614a1-3951-528a-a8c3-2d5a9090d66f | textbox | Backfill used:
70ba6766-b3c7-58f2-9eab-5e9e8b467b00 | tickbox | Photo of backfill
ca7ef0a8-37c0-4c9a-a31d-41975816ca96 | checkpoint | Sufficient photo evidence uploaded
51893cce-12e6-5adf-abb2-33bee503c1c3 | note | Attach Photos:
ae329d77-ba6b-5afc-8e59-e8d2cad78eab | tickbox | Before install
9aa440ff-5e8c-59b4-b7bc-e7066548fd8b | tickbox | During install
5e822094-f3dd-5b9b-86f1-c189ac128069 | tickbox | Pre backfill
3c5c7821-4d7e-5ea0-94cb-c9aa47638b8f | tickbox | Finish
5a174fae-ea93-45ef-b3d2-19fa6233a452 | signoff | Heyday sign off