## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | SNPBE1-00-QCL-ITP-3150 - Master | itp |  |  |  |  | SNPBE1-00-QCL-ITP-3150 - Master Rev A
section | SECTION 3 – FINAL INSPECTION AND HANDOVER
checkpoint | 3.1 - Completions – Fabrication of Structure and Assembly of Steel Work
label | INSPECTION POINT: QUALITY CONTROL ACTIVITY - ITP Completion and Submission.
label | ACCEPTANCE CRITERIA - Client Sign off.
label | VERIFYING DOCUMENT - Completed ITP, SNPBE1-00-QCL-ITP-3151
label | Inspection/ Test: Key - R
label | Inspection/ Test: By - NEI-PE, QM
checkpoint | 3.2 - Completions – Building Services
label | INSPECTION POINT: QUALITY CONTROL ACTIVITY - ITP Completion and Submission.
label | ACCEPTANCE CRITERIA - Client Sign off.
label | VERIFYING DOCUMENT - Completed ITP, SNPBE1-00-QCL-ITP-3152
label | Inspection/ Test: Key - R
label | Inspection/ Test: By - NEI-PE, QM
checkpoint | 3.3 - Completions – Building Fit Out
label | INSPECTION POINT: QUALITY CONTROL ACTIVITY - ITP Completion and Submission.
label | ACCEPTANCE CRITERIA - Client Sign off.
label | VERIFYING DOCUMENT - Completed ITP, SNPBE1-00-QCL-ITP-3153
label | Inspection/ Test: Key - R
label | Inspection/ Test: By - NEI-PE, QM
checkpoint | 3.4 - Completions – Site Installation and Assembly
label | INSPECTION POINT: QUALITY CONTROL ACTIVITY - ITP Completion and Submission.
label | ACCEPTANCE CRITERIA - Client Sign off.
label | VERIFYING DOCUMENT - Completed ITP, SNPBE1-00-QCL-ITP-3154
label | Inspection/ Test: Key - R
label | Inspection/ Test: By - NEI-PE, QM
section | SECTION 4 – COMMENTS
checkpoint | Client Release Granted:
textbox | Certificate No:
date | Date:
holdpoint | Client Release Granted
checklist | 33kV Control Room ITR Register 0003 - Light and Power | itp |  |  |  |  | 33kV Control Room ITR Register 0003 - Light and Power
section | General Lighting - Internal
checkpoint | 4 x 5ft LED Light Fitting
label | ITR - Ref: PFI-ITR-0103
checkpoint | 2 x 90deg PIR Sensor (internal lighting)
label | ITR - Ref: PFI-ITR-0103
checkpoint | 2 x LED External Bulkhead Light Fitting
label | ITR - Ref: PFI-ITR-0104
section | General Lighting - Emergency Internal
checkpoint | 2 x 5ft LED Emergency Light Fitting
label | ITR - Ref: PFI-ITR-0103
checkpoint | 2 x Illuminated EXIT light fitting with Batt backup
label | ITR - Ref: PFI-ITR-0103
section | General Electrical - GPO
checkpoint | 2 x Double 10A 1ø Switched Socket Outlet
label | ITR - Ref: PFI-ITR-0100
checkpoint | 2 x Double 10A 1ø UPS Protected Red Switched Socket Outlet
label | ITR - Ref: PFI-ITR-0100
checkpoint | 1 x 15A 1ø Weatherproof Exterior Switched Socket Outlet
label | ITR - Ref: PFI-ITR-0100
checkpoint | 1 x 32A 3ø Weatherproof Exterior Switched Socket Outlet
label | ITR - Ref: PFI-ITR-0100
section | General Lighting - Switch
checkpoint | 2 x Two-Way Two-Gang Switch
label | ITR - Ref: PFI-ITR-0103
checkpoint | 1 x Auto-Off-Manual Switch
label | ITR - Ref: PFI-ITR-0103