## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Stage 1 - Progress
| Scope |  |  | Stage 1 - B01
Rows
|  | B01 - Level 2 - Area A | dynamic | Stage 1 - B01 | B01 - Level 2 | Area A
|  | B01 - Level 2 - Area B | dynamic | Stage 1 - B01 | B01 - Level 2 | Area B
|  | B01 - Level 2 - Area C | dynamic | Stage 1 - B01 | B01 - Level 2 | Area C
|  | B01 - Level 2 - Area D | dynamic | Stage 1 - B01 | B01 - Level 2 | Area D
|  | B01 - Level 2 - Area E1 | dynamic | Stage 1 - B01 | B01 - Level 2 | Area E1
|  | B01 - Level 2 - Area F | dynamic | Stage 1 - B01 | B01 - Level 2 | Area F
|  | B01 - Level 1 - Area A | dynamic | Stage 1 - B01 | B01 - Level 1 | Area A
|  | B01 - Level 1 - Area B | dynamic | Stage 1 - B01 | B01 - Level 1 | Area B
|  | B01 - Level 1 - Area C | dynamic | Stage 1 - B01 | B01 - Level 1 | Area C
|  | B01 - Level 1 - Area D | dynamic | Stage 1 - B01 | B01 - Level 1 | Area D
|  | B01 - Level 1 - Area E1 | dynamic | Stage 1 - B01 | B01 - Level 1 | Area E1
|  | B01 - Level 1 - Area F | dynamic | Stage 1 - B01 | B01 - Level 1 | Area F
|  | B01 - Level G - Area A | dynamic | Stage 1 - B01 | B01 - Level G | Area A
|  | B01 - Level G - Area B | dynamic | Stage 1 - B01 | B01 - Level G | Area B
|  | B01 - Level G - Area C | dynamic | Stage 1 - B01 | B01 - Level G | Area C
|  | B01 - Level G - Area D | dynamic | Stage 1 - B01 | B01 - Level G | Area D
|  | B01 - Level G - Area E1 | dynamic | Stage 1 - B01 | B01 - Level G | Area E1
|  | B01 - Level G - Area E2 | dynamic | Stage 1 - B01 | B01 - Level G | Area E2
|  | B01 - Level G - Area F | dynamic | Stage 1 - B01 | B01 - Level G | Area F
|  | B01 - Level B - Area A/B | dynamic | Stage 1 - B01 | B01 - Level B | Area A/B
Columns
|  | Substrate acceptable - free of dust & construction waste |  | Substrate acceptable - free of dust and construction waste
|  | Light grind completed |  | Light grind completed
|  | Specified vapour barrier shield applied |  | Specified vapour barrier shield applied
|  | Apply specified adhesive & lay flooring |  | Apply specified adhesive and lay flooring
|  | Vinyl skirting laps 150mm onto wall lining |  | Vinyl skirting laps 150mm onto the wall lining
|  | Minimum 10mm perimeter gap between flooring & wall |  | Minimum 10mm perimeter gap between flooring and wall
|  | Coving bead & capping installed to vinyl coving |  | Coving bead and capping installed to vinyl coving
|  | Trim bar finish applied to carpet to vinyl transition areas |  | Trim bar finish applied to carpet to vinyl transition areas
|  | Clean finished surface - Completed to spec. |  | Clean finished surface - Completed to specification
|  | Flooring prep/levelling compound completed if required |  | Flooring prep/levelling compound completed if required
|  | Substrate/Underlay installed to meet required spec. |  | Substrate/Underlay installed to meet required specification
|  | Carpet/Rubber Installation work completed - specified level of finish achieved |  | Carpet/Rubber Installation work completed - specified level of finish achieved
|  | Carpet/Rubber protection layer installed |  | Carpet/Rubber protection layer installed
|  | Inspections completed & issued to Foreman |  | Inspections completed and issued to Foreman