## T2W Numbering & Metadata
1. Document Numbering Convention | [10 empty] | 3. Document Numbering Metadata Component
LOT MANAGEMENT SYSTEM | [10 empty] | FOLDER STRUCTURE |  | Folder | Lot Setup
1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 | Project Code | Project Name | Zone | Site Ref | Site Name | Site Ref (Full Name) | Discipline Code | Discipline Description | Doc Type Code | Doc Type Description | Full Name | Created by Org / Sender Org | Org Name | Treatment Description | ACTION
Project Code |  | Site Ref |  | Discipline |  | Doc Type |  | Created by Org |  | Sequential Number (4 digits) | T2W | Tirau to Waiouru | Zone 1 | 101 | Horahora | 101 - Horahora | QC | Quality | CHK | Checklist | CHK - Checklist | DOW | Downer | Foam Bitumen Stabilisation | 28th Aug | Wed | Graeme to send Sudeshan 2 ITPs for set up
[11 empty] | (Default) |  | Zone 2 | 102 | Oak Tree Bends | 102 - Oak Tree Bends |  |  | INS | Instruction | INS - Instruction |  |  | Foam Bitumen Stabilisation Thin Asphaltic Concrete | 30th Aug | Fri | Graeme, Kelvin to send support@conqahq.com
T2W | - | 304 | - | QC | - | ITP | - | DOW | - | 0001 |  |  | Zone 3 | 103 | Tirau | 103 - Tirau |  |  | ITP | Inspection & Test Plan | ITP - Inspection & Test Plan |  |  | Micro Surfacing | 3rd Sep | Tue | Socheata to set up a review seasion at 12:30pm NZ time
[13 empty] | Zone 4 | 201 | Hutton's | 201 - Hutton's |  |  | SNG | Snag List | SNG - Snag List |  |  | Structural Asphalt Concrete Inlay
[13 empty] | Zone 5 | 202 | Putaruru | 202 - Putaruru | [7 empty] | Structural Asphalt Concrete Overlay
[13 empty] | Zone 6 | 301 | Market Street | 301 - Market Street | [7 empty] | Thin Asphaltic Concrete
2. Navigation | [12 empty] | Zone 7 | 302 | Pinedale North | 302 - Pinedale North | [7 empty] | Shoulder Cleaning
[13 empty] | Zone 8 | 303 | Timber Museum | 303 - Timber Museum | [7 empty] | Sub Soil Drainage
1 | [12 empty] | Zone 9 | 304 | Eketone's | 304 - Eketone's | [7 empty] | Dig Outs
Project Code | [13 empty] | 305 | Weigh In Motion Stn | 305 - Weigh In Motion Stn | [7 empty] | Guard Rail Works
[14 empty] | 306 | Puriri | 306 - Puriri | [7 empty] | Kerb and Channel New
T2W | - | [12 empty] | 307 | West Road Passing Lane | 307 - West Road Passing Lane | [7 empty] | Kerb and Channel Renewal
|  | 2 | [11 empty] | 308 | Newell Road | 308 - Newell Road | [7 empty] | Accesses Ways 1No.
|  | Zone | [11 empty] | 309 | Tokora begin of Split Carrage | 309 - Tokora begin of Split Carrage | [7 empty] | Clean Kerb and Channel Cleaning
[14 empty] | 401 | SH32 Approach/Intersection | 401 - SH32 Approach/Intersection | [7 empty] | Culvert Extension
|  | Zone 3 | - | [10 empty] | 402 | Campbell Road | 402 - Campbell Road | [7 empty] | Dishdrain Extension
|  |  |  | 3 | [9 empty] | 403 | Over Bridge | 403 - Over Bridge
|  |  |  | Site Ref | [9 empty] | 404 | Barron Road | 404 - Barron Road
[14 empty] | 405 | Mc Cracken Road | 405 - Mc Cracken Road
|  |  |  | 304 | - | [8 empty] | 501 | Kiwi Road | 501 - Kiwi Road
[6 empty] | 4 | [7 empty] | 503 | Hill Road Passing Lane | 503 - Hill Road Passing Lane
[6 empty] | Doc Type | [7 empty] | 504 | Tram Road | 504 - Tram Road
2024-08-19 | [13 empty] | 505 | McLauchlin's | 505 - McLauchlin's
REV 1 | [5 empty] | ITP | - | [6 empty] | 506 | Oruanui | 506 - Oruanui
[8 empty] | 5 | [5 empty] | 507 | Palmer Mill Road | 507 - Palmer Mill Road
[8 empty] | Sequential Number (4 digits) | [5 empty] | 601 | Centennial Drive | 601 - Centennial Drive
[14 empty] | 701 | Waitahanui | 701 - Waitahanui
[8 empty] | DOW-0001 | [5 empty] | 702 | Earthquake Gully A | 702 - Earthquake Gully A
[14 empty] | 703 | Earthquake Gully B | 703 - Earthquake Gully B
[14 empty] | 704 | Hatepe Hill | 704 - Hatepe Hill
[14 empty] | 705 | Hallets Bay | 705 - Hallets Bay
[14 empty] | 706 | Kiko Road | 706 - Kiko Road
[14 empty] | 707 | Motuoapa | 707 - Motuoapa
[14 empty] | 801 | Red Hut Pools | 801 - Red Hut Pools
[14 empty] | 802 | Pukererata | 802 - Pukererata
[14 empty] | 803 | Mangamate | 803 - Mangamate
[14 empty] | 804 | Oturere | 804 - Oturere
[14 empty] | 805 | Mangatoetoe-nui | 805 - Mangatoetoe-nui
[14 empty] | 901 | Desert Rd AWPT 04/05 | 901 - Desert Rd AWPT 04/05
[14 empty] | 902 | Waiaruhu | 902 - Waiaruhu

## WBS
Site Ref | Programme / Zone | Site Name (To be confrimed by T2W) | Site Name | treat_2024 | sectionName (RS) | locFrom (RP-Start) | locTo (RP-Finish) | Length | lane | info_length | info_noOfLanes | info_laneLength | info_width | info_totalArea | TTM | Wearing Course | Aggregate | reason_2024 | cost est. | Diversion | Alt Div | Drive over comments | Additional Comments | Risk Rating
101 | 1: SH29 to SH05 (Tirau) | Horahora | Horahora | SAC IL | 01N-0594/00.08 | 934 | 1022 | 88 | All | 88 | 2 | 176 | 10 | 880 | Lane CLosure | SMA |  | FL | 250624 | SH29/27 | N/A |  |  | H
102 | 1: SH29 to SH05 (Tirau) | Oak Tree Bends | Oak Tree Bends | SAC OL | 01N-0594/00.08 | 4165 | 4864 | 699 | All | 699 | 2 | 1398 | 10 | 6990 | Road Closure | OGPA |  | PA | 1946715 | SH29/27 | N/A |  | TF: MSI - SAC-OL not appropriate. Should change to FBS_TAC | H
103 | 1: SH29 to SH05 (Tirau) | Tirau | Tirau | SAC IL | 01N-0605 | 788 | 1268 | 480 | All | 480 | 2 | 960 | 10 | 4800 | Road Closure | SMA | HPSV | FL | 1367040 | SH29/28 | LV SH29/LR/SH30 | changed to AC? | Guardrail needs lifting (Bridge issues with height) | H
103 | 1: SH29 to SH05 (Tirau) | Tirau | Oraka Stream Bridge | TAC | 01N-0605 | 1268 | 1298 | 30 | All | 30 | 2 | 60 | 10 | 300 | Road Closure | SMA |  |  | 35460 | SH29/28 | LV SH29/LR/SH28 | AC over Bridge only. Abutments SAC | Guardrail needs lifting (Bridge issues with height) | H
103 | 1: SH29 to SH05 (Tirau) | Tirau | SH 1/5 Int | SAC IL | 01N-0605 | 1298 | 1633 | 335 | All | 335 | 2 | 670 | 10 | 3350 | Road Closure | SMA | HPSV |  | 954080 | SH29/28 | LV SH29/LR/SH28 | Only on Approach | Guardrail needs lifting (Bridge issues with height) | H
201 | 2: SH05 to SH28 | Hutton's | Hutton's | FBS_TAC | 01N-0607 | 1970 | 2501 | 531 | All | 531 | 2 | 1062 | 10 | 5310 | Road Closure | OGPA |  | PA | 1387141.92 | SH5/SH28 | LV SH29/LR/SH28 | Review treatment |  | H
201 | 2: SH05 to SH28 | Hutton's | Hutton's | FBS_TAC | 01N-0607 | 2501 | 2883 | 382 | All | 382 | 2 | 764 | 10 | 3820 | Road Closure | OGPA |  | PA | 997906.24 | SH5/SH28 | LV SH29/LR/SH28 | Review treatment |  | H
201 | 2: SH05 to SH28 | Hutton's | Hutton's | FBS_TAC | 01N-0607 | 2883 | 2985 | 102 | All | 102 | 2 | 204 | 10 | 1020 | Road Closure | OGPA |  | PA | 266456.64 | SH5/SH28 | LV SH29/LR/SH28 | Review treatment |  | H
202 | 2: SH05 to SH28 | Putaruru | Putaruru | FBS_TAC | 01N-0607 | 3520 | 4760 | 1240 | All | 1240 | 3 | 3720 | 13.5 | 16740 | Lane Closure | OGPA |  | RU | 4373023.68 | SH5/SH28 | LV SH29/LR/SH28 |  |  | H
301 | 3: SH28 to SH32 (Tokoroa) | Market Street | Market Street | TAC | 01N-0613 | 1698 | 1839 | 141 | All | 141 | 2 | 282 | 17.95 | 2530.95 | Road Closure | SMA | HPSV | FL | 299158.29 | SH5/SH30 | LV Ara/Lich | changed to AC? |  | H
301 | 3: SH28 to SH32 (Tokoroa) | Market Street | East Street | TAC | 01N-0613 | 1839 | 2040 | 201 | All | 201 | 2 | 402 | 17.26 | 3469.26 | One way Detour | SMA |  | CR | 410066.532 | SH5/SH30 | LV Ara/Lich | changed to AC? |  | H
301 | 3: SH28 to SH32 (Tokoroa) | Market Street | Sholson Street | TAC | 01N-0613 | 2040 | 2390 | 350 | All | 350 | 2 | 700 | 10.56 | 3696 | One way Detour | SMA |  | CR | 436867.2 | SH5/SH30 | LV Ara/Lich | changed to AC? | TF: this last section could be dropped: there's only one 40m x 2m wide SAC_IL required at 2135-2175 | H
302 | 3: SH28 to SH32 (Tokoroa) | Pinedale North | Pinedale North | FBS_TAC | 01N-0613 | 3860 | 3988 | 128 | All | 128 | 2 | 256 | 12.2 | 1561.6 | Road Closure | SMA |  |  | 407939.8912 | SH5/SH30 | LV Ara/Lich | Guarrail constraints | May need to go down and then up | H
302 | 3: SH28 to SH32 (Tokoroa) | Pinedale North | Pinedale North | FBS_TAC | 01N-0613 | 3988 | 4322 | 334 | All | 334 | 2 | 668 | 12.2 | 4074.8 | Road Closure | SMA | HPSV |  | 1064468.1536 | SH5/SH30 | LV Ara/Lich |  |  | H
303 | 3: SH28 to SH32 (Tokoroa) | Timber Museum | Timber Museum | SAC OL | 01N-0613 | 5601 | 6280 | 679 | All | 679 | 2 | 1358 | 10.3 | 6993.7 | Road Closure | SMA |  | CR | 1947745.45 | SH5/SH30 | LV Ara/Lich |  |  | H
304 | 3: SH28 to SH32 (Tokoroa) | Eketone's | Eketone's | SAC OL | 01N-0613 | 10343 | 11017 | 674 | All | 674 | 2 | 1348 | 11 | 7414 | Road Closure | OGPA |  | FL | 2064799 | SH5/SH30 | LV Ara / OT /SH32 |  | TF: This should be FBS due to MSI - could go to Combination Seal | H
304 | 3: SH28 to SH32 (Tokoroa) | Eketone's | Eketone's | SAC OL | 01N-0613 | 11017 | 11270 | 253 | All | 253 | 2 | 506 | 11 | 2783 | Road Closure | OGPA |  | FL | 775065.5 | SH5/SH30 | LV Ara / OT /SH32 |  |  | H
305 | 3: SH28 to SH32 (Tokoroa) | Weigh In Motion Stn | Weigh In Motion Stn | MICRO | 01N-0625 | 3710 | 3842 | 132 | All | 132 | 2 | 264 | 10.6 | 1399.2 | Road Closure | Micro |  | CR | 41976 | SH5/SH30 | LV Ara / OT /SH32 |  |  | H
306 | 3: SH28 to SH32 (Tokoroa) | Puriri | Puriri Road Intersection - Correction | SAC IL | 01N-0625 | 5083 | 5143 | 60 | All | 60 | 3 | 180 | 14.2 | 852 | One Way Closure | SMA |  | CR | 242649.6 | SH5/SH30 | LV Ara / OT /SH32 | Review treatment |  | H
306 | 3: SH28 to SH32 (Tokoroa) | Puriri | Puriri Road Intersection | SAC OL | 01N-0625 | 5143 | 5230 | 87 | All | 87 | 3 | 261 | 14.2 | 1235.4 | One Way Closure | SMA |  | CR | 344058.9 | SH5/SH30 | LV Ara / OT /SH32 | Review treatment |  | H
306 | 3: SH28 to SH32 (Tokoroa) | Puriri | Puriri Passinglane | FBS_TAC | 01N-0625 | 5230 | 5500 | 270 | L1 | 270 | 1 | 270 | 4.73 | 1277.1 | One Way Closure | SMA |  | CR | 333619.3872 | SH5/SH30 | LV Ara / OT /SH32 | Review treatment |  | H
306 | 3: SH28 to SH32 (Tokoroa) | Puriri | Puriri Passinglane | FBS_TAC | 01N-0625 | 5230 | 5500 | 270 | R1 | 270 | 1 | 270 | 4.73 | 1277.1 | One Way Closure | SMA |  | CR | 333619.3872 | SH5/SH30 | LV Ara / OT /SH32 | Review treatment |  | H
306 | 3: SH28 to SH32 (Tokoroa) | Puriri | Puriri Passinglane | FBS_TAC | 01N-0625 | 5230 | 5500 | 270 | R2 | 270 | 1 | 270 | 4.73 | 1277.1 | One Way Closure | SMA |  | CR | 333619.3872 | SH5/SH30 | LV Ara / OT /SH32 | Review treatment |  | H
306 | 3: SH28 to SH32 (Tokoroa) | Puriri | Puriri Passinglane | FBS_TAC | 01N-0625 | 5500 | 6244 | 744 | L1 | 744 | 1 | 744 | 4.73 | 3519.12 | One Way Closure | SMA |  | CR | 919306.7558 | SH5/SH30 | LV Ara / OT /SH32 | Review treatment |  | H
306 | 3: SH28 to SH32 (Tokoroa) | Puriri | Puriri Passinglane | FBS_TAC | 01N-0625 | 5500 | 6244 | 744 | R1 | 744 | 1 | 744 | 4.73 | 3519.12 | One Way Closure | SMA |  | CR | 919306.7558 | SH5/SH30 | LV Ara / OT /SH32 | Review treatment |  | H
306 | 3: SH28 to SH32 (Tokoroa) | Puriri | Puriri Passinglane | FBS_TAC | 01N-0625 | 5500 | 6244 | 744 | R2 | 744 | 1 | 744 | 4.73 | 3519.12 | One Way Closure | SMA |  | CR | 919306.7558 | SH5/SH30 | LV Ara / OT /SH32 | Review treatment |  | H
307 | 3: SH28 to SH32 (Tokoroa) | West Road Passing Lane | West Road Passing Lane | FBS_TAC | 01N-0625 | 6244 | 6563 | 319 | All | 319 | 3 | 957 | 13.8 | 4402.2 | One Way Closure | SMA |  | CR | 1149995.5104 | SH5/SH30 | LV Ara / OT /SH32 | Review treatment |  | H
307 | 3: SH28 to SH32 (Tokoroa) | West Road Passing Lane | West Road Passing Lane | FBS_TAC | 01N-0625 | 6563 | 6670 | 107 | All | 107 | 3 | 321 | 13.8 | 1476.6 | One Way Closure | SMA |  | CR | 385735.1712 | SH5/SH30 | LV Ara / OT /SH32 | Review treatment |  | H
307 | 3: SH28 to SH32 (Tokoroa) | West Road Passing Lane | West Road Passing Lane | FBS_TAC | 01N-0625 | 6670 | 6840 | 170 | All | 170 | 3 | 510 | 13.8 | 2346 | One Way Closure | SMA |  | CR | 612850.272 | SH5/SH30 | LV Ara / OT /SH32 | Review treatment |  | H
307 | 3: SH28 to SH32 (Tokoroa) | West Road Passing Lane | West Road Passing Lane | FBS_TAC | 01N-0625 | 6840 | 7150 | 310 | All | 310 | 2 | 620 | 11.25 | 3487.5 | One Way Closure | SMA |  | CR | 911046.6 | SH5/SH30 | LV Ara / OT /SH32 | Review treatment |  | H
308 | 3: SH28 to SH32 (Tokoroa) | Newel Road | Newell Road | SAC IL | 01N-0625 | 9778 | 10400 | 622 | All | 622 | 2 | 1244 | 12.47 | 7756.34 | One Way Closure | SMA |  | FL | 2209005.632 | SH5/SH30 | LV Ara / OT /SH32 |  |  | H
309 | 3: SH28 to SH32 (Tokoroa) | Tokoroa begin Split Carrage | Tokora begin of Split Carrage | SAC IL | 01N-0625 | 11083 | 11161 | 78 | All | 78 | 2 | 156 | 10.1 | 787.8 | One Way Closure | SMA |  | CR | 224365.44 | SH5/SH30 | LV Ara / OT /SH32 |  |  | H
401 | 4: SH32 to SH30 (Rotorua) | SH32 Approach/Intersection | SH32 Approach | SAC IL | 01N-0625/12.01 | 12526 | 12603 | 77 | All | 77 | 2 | 154 | 15.1 | 1162.7 | One Way Closure | SMA |  | CR | 331136.96 | SH5/SH30 | LV SH32 / Poihipi |  |  | H
401 | 4: SH32 to SH30 (Rotorua) | SH32 Approach/Intersection | SH32 Intersection | SAC IL | 01N-0638 | 0 | 48 | 48 | All | 48 | 2 | 96 | 12.2 | 585.6 | One Way Closure | SMA |  | CR | 166778.88 | SH5/SH30 | LV SH32 / Poihipi |  |  | H
402 | 4: SH32 to SH30 (Rotorua) | Campbell Road | Campbell Road | FBS_TAC | 01N-0638 | 2020 | 2120 | 100 | All | 100 | 2 | 200 | 10.58 | 1058 | One Way Closure | SMA |  | CR | 276383.456 | SH5/SH30 | LV SH32 / Poihipi |  |  | H
402 | 4: SH32 to SH30 (Rotorua) | Campbell Road | Campbell Road | FBS_TAC | 01N-0638 | 2120 | 3280 | 1160 | All | 1160 | 2 | 2320 | 10.8 | 12528 | One Way Closure | OGPA |  | FL | 3272714.496 | SH5/SH30 | LV SH32 / Poihipi |  |  | H
402 | 4: SH32 to SH30 (Rotorua) | Campbell Road | Nursery Road | FBS_TAC | 01N-0638 | 3280 | 3400 | 120 | All | 120 | 2 | 240 | 10.8 | 1296 | One Way Closure | OGPA |  | FL | 338556.672 | SH5/SH30 | LV SH32 / Poihipi |  |  | H
402 | 4: SH32 to SH30 (Rotorua) | Campbell Road |  | FBS_TAC | 01N-0638 | 3400 | 3890 | 490 | All | 490 | 2 | 980 | 10.8 | 5292 | One Way Closure | OGPA |  | FL | 1382439.744 | SH5/SH30 | LV SH32 / Poihipi |  |  | H
403 | 4: SH32 to SH30 (Rotorua) | Overbridge | Over Bridge | FBS_TAC | 01N-0638 | 4414 | 4620 | 206 | All | 206 | 2 | 412 | 10.8 | 2224.8 | One Way Closure | OGPA |  | FL | 581188.9536 | SH5/SH30 | LV SH32 / Poihipi |  |  | H
403 | 4: SH32 to SH30 (Rotorua) | Overbridge | Nursery Road | FBS_TAC | 01N-0638 | 4620 | 5000 | 380 | All | 380 | 2 | 760 | 10.8 | 4104 | One Way Closure | OGPA |  | FL | 1072096.128 | SH5/SH30 | LV SH32 / Poihipi |  |  | H
403 | 4: SH32 to SH30 (Rotorua) | Overbridge | Nursery Road | FBS_TAC | 01N-0638 | 5000 | 6119 | 1119 | All | 1119 | 2 | 2238 | 10.8 | 12085.2 | One Way Closure | OGPA |  | PA | 3157040.9664 | SH5/SH30 | LV SH32 / Poihipi | SMAfor last 200m | Guardrail needs lifting | H
404 | 4: SH32 to SH30 (Rotorua) | Barron Road | Barron Road | FBS_TAC | 01N-0638 | 9000 | 9360 | 360 | All | 360 | 2 | 720 | 11.3 | 4068 | Road Closure | SMA |  | CR/FL | 1062691.776 | SH5/SH30 | LV SH32 / Poihipi |  | Guardrail needs lifting | H
404 | 4: SH32 to SH30 (Rotorua) | Barron Road | Rollor Coaster | FBS_TAC | 01N-0638 | 9360 | 10100 | 740 | All | 740 | 2 | 1480 | 11.3 | 8362 | Road Closure | SMA |  | CR/FL | 2184421.984 | SH5/SH30 | LV SH32 / Poihipi | Review treatment |  | H
404 | 4: SH32 to SH30 (Rotorua) | Barron Road | Rollor Coaster | FBS_TAC | 01N-0638 | 10100 | 11094 | 994 | All | 994 | 2 | 1988 | 11.3 | 11232.2 | Road Closure | SMA |  | CR/FL | 2934210.0704 | SH5/SH30 | LV SH32 / Poihipi | Review treatment |  | H
404 | 4: SH32 to SH30 (Rotorua) | Barron Road | Maunga-iti Hill | FBS_TAC | 01N-0638 | 11094 | 11840 | 746 | All | 746 | 2 | 1492 | 11.3 | 8429.8 | Road Closure | OGPA |  | CR/FL | 2202133.5136 | SH5/SH30 | LV SH32 / Poihipi | Review treatment | WSP 20%PDR - Sec. 67 & 68: 0638-11.58-17.10 | H
405 | 4: SH32 to SH30 (Rotorua) | Mc Cracken Road | Mc Cracken Road | FBS_TAC | 01N-0638 | 16646 | 16980 | 334 | All | 334 | 2 | 668 | 10.9 | 3640.6 | Road Closure | SMA |  | FL | 951041.2192 | SH5/SH30 | LV SH32 / Poihipi |  | WSP 20%PDR - Sec. 67 & 68: 0638-11.58-17.10 | H
405 | 4: SH32 to SH30 (Rotorua) | Mc Cracken Road |  | FBS_TAC | 01N-0638 | 16980 | 17250 | 270 | All | 270 | 2 | 540 | 10.9 | 2943 | Road Closure | OGPA |  | FL | 768805.776 | SH5/SH30 | LV SH32 / Poihipi |  | WSP 20%PDR - Sec. 67 & 68: 0638-11.58-17.10 | H
405 | 4: SH32 to SH30 (Rotorua) | Mc Cracken Road | Mc Cracken Road | FBS_TAC | 01N-0638 | 17250 | 17565 | 315 | All | 315 | 2 | 630 | 10.9 | 3433.5 | Road Closure | OGPA |  | FL | 896940.072 | SH5/SH30 | LV SH32 / Poihipi | Review treatment |  | H
405 | 4: SH32 to SH30 (Rotorua) | Mc Cracken Road | Wallace Road | FBS_TAC | 01N-0638 | 17565 | 18810 | 1245 | All | 1245 | 2 | 2490 | 10.9 | 13570.5 | Road Closure | OGPA |  | FL | 3545048.856 | SH5/SH30 | LV SH32 / Poihipi | Review treatment |  | H
405 | 4: SH32 to SH30 (Rotorua) | Mc Cracken Road | Wallace Road | FBS_TAC | 01N-0638 | 18810 | 18920 | 110 | All | 110 | 2 | 220 | 10.9 | 1199 | Road Closure | OGPA |  | FL | 313217.168 | SH5/SH30 | LV SH32 / Poihipi | Review treatment |  | H
501 | 5: SH30 (Rotorua) to SH5 (Wairakei) | Kiwi Road | Kiwi Road | SAC IL | 01N-0657-C030 | 1570 | 1650 | 80 | All | 80 | 2 | 160 | 11 | 880 | Road Closure | SMA |  | CR | 250624 | SH32/SH30 | N/A | Review treatment |  | H
501 | 5: SH30 (Rotorua) to SH5 (Wairakei) | Kiwi Road | Kiwi Road | SAC IL | 01N-0657-C030 | 1650 | 1705 | 55 | All | 55 | 2 | 110 | 11 | 605 | Road Closure | SMA |  | CR | 172304 | SH32/SH30 | N/A | Review treatment |  | H
501 | 5: SH30 (Rotorua) to SH5 (Wairakei) | Kiwi Road | Mangaharakeke | SAC IL | 01N-0657-C030 | 1705 | 1713 | 8 | All | 8 | 2 | 16 | 11 | 88 | Road Closure | SMA |  | CR | 25062.4 | SH32/SH30 | N/A | Review treatment |  | H
503 | 5: SH30 (Rotorua) to SH5 (Wairakei) | Hill Road | Hill Road Passing Lane | SAC IL | 01N-0664 | 10022 | 10600 | 578 | All | 578 | 3 | 1734 | 13.08 | 7560.24 | Road Closure | SMA |  | FL | 2153156.352 | SH30/32/Poi | HPMV SH30/SH5 | Review treatment |  | H
503 | 5: SH30 (Rotorua) to SH5 (Wairakei) | Hill Road | Hill Road Passing Lane | SAC IL | 01N-0664 | 10600 | 10724 | 124 | All | 124 | 2 | 248 | 12.4 | 1537.6 | Road Closure | SMA |  | FL | 437908.48 | SH30/32/Poi | HPMV SH30/SH5 | Review treatment |  | H
503 | 5: SH30 (Rotorua) to SH5 (Wairakei) | Hill Road | Maroa Road | SAC IL | 01N-0664 | 10724 | 10980 | 256 | All | 256 | 2 | 512 | 12.4 | 3174.4 | Road Closure | SMA |  | FL | 904069.12 | SH30/32/Poi | HPMV SH30/SH5 | Review treatment |  | H
504 | 5: SH30 (Rotorua) to SH5 (Wairakei) | Tram Road | Tram Road | SAC IL | 01N-0664 | 15226 | 15326 | 100 | All | 100 | 2 | 200 | 11.6 | 1160 | Road Closure | SMA |  | CR | 330368 | SH30/32/Poi | HPMV SH30/SH5 |  |  | H
505 | 5: SH30 (Rotorua) to SH5 (Wairakei) | McLauchlin's | McLauchlin's | FBS_TAC | 01N-0664 | 16042 | 16694 | 652 | All | 652 | 2 | 1304 | 11.6 | 7563.2 | One way Detour | SMA |  | CR | 1975749.8624 | SH30/32/Poi | HPMV SH30/SH5 | Review treatment |  | H
505 | 5: SH30 (Rotorua) to SH5 (Wairakei) | McLauchlin's |  | FBS_TAC | 01N-0664 | 16694 | 16972 | 278 | All | 278 | 2 | 556 | 11.6 | 3224.8 | One way Detour | SMA |  | CR | 842420.9536 | SH30/32/Poi | HPMV SH30/SH5 | Review treatment |  | H
506 | 5: SH30 (Rotorua) to SH5 (Wairakei) | Oruanui | Oruanui | FBS_TAC | 01N-0680 | 2455 | 2680 | 225 | All | 225 | 2 | 450 | 10.2 | 2295 | One way Detour | SMA |  | FL | 599527.44 | SH30/32/Poi | HPMV SH30/SH5 | Review treatment |  | H
506 | 5: SH30 (Rotorua) to SH5 (Wairakei) | Oruanui | Oruanui | FBS_TAC | 01N-0680 | 2680 | 3200 | 520 | All | 520 | 2 | 1040 | 10.2 | 5304 | One way Detour | OGPA |  | FL | 1385574.528 | SH30/32/Poi | HPMV SH30/SH5 | Review treatment |  | H
507 | 5: SH30 (Rotorua) to SH5 (Wairakei) | Palmer Mill Road | Palmer Mill Road | FBS_TAC | 01N-0680 | 8000 | 8641 | 641 | All | 641 | 2 | 1282 | 9.6 | 6153.6 | Road Closure | SMA |  | CR | 1607517.2352 | SH30/32/Poi | HPMV SH30/SH5 | Review treatment |  | H
507 | 5: SH30 (Rotorua) to SH5 (Wairakei) | Palmer Mill Road | Palmer Mill Road | FBS_TAC | 01N-0680 | 8641 | 8884 | 243 | All | 243 | 2 | 486 | 9.6 | 2332.8 | Road Closure | SMA |  | CR | 609402.0096 | SH30/32/Poi | HPMV SH30/SH5 | Review treatment |  | H
601 | 6: SH05 (Wairakei) to SH05 (Napier) | Centennial Drive | Centennial Drive | FBS_TAC | 01N-0696-C005 | 2353 | 3061 | 708 | All | 708 | 3 | 2124 | 14.75 | 10443 | Road Closure | SMA |  | CR | 2728045.776 | SH32 thru tr | LV old SH1 |  | Added by TF | H
601 | 6: SH05 (Wairakei) to SH05 (Napier) | Centennial Drive | Centennial Drive | FBS_TAC | 01N-0696-C005 | 3061 | 4898 | 1837 | All | 1837 | 2 | 3674 | 12.5 | 22962.5 | Road Closure | DG/OGPA |  | PA | 5998539.8 | SH32 thru tr | LV old SH1 |  |  | H
701 | 7: SH05 (Napier) to SH41 (Turangi) | Waitahanui | Waitahanui | SAC IL | 01N-0713 | 6616 | 8042 | 1426 | L1 | 1426 | 1 | 1426 | 4.17 | 5946.42 | Road Closure | OGPA |  | CR | 1693540.416 | SH32/SH41 | LV Poi/SH32/SH41 |  |  | H
701 | 7: SH05 (Napier) to SH41 (Turangi) | Waitahanui | Waitahanui | TAC | 01N-0713 | 6616 | 8042 | 1426 | L2 | 1426 | 1 | 1426 | 4.17 | 5946.42 | Road Closure | OGPA |  | CR | 702866.844 | SH32/SH41 | LV Poi/SH32/SH41 |  |  | H
701 | 7: SH05 (Napier) to SH41 (Turangi) | Waitahanui | Waitahanui | SAC IL | 01N-0713 | 6616 | 8042 | 1426 | R1 | 1426 | 1 | 1426 | 4.17 | 5946.42 | Road Closure | OGPA |  | CR | 1693540.416 | SH32/SH41 | LV Poi/SH32/SH41 |  |  | H
702 | 7: SH05 (Napier) to SH41 (Turangi) | Earthquake Gully A | Earthquake Gully A | FBS_TAC | 01N-0713 | 10048 | 10784 | 736 | All | 736 | 2 | 1472 | 10.1 | 7433.6 | Road Closure | DG/OGPA |  | FL | 1941894.1952 | SH32/SH41 | LV Poi/SH32/SH41 |  |  | H
703 | 7: SH05 (Napier) to SH41 (Turangi) | Earthquake Gully B | Earthquake Gully B | FBS_TAC | 01N-0713 | 12960 | 13090 | 130 | All | 130 | 2 | 260 | 10.6 | 1378 | Road Closure | DG/OGPA |  | FL | 359977.696 | SH32/SH41 | LV Poi/SH32/SH41 |  |  | H
703 | 7: SH05 (Napier) to SH41 (Turangi) | Earthquake Gully B | Earthquake Gully B | FBS_TAC | 01N-0713 | 13090 | 13312 | 222 | All | 222 | 2 | 444 | 10.6 | 2353.2 | Road Closure | DG/OGPA |  | FL | 614731.1424 | SH32/SH41 | LV Poi/SH32/SH41 |  |  | H
704 | 7: SH05 (Napier) to SH41 (Turangi) | Hatepe Hill | Hatepe Hill | SAC IL | 01N-0713 | 13658 | 15736 | 2078 | L1 | 2078 | 1 | 2078 | 4.1 | 8519.8 | One Way Detour | OGPA |  | CR | 2426439.04 | SH32/SH41 | LV Poi/SH32/SH41 |  |  | H
704 | 7: SH05 (Napier) to SH41 (Turangi) | Hatepe Hill | Hatepe Hill | TAC | 01N-0713 | 13658 | 15736 | 2078 | R2 | 2078 | 1 | 2078 | 4.1 | 8519.8 | One Way Detour | OGPA |  | CR | 1007040.36 | SH32/SH41 | LV Poi/SH32/SH41 |  |  | H
705 | 7: SH05 (Napier) to SH41 (Turangi) | Hallets Bay | Hallets Bay | FBS_TAC | 01N-0726 | 2949 | 3500 | 551 | All | 551 | 2 | 1102 | 7.7 | 4242.7 | Road Closure | DG/OGPA |  | FL | 1108329.0064 | SH32/SH41 | LV Poi/SH32/SH41 | Review treatment |  | H
706 | 7: SH05 (Napier) to SH41 (Turangi) | Kiko Road | Kiko Road | FBS_TAC | 01N-0726 | 15514 | 15900 | 386 | All | 386 | 2 | 772 | 10.4 | 4014.4 | Road Closure | SMA |  | FL | 1048689.7408 | SH32/SH41 | LV Poi/SH32/SH41 |  |  | H
707 | 7: SH05 (Napier) to SH41 (Turangi) | Motuoapa | Motuoapa | FBS | 01N-0744 | 0 | 990 | 990 | All | 990 | 2 | 1980 | 9.69 | 9593.1 | Road Closure | Chipseal |  | FL | 1848897.3492 | SH32/SH41 | LV Poi/SH32/SH41 |  |  | H
801 | 8: SH41 (Turangi) to Desert Rd Summit | Red Hut Pools | Red Hut Pools | FBS | 01N-0753 | 4712 | 5798 | 1086 | All | 1086 | 2 | 2172 | 10.8 | 11728.8 | Road Closure | Chipseal |  | PA,RU,FL | 2260515.0816 | SH41/47/4/49 | N/A |  |  | H
801 | 8: SH41 (Turangi) to Desert Rd Summit | Red Hut Pools | Poutu | FBS | 01N-0753 | 5880 | 6216 | 336 | All | 336 | 2 | 672 | 10.8 | 3628.8 | Road Closure | Chipseal |  | PA,RU | 699385.8816 | SH41/47/4/49 | N/A | Review treatment |  | H
801 | 8: SH41 (Turangi) to Desert Rd Summit | Red Hut Pools | Poutu South | FBS | 01N-0753 | 6216 | 6521 | 305 | All | 305 | 2 | 610 | 10.8 | 3294 | Road Closure | Chipseal |  | PA,RU | 634859.208 | SH41/47/4/49 | N/A |  |  | H
801 | 8: SH41 (Turangi) to Desert Rd Summit | Red Hut Pools | Tongariro to Rangipo | FBS | 01N-0753 | 6521 | 7721 | 1200 | All | 1200 | 2 | 2400 | 10.8 | 12960 | Road Closure | Chipseal |  | PA,RU | 2497806.72 | SH41/47/4/49 | N/A |  |  | H
801 | 8: SH41 (Turangi) to Desert Rd Summit | Red Hut Pools | Rangipo Prison | FBS | 01N-0753 | 7721 | 8607 | 886 | All | 886 | 2 | 1772 | 10.8 | 9568.8 | Road Closure | Chipseal |  | PA,RU | 1844213.9616 | SH41/47/4/49 | N/A |  |  | H
801 | 8: SH41 (Turangi) to Desert Rd Summit | Red Hut Pools | Rangipo | FBS | 01N-0753 | 8607 | 9478 | 871 | All | 871 | 2 | 1742 | 10.8 | 9406.8 | Road Closure | Chipseal |  | FL | 1812991.3776 | SH41/47/4/49 | N/A |  |  | H
802 | 8: SH41 (Turangi) to Desert Rd Summit | Puketarata | Puketarata Stream 24/25 | SAC IL | 01N-0763 | 3714 | 3764 | 50 | All | 50 | 2 | 100 | 9.5 | 475 | Road Closure | SMA |  |  | 135280 | SH41/47/4/49 | N/A |  |  | H
802 | 8: SH41 (Turangi) to Desert Rd Summit | Puketarata | Puketarata Stream Bridge | TAC | 01N-0763 | 3764 | 3818 | 54 | All | 54 | 2 | 108 | 9.5 | 513 | Road Closure | SMA |  |  | 60636.6 | SH41/47/4/49 | N/A |  |  | H
802 | 8: SH41 (Turangi) to Desert Rd Summit | Puketarata | Puketarata Hill 24/25 | SAC IL | 01N-0763 | 3818 | 3868 | 50 | All | 50 | 2 | 100 | 9.5 | 475 | Road Closure | SMA |  |  | 135280 | SH41/47/4/49 | N/A |  |  | H
802 | 8: SH41 (Turangi) to Desert Rd Summit | Puketarata | Puketarata Hill 24/25 | FBS_TAC | 01N-0763 | 3818 | 4265 | 447 | All | 447 | 2 | 894 | 9.5 | 4246.5 | Road Closure | SMA |  |  | 1109321.688 | SH41/47/4/49 | N/A |  |  | H
803 | 8: SH41 (Turangi) to Desert Rd Summit | Mangamate | Mangamate | SAC IL | 01N-0763 | 9822 | 9933 | 111 | All | 111 | 2 | 222 | 9.6 | 1065.6 | Road Closure | SMA |  | CR | 303482.88 | SH41/47/4/49 | N/A | Review treatment |  | H
803 | 8: SH41 (Turangi) to Desert Rd Summit | Mangamate | Mangatawai | SAC IL | 01N-0763 | 9933 | 10330 | 397 | All | 397 | 2 | 794 | 9.6 | 3811.2 | Road Closure | SMA |  | CR | 1085429.76 | SH41/47/4/49 | N/A | Review treatment |  | H
804 | 8: SH41 (Turangi) to Desert Rd Summit | Oturere | Oturere Hill Nth | SAC IL | 01N-0763 | 13702 | 13962 | 260 | All | 260 | 2 | 520 | 11.5 | 2990 | Road Closure | SMA |  | CR | 851552 | SH41/47/4/49 | N/A | Review treatment |  | H
804 | 8: SH41 (Turangi) to Desert Rd Summit | Oturere | Oturere Hill Nth | SAC IL | 01N-0763 | 13962 | 14528 | 566 | All | 566 | 2 | 1132 | 11.5 | 6509 | Road Closure | SMA |  | CR | 1853763.2 | SH41/47/4/49 | N/A |  |  | H
804 | 8: SH41 (Turangi) to Desert Rd Summit | Oturere | Oturere Hill Nth | SAC IL | 01N-0763 | 14528 | 14700 | 172 | All | 172 | 2 | 344 | 11.5 | 1978 | Road Closure | SMA |  | CR | 563334.4 | SH41/47/4/49 | N/A |  |  | H
804 | 8: SH41 (Turangi) to Desert Rd Summit | Oturere | Oturere Hill Nth | TAC | 01N-0763 | 14700 | 14832 | 132 | All | 132 | 2 | 264 | 11.5 | 1518 | Road Closure | SMA |  | CR | 179427.6 | SH41/47/4/49 | N/A |  |  | H
804 | 8: SH41 (Turangi) to Desert Rd Summit | Oturere | Oturere Stream | SAC IL | 01N-0777 | 0 | 15 | 15 | All | 15 | 2 | 30 | 10.4 | 156 | Road Closure | SMA |  | CR | 44428.8 | SH41/47/4/49 | N/A |  |  | H
804 | 8: SH41 (Turangi) to Desert Rd Summit | Oturere | Oturere Hill Sth | SAC IL | 01N-0777 | 15 | 211 | 196 | All | 196 | 2 | 392 | 10.4 | 2038.4 | Road Closure | SMA |  | CR | 580536.32 | SH41/47/4/49 | N/A |  |  | H
805 | 8: SH41 (Turangi) to Desert Rd Summit | Mangatoetoe-nui | Mangatoetoe-nui | FBS_TAC | 01N-0777 | 5929 | 5979 | 50 | All | 50 | 2 | 100 | 10.9 | 545 | Road Closure | SMA |  | CR | 142371.44 | SH41/47/4/49 | N/A | Review treatment |  | H
805 | 8: SH41 (Turangi) to Desert Rd Summit | Mangatoetoe-nui | Mangatoetoe-nui | TAC | 01N-0777 | 5979 | 6487 | 508 | All | 508 | 2 | 1016 | 10.9 | 5537.2 | Road Closure | SMA |  | CR | 654497.04 | SH41/47/4/49 | N/A | Review treatment |  | H
805 | 8: SH41 (Turangi) to Desert Rd Summit | Mangatoetoe-nui | Mangatoetoe-nui | FBS_TAC | 01N-0777 | 6487 | 8030 | 1543 | All | 1543 | 2 | 3086 | 10.62 | 16386.66 | Road Closure | SMA |  | CR | 4280719.9651 | SH41/47/4/49 | N/A | Review treatment |  | H
901 | 9: Desert Rd Summit to South boundary | Desert Rd AWPT 04/05 | Desert Rd AWPT 04/05 | FBS_TAC | 01N-0794 | 2037 | 2786 | 749 | All | 749 | 2 | 1498 | 10.1 | 7564.9 | Road Closure | SMA |  | FL | 1976193.9568 | SH41/47/4/49 | N/A |  |  | H
902 | 9: Desert Rd Summit to South boundary | Waiaruhu | Waiaruhu | FBS | 01N-0815 | 4800 | 5476 | 676 | All | 676 | 2 | 1352 | 10.4 | 7030.4 | Road Closure | Chipseal |  | PA | 1354983.0528 | FBS | 214 RHAB |  |  | H