## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | QA - Aquafin
section | Details
checkpoint | Ensure all concrete surfaces are cleaned sufficiently for application of Equus Chevacryl Admix primer.
holdpoint | Signed off by Building Contractor
checkpoint | Apply Equus Chevacryl Admix 50/50 primer to concrete substrate.
checkpoint | Apply Equus Epistixx AC primer to all ferrous substrate. Allow to cure.
checkpoint | Apply first coat of Aquafin 2-K/M Plus by brush or trowel at approx. 2kgs per m2
checkpoint | Apply an Equus Schomburg Aquafin 2-K/M Plus reinforcement bandage to nominated areas-penetrations, concrete to termination bar
checkpoint | Apply second coat of Aquafin 2-K/M Plus by brush at approx. 2kgs per m2.
checkpoint | Check for pinholes and touch up as necessary by means of brush.
checkpoint | System to be inspected on completion.
checklist | QA - Colphene BSW
section | Details
checkpoint | Concrete and other site surfaces satisfactory for installation of COLPHENE BSW by Equus Certified Applicator.
checkpoint | Loose-lay COLPHENE BSW H to lift pits. Ensure sheet joints are closed using DUO SELVEDGE lap technology
checkpoint | Ensure all pile caps, beams, piles, and pillar caps are reinforced with a strip of COLPHENE BSW H over SOPRADERE QUICK Primer.
checkpoint | Any details shall be carried out using ALSAN FLASHING with reinforcement fleece a minimum 150mm all direction
checkpoint | HORIZONTAL: Loose lay COLPHENE BSW H
checkpoint | To fit inside the formwork, compacted hardfill covered with sand or site concrete with sanded surface facing upwards.
checkpoint | HORIZONTAL: Sheet joints are closed using DUO SELVEDGE lap with a minimum 100mm ensure all are well sealed. Minimum end laps shall be 150mm
checkpoint | Any details shall be carried out using ALSAN FLASHING with reinforcement fleece a minimum 150mm all direction
checkpoint | VERTICAL PRE-APPLIED against lost formwork: Install drainage layer within mechanical fixings and apply COLPHENE BSW V to the drainage layer. (Where thermal insulation is required, install against lost formwork before drainage layer. Held in place with DOUBLE-STICK tape or EQUUS SOPREMA Fixings.)
checkpoint | VERTICAL PRE-APPLIED against lost formwork: Sheet joints are closed using DUO SEL- VEDGE lap with a minimum 100mm ensure all are well sealed by torch or hot air.
checkpoint | Any details shall be carried out using ALSAN FLASHING with reinforcement fleece a minimum 150mm all direction
checkpoint | Install vertical Equus Thermal Insulation against COLPHENE membrane, held in place by dots of DOUBLESTICK tape.
checkpoint | Install Equus drainage layer against vertical COLPHENE membrane, and secure with Equus Termination Bar and sealant.
checkpoint | VERTICAL POST-APPLIED REFER TO "4131EB 4.4 COLPHENE 3000 METHOD AND STATEMENT"
checkpoint | Installation of Steel work by others.
checkpoint | Areas that have been perforated or damaged to be repaired by heat welding a piece of COLPHENE BSW H including a minimum 150mm overlap.
checkpoint | Concrete pour by others.
checkpoint | Precast panels or blockwork stood by others.
checkpoint | Waterstops placed where required. Cold joins and stitch joins.
checkpoint | Any loose areas on the upper edge of the membrane can be torched into place or sealed with the Equus Termination Bar and bead of ALSAN MASTIC 2200 sealant.
checkpoint | System to be inspected on completion.
holdpoint | Signed off by Building Contractor
checklist | QA - Cophene 3000
section | Details
checkpoint | Concrete and other surfaces satisfactory for installation of COLPHENE 3000 by Equus Certified Applicator.(Note:Any sharpe corner please shamper edge).
checkpoint | All vertical areas such as foundation walls shall be primed with Equus Peel and Stick Primer at a rate of 6 to 8 m2/L and allowed to dry for minimum 1 hour.
checkpoint | Apply COLPHENE 3000 reinforcement strip to in all internal and external corners and connections between floor and wall areas.
checkpoint | Apply COLPHENE 3000 self-adhesive membrane to walls by removing the siliconized film and pressing against the primed surface.
checkpoint | Heat weld all sheet joints by hot air welder if required and ensure all are well sealed.
checkpoint | Including end joints. Ensure a minimum of 75mm overlap at all connections.
checkpoint | (where required) Install vertical Equus Thermal Insulation against COLPHENE 3000 membrane, held in place by dots of DOUBLE-STICK tape.
checkpoint | (where requierd) Asian Flashing with reinforcement fleece a minimum 150mm all direction
checkpoint | Inspection of all areas before Equus drainage layer installation.
checkpoint | Areas that have been perforated or damaged to be repaired by self-adhering a piece of COLPHENE 3000 including a minimum 150mm overlap.
checkpoint | Waterstops placed where required. Cold joins and stitch joins.
checkpoint | Install Equus drainage layer against COLPHENE 3000, and secure with Equus Termination Bar and nominated sealant or Aquafin 2KM. (For Aquafin application refer to "Aquafin 2-K/M Checklist and Method Statement ")
checkpoint | Final Inspection required prior to back filling.
holdpoint | Signed off by Building Contractor