## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Hychem E 100 Primer + Supafloor TX
section | Details
checkpoint | Relevant Australian Standards Checked
label | Specification / Standard: AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | Attach Photo
checkpoint | Moisture Content Test
label | Attach Photo
checkpoint | Cutting - Make sure that adjoining ends of intersecting waterstop segments are cut extremely straight
label | Attach Photo
checkpoint | Apply primer using a brush or roller (Apply Hychem E 100 Primer (where necessary) using a medium nap roller at a coverage rate of 4-6 sqm per litre depending on the coarseness of the surface. Allow to become tack free before applying HYCHEM Supafloor TX.)
label | Attach Photo
checkpoint | Epoxy Application (1st coat) - Apply first coat of Hychem Supafloor TX using a medium nap roller at a coverage rate of 4 to 6 sqm. Allow to cure to a tack free finish.
label | Non-Slip Finish: If aggregate is required, Broadcast grit aggregate (size to suit anti-slip requirement) into the first coat while it is still wet and allow to cure overnight.
label | ○ Sweep off loose quartz aggregate.
checkpoint | Epoxy Application (2nd Coat) - Apply second coat of Hychem Supafloor TX at a coverage rate of approximately 4-6 sqm per litre. Allow to cure for a minimum of 24 hours before subjecting to traffic and 3 days before normal use.
checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF