## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | FHC-ITP-013 - General Concrete Paving | itp |  |  |  |  | FHC-ITP-013 - General Concrete Paving
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.3 Submission & Approval of Concrete Mix Design
note | FREQUENCY: Prior to first concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 610.07(b)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed, Mix design approval
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Superintendent
note | – – – – – – – – –
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 Setting Out
note | FREQUENCY: Prior to start
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.17
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/Superintendent
note | – – – – – – – – –
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Excavation Permit
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Excavation permit
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.3 Excavation
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Excavation completed to required depth to allow placement of the bedding layer
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.2
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.4 Bedding
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All bedding material used shall be as follows:
note | – 100mm thick layer of 20mm Class 3 crushed rock bedding for median infill
note | – 150mm thick layer of 20mm Class 4 crushed rock bedding for footpath/pram crossing
note | – Bedding trimmed, moistened, and compacted as per Section 304
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.21 Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.5 Formwork
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.12 AS 3610
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.6 Reinforcement
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Reinforment used shall consist of SL82 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings).
note | • Reinforcement must comply with the requirements of AS/NZS 4671.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.13
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.7 Concrete Placement
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Concrete shall be thoroughly compaction via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
note | • Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.05(a) 703.08
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.8 Surface Finish
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces in accordance with AS 3610.
note | • Footpaths and other Surfacing shall be compelted with a wooden float.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.25
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.9 Pram Crossings
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that pram crossings are constructed in accordance with requirements for access and mobility.
note | – For pram crossings within concrete kerb refer to Figure 24A of AS 1428.1
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Figure 24A AS1428.1 Design Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.10 Joints
note | FREQUENCY: Each Joint
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Expansion joints shall be installated at 10m regular intervals using 15mm wide cork or bituminous imtergrate particle board.
note | • Control joints at 2.5m regular intervals, 25% of pavement depth and 5mm wide
note | • Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.26
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.11 Protection of concrete
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
note | • Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.27
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.12 Curing
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Concrete shall be cured immediately either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
note | • Curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.1
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.13 Ambient Weather
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Concreting operations shall comply with the requirements of clauses 610.17(a), 610.17(b), 610.17(c) and 610.17(d) for limits, restrictions and treatments to be applied for concreting in hot, cold and wet weather, except that curing shall be in accordance with clause 703.10.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 610.17(a), 610.17(b), 610.17(c) 610.17(d) 703.09
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/Site Foreman
note | – – – – – – – – –
textbox | DATE:
section | 3 - Completion
checkpoint | 3.1 Carry out sampling of concrete - strength and consistency
note | FREQUENCY: Each 50m3
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
note | • The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and Clause 5.2 of AS 1379
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.11
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Checklist
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed/Test Records
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.2 Tolerances
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
note | Section dimensions shall be constructed within the following tolerances:
note | – 5mm and 15mm for width; or
note | – ±3mm for dimensions less than 25mm.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.15 Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.3 Backfilling
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: After curing, no earlier than 3 days, backfilling shall be completed as per the below:
note | – Topsoil compacted in layers < 150mm
note | – Width ≥ 300mm behind edging to top of edging
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.29
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: