## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-000
[11 empty] | Revision : 0 | 2023-07-20
Client: |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  |  | Contract Hold Points - Pre Construction |  | Name: | Jake Cardillo | Name: | Aaron Hatch |  | Name: | Shaun Kent
Contract No: |  |  |  | Specifications: As outlined
|  |  |  | Structure / Component: Tram Track Renewal |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : 20/07/23 |  | Date : 20/07/23 |  |  | Date : 20/07/23
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Pre - Construction Works
1.1 | Asphalt - submission of asphalt mix design |  | Prior to commencing asphalt | Ensure the mix design/s have been registered and are approved by Superintendent prior to laying mix. | VicRoads Spec. Cl.407.09. RAP DoT letter from production plant | Correspondence of receipt of mix design from the RAP DoT Letter. | Superintendent approval via hold point release | HP | Site Engineer/ Asphalt Supervisor / Superintendent
1.2 | Concrete - submission & approval of concrete mix design prior to commencement of project |  | Prior to first concrete pour | Concrete mix design submitted and approved at least 2 weeks prior to first pour. Mix shall contain minimum 460 kg/m3 cement content. Special 50 mPa mix is to be VS502B25MET1 with a suitably flowable design slump agreed prior to construction. | CE-019-ST-0033 VicRoads Spec. Cl. 503.04 | Correspondence of receipt of mix design from supplier | Superintendent approval via hold point release | HP | FH Engineer / Superintendent |  |  | N/A
1.3 | Welders qualifications, competencies & work methodology |  | Prior to commencing works | Weld methodology to be submitted prior to commencement of works. Welders shall be trained and compliant in Australian aluminothermic welding competencies as outlined below; - TLIW2012 Grind Rails - TLIW3015 Weld Rails using Aluminothermic welding process - TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry | CE-019-ST-0033 Appendix C | Welding methodology | Superintendent approval via hold point release | HP | FH Engineer / Superintendent
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent