## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-049-CPD-RAIL-Calder Park-OHLE Wire Regrading | itp |  |  |  | Yes | ITP-049-CPD-RAIL-Calder Park-OHLE Wire Regrading - Rev 1
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: OHLE-ITP-MRPA-Calder Park-OHLE Wire Regrading
label | ITP Description: OHLE
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): OHLE
label | Revision Number: 1
label | Revision Date: 24/07/2023
label | ITP created by: Kevin Liang
checkpoint | 1.1 - Overhead Line Electrification
label | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
checkpoint | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | Reference - VRIOGS 001 AS 4100
checkpoint | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
label | Reference - L1-CHE-STD-015(1) MEST 000002-06(1)
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Procurement Materials delivered/collected to stores/Site.
label | Reference - Contractor - Site Material Control procedure.
label | • Cat5 Material received -Calder Park Tracking sheet
label | Acceptance Criteria - Ensure materials are delivered/collected as required.
label | • Certificates of Conformity provided by MRPA
label | Method - Document Review
label | Frequency - Once for each supplier, prior to works start
label | Category - IP
label | Responsibility - MRPA Issue, CAT5 Receive
label | Responsible person - MRPA
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Produce Work Package Plan
label | Reference - Work Package Plan
label | Acceptance Criteria - Submission of Work Package Plan and MRPA approval and acceptance. Ensure work is carried out in a safe manner.
label | Method - Document Review
label | Frequency - Prior to Works Start
label | • TBC in accordance with MTM Standards
label | Category - HP
label | Responsibility - MRPA/CAT5
label | Responsible person - MRPA/CAT5 Engineer
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction Activities
checkpoint | 4.1 - Approval of IFC drawings
label | Reference - Contractor Design Management procedure. MRP-DPK-060-00-ETN
label | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
label | Method - Document/Drawings Review
label | Frequency - Prior to Works and at regular intervals.
label | • TBC in accordance with MTM Standards
label | Category - HP
label | Responsibility - MRPA/CAT5
label | Responsible person - MRPA/CAT5 Engineer
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Task Specific Permits
label | Reference - Working at height permit. OHLE SWMS
label | Acceptance Criteria - Ensure all task and activities have relevant permits issued and received.
label | • Task Permits to be generated and signed off by appointed person.
label | • Task specific documents - MTM to issue permit to enter/Isolation permits etc.
label | Method - Visual, Document Review
label | Frequency - Each Task prior to works start.
label | • TBC in accordance with MTM Standards
label | Category - IP
label | Responsibility - CAT5/MRPA
label | Responsible person - MRPA/CAT5 Engineer
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
checkpoint | 4.3 - Cantilever assembled.
label | Reference - Cantilever assembled as per IFC design.
label | Acceptance Criteria - Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
label | Method - Visual, Document Review
label | Frequency - Each Task prior to works start.
label | • TBC in accordance with MTM Standards
label | Category - IP
label | Responsibility - CAT5/MRPA
label | Responsible person - MRPA/CAT5 Engineer
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
checkpoint | 4.4 - Pre-Installation check
label | Reference - IFC wiring layouts, IFC cross sections and BOQ.
label | • Engineering Drawings Management Policy (IFC/As-built) L1-CHE-MAN-001
label | Acceptance Criteria - Ensure that locations matches most relevant IFC drawings
label | Method - Visual, Document Review
label | Frequency - Each Task prior to works start.
label | • TBC in accordance with MTM Standards
label | Category - IP
label | Responsibility - CAT5/MRPA
label | Responsible person - MRPA/CAT5 Engineer
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
section | 5. Construction Activities
checkpoint | 5.1 - Cantilever installed.
label | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
label | Acceptance Criteria - Work instructions in accordance to IFC design
label | Method - Measure, Visual
label | Frequency - Each OHLE Structure
label | Category - IP
label | Responsibility - CAT5/MRPA
label | Responsible person - MRPA/CAT5 Engineer
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
checkpoint | 5.2 - Install SPS to correct height / position relative to track
label | Reference - Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | Acceptance Criteria - Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
label | Method - Measure, Visual
label | Frequency - Each OHLE Structure
label | Category - IP
label | Responsibility - CAT5/MRPA
label | Responsible person - MRPA/CAT5 Engineer
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
checkpoint | 5.3 - Cantilever checked once installed.
label | Reference - Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet.CAT5/OHLE/CHK002
label | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
label | Method - Measure, Visual
label | Frequency - Each OHLE Structure
label | Category - IP
label | Responsibility - CAT5/MRPA
label | Responsible person - MRPA/CAT5 Engineer
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
checkpoint | 5.4 - Installation of wire supports at the correct height and stagger.
label | Reference - Install as per design drawings.
label | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | Method - Visual
label | Frequency - Each OHLE BWA structure
label | Category - IP
label | Responsibility - CAT5/MRPA
label | Responsible person - MRPA/CAT5 Engineer
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
checkpoint | 5.5 - Installation of small parts
label | Reference - Install as per design, use span/ambient temp. tension charts.
label | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
label | Method - Measure, Visual
label | Frequency - Prior termination
label | Category - IP
label | Responsibility - CAT5/MRPA
label | Responsible person - MRPA/CAT5 Engineer
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
checkpoint | 5.6 - Complete Clearance Checks
label | Reference - Install as per design, use span/ambient temp. tension charts.
label | Acceptance Criteria - Visual inspection for clearance and wire staging from Hirail EWP
label | Method - Measure, Visual
label | Frequency - Prior termination
label | Category - IP
label | Responsibility - CAT5/MRPA
label | Responsible person - MRPA/CAT5 Engineer
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
checkpoint | 5.7 - Complete Pan Run Test
label | Reference - Install as per design, use span/ambient temp. tension charts.
label | Acceptance Criteria - Check for wire take up, clearance, stagger limits and pantograph interaction to the contact wire
label | Method - Measure, Visual
label | Frequency - Prior termination
label | Category - IP
label | Responsibility - CAT5/MRPA
label | Responsible person - MRPA/CAT5 Engineer
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
section | 6. Post-construction Activities
checkpoint | 6.1 - Defects/Temporary Works
label | Reference - IFC wiring layouts, cross sections and design drawings.
label | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
label | • Defect list to be provided at the end of Occo identifying planned work to rectify
label | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
label | Method - Document Review, Visual
label | Frequency - Each OHLE Structure
label | Category - IP
label | Responsibility - CAT5/MRPA
label | Responsible person - MRPA/CAT5 Engineer
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
checkpoint | 6.2 - Relevant documentation readily available. (As-built Survey)
label | Reference - As built drawings and check sheets to accordance to MTM Design spec.
label | Acceptance Criteria - Ensure delivery of relevant documentation to client.
label | • As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
label | Method - Document Review, Visual
label | Frequency - Each OHLE Structure
label | Category - IP
label | Responsibility - CAT5/MRPA
label | Responsible person - MRPA/CAT5 Engineer
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | Reference - MTM Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP
label | Responsibility - CAT5/MRPA
label | Responsible person - MRPA/CAT5 Engineer
label | Verifying Documents - This ITP Signed Off
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP