## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Concrete Pre-Pour QA |  |  |  |  | Yes | Concrete Pre-Pour QA Checklist | 07c91d3a-6830-4c1d-8fa4-c0e15e9bcdfc
checkpoint-status |  |  | checkpoint | Design items
button | 0750fbdf-00ea-5563-9cea-a7d28184b06d |  | button | Correct concrete MPA and mix design ordered | OK,NOK
button | 6e40f362-1966-5dfc-82f3-66e9704586b1 |  | button | Concrete tester organised and testing as required | OK,NOK
button | 97d7d47a-972c-5354-8107-74898ffd9d80 |  | button | Correct slump for project ordered | OK,NOK
button | 6189717c-729d-5dff-8bc1-5ee5003fc2ea |  | button | Max slump 80 or less if specified. | OK,NOK
button | 0f478721-31f1-5cc2-93e2-870dda0f95c2 |  | button | Correct finish type, please note: | OK,NOK
checkpoint-status |  |  | checkpoint | Pre pour items
label | 783887e0-8e2e-5c5a-b79a-daabf462d07b |  | note | Confirmed area to be poured including:
button | cfd93bee-c3f4-5c62-8fa2-6f67891a39f6 |  | button | Levels | OK,NOK
button | 3e65cf8a-40bf-5abf-80d9-9e5f76823ecc |  | button | Step downs | OK,NOK
button | ef79f8a7-e6ea-5e3d-a9c8-aa4ecaeeca54 |  | button | Items to be stripped during the pour | OK,NOK
button | cb0810c8-6879-59db-9ce7-067b0f779d4e |  | button | Finishes | OK,NOK
button | 0560d9ab-57b8-58f3-a0b1-79e898e68b74 |  | button | Extent | OK,NOK
label | 0c5b234c-74b6-5241-b8cd-1874e6629852 |  | note | Checked reinforcing for the following:
button | 2f6a203b-7594-55c7-8111-818a7ccb0827 |  | button | Cover | OK,NOK
button | 026c9d39-4ccb-5576-935e-7d78dbfe64b2 |  | button | Reinforcing installed vs. drawings | OK,NOK
button | f1c2b35f-3540-5b3e-9533-b7d724e39b7d |  | button | Bar chairs adequate | OK,NOK
button | f7e2493d-1e83-54bc-b945-691e63bbf2d8 |  | button | DJC, SCJ, CJ, and all other joints confirmed | OK,NOK
button | eb62bfc5-f207-5115-9926-e1b167f90999 |  | button | Correct curing organised | OK,NOK
button | 28e6eb9d-da78-538d-8c02-2ca79aabfb4a |  | button | Saw cutting | OK,NOK
holdpoint |  |  | signoff | Hold point do not proceed without an inspection
checkpoint-status |  |  | checkpoint | Post pour items
button | d565d881-8829-57bd-8d55-ab37d2af4831 |  | button | Adequate founding depth achieved | OK,NOK
button | 2c9a1271-3bf1-5219-af3a-c479b55a44b5 |  | button | Strip formwork | OK,NOK
button | 1576adb7-2e93-5f7a-9b80-7e098a55e39d |  | button | Concrete curing | OK,NOK
button | 892f8fc3-c596-52a9-a87b-815f30b4fbbd |  | button | Levels checked | OK,NOK
checkpoint-no-status |  |  | checkpoint | Additional comments:
text | ef2c7c44-07a4-5f3e-8c02-ba9318963451 |  | textbox | Pre-pour checklist completed by:
holdpoint |  |  | signoff | Signature
checklist-sectioned |  |  | checklist | CC0394 - ITP-012 - Asphalt | itp |  |  |  | Yes | CC0394 - ITP-012 - Asphalt REV0 | 1d018ecb-d150-4f4c-8e86-d9d2629449a8
checkpoint-group |  |  | section | Lot Conformance.
checkpoint-status |  |  | checkpoint | Works complete
text | fc2830e2-42b9-5fed-8434-67d4159e6f73 |  | textbox | Name:
text | 70386a82-b780-5d63-8971-f467458e0d53 |  | textbox | Position:
text | 46986412-496e-5fcd-bc58-21f9624152e0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | 6c3f054a-e380-504a-9aa3-06fb8ea0b43e |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | 5cb1b97b-9b5e-5978-9117-60d16cc1234b |  | textbox | Lot opened date:
text | e72c71e9-3c86-56bf-889d-1029f788f3f7 |  | textbox | Lot opened by:
text | 29085b28-03a3-5137-8959-17b154d34f40 |  | textbox | Date lot closed:
button | c6737d90-a8be-56a9-9a5b-a7b4a402b08b |  | button | NCR raised? | Yes, No
text | 06817190-615a-5e74-bc38-c9641cafb9ee |  | textbox | NCR Raised Date:
button | 9ded895a-2672-52c0-846e-f656c345573a |  | button | NCR closed? | Yes, No
text | 960d2892-541c-5abd-bacd-005f6850951c |  | textbox | NCR Closed Date:
text | c61dd5e9-b935-5be9-9121-a30f7a54a499 |  | textbox | NCR Number:
text | bf285431-2f24-5db5-aec3-5c1e637869f7 |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP
checkpoint-group |  |  | section | 1.0
checkpoint-status |  |  | checkpoint | 1.1 - Determine Lot Size
label | 7daf3d14-9c1c-57a5-bb6b-f9e6a85553d6 |  | note | Ref docs - IFC Drawings
label | 90044c78-06e5-52c9-826d-77918909e912 |  | note | Acceptance criteria - Maximum Lot Size = 4000m2
button | e870877b-3d6c-589e-ba05-d466e1820165 |  | button | Acceptance | Yes,No,N/A
label | 03a2210f-1224-5079-892f-a48ae2e1dc20 |  | note | • See Work Lot Map
label | 15bed521-bf5c-5a6f-b6bc-4679facbdfbb |  | note | Resp - SE
label | 8c82a2f1-7b90-57c8-9ae0-eed5a4bb0b58 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 39c1b022-6416-5ac1-88b4-46a896283d8f |  | tickbox | Work Lot Map
checkpoint-status |  |  | checkpoint | 1.2 - Survey Set-out
label | 528db78f-a7d4-5245-b573-8d3a226e9000 |  | note | Ref docs - IFC Drawings
label | 50a1de37-603e-5558-8483-c0b2c7cdff5b |  | note | Acceptance criteria - Prior to the commencement of works, the contractor shall engage a suitably qualified surveyor to set out the works and clearly mark its limits.
button | 48028495-a3f5-5f16-a3aa-87cd77da1a50 |  | button | Acceptance | Yes,No,N/A
label | 54cdc47a-114b-5337-8acf-18aed37bc4f9 |  | note | Key - W
label | 519c4a89-9d55-58c4-acd5-1091c895cf4c |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.3 - Approved Material Type
label | a0ed9071-9073-591d-88e6-1a1d323f5737 |  | note | Ref docs - IFC Drawings
label | 5d39d9ab-e1bc-5c0f-8338-7e8837b8a887 |  | note | Acceptance criteria - Asphalt types specified within IFC Drawings.
label | 2f09938a-1967-59d0-bc8f-1d5d2f19728b |  | note | Acceptance
boolean | f1c29091-093f-5fd1-baf7-9982176ff5d8 |  | tickbox | 40mm wearing course size 10mm Type H (C320) Asphalt 7mm Cationic rapid setting (CSR) emulsified primerseal (C170); or primer AMCO
label | e9ff1fd2-06e4-5c83-a407-b45fca8f8210 |  | note | Key - H
label | 81b8d3ff-5ea5-5d83-99e1-863a3bb44f43 |  | note | Resp - SE
checkpoint-group |  |  | section | 2.0
checkpoint-status |  |  | checkpoint | 2.1 - Storage of Asphalt
label | 79256b93-33d5-5ed3-a4e8-f19945365ca6 |  | note | Acceptance criteria - Asphalt mix has not been stored in a hot bin for more than 18 hours prior to use.
button | 60bfa9c8-2498-5d42-ba2c-6d643f883032 |  | button | Acceptance | Yes,No,N/A
label | 24f501e0-c483-546c-8110-1dd0eb2afe7f |  | note | Key - S
label | d316eb05-cf53-5a64-9be7-ce41f36445dd |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 2.2 - Conditions for Placing
label | c91f9653-c213-5ba0-9025-df419b5d518c |  | note | Acceptance criteria - Surface on which asphalt is to be placed is dry, free from surface water & has a surface temperature >10⁰C
button | 46c9ba72-2d81-5af6-92c9-6414ca0c7c4f |  | button | Acceptance | Yes,No,N/A
label | 1a2a1e75-60a4-5033-a995-a4ab03afdb30 |  | note | Key - S
label | 8c96e1d1-56d0-59a4-a750-0993d7d64f6e |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 2.3 - Commencement of Placing
label | f6352dd0-a482-5320-90a4-7b59a475fa19 |  | note | Ref docs - IFC Drawings
label | d8e843b4-84a7-58e6-bb47-98f2dcf44cb2 |  | note | Acceptance criteria - Crushed rock surface to be primed prior to placement of asphalt.
button | 06e39577-5661-5510-91b0-0f1158040ea2 |  | button | Acceptance | Yes,No,N/A
label | 1a092c9b-a7c2-5358-bf8d-9f57f1febad8 |  | note | Key - S
label | 28142b4b-ccf3-54fe-90db-89d110bc5063 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 2.4 - Spreading
label | 18ee5a54-cf4b-50d6-a6ec-ad99da3a2424 |  | note | Ref docs - IFC Drawings
label | 053d423e-f59e-5d73-8635-6450c32e832b |  | note | Acceptance criteria - All asphalt shall be spread with an asphalt paver except for small areas where use of a paver is not practicable.
label | 4f400337-b3b9-5941-901c-49a4ea29193f |  | note | • All asphalt shall be spread to form a uniformly smooth asphalt mat without segregation, tearing or gouging.
button | 747162a8-a6d0-59fe-ba23-2802f3901fa0 |  | button | Acceptance | Yes,No,N/A
label | 1e9a39a7-c515-58af-a4bd-e5715a714d66 |  | note | Key - S
label | 2ca6ebe6-aa4d-5113-9b67-82a40eda0f06 |  | note | Resp - SE
label | 1d9f01bb-643c-5777-9b3e-2de557c48ef7 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | bbf25acc-1bd5-5c05-aa03-c0dc97193d21 |  | tickbox | As-Built Attached
checkpoint-status |  |  | checkpoint | 2.5 - Joints & Junctions
label | 6cd082e9-9af3-597a-bd97-e7ba3460d969 |  | note | Acceptance criteria - If the paver is required to stop & asphalt in front of the screed cools to below 120⁰C, a transverse joint shall be constructed.
label | 1cd562f7-25f8-5a66-ac29-e512e9c7d51e |  | note | • Longitudinal joints in the wearing course shall be parallel to the traffic lanes.
button | 3a9f7f34-8bfb-568c-b6c4-690f858dd989 |  | button | Acceptance | Yes,No,N/A
label | 4955be7c-db8a-5505-9119-43c99bddce74 |  | note | Key - S
label | c95c3713-a4a7-5b44-9f25-221d61a47d53 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 2.6 - Surface Finish
label | c9476525-ed2f-5448-9fb1-0dc1d041b0ef |  | note | Ref docs - IFC Drawings
label | 8b6aa126-e370-5b0e-a150-84b55b7d291e |  | note | Acceptance criteria - The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches & roller marks.
label | ca746d82-bafc-5449-8872-beba895978f4 |  | note | • Where asphalt is placed against kerb, the surface at the edge of the wearing course shall be either flush with or not more than 5mm above the lip of the channel.
label | 75a37bde-0848-5a41-9cc6-f8e7bad09f59 |  | note | • No point on the finished surface of the wearing course shall lie more than 4mm below a 3m straight edge laid either parallel to the centreline.
button | 1628b6a2-5c8a-50f3-8232-63e3d1be6dee |  | button | Acceptance | Yes,No,N/A
label | 1f78c43c-b9af-59e2-a634-5385d8694767 |  | note | Key - S
label | 3193e980-14e9-58bd-869a-f8bb64dde878 |  | note | Resp - SE
checkpoint-group |  |  | section | 3.0
checkpoint-status |  |  | checkpoint | 3.1 - Compaction Testing
label | 8d98d164-0fc2-5ea3-a7e0-6f123901181c |  | note | Ref docs - IFC Drawings
label | 611b9ab9-4b69-57e3-b1b0-3871e43bae1b |  | note | Acceptance criteria - Testing to be undertaken in accordance with XXX
button | 08f72404-5f56-5762-948d-81e59e823a2e |  | button | Acceptance | Yes,No,N/A
label | 50e1086b-1a8f-53c1-b5aa-b4483224a2d1 |  | note | Key - H
label | 60bcdeb0-8252-5cb6-ab9a-067a16031d5f |  | note | Resp - SE
label | 11ae20b3-057c-53e8-add2-8f1d750b57ac |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 18ad5657-1a33-5dd8-a7fc-f409126575fd |  | tickbox | Testing Attached
checkpoint-status |  |  | checkpoint | 3.2 - As-Builts
label | b12062fd-3508-57c7-9498-b607ac081a49 |  | note | Ref docs - IFC Drawings
label | efad21fb-c54d-5df1-bcfb-48f633c5d9f0 |  | note | Acceptance criteria - Measurements have been taken randomly throughout the lot & are within tolerance.
label | cc1b0125-bd94-515a-ab0b-c2e9076660c1 |  | note | Scale B:
label | d944a5d3-4b43-57a9-bdf5-32063f0dfa7c |  | note | • Measurements: 40
label | 46c2d5dc-d907-55fe-a5bf-a3088ebd43a4 |  | note | • Mean: ±8mm
label | 91b319de-3faa-5633-9ea8-99eb9c5a1838 |  | note | • SD: 10mm
button | ddf96c59-a2b2-5408-817b-df47fdfb4714 |  | button | Acceptance | Yes,No,N/A
label | b0709da3-8fc2-5c48-b07a-d8ce24a5ab80 |  | note | Key - H
label | dc5339af-91db-5795-af69-70c197e89a23 |  | note | Resp - SE
label | b9aaca72-bd5d-5a8e-90c3-fc9b2e2a49b7 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 6451c72e-8e5c-5c13-acff-6198d8e7626a |  | tickbox | Survey Attached
checklist-sectioned |  |  | checklist | CC0394 - ITP-006 - Concrete Pavements and Crossovers | itp |  |  |  | Yes | CC0394 - ITP-006 - Concrete Pavements and Crossovers REV0 | 40d3e093-effd-43df-ae2f-6f443fdd9aeb
checkpoint-group |  |  | section | Lot Conformance.
checkpoint-status |  |  | checkpoint | Works complete
text | 3348630e-aabd-5ab7-98e5-d0a6cf769f0e |  | textbox | Name:
text | 9e6d9d59-31f8-560e-af94-47a6fa83b8dc |  | textbox | Position:
text | 5b26d510-e614-5bd6-8f08-7e9140a4bca2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | 155168dc-6901-55a8-b38b-c511eaa84197 |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | 9f514667-35d1-5d76-ab7b-3172a4bb46d7 |  | textbox | Lot opened date:
text | 4a0808fe-cc69-5abc-8281-48dfe5b7427f |  | textbox | Lot opened by:
text | a69205a1-a984-5235-a6f5-22d667276020 |  | textbox | Date lot closed:
button | 0856f5a6-b92d-521d-a07e-19e6ae6ef8c1 |  | button | NCR raised? | Yes, No
text | ade5f14f-a69c-580c-8448-40710d843034 |  | textbox | NCR Raised Date:
button | 41e2dd38-e5a5-58a7-a67a-3f7971dd5351 |  | button | NCR closed? | Yes, No
text | d6396375-1d3e-50dc-8a15-a52f5dff9198 |  | textbox | NCR Closed Date:
text | bb18fc81-9cf8-566d-881a-89e661d6ea27 |  | textbox | NCR Number:
text | b20edf05-a8a0-5ca4-8598-19ea92266120 |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP
checkpoint-group |  |  | section | 1.0
checkpoint-status |  |  | checkpoint | 1.1 - Determine Lot Size
label | 288ff9f0-0c0f-5d24-881b-6745a53bedb3 |  | note | Acceptance criteria - Day’s Productivity
button | 4abf30c6-4fb9-5386-bedb-90bc22c948cc |  | button | Acceptance | Yes,No,N/A
label | 67924608-3dc5-5349-bf69-201d63ab69c1 |  | note | • See Work Lot Map
label | 55767272-7d7a-589d-9281-0f363c571911 |  | note | Resp - SE
label | 131240b5-0a5d-5059-98f1-6e19bcd91d72 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 0dde3435-c3a9-507a-8f1e-30b48f928401 |  | tickbox | Work lot map attached
checkpoint-status |  |  | checkpoint | 1.2 - Survey Set-out
label | 3d3b7e4f-169e-5191-aa2f-5726ed66badb |  | note | Ref docs - IFC Drawings
label | 63c1252a-b256-5dcb-b19e-23c565a7c0b3 |  | note | Acceptance criteria - Has the work area been set out for line and level?
label | a8b8c181-3d13-5551-8946-7a16972326fc |  | note | • Preceding pavement layer has been picked up and confirmed within tolerance.
button | 0361da81-ecad-5d73-8312-cba4cbbb8408 |  | button | Acceptance | Yes,No,N/A
label | f17f06da-8d15-5c99-ab47-de8399176db0 |  | note | Key - W
label | cd6c2845-44d9-519f-8f0a-e1c5c0ea3aaf |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.3 - Confirm Pavement Type
label | b62f9f83-e6bb-573d-81cf-84ab25529657 |  | note | Ref docs - IFC Drawings
label | b6b0425b-fd30-5e32-85c0-38fa122e7953 |  | note | Acceptance criteria - Confirm pavement type/s within the work lot, and the concrete pavement depth associated.
label | 6e8aff10-bb00-5e6a-a217-86355910d0eb |  | note | Acceptance
text | a4c20fae-c602-5e9f-86c2-c0e76f9bf6d4 |  | textbox | Pavement Type:
text | 3d43ba8c-dd3e-5c24-9dd3-b44f518f86a9 |  | textbox | Pavement Depth:
label | 1ede0467-ac04-5062-a218-e06b87305aa7 |  | note | Key - H
label | 29fa6b8a-d342-569c-822a-51bb4d5bf36b |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.4 - Confirm Concrete Strength & Colour Required
label | e971ece6-b23c-5148-b0d1-d5a1b3607d3c |  | note | Ref docs - IFC Drawings
label | fafbd49a-634b-5709-ad9e-cee7decd36b9 |  | note | Acceptance criteria - Confirm correct concrete mix in use prior to commencement of pour.
label | cb3c948e-3321-5302-b4e6-8c064686f6ef |  | note | Acceptance
text | 1eac3363-6ca1-57d0-ae5a-83a154c2dd1b |  | textbox | Concrete mix:
text | 43d8e847-5679-5c97-a391-16b6ae6fdeb9 |  | textbox | Strength:
text | 682bb1df-34e5-5e3e-9e86-ea5bad879208 |  | textbox | Slump:
text | 3ab8973b-02fc-5db9-b777-5b0f47f634fe |  | textbox | Aggregate size:
label | be949665-d298-5a0f-83b9-fc30baca6351 |  | note | Key - H
label | c2f54ffd-58d3-5473-93b2-e72ed5b8c8e5 |  | note | Resp - SE
label | c8289bd4-3c6b-5279-a9f7-88bc80a910b7 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 4bd920c3-ddcf-5de6-a224-1a477b0b60a9 |  | tickbox | Docket attached
boolean | acdd2353-e9de-5a41-87db-f3984247ac1b |  | tickbox | Pre-pour inspection checklist
checkpoint-group |  |  | section | 2.0
checkpoint-status |  |  | checkpoint | 2.1 - Preparation of Subgrade and Base Pavement
label | 2dc6d343-05ba-5f8a-abe1-89f86b9f5beb |  | note | Ref docs - IFC Drawings
label | 7afc05df-08da-5f67-9ecb-5ffc0811be6d |  | note | Acceptance criteria - Subgrade trimmed and compacted prior to prior to placement of successive pavement layers.
label | 261610e8-4b75-51dc-9619-2857c07260e1 |  | note | • Subbase placed and compacted to the correct line and level. Confirm compaction and tolerance prior to commencement.
button | 0244a041-bf84-56a7-ae8e-b01055c882ca |  | button | Acceptance | Yes,No,N/A
label | e855f438-0927-59b9-9e25-f23e58ef2ab2 |  | note | Key - S
label | 5105aa39-7dcd-53ab-84be-9f3974ceb9fa |  | note | Resp - SE
label | 2f033678-ba10-5eba-8125-e71b887290fe |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 688cadbe-cf21-5d84-8900-1c7f46ddf5c3 |  | tickbox | QA for preceding pavement layers complete
checkpoint-status |  |  | checkpoint | 2.2 - Install Reinforcement
label | c89a864e-7fde-5814-bc61-3c1a7f9803ed |  | note | Ref docs - IFC Drawings
label | 95f3a620-ec2c-59ed-94f2-01b2c6bcf324 |  | note | Acceptance criteria - Reinforcement installed as per IFC Drawings, City of Casey Standard Drawings and Specifications.
label | 8b6c4137-3bd9-5f25-9125-aefe2fd0d23a |  | note | • Symal to confirm prior to commencement of pour.
button | 2fe193ad-559d-57a5-8ea3-e9f372b01d65 |  | button | Acceptance | Yes,No,N/A
label | 17a99b27-8d15-5989-b980-64df9a4a6e02 |  | note | Key - S
label | 00755bba-3cc2-5de8-a7b6-338fed4f39a1 |  | note | Resp - SE
label | 0d879887-b5a0-5a3e-8402-49142ad502ed |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 6c026b9c-644d-583e-ad06-98007602cf25 |  | tickbox | Pre-pour inspection checklist
checkpoint-status |  |  | checkpoint | 2.3 - Concrete Pour
label | fd110373-94cc-5b85-96af-82e4a9f55a2d |  | note | Ref docs - IFC Drawings
label | 998503c4-e1db-5917-9470-4669ae9c6909 |  | note | Acceptance criteria - Confirm via delivery dockets that concrete is in accordance with that listed above.
label | 84a2961b-9ef7-575b-b80a-5639921d8be9 |  | note | • Contractor shall place concrete to avoid segregation. The placing of concrete in a section shall be carried on continuously until that section is completed.
button | 0633634f-4d7b-5409-bdb7-e5fb5ad56184 |  | button | Acceptance | Yes,No,N/A
label | 7cbfdcf8-b75a-5825-8054-f3e24acaa3a1 |  | note | Key - S
label | f95c0f83-6ea9-5c05-8c2d-9b8670bac086 |  | note | Resp - SE
label | 356c12e1-4a84-520f-843f-dc1304e1b3f1 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 1b9ab45e-ea62-58ce-b613-6e110901b487 |  | tickbox | Docket attached
checkpoint-status |  |  | checkpoint | 2.4 - Jointing
label | 686f4e43-8fae-53ab-a198-cb6ff121e48a |  | note | Ref docs - IFC Drawings, City of Casey Specification
label | 4f9934d1-4f8d-51d1-a055-f488fea9ca7e |  | note | Acceptance criteria - All jointing/saw cutting completed in accordance with IFC Drawings and relevant Specification.
label | 73ad75ea-b41a-5c77-a799-a21665607f85 |  | note | • Joint placement to be confirmed on site.
button | 5df49ff7-4528-538d-85a2-4fdd2f590fa5 |  | button | Acceptance | Yes,No,N/A
label | 25552cea-c7f2-524d-91fa-03a15d559e4d |  | note | Key - S
label | 44f5dea6-66c1-5e35-b7fd-0f50ae1301b0 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 2.5 - Concrete Testing
label | f09ec6ba-f01d-5375-a092-2a67255a9109 |  | note | Ref docs - IFC Drawings
label | 37707531-0e00-529a-b4f9-0fe628a767f7 |  | note | Acceptance criteria - 1 sample to be taken per 50m3 placed.
label | 99970e1a-9bc5-564a-beb8-81b2876ba2b6 |  | note | • 3 cylinders to be taken per sample.
button | bd010e1b-7158-5056-b7c0-ac2fbc4acf18 |  | button | Acceptance | Yes,No,N/A
label | 6031b5b3-f63e-5e23-a5ca-88b66c62b4df |  | note | Key - S
label | 9a15ccfd-c09a-55f3-931d-6c39ec20e1a2 |  | note | Resp - SE
checkpoint-group |  |  | section | 3.0 Conformance Check
checkpoint-status |  |  | checkpoint | 3.1 - Finish
label | 99206d4e-febd-5093-a941-825ab72a4ff9 |  | note | Ref docs - IFC Drawings
label | 059b1007-2689-5aff-b127-992c3853ec87 |  | note | Acceptance criteria - Confirm finish is in accordance with IFC Drawing and Casey City Council specification
label | fc3ea62a-2820-540d-9570-510e6a246cac |  | note | Acceptance
text | f23320e3-c7fb-5879-99b9-e43681def7ec |  | textbox | Finish Type:
label | 9cb97214-7246-5cee-9059-c345ce4f9182 |  | note | Key - S
label | 1c1e1e6a-dcc5-5736-a42f-80edb74f8cf6 |  | note | Resp - SE
checkpoint-group |  |  | section | 5.0
checkpoint-status |  |  | checkpoint | 5.2 - Visual Inspection
label | cbd2afc2-9f48-5649-8e95-752dcef93544 |  | note | Ref docs - IFC Drawings
label | 35bf23da-ddb2-54cf-9802-88f97be9332d |  | note | Acceptance criteria - Do not cover or conceal work until it has been inspected by Symal.
button | e409e4dd-5769-5a6c-98eb-99f249628b0f |  | button | Acceptance | Yes,No,N/A
label | 70c9454f-0584-5c31-b4f6-5ff372182281 |  | note | Key - H
label | d8bf91d7-ca41-55a8-8c8b-c0c1714eae5a |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 5.3 - As-Builts
label | aa982dbd-dec4-5afc-a198-b92cd9579324 |  | note | Ref docs - IFC Drawings
label | 0227a911-0d9e-5add-866a-6e7ee1a8e28b |  | note | Acceptance criteria - As-built survey of work lot attached.
label | c0394097-d7bf-57ba-92c6-e9b60e2592cb |  | note | • All points within tolerance.
button | 2762dec2-11ad-50c8-b186-3422ff9aef2c |  | button | Acceptance | Yes,No,N/A
label | 64abb78f-30e6-5a93-9618-f8537bc69869 |  | note | Key - H
label | 297d9d42-dfc1-54ee-81c8-249c4825088d |  | note | Resp - SE
label | f498cb06-d3af-59c4-922a-0a3093180961 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | dc9a3c3e-bcbc-5c30-bb49-c7503cf427d7 |  | tickbox | As-Built Attached
checklist-sectioned |  |  | checklist | CC0394 - ITP-002 - Site Clearing | itp |  |  |  | Yes | CC0394 - ITP-002 - Site Clearing REV0 | 58eeac06-ed6b-4de0-a80b-e663e05692aa
checkpoint-group |  |  | section | Lot Conformance.
checkpoint-status |  |  | checkpoint | Works complete
text | 3b6c3a68-cca1-5a9b-a966-2c70a2dc9fb7 |  | textbox | Name:
text | e2bd9e23-e0d3-5efa-867a-a3fe7d1073a7 |  | textbox | Position:
text | 1f55bfc9-1d5d-55ed-aa98-1b99a8d8412e |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | 87134c1d-f304-5636-995c-ac032c447481 |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | a48cd31e-cd0c-51cf-a19a-73c4f18e09a5 |  | textbox | Lot opened date:
text | f620d336-f9b9-521b-8cec-69c102bca9d0 |  | textbox | Lot opened by:
text | 63ef9f10-3968-59a5-9c05-96a3918ff2e1 |  | textbox | Date lot closed:
button | 392c50d3-4a82-5d30-9f55-134311c3ab96 |  | button | NCR raised? | Yes, No
text | 35784289-f0f8-5fde-8f38-b632be942455 |  | textbox | NCR Raised Date:
button | 52d3ee01-1144-5fb9-a5cd-9c68db1e0d79 |  | button | NCR closed? | Yes, No
text | a55fbc58-c6b1-52a7-ab6b-102e579cc8c7 |  | textbox | NCR Closed Date:
text | a1d25579-f619-5e42-a0e0-1ad406c03d34 |  | textbox | NCR Number:
text | e7e26d20-6c81-58e3-83e0-0166a21e73e9 |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Determine Lot Size
label | f7807aec-e164-50e6-8aef-5bb5f34cd206 |  | note | Acceptance criteria - What is the lot size?
text | 752ccd74-b74e-542b-8342-a2525389d441 |  | textbox | Acceptance |  |  | m2
label | c97e8986-5ac5-565c-96d6-0d56a614f637 |  | note | • Maximum lot size = 4,000m2
label | d13c00b7-a4e9-5787-9cc8-204c999321f1 |  | note | Resp - SE
label | 69ea02df-ba9a-5a5e-bec4-91cde94baede |  | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
boolean | ed96472e-d01b-5a87-ab0b-4b76f051ca92 |  | tickbox | Work Lot Map
checkpoint-status |  |  | checkpoint | 1.2 - Safety
label | 5bf8445e-a109-5e3f-a040-cb303aaf7a79 |  | note | Ensure that the following items have been actioned:
label | cfbfcc5a-1b3e-5a14-8842-2b01efe8b34e |  | note | – SWMS if applicable
label | 3a63f73c-409f-5b62-9b19-b22db6402654 |  | note | – All staff inducted
label | 25616709-ca6a-56d9-8b46-77a1e096e3e3 |  | note | – Plant Pre-start Inspection
label | 04f4e359-26de-5d96-abc6-f93bf0518bb4 |  | note | – Service locations identified
label | 21da4d9a-472c-504a-9706-a35018b68b02 |  | note | – Traffic Management Plans (if req’d)
label | e9a00efd-8bf4-5b76-8e69-3abed64ff6a6 |  | note | Ref docs - SMP
label | 9a020ed8-0fa3-571f-8679-6174a495fed6 |  | note | Acceptance criteria - SWMS submitted reviewed and accepted if required.
label | 95c01732-1db4-561b-bf54-f7bf47ea3bee |  | note | • Personnel inducted to RJE requirements.
label | bd0b4199-f24e-5207-8635-45e6070c1b56 |  | note | • Plant inspections completed and entered.
label | eb780fac-89fc-59b7-9581-2faf322f7a89 |  | note | • Pre-work briefings completed.
label | 04fe9857-e834-5ee7-9be7-8a0b77503e10 |  | note | • Service diagrams available and services located.
button | b91549ef-ba90-5c9a-ae9f-3f84daeb00dd |  | button | Acceptance | Yes,No,N/A
label | 8b4137cf-e920-5b59-a602-4222f279ac8d |  | note | Freq - Once (Pre-Start)
label | 3f3834e7-5fc2-5f66-9a5f-ba4da4b3b55f |  | note | Key - H
label | e3e577dd-18d7-59f8-aa86-22f60a94b3e0 |  | note | Resp - SS
label | f93e0368-54f4-5b98-b419-1a6e768b7441 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 1.3 - Excavation Permit
label | d500396a-a498-57ed-ac93-761f202e9d90 |  | note | Ref docs - SMP
label | 9b21c6b6-0cd9-5076-b928-73d90b152efd |  | note | Acceptance criteria - All identified underground services marked and potholed to confirm location and depth. No machine excavation within 1m of underground services. Permit available and signed.
button | 8baeda0d-0980-57a7-b90f-89a87167451b |  | button | Acceptance | Yes,No,N/A
label | 10be78ff-4e79-5854-8cfc-63efc51c2fed |  | note | Freq - Prior to start of works
label | 00a46745-b4c7-554d-af65-7775dd9cf7ef |  | note | Key - H
label | 459a4644-9e77-547d-99d5-552f6641e530 |  | note | Resp - SS
label | 424415f6-4300-55be-a842-8336f3624006 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 1.4 - Check Survey Set-out
label | c3d59870-5dde-580c-8680-756f147078ff |  | note | Ref docs - Construction Drawings
label | 28e35b1a-c922-5d89-a1c1-94e41e7f0584 |  | note | Acceptance criteria - Survey setout extend of works
button | 7b2f5a08-ec44-521b-8663-ad06d0edb100 |  | button | Acceptance | Yes,No,N/A
label | 7eccd965-7336-5649-be37-a11f9f0f0b27 |  | note | Freq - Prior to start of Works
label | f58f2e00-b027-5ae9-b7c4-a4ff91ba2237 |  | note | Key - H
label | 262f3c23-b424-5e6a-a1c3-f460381f11cf |  | note | Resp - SV, SS
label | 0b8da06f-bf49-5b9d-8b6a-1dd9cc28a5b7 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 1.5 - Tree Protection
label | 7e345987-57e6-5bfc-85c2-345593fc6a51 |  | note | Ref docs - Construction Drawings
label | ff63792c-5638-58a1-b19d-d055e1689296 |  | note | Acceptance criteria - Have all trees / native flora and fauna been protected including the establishment of no go zones as indicated in the construction documentation, CHMP and CAB?
button | 63eb3e76-b8b9-5fbe-89ab-f8e1fbbc6c9b |  | button | Acceptance | Yes,No,N/A
label | 7b44ddd0-e98e-564f-bde0-137fd38c85f0 |  | note | Freq - Prior to start of Works
label | 782f597b-8289-59b0-8144-b58b191330d4 |  | note | Key - H
label | 50bac8b5-f075-5a19-b717-de591cde63d0 |  | note | Resp - SE
label | 38256ef8-e1eb-5c2a-877a-bf04a6fc9d54 |  | note | RJE Key - S
checkpoint-group |  |  | section | 2.0 CLEARING AND GRUBBING
checkpoint-status |  |  | checkpoint | 2.1 - Clearing and Grubbing
label | 2462ff2f-10fc-54f7-b2aa-747ec775d92f |  | note | Acceptance criteria - Have the identified areas been cleared of all vegetation, refuse, unsuitable material and obstructions down to natural surface?
label | 7fdd760e-5997-5100-b2e6-2f34b5dd7cfc |  | note | • In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed.
label | 0bf729ce-679b-53b6-97b3-4b7d4d0efb20 |  | note | • Unsuitable material and topsoil is to be stockpiled in the designated location and is not to be used as fill material.
button | 39bab999-9379-54e0-a5b7-5acbb873c588 |  | button | Acceptance | Yes,No,N/A
label | 1223337b-e247-5f74-886f-cd09dbbac475 |  | note | Freq - Visual Inspection
label | 280715b1-12eb-5faa-9272-f070c305e987 |  | note | Key - H
label | fa6a3fc8-34c2-58f3-b3fa-08d5479e9e99 |  | note | Resp - SS
label | 47d351a8-3e33-5978-9d78-1084df10a062 |  | note | RJE Key - S
checkpoint-group |  |  | section | 3.0 Topsoil Stripping
checkpoint-status |  |  | checkpoint | 3.1 - Stripping
label | a9eac23a-c936-5084-a7a8-31c264dd3616 |  | note | Acceptance criteria - Is the appropriate equipment being used to ensure topsoil and subsoil layers are not mixed.
button | 92d3d99e-91c9-5e8b-b3ac-4b56905450d0 |  | button | Acceptance | Yes,No,N/A
label | 78e4c586-2b95-5960-a9d3-66ea8d2afead |  | note | Freq - Visual Inspection
checkpoint-status |  |  | checkpoint | 3.2 - Stripping
label | 9809ef4a-f775-57bc-b45c-fa88664efca4 |  | note | Acceptance criteria - Has the area been stripped and stockpiled to an appropriate depth (minimum top 50mm) removing surface topsoil and unsuitable material in a way to leave the surface evenly graded and free-draining?
button | 01739821-b188-505f-9232-4d749a03302e |  | button | Acceptance | Yes,No,N/A
label | d52ef1d6-b81f-5e53-9067-6a28c10f1cd4 |  | note | Freq - Visual Inspection
label | 0cf03221-c28a-50bc-b417-c81eda113541 |  | note | Key - W
label | 768fd132-ceca-5c02-808b-165365da6e54 |  | note | Resp - SS
label | bc83a625-d949-5e47-a6b9-1c6b93ab18b8 |  | note | RJE Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Top soil export / stockpiling
label | 069501f5-821a-581a-baaf-4caed7dae7df |  | note | Acceptance criteria - Has the topsoil being stockpiled been approved by RJE (where applicable).
label | 3bfdb715-c098-5b15-8d48-2755f2128040 |  | note | • Have the environmental controls as per CEMP been adhered to?
label | 9119b2cd-93b0-52ae-ba90-cbb84616abbb |  | note | • Dispose material as per CEMP requirements
button | ad46d5fd-b3d9-509e-8d39-3d40fe6eeb0a |  | button | Acceptance | Yes,No,N/A
label | e745af21-8708-5b59-99cc-c24ab531fcd5 |  | note | Freq - Visual inspection
label | 2fc47736-e634-5297-b8d7-4a28fec15c39 |  | note | Key - W
label | 6828553b-1abf-5065-b111-e32de2fb7378 |  | note | Resp - SS
label | 14d4e314-2ccd-57f8-b5f2-0ea97c8b6cb6 |  | note | RJE Key - S
checklist-sectioned |  |  | checklist | CC0394 - ITP-004 - Storm Water Drainage | itp |  |  |  | Yes | CC0394 - ITP-004 - Storm Water Drainage REV0 | 97625f6e-fd62-47be-a45c-3f2bef96873d
checkpoint-group |  |  | section | Lot Conformance.
checkpoint-status |  |  | checkpoint | Works complete
text | e9730a03-9070-5230-aa8d-9d48ff0a2eb2 |  | textbox | Name:
text | 7282fdfe-a1f6-5e63-aefd-35502f7a368b |  | textbox | Position:
text | c71139f2-3475-5dcf-944c-a0eda5d455c6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | 5b3cdb7e-7104-538b-a0b7-5b8cf7b37ca6 |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | a5d02fc3-ef88-55e7-9ece-8cbaa8ee4276 |  | textbox | Lot opened date:
text | 857a4472-6d18-5a4b-9ca2-8cb608d4a91f |  | textbox | Lot opened by:
text | 069df944-5c6b-5c08-9d25-97628764fbb9 |  | textbox | Date lot closed:
button | ae2b4955-3042-5369-b37b-a51793cac3f0 |  | button | NCR raised? | Yes, No
text | 27c894cd-8e76-56e5-9392-446a72b44158 |  | textbox | NCR Raised Date:
button | c4d6afad-9428-511c-8fa4-6224c247272f |  | button | NCR closed? | Yes, No
text | 0a811ec4-9de3-5957-bdf6-3799b364bd3a |  | textbox | NCR Closed Date:
text | 4a1d18fa-1042-5322-ab4b-763285dd52e1 |  | textbox | NCR Number:
text | e5925ea5-c17e-5387-bf50-ba8805808165 |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP
checkpoint-group |  |  | section | 1.0
checkpoint-status |  |  | checkpoint | 1.1 - Determine Lot Size
label | b587ef64-134f-5fb8-b0fb-4d7059cfea1e |  | note | Ref docs - IFC Drawings
label | 508c1d6c-f03a-5d77-b4b4-bd8bc6a6087b |  | note | Acceptance criteria - Pit to Pit
label | 62504270-9d96-5acc-8ab5-f158f3d04d4d |  | note | Acceptance
text | c9e40a8b-2a7c-5a48-97c2-3d3bc86db137 |  | textbox
label | ecf2017e-22d0-523b-a36f-c3f2c566f032 |  | note | to
text | 8181fd9d-bfc8-5550-a11b-08b23f949a23 |  | textbox
label | d92550ff-52d2-54e7-b858-ce14be01e924 |  | note | Resp - SE
label | 1a9d58a6-4f98-5648-abd3-064fb72d7481 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 209c4e8f-57e0-5c8d-909e-33dfcfe59cf4 |  | tickbox | Work Lot Map
checkpoint-status |  |  | checkpoint | 1.2 - Survey Set-out
label | a15ec3ea-33ef-5417-95b8-9965e83e2d52 |  | note | Ref docs - IFC Drawings
label | cb6c9084-8209-5bd4-b25f-e924a4ae9c11 |  | note | Acceptance criteria - Prior to excavations being carried out, the contractor shall engage a suitably qualified surveyor to set out all drainage lines including manholes, temporary benchmarks, sewage wet wells etc.
label | 4d050374-6c2c-5e11-b3b3-39828758651d |  | note | • Clearly mark limits of works.
label | 4627a097-17b1-5848-bd87-1ca597e08012 |  | note | • Chainage, offsets, cut/fill level, cutting slopes, grades and cross sections specified or shown on the drawings, etc.
button | 3865a30e-5146-5fba-bdae-2079055a66e6 |  | button | Acceptance | Yes,No,N/A
label | b12d63ce-e5cb-556e-a28e-8c5ad8f367a5 |  | note | Key - W
label | 639638e3-2fbc-579b-a341-0168df1d65ea |  | note | Resp - SE
label | 1c504bc0-dd23-512b-a7d5-f92a69392dd1 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 1.3 - Approved Material Type
label | 4060fb57-94d1-5b5f-b8ab-838caac1692d |  | note | Ref docs - IFC Drawings AS1260
label | 037d16d0-3ef9-5f18-987d-e8876aa2f424 |  | note | Acceptance criteria - In accordance with IFC Drawings:
label | 807a0f30-7bb2-561e-b447-9035c41ac231 |  | note | • Storm Pro
label | f3476ab2-faa1-53c8-9a99-8a6512fadf1f |  | note | • PVC
label | 4ab98be7-0bfd-576c-a53a-121619a5d5b5 |  | note | • All pipework to be clearly labelled & detectable to identify it as stormwater drainage.
text | 23195226-3728-5f70-a673-f27ecf1dd2d4 |  | textbox | Acceptance | Yes,No,N/A | Pipe Size/Class
label | 263c366d-0e49-5407-95ac-a6319f585f42 |  | note | Key - H
label | 03797eed-d44d-54a1-ab67-f809a57646ac |  | note | Resp - SE
label | 94b1121c-105f-5703-bff5-1432f2ecc7cb |  | note | RJE Key - H
label | 472a16a8-fbb2-5511-8847-0d3e60156aa1 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | d5f8de15-b26c-5c9c-89ed-4c78029f9f18 |  | tickbox | Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Excavation of Drainage Trench
checkpoint-status |  |  | checkpoint | 2.1 - Excavation
label | 934f8e53-616b-59c0-b49d-c96b884e6759 |  | note | Ref docs - IFC Drawings AS3500
label | cf76e192-5177-59a4-ae06-ade1f6a15bd9 |  | note | Acceptance criteria - All excavations subject to inspection prior to the installation of services and throughout the duration of the excavation.
label | 425421af-c07a-5af9-8746-d897dc389f7c |  | note | • Excavate to the lines, levels and grades as required for in ground services specified in accordance with the requirements of AS 3500.
label | 7260ce23-8e81-5835-a731-3f95b79a3904 |  | note | • Keep trench width & depth to that required by the service & its bedding method.
button | 8f38e0e5-0c8c-57dd-a41f-7c42d8417565 |  | button | Acceptance | Yes,No,N/A
label | d94813f9-8eb7-5b65-8d5b-54fa9c2ebebb |  | note | Key - W
label | c943b201-88db-5ee5-a984-662b62287b1f |  | note | Resp - SE
label | e0e3e507-2ed2-5f6f-a13c-5e53f932b4b5 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 2.2 - Removal of Obstructions
label | c7410587-9149-59f6-ad37-aa1e0e466713 |  | note | Acceptance criteria - Remove obstructions including roots, stumps, boulders and the like which may interfere with the proper functioning of the service
button | 92be3b15-5a04-5a5c-bb7f-c4dd66eaae6a |  | button | Acceptance | Yes,No,N/A
label | 84469ef8-a74a-5ef9-9679-314a295c0a33 |  | note | Key - S
label | 6ae6c82a-f174-55ce-85ee-3e1b57bbb311 |  | note | Resp - SE
label | 6a4f1a79-02cf-5d99-8ca7-f17ccab17080 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 2.3 - Water Management
label | 5b544aff-9b9b-53a6-998b-f041482a1708 |  | note | Acceptance criteria - Symal shall maintain all excavations in a well-drained condition.
label | 65e2aa92-622e-5b4b-a1fc-9cc52f1f61cd |  | note | • No bedding material or pipe work shall be placed in excavations containing standing or running water.
button | 484d5136-5866-52d9-837c-0859525462b2 |  | button | Acceptance | Yes,No,N/A
label | ec57d7e4-dab5-5128-ad1a-03bf17dd63cc |  | note | Key - S
label | 2b5137ae-8c91-50a2-86c6-d7859949df0a |  | note | Resp - SE
label | ad17f790-66be-5f6e-9688-1739f1a4d351 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 2.4 - Bedding Material
label | c55840c5-3eff-5d83-830a-02df30296ec1 |  | note | Ref docs - IFC Drawings
label | 70a9782f-b3cb-5d0d-a8f4-77ce3f0ca97c |  | note | Acceptance criteria - All Pipes shall be installed with well graded washed clean sand to AS3725
label | 3bfc5fbc-bf5c-5d80-aeba-f8e24cfe6da4 |  | note | • Bedding material to be placed the full width of the trench and not less than 100mm in thickness.
button | 18964554-5fb5-52ba-ba20-904823f2674c |  | button | Acceptance | Yes,No,N/A
label | dcdc47c4-70d7-5c55-b65c-df90d8d841c3 |  | note | Key - W
label | af9a6f7d-aed0-5ba4-9893-7dc4e0a3b593 |  | note | Resp - SE
label | 9e36bc16-c2cd-5837-82bb-9609f30e0e9a |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 2.6 - Compaction of Bedding
label | f8044471-afef-504c-b8ec-0516e95f5683 |  | note | Ref docs - IFC Drawings
label | e255f888-b5bd-5388-9dc1-de4516765192 |  | note | Acceptance criteria - Bedding material shall be compacted to refusal handheld mechanical equipment.
button | 1238c908-6c28-5c4a-9703-4b016c5507b7 |  | button | Acceptance | Yes,No,N/A
label | 4adcdb04-7cda-58a6-9d77-bb1cd8c1404e |  | note | Key - W
label | af5fbaa8-cec4-5581-8d42-77672674c811 |  | note | Resp - SE
label | 90081ab3-f823-5440-b3f5-fde3a190d07c |  | note | RJE Key - S
checkpoint-group |  |  | section | 3.0 Installation of Drainage Pipe
checkpoint-status |  |  | checkpoint | 3.1 - Pipe Installation
label | 34e97bbe-8f8f-5854-a4f6-c82ea9c0d64c |  | note | Ref docs - AS 3500
label | 740f4b07-cd1b-5260-9ca5-056e57d3178a |  | note | Acceptance criteria - All excavations subject to inspection prior to the installation of services and throughout the duration of the excavation.
label | 3a227341-058e-5fa9-aa2b-ca7d6da27e03 |  | note | • Pipes shall be bedded evenly to ensure sockets to not bear on the base of the trench
label | 4184ef72-d258-5190-951e-707c73e0fb92 |  | note | • Pipe laying shall commence at upstream end at downstream end of the run. All pipes shall be laid with sockets pointing upstream.
label | 2246b8f9-4393-5a65-8442-d0bf53c44e38 |  | note | • Lay at min grade 1:100
label | 760c5cab-740e-51dc-8192-6c2b523ac51d |  | note | • Excavate to the lines, levels and grades as required for in ground services specified in accordance with the requirements of AS 3500.
label | 6cea8d57-39e6-5ac8-a139-ac666397d6f8 |  | note | • Keep trench width & depth to that required by the service & its bedding method.
button | f7184e7f-1fa0-5dff-af01-aa15ce5cfc66 |  | button | Acceptance | Yes,No,N/A
label | c5f43417-e2c0-577c-a970-9d5725d1d28b |  | note | Key - W
label | 89427b63-af68-58cc-a7ef-966cb46c356e |  | note | Resp - SE
label | be3bb390-b6d8-5f22-9708-c6a47f602965 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 3.2 - Pipe Grade
label | b1348273-3056-58e8-bd2e-d82dbb97f78c |  | note | Ref docs - IFC Drawings
label | 010ed532-1557-5c2f-b022-989300a88ea5 |  | note | Acceptance criteria - Install piping in straight lines at uniform grades without sags.
button | 5adaca6e-ad1b-50a2-b189-cf868beec39f |  | button | Acceptance | Yes,No,N/A
label | 6b20ab11-117c-5fc6-94c1-83768897516d |  | note | Key - W
label | 37fb2dfd-9a9f-50ab-9264-f70521550f63 |  | note | Resp - SE
label | b4b2d19b-69ec-55eb-9de5-13a7222334d3 |  | note | RJE Key - S
label | 2e0cca73-ec07-58d8-a985-afa6c58c6275 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 3ac7c9b1-be35-57d5-87c4-4ab623b9ea31 |  | tickbox | CCTV Report
checkpoint-status |  |  | checkpoint | 3.3 - Tolerances
label | d7549f23-d61d-5eb9-ac4a-eebfe92fa707 |  | note | Acceptance criteria - Unless otherwise specified, tolerances as follows:
label | 09204dec-28f9-56a7-9268-6df87f995b52 |  | note | • Offset of entry pits required to match lines of kerbs or barriers ±20mm
label | f44b2101-2720-5eb9-ab2e-2bbae135a428 |  | note | • Plan location of pits other than offsets to kerb lines or barriers ±100mm
label | 276b8ac4-b7a5-5ea1-9aa2-b3c9c2f2d9ca |  | note | • Invert level of pipes at pits ±50mm
label | 73b679d0-45ea-59c8-8726-c1183a65676d |  | note | • Departure from design grade of pipe runs ±10mm in 10m provided minimum grade is not less than 1:250
button | 6f9d6691-5ab9-5c0b-9252-7f6c0da0bf88 |  | button | Acceptance | Yes,No,N/A
label | 9f7897aa-92ed-5fcc-8a3a-5220c9925df3 |  | note | Key - R
label | 1e9bd445-e9cf-5fc3-9b43-965de9cb1c3b |  | note | Resp - SE
label | d0a45e34-3dd7-50fd-8f1e-da44aa52be11 |  | note | RJE Key - S
label | b76191fd-e687-5ce8-84c2-4557f59969d2 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 7aa1c203-bffb-5a9e-9ef8-01234138bea9 |  | tickbox | As-Built
checkpoint-status |  |  | checkpoint | 3.4 - Pipe Fittings, Supports & Fixings
label | 45b6d54a-cec9-5dc3-a453-305bf80383d9 |  | note | Ref docs - AS3500
label | 511cc929-fa97-5a12-92aa-e432287c1456 |  | note | Acceptance criteria - Provide all bends, junctions, inspection openings and other fittings as necessary for the completion of all systems.
button | 5cac9259-3999-500c-9994-0475ff5174e7 |  | button | Acceptance | Yes,No,N/A
label | fab15048-1b21-5076-b621-83cc29a176de |  | note | Key - H
label | 1bbfe98b-44df-5cf0-9b37-dafcb0992576 |  | note | Resp - SE
label | 47361722-fde8-5f56-a8f8-19efc678234c |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 3.5 - Pit Install
label | 85ce6b89-cf08-505c-b99e-eabbe8af27e8 |  | note | Ref docs - AS3500 IFC Drawings
label | 7afd076e-8ff8-562f-a5a9-58fc957d7cb6 |  | note | Acceptance criteria - Pits are to be constructed in accordance with project specifications, with internal surfaces and exposed surfaces finished smooth & true. All pipe break-ins are to be made neat and finished smooth without gaps/cavities.
button | 5f47c107-0139-5cc7-bf3e-9e4f7087d57b |  | button | Acceptance | Yes,No,N/A
label | 7f2d6afd-2487-5369-bf85-cbdbf3c51118 |  | note | Key - W
label | 36631dd3-2e7b-5bcc-873e-f793c28237cb |  | note | Resp - SE
label | 65d6874f-de97-5bbe-990a-56af892aa979 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 3.6 - Survey of Installed Services
label | c38b188d-3299-55d0-b897-fe55ac03c461 |  | note | Acceptance criteria - Accurately record the routes of underground cables and pipes before backfilling. Include on the record drawings.
button | b723f1f2-3b76-5ca6-8706-e039c920602f |  | button | Acceptance | Yes,No,N/A
label | a9856a9b-9a21-5e9f-9784-67d00aafaaf6 |  | note | Key - R
label | 680ddd35-40d3-5f22-8e54-18c87f489fa2 |  | note | Resp - SE
label | 65e5a25b-2971-54e3-9d43-bdcd31b5779a |  | note | RJE Key - S
checkpoint-group |  |  | section | 4.0 Backfill
checkpoint-status |  |  | checkpoint | 4.1 - Backfill Material
label | 7adc9fb3-ae8b-5b89-801d-13b8e42000f5 |  | note | Ref docs - IFC Drawings
label | b69f8cf3-1135-5be0-83de-8dee35f03ebb |  | note | Acceptance criteria - After pipes & fittings have been set in the correct position, jointed, and tested, further bedding material shall be used to fill all recesses below sockets, and bottoms of trenches.
button | 2cb19dd7-cebb-5684-9de3-4749cf48943d |  | button | Acceptance | Yes,No,N/A
label | e11744b1-d806-5bee-ae3c-3e6480b04f08 |  | note | Key - W
label | 9ef708a9-53ee-59b7-8923-895c4c6cde5c |  | note | Resp - SE
label | e9152e86-7658-5867-afa2-80e086280fe2 |  | note | RJE Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Layer Thickness
label | a71c75af-0389-53ea-a107-bf0fa04ee531 |  | note | Ref docs - IFC Drawings
label | 790c7ebb-4492-5e05-8594-a1b40d66eac1 |  | note | Acceptance criteria - Backfill material must be placed and compacted in maximum 150mm layers.
label | 28bd081a-d042-50a9-a15b-f2a3587fbff3 |  | note | • Backfill trenches as soon as possible after satisfactory testing & approval of laid and bedded service.
button | 3720e05a-6b72-59ff-a4de-adb85e830650 |  | button | Acceptance | Yes,No,N/A
label | d53d6af3-a20e-5e27-901c-477121497305 |  | note | Key - W
label | e8a17355-a73f-5dbc-9e82-65ef8e363fbf |  | note | Resp - SE
label | b9d5e4be-ad16-567f-88ea-413057cb6535 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 4.3 - Compaction Testing
label | 8c8c2232-d37d-5bf0-b19b-1d011300fa3a |  | note | Ref docs - IFC Drawings AS1289
label | 16b3b12e-9e5e-5635-8648-879af3c8b8fd |  | note | Acceptance criteria - Layers must achieve 98% Standard Compaction at optimum moisture conditions.
button | e74bbf21-b531-5df7-aa27-cd34bd92490f |  | button | Acceptance | Yes,No,N/A
label | f6d18d98-726f-5b1d-ae06-816f388df180 |  | note | Key - W
label | a26cbe21-cea7-50af-b3ba-aeb1c35d138f |  | note | Resp - SE
label | f9448030-b2f8-5ce2-a2dd-71621bcd7fef |  | note | RJE Key - S
label | e6d1cedc-b049-5c6a-a11c-7a6121391d6c |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | e1c1cb9e-d237-53dc-b772-77fda3b44bd4 |  | tickbox | Compaction Test Report
checkpoint-group |  |  | section | 5.0 Conformance Check
checkpoint-status |  |  | checkpoint | 5.1 - Clean & Finish
label | c97bb797-4481-510e-bbe4-aff6b428ec2a |  | note | Ref docs - IFC Drawings
label | cd7ec6a6-eaa2-539a-bc36-5336994328fd |  | note | Acceptance criteria - On completion, each drainage line shall be free from dirt, debris, or other impediments.
button | f8f60be0-c323-5c46-a54a-6ac03f60c894 |  | button | Acceptance | Yes,No,N/A
label | abbcf80c-0048-576a-a506-9a0103f6fb45 |  | note | Resp - SE
label | 9dba6916-4f05-52d6-9499-734dfb5297f9 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 37b00dc9-bbce-5ab6-a16f-83f9b4ef9d34 |  | tickbox | CCTV Report
checkpoint-status |  |  | checkpoint | 5.2 - Visual Inspection
label | 29c01485-6fca-51bd-b002-3ac38970fa99 |  | note | Acceptance criteria - Do not cover or conceal work until it has been tested. Leave pipe joints exposed to enable witness testing.
button | 67962751-932c-5529-8fc8-22fbbe40e982 |  | button | Acceptance | Yes,No,N/A
label | ecafd4b6-93dd-52e3-8bd4-8f083bb6bf99 |  | note | Key - H
label | 6192e688-fdc9-5d61-85d1-bc45807b96f0 |  | note | Resp - SE
checklist-sectioned |  |  | checklist | CC0394 - ITP-001 - Sediment Control | itp |  |  |  | Yes | CC0394 - ITP-001 - Sediment Control REV0 | 9ad8e190-1c9b-456d-9dd2-f3fc6d871ac8
checkpoint-group |  |  | section | Lot Conformance.
checkpoint-status |  |  | checkpoint | Works complete
text | 5117c05a-6360-5e38-98bb-a68a4e13d42d |  | textbox | Name:
text | c2f0a65a-2cfa-5b28-9801-79aa246cfaf4 |  | textbox | Position:
text | 6f0010f8-9780-5aa1-9cda-863dbdc1e769 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | 10463669-2aff-5e12-a399-e0a2a253364c |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | 4d46bc31-ee7b-51d9-b3f2-bff980f39401 |  | textbox | Lot opened date:
text | 6e4fbbac-129e-50cf-9043-df6f6e140d2b |  | textbox | Lot opened by:
text | 71b01ddd-7cfc-5020-bfd9-2a1da5f9d1d3 |  | textbox | Date lot closed:
button | 23301aab-6adb-5a1a-9e0c-b750432f1071 |  | button | NCR raised? | Yes, No
text | ee2b251a-6046-5605-baf5-3f2c62cd471a |  | textbox | NCR Raised Date:
button | f5d28682-d929-5c8d-8499-3a6fc4777f48 |  | button | NCR closed? | Yes, No
text | 75cfec9f-4aa2-50d2-a086-1d11d2f8ca2a |  | textbox | NCR Closed Date:
text | 742dee44-aab5-5ba7-a9e8-b5bdd6b72e0c |  | textbox | NCR Number:
text | 55bd180b-eb82-50b5-9a54-5b41fd9ccf14 |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-status |  |  | checkpoint | 1.1 - Safety
label | f9bca9f9-7118-5a51-a27e-e35417654545 |  | note | Ensure that the following items have been actioned:
label | 1fd6fe21-5f49-589e-9503-875f7c938b50 |  | note | – SWMS if applicable
label | f8998f38-2cf4-559d-be33-7dc5e6425f25 |  | note | – Plant Pre-start Inspection
label | 6cfaa091-6367-5052-924a-98bb03ecc920 |  | note | – Service locations identified
label | f6527eb9-bed7-56dd-b94e-4f3c08e45ac9 |  | note | – Traffic Management Plans (if req’d)
label | e89df8c0-9490-59b8-b879-48bc7f498366 |  | note | – All staff inducted
label | 12319051-2617-517f-8cea-ed46cd5fc532 |  | note | Ref docs - SMP
label | dfe0e5ae-7fde-5c70-97c6-07a7cb5335e6 |  | note | Acceptance criteria - SWMS submitted reviewed and accepted if required.
label | 6523fdac-ac9d-5c0e-8293-cb210dd29e7a |  | note | • Personnel inducted to RJE requirements.
label | 339e8748-27b5-58f6-b25d-81ac43417c12 |  | note | • Plant inspections completed and entered.
label | 56aab71f-cc42-5a01-9c6c-6749308a7835 |  | note | • Pre-work briefings completed.
label | f91e950a-c9b3-57d3-ab49-110ce5edf75c |  | note | • Service Diagrams available and services located.
label | 264da3d5-4d18-5405-930a-f9d245e7d9b8 |  | note | Freq - Once (Pre-Start)
label | fff8e3fa-afb8-5207-8904-415fef679b5a |  | note | Key - H
label | ae58cf2d-3d22-56fe-8dd3-35ba07334028 |  | note | Resp - SS
label | e05a528d-ef3b-5a3a-968e-824c5a350e12 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 1.2 - Excavation Permit
label | cfd1fc89-6da9-54ce-b796-db228c377395 |  | note | Ref docs - SMP
label | 8713dacb-9f75-5278-9801-0cb17a5d5cfe |  | note | Acceptance criteria - All identified underground services marked and potholed to confirm location and depth. No machine excavation within 1m of underground services. Permit available and signed.
label | d84f2043-9d4f-5208-b91d-f821af09d311 |  | note | Freq - Prior to start of works
label | 9e9b6238-c175-5dcb-864f-22e50210c3bb |  | note | Key - H
label | 811a982b-7297-580b-9907-5b575645dbac |  | note | Resp - SS
label | 4492eb3b-eccb-5d96-a609-3195531732a9 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 1.3 - Check Survey Set-out
label | ea688e28-f374-544f-a41e-1186e06a889f |  | note | Ref docs - Drawing: 5668-122-1010
label | bd82d330-a493-5aeb-a061-5a0437bd3194 |  | note | Acceptance criteria - Survey Setout extend of works
label | 39f8fbba-a75c-55e3-861b-46cf82636815 |  | note | Freq - Prior to start of Works
label | f8f37293-4526-5ece-a9c3-4b861be263a6 |  | note | Key - H
label | 42760802-fdda-5b00-aeeb-fd11f4f12c07 |  | note | Resp - SV, SS
label | db4c33db-adce-51f3-814b-3bfcad673fef |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 1.4 - Material Specifications Checked and Conforming
label | 39254633-a66e-5d54-91b4-ad427af0cc90 |  | note | Ref docs - RFI Approval
label | 98e79747-02b4-5773-aacb-38474c217162 |  | note | Acceptance criteria - RJE approval of sediment fence material
label | 26685af7-cc14-5d30-b894-9c3a7a121936 |  | note | Freq - Prior to start of Works
label | 502b9014-4c5d-5b9e-a7f3-7d56f2cd684e |  | note | Key - H
label | fa9c4bb1-2514-5d32-8973-fe82cdb60cd0 |  | note | Resp - SE
label | a1e98db5-4da9-518b-a988-cccd29fd66c3 |  | note | RJE Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Install works
checkpoint-status |  |  | checkpoint | 2.1 - Sediment Fence Install
label | dcb71f1f-9bfd-54d3-82a1-23361b2c667b |  | note | Ref docs - Drawing: 5668-122-1010
label | 84763a54-c76f-520b-9a18-992c974e61c1 |  | note | Acceptance criteria - Correct fence material is onsite, Stakes installed at 2000mm spacing, silt fence buried at least 200mm into soil, Fence secured to stakes using appropriate fixtures.
label | 7b7b76fe-cc5c-50cf-8d09-08631b3fcb5d |  | note | Freq - On delivery and installation
label | 0f04efa5-01dc-5f93-9615-fcdfd83a4976 |  | note | Key - H
label | 188bbb49-efa8-534b-ba86-676815ec4c37 |  | note | Resp - SS
label | b0f8977a-4903-5ebc-9c05-bb722801ac6e |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 2.2 - Temporary swale & earth bund construction
label | 2c405fa0-70fe-591b-ba2d-c38a99d8158b |  | note | Ref docs - Drawing: 5668-122-1010
label | f3d43bb8-33df-5dca-abde-af87d2331b71 |  | note | Acceptance criteria - Construction conforms with IFC drawings unless approved otherwise.
label | ed725695-435d-5c44-8371-e84468f28e42 |  | note | Freq - On delivery and installation
label | bd013305-b051-5294-99e5-0fc6d27e06fb |  | note | Key - S
label | 97b03830-1850-5686-bc29-b8ba4d5d856b |  | note | Resp - SS, SE
label | 3dfd7a1d-f28c-57d0-9f3d-ac0df3536bb7 |  | note | RJE Key - S
checkpoint-group |  |  | section | 3.0 Conformance check
checkpoint-status |  |  | checkpoint | 3.1 - Carry out corrections and clean-up
label | 25dc2631-36c6-5e24-b636-f298f635293e |  | note | Acceptance criteria - Area clear of debris, silt fence is sturdy and intact, earth bund and swale sediment controls working as intended – efficiently carries water where required, prevents silt run-off and erosion.
label | 166c06b5-f27b-5d6c-81e7-93d51ac92504 |  | note | Freq - Visual Inspection once complete
label | 9d1b80c0-7043-53b3-9a86-805854b39b94 |  | note | Key - W
label | 3aa78827-30e5-56b7-86e8-6cc2bf2362cc |  | note | Resp - CR
label | feb250f7-ca92-57e9-9b12-61bca9dbab25 |  | note | RJE Key - W
checklist-sectioned |  |  | checklist | CC0394 - ITP-005 - Crushed Rock Pavement Construction | itp |  |  |  | Yes | CC0394 - ITP-005 - Crushed Rock Pavement Construction REV0 | a0980a32-1eec-4a03-b12e-496e72e0dce7
checkpoint-group |  |  | section | Lot Conformance.
checkpoint-status |  |  | checkpoint | Works complete
text | 35887d7c-2def-5fba-ad7c-81311119294a |  | textbox | Name:
text | 71fb8346-dfa2-5425-a684-73e52e0597f2 |  | textbox | Position:
text | 4c75dafa-a8bb-52c1-b3b5-e89501940f84 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | b9865121-e4f8-5e59-8e0a-193a7978756a |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | 88aa7814-aed0-5d14-bcfe-e6f74dedbc37 |  | textbox | Lot opened date:
text | 8e6ffaf1-85bf-5b1c-b84a-b35ebcfebc81 |  | textbox | Lot opened by:
text | e5d25978-9c3a-5476-9781-e245bff7dde7 |  | textbox | Date lot closed:
button | 90ae7f38-9d50-520b-8798-18e084030f74 |  | button | NCR raised? | Yes, No
text | 14cc4f2a-83a8-57d1-922d-d154a96eb9a1 |  | textbox | NCR Raised Date:
button | 583fc6ca-fdcc-545c-8ce0-7a3fb7dcb3a7 |  | button | NCR closed? | Yes, No
text | 7628b56f-38d1-5d5d-bccd-ecda12f543af |  | textbox | NCR Closed Date:
text | 4a29aac2-af10-56a7-aee1-958a222252e6 |  | textbox | NCR Number:
text | c0d92b73-d57a-56d6-b786-6c803ae41427 |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP
checkpoint-group |  |  | section | 1.0
checkpoint-status |  |  | checkpoint | 1.1 - Determine Lot Size
label | cdf6cd5d-55eb-5d54-a025-a48114e5f52e |  | note | Acceptance criteria - What is the lot size?
text | 709b9433-edf6-5bc5-8f3c-ad4b1242f6b4 |  | textbox | Acceptance |  |  | m2
label | 94195851-fa51-5d80-8569-704d1a9aeec2 |  | note | • Maximum lot size = See pre-approved lot maps
label | 44e1c993-9d8a-5513-b4b4-ceb00636875a |  | note | Resp - SE
label | ea3921d0-44e9-5173-b908-a787e74be51b |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 128ec6c1-f3ec-5f36-be31-87fb09ad371a |  | tickbox | Work Lot Map
checkpoint-status |  |  | checkpoint | 1.2 - Survey Set-out
label | a665881f-3d33-5655-9cb3-5cd40133189d |  | note | Ref docs - IFC Drawings
label | dbbc7c1d-4abc-572c-bd87-e358835abad3 |  | note | Acceptance criteria - Has the work area been set out for line and level?
button | 695bd86e-12a1-5fc2-ad2e-9831077e3120 |  | button | Acceptance | Yes,No,N/A
label | e85ddfae-5e1e-5649-bb28-220c7671d607 |  | note | Key - W
label | e21fe9bf-c453-5218-9290-163d0005d3fc |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.3 - Material Classification & Source
label | b90b17c5-c938-504b-858f-958b6b3ee56c |  | note | Ref docs - IFC Drawings
label | 008491aa-d615-5d87-9650-3b754c95f04d |  | note | Acceptance criteria - Is the correct material being used?
button | c97ad939-9caf-5273-ad08-fe26fd30cbf1 |  | button | Acceptance | Yes,No,N/A
label | c3baa1a7-7015-529b-af4c-a2b40e103d0a |  | note | Please tick appropriate Box:
boolean | 9df9dd85-f06f-5b17-a78f-3dbf5b734a26 |  | tickbox | Site Won
boolean | aedb946a-847c-5a06-9cf3-18f4ba542d32 |  | tickbox | 20mm Class 2
boolean | f0039bd3-6656-5f7f-b165-4a61f5c89409 |  | tickbox | 20mm Class 3
boolean | 03821815-54e0-5be1-8250-d818f656cca2 |  | tickbox | 20mm Class 4
text | 7e52d1ac-955b-54fb-84e1-38246021e4d5 |  | textbox | Other
label | 7e3cf997-3b70-5f57-a9d5-ed9883e1b1ea |  | note | Key - H
label | 77f1e18b-bd79-5fc2-b275-6763b0c2b116 |  | note | Resp - SE
checkpoint-group |  |  | section | 2.0
checkpoint-status |  |  | checkpoint | 2.1 - Conformance of Previous Layer
label | 990cfbed-91b4-5099-8c00-399b09f93777 |  | note | Ref docs - IFC Drawings
label | d784cbce-dd68-5cb0-a867-d36e6e37a4e1 |  | note | Acceptance criteria - Has the previous layer passed acceptance criteria?
button | 075347a9-5acf-5739-b6d9-9456c77f6b43 |  | button | Acceptance | Yes,No,N/A
label | 32e4286a-589a-53ba-81c1-65ea5d5d577a |  | note | Key - W
label | b204799c-53da-5a6b-b902-90291f80c51d |  | note | Resp - SE
label | 0e74f50a-4504-5654-abef-7576e9ef74c0 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 9a7d7f44-03cc-5c09-b175-e2874035aebe |  | tickbox | Refer to ITP for previous layer
checkpoint-group |  |  | section | 3.0
checkpoint-status |  |  | checkpoint | 3.1 - Placement
label | df57071a-8818-59df-b216-dbe29735040b |  | note | Ref docs - IFC Drawings
label | e300ad99-0943-5e18-9628-ae6d4f3d6f5d |  | note | Acceptance criteria - Has the fill been placed in a maximum compacted layer as outlined below?
label | 8c005233-6347-56ab-8dfe-975b78840386 |  | note | • Maximum Layer Depth: 200mm
button | d1d25de0-4a39-5635-8dc4-2a097ab3eb87 |  | button | Acceptance | Yes,No,N/A
label | a0f967f6-105d-56e7-ba97-8167b419068e |  | note | Key - S
label | cb95eede-bd62-5f34-b56c-ed8f8f4ef53b |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.2 - Moisture
label | f62defce-a951-5e05-8388-9bf876649af4 |  | note | Ref docs - IFC Drawings
label | 3d7eeb1e-7241-54a1-8b73-aef8bedff322 |  | note | Acceptance criteria - Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction?
button | 71f44e5a-eb29-5b48-8078-502c771c205f |  | button | Acceptance | Yes,No,N/A
label | 2748664d-5688-508c-8baa-4e6c357080d2 |  | note | Key - S
label | f9e98a1c-9c71-5ee0-add7-22351e084e76 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.3 - Compaction
label | b00fc3fe-21e6-5b19-816e-5aaea1356c25 |  | note | Ref docs - IFC Drawings Civil Specification
label | f2274e02-2355-59f7-86ed-8fb7c6e90703 |  | note | Acceptance criteria - Has the layer been adequately compacted achieving a mean value density ratio of:
label | ed88c015-6dd2-5be9-bfea-5a759ac3a9b7 |  | note | • Lower Subbase: 98% Std
label | 35b6f60a-0d0c-59a5-a700-36350c61ad7c |  | note | • Upper Subbase: 95% Mod
label | d06ac943-06d6-52ec-a38d-29b16deae856 |  | note | • 3 x tests to be conducted per compacted layer per approved lot map.
button | 17753ba1-49e8-50fd-a569-ebaf1cf0721d |  | button | Acceptance | Yes,No,N/A
label | f4acfd7b-b677-5f20-958f-b2f7d6589f6b |  | note | Key - W
label | 79cd9298-e759-525e-8bff-cc2a31c196fc |  | note | Resp - SE
label | 53d2fdd7-b5ff-543a-b39d-523e12e0ad34 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 5c72fa10-f344-5776-865a-fd6524e4494f |  | tickbox | Compaction test results
checkpoint-status |  |  | checkpoint | 3.4 - Test Rolling
label | 176159a5-664d-53f2-bc86-5d7018d39126 |  | note | Ref docs - IFC Drawings
label | 3ffcfccb-6777-5870-bfc4-9ca01af1fb14 |  | note | Acceptance criteria - Does the layer withstand test rolling without visible deformation of springing?
text | ac6863c8-1510-5283-b878-be18f149d5ef |  | textbox | List attendees:
button | 5f0b76e1-0fc4-524a-af31-e1a95c79abc3 |  | button | Acceptance | Yes,No,N/A
label | 9bf66fd0-0a9e-5133-9f78-822ab8ba767e |  | note | • If ‘no’, please see sections 3.5 and 3.6.
label | 45505644-99ff-54dc-96c2-1750aad7370f |  | note | • If ‘yes’, proceed to section 4.0.
label | c11841a9-4889-557d-bdef-4fbf0c827ebe |  | note | Key - H
label | bd683620-bc2f-597c-aae2-c7f5cdcc6b6b |  | note | Resp - SE
label | e90c588b-0790-554a-bd1a-2318a1a5fc7f |  | note | RJE Key - W
checkpoint-status |  |  | checkpoint | 3.5 - Identification of soft, wet or unstable material
label | 63bfcd15-a562-5ea0-a660-80143c98f6c1 |  | note | Acceptance criteria - What quantity of soft, wet or unstable material is present?
text | 41160065-0334-5464-b4d0-9b7ba190a902 |  | textbox | Acceptance |  |  | m
label | 516247a6-cbee-542a-85ee-b1fda4c75748 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 3.6 - Treatment of unsuitable material
label | 629d7526-07fe-5223-9177-247204687c9e |  | note | Acceptance criteria - Has rectification process been submitted for review?
label | ff9cbc4f-662b-5e0b-a464-300ec55ef1c4 |  | note | • What was the rectification process used?
button | 3280043d-6e76-55cd-a786-e3f75dbed375 |  | button | Acceptance | Yes,No,N/A
text | d9d71016-bff1-546e-b608-7fafb9355468 |  | textbox | Process Used:
label | 97268a5e-91e6-5423-9b45-b279672887e5 |  | note | Resp - SE
checkpoint-group |  |  | section | 4.0
checkpoint-status |  |  | checkpoint | 4.1 - Pavement Finish
label | 5a78741d-ae8c-58d3-8700-cb16d962429c |  | note | Acceptance criteria - Has the pavement course been finished to a smooth and uniform surface?
button | 3f24f1aa-be3f-5b9b-9ab9-d4c492ebeffd |  | button | Acceptance | Yes,No,N/A
label | 54c29084-a42e-59e3-afe2-e1e1f89ecf92 |  | note | Key - W
label | 7980d070-218c-5a91-a466-fcc6f4f5dc89 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 4.2 - Width & Alignment
label | 0e228b1b-6a7a-5d93-b6dc-2a7934eae341 |  | note | Acceptance criteria - Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
button | 933b2f40-855c-54c7-8158-3e528ed2761e |  | button | Acceptance | Yes,No,N/A
label | 0c9d7578-8148-56ba-a84c-aaefcaf5f19e |  | note | Key - W
label | edf75990-3ac6-554e-b973-aa8f24d78c59 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 4.3 - Surface Level of Pavement Courses
label | 7920e365-1665-5d36-8c2a-a44195d1477f |  | note | Acceptance criteria - Has the prepared layer been surveyed in accordance with and verifying specified requirements?
label | d342d55e-89ec-5518-a7cc-d0aa63252e84 |  | note | All crushed rock layers:
label | c238dd2b-2aa9-5296-942b-c97ee4508041 |  | note | • Mean Range: +10mm to -10mm
button | 232abf2d-3652-5a97-bdef-2064e47368c0 |  | button | Acceptance | Yes,No,N/A
label | bdcfd733-1704-5b64-92b7-e6c4856e9417 |  | note | Key - H
label | c8000161-a8a8-5cab-b69d-dcc3ecdf1e6f |  | note | Resp - SE
label | 448089fd-716a-585f-a338-f9acd7a9df0c |  | note | RJE Key - H
label | 98c472a2-b726-5b8f-ba88-116cc70c45b6 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 94f4d4de-c80b-5608-928f-be913980e2d5 |  | tickbox | As-Built Reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | CC0394 - ITP-011 - Kerb | itp |  |  |  | Yes | CC0394 - ITP-011 - Kerb REV0 | aaf6b5a9-e813-421c-ae01-16979d3d97b5
checkpoint-group |  |  | section | Lot Conformance.
checkpoint-status |  |  | checkpoint | Works complete
text | 218666c2-27ba-502e-9cad-2c3bad812763 |  | textbox | Name:
text | 33008354-9542-54d8-8706-063820a39c07 |  | textbox | Position:
text | 4c5c8cf6-caa0-5fe4-b6bf-4ce7a42d07a6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | 0b9e7f7a-cca3-56e5-96a6-822791e336dd |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | 7c6af287-160e-5f24-84cf-37df0eb53e33 |  | textbox | Lot opened date:
text | 087e658e-a5d9-5b2f-8273-f003536350d2 |  | textbox | Lot opened by:
text | ec8b895b-683c-5b4d-be73-241bf6f9d384 |  | textbox | Date lot closed:
button | 5bee4182-0dc8-5aa9-b207-d54e0de95be4 |  | button | NCR raised? | Yes, No
text | c241be9e-e369-549a-92e6-af82a2b287fb |  | textbox | NCR Raised Date:
button | ce9c905e-6130-571a-806e-79e49567cdaa |  | button | NCR closed? | Yes, No
text | 80b08690-a1a8-5865-bed9-50cad3861bfa |  | textbox | NCR Closed Date:
text | 480bb26f-0ccb-52f1-b9b4-0b72112f52fb |  | textbox | NCR Number:
text | 2bd8c049-5c3f-5e2c-b1ee-81b99d6f20f6 |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP
checkpoint-group |  |  | section | 1.0
checkpoint-status |  |  | checkpoint | 1.1 - Survey Set-out
label | 0ae6d879-0ae1-5286-81bb-b2a75801a83a |  | note | Ref docs - IFC Drawings
label | 35863936-8604-5e6b-8120-4845cb85e794 |  | note | Acceptance criteria - Prior to the commencement of works, the contractor shall engage a suitably qualified surveyor to set out the works and clearly mark its limits.
button | 36c858ab-3aef-5d22-a709-2119c76a191e |  | button | Acceptance | Yes,No,N/A
label | abc86fe8-48cc-524d-8214-9cb8f8a3ab46 |  | note | Key - W
label | 927beacf-0c07-518d-ada5-7ce49d6ca835 |  | note | Resp - SE
label | c9957923-1178-591a-a41a-e29da33ed7e8 |  | note | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.) -
boolean | 26078f25-9f57-55ba-b62d-0e525c4aaeea |  | tickbox | Work Lot Map
checkpoint-status |  |  | checkpoint | 1.2 - Approved Material Type
label | 49c41681-404a-56dd-bba4-6ca212f9df95 |  | note | Ref docs - IFC Drawings
label | 4481e486-9152-53d5-ad78-9d7bced254cc |  | note | Acceptance criteria -
label | 03142c48-01bb-515d-9af0-9fbb6e3dbc3f |  | note | Acceptance
text | 3b4af81c-52ce-5c6e-8e6f-fbbdf7c07a1d |  | textbox | Approved kerb mix:
label | 5d1bd4e7-9dcc-5c4e-a64f-11eac0d74552 |  | note | Key - H
label | 7633aa1c-2594-584f-b1f5-040956ecccba |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.3 - Preparation of Bedding
label | 53c2c47e-355d-59e6-81e6-b7556041d397 |  | note | Ref docs - AS2876
label | 13b31c32-eec0-5c9c-b7dc-92f29c542613 |  | note | Acceptance criteria - Where kerb is constructed over pavement layers, bedding shall be provided between the pavement layer & the underside of the edging, or the edging thickened to match the pavement layer.
label | 2ee6adde-c78c-5f37-8ab0-e3f0ee19ec8e |  | note | • Where edgings are not constructed over pavement layers, bedding shall be greater than 100mm compacted thickness.
button | d051ef3c-824b-5a51-8f20-8d66e5f3702b |  | button | Acceptance | Yes,No,N/A
label | db75f9f2-6612-5071-9bea-dc20ada939aa |  | note | Key - S
label | 013933fc-6ec8-598a-bcf2-d2297410e03b |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.4 - Air Temperature
label | 2630eaa2-e72a-5bad-a028-b819a8e1f9e9 |  | note | Ref docs - AS2876
label | e96201d9-3214-573a-b891-05563b986953 |  | note | Acceptance criteria - Concrete shall not be mixed when the temperature is lower than 5⁰C or greater than 35⁰C.
button | 06096772-3cf5-5619-8b6e-9886b1161e25 |  | button | Acceptance | Yes,No,N/A
label | 789c82ec-323f-5dc3-9d10-e9399cb36e15 |  | note | Key - S
label | dad0a39e-2262-5362-b56d-b3e5bd075ca2 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.5 - Concrete Placement
label | de757d1f-7d44-5c3e-a712-e62b6e281d59 |  | note | Ref docs - AS3610 AS2876
label | 6b6ab994-342e-554e-9b12-f99916d6c1b2 |  | note | Acceptance criteria - Concrete shall be thoroughly compacted by means of continuous tamping & internal vibration shall be worked around any embedment’s & into corners of formwork to produce a dense concrete free from voids, honeycombing, segregation, or surface defects.
label | 1d13dab3-b156-54c9-b6a5-f5b5a44b37a1 |  | note | • Concrete shall be finished to ensure a smooth surface with a uniform colour & appearance, & screeded to achieve the specified level, dimensions, falls & tolerances.
button | 7e7d8020-1cdc-5608-a3e1-d9dc919d9060 |  | button | Acceptance | Yes,No,N/A
label | 500df396-f791-52d5-b810-b7c9b8466110 |  | note | Key - S
label | bc0f26c2-5584-520b-b0bf-e7d4c3e7ab8c |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.6 - Joints
label | 993425b7-1371-5c9c-b201-cd825ec9c568 |  | note | Ref docs - AS3610 AS2876
label | 54fb89f2-8687-592c-a7e6-7d54e1bee095 |  | note | Acceptance criteria - Transverse joints shall be constructed at regular intervals not exceeding 3m. For extruded edgings this shall be done by a method which does not damage or distort the adjacent surfaces.
label | 7a7c17c0-c366-5aca-bad3-5f06373d793a |  | note | • 6mm saw cut joints within 24-72hrs post pour
label | 1cef008c-e77f-5762-b01e-bfb76c29c4cb |  | note | • Sikaflex polyurethane joint sealant or equivalent used to fill saw cuts.
button | 605f3fe8-313a-5dd0-9d21-acc787dc4597 |  | button | Acceptance | Yes,No,N/A
label | 36636ede-8f00-5a5d-84b9-bb643e6de99b |  | note | Key - S
label | ebf13f6b-3fe9-54cc-ad52-1c97b2029869 |  | note | Resp - SE
checkpoint-status |  |  | checkpoint | 1.7 - Completion of Works
label | 6e926377-d864-594d-a0af-e92f657e695b |  | note | Ref docs - IFC Drawings
label | 3cd62c15-f223-52c4-a389-236adca77f9a |  | note | Acceptance criteria - Correct kerb type installed as per IFC drawings.
label | c0d83e38-00b9-58f5-94e9-ffb9bc10c719 |  | note | • Line & level confirmed at time of pour.
button | ee7821e4-6360-5c7b-b186-129b1cebde04 |  | button | Acceptance | Yes,No,N/A
label | 1f22de03-75b1-5a57-9d73-e762c0fe8f12 |  | note | Key - H
label | 3956a781-879e-5070-beeb-1a0cf2d048e3 |  | note | Resp - SE
checklist-sectioned |  |  | checklist | CC0394 - ITP-003 - Bulk Earthworks | itp |  |  |  | Yes | CC0394 - ITP-003 - Bulk Earthworks REV0 | b2979dc7-a128-4cf0-a511-df61e1ba705a
checkpoint-group |  |  | section | Lot Conformance.
checkpoint-status |  |  | checkpoint | Works complete
text | 05c5ccfa-d70d-5a1d-bd08-f05c6b01698e |  | textbox | Name:
text | 9a1ca718-9c9a-5633-bd97-cb987002c746 |  | textbox | Position:
text | 70dfd82f-f44b-599c-865e-04a036f02387 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Lot Conformance
select | de469245-1a63-53c5-8b23-a581d562d93e |  | dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | 9c773193-0503-5cb8-a950-67cca4073a24 |  | textbox | Lot opened date:
text | 5d24f461-6870-51b1-bd21-7566c2079fad |  | textbox | Lot opened by:
text | c04cfb9c-8309-5589-a355-042b58d35a25 |  | textbox | Date lot closed:
button | d7cfb689-976c-59a5-bb48-f761e11d1550 |  | button | NCR raised? | Yes, No
text | 956d73d6-920e-5a04-8987-89dfa31dfd71 |  | textbox | NCR Raised Date:
button | 12a5ba4f-7b01-588a-affc-c76156f9d7c1 |  | button | NCR closed? | Yes, No
text | b10f7c01-7868-5093-9e9d-5aaa7bdf35f8 |  | textbox | NCR Closed Date:
text | e74ad5c7-e502-51e3-adc0-d1f78d624735 |  | textbox | NCR Number:
text | 8250a958-97dc-5dd0-8315-12863f057b98 |  | textbox | Comments
holdpoint |  |  | signoff | Sign ITP
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | 1.1 - Determine lot size
label | fb388d28-7666-5ea8-bf4a-84673ee2c930 |  | note | Acceptance criteria - What is the lot size?
text | 33d7c741-a575-546e-a4c0-69012298a3d5 |  | textbox | Acceptance |  |  | m2
checkpoint-status |  |  | checkpoint | 1.2 - Survey set-out
label | 95ff886e-776c-5af4-b6a5-054b76a0769c |  | note | Ref docs - Construction drawings
label | 2a6ab22a-7304-59b9-9098-0ed7b74485af |  | note | Acceptance criteria - Has the work area been set out for line and level?
button | fb9cdc2d-770a-58b4-9379-9ded8a44af49 |  | button | Acceptance | Yes,No,N/A
label | f90c0889-fb53-55b2-acee-b6d29f2e35e9 |  | note | Key - W
label | a31dd83c-5274-5ac7-af76-a565a17447e1 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 1.3 - Excavation material classification
label | 93a2baf5-ed2a-542e-896d-344fa418c16c |  | note | Acceptance criteria - Has the material being excavated been inspected with category agreed upon by Superintendent?
label | eda3fdee-b433-546c-b63d-73d1860cea40 |  | note | • Tick category below:
boolean | ac1e8497-b27c-5374-b8b9-911637468e2c |  | tickbox | Topsoil
boolean | 632d957f-096a-5f79-bcf0-7dad1053c3eb |  | tickbox | Unsuitable material
boolean | 0ae96207-2c2a-5360-bc9d-a9035212ac7a |  | tickbox | Fill material
button | 9c2a6eac-3d8c-5bc3-956b-6809a1a42d5e |  | button | Acceptance | Yes,No,N/A
label | 054ba449-2a7d-5eea-b70f-b280aa4928ee |  | note | Key - H
label | f06e8884-9e67-5ebc-9181-0d6a4e2183d2 |  | note | RJE Key - W
checkpoint-status |  |  | checkpoint | 1.4 - Fill material classification
label | 2dab8dce-66d6-56f2-8e6b-57335bfff03d |  | note | Acceptance criteria - Has the material to be used been approved for use?
button | 27b7a221-e70f-5e38-863a-598d4496ab45 |  | button | Acceptance | Yes,No,N/A
text | 9aaf69b8-c16d-5062-b43d-d25b1c2832c2 |  | textbox | Material Type
label | b1fc097b-8944-51c8-af99-c14cfe163992 |  | note | Key - H
label | 77549292-7e26-5c23-ba86-d7a4b1445854 |  | note | RJE Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Water management
label | 61118c7a-284c-5751-9ee3-faeb5e5afa50 |  | note | Acceptance criteria - Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation?
button | 2d8dc848-5ecf-5c87-9df1-36bfe9c44c64 |  | button | Acceptance | Yes,No,N/A
label | 54a1e2a8-3a8e-5fc0-94cf-c7326511c756 |  | note | Key - S
label | 3d1765b5-378e-5ce1-9ef4-55a6ef1999e4 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 1.6 - Clearing
label | e35b41a3-94a5-5e05-bed8-b73d36d9d771 |  | note | Ref docs - CC0394 - ITP-002
label | 495900d6-61d0-54b3-b0ad-e814439e9c0d |  | note | Acceptance criteria - Has the area been cleared and grubbed in accordance with ITP-002?
button | 5f42f77b-1514-59ef-b099-558adc4d0233 |  | button | Acceptance | Yes,No,N/A
label | 5217ad84-3f6a-5db6-8cdb-d52d47936476 |  | note | Key - H
label | 320eebf5-bd19-5ad8-8fce-8a26c02dae61 |  | note | RJE Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Bulk earthworks – cut
checkpoint-status |  |  | checkpoint | 2.1 - Subgrade protection
label | dd5c5c33-bcb8-5c71-b132-f9cf1d5aa1b6 |  | note | Acceptance criteria - Have external factors such as weather and construction activities been considered to ensure excavations will be protected from water, erosion, deterioration and excessive drying or wetting?
button | 04c4a480-54f2-50c9-ac00-363df9945a41 |  | button | Acceptance | Yes,No,N/A
label | 6045fc1b-b9ee-56d8-a738-ec68d05ce424 |  | note | Key - S
label | 77bb54fb-fad8-5340-b3c9-8036ee82c1c2 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 2.2 - Subgrade preparation
label | 1182f4e8-5ba0-5f7e-8711-293ef3d5452f |  | note | Ref docs - Construction Drawings
label | 122ffe19-3616-5051-9894-10f610a61f3e |  | note | Acceptance criteria - Has the cut surface been trimmed to an even surface free from lose material?
label | 2eaaeb30-b4d7-5cba-828d-2c41a20d32b8 |  | note | • Have surface levels been checked to avoid over excavation?
button | 2196fecc-00c4-5fdc-b369-451e54173ef8 |  | button | Acceptance | Yes,No,N/A
label | 709ac405-d282-5f1b-a657-a9a1a2c2dc55 |  | note | Key - S
label | cf7076b2-dfe6-5dd9-b4f4-aa667f554344 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 2.3 - Lime mix
label | 60ece475-2cb6-5b89-8f68-7510db3d4813 |  | note | Ref docs - Construction Drawings
label | 9a98d775-1def-53d9-af6a-7f69d326e066 |  | note | Acceptance criteria - Has mix design been completed and submitted?
label | 0daf7e6f-477e-5f8a-87e2-07385c89fff2 |  | note | • Have Lime spreading rates been submitted to RJE?
button | 3069b7f4-d8e1-5f93-8529-204bcc7c4439 |  | button | Acceptance | Yes,No,N/A
label | 2f0c26c5-031a-51c6-908c-030cb88afe7a |  | note | Key - H
label | 3c66828e-710f-5aa7-bdd8-3dc6f3754127 |  | note | RJE Key - H
label | 7ea0738d-b524-5436-8ba5-719feb240310 |  | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | c33a26e4-e887-5344-bea1-47d0304d2b84 |  | tickbox | Test reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Trial site
label | bcfb821c-dc53-5256-92d9-efefe815208b |  | note | Acceptance criteria - Has trial site been established and confirmed?
button | 0029b5b6-42e4-5e84-9c73-21eab4134801 |  | button | Acceptance | Yes,No,N/A
label | 6b1574d2-aac2-5dfd-89a1-041765e95c6a |  | note | Key - H
label | 1aab58b7-f87b-5e86-a720-44d9b26db54d |  | note | RJE Key - W
checkpoint-status |  |  | checkpoint | 2.5 - Lime stabilisation
label | 20c2f40d-3df7-5a33-80db-9fc374e1fa31 |  | note | Ref docs - Construction Drawings
label | c6e80a95-a633-52bc-a76e-abfd4e8242da |  | note | Acceptance criteria - Has the prepared subgrade been lime stabilised as per the IFC design?
button | 591eb1f9-c454-5bdf-abd4-0025b31046ee |  | button | Acceptance | Yes,No,N/A
label | 1e732640-4927-5798-9b71-b5dc07c62d14 |  | note | Key - S
label | b1f61fa3-3c17-5da7-b69b-112a29ac70e2 |  | note | RJE Key - W
checkpoint-status |  |  | checkpoint | 2.6 - Compaction
label | 49a10cf9-a45d-5c2d-a3b8-9cec53e029c5 |  | note | Acceptance criteria - Compaction Scale: 3 tests per lot. See RJE approved lots:
label | 06813a79-dad5-5ca4-be9c-ec079c966ccc |  | note | • Combi Slab: 1, 2, 3, 4, 5
label | 6015367c-28c0-5759-a04d-cc3745f7a7de |  | note | • Temporary compound: Lot 1 & 2
label | ad036a08-2769-503a-bf62-e1b1ed6c911f |  | note | • Has the stabilised subgrade been adequately compacted achieving 98% SMDD / 95% MMDD (in-situ materials or subgrade preparation), or 75% density index for the in-situ and fill materials. Using a nuclear density gauge.
label | e5bd0e70-fe09-5016-9797-e9af3fa05c0f |  | note | • Is the subgrade material with 2% of the optimum moisture content.
label | bc3cbaa7-5926-5ec8-aa24-9b1428350ac0 |  | note | • Is the subgrade within +/- 20mm of design surface?
button | 3c4b32df-bb34-561a-8985-8e107f4e5561 |  | button | Acceptance | Yes,No,N/A
label | c15693e0-d380-51a4-baa6-bf7643b3fe5c |  | note | Key - W
label | 1c4540de-de24-5046-927b-edb9054e5c26 |  | note | RJE Key - S
label | 1b8646bb-9695-5d22-81a8-f00eac281a2c |  | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | 0e5ddb6c-e530-5e14-a908-bab7241dd957 |  | tickbox | Test reports
checkpoint-status |  |  | checkpoint | 2.7 - Test Rolling
label | bea36602-3020-527a-bd8b-3bf5f9751d47 |  | note | Acceptance criteria - Does the layer withstand test rolling without visible deformation or springing?
text | 57c9e4db-b594-58ff-adf5-409eb0481eb2 |  | textbox | List Attendees:
button | ec998bbc-4d6b-5fe5-b421-000ea57f6867 |  | button | Acceptance | Yes,No,N/A
label | 914cf06c-16d0-5737-a0f7-9aa36edf0897 |  | note | • If ‘no’ please see below.
label | 40c04d0d-55b4-5337-9656-42b03b357d6a |  | note | • If ‘yes’ please proceed
label | 0653628b-2eac-540f-97f9-e75fa14c95e6 |  | note | Key - H
label | ff467bb5-57c6-5b87-b455-1eb0986f574b |  | note | RJE Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Identification of soft wet or unstable material
label | 27bc2796-3642-50ff-b4d8-be472959ea36 |  | note | Acceptance criteria - What quantity of soft, wet or unstable material is present?
label | 0ec1ea83-e288-50e5-a808-aa6f6e8f1f92 |  | note | Acceptance
text | 2e9582d8-9406-5568-8305-09d1a963e6dc |  | textbox |  |  |  | m2
text | 0d383459-1111-5a9f-b6df-8854023bb18f |  | textbox |  |  |  | m3
checkpoint-status |  |  | checkpoint | Treatment of unsuitable material
label | 26c1fdb8-42b5-5845-966e-98569e62a301 |  | note | Acceptance criteria - Has rectification process been submitted to RJE for review?
label | f36f04f5-6bd9-5596-969c-73412ee24599 |  | note | • What was the rectification process used?
button | ce9bdbd5-aa48-5402-87ea-5198c2f558a0 |  | button | Acceptance | Yes,No,N/A
text | 9e13c168-ce93-5a76-bcab-c1d09352b9b7 |  | textbox | Rectification Process:
checkpoint-group |  |  | section | 3.0 Bulk earthworks - fill
checkpoint-status |  |  | checkpoint | 3.1 - Stripped surface - test rolling (If applicable)
label | f251418b-bf02-59df-861d-6538a15bde5b |  | note | Acceptance criteria - Does the stripped surface to be filled withstand test rolling without visible deformation or springing?
text | 82984101-ded7-5294-badc-e1766bc5a889 |  | textbox | List Attendees:
button | 4c1d8524-1e62-5ec8-88ed-43da16b0e79b |  | button | Acceptance | Yes,No,N/A
label | df964d36-257b-58ee-83cb-bbb03accce53 |  | note | • If ‘no’ please see below.
label | 0b907cbc-161f-58c7-8273-b6b67742353e |  | note | • If ‘yes’ please proceed to item 3.2
label | 126ae3e9-63a2-5048-9278-7573688d9bfd |  | note | Key - H
label | 7e688889-4261-5843-91f7-afe1916b3c5b |  | note | RJE Key - H
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Identification of soft wet or unstable material
label | 3254bd37-46d2-5cc4-955e-dca24d25d04f |  | note | Acceptance criteria - What quantity of soft, wet or unstable material is present?
label | a90705da-44de-50a0-8c0f-e704491b50ee |  | note | Acceptance
text | 5c605bea-f594-56af-a4e4-87a503ddec22 |  | textbox |  |  |  | m2
text | cd86e50c-4be7-5233-b6d1-207240a4e32d |  | textbox |  |  |  | m3
checkpoint-status |  |  | checkpoint | Treatment of unsuitable material
label | 1bf99163-62e6-511e-b208-adb3232824e1 |  | note | Acceptance criteria - What rectification process is to be undertaken?
checkpoint-status |  |  | checkpoint | 3.2 - Preparation of surface
label | 67e52ebd-7c67-5cfb-8d23-e115d38ab6fe |  | note | Acceptance criteria - Has adequate water been added to the stripped surface to ensure adhesion to the next layer?
button | 9c94d6f4-1e3c-5e07-9d8f-bcf4a67713e1 |  | button | Acceptance | Yes,No,N/A
label | 4b26efc3-2209-59a1-bd29-83db574cfb42 |  | note | Key - S
label | 321063a0-2a21-54db-a02c-f4d15a2a19d7 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 3.4 - Fill Placement
label | a8aee3b9-0659-5f16-9489-22e7db47adb4 |  | note | Acceptance criteria - Has fill been placed in maximum 300mm and minimum 100mm compacted layer thickness?
button | 2ca9cb48-2225-5292-8c83-f3e12c4c0975 |  | button | Acceptance | Yes,No,N/A
label | f87e015b-8039-5e34-b0fd-411b37afdeae |  | note | Key - S
label | 068b9c84-b613-52c7-a272-85d514412e1f |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 3.5 - Moisture
label | e8fd682d-efc4-5417-b2b9-97ee304f2a89 |  | note | Acceptance criteria - Has the material maintained at optimum moisture content (within 2% of optimum moisture), with additional water being added if required during compaction?
button | d7986b85-622e-57dc-9232-3ffc8e2dabe5 |  | button | Acceptance | Yes,No,N/A
label | 9646400b-c3ad-56bd-aea4-9e233dc32ea4 |  | note | Key - S
label | 33462c76-838b-548a-a5a2-217fb14a7497 |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 3.6 - Compaction
label | a9abc48d-3a3c-5f3f-9b7e-0a76e5d8b8b7 |  | note | Acceptance criteria - Compaction Scale: 3 tests per lot. See RJE approved lots:
label | 23380aaa-2435-5ec7-b03e-e80dd50ad720 |  | note | • Combi Slab: 1, 2, 3, 4, 5
label | 62221257-1fb2-5844-890c-a38376f2470f |  | note | • Tempoary compound: Lot 1 & 2
label | 548aaeef-cff6-5e79-8696-b8a01e541d03 |  | note | • Has the subgrade been adequately compacted achieving 98% SMDD / 95% MMDD (in-situ materials or subgrade preparation), or 75% density index for the in-situ and fill materials. Using a nuclear density gauge.
label | 8eea5994-adab-55ad-a314-8df5fdcb17ad |  | note | • Is the subgrade within +/- 20mm of design surface.
button | 86c15c8d-d1ce-5376-91da-b1bc40359868 |  | button | Acceptance | Yes,No,N/A
label | d395b51c-6917-5669-96be-713954225b03 |  | note | Key - W
label | ec375641-d687-598d-af92-024a03e3beb4 |  | note | RJE Key - S
label | fa6933ca-d2d9-5c17-9533-5efaffc17a52 |  | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | 6302217e-1e21-5988-83dc-d83a0ec235b2 |  | tickbox | Test reports
checkpoint-status |  |  | checkpoint | 3.7 - Fill layer – test rolling
label | da4e3221-8552-51b3-8f53-319ef36131db |  | note | Acceptance criteria - Does the layer withstand test rolling without visible deformation or springing?
text | 6e69925e-1b79-5f75-b5c1-2cda14d701c5 |  | textbox | List Attendees:
button | 9d877d46-c563-5e19-98be-94f2c67ac33a |  | button | Acceptance | Yes,No,N/A
label | 9fb16cf7-c9e1-5728-92aa-8c114cc5906f |  | note | • If ‘no’ please see below
label | f5ffc98c-5870-59b9-90b0-30b1a2f92c1d |  | note | • If ‘yes’ please proceed to fill construction
label | 5383d0ed-c2f5-577e-a698-c298f79738a1 |  | note | Key - H
label | aca6b9b7-6d48-5e0a-a18c-43a4bc17bc1e |  | note | RJE Key - W
checkpoint-status |  |  | checkpoint | Identification of soft wet or unstable material
label | 13a02534-b26b-509a-ac62-921508928a42 |  | note | Acceptance criteria - What quantity of soft, wet or unstable material is present?
label | b61c0633-027a-547b-b2bb-7fbecc7966cc |  | note | Acceptance
text | 69c25fa2-7bdc-5683-8231-230922bdb39f |  | textbox |  |  |  | m2
text | 241939d6-6ee4-56c7-a061-17b8958c7b05 |  | textbox |  |  |  | m3
checkpoint-status |  |  | checkpoint | Treatment of unsuitable material
label | eb6d9cbe-d1d5-59d6-b4e2-f23c9eb8e047 |  | note | Acceptance criteria - Has rectification process been submitted to RJE for Review?
label | 9bd8b782-48d0-56d1-b891-7104eb8bf1e2 |  | note | • What was the rectification process used?
button | 61ad5d85-28d1-5fb8-be32-b9b374c68bea |  | button | Acceptance | Yes,No,N/A
text | fa3c976b-6dbd-50ac-83aa-1917a619bb50 |  | textbox | Rectification Process:
checkpoint-group |  |  | section | 4.0 Conformance check
checkpoint-status |  |  | checkpoint | 4.1 - Width and alignment
label | 4f162c62-44b0-5f57-ae1b-d221d9cb2430 |  | note | Acceptance criteria - Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
button | 98869598-d49d-54fd-a83e-87612c1d39d2 |  | button | Acceptance | Yes,No,N/A
label | 5e615242-66a2-58d2-a2b7-d0c2cd87dfa7 |  | note | Key - H
label | 2e6f40f5-82db-5ab2-b6fc-f5b98690511c |  | note | RJE Key - S
checkpoint-status |  |  | checkpoint | 4.2 - Subgrade level and shape
label | 59b106d8-d47a-5c3a-b156-ad2499f1dc53 |  | note | Acceptance criteria - Has the prepared subgrade been surveyed in accordance with and verifying specified requirements?
label | 7bfc0b1d-5129-5dd7-83ba-51d964d72535 |  | note | • Is the subgrade within +/- 20mm of design surface.
button | 7514a571-9b4c-5bd6-b975-296dd5e4c57d |  | button | Acceptance | Yes,No,N/A
label | e74b69c0-ece4-54f0-aaf1-c4f8d28bde18 |  | note | Key - H
label | f803be14-8197-5c12-8233-6b79b5635c35 |  | note | RJE Key - S
label | 93190d0f-59da-5e5c-8d27-b48559e5e3c7 |  | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | 62ff74cb-e13c-50ee-83ff-c1e8dcc34b85 |  | tickbox | As built report