## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
af6ef55c-b14c-40eb-93ed-addc208c7613 | checklist | ITC 010A - Inground Pits |  | ITC 010A - Inground Pits
3212c14b-cee3-4e7a-9489-9fac4234278b | section | Referenced Drawings and Revision Number
458b8b8a-40f8-47f7-8f1d-64ad7f29170b | checkpoint-no-value | Details
f5bd0caf-85e9-594d-af0f-2bc62d29d936 | textbox | Drawing and revision number
72bb4e79-5c0c-4086-a751-1b840173e929 | section | INSPECTION AND TEST RECORD FOR: INGROUND PITS
eb1a221b-d231-4ec6-85a8-7e879243d2c5 | checkpoint-no-value | Description of Work Area
856f34f5-c905-5d12-9de1-05c4a7093558 | textbox | Description:
a8ab8a0d-c738-46a6-b453-cf94b7f6b5ec | checkpoint-no-value | Attach mark-up of work area
a3f02e3b-6330-4f69-a3c6-011893916a63 | checkpoint | Set-out pits and any other items in accordance with the IFC documentation ahead of commencing excavation
1a070df1-4ae5-4b8b-a79b-af27b49e6607 | checkpoint | Excavate to design levels.
31ee27c9-1061-4d4f-b4d4-b4323d074412 | checkpoint | Ensure Drainage Holes are provided on bottom of pit
1db6d5f5-af2c-4cd3-89b7-a2df747a58cb | checkpoint | Ensure connected connection to Stormwater System where applicable.
07f96660-15cd-48a6-b315-c582242842c0 | checkpoint | Place bedding sand in bottom of trench.
889c5d0d-dc56-5adf-b662-c976a6dd94f1 | note | Check that 100mm bedding sand is achieved.
e798f0da-31bd-45a1-b6e9-951c9c465bdb | checkpoint | Place Hessian Underlay above
ee261dd1-892e-4582-84ed-71d7bca59839 | checkpoint | Place Gravel above Hessian Underlay .
646e1d09-200c-585e-86a8-f053ac0579ed | note | Check that 150mm gravel is achieved.
3f92216e-59f8-46cf-b1e9-d11679aa9112 | checkpoint | Install Pit ensure levelled to correct RL
d4585cdb-b30c-4fe0-9f75-82680544a61c | checkpoint | Take photos of pits prior to backfill.
201c75d3-6166-50bc-8034-995fa11ed69e | note | (Upload separately below).
c2ec1325-9207-4b5a-a1ef-56ac242c17fc | checkpoint | Client to inspect pits prior to backfill.
| signoff | HOLD POINT
4cde0a7e-b1f5-4253-8407-9b2195a1a67f | checkpoint | Place and compact suitable material to remaining depth around pits inline with manufactures data sheet.
| signoff | Request Sign Off
54938bf1-9a32-4111-b185-d3054350c23a | checkpoint | Pits cleaned & sealed
384a8d32-7e2d-4209-96d2-df28a91d7659 | checkpoint | Ensure Pit Lids are clearly labelled with service type
7ebe3d02-4911-4502-9c47-fca8b71143fc | checkpoint-no-value | Attach photos of conduits
22f92548-4181-404d-80ec-e4427de846a9 | checkpoint-no-value | Attach as-built survey
ab3ac4b0-444f-43ab-ae8d-3e19646d1265 | checkpoint-no-value | Attach any other relevant items (optional)
96e24ecd-a1f0-4e59-8287-f9e0f89c9b4d | checkpoint-no-value | Client to review completed ITC and confirm acceptance - final acceptance
9638d819-2c41-4e16-8ec1-3169ffcb2b9e | signoff | Client Final Acceptance