## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Job Details |  |  |  |  | Yes | Job Details | 1b60aab2-d3b0-45ed-ba28-4eae865cbd70
checkpoint-status |  |  | checkpoint | Project details entered below
text | d65d6bc0-a7e6-5990-b932-6fe20321ea0a |  | textbox | Job Number
text | 25dd8290-5e42-5ab9-b369-177d5ab56237 |  | textbox | Project Name
text | 22d70181-a904-5af1-b73f-6003ef3405ff |  | textbox | Site Address
text | 79d8ef56-716c-5342-84b1-b10b233ea858 |  | textbox | Builder
text | 1609e1ab-2f94-5e49-be71-26c096d81cfc |  | textbox | Euro Precast Project Manager
text | 3de13c67-2ca7-54e2-9696-969a0b65c0cd |  | textbox | Euro Precast Lead Draftsperson
text | af53f433-6c6a-54e2-9bec-23fd3a8e21aa |  | textbox | Euro Precast Installer
checkpoint-status |  |  | checkpoint | Grouts submitted for approval (UPLOAD TDS and SDS for each grout submitted)
checkpoint-status |  |  | checkpoint | Have submitted grouts been approved? (UPLOAD copy of approval)
checkpoint-status |  |  | checkpoint | Caulking products submitted for approval (UPLOAD TDS and SDS for each caulking product submitted)
checkpoint-status |  |  | checkpoint | Have submitted caulking products been approved? (UPLOAD copy of approval)
checkpoint-status |  |  | checkpoint | Patching products submitted for approval (UPLOAD TDS and SDS for each patching product submitted)
checkpoint-status |  |  | checkpoint | Have patching products been approved? (UPLOAD copy of approval)
checklist-sectioned |  |  | checklist | Installation Checklist |  |  |  |  | Yes | Installation Checklist | 38ed6673-05a9-418f-8761-75e93db25bc9
checkpoint-group |  |  | section | Element Install & Grouting
checkpoint-status |  |  | checkpoint | Bedding grout placed and finished as per project requirements
boolean | 077ee9b6-e1ba-538c-a4f9-135acf784996 |  | tickbox | Bedding grout (trowelable) used is as per project specification (PHOTO REQUIRED of the grout bag)
boolean | ff2926c3-d06d-5161-9a5f-1e91e39b3c4c |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | f5f92c7c-d2e7-5e92-a786-491f4bf7d408 |  | tickbox | Grout bed sufficient to ensure full coverage (PHOTO REQUIRED of grout bed prior to landing element)
checkpoint-status |  |  | checkpoint | Element installed to (PHOTO REQUIRED to show survey pins and spirit level bubble):
boolean | ba373bb1-b816-5821-ad5f-62732e6241c1 |  | tickbox | Survey Pins
boolean | 292a8dfe-1ada-5287-a31f-baf7726067db |  | tickbox | Within 5mm of vertical plumb
boolean | e4ca99df-c1e5-5b46-b554-05750c74dca6 |  | tickbox | Face alignment within 5mm
checkpoint-status |  |  | checkpoint | Element propped as per Euro Precast PEDS (PHOTO REQUIRED of element propped)
boolean | bff51322-985e-561f-930e-c79f65cd8bec |  | tickbox | Prop bolts installed with tool to ensure locking mechanism can't be removed by hand
checkpoint-status |  |  | checkpoint | Dowel tube (flowable) grout placed and finished as per project requirements
boolean | 96751ab4-595f-571a-ac9b-b16c848c4a2a |  | tickbox | Dowel tube grout used is as per project specification (PHOTO REQUIRED of the grout bag)
boolean | c6b82a66-5613-5356-91d7-19175b655a6f |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | 964581d6-c17a-5458-be48-7dcabf20cdec |  | tickbox | Dowel tubes filled to top of tubes
checkpoint-status |  |  | checkpoint | Is there any transport or erection damage that needs to be fixed (PHOTO REQUIRED of damaged area)
label | 97c9c6e1-867d-5362-91f2-b4c9e9929280 |  | note | If there is damage, mark as FAIL. Once the damage is repaired, take another photo (PHOTO REQUIRED) and then change the status to PASS
checkpoint-status |  |  | checkpoint | Area has been cleaned from grout and rubbish (PHOTO REQUIRED of the area before leaving)
checkpoint-group |  |  | section | HOLD POINT - Confirmation that Props can be removed
checkpoint-status |  |  | checkpoint | Has the Builder given us written confirmation that props can be removed (UPLOAD copy of correspondence)
checkpoint-status |  |  | checkpoint | PHOTO REQUIRED of element after the props have been removed
checklist-flat |  |  | checklist | Level Sign Off |  |  |  |  | Yes | Level Sign Off | 3e447ca1-891c-4c11-9874-b3f71c30a689
checkpoint-status |  |  | checkpoint | Details complete
text | 28e3afe0-951c-5e75-a692-2acee8ade145 |  | textbox | Date:
text | b186117c-89a7-54be-88db-a5f0da5362fe |  | textbox | Level:
checkpoint-status |  |  | checkpoint | Builder Sign Off
label | 2c99a2de-405c-5401-ab78-ef3d92fb90e5 |  | note | In signing the below, you agree and acknowledge that on this level:
label | 9c365cba-dfe3-58c0-92a4-c8d103a20931 |  | note | All props have been removed
label | e4a18e09-98d6-5ce9-9bba-d154be302cd8 |  | note | All grouting has been completed
label | a7272d6e-851e-5fe4-9219-bb27efbd9ba5 |  | note | All patching has been completed
label | ea2e5fe7-c5f0-5d77-9b16-fc632f4b493f |  | note | All sealing has been completed
label | e24b82d2-6318-5f71-9dc0-81a0336a1305 |  | note | All issued defects have been completed
holdpoint |  |  | signoff | BUILDER SIGNATURE (MUST INCLUDE NAME)
checklist-sectioned |  |  | checklist | Manufacturing Checklist |  |  |  |  | Yes | Manufacturing Checklist | 58e0f899-ec45-470e-a18c-edddb8295238
checkpoint-group |  |  | section | Manufacturing Documents
checkpoint-no-status |  |  | checkpoint | IFC Element Drawing
checkpoint-no-status |  |  | checkpoint | Euro Precast Primary Lifting and Propping Certification
checkpoint-no-status |  |  | checkpoint | Secondary Lifting Certification
checkpoint-status |  |  | checkpoint | All Manufacturing Documents uploaded
checkpoint-group |  |  | section | Pre-Pour Checks
checkpoint-status |  |  | checkpoint | Mould check
boolean | 60c0f1db-89a8-5af6-a6c2-d238c3438187 |  | tickbox | Mould clean with release oil applied correctly
boolean | 9e876f64-d8fc-5ed0-af5b-5a49a3d071cb |  | tickbox | Primary & diagonal dimensions checked
boolean | bc60b2c1-ddc5-5173-b933-699b92cacaf7 |  | tickbox | Openings Checked and Correct
boolean | 1a023f0e-98ea-585b-bfda-27613635cbab |  | tickbox | Rebates, Architectural Grooves Installed Correctly
boolean | 8fb2a237-8ad1-5775-9dd2-ad20b988a692 |  | tickbox | Formwork chamfers installed correctly where required
checkpoint-status |  |  | checkpoint | Reinforcing check
boolean | 9ab95f11-c167-5ab0-a935-9dacee795897 |  | tickbox | Correct Size and Type
boolean | da70fc71-e314-553e-b1fb-02d935809918 |  | tickbox | Laps and Splices correct
boolean | 4a31ecd7-f451-5ed9-a2b5-1940c8104582 |  | tickbox | Cover Checked
boolean | bfa811a7-69e0-5eef-ba35-f6f2915463c4 |  | tickbox | Spacing Checked
checkpoint-status |  |  | checkpoint | Cast in items check
boolean | c2ec23de-e915-5e50-8256-84d1d3b2a9c6 |  | tickbox | Ferrules/Inserts installed, checked and correct
boolean | ebc1d970-0e79-580c-8be2-538586b7f934 |  | tickbox | Starter Bars inserted, checked and correct
boolean | 3fc1316a-7e26-5499-8645-dcbde3f7171d |  | tickbox | Lifting anchors installed, checked and correct
checkpoint-status |  |  | checkpoint | Check Minimum Cover
checkpoint-status |  |  | checkpoint | ID Tag installed in non-visible face
checkpoint-status |  |  | checkpoint | Pre-Pour checks completed and approval given to pour Element
label | d68372e1-4419-50fb-8459-9d298313137e |  | note | Upload sufficient number of photos of element
checkpoint-status |  |  | checkpoint | Upload photo of signed pre-pour check of shop drawing
checkpoint-group |  |  | section | Concrete Pour Checks
checkpoint-status |  |  | checkpoint | Concrete Strength correct as per design
boolean | f7e3ed27-a499-5ae9-a169-14c017d30d14 |  | tickbox | All Concrete Dockets Attached
text | a587c78b-fb52-595a-9f8c-d132b1e40a9f |  | textbox | Date element was cast
checkpoint-group |  |  | section | Post-Pour / Pre Delivery Checks
checkpoint-status |  |  | checkpoint | Visual Check
boolean | 7fe5b5c2-ca9e-598b-a1c3-2ea2a4563ca7 |  | tickbox | Does the finish meet class 2 as per AS3610
boolean | c00f4b97-4fbd-5f7d-bfc4-7ae988ea284a |  | tickbox | Chamfers clean, neat and on all required edges
boolean | 57e3d18a-22dc-5290-ac7b-a307ecc14937 |  | tickbox | Lifting anchors checked and approved
boolean | d2597588-cb3f-58e9-b7d3-dd1a8853ac12 |  | tickbox | Critical fitments / fixtures checked and approved
boolean | 418d3a91-f169-5546-91d6-08b9eb3beb5c |  | tickbox | Openings (formwork removed)
boolean | 4cf0ae65-684e-5f25-8ef7-040d2bfbe644 |  | tickbox | Nailplates / Recesses etc removed
checkpoint-status |  |  | checkpoint | Any Strongbacks Installed where required
checkpoint-status |  |  | checkpoint | Element free from defects that will impact structural integrity or durability?
label | fd108b89-2016-5d8d-b155-3eefbe42f580 |  | note | If 'FLAG', raise NCR and notify EP Project Manager to discuss with builder
boolean | 9dbe548b-8cc0-5025-a911-6772b48f9883 |  | tickbox | If NCR raised, take photo of completed approved works
checkpoint-status |  |  | checkpoint | All Post Pour Works complete - Element Checked, Approved and Ready for delivery
checkpoint-group |  |  | section | Concrete Test Results
checkpoint-no-status |  |  | checkpoint | Concrete Test Result attached
label | fd1bb323-e2ed-5994-bc94-75a0d84f7a56 |  | note | Upload actual test result OR a test result of the same mix design from the same day
checkpoint-status |  |  | checkpoint | Concrete Test Results uploaded
checklist-flat |  |  | checklist | Grout Testing Checklist |  |  |  |  | Yes | Grout Testing Checklist | 83db512b-1e08-47cf-a7e9-e80807574b2a
checkpoint-status |  |  | checkpoint | To organise grout testing, call Construction Sciences. Primary contact is Michael Hardcastle on 0429 791 069. Secondary contact is Joshua Borg on 0429 790 444
text | b449fd6d-46a4-59fe-b5c7-3120ff6a22d2 |  | textbox | Date:
text | e5aca2f1-94a0-5688-8de9-ac5a3f4615b4 |  | textbox | Project Name:
text | c947ae9e-7d95-5096-8ae1-6d3f8a407ffe |  | textbox | Time of test:
text | 89a25d49-2f76-536b-a823-938248276412 |  | textbox | Grouts tested:
checkpoint-status |  |  | checkpoint | Upload grout test results
checklist-sectioned |  |  | checklist | Variation works completed |  |  |  |  | Yes | Add New Variation | 9871845f-6c50-42e4-898d-5d4bf87ff2ac
checkpoint-group |  |  | section | Works completed
checkpoint-status |  |  | checkpoint | Details entered below
text | c1876c5e-9363-593c-8eae-090e7e67aabe |  | textbox | Date:
text | e48c2ef2-7c9a-5f60-8588-3bb024bff947 |  | textbox | Name of people who completed the works:
select | b90eac2f-d675-5854-8254-d73c31208848 |  | dropdown | Time started at site: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 9c1bc354-2aa7-5474-b55a-79c1d825e492 |  | dropdown | Time finished at site: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
text | 4a6b40d7-361f-5737-b1e5-ea343ebf6761 |  | textbox | Consumables used:
text | 89b4f543-41c5-5f1f-8493-03d9b87fa0e2 |  | textbox | Summary of works completed
checkpoint-group |  |  | section | Builder sign-off
checkpoint-status |  |  | checkpoint | Builder sign-off
label | 26b61b0b-0ae9-5937-9b1f-38d7a598bfd9 |  | note | By signing below you acknowledge the above summary as a true and accurate record of the day.
holdpoint |  |  | signoff | Builder Signature (must be authorised person)
checklist-sectioned |  |  | checklist | Delivery / Installation Day Checklist |  |  |  |  | Yes | Delivery / Installation Day Checklist | c43a27ad-83ad-435c-bddb-924a5106cd26
checkpoint-group |  |  | section | HOLD POINT - Confirmation of slab strength
checkpoint-status |  |  | checkpoint | Has the slab reached the minimum strength required (UPLOAD copy of concrete slab test result)
label | c9bbf854-3550-5dcf-b99e-2aa2642a158e |  | note | 12MPa for cast-in anchors and 20MPa for post installed anchors
checkpoint-group |  |  | section | Prestart / Start-up
checkpoint-status |  |  | checkpoint | Date of Installation
checkpoint-status |  |  | checkpoint | Installation team completing the install today
label | 2e9de6a9-8443-50b6-8719-3f96e702f0c9 |  | note | List names in comments
checkpoint-status |  |  | checkpoint | Exclusion Zone is set up (PHOTO REQUIRED of the exclusion zone)
checkpoint-status |  |  | checkpoint | Plant & Equipment prestart/logbooks filled out (PHOTO REQUIRED of logbooks)
checkpoint-status |  |  | checkpoint | Toolbox Talk / Pre-Start has been completed (PHOTO REQUIRED of talk)
checkpoint-group |  |  | section | Summary of the day
checkpoint-status |  |  | checkpoint | Hours worked
select | 78d03587-565c-5bab-926a-b4740dbf00a7 |  | dropdown | Time started on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 3c43c761-e0cc-5dda-a17e-e255c537b145 |  | dropdown | Time finished on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-status |  |  | checkpoint | Elements Installed today
label | 4d0b8069-eb4f-5b81-95fc-08e191d04ec9 |  | note | COMMENT below if number of elements installed doesn't match the Load Lists in the Safe Load Declarations
select | 2ada973d-8803-5f88-8f23-e67ec388aa3e |  | dropdown | How many elements were installed today? | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28, 29, 30, 31, 32, 33, 34, 35, 36, 37, 38, 39, 40
checkpoint-status |  |  | checkpoint | Were there any delays?
label | 87faf9ba-5e3f-5b3d-aaee-0a556769d8b7 |  | note | COMMENT below in enough detail to explain the delay and what caused it. Add PHOTO if it helps record the delay.
select | d3140643-7f44-5203-8eb3-18b5642f0f44 |  | dropdown | How long was the delay? | N/A, 30mins, 1hr, 1.5hr, 2hr, 2.5hr, 3hr, 3.5hr, 4hr, 4.5hr, 5hr, 5.5hr, 6hr, 6.5hr, 7hr, 7.5hr, 8hr
select | 58046ee7-6a2f-55a4-9755-818c7abe3b68 |  | dropdown | How many installers were impacted by the delay/s? | 1, 2, 3, 4, 5, 6
select | ede201f0-4afc-511e-b34f-570146242cef |  | dropdown | How many trucks were impacted by the delay/s? | 1, 2, 3, 4, 5, 6
checkpoint-status |  |  | checkpoint | Builder sign-off
label | f4a9c5b1-6546-51e0-a12c-90fcd787c5e0 |  | note | By signing below you acknowledge the above summary as a true and accurate record of the day.
holdpoint |  |  | signoff | Builder Signature (must be authorised person)
checklist-flat |  |  | checklist | Safe Load Declaration Checklist |  |  |  |  | Yes | Safe Load Declaration Checklist | e907bd1a-9905-447f-bed0-13ddea6caa13
checkpoint-status |  |  | checkpoint | Details complete
text | 07b076b1-77e2-5220-abea-0d8d0aca550c |  | textbox | Date:
text | 3032a920-cd2a-5dc7-a7c1-cb75656f11cc |  | textbox | Time truck arrived at Factory:
text | 791f99aa-35d2-59eb-978c-82dd4547b617 |  | textbox | Time truck departed Factory:
text | de22b9e2-75fc-5abf-8bb7-8a86b261de6d |  | textbox | Transport Company:
text | 72527c27-d707-5ead-92e7-48f36ff4a96a |  | textbox | Truck Registration #
text | d5e44f97-eaf9-51aa-a9c8-0a5ea43dfa13 |  | textbox | Trailer Registration
select | 2aa9d15b-d14a-556f-a4b8-fb661d545ed0 |  | dropdown | Trailer Type: | Drop Deck, Drop Deck No Frame, Flat Top, Layover, Super Layover, Commission
checkpoint-status |  |  | checkpoint | Upload photo of Load List used for load
checkpoint-status |  |  | checkpoint | Upload photos of both sides of loaded truck (after being chained down)
checkpoint-status |  |  | checkpoint | Load Declaration
label | 45eda7f3-fed9-5826-ab6e-3f40ef341356 |  | note | In signing below, you agree and acknowledge that:
label | 996d49d9-74ad-5b67-b707-707d88082d66 |  | note | You are not permitted to leave the Euro Precast factory unless a Safe Load Declaration has been completed
label | f486cb80-06e1-54c1-9858-ce6caea6eadb |  | note | You have been provided with a copy of the load list that indicates individual element weights and total approximate load weight (excluding trailer/frame weight)
label | cc666dc1-1751-57ba-b3bf-b458b69b6399 |  | note | You have chained down all units/elements in a safe and secure manner and in accordance with the latest published government/industry best practice guidance material
label | 73a2a52f-48de-5d82-8f9d-59a0d2c55a86 |  | note | You will abide by all safety rules, PPE requirements and client instructions on the project site at all times.
label | cbdf9d8e-b69c-5acc-901c-bc5cbf450062 |  | note | You as an individual, the truck, the trailer and load comply with the latest requirements of the Heavy Vehicle National Law and Regulations (HVNL)
holdpoint |  |  | signoff | Driver Signature (must include Company)