## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Job Details |  |  |  |  | Yes | Job Details | 3ea038e1-24d3-4ab7-81cf-be01e02220e5
checkpoint-status |  |  | checkpoint | Project details entered below
text | 38c83dd9-1d3e-5af0-8d43-2ace280d762d |  | textbox | Job Number
text | 1558e7df-b120-58a3-b129-e919b3b3db94 |  | textbox | Project Name
text | a9a93357-b8a6-5898-829f-8ff86ec56676 |  | textbox | Site Address
text | ebe1cd40-2177-51cd-8e87-e0fb841ea54c |  | textbox | Builder
text | bf5ce90c-1047-5af0-9078-5bf5531616f4 |  | textbox | Euro Precast Project Manager
text | 434901e4-5a43-50ce-b6d7-e07175496939 |  | textbox | Euro Precast Lead Draftsperson
text | 73fe9d0c-fe92-53e0-aeec-bf4bc1aba93e |  | textbox | Euro Precast Installer
checkpoint-status |  |  | checkpoint | Grouts submitted for approval (UPLOAD TDS and SDS for each grout submitted)
checkpoint-status |  |  | checkpoint | Have submitted grouts been approved? (UPLOAD copy of approval)
checkpoint-status |  |  | checkpoint | Caulking products submitted for approval (UPLOAD TDS and SDS for each caulking product submitted)
checkpoint-status |  |  | checkpoint | Have submitted caulking products been approved? (UPLOAD copy of approval)
checkpoint-status |  |  | checkpoint | Patching products submitted for approval (UPLOAD TDS and SDS for each patching product submitted)
checkpoint-status |  |  | checkpoint | Have patching products been approved? (UPLOAD copy of approval)
checklist-flat |  |  | checklist | Level Sign Off |  |  |  |  | Yes | Level Sign Off | 464d54fa-48a0-46c1-b085-d6b4c91d5d0b
checkpoint-status |  |  | checkpoint | Details complete
text | a017d843-b30c-5e9c-a3ab-b4241ac24dde |  | textbox | Date:
text | 62fd865c-650a-5aad-9a4c-a9b730aa250f |  | textbox | Level:
checkpoint-status |  |  | checkpoint | Builder Sign Off
label | 165946aa-e79b-5e69-988e-268717297620 |  | note | In signing the below, you agree and acknowledge that on this level:
label | ad438654-52f8-5f9b-a757-655b11a144af |  | note | All props have been removed
label | f1d8f701-e809-5f04-9df3-241ae8a2f488 |  | note | All grouting has been completed
label | 82fb1898-f9f6-5ce8-82b2-26d0732889e3 |  | note | All patching has been completed
label | d1f90dc7-cf4a-559a-b1cc-be396d8bd723 |  | note | All sealing has been completed
label | ecbad982-ec0b-5f8e-bc26-ecc6e3254b83 |  | note | All issued defects have been completed
holdpoint |  |  | signoff | BUILDER SIGNATURE (MUST INCLUDE NAME)
checklist-sectioned |  |  | checklist | Manufacturing Checklist |  |  |  |  | Yes | Manufacturing Checklist | 64133d0b-7048-41f0-a69a-a40a422b0714
checkpoint-group |  |  | section | Manufacturing Documents
checkpoint-status |  |  | checkpoint | IFC Element Drawing
checkpoint-status |  |  | checkpoint | Euro Precast Primary Lifting and Propping Certification
checkpoint-status |  |  | checkpoint | Secondary Lifting Certification
checkpoint-group |  |  | section | Pre-Pour Checks
checkpoint-status |  |  | checkpoint | Mould check
boolean | 571ac1d8-af07-523b-8a25-3de0dd4edd37 |  | tickbox | Mould clean with release oil applied correctly
boolean | 5d33bb52-7f0f-5e02-b4ae-4b37a1a5e147 |  | tickbox | Primary & diagonal dimensions checked
boolean | 2ae37f93-2905-5e04-8822-335f869f8523 |  | tickbox | Openings Checked and Correct
boolean | 1310aada-fbc7-5514-b387-af8777585a2b |  | tickbox | Rebates, Architectural Grooves Installed Correctly
boolean | 24742c92-58ef-5a14-8269-2b3e6d3e8518 |  | tickbox | Formwork chamfers installed correctly where required
checkpoint-status |  |  | checkpoint | Reinforcing check
boolean | 40b87e1c-28db-5546-97e2-037ffd4a3b4b |  | tickbox | Correct Size and Type
boolean | 82e3150c-e877-5978-804c-090cb4ba884d |  | tickbox | Laps and Splices correct
boolean | ca3a5821-cba9-5b74-89ef-3bde6d25f2bf |  | tickbox | Cover Checked
boolean | 5864a7d0-61ed-58bd-b4f6-ec6cf6774c6e |  | tickbox | Spacing Checked
checkpoint-status |  |  | checkpoint | Cast in items check
boolean | 14e2ec21-0398-5957-a4a9-504cd37f2fba |  | tickbox | Ferrules/Inserts installed, checked and correct
boolean | 03cdec17-d182-5249-85cc-6711a9fc9444 |  | tickbox | Starter Bars inserted, checked and correct
boolean | 91c0360a-2046-5f26-a963-9c714bb5366e |  | tickbox | Lifting anchors installed, checked and correct
checkpoint-status |  |  | checkpoint | Check Minimum Cover
checkpoint-status |  |  | checkpoint | ID Tag installed in non-visible face
checkpoint-status |  |  | checkpoint | Pre-Pour checks completed and approval given to pour Element
label | 81e59552-ae49-50da-8feb-3a288b3c64a8 |  | note | Upload sufficient number of photos of element
checkpoint-status |  |  | checkpoint | Upload photo of signed pre-pour check of shop drawing
checkpoint-group |  |  | section | Concrete Pour Checks
checkpoint-status |  |  | checkpoint | Concrete Strength correct as per design
boolean | 7afaf45c-1319-5268-8f8e-0358ab7a4feb |  | tickbox | All Concrete Dockets Attached
text | 1137cb9c-eafd-568a-8737-9265fce971c4 |  | textbox | Date element was cast
checkpoint-group |  |  | section | Post-Pour / Pre Delivery Checks
checkpoint-status |  |  | checkpoint | Visual Check
boolean | 92db6beb-118d-57c2-8738-b54abf8d1550 |  | tickbox | Does the finish meet class 2 as per AS3610
boolean | 8aa80c37-7f87-5d79-be3b-78428eac4885 |  | tickbox | Chamfers clean, neat and on all required edges
boolean | 0aeca1b3-39b6-52b2-b4c0-ff6c01ec60fa |  | tickbox | Lifting anchors checked and approved
boolean | 4eab57ff-ec86-52d0-a301-9e8959d806db |  | tickbox | Critical fitments / fixtures checked and approved
boolean | cc448cb7-e935-500e-b416-7043afbaf168 |  | tickbox | Openings (formwork removed)
boolean | 50ffe14b-0a2d-545a-a05c-0caf29d8298e |  | tickbox | Nailplates / Recesses etc removed
checkpoint-status |  |  | checkpoint | Any Strongbacks Installed where required
checkpoint-status |  |  | checkpoint | Element free from defects that will impact structural integrity or durability?
label | 65cd5636-40c2-5531-8b0c-e0c822690fa7 |  | note | If 'FLAG', raise NCR and notify EP Project Manager to discuss with builder
boolean | 21d56131-ee3d-527c-92c0-238c4c3e82a1 |  | tickbox | If NCR raised, take photo of completed approved works
checkpoint-status |  |  | checkpoint | All Post Pour Works complete - Element Checked, Approved and Ready for delivery
checkpoint-group |  |  | section | Concrete Test Results
checkpoint-status |  |  | checkpoint | Concrete Test Result attached
label | 0dde55c6-4753-51b5-b893-99d1ce3893ba |  | note | Upload actual test result OR a test result of the same mix design from the same day
checklist-flat |  |  | checklist | Grout Testing Checklist |  |  |  |  | Yes | Grout Testing Checklist | 7241c797-8ed8-4d3c-9b2c-a2368beb5174
checkpoint-status |  |  | checkpoint | To organise grout testing, call Construction Sciences. Primary contact is Michael Hardcastle on 0429 791 069. Secondary contact is Joshua Borg on 0429 790 444
text | 12096035-0a0c-56ff-bd08-93e2efaba7f6 |  | textbox | Date:
text | 3030b09b-dcbc-5859-a59c-1503d4ba8739 |  | textbox | Project Name:
text | 83491eda-c6bd-5210-9fbd-adb124e72343 |  | textbox | Time of test:
text | a80b95c0-96da-5f1f-be0b-7bb92622d92e |  | textbox | Grouts tested:
checkpoint-status |  |  | checkpoint | Upload grout test results
checklist-sectioned |  |  | checklist | Variation works completed |  |  |  |  | Yes | Add New Variation | 7db2a64d-01aa-4540-9a57-858bc0809cae
checkpoint-group |  |  | section | Works completed
checkpoint-status |  |  | checkpoint | Details entered below
text | c1876c5e-9363-593c-8eae-090e7e67aabe |  | textbox | Date:
text | e48c2ef2-7c9a-5f60-8588-3bb024bff947 |  | textbox | Name of people who completed the works:
select | b90eac2f-d675-5854-8254-d73c31208848 |  | dropdown | Time started at site: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 9c1bc354-2aa7-5474-b55a-79c1d825e492 |  | dropdown | Time finished at site: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
text | 4a6b40d7-361f-5737-b1e5-ea343ebf6761 |  | textbox | Consumables used:
text | 89b4f543-41c5-5f1f-8493-03d9b87fa0e2 |  | textbox | Summary of works completed
checkpoint-group |  |  | section | Builder sign-off
checkpoint-status |  |  | checkpoint | Builder sign-off
label | 26b61b0b-0ae9-5937-9b1f-38d7a598bfd9 |  | note | By signing below you acknowledge the above summary as a true and accurate record of the day.
holdpoint |  |  | signoff | Builder Signature (must be authorised person)
checklist-sectioned |  |  | checklist | Installation Checklist |  |  |  |  | Yes | Installation Checklist | 9913c32f-4b78-46c1-983e-7570776b304c
checkpoint-group |  |  | section | Element Install & Grouting
checkpoint-status |  |  | checkpoint | Bedding grout placed and finished as per project requirements
boolean | f35a015c-a7c5-5e72-b3c0-f1d2f643089a |  | tickbox | Bedding grout (trowelable) used is as per project specification (PHOTO REQUIRED of the grout bag)
boolean | be66fcda-3418-5f56-a849-c68c2faefaf0 |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | 13820dd0-c5ff-55f9-8df5-12a9765cb004 |  | tickbox | Grout bed sufficient to ensure full coverage (PHOTO REQUIRED of grout bed prior to landing element)
checkpoint-status |  |  | checkpoint | Element installed to (PHOTO REQUIRED to show survey pins and spirit level bubble):
boolean | 449b627d-d390-5c67-9f54-c718876a88c7 |  | tickbox | Survey Pins
boolean | 5e61a5c5-4fc8-5a74-8466-e29d35a6cc0f |  | tickbox | Within 5mm of vertical plumb
boolean | 5eebb43a-e842-5ef7-87f0-9917d0348752 |  | tickbox | Face alignment within 5mm
checkpoint-status |  |  | checkpoint | Element propped as per Euro Precast PEDS (PHOTO REQUIRED of element propped)
boolean | f7172c76-62ad-5c80-beaa-6bb5c20aea5d |  | tickbox | Prop bolts installed with tool to ensure locking mechanism can't be removed by hand
checkpoint-status |  |  | checkpoint | Dowel tube (flowable) grout placed and finished as per project requirements
boolean | 0e5243ed-4fa4-5b70-b76d-d4112eb6a4b9 |  | tickbox | Dowel tube grout used is as per project specification (PHOTO REQUIRED of the grout bag)
boolean | 2675b456-6c19-5ef3-96b9-1c0de43d4735 |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | 5c5aeb76-5858-5a1a-b1e9-1dc78d0a5711 |  | tickbox | Dowel tubes filled to top of tubes
checkpoint-status |  |  | checkpoint | Is there any transport or erection damage that needs to be fixed (PHOTO REQUIRED of damaged area)
label | 400c6786-eafa-5d39-b711-d41fedab13a1 |  | note | If there is damage, mark as FAIL. Once the damage is repaired, take another photo (PHOTO REQUIRED) and then change the status to PASS
checkpoint-status |  |  | checkpoint | Area has been cleaned from grout and rubbish (PHOTO REQUIRED of the area before leaving)
checkpoint-group |  |  | section | Element Caulking
checkpoint-status |  |  | checkpoint | Element caulked as per project requirements
boolean | 956d9c13-50b2-59ce-a105-48c87cf328c6 |  | tickbox | Caulking product used as per element/project requirements (PHOTO REQUIRED of caulking product used)
boolean | 3e55a4cd-dd1c-5606-95fa-5982bd73b11c |  | tickbox | Open or closed cell backing rod used? (SPECIFY in comments section below)
boolean | 1ff932ba-aa03-5c58-90cf-2c48d6acaaca |  | tickbox | Caulking installed and checked (PHOTO REQUIRED of caulked joint/s)
checkpoint-group |  |  | section | HOLD POINT - Confirmation that Props can be removed
checkpoint-status |  |  | checkpoint | Has the Builder given us written confirmation that props can be removed (UPLOAD copy of correspondence)
checkpoint-status |  |  | checkpoint | PHOTO REQUIRED of element after the props have been removed
checkpoint-group |  |  | section | Basic Patch
checkpoint-status |  |  | checkpoint | Have the lifting anchors been patching as per project requirements
checkpoint-status |  |  | checkpoint | Have the prop points been patching as per project requirements
checkpoint-status |  |  | checkpoint | Have the grout tubes been patching as per project requirements
checkpoint-group |  |  | section | Final Finish
checkpoint-status |  |  | checkpoint | Has all outstanding patching been completed (PHOTO REQUIRED of all visible faces of element)
checklist-flat |  |  | checklist | Daily Diary / Timesheet |  |  |  |  | Yes | Daily Diary / Timesheet | 9976a616-0553-49c2-ac07-424f75a5fcac
checkpoint-status |  |  | checkpoint | Site 1: Details entered below
text | 73455286-80f6-584f-8272-11112ff83e45 |  | textbox | Site 1:
select | 8a64f9db-50d6-573b-a929-0c48faec9b15 |  | dropdown | Time started on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | f53ccaf4-8dcc-5b85-a461-efe72517b070 |  | dropdown | Time left site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-no-status |  |  | checkpoint | Site 1: Activities completed
boolean | d1552211-a8d5-51e8-89f7-fef57d8efa93 |  | tickbox | Set out
select | 367720f5-5c2b-5917-97bd-ebcc71b23a34 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | edeb057e-229c-5870-9cc5-24ff1dca0a5f |  | tickbox | Panel Install
select | 54b17ed8-3755-5813-b1ba-4a291af7554e |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 959f0213-a415-5f25-9071-92cda4e9f9bd |  | tickbox | Patching
select | e1978673-0bdc-5ede-acda-8f470b3ba9f0 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 83089ccf-602f-53d3-9d81-10bc6998476e |  | tickbox | Joint Sealing
select | cc2d8497-b61d-5791-a6c3-ec384db2b6cb |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 28553334-ad97-5fe4-b33e-0c3bda21fcf1 |  | tickbox | Prop Removal
select | d88503a6-3899-5050-b40a-3326e6ee2530 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
text | fcfba898-d112-5537-b7c2-7d2c7857284a |  | textbox | Other (add in comments)
select | fcc93e76-be5c-5d61-935d-c86f59cc1c6a |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
checkpoint-status |  |  | checkpoint | Site 2: Details entered below
text | 1c6892a6-306a-5511-a4a9-afa426100b4c |  | textbox | Site 2:
select | 9230b54f-a5a3-5c52-a1f7-b350eb0c9a9c |  | dropdown | Time started on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 69a3536d-24e9-5d69-9f07-14fe392f84f3 |  | dropdown | Time left site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-no-status |  |  | checkpoint | Site 2: Activities completed
boolean | 11c4d861-3ba7-5f9b-995c-e268ca0cf06e |  | tickbox | Set out
select | 7dc6b993-2d05-573c-bedc-f984588e571f |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 2962fd2d-7279-5c79-a2ee-3d155ef28cc1 |  | tickbox | Panel Install
select | 9d029ea0-235d-5499-ac9f-6e0de788d1d4 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | b0ffe0b5-7fab-55dd-9f24-fef55a7c3047 |  | tickbox | Patching
select | ec580a8c-f0c9-58aa-b780-9db9e6d11e49 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 4c07066f-f1f3-57c9-8ebd-0e66c98711af |  | tickbox | Joint Sealing
select | 5a50833d-b033-5e96-b3fc-b509ac619dd9 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | e0615532-a95b-5b7a-acd0-8eaa7f8df5a6 |  | tickbox | Prop Removal
select | 69d5472e-072b-5334-af30-797e1cff7cb3 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
text | 02c00887-cb00-596e-864b-efe89126932c |  | textbox | Other (add in comments)
select | fa91726a-f850-5547-b68b-07542872225c |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
checkpoint-status |  |  | checkpoint | Site 3: Details entered below
text | f70170e7-7195-5bed-b1fa-35ff7d0b6b31 |  | textbox | Site 3:
select | b03a41a5-2725-55e4-94b1-e551e5f9b664 |  | dropdown | Time started on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 982a20a6-9614-5f59-b67c-1c4b25157489 |  | dropdown | Time left site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-no-status |  |  | checkpoint | Site 3: Activities completed
boolean | f713a8a2-56b3-5e2f-8f82-a616cafbf347 |  | tickbox | Set out
select | 9f7ce3b6-8937-5e1c-bc80-46d435ead825 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 303a0942-086b-5787-b44b-fd2af38b16fc |  | tickbox | Panel Install
select | 32552eff-84a1-506b-a96c-711a5bf3545d |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 0d31f48e-7b19-5222-b9d5-12fd9baf68bc |  | tickbox | Patching
select | 1d00f8c0-6c83-5a75-aaa4-8896eab0e2f7 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | e7bec026-76df-5c95-a027-4b798b3659ab |  | tickbox | Joint Sealing
select | 29e2bb92-5a56-5192-9a0d-f0d4d11a562e |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 089e43de-a1f7-55b0-ab54-3984ccc1569f |  | tickbox | Prop Removal
select | 1437e266-25e4-53b5-9e32-2fb80e156171 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
text | c944b06c-2886-5df1-8c29-def33ae4673d |  | textbox | Other (add in comments)
select | 4baae6e6-0908-5ac4-96d7-4f2358b807f8 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
checkpoint-status |  |  | checkpoint | Site 4: Details entered below
text | c820988b-2377-59e2-96eb-a97dac5253f8 |  | textbox | Site 4:
select | 21163298-c1f8-5d13-9e77-5194f331e8b9 |  | dropdown | Time started on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | d288abab-36e5-5589-89bc-240ae52e4967 |  | dropdown | Time left site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-no-status |  |  | checkpoint | Site 4: Activities completed
boolean | 8a1bae0c-474d-5ad9-9131-3d0a8d94b299 |  | tickbox | Set out
select | ed53667f-8337-5912-9719-1dfb76a1b6e6 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | 8ffa2760-cf95-5472-adbb-156da6575465 |  | tickbox | Panel Install
select | d236c23d-73eb-5509-bafd-93b7e9dda39f |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | a7c1d70b-28cd-5b1c-a8d2-30fa975529fc |  | tickbox | Patching
select | eb9a92d0-01ae-512a-899c-27344c5b73d8 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | f8bbfb28-47c1-5b7c-bf96-df3becd18937 |  | tickbox | Joint Sealing
select | 37d2f4f2-b0d2-56bb-bfe3-a815d4bc23e3 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
boolean | ce82ccd0-c8d6-51bb-b481-55f1bd3b5eab |  | tickbox | Prop Removal
select | b4e2f7c2-9d4f-5470-8e85-d92464c7653d |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
text | 7f3a7c81-4ff6-5b32-b372-d94794de499f |  | textbox | Other (add in comments)
select | a8a8a87a-5792-5eb1-8260-3afca07d7169 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1:30hr, 2hr, 2:30hr, 3hr, 3:30hr, 4hr, 4:30hr, 5hr, 5:30hr, 6hr, 6:30hr, 7hr, 7:30hr, 8hr, 8:30hr, 9hr, 9:30hr, 10hr, 10:30hr, 11hr, 11:30hr, 12hr
checkpoint-status |  |  | checkpoint | Euro Precast Employee signoff
checkpoint-status |  |  | checkpoint | Euro Precast Manager signoff
holdpoint |  |  | signoff | Add signature
checkpoint-status |  |  | checkpoint | When complete please send timesheet as report to jane@europrecast.com
checklist-flat |  |  | checklist | Safe Load Declaration Checklist |  |  |  |  | Yes | Safe Load Declaration Checklist | cce5d90e-3d5d-456a-9298-2aa13398d407
checkpoint-status |  |  | checkpoint | Details complete
text | b04b042c-446a-50a5-9d2d-68f7e8c24f95 |  | textbox | Date:
text | d93fd580-fd5f-5b87-9733-7dd1ed3ef4f8 |  | textbox | Time truck arrived at Factory:
text | ccd4ae79-5214-5ced-ab90-8a9beb75af17 |  | textbox | Time truck departed Factory:
text | 66617271-b3db-5e73-a367-a6adeb189253 |  | textbox | Transport Company:
text | f4a92464-4ddf-5dc5-96a1-80e76d86a16a |  | textbox | Truck Registration #
text | 1d54ad52-a509-5d02-83ea-a413c8fb8a38 |  | textbox | Trailer Registration
select | a5cab4a8-aab0-5735-b9a0-9f43437544da |  | dropdown | Trailer Type: | Drop Deck, Drop Deck No Frame, Flat Top, Layover, Super Layover, Commission
checkpoint-status |  |  | checkpoint | Upload photo of Load List used for load
checkpoint-status |  |  | checkpoint | Upload photos of both sides of loaded truck (after being chained down)
checkpoint-status |  |  | checkpoint | Load Declaration
label | c375310f-5f4f-58ab-9efe-d7d0885f171a |  | note | In signing below, you agree and acknowledge that:
label | e2031acb-ecdc-580d-b6b2-21664fbceced |  | note | You are not permitted to leave the Euro Precast factory unless a Safe Load Declaration has been completed
label | 740c8ca2-2517-536d-92a4-43efe888471b |  | note | You have been provided with a copy of the load list that indicates individual element weights and total approximate load weight (excluding trailer/frame weight)
label | dfb2c7e8-e330-56ea-b1cb-444bf28770cf |  | note | You have chained down all units/elements in a safe and secure manner and in accordance with the latest published government/industry best practice guidance material
label | b248911b-3093-5150-ab16-c9289277609a |  | note | You will abide by all safety rules, PPE requirements and client instructions on the project site at all times.
label | 0831ae1a-3388-5167-bdf9-facf5bad8aea |  | note | You as an individual, the truck, the trailer and load comply with the latest requirements of the Heavy Vehicle National Law and Regulations (HVNL)
holdpoint |  |  | signoff | Driver Signature (must include Company)
checklist-sectioned |  |  | checklist | Delivery / Installation Day Checklist |  |  |  |  | Yes | Delivery / Installation Day Checklist | fc83cbe0-2598-41d6-a4d7-a9cf7a3c6204
checkpoint-group |  |  | section | HOLD POINT - Confirmation of slab strength
checkpoint-status |  |  | checkpoint | Has the slab reached the minimum strength required (UPLOAD copy of concrete slab test result)
label | c9bbf854-3550-5dcf-b99e-2aa2642a158e |  | note | 12MPa for cast-in anchors and 20MPa for post installed anchors
checkpoint-group |  |  | section | Prestart / Start-up
checkpoint-status |  |  | checkpoint | Date of Installation
checkpoint-status |  |  | checkpoint | Installation team completing the install today
label | 2e9de6a9-8443-50b6-8719-3f96e702f0c9 |  | note | List names in comments
checkpoint-status |  |  | checkpoint | Exclusion Zone is set up (PHOTO REQUIRED of the exclusion zone)
checkpoint-status |  |  | checkpoint | Plant & Equipment prestart/logbooks filled out (PHOTO REQUIRED of logbooks)
checkpoint-status |  |  | checkpoint | Toolbox Talk / Pre-Start has been completed (PHOTO REQUIRED of talk)
checkpoint-group |  |  | section | Summary of the day
checkpoint-status |  |  | checkpoint | Hours worked
select | 78d03587-565c-5bab-926a-b4740dbf00a7 |  | dropdown | Time started on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 3c43c761-e0cc-5dda-a17e-e255c537b145 |  | dropdown | Time finished on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-status |  |  | checkpoint | Elements Installed today
label | 4d0b8069-eb4f-5b81-95fc-08e191d04ec9 |  | note | COMMENT below if number of elements installed doesn't match the Load Lists in the Safe Load Declarations
select | 2ada973d-8803-5f88-8f23-e67ec388aa3e |  | dropdown | How many elements were installed today? | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28, 29, 30, 31, 32, 33, 34, 35, 36, 37, 38, 39, 40
checkpoint-status |  |  | checkpoint | Were there any delays?
label | 87faf9ba-5e3f-5b3d-aaee-0a556769d8b7 |  | note | COMMENT below in enough detail to explain the delay and what caused it. Add PHOTO if it helps record the delay.
select | d3140643-7f44-5203-8eb3-18b5642f0f44 |  | dropdown | How long was the delay? | N/A, 30mins, 1hr, 1.5hr, 2hr, 2.5hr, 3hr, 3.5hr, 4hr, 4.5hr, 5hr, 5.5hr, 6hr, 6.5hr, 7hr, 7.5hr, 8hr
select | 58046ee7-6a2f-55a4-9755-818c7abe3b68 |  | dropdown | How many installers were impacted by the delay/s? | 1, 2, 3, 4, 5, 6
select | ede201f0-4afc-511e-b34f-570146242cef |  | dropdown | How many trucks were impacted by the delay/s? | 1, 2, 3, 4, 5, 6
checkpoint-status |  |  | checkpoint | Builder sign-off
label | f4a9c5b1-6546-51e0-a12c-90fcd787c5e0 |  | note | By signing below you acknowledge the above summary as a true and accurate record of the day.
holdpoint |  |  | signoff | Builder Signature (must be authorised person)