## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Deckwork |  |  |  |  | Yes | Deckwork | 009e91a3-ba4b-4847-b44b-ed273af6745a
checkpoint-status |  |  | checkpoint | The correct drawing has been used. Is it issued for construction and which issue is it
checkpoint-status |  |  | checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint-status |  |  | checkpoint | Appropriate materials have been used for application, also sizing is correct
checkpoint-status |  |  | checkpoint | Invert levels been checked, pipework has correct fall as per drawing
checkpoint-status |  |  | checkpoint | Fire Collars are secured properly
checkpoint-status |  |  | checkpoint | Q/A been done to ensure all collars and pipework is in place and in correct postion (Plan attached)
checkpoint-status |  |  | checkpoint | Fire collars are approved for there application
holdpoint |  |  | signoff | Signed off by Commodore Plumbing & RCC
checklist-flat |  |  | checklist | Wall and Ceiling Pressure Services Checklist |  |  |  |  | Yes | Wall and Ceiling Pressure Services Checklist | 64e996a6-d184-42ee-948d-4c6a8d89e3af
checkpoint-status |  |  | checkpoint | The correct drawings have been used and issued for construction
checkpoint-status |  |  | checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint-status |  |  | checkpoint | Appropriate materials have been used for application and sizing is as per drawings
checkpoint-status |  |  | checkpoint | Meter marks have been issued by RCC and works have been completed off them
checkpoint-status |  |  | checkpoint | Q/A been done to ensure all pipework/fittings is in place and in correct position
checkpoint-status |  |  | checkpoint | All pipework is installed and secured as per AS/NZS 3500
checkpoint-status |  |  | checkpoint | Pipework has been pressure tested for 24 hours - attach photo of pressure gauge
checkpoint-status |  |  | checkpoint | Stud grommets are installed and pipes through studs are siliconed
checkpoint-status |  |  | checkpoint | Check for cross connections
holdpoint |  |  | signoff | Signed off by Commodore Plumbing & RCC
checklist-flat |  |  | checklist | In Ground Sewer Checklist |  |  |  |  | Yes | In Ground Sewer Checklist | 8a7f589c-b816-4781-9817-81c1cbcd6617
checkpoint-status |  |  | checkpoint | The correct drawing has been used and it is issued for construction
checkpoint-status |  |  | checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint-status |  |  | checkpoint | Appropriate materials have been used for application and sizing is as per drawings
checkpoint-status |  |  | checkpoint | Invert levels been checked, pipework has correct fall as per drawing
checkpoint-status |  |  | checkpoint | Pipework bedding is correct material and depth
checkpoint-status |  |  | checkpoint | Q/A been done to ensure all pipework is in place and in correct position
checkpoint-status |  |  | checkpoint | All pipework is installed as per AS/NZS 3500
checkpoint-status |  |  | checkpoint | All floor wastes are charged by a fixture
checkpoint-status |  |  | checkpoint | All open ends are capped off/taped off
holdpoint |  |  | signoff | Signed off by Commodore Plumbing & RCC
checklist-flat |  |  | checklist | In Ground Stormwater Checklist |  |  |  |  | Yes | In Ground Stormwater Checklist | 9695a34b-3c88-4eaf-8b78-a7f70936cff6
checkpoint-status |  |  | checkpoint | The correct drawing has been used. Is it issued for construction and which issue is it
checkpoint-status |  |  | checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint-status |  |  | checkpoint | Appropriate materials have been used for application, also sizing is correct
checkpoint-status |  |  | checkpoint | Invert levels been checked, pipework has correct fall as per drawing
checkpoint-status |  |  | checkpoint | Pipework is secured properly, penetrations through pits are correct (pits by others)
checkpoint-status |  |  | checkpoint | Q/A been done to ensure all pipework is in place and in correct position (Plan attached)
checkpoint-status |  |  | checkpoint | Pipework has been tested and are all open ends capped/taped off
holdpoint |  |  | signoff | Signed off by Commodore Plumbing & RCC
checklist-flat |  |  | checklist | Stacks Checklist |  |  |  |  | Yes | Stacks Checklist | f291bbf8-0cd7-4812-b0e0-5cb5a27f9fab
checkpoint-status |  |  | checkpoint | Has the correct drawing been used. Is it issued for construction
checkpoint-status |  |  | checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint-status |  |  | checkpoint | Pipework is co-ordinated with other trades and finished ceiling heights
checkpoint-status |  |  | checkpoint | Pipework has correct fall and is sized correctly
checkpoint-status |  |  | checkpoint | Stackwork has been water tested and visual inspection for leaks
checkpoint-status |  |  | checkpoint | Stack cap has been removed
checkpoint-status |  |  | checkpoint | Stackwork has been clipped as per ASNZS3500
checkpoint-status |  |  | checkpoint | Stackwork is acoustically lagged if applicable
holdpoint |  |  | signoff | Signed off by Commodore Plumbing & RCC
checklist-flat |  |  | checklist | Trade Waste Checklist |  |  |  |  | Yes | Trade Waste Checklist | f7ad42f7-9af8-440e-9a08-a513d1b399a7
checkpoint-status |  |  | checkpoint | The correct drawing has been used. Is it issued for construction and which issue is it
checkpoint-status |  |  | checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint-status |  |  | checkpoint | Appropriate materials have been used for application, also sizing is correct
checkpoint-status |  |  | checkpoint | Invert levels been checked, pipework has correct fall as per drawing
checkpoint-status |  |  | checkpoint | Pipework is secured properly
checkpoint-status |  |  | checkpoint | Q/A been done to ensure all pipework is in place and in correct postion (Plan attached)
checkpoint-status |  |  | checkpoint | Pipework has been tested and are all open ends capped/taped off
holdpoint |  |  | signoff | Signed off by Commodore Plumbing & RCC
checklist-flat |  |  | checklist | In Ground Pressure Services Checklist |  |  |  |  | Yes | In Ground Pressure Services Checklist | fdf960d3-5bad-4f37-b66c-5c4fef692859
checkpoint-status |  |  | checkpoint | The correct drawing has been used and it is issued for construction
checkpoint-status |  |  | checkpoint | All workers been inducted and read appropriate SWMS for tasks and prestart signed
checkpoint-status |  |  | checkpoint | Appropriate materials have been used for application and sizing is as per drawings
checkpoint-status |  |  | checkpoint | Pipework bedding is correct material and depth
checkpoint-status |  |  | checkpoint | Q/A been done to ensure all pipework is in place and in correct position
checkpoint-status |  |  | checkpoint | All pipework is installed as per AS/NZS 3500
checkpoint-status |  |  | checkpoint | Pipework has been pressure tested for 24 hours - attach photo of pressure gauge
checkpoint-status |  |  | checkpoint | All open ends are capped off/taped off
holdpoint |  |  | signoff | Signed off by Commodore Plumbing & RCC