## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | WOAP - ITP001 Pavement | itp |  |  |  |  | WOAP - ITP001 Pavement
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings C10, C11, C12, C20, C21, C22, C30, C31, C40, C41, C42,C43, C44, C45, C50, C60, C61
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Project Manager
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP,& SWMS.
label | REFERENCE DOCUMENTS: EMP, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Project Manager
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Survey Set-Out
label | FREQUENCY: Prior to commencement of excavation.
label | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Verify using GPS Model
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Supervisor
date | Date Completed:
checkpoint | 2.2 - Excavation Permit
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Project Manager
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Lot 1
checkpoint | 3.1 - Subgrade Material Properties
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: In situ material within 400mm of cut floor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%. If parameter met, rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
label | INSPECTION/TEST METHOD: Site Inspection, Test Report
label | RECORD OF CONFORMITY: Signed ITP, Test Report
label | TP
label | RESPONSIBILITY: Site Supervisor, Geotech Inspection
date | Date Completed:
checkpoint | 3.2 - Subgrade Inspection of Material
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Subgrade Material Classified as Silt
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Geotech Engineer
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP, Area treated detailed on marked up drawing
label | HP
label | RESPONSIBILITY: Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Subgrade Acceptance
label | FREQUENCY: Prior construction of the regulating layer.
label | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of subgrade shall be presented for acceptance. Bulk Excavation Level Confirmed.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Site Inspection, Document Review, GPS Model, Proof Rolling
label | RECORD OF CONFORMITY: Signed ITP, Photos, Videos
label | HP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Subgrade Unsuitable Material
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, proposed in-situ treatment must be submitted to the Project Manager for review.
label | INSPECTION/TEST METHOD: Visual Inspection, Proof Roll
label | RECORD OF CONFORMITY: Signed ITP & Test Reports
label | HP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Subgrade Groundwater
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the Project Manager who shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP & Test Reports
label | HP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Subbase – Rock Placement
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: 200mm Compacted Thickness of 40mm recycled crushed concrete placed in 100mm layers
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Site Inspection/ GPS Survey Report
label | RECORD OF CONFORMITY: GPS Survey
label | SCP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
checkpoint | 3.8 - Subbase – Rock Placement
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: 200mm Compacted Thickness of 20mm Class 2 crushed rock placed in 100mm layers
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Site Inspection/ GPS Survey Report
label | RECORD OF CONFORMITY: GPS Survey
label | SCP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
checkpoint | 3.9 - Subbase Trimming and level conformity
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | Level tolerances:
label | ○ Range x = +5, -25mm
label | ○ Max S = 15 mm
label | ○ 40 measurements per lot (Scale B)
label | INSPECTION/TEST METHOD: Site Inspection/ GPS Survey Report
label | RECORD OF CONFORMITY: GPS Survey
label | SCP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
checkpoint | 3.10 - Subbase Test Rolling
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: No visible deformation or springing. Pneumatic tyred plant nominated for test rolling procedures shall have a mass of not less than 15 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre.
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP, Photos, Videos
label | HP/WP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.11 - Subbase Compaction Testing
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Subbase Rock layers to have minimum compaction 98%.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Signed ITP & Test Report
label | TP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
section | Lot 2
checkpoint | 4.1 - Subgrade Material Properties
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: In situ material within 400mm of cut floor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%. If parameter met, rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Site Inspection, Test Report
label | RECORD OF CONFORMITY: Signed ITP, Test Report
label | TP
label | RESPONSIBILITY: Site Supervisor, Geotech Inspection
date | Date Completed:
checkpoint | 4.2 - Subgrade Inspection of Material
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Subgrade Material Classified as Silt
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Geotech Engineer
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP, Area treated detailed on marked up drawing
label | HP
label | RESPONSIBILITY: Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Subgrade Acceptance
label | FREQUENCY: Prior construction of the regulating layer.
label | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of subgrade shall be presented for acceptance. Bulk Excavation Level Confirmed.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Site Inspection, Document Review, GPS Model, Proof Rolling
label | RECORD OF CONFORMITY: Signed ITP, Photos, Videos
label | HP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Subgrade Unsuitable Material
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, proposed in-situ treatment must be submitted to the Project Manager for review.
label | INSPECTION/TEST METHOD: Visual Inspection, Proof Roll
label | RECORD OF CONFORMITY: Signed ITP & Test Reports
label | HP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6 - Subgrade Groundwater
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the Project Manager who shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP & Test Reports
label | HP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.7 - Subbase – Rock Placement
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: 200mm Compacted Thickness of 40mm recycled crushed concrete placed in 100mm layers
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Site Inspection/ GPS Survey Report
label | RECORD OF CONFORMITY: GPS Survey
label | SCP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
checkpoint | 4.8 - Subbase – Rock Placement
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: 200mm Compacted Thickness of 20mm Class 2 crushed rock placed in 100mm layers
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Site Inspection/ GPS Survey Report
label | RECORD OF CONFORMITY: GPS Survey
label | SCP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
checkpoint | 4.9 - Subbase Trimming and level conformity
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | Level tolerances:
label | ○ Range x = +5, -25mm
label | ○ Max S = 15 mm
label | ○ 40 measurements per lot (Scale B)
label | INSPECTION/TEST METHOD: Site Inspection/ GPS Survey Report
label | RECORD OF CONFORMITY: GPS Survey
label | SCP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
checkpoint | 4.10 - Subbase Test Rolling
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: No visible deformation or springing. Pneumatic tyred plant nominated for test rolling procedures shall have a mass of not less than 15 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre.
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP, Photos, Videos
label | HP/WP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.11 - Subbase Compaction Testing
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Subbase Rock layers to have minimum compaction 98%.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Signed ITP & Test Report
label | TP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
section | Lot 3
checkpoint | 5.1 - Subgrade Material Properties
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: In situ material within 400mm of cut floor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%. If parameter met, rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
label | INSPECTION/TEST METHOD: Site Inspection, Test Report
label | RECORD OF CONFORMITY: Signed ITP, Test Report
label | TP
label | RESPONSIBILITY: Site Supervisor, Geotech Inspection
date | Date Completed:
checkpoint | 5.2 - Subgrade Inspection of Material
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Subgrade Material Classified as Silt
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Geotech Engineer
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP, Area treated detailed on marked up drawing
label | HP
label | RESPONSIBILITY: Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Subgrade Acceptance
label | FREQUENCY: Prior construction of the regulating layer.
label | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of subgrade shall be presented for acceptance. Bulk Excavation Level Confirmed.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Site Inspection, Document Review, GPS Model, Proof Rolling
label | RECORD OF CONFORMITY: Signed ITP, Photos, Videos
label | HP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Subgrade Unsuitable Material
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, proposed in-situ treatment must be submitted to the Project Manager for review.
label | INSPECTION/TEST METHOD: Visual Inspection, Proof Roll
label | RECORD OF CONFORMITY: Signed ITP & Test Reports
label | HP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 - Subgrade Groundwater
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the Project Manager who shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP & Test Reports
label | HP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.7 - Subbase – Rock Placement
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: 200mm Compacted Thickness of 40mm recycled crushed concrete placed in 100mm layers
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Site Inspection/ GPS Survey Report
label | RECORD OF CONFORMITY: GPS Survey
label | SCP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
checkpoint | 5.8 - Subbase – Rock Placement
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: 200mm Compacted Thickness of 20mm Class 2 crushed rock placed in 100mm layers
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Site Inspection/ GPS Survey Report
label | RECORD OF CONFORMITY: GPS Survey
label | SCP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
checkpoint | 5.9 - Subbase Trimming and level conformity
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | Level tolerances:
label | ○ Range x = +5, -25mm
label | ○ Max S = 15 mm
label | ○ 40 measurements per lot (Scale B)
label | INSPECTION/TEST METHOD: Site Inspection/ GPS Survey Report
label | RECORD OF CONFORMITY: GPS Survey
label | SCP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
checkpoint | 5.10 - Subbase Test Rolling
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Rock layers to have minimum compaction 98%.
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Signed ITP & Test Report
label | TP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
checkpoint | 5.11 - Subbase Compaction Testing
label | FREQUENCY: Each lot as required
label | ACCEPTANCE CRITERIA: Subbase Rock layers to have minimum compaction 98%.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Signed ITP & Test Report
label | TP
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: