## ITP-008
ConQA Team Notes:
Document Title: |  | ITP-134-CIV-SSB-Stormwater drainage materials and CCTV
ITP Description: |  | SSB-Stormwater drainage materials and CCTV
Discipline (e.g. CIV/STR/RAIL): |  | 134-CIV
Revision Number: |  | 0
Revision Date: |  | 2023-01-30
ITP created by: |  | Hiruni Wickramarathne
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP for Beaconsfield Station
Inspection & Test Plan -Drainage materials and CCTV
[9 empty] | Revision: | 0
[9 empty] | Date: | 2023-01-30
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 701 (May 2020) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 705 (June 2021) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries-Materials
2.2 | Drainage Flexible Pipes | Section 701.08 | Flexible pipes shall be supplied in accordance with 701.08 Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | Nominated Authority | Teambinder Material Approval
2.3 | Precast Drainage Pit | Section 705.07 Section 705.04 Section 705.09 | Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09 All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041 Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | Nominated Authority | Teambinder Material Approval
2.4 | Cast in Place Drainage Pit | Section 705.06 IFC Drawings | Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings. | Document Review | Each lot | HP | Nominated Authority | Teambinder Material Approval
2.5 | Drainage Pit - Step Irons | Section 705.04 Section 705.12 | Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04 Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12 Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | Nominated Authority | Teambinder Material Approval
2.6 | Drainage Bedding Material | Section 701.09 | Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092. Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | Nominated Authority | Teambinder Material Approval
2.7 | Drainage Backfill Material | Section 701.09 Section 701.19 | Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092. Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19 Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | Nominated Authority | Teambinder Material Approval
5 | Construction / Installation Activities
5.1 | Pits - installation | IFC Drawings VR 701 VR 705 | All the pits for this separable package are installed and respecting Lots are closed | Document review | Eachdrainage separable package | IP | PE | This separable package Pit installation Lots
5.1 | Pipes - installation | IFC Drawings VR 701 VR 705 | All the pipe runs for this separable package are installed and respecting Lots are closed | Document review | Each drainage separable package | IP | PE | This separable package Pipe installation Lots
6 | Post-construction / Post-installation Activities
6.1 | Flushing & CCTV | Section 701.28 Section 701.30 | All culverts shall be flushed clean from end to end on completion and maintained in proper working order. All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects. | Record Review | Each lot | HP | Nominated Authority | This ITP CCTV Reports
6.2 | As Built Survey | Section 701.10 | Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10 | Document Review | Each lot | IP | SE | This ITP As Built Survey Report
6.4 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | PE | This ITP
6.3 | Repairs to Damaged Pipes | Section 701.31 | Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance: • cracks wider than 0.5 mm • spalling of concrete • exposed reinforcement • joints that are not fully engaged. Any pipes with defects greater than the following limits shall be removed and replaced: • longitudinal cracks greater than 2 mm • circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm • circumferential cracks around part of the circumference with width greater than 4 mm • penetrations with area greater than 400 mm2 • pipe joints that are separated. The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments: • hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement • fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm • spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689. The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans. No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures. All repairs shall be inspected using CCTV to verify compliance with the repair specifications. | Document Review for Repair Procedure CCTV Report Review Visul Inspection | Each lot | HP | Nominated Authority | This ITP Approved Repair Procedure Post Repair CCTV Report
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: