## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1630-P200-SYM-QAC-ITP-0028 Installation of Precast Elements | itp |  |  |  |  | 1630-P200-SYM-QAC-ITP-0028 Installation of Precast Elements
section | ITP Details
checkpoint | ITP Details
label | ITP No. - 0028
label | Rev No. - 00
label | Date of Issue - 06/02/2024
label | ITP Type - New
section | 1.0 Pre-start activities
checkpoint | 1.1 - Survey & Set out
label | Ref docs - IFC drawings
label | Acceptance criteria - Limits of work areas / chainage / landing points clearly marked out
label | Freq - Prior to start of works
label | Key - R
label | Resp - SE
checkpoint | 1.2 - Working Platform (as required)
label | Ref docs - Geotechnical Recommendations
label | Acceptance criteria - Working platform prepared in accordance with Geotechnical recommendation
label | Freq - Prior to start of works
label | Key - R
label | Resp - SE
checkpoint | 1.3 - Completed lift Study / Approved lift plan / Critical lift plan
label | Ref docs - VR 620.07
label | Acceptance criteria - Lift study / plan to be prepared and approved by 3rd party engineer with relevant state requirements. Min 5 years’ experience.
label | Freq - Prior to start of works
label | Key - R
label | Resp - SE
checkpoint | 1.4 - Approved Temp works
label | Ref docs - Design Recommendations
label | Acceptance criteria - Temp works used in accordance with temp works IFC design
label | Freq - Prior to start of works
label | Key - R
label | Resp - SE
section | 2.0 Element delivery
checkpoint | 2.1 - Birth certificates
label | Ref docs - Vic roads 620.09
label | Acceptance criteria - All manufactured precast concreate shall be traced from the completion of manufacture to the final location by a unique identification number.
label | ○ Precast elements to be supplied with a birth certificate matching to the ID number of the element to ensure traceability.
label | Freq - Each lot
label | Key - R
label | Resp - SE
checkpoint | 2.2 - On-site inspection
label | Acceptance criteria - Precast elements are clean and free from defects. Date of manufacture & unique ID numbers marked on units. Units transported after 7 days from casting. Visual inspection for signs of defects/damages during transport.
label | Freq - Prior to unloading
label | Key - I
label | Resp - SE
section | 3.0 Installation of precast element
checkpoint | 3.1 - Handling of precast elements
label | Ref docs - VR 620.07
label | Acceptance criteria - Handling of precast elements via designed lifting locations with appropriate lugs/clutches
label | Freq - Each unit
label | Key - I
label | Resp - SE
checkpoint | 3.2 - Erection of Beams and other Precast Units on recently poured underlying concrete members
label | Ref docs - VR 610.27
label | Acceptance criteria - Prestressed and reinforced concrete beams and other concrete members shall not be erected and landed until the specified 28 day concrete compressive strength for piers, abutment, deck or pile caps has been achieved.
label | ○ And not before 14 days after casting or as required by the relevant design package.
label | ○ Beams shall not be placed until at least seven days after the pedestals have been cast.
label | ○ Any relaxations from the above requires approved RFI from designers as well as consultation with MRPV to proceed.
label | Freq - Each unit
label | Key - R
label | Resp - SE
checkpoint | 3.3 - Lifting of Precast Element into Place
label | Ref docs - VR 620.07
label | Acceptance criteria - Precast elements placed in accordance with drawings and survey set‐out points. Lifting clutches approved for use
label | Freq - Each unit
label | Key - R
label | Resp - SE
checkpoint | 3.4 - Propping / Bracing of Precast Element
label | Ref docs - Design Recommendation
label | Acceptance criteria - Propping used in accordance with design recommendation and manufacturers specification – not to be removed till element cast in place with stich pour
label | Freq - Each unit
label | Key - I
label | Resp - SE
checkpoint | 3.5 - Secure Precast element against slipping
label | Ref docs - Design Recommendation, P
label | Acceptance criteria - Precast element secured against slipping as per design recommendation – not to be removed till element cast in place with stich pour
label | Freq - Each unit
label | Key - I
label | Resp - SE
checkpoint | 3.6 - Grout Infill ﴾where required﴿
label | Ref docs - Design Recommendation, VR 610.33
label | Acceptance criteria - Grouting placed in accordance with design recommendation; not to be conducted till element secured in place with stich pour, and sealed against leakage.
label | ○ Grout used to be approved & appropriate for use.
label | ○ Test cubes taken in accordance with VR spec
label | Freq - Each unit
label | Key - R
label | Resp - SE
section | 4.0 Work Lot Close Out
checkpoint | 5.1 - Survey As-built
label | Acceptance criteria - As‐built survey is within tolerance when compared to design specifications. IFC marked up with redlines.
label | Freq - Each lot
label | Key - R
label | Resp - SE
checkpoint | 5.2 - Concrete Patch Repairs (as required)
label | Ref docs - Design Recommendation, VR 610.31
label | Acceptance criteria - Minor imperfections not conforming to the class of surface finish to be repaired
label | Freq - Each lot
label | Key - I
label | Resp - SE
checkpoint | 5.3 - Final Inspection with Subcontractor
label | Acceptance criteria - Works completed in accordance with approved drawings and any relevant specifications
label | Freq - Each lot
label | Key - I
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Completed Checklist (if applicable) and reports and other compliance records attached.
checkpoint | 5.4 - Product Non-Conformance
label | Ref docs - QMP
label | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | Freq - Each lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - NCR reports