## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 84547920-a74c-4ece-b188-4ee26828e461 |  | checklist | ITP-001 - Installation Of Stormwater Drainage |  |  |  |  | Yes | ITP-001 - Installation Of Stormwater Drainage | 3ca677de-3c44-4b89-8ccb-a48b084de7de
checkpoint-group | cb94caea-bd31-482b-8511-cd652d7d468d |  | section | Pre-Construction
checkpoint-status | abc8bbde-8f2d-4aa0-bc10-df523f7f303c |  | checkpoint | Are approved "For Construction" plans available?
checkpoint-status | d4ac7a61-b635-4c8e-8331-ca2bfe3359da |  | checkpoint | Are Earthworks completed to Finished Level?
checkpoint-status | 750ca514-2521-43db-b3eb-e093107661e3 |  | checkpoint | Has the Client been advised of start date?
text | 22ea6f2d-1369-5dee-bd76-b1f6af1b4c12 |  | textbox | Pit / Line Information:
text | c93655f9-7d0d-5a33-ad4b-a021e4974d4e |  | textbox | Date Works Commenced:
checkpoint-status | 7b76357f-b80f-483f-b7e5-106f58ad9fc6 |  | checkpoint | Existing services located and clearly marked (attach DBYD if applicable)
checkpoint-status | 1473847f-0d23-4d12-afdd-6e9ddb307e63 |  | checkpoint | All materials delivered to site have been inspected thoroughly and: a) Are free of damage/cracks b) Pipe class, type and size matches plans. (upload images of damaged materials here)
holdpoint | 4d324994-4a89-4ef0-af74-7ab074f3ed3c |  | signoff | HOLD POINT - Clients representative to acknowledge materials have been inspected and are free of damage/cracks.
checkpoint-group | ff130204-b5ba-4448-8876-a33379016e01 |  | section | Construction
checkpoint-status | ce15851d-c1ad-4f3d-9f5d-bcefc500d450 |  | checkpoint | Excavation Permit Completed
checkpoint-status | 0315e98d-f93a-47a6-a669-a205ef3b1d21 |  | checkpoint | Pits/Trenches set out clearly & accurately
checkpoint-status | ddb0b98c-b9bb-416c-bb89-67478c8b4627 |  | checkpoint | Pits excavated to depth and checked with laser (allowed for 100mm bedding)
checkpoint-status | 3b9c70fd-65c3-4707-a6e5-e75db0b34a05 |  | checkpoint | Pits exceeding 1.5m are correctly battered or compliant shoring installed
checkpoint-status | 67309e00-5227-43b2-ac41-b803c91e481b |  | checkpoint | Pits Installed at correct height and orientation
checkpoint-status | 6372a54d-6b46-4339-ab6e-8aace1acda57 |  | checkpoint | Trenches excavated to depth and checked with grade laser (allowed for 100mm bedding)
checkpoint-status | c15a3ff4-9078-4b0e-9e01-d71a758569cb |  | checkpoint | Trenches exceeding 1.5m are correctly battered or compliant shoring installed
holdpoint | 50e8fd1a-2b7f-4c7e-8669-51ee79090641 |  | signoff | HOLD POINT - Presence of groundwater or contaminated material authorisation to proceed Requested & Approved (If Applicable)
checkpoint-status | 202ea3f2-d935-40da-9309-f8dee1750ec9 |  | checkpoint | Trench bedding material installed as per specification
checkpoint-status | 8db7362d-fcdc-41df-af19-8c1d3755efc9 |  | checkpoint | Pipe laid to grade (as per drawings) ensuring socket faces upstream and is free of foreign materials prior to installation of adjoining pipe
checkpoint-status | 4e60f8d5-5f3a-471b-845d-466deb3fc608 |  | checkpoint | Each joint visually inspected (rubber rings, witness marks, etc) and lifting holes plugged
holdpoint | 44184048-fa72-4a64-8662-233bf6d26a69 |  | signoff | HOLD POINT - Clients representative to acknowledge compliant Pipe/Pit Installation
checkpoint-group | 96c18bbd-f8aa-4576-8e7c-e14a37c0e28e |  | section | Backfill
checkpoint-status | 75600bb9-c18f-4d6c-a64e-134ffa288510 |  | checkpoint | Suitable material backfilled in layers not exceeding 150mm compacted thickness
holdpoint | ed276ddd-0931-4604-8024-7c3d81b089b1 |  | signoff | HOLD POINT - Clients representative to acknowledge Bedding, Haunching & backfill compliance
checkpoint-status | 161305c1-b457-4106-976c-9f9d7e2e5d65 |  | checkpoint | Compaction testing Completed and Complies (attach compaction test results)
checkpoint-status | b406617d-6ae7-4a8d-b960-9c14c2ece076 |  | checkpoint | CCTV Carried out upon completion of works (If applicable)
text | c6a85456-2463-5054-b9cf-cd62d14b3879 |  | textbox | Date Section Completed
text | 43cd04c8-f0e2-5c3f-832d-051fe8f49f71 |  | textbox | Additional Comments
label | 9d39f5c5-f7a1-5a62-8cc5-bebc92d02c74 |  | note | Concrete Dockets attached
label | 9bc45165-8474-5525-ab37-68740e7204d0 |  | note | Concrete Test Reports Attached
label | dd6e6dd1-1fe6-56ea-8648-34c93aa84853 |  | note | Images of works
holdpoint | 46f6858a-7fe4-4d36-a82b-4c3f28dd7f99 |  | signoff | Signatures
checklist-sectioned | e547b5b1-d0a1-4cec-bfbb-544dc85da65d |  | checklist | ITP - Flood Recovery Combined |  |  |  |  | Yes | ITP - Flood Recovery Combined | a678c691-2bbc-4ddd-ab8e-33f100282a6e
checkpoint-group | a8f09b49-d702-416a-8383-25113eff35ac |  | section | Preliminaries - Project Management Responsibility
checkpoint-status | 83347f70-cd0d-4a71-8673-269330b38407 |  | checkpoint | Possession of Site
text | deec7287-f45f-503b-b8ef-d0ca3247f6c0 |  | textbox | Date of possession:
checkpoint-status | b70ba7f3-dd1b-46fd-8983-5b4f3b788a29 |  | checkpoint | Dial Before You Dig (DBYD) and Permit to Excavate completed and signed onto by personnel - HOLD POINT REQUIRED
holdpoint | 8d048e8e-2245-4c96-a09e-03411caea7b5 |  | signoff | Confirmation of DBYD uploaded to CONQA and acknowledged by RCC PM and Supervisor
checkpoint-status | 74b80535-a657-485c-ac49-ae3758ccf9b9 |  | checkpoint | TSC Scope Agreed
text | 5a0831a4-26d4-5cce-acb8-d48dbd6495dd |  | textbox | (Upload scope doc here)
holdpoint | 7157baa8-92cf-4549-b69e-66d0036664df |  | signoff | Confirmation of Scope and Extent of Works with Project Team, including RCC and TSC
checkpoint-status | 65756d7b-e275-4edd-9720-c5b9bfca6ed9 |  | checkpoint | Variations to Scope
text | cfa006d3-348e-5083-9409-5ab64fcbd67f |  | textbox | Details any Variations below and confirm if these have been uploaded to Assigner:
holdpoint | b4c738fd-5b90-4d35-997f-5ddebfedb073 |  | signoff | Confirmation of any variations to scope of work
checkpoint-status | 7fd88817-f76a-4a0b-a290-9e845dba3913 |  | checkpoint | Testing required for the scope:
text | d6072286-1a93-53b1-ab84-7385f69a526c |  | textbox | Concrete testing
text | 88d1b87d-1609-5b0a-84bd-684e59ae1ddf |  | textbox | Density Testing
text | d0f33317-0445-55bd-a953-e62174841e29 |  | textbox | Gravel Testing Other
text | 077d7b80-c958-5311-ba3f-be1734362d79 |  | textbox | Other
checkpoint-status | bb5e820b-4218-4834-bdf6-09044bcc5426 |  | checkpoint | Traffic Control – TGS approved and appropriately selected for the works
checkpoint-status | 44faa37c-cabe-4042-8cf2-862b05fefc87 |  | checkpoint | TGS No
checkpoint-status | 84e3c3b3-78d4-424a-a1d4-69c10c6709fe |  | checkpoint | Erosion and Sediment Control:
text | df89c83d-8e69-5328-b6de-8f997e9a9e77 |  | textbox | Silt Boom Earth Bund
text | b8452f3f-0925-5881-b9ea-0097631a7ca2 |  | textbox | Sediment Fence
text | 9d4719f8-ea05-58b7-8a3b-dddbd5f1104f |  | textbox | Other
checkpoint-group | 9abbc2e0-e059-46fc-aab9-20c1f818f8e3 |  | section | C213 Earthworks
checkpoint-status | 748d7293-2b10-4781-aabf-343cbc996965 |  | checkpoint | Minor clearing of vegetation undertaken – where applicable.
checkpoint-status | 4499ec1f-8313-414a-80fd-7e559408969e |  | checkpoint | Demolition works / Spoil Removal undertaken and spoil removed from site to Quirks Quarry - HOLD POINT REQUIRED
label | 826175d6-2821-55cd-851b-8e12828d6018 |  | note | TSC Direction
checkpoint-status | 1c9bce0d-29d4-4eda-bc3a-ea26892720df |  | checkpoint | Is subgrade or sub base suitable
holdpoint | 1af0709a-622f-46f8-96e7-53a86986d9b2 |  | signoff | HOLD POINT: If unsuitable is encountered TSC to be notified prior to works continuing
checkpoint-status | 13829375-1942-42d1-887d-8d3f5e6f3314 |  | checkpoint | Table drains shaped to allow water to flow freely and best marry into existing surfaces.
checkpoint-group | 27f6be8d-f4e4-489d-8360-0daf52390f89 |  | section | C242 Flexible Pavements
checkpoint-status | 9b3a76d0-db17-46ef-a579-eaed9e59271e |  | checkpoint | Proof roll subgrade: If foundation fails TSC to be notified and to site instruction required - HOLD POINT REQUIRED
label | 3045f108-f4ae-5ddb-a8d1-825d8d602377 |  | note | TSC Approval
holdpoint | e4247952-5028-4716-8ba6-4c35a0e494bf |  | signoff | HOLD POINT
checkpoint-status | daa9681d-d8a8-4d0b-8011-7b6e27686363 |  | checkpoint | Road base Material: Material source along with conforming material NATA test certificates have been submitted and approved by the Principal (Material Stockpile Lot)
checkpoint-status | 82351fd0-7695-46b1-9a40-20d3706c142f |  | checkpoint | If testing required - Layers compacted to 100% Standard compaction for full formation width. Compaction testing to be done 1 test per 500m2, minimum of 3 test taken at a time (per lot) or as directed otherwise.
checkpoint-status | f9a49572-a28e-4a8f-b410-869907bff6ef |  | checkpoint | Levels of gravel marry into existing and deviation does not exceed 12mm over the length of a 3m straight edge.
holdpoint | 682915e8-6be0-4480-b7b2-9e4f250dc02b |  | signoff | HOLD POINT – Carry out a proof roll of finished pavement where applicable
checkpoint-group | 44b96ee5-07bc-44e6-ad9b-08af1bab6814 |  | section | Rock Revetment
checkpoint-status | 434142de-6c79-4e13-b082-8a98259bb0c9 |  | checkpoint | Geotextile – A34 Geotextile separator placed prior to rock placement IF DIRECTED or WITHIN SCOPE
checkpoint-status | e2b57e31-a6cd-423e-8f97-5926e67fbe87 |  | checkpoint | Rock Placement - Rock to be placed in completed drain profile as per agreed scope. Correct Rock Size Placed
text | db56694c-4f9e-5b67-95b3-81bb8a05f89f |  | textbox | 40-70mm - Quantity
text | f277fbdc-96c9-5518-a47b-35d374b7af3a |  | textbox | 150-250mm - Quantity
text | c4974332-1556-5786-ada6-151fc20c47d3 |  | textbox | 300-500mm - Quantity
text | 9ec1a032-2c78-5437-89ce-af19b490ce9e |  | textbox | 600-900mm - Quantity
text | 9866f571-fb56-5d8f-8db8-e6d083fb9283 |  | textbox | Other
checkpoint-group | 4e126908-31e7-4dfc-8da9-6c2b62ceb774 |  | section | Grouted Rock Pitching
checkpoint-status | cba87760-c691-4da0-9438-640543ba1052 |  | checkpoint | Existing rock to be grouted as per agreed scope
text | fb78ba51-f918-5ec6-9eaa-dd8fce0a5bac |  | textbox | Approx m2
checkpoint-status | 376b41c9-f347-42d1-9c56-4b108c5dcda0 |  | checkpoint | Rocks to be cleaned down at end of grouting for neat finish
checkpoint-group | d30db0c4-9c61-4ecd-91b2-ca49840e6ad9 |  | section | Concrete Works
checkpoint-status | a4b39cf5-a0b0-4dd2-bd50-dc5feed15352 |  | checkpoint | Excavation & Preparation - Suitable subgrade material and prepared to suitable surface
checkpoint-status | 3709a941-e59c-4223-a98c-1f060a46d780 |  | checkpoint | Formwork & Reinforcement - Dimensions and positions of forms shall be carefully checked after the forms are erected. Forms shall be aligned accurately and the location of all fittings, hold formers etc. checked prior to placing of concrete.
checkpoint-status | 40412a65-f284-4e42-be7f-3a5ee073eacc |  | checkpoint | Formwork & Reinforcement - Placing of reinforcement as per agreed scope, with reference to Typical Construction Details. Reinforcement to maintain a 50mm vertical and horizontal cover unless directed otherwise.
text | ab4c65f7-1a0c-55d8-aa85-0ded6be607f8 |  | textbox | TSC Approval
holdpoint | 34b028fb-66ed-42e8-9cb5-a14e57f8b06d |  | signoff | HOLD POINT – PRE-POUR INSPECTION The formwork shall be inspected by the Superintendent, and the placing of reinforcement in the spaces formed, where specified, shall not commence until the formwork is approved by the Superintendent.
checkpoint-status | 875b1a54-6f90-4ec3-8a47-a34fc3dfd604 |  | checkpoint | Ready Mix Concrete - The concrete shall be mixed and delivered in accordance with the requirements of AS 1379 - PLEASE ATTACH OR TAKE PHOTOS OF LAST DOCKETS FROM EACH POUR
text | ba254f67-baa5-5973-aced-0d79d08bc581 |  | textbox | Concrete Mix Used:
text | b002126e-9cd4-5055-a65c-f013de92fc4b |  | textbox | 20/20/80
text | ab94d363-52c8-5e1a-8924-1d21f742b628 |  | textbox | 25/20/80
text | d85c42d0-d698-540f-8f2d-2824d50098d9 |  | textbox | 32/20/80
text | 724669f4-81a7-5548-ad29-6cefb2cbd8c1 |  | textbox | 32/20/100
text | fafd4d73-4c8b-502c-a5d0-4510b48d4b75 |  | textbox | 40/20/80
text | b261ab8d-fb88-5e47-b978-5774c2ed7bf7 |  | textbox | Grout
text | 2ea9a3cf-8628-57e6-8105-cb43b44d30f2 |  | textbox | Shotcrete Shotcrete w/ poly-fibre
text | 67c58a2a-ce95-599a-9551-c286ef433107 |  | textbox | Other
checkpoint-status | df406511-0a14-434b-85bc-642e112e3cb0 |  | checkpoint | Concrete Placement - Concrete finished to TSC Standard
checkpoint-status | a0250777-c3a4-4fc3-9a9c-31bc5153487a |  | checkpoint | Two pairs of test specimens shall be moulded for each 15 cubic metres of concrete, or part thereof, one pair being intended for the 7-day test if required and the other pair for a 28-day test.
holdpoint | 28da5238-7b5e-4c95-9165-992eae19c9bc |  | signoff | WITNESS POINT: Concrete test specimens to be taken in presence of Superintendent or Superintendent’s representative
checkpoint-group | caf86df7-c8e6-40a2-9d59-ab422d303aff |  | section | Stormwater Drainage
checkpoint-status | 6589e29f-6aee-4e22-8d6a-84d1034b8aa0 |  | checkpoint | Stormwater components installed as per scope of works - HOLD POINT REQUIRED
text | 979ac19f-73cc-5a80-86ad-1e500310a5e9 |  | textbox | Size & quantity of pipe & pits installed
text | 893b0e0c-e4e2-5d53-8308-45ce6ad9920f |  | textbox | Other
holdpoint | ff7bfe5c-1b0d-4c27-ae4f-0e105d32ee2b |  | signoff | HOLD POINT: Inspection prior to backfill
checkpoint-status | 0ba69685-6ea2-412c-ab89-5010c50f0111 |  | checkpoint | Density testing of pipeline required if within roadway:- 100% compaction to be achieved
checkpoint-group | 130d2b12-0472-43f5-af6c-01f3f8a957b1 |  | section | Demobilisation
checkpoint-status | 9688c3c0-d2a4-489d-8cc7-08d75b328534 |  | checkpoint | Site left tidy & DM spray mark removed
checkpoint-group | 1db51bf5-0574-4bde-ba11-8dd581b63eff |  | section | Close Out
checkpoint-status | b59bfe74-8758-4371-ab0d-b1210a53c849 |  | checkpoint | Site Handover: All works complete, demobilised and site handed back to TSC
text | 45097fcd-2c9a-594e-b19d-3058f3f26768 |  | textbox | Date of handback
holdpoint | 0fef3379-59d9-4215-8d3b-3b0601cebeb1 |  | signoff | TSC Signature
checkpoint-status | 966fbd6c-efc7-48fa-94f1-87f164e0d3ee |  | checkpoint | Verify conformance including close out of NCR’s
text | 5885fb03-6f69-5c06-8bf9-2bc75018cbc7 |  | textbox | NCR NO:
label | 93c4a92f-233a-5c02-9690-b0a949e187f5 |  | note | NATA Certificates
label | 81a62b56-6729-5c84-bd64-b0053197ea7e |  | note | Survey Report
label | ef604807-0a18-5333-8f35-adfa3ea2015e |  | note | Geotechnical testing reports
label | 05774f72-b919-5a32-a1da-21042c2a4880 |  | note | Concrete test reports
label | d5a75f28-0c81-526c-a2bb-dd68be86fc04 |  | note | Proof of works report
label | b87c0249-7aa3-5815-9fbb-baeec2b84a49 |  | note | Photographs of completed work
checkpoint-status | eafdfaac-0b67-4185-b6f4-743b7f700772 |  | checkpoint | Damage No. (DM) signed off and closed by PM or representative
holdpoint | 594f50a2-ab52-469c-95e6-831977af456f |  | signoff | Signatures
checklist-sectioned | e32ab440-910f-4957-ac5d-2f3a39d4d08f |  | checklist | SYS - ITP - Flood Recovery Combined (archived) |  |  |  |  | Yes | SYS - ITP - Flood Recovery Combined (archived) | efb15ea3-e4f2-415b-8ca1-2938276aa15f
checkpoint-group | da4291ba-661e-4495-8845-d5df5142ea97 |  | section | Preliminaries - Project Management Responsibility
checkpoint-status | 12fef82b-aa37-40db-8a68-c2e17c22fd63 |  | checkpoint | Possession of Site
text | deec7287-f45f-503b-b8ef-d0ca3247f6c0 |  | textbox | Date of possession:
checkpoint-status | 0534d861-d593-4b99-9bc7-9da5c8c7ff3c |  | checkpoint | Dial Before You Dig (DBYD) and Permit to Excavate completed and signed onto by personnel - HOLD POINT REQUIRED
text | 278162db-9fb7-5294-8972-c053a93b0254 |  | textbox | TSC Scope Agreed:
holdpoint | 58ebee3a-5ec6-417d-a581-49abbc36666c |  | signoff | Confirmation of Scope and Extent of Works with Project Team, including RCC and TSC
checkpoint-status | 5d39d263-115a-46b8-b34a-1029c7009479 |  | checkpoint | Testing required for the scope:
text | 5a0831a4-26d4-5cce-acb8-d48dbd6495dd |  | textbox | Concrete testing
text | b2deff86-2233-5b47-8e9f-5d4a0b87ad91 |  | textbox | Density Testing
text | 7a044b24-753f-50bd-a442-306cd8f56748 |  | textbox | Gravel Testing Other
text | 2516ec8b-6a1c-5bb6-baee-065abc6a4483 |  | textbox | Other
checkpoint-status | ca1cf830-9def-4294-a07f-85424cadda6d |  | checkpoint | Traffic Control – TGS approved and appropriately selected for the works
checkpoint-status | 92abbbe1-e569-4193-9f54-0a44b053cc45 |  | checkpoint | TGS No
checkpoint-status | 58ce92e1-6fb2-4953-a09d-c05cd8fedcd9 |  | checkpoint | Erosion and Sediment Control:
text | 71113da9-5057-5e21-9ba1-4e6d9fbf936c |  | textbox | Silt Boom Earth Bund
text | eeea725e-199a-5c8e-9efe-1f306ad7607c |  | textbox | Sediment Fence
text | a565e387-c2dc-52c1-b58b-aae948045caa |  | textbox | Other
checkpoint-group | 40eb814e-ee89-4dc1-a3c0-e5da98a3537d |  | section | C213 Earthworks
checkpoint-status | 7f08798c-5769-4b0b-9fb9-7918ee3f7abf |  | checkpoint | Minor clearing of vegetation undertaken – where applicable.
checkpoint-status | b3be097f-bc68-434e-9f9d-5ee3635905e8 |  | checkpoint | Demolition works / Spoil Removal undertaken and spoil removed from site to Quirks Quarry - HOLD POINT REQUIRED
label | 826175d6-2821-55cd-851b-8e12828d6018 |  | note | TSC Direction
checkpoint-status | ff9314af-f695-4f47-991e-283b036e8a4b |  | checkpoint | Is subgrade or sub base suitable
holdpoint | 1f11c6a9-a206-4322-a87d-310f8ac8e580 |  | signoff | HOLD POINT: If unsuitable is encountered TSC to be notified prior to works continuing
checkpoint-status | 68ab0341-16a6-44ab-a8b9-8a3be471e33c |  | checkpoint | Table drains shaped to allow water to flow freely and best marry into existing surfaces.
checkpoint-group | 6f1956ee-2178-4eb9-9829-433edefe0dab |  | section | C242 Flexible Pavements
checkpoint-status | eb29b47f-1a5f-4150-be91-f18b925db32b |  | checkpoint | Proof roll subgrade: If foundation fails TSC to be notified and to site instruction required - HOLD POINT REQUIRED
label | 3045f108-f4ae-5ddb-a8d1-825d8d602377 |  | note | TSC Approval
holdpoint | d21d4fb0-e74a-499d-845c-685f92807ad6 |  | signoff | HOLD POINT
checkpoint-status | c816d9d0-a6a8-4d98-878f-76f8bc5cf68b |  | checkpoint | Road base Material: Material source along with conforming material NATA test certificates have been submitted and approved by the Principal (Material Stockpile Lot)
checkpoint-status | 5980ff9c-95b6-473e-be34-6b65f9530ab0 |  | checkpoint | If testing required - Layers compacted to 100% Standard compaction for full formation width. Compaction testing to be done 1 test per 500m2, minimum of 3 test taken at a time (per lot) or as directed otherwise.
checkpoint-status | e25652b4-1956-45a9-ba57-9c314d414a46 |  | checkpoint | Levels of gravel marry into existing and deviation does not exceed 12mm over the length of a 3m straight edge.
holdpoint | 12b702b0-12b3-4083-b090-009a1b20f153 |  | signoff | HOLD POINT – Carry out a proof roll of finished pavement where applicable
checkpoint-group | 1dcf00a7-7334-4188-ae4b-fec2462df913 |  | section | Rock Revetment
checkpoint-status | 39a479ca-6c9f-44a4-9e0d-e79dede65113 |  | checkpoint | Geotextile – A34 Geotextile separator placed prior to rock placement IF DIRECTED or WITHIN SCOPE
checkpoint-status | f3ea1c10-e1a0-463e-b2a0-3a6f03d3248b |  | checkpoint | Rock Placement - Rock to be placed in completed drain profile as per agreed scope. Correct Rock Size Placed
text | db56694c-4f9e-5b67-95b3-81bb8a05f89f |  | textbox | 40-70mm - Quantity
text | f277fbdc-96c9-5518-a47b-35d374b7af3a |  | textbox | 150-250mm - Quantity
text | c4974332-1556-5786-ada6-151fc20c47d3 |  | textbox | 300-500mm - Quantity
text | 9ec1a032-2c78-5437-89ce-af19b490ce9e |  | textbox | 600-900mm - Quantity
text | 9866f571-fb56-5d8f-8db8-e6d083fb9283 |  | textbox | Other
checkpoint-group | 17bae73b-a42f-4938-b4d9-4ea181101e5d |  | section | Grouted Rock Pitching
checkpoint-status | 1b63938f-6520-41f7-a6e1-a011515958b5 |  | checkpoint | Existing rock to be grouted as per agreed scope
text | fb78ba51-f918-5ec6-9eaa-dd8fce0a5bac |  | textbox | Approx m2
checkpoint-status | 61589245-1400-404c-bda8-0104ef058750 |  | checkpoint | Rocks to be cleaned down at end of grouting for neat finish
checkpoint-group | f73c29b6-5d1c-4d2f-89db-f6f13d5eae10 |  | section | Concrete Works
checkpoint-status | d555056b-d199-41df-b1ea-a4b0f1100572 |  | checkpoint | Excavation & Preparation - Suitable subgrade material and prepared to suitable surface
checkpoint-status | ccf327dc-a0f4-41b7-9649-6e4d4f5666b2 |  | checkpoint | Formwork & Reinforcement - Dimensions and positions of forms shall be carefully checked after the forms are erected. Forms shall be aligned accurately and the location of all fittings, hold formers etc. checked prior to placing of concrete.
checkpoint-status | 8846ea92-8a53-4322-af35-05318552fad7 |  | checkpoint | Formwork & Reinforcement - Placing of reinforcement as per agreed scope, with reference to Typical Construction Details. Reinforcement to maintain a 50mm vertical and horizontal cover unless directed otherwise.
text | ab4c65f7-1a0c-55d8-aa85-0ded6be607f8 |  | textbox | TSC Approval
holdpoint | 16ffb3a9-4bd3-4bf4-886f-613dfeb47dad |  | signoff | HOLD POINT – PRE-POUR INSPECTION The formwork shall be inspected by the Superintendent, and the placing of reinforcement in the spaces formed, where specified, shall not commence until the formwork is approved by the Superintendent.
checkpoint-status | aa2370d7-db83-44be-a271-97c188ee661d |  | checkpoint | Ready Mix Concrete - The concrete shall be mixed and delivered in accordance with the requirements of AS 1379 - PLEASE ATTACH OR TAKE PHOTOS OF LAST DOCKETS FROM EACH POUR
text | ba254f67-baa5-5973-aced-0d79d08bc581 |  | textbox | Concrete Mix Used:
text | b002126e-9cd4-5055-a65c-f013de92fc4b |  | textbox | 20/20/80
text | ab94d363-52c8-5e1a-8924-1d21f742b628 |  | textbox | 25/20/80
text | d85c42d0-d698-540f-8f2d-2824d50098d9 |  | textbox | 32/20/80
text | 724669f4-81a7-5548-ad29-6cefb2cbd8c1 |  | textbox | 32/20/100
text | fafd4d73-4c8b-502c-a5d0-4510b48d4b75 |  | textbox | 40/20/80
text | b261ab8d-fb88-5e47-b978-5774c2ed7bf7 |  | textbox | Grout
text | 2ea9a3cf-8628-57e6-8105-cb43b44d30f2 |  | textbox | Shotcrete Shotcrete w/ poly-fibre
text | 67c58a2a-ce95-599a-9551-c286ef433107 |  | textbox | Other
checkpoint-status | 7bc48803-5b0b-4ecf-8fe7-6868142e1e59 |  | checkpoint | Concrete Placement - Concrete finished to TSC Standard
checkpoint-status | 2cfa392b-1901-4b9a-8ef0-cb9a5945fc28 |  | checkpoint | Two pairs of test specimens shall be moulded for each 15 cubic metres of concrete, or part thereof, one pair being intended for the 7-day test if required and the other pair for a 28-day test.
holdpoint | 11830ecf-eef0-4e57-b288-5dc3a07719ba |  | signoff | WITNESS POINT: Concrete test specimens to be taken in presence of Superintendent or Superintendent’s representative
checkpoint-group | d7b00c04-06eb-4856-bad9-b7627df90fb7 |  | section | Stormwater Drainage
checkpoint-status | 5ee0cfe8-c88a-4f6a-9589-86de9cf411c0 |  | checkpoint | Stormwater components installed as per scope of works - HOLD POINT REQUIRED
text | 979ac19f-73cc-5a80-86ad-1e500310a5e9 |  | textbox | Size & quantity of pipe & pits installed
text | 893b0e0c-e4e2-5d53-8308-45ce6ad9920f |  | textbox | Other
holdpoint | 26181ee9-7fee-4498-b8e4-54d1eff14ae4 |  | signoff | HOLD POINT: Inspection prior to backfill
checkpoint-status | 0a6643d0-3cce-4655-ae81-1501220c7b4c |  | checkpoint | Density testing of pipeline required if within roadway:- 100% compaction to be achieved
checkpoint-group | 2e08b46a-9dc2-40c7-ac2b-9f0fa6bd45b9 |  | section | Demobilisation
checkpoint-status | a74183f3-ab44-4ad3-9e23-60c78f3de5d1 |  | checkpoint | Site left tidy & DM spray mark removed
checkpoint-group | 739c0bfa-e29f-45c8-8dac-92e765a3ebd7 |  | section | Close Out
checkpoint-status | d292ead3-5e10-4eee-8164-01f6d781e88a |  | checkpoint | Site Handover: All works complete, demobilised and site handed back to TSC
text | 45097fcd-2c9a-594e-b19d-3058f3f26768 |  | textbox | Date of handback
holdpoint | cb6782ad-077b-4580-9704-d6a994c5d17b |  | signoff | TSC Signature
checkpoint-status | bd1b73ea-563d-4970-921f-49464fe364f6 |  | checkpoint | Verify conformance including close out of NCR’s
text | 5885fb03-6f69-5c06-8bf9-2bc75018cbc7 |  | textbox | NCR NO:
label | 93c4a92f-233a-5c02-9690-b0a949e187f5 |  | note | NATA Certificates
label | 81a62b56-6729-5c84-bd64-b0053197ea7e |  | note | Survey Report
label | ef604807-0a18-5333-8f35-adfa3ea2015e |  | note | Geotechnical testing reports
label | 05774f72-b919-5a32-a1da-21042c2a4880 |  | note | Concrete test reports
label | d5a75f28-0c81-526c-a2bb-dd68be86fc04 |  | note | Proof of works report
label | b87c0249-7aa3-5815-9fbb-baeec2b84a49 |  | note | Photographs of completed work
checkpoint-status | a1693cb2-82f4-4735-a67b-7fe6fef38dd2 |  | checkpoint | Damage No. (DM) signed off and closed by PM or representative
holdpoint | 1d2f6bc6-733a-4a61-b03c-1b120f00eb00 |  | signoff | Signatures