## Sheet1
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | F3002D Mangahuini long drop site REV 1 |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: |  |  | Name / Signature | Name / Signature | Site Engineer | Amritpal Singh
Inspection & Test Plan / Checklist | [6 empty] | 30.04.2024 | 30.04.2024 | Quality Eng. | Jose Buenaventura
Lot No:F3002D |  |  |  | Corresponding Work Instruction: |  | https://trecnz.sharepoint.com/:f:/s/ZONEF-SH35-TAIRAWHITI/Es4022E44SVGrVoRrYmNAr4BExrkT-CsDDn6vlhwfcnB1A?e=YTx1Q7 |  | Compliance with Work Instructions and Specifications
Detailed Location:SH35 RS225. RP7.802
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Specification/Drawings Reference | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
Section 1: RECEIVING INSPECTIONS
1.1 | Buttress Rock Armour (D50=800mm) | W | F3002D 2-U3436.BM | Prior to commencement | Supplier material test certificate | Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 to 800mm with a minimum specific Gravity SG of 2350kg/m3. | Material source test results, Delivery dockets, Photo's | Site Engineer
1.2 | Culvert Rip rap rock (D50 = 500mm) | W | F3002D 2-U3436.BM | Prior to commencement | Supplier material test certificate | Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 to 500mm with a minimum specific Gravity SG of 2350kg/m | Material source test results, Delivery dockets, Photo's | Site Engineer
1.3 | Drainage material | W | F3002D 2-U3436.BM, TNZ F/2 | Prior to commencement | Supplier material test certificate | Comply with TNZ F/2 or approved equivalent. | Material source test results, Delivery dockets | Site Engineer
1.4 | AP65 Granular fill | W | F3002D 2-U3436.BM | Prior to commencement | Particle size distribution test | Test results from a representative general fill sample tested in an independent accredited laboratory | Material compliance cert, delivery dockets | Site Engineer
1.5 | Geogrid: Miragrid 80/20 Biaxial Grid or Similar Approved | W | Mangahauini Long Drop Site NTC F3002D SH35RS225RP7.8 final | Prior to installation | Supplier material test certificate | Delivery dockets with roll details. Check information on the delivery docket against the requirements indicated on the Drawings. | Material compliance cert, delivery dockets | Site Engineer
1.6 | Class D A49 Geotextile | W | F3002D 2-U3436.BM, NZTA F/7 | Prior to commencement | Manufacturers certificate | Non-woven & NZTA F/7 compliant On dry bed below fill | Material compliance cert, photo's, delivery dockets | Site Engineer
1.7 | Perforated lateral drains | W | F3002D 2-U3436.BM | Prior to commencement | Manufacturers certificate | Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter perforated lateral subsoil drain, or similar approved. | Material compliance cert, photo's, delivery dockets | Site Engineer
1.8
1.8 | Precast concrete box culverts | W | F3002D 2-U3436.BM | Prior to commencement | Manufacturers certificate | Delivery Dockets are collected and signed before precast wing walls are removed from the truck. | Material compliance cert, photo's, delivery dockets | Site Engineer
1.9 | Precast concrete wing walls | W | F3002D 2-U3436.BM | Prior to commencement | Manufacturers certificate | Delivery Dockets are collected and signed before precast wing walls are removed from the truck. | Material compliance cert, photo's, delivery dockets | Site Engineer
1.1 | Precast materials | H |  | Prior to unloading | Visual inspection | Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed | Photo's | Site Engineer | CPS Engineer
1.11 | AP40 (Basecourse) | W | TNZ M/4 | Prior to commencement | Submission | Source property testing | Lab test reports, Delivery dockets | Site Engineer
Traceability of all materials delivered to site
1.12 | AP65 (Sub-base) | W |  | Prior to commencement | Submission | Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak) | Lab test report, Delivery dockets | Site Engineer
1.13 | Grade 2/4 Chip | W | NZTA M/6 | Prior to commencement | Submission | Source property testing | Lab test reports, Delivery dockets | Site Engineer
Traceability of all materials delivered to site
1.14 | Cement Material cert | W |  | Prior to commencement | Submission |  | Material certificate(s) | Site Engineer
1.15 | Bitumen | W | TNZ M/1 | Prior to commencement | Submission | Binder to meet TNZ M/1 standard. E2 Certificate | E2 Certificate | Site Engineer
Section 2: REVETMENT & BACKFILL INSPECTIONS
2.1 | Survey Setout | H | Consistency with Construction Drawing | Prior to commencement | Survey | Set out extents of fill and check against design drawings | Survey receipt | Site Engineer | CPS Engineer
2.2 | Unsuitable loose material and vegetation | W | F3002D 2-U3436.BM | During Construction | Visual Inspection | Remove and clear any vegetation, trees and unsuitable material | Photo's | Site Engineer
2.3 | Subgrade Inspection | H | F3002D 2-U3436.BM | Per area as required | Visual Inspection | Inspect fill foundation Fill foundation must be approved, in writing, before filling commences | CPS COR Report, Photo's | Site Engineer | CPS Engineer
2.4 | Class D (A49) Geotextile placement | M | F3002D 2-U3436.BM | During Construction | Visual Inspection | Excavation undercut to be underlain with Bidim A49 or similar approved before placing granular fill. Bidim layer required between granular fill and rock armour. | Photo's | Site Engineer
2.5 | Sub soil drainage | H | F3002D 2-U3436.BM, TNZ F/2 | At lower bench level and mid bench prior to placing granular fill. | Visual Inspection | Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter perforated lateral subsoil drain, or similar approved. To be inspected and approved by CPS Engineer prior to install | CPS COR Report, Photo's | Site Engineer | CPS Engineer
2.6 | Imported Granular Fill Placement | H | F3002D 2-U3436.BM, NZS4431:2022 | During Construction | Visual Inspection | Granular fill to be placed in layers of maximum 150mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade | CPS COR Report, Photo's | Site Engineer | CPS Engineer
2.7 | Imported Granular Fill Compaction | H | F3002D 2-U3436.BM, NZS 4402:1986, Test 4.1.3 | During Construction | NDM & Clegg hammer testing | A target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3. Testing done as per Site Instruction by CPS Engineer | Test results, Photo's | Site Engineer | CPS Engineer
2.8 | Geogrid Placement | H | Mangahauini Long Drop Site NTC F3002D SH35RS225RP7.8 final | During Construction | Visual Inspection | Geogrid to be placed in engineered fill 300mm thick between geogrid layers. Geogrid to be wrapped with a minimum overlap of 2.0m. Panel overlap on geogrid layers to be minimum 0.5m or manufacturers minimum. | CPS COR Report, Photo's | Site Engineer | CPS Engineer
2.9 | Form and cut fill batter as per design 1.5H:1V | H | F3002D 2-U3436.BM | During Construction | Visual Inspection | Benches to be cut and profiled to suit slope profile | CPS COR Report, Photo's | Site Engineer | CPS Engineer
3 | Rock Armour (50-800dia) to form revetment | M | F3002D 2-U3436.BM | During Construction | Visual Inspection | The buttress is to be keyed in to ground directly behind existing displaced reno mattresses and existing railway line timber panel retaining wall | Photo's | Site Engineer
Section 3:Fish Passage INSPECTIONS
3.1 | Survey Setout | H | NTC F3002 D | During Construction | Visual Inspection | Set out extents of fill and check against design drawings | CPS COR Report, Photo's | Site Engineer | CPS Engineer
3.2 | Void Fillings | H | NTC F3002 D | During Construction | Visual Inspection | Measurements of Materials | CPS COR Report, Photo's | Site Engineer | CPS Engineer
3.3 | Gradient of the fish passage | H | NTC F3002 D | During Construction | Visual Inspection | Set out extents of fill and check against design drawings | CPS COR Report, Photo's | Site Engineer | CPS Engineer
3.4 | Clear, reshape & apply rip rap to culvert inlet | H |  | During Construction | Visual Inspection | As agreed on site with CPS Engineer | CPS COR Report, Photo's | Site Engineer | CPS Engineer
Section 4: PAVEMENT INSPECTIONS
4.1 | Saw cut existing pavement | W |  | Prior to pavement construction | Visual inspection | Smooth and straight saw cut | Photo's | Site Engineer
4.2 | Subgrade construction | W | TNZ B2 | Every 20m and/or at random | NDM testing | 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92% | Subgrade Approval Check sheet, Test (CS-4100) reports | Site Engineer
4.3 | Subgrade Cement Application rate | W |  |  | Bag test | 2% cement stabilisation at 250mm deep subgrade | Bag test records | Site Engineer
4.4 | Pavement construction: Sub base and base course | M | F3002D 2-U3436.BM | During Construction | Visual Inspection | Sub base and base course to be placed in accordance with TNZ B2. Compaction required in accordance with NZS 4407:2015. Cement supplied to NZS3122 and stabilised in accordance with TNZ B/5. | Photo's | Site Engineer
4.5 | Sub-base construction | W | TNZ B2 | Every 20m and/or at random | NDM testing | 200mm thick AP65 sub-base compacted to a minimum dry density of 95% | Test reports | Site Engineer
Average 95% of MDD with nothing less than 92%
4.6 | Sub-base construction | W | TNZ B2 | Every 20m and/or at random | Clegg Hammer testing | CIV>=25 | Clegg Hammer Checksheet (CS-4037c), Test reports, Photo's | Site Engineer
4.7 | Sub-base construction | W | TNZ B2 |  | Survey | Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction | Survey as-builts | Site Engineer
4.8 | Basecourse construction | W | TNZ B2 | Every 20m and/or at random | NDM testing | 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98% | Test reports, Photo's | Site Engineer
Average 98% of MDD with nothing less than 95%
4.9 | Basecourse Cement application rate | W | TNZ B/5 |  | Visual inspection | 2% cement stabilisation at 150mm deep basecourse | Photo's | Site Engineer
4.1 | Basecourse construction | W | TNZ B2 | Every 20m | Survey | Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction | Survey as-builts | Site Engineer
4.11 | Basecourse construction | W | TNZ B2 | Every 20m and/or at random | Clegg Hammer testing | CIV>=25 | Clegg Hammer Checksheet (CS-4037c), Test reports, Photo's | Site Engineer
4.12 | Basecourse construction | W | TNZ B2 | Before sealing | Pre-seal checksheet | Mosaic surface | Photo's, Pre-seal checksheet (CS-4060) | Site Engineer
4.13 | Applying Bitumen | W | NZTA M/6 |  | Visual inspection | Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours | Photo's, Pre-seal checksheet (CS-4060) | Site Engineer
4.14 | Degree of saturation | W |  | Before sealing | Pre-seal checksheet | Degree of saturation should not exceed 80% | Pre-seal checksheet (CS-4060) | Site Engineer
4.15 | Chip seal laying | M | F3002D 2-U3436.BM, NZTA M/6 | During Construction | Visual Inspection | Chip seal will match existing seal. The seal will be placed and compacted in accordance with NZTA P/17. The seal will be rolled in accordance with NZTA P/3 | Photo's | Site Engineer
4.16 | Verge | M | F3002D 2-U3436.BM | During Construction | Visual Inspection | Verge reinstatement to match existing | Photo's | Site Engineer
4.17 | Sweep & Line mark new chip seal road | W | TNZ P/12:2000 | During Construction | Visual inspection | As per TNZ P/12:2000 | Photo's | Site Engineer
4.18 | Install Traffic services | W | F3002D 2-U3436.BM | During Construction | Visual Inspection | Traffic services including signs and edge marker posts to be supplied and placed in accordance with TNZ C/20 | Photo's | Site Engineer
4.19 | As-built Survey | H |  | At completion of Lot | Survey / Drawings | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer | As-builts, CPS COR Report | Site Engineer | CPS Engineer
Section 5: Final Inspection and Handover
5.1 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
5.2 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Engineer: |  |  |  |  | Signature: |  |  | Date:
Note on I41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Amritpal Singh Hold Point
Note on I42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Amritpal Singh Hold Point
Note on I43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Amritpal Singh Hold Point
Note on I44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Amritpal Singh Hold Point
Note on J44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Amritpal Singh Site Engineer
Note on H69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Gordon Williamson can you please send me this spec? TNZ C/20