## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - F3002D - Mangahuini Long Drop Site - ITP for works | itp |  |  |  | Yes | ITP - F3002D - Mangahuini Long Drop Site - ITP for works REV 1 | c5f2bb34-e766-4f47-a09e-75e6088ceda2
checkpoint-group |  |  | section | Section 1: RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 69ba1670-d957-5bf0-aab6-a05b34916406 |  | textbox | CPS Eng.
text | 8c1f7a61-58b7-54cc-985b-9d091d0caa12 |  | textbox | Site Engineer
text | 77331545-1f61-5d64-86b1-70c1c05c6353 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Buttress Rock Armour (D50=800mm)
label | 77a1b739-aa7d-52af-873f-8fea8d11d5f0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c00b327c-0b7d-55f3-8a4e-94cd541a9503 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 38104185-906c-5367-bb72-f1624cd0c436 |  | note | Frequency - Prior to commencement
label | 0345be39-11ca-56cb-a012-bd64752adead |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 37043cb7-64ff-53c9-a037-eff6e5916412 |  | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 to 800mm with a minimum specific Gravity SG of 2350kg/m3.
label | 63e617f4-6f33-584a-8c0f-23e714aa66dd |  | note | Records - Material source test results, Delivery dockets, Photo's
checkpoint-status |  |  | checkpoint | 1.2 - Culvert Rip rap rock (D50 = 500mm)
label | cbb5e7b4-aee7-54a5-9db8-f2133086a8d3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a5d0924d-c932-5dec-9668-c2ab2dc2c891 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 147b2162-95d4-59bd-aa36-caa7c047e1b3 |  | note | Frequency - Prior to commencement
label | 4d1cde87-9a24-5ee6-891a-fe000445b504 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | e86ac567-be0a-57ff-8535-eadfe4166e36 |  | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 to 500mm with a minimum specific Gravity SG of 2350kg/m
label | cbd6ea1e-10bd-5ddc-b1a7-a1b0ebcd524a |  | note | Records - Material source test results, Delivery dockets, Photo's
checkpoint-status |  |  | checkpoint | 1.3 - Drainage material
label | aca1b633-ca8c-5e14-a0a3-91b599b2cf37 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0b226452-4dd7-52ae-9c5a-3cc6e5bee58e |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, TNZ F/2
label | 12864a85-e69f-5cb8-bc9a-0fa19845ccd2 |  | note | Frequency - Prior to commencement
label | a3b42221-b1c2-50d1-a6bc-06f01c20a0c7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 06f86aa8-369a-5c49-9c4f-ec4c106d0de2 |  | note | Conformance Criteria - Comply with TNZ F/2 or approved equivalent.
label | 86a71b0d-58b8-585c-9914-f3579c766ce0 |  | note | Records - Material source test results, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.4 - AP65 Granular fill
label | 81656688-a056-5b33-bcea-1f01a771a750 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4bdae82d-30d9-58a3-8361-04931f16a23a |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 979eea29-ffbc-573b-a8a5-780d1813811e |  | note | Frequency - Prior to commencement
label | 2b3e77d0-9b52-5237-ab18-263603d9d2b0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Particle size distribution test
label | 75bdec89-211c-508b-b6c9-d5d14e57ecda |  | note | Conformance Criteria - Test results from a representative general fill sample tested in an independent accredited laboratory
label | d55bd3b5-a234-5c65-a02b-8762d25d8b55 |  | note | Records - Material compliance cert, delivery dockets
checkpoint-status |  |  | checkpoint | 1.5 - Geogrid: Miragrid 80/20 Biaxial Grid or Similar Approved
label | 91bb69ac-64d5-52b1-a6da-7340bf460ccd |  | note | ACTION (Hold, Monitor, Witness) - W
label | 307e4e13-bea8-5f07-bb23-742da2ab9dbc |  | note | Specification/Drawings Reference - Mangahauini Long Drop Site NTC F3002D SH35RS225RP7.8 final
label | 6b4056aa-a48e-5642-926e-c73d49bce54b |  | note | Frequency - Prior to installation
label | e3345105-59eb-5e15-9c12-0f21546c8b10 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 3fdd3c05-1843-5866-93b3-8889d1237307 |  | note | Conformance Criteria - Delivery dockets with roll details. Check information on the delivery docket against the requirements indicated on the Drawings.
label | b3a20d44-55b7-588e-9dc4-d43f2539ab8f |  | note | Records - Material compliance cert, delivery dockets
checkpoint-status |  |  | checkpoint | 1.6 - Class D A49 Geotextile
label | 3e88f360-590e-566c-b998-430c6c1e2296 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0721bf09-a894-5c53-9878-3215d6accd88 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZTA F/7
label | f8ed2091-ed7b-5511-9b3d-190772d28f39 |  | note | Frequency - Prior to commencement
label | 93f77f79-9d09-5bac-a2f4-f5c3f34d2a8f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 007fd651-2825-5d3d-9224-6ad73a0eed39 |  | note | Conformance Criteria - Non-woven & NZTA F/7 compliant On dry bed below fill
label | 61602227-dab1-57e2-829d-06fcbb4f9853 |  | note | Records - Material compliance cert, photo's, delivery dockets
checkpoint-status |  |  | checkpoint | 1.7 - Perforated lateral drains
label | b61e6e97-3878-5994-bc6f-8219890ecdf7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ac6bd562-86fe-56fc-958b-a5ab06b05628 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 22373b6a-52c9-5722-bce0-343bbedcab13 |  | note | Frequency - Prior to commencement
label | 5a2cfc61-174d-5810-9f4a-6458a6a3a0d7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 3bbaa945-929b-5765-8731-993eac9c9a77 |  | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter perforated lateral subsoil drain, or similar approved.
label | 4ff021b4-a716-5d7d-9a3e-2854f222e565 |  | note | Records - Material compliance cert, photo's, delivery dockets
checkpoint-status |  |  | checkpoint | 1.11 - AP40 (Basecourse)
label | cf0b8a31-c159-5e3e-8093-337c41592bfb |  | note | ACTION (Hold, Monitor, Witness) - W
label | 215115cd-2af9-58e6-93ba-8eb51d9731db |  | note | Specification/Drawings Reference - TNZ M/4
label | 9b7574c2-5927-527d-9f54-cefa95d853e5 |  | note | Frequency - Prior to commencement
label | 1e984488-a525-54ec-98c6-521b044cad1f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 1f0438b5-ec5d-5177-9bd6-dabbc262042e |  | note | Conformance Criteria - Source property testing
label | c057982e-e6f8-5883-8091-e712b47b3d41 |  | note | Records - Lab test reports, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.12 - AP65 (Sub-base)
label | 19bad9ec-6394-5b2f-8bc3-ff8f93dfa23a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7b0fa3cd-7cbe-5425-bcc1-af691c1c4b2b |  | note | Frequency - Prior to commencement
label | 58d3418d-3265-5a7e-9f8c-54978e7d2c51 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | a4fc5c80-af03-57e3-82d5-b91bc42a8f95 |  | note | Conformance Criteria - Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak)
label | 52456a5a-6278-583c-a8ff-90b515c1d9cc |  | note | Records - Lab test report, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.13 - Grade 2/4 Chip
label | 713ae944-f691-501f-b2b3-aa37889a90c6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 81f2c5cd-6d1c-5947-b7e6-33f5d32b2bb1 |  | note | Specification/Drawings Reference - NZTA M/6
label | baacf0dc-3a17-52a4-93e0-fa642ba86f26 |  | note | Frequency - Prior to commencement
label | edd2a852-1b29-5250-a868-661a5a84154a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 13b6c27e-af8c-5629-833a-a6c23777fbcb |  | note | Conformance Criteria - Source property testing
label | fe4e9545-21fa-564e-822b-621ecda0f051 |  | note | Records - Lab test reports, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.14 - Cement Material cert
label | 187b79f7-a78e-584e-8ecd-e31951799b00 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 01f01242-bdc2-55a7-bd4c-180ee1d34136 |  | note | Frequency - Prior to commencement
label | abb65add-a615-5900-8b02-475699c7c0ed |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 870d7da7-872c-5f0b-9316-62752b762745 |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.15 - Bitumen
label | e774e17d-5d65-5475-a031-b8c571c34639 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a7687c65-8b09-5572-b7ca-cb2ec4e61d22 |  | note | Specification/Drawings Reference - TNZ M/1
label | 30934812-4a16-57b8-830a-25658fb405d1 |  | note | Frequency - Prior to commencement
label | 5e896a46-fe5e-5bca-8da9-3625898c8ab1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 851b358b-f1b1-559d-8f03-fbe7dee87474 |  | note | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
label | 07254412-94a2-58dd-b1be-6bb4b52f1f5f |  | note | Records - E2 Certificate
checkpoint-group |  |  | section | Section 2: REVETMENT & BACKFILL INSPECTIONS
checkpoint-status |  |  | checkpoint | 2.1 - Survey Setout
label | 77243461-0405-5401-b865-7c94cc5422ce |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5462632e-00fb-5c00-8aa1-6133221795d6 |  | note | Specification/Drawings Reference - Consistency with Construction Drawing
label | 77c11763-b412-598f-9074-76f7bd4ea803 |  | note | Frequency - Prior to commencement
label | 68448adb-6031-5c27-a369-ca09ea462244 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | b9931fc1-f327-53c8-a357-5edd7aaa0492 |  | note | Conformance Criteria - Set out extents of fill and check against design drawings
label | 9519d962-d180-50a2-9da2-13654bcda9e8 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Unsuitable loose material and vegetation
label | e17bbec4-b120-5755-91e8-041e3a842e4f |  | note | ACTION (Hold, Monitor, Witness) - W
label | d73b5d0e-f59c-5a56-8595-2da4f162e89d |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 1f764354-1045-50f3-a5ef-5af7767258a3 |  | note | Frequency - During Construction
label | a40660a0-0c17-5d04-8777-439a001d6cb7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b37b6f9b-46d2-525d-beff-2446d3fac350 |  | note | Conformance Criteria - Remove and clear any vegetation, trees and unsuitable material
label | 662e07a7-deb1-5865-8663-a864df0f2880 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.3 - Subgrade Inspection
label | 1b73dbf1-4e95-5edd-bfe7-20812ba5f68a |  | note | ACTION (Hold, Monitor, Witness) - H
label | ed5216f2-91e3-5fb6-8004-c6ceeef73475 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 4095da97-1525-5c47-a84f-6b90b7ca096f |  | note | Frequency - Per area as required
label | b16f65aa-22fa-5e62-b78d-09afdbae9592 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 5522a425-5a6d-5692-ba9e-b8330d9a85a1 |  | note | Conformance Criteria - Inspect fill foundation. Fill foundation must be approved, in writing, before filling commences.
label | 65db3e2d-382a-5a49-8da8-5805d36eb4b0 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Class D (A49) Geotextile placement
label | 366c7b76-67c4-594d-8c94-24ac9cc27afe |  | note | ACTION (Hold, Monitor, Witness) - M
label | a6c3967f-ca4e-54a7-bc58-453a1d18e291 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 58de8393-4019-5c37-b418-6833605779b8 |  | note | Frequency - During Construction
label | 51cbc4a5-2cfd-5a1e-ac57-4c1074b475c2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | f4ce3702-28a7-5023-ade6-34b0d123ec40 |  | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A49 or similar approved before placing granular fill. Bidim layer required between granular fill and rock armour.
label | 9ef26a1f-daea-5171-8e03-17e9afa40833 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.5 - Sub soil drainage
label | bf12397b-2030-5353-84da-4965698066e3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | de08250f-01c0-5e3f-85ca-787fc2e1909e |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, TNZ F/2
label | 0ebcebef-8d19-54d3-8c4f-355aa1b026a5 |  | note | Frequency - At lower bench level and mid bench prior to placing granular fill.
label | 90ee9db3-26e2-562d-aa44-588375753c5d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 9f927b06-fa36-5846-86d8-1dee158aa795 |  | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter perforated lateral subsoil drain, or similar approved. To be inspected and approved by CPS Engineer prior to install.
label | 531837d0-3b74-55d3-948a-fbee43382917 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Imported Granular Fill Placement
label | 732b3b5f-e0d1-53f4-8e48-a9bf00296c6f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6436c7d9-837b-5d54-aa8b-b0a1caf8e548 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZS4431:2022
label | 6b02f525-f74f-5e9e-a978-81f2b996c94a |  | note | Frequency - During Construction
label | b544d24e-3511-5dbb-a33a-2023ae38bb56 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 1624f3d2-4ed1-53ec-b06d-20f90f4dbc5b |  | note | Conformance Criteria - Granular fill to be placed in layers of maximum 150mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade
label | c6502f86-fd87-5379-9582-98d134354f6e |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Imported Granular Fill Compaction
label | 6d14a2ea-9b2c-5f9f-92ae-ca122ab0b323 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 03661876-f6ed-5c8f-beab-78cac80c4719 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZS 4402:1986, Test 4.1.3
label | 7dfa6c83-1fc1-55ab-a11d-065dce8e550a |  | note | Frequency - During Construction
label | cf0a0ed0-f9d7-5e82-b47c-58b66054572b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM & Clegg hammer testing
label | ab9b46bf-bd68-579e-b02d-c36213cb9256 |  | note | Conformance Criteria - A target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3. Testing done as per Site Instruction by CPS Engineer.
label | 10597727-27f6-54d0-b91e-5601fed515f1 |  | note | Records - Test results, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Geogrid Placement
label | 71a9322d-065d-5203-aba6-2673b1a221eb |  | note | ACTION (Hold, Monitor, Witness) - H
label | d958f2e6-ab7c-511e-a2cb-7bf786661d28 |  | note | Specification/Drawings Reference - Mangahauini Long Drop Site NTC F3002D SH35RS225RP7.8 final
label | d6ddd0c0-6107-5153-bb2c-5be25ccdf127 |  | note | Frequency - During Construction
label | 884e212d-fd3f-56cc-a38d-b063e4f71172 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | eb956fbd-9b5a-5f67-a96d-7caaa20d5d0e |  | note | Conformance Criteria - Geogrid to be placed in engineered fill 300mm thick between geogrid layers. Geogrid to be wrapped with a minimum overlap of 2.0m. Panel overlap on geogrid layers to be minimum 0.5m or manufacturers minimum.
label | 1f9a3541-9511-503d-ae6b-b36dd5e8af33 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Form and cut fill batter as per design 1.5H:1V
label | 61252a02-4800-5d33-b00c-c7d4ba723fc3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a5770630-99c6-54e8-bbcd-d61657489c80 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 8d5591c7-1ea7-553f-b832-cf39d8a8c8f8 |  | note | Frequency - During Construction
label | a8ba870b-c554-5783-90b3-f56cfe32d638 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | da3fdaa7-8770-5515-b4ff-2d250a603179 |  | note | Conformance Criteria - Benches to be cut and profiled to suit slope profile
label | a3706d50-7949-573f-bf52-ea0957c273df |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Rock Armour (50-800dia) to form revetment
label | 5bf79f7e-dcda-59bb-94c3-1f19f1979fdb |  | note | ACTION (Hold, Monitor, Witness) - M
label | 880d5199-68b6-5f7a-8dfe-c0a9b205523e |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 1c85ac03-a6c6-5ddc-8e97-eb900bfae1b2 |  | note | Frequency - During Construction
label | 4972af42-8c66-5246-802c-179c1883cea6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 544f5f91-b24e-5240-974e-8ab8608bd848 |  | note | Conformance Criteria - The buttress is to be keyed in to ground directly behind existing displaced reno mattresses and existing railway line timber panel retaining wall
label | 22e0777b-ef4b-5a57-9bf3-1398f12f387a |  | note | Records - Photo's
checkpoint-group |  |  | section | Section 3: FISH PASSAGE INSPECTIONS
checkpoint-status |  |  | checkpoint | 3.1 - Survey Setout
label | 5d084ca1-c657-5a90-8342-72273b53dbcf |  | note | ACTION (Hold, Monitor, Witness) - H
label | 07c391a5-109c-5fd1-b33c-83730d13a857 |  | note | Specification/Drawings Reference - NTC F3002 D
label | 63710ad7-547b-52a7-a4b0-c173d8131809 |  | note | Frequency - During Construction
label | 3cf3b01e-2436-5c8a-92f8-44c1642fbedc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 94b71ae2-1a24-5f45-a62e-247a56006e82 |  | note | Conformance Criteria - Set out extents of fill and check against design drawings
label | 6b19af11-661c-5833-9e98-eb843a5b46ee |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Void Fillings
label | 61c9f388-b059-548e-919b-0a0c4a20cb76 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ab3eea29-6be5-5d41-83ed-6f10f6fe8492 |  | note | Specification/Drawings Reference - NTC F3002 D
label | f0b77a74-192c-51d4-afd3-7e78d8bece84 |  | note | Frequency - During Construction
label | 5f84243d-6781-5f16-9640-214a829a36d6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 9ce95f60-291d-5ce4-a467-966a4d488148 |  | note | Conformance Criteria - Measurements of Materials
label | 088e556e-739e-53a7-8c7b-1909cf4fca16 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Gradient of the fish passage
label | 27faf134-ee3f-5d9d-bc90-484c7144689f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6955f498-b90e-5f8b-8bd1-e4579049095a |  | note | Specification/Drawings Reference - NTC F3002 D
label | c661b9ea-bd52-558a-beef-da89998ebbea |  | note | Frequency - During Construction
label | 6574d70d-96f8-542e-b0bd-1405da94d0ec |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | f5abfa32-1bed-596b-9c47-bd0c1334cbf5 |  | note | Conformance Criteria - Set out extents of fill and check against design drawings
label | f2419f99-43ea-5ae5-ae31-fb607d04e078 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Clear, reshape & apply rip rap to culvert inlet
label | ca073347-b1aa-5580-9e8b-27e587454f24 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 566ab8fc-34d7-52ee-b3a6-1e2114ccc74d |  | note | Frequency - During Construction
label | d1044034-9e45-529f-ae75-f06a619993b5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 984648b4-15be-59d2-ae5b-c6a66651b2a8 |  | note | Conformance Criteria - As agreed on site with CPS Engineer
label | 27d636a1-7246-5f91-a136-156c813d798a |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 4: PAVEMENT INSPECTIONS
checkpoint-status |  |  | checkpoint | 4.1 - Saw cut existing pavement
label | e3ae9fe2-d9d7-5b3c-8e87-6c33a5594485 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 69f866f3-5564-5809-9830-64869c8d22b2 |  | note | Frequency - Prior to pavement construction
label | d8b4bbf7-6894-5014-80d5-fceb9816f462 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 8fddf259-83e2-5239-ab1a-507660d5f143 |  | note | Conformance Criteria - Smooth and straight saw cut
label | ec85849f-19ec-5b41-9167-3db26ced296d |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.2 - Subgrade construction
label | 8a78d471-4505-5de9-9d75-5b3d9dca3871 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c659d7fd-1148-514b-b560-41aea63bdf53 |  | note | Specification/Drawings Reference - TNZ B2
label | 6ee9f9da-bbe9-5134-a21d-8c4b98c7b2b7 |  | note | Frequency - Every 20m and/or at random
label | 6f721878-33aa-5093-b58b-0165bf708462 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | 17496a70-f1d1-522f-aff8-00ff70ff25e8 |  | note | Conformance Criteria - 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92%
label | 09fefa71-1164-5a2a-91dc-66ae39e81cb3 |  | note | Records - Subgrade Approval Check sheet, Test (CS-4100) reports
checkpoint-status |  |  | checkpoint | 4.3 - Subgrade Cement Application rate
label | 73b3f88d-d1cf-5570-9923-ce47bc149d0d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 36e174b4-6f93-55ea-8068-0ec45de986d1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
label | f2bc55d7-74a4-5d11-a37e-888744e0e95c |  | note | Conformance Criteria - 2% cement stabilisation at 250mm deep subgrade
label | d1da49ae-186a-56ff-b180-999619d3b293 |  | note | Records - Bag test records
checkpoint-status |  |  | checkpoint | 4.4 - Pavement construction: Sub base and base course
label | 7fcf9c73-9ac2-5ec7-87d6-aad027db7a4d |  | note | ACTION (Hold, Monitor, Witness) - M
label | caf1d79d-9fb4-545a-985d-16b9a8339133 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 14ba1bc4-e16f-5671-8317-ff422c97caca |  | note | Frequency - During Construction
label | 710c2693-2418-5438-9ef1-1674e46df538 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 03ec83f2-73ed-530b-b079-5c4e2aff29fb |  | note | Conformance Criteria - Sub base and base course to be placed in accordance with TNZ B2. Compaction required in accordance with NZS 4407:2015. Cement supplied to NZS3122 and stabilised in accordance with TNZ B/5.
label | 57d2a0d9-7303-51ae-b926-0b79349b88ab |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.5 - Sub-base construction
label | a922f33f-5424-5091-90b3-e476b86d8983 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 28e9b5e2-65cc-5967-bb9d-887adcd93b10 |  | note | Specification/Drawings Reference - TNZ B2
label | fc27ada3-350c-5358-9314-0eac7b0aa95e |  | note | Frequency - Every 20m and/or at random
label | f4475cc5-3870-5581-8aad-a2fd217f52ce |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | 873f65af-5b16-5ac4-a75c-065812de0155 |  | note | Conformance Criteria - 200mm thick AP65 sub-base compacted to a minimum dry density of 95%. Average 95% of MDD with nothing less than 92%.
label | d5255fc9-41ae-5d3c-9d81-7b56b8c80e51 |  | note | Records - Test reports
checkpoint-status |  |  | checkpoint | 4.6 - Sub-base construction
label | 94210b9c-2b05-56f0-ac19-991fa81ebab3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ace5074a-1705-5ca4-95fe-de98e9761845 |  | note | Specification/Drawings Reference - TNZ B2
label | d5e69c2c-6ab1-5397-a858-277275b218f0 |  | note | Frequency - Every 20m and/or at random
label | d983ea52-b33e-5e67-9702-513fc54e3597 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | cbd37141-8c2e-5dad-acc4-828f44a3960d |  | note | Conformance Criteria - CIV>=25
label | 53fbd93f-8de9-56e5-9450-5cfbed7c11f8 |  | note | Records - Clegg Hammer Checksheet (CS-4037c), Test reports, Photo's
checkpoint-status |  |  | checkpoint | 4.7 - Sub-base construction
label | 73ca106a-8345-5539-8b01-bd9d554a4201 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5e5377f3-d0e6-5421-8250-cb15db8b47db |  | note | Specification/Drawings Reference - TNZ B2
label | 598d6281-ca43-5eb2-b503-6dbc13c14b56 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 69d41c07-e05c-50d3-9c0f-8fdd6754a999 |  | note | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
label | 8d3c3826-1225-59cd-9faa-f5c882927bda |  | note | Records - Survey as-builts
checkpoint-status |  |  | checkpoint | 4.8 - Basecourse construction
label | 1babbece-6e2d-5b6b-9995-d18a660f29f0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3c05a4a1-e58f-5e12-a674-a70beace4fcc |  | note | Specification/Drawings Reference - TNZ B2
label | d7be59e4-8cb4-52cd-b8ef-7689cd1300a2 |  | note | Frequency - Every 20m and/or at random
label | 54ba58bf-5af0-5007-9f4c-906154cf3e08 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | c13516f4-c684-526f-b0ad-b90992a4fdab |  | note | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%. Average 98% of MDD with nothing less than 95%.
label | cc84b23a-7814-5d99-b7eb-4a5f9a6c248f |  | note | Records - Test reports, Photo's
checkpoint-status |  |  | checkpoint | 4.9 - Basecourse Cement application rate
label | 8cc691fe-6701-5bec-b1e3-33f0414ce5de |  | note | ACTION (Hold, Monitor, Witness) - W
label | 456bb4b5-2e36-5cc6-b679-31a375a52c1d |  | note | Specification/Drawings Reference - TNZ B/5
label | c3423cb9-8d48-574b-97fa-48687d0a35ce |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 03940fb6-1936-5c84-8a58-843fab5ba2f4 |  | note | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
label | a3fa84e9-6cf0-5694-8a76-9a824686655a |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.10 - Basecourse construction
label | 6ff3dd56-ac1d-5f23-8088-092372b9d5a3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5abe17a8-ee53-52f0-9939-18a6dd34002f |  | note | Specification/Drawings Reference - TNZ B2
label | 5a0ea1e0-47aa-5039-ac88-c0e0ab356f48 |  | note | Frequency - Every 20m
label | 35d67124-04ef-52f3-8866-ad8900187bac |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 6405343b-bdf9-5a65-8cf9-f8c0dcff6e74 |  | note | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
label | 71473fc3-30c9-5590-bef3-f9fd80eba79c |  | note | Records - Survey as-builts
checkpoint-status |  |  | checkpoint | 4.11 - Basecourse construction
label | 2913bcb9-a245-5945-913e-089c5debc8a3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ac7cda92-e8e5-5898-95c4-b49a90b66755 |  | note | Specification/Drawings Reference - TNZ B2
label | f5d7089a-9846-57b7-8679-474b7f240099 |  | note | Frequency - Every 20m and/or at random
label | aa313e2c-d2fb-514e-ac0a-4999f46b8e43 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | 65f3b842-4d8a-53a5-8aed-888e602fcd7e |  | note | Conformance Criteria - CIV>=25
label | a2d2d79c-f5b7-5013-8af8-814b4a1f3e37 |  | note | Records - Clegg Hammer Checksheet (CS-4037c), Test reports, Photo's
checkpoint-status |  |  | checkpoint | 4.12 - Basecourse construction
label | f843ddba-0355-5072-ab3e-8271b35a7ae3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1815ae73-b8ca-540a-8ef3-0dcdb1ebac4d |  | note | Specification/Drawings Reference - TNZ B2
label | f606d52c-63f3-5484-bebd-74872d11e5d1 |  | note | Frequency - Before sealing
label | c1818244-e088-50e9-bff5-614479e20b79 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | 8197e20c-1192-5c84-9f3b-2bfe92a97281 |  | note | Conformance Criteria - Mosaic surface
label | 72d1e3dd-8881-5065-9d48-ac6bd252741e |  | note | Records - Photo's, Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 4.13 - Applying Bitumen
label | 32f8ab63-a791-54a0-8b3a-b7674cd2fef9 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b8cd8ca5-8aac-5112-a313-4e13922acab8 |  | note | Specification/Drawings Reference - NZTA M/6
label | 5244362d-05eb-5e37-ac16-e7af59156ddc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | f871c2c9-444a-5a18-96b2-7521996de80b |  | note | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
label | 191aca1e-0629-5ce1-b488-0b5a8c188f1b |  | note | Records - Photo's, Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 4.14 - Degree of saturation
label | 9f484139-7754-5d2f-9f64-8f6a9d75501f |  | note | ACTION (Hold, Monitor, Witness) - W
label | e9b475d5-531d-5cba-a1f1-75c64497e7e3 |  | note | Frequency - Before sealing
label | 8c2c0399-b533-5a54-aaeb-c8bed1be3abb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | 899338fd-bd25-5daf-90f8-53d293bab74e |  | note | Conformance Criteria - Degree of saturation should not exceed 80%
label | 08537d5f-4a0c-573a-a3c1-d39f09e519c3 |  | note | Records - Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 4.15 - Chip seal laying
label | d8fb7d51-db7f-59ac-8eb4-72d89aea975a |  | note | ACTION (Hold, Monitor, Witness) - M
label | 4eda1095-4a39-5e97-9396-dc14660e75b1 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZTA M/6
label | 756d26d9-b79b-565a-b282-396208cc5b49 |  | note | Frequency - During Construction
label | 0051120d-4222-590a-b9a5-c9b671e0f618 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | a0d2c8c2-86a0-5a7e-af94-7ba01bf0fe45 |  | note | Conformance Criteria - Chip seal will match existing seal. The seal will be placed and compacted in accordance with NZTA P/17. The seal will be rolled in accordance with NZTA P/3
label | a228eca9-bb26-5144-92a7-241f48e01d72 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.16 - Verge
label | f17a5978-f022-5980-aefd-a21fe408f485 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 831a439a-f6d3-5880-bd53-2ca39bbc3142 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 178ce6d7-0b4d-5033-b2ce-deddf9904c1a |  | note | Frequency - During Construction
label | 1c1d93c0-b2a9-5d94-8eae-f88e4e909016 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 171f9219-b694-5de1-9eba-b4baff33d4a1 |  | note | Conformance Criteria - Verge reinstatement to match existing
label | bab5eba6-b22b-57d3-896c-c21f10141478 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.17 - Sweep & Line mark new chip seal road
label | d7ec98cf-1d78-533f-9658-fb694cdfd56a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 70362e1f-b03d-5c3b-9ac0-2fec1751085b |  | note | Specification/Drawings Reference - TNZ P/12:2000
label | d6ac6e36-b352-5525-9104-a4a62a49cfe1 |  | note | Frequency - During Construction
label | 1dd2d797-4310-59a2-b5fc-8af5b460ae47 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 615e77f3-90fe-5221-a653-04ba4a2ee7e3 |  | note | Conformance Criteria - As per TNZ P/12:2000
label | b9ea0ed8-6d8a-561a-8079-8da3ee899d55 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.18 - Install Traffic services
label | a5515068-2261-5479-b4f0-3cb3b7182bf9 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c6fcb241-e371-5f18-9dad-2376c68dc9c5 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 7bbd97b3-4f5a-583c-b99f-d3b24e4c8102 |  | note | Frequency - During Construction
label | d5a6f097-efa5-5774-965b-52f1f379737f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c05f1cad-f858-5fac-89de-bbd2771f85c7 |  | note | Conformance Criteria - Traffic services including signs and edge marker posts to be supplied and placed in accordance with TNZ C/20
label | bc41fc26-2540-5ded-8b67-612583f44bee |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.19 - As-built Survey
label | fa744596-59ef-5f9c-8e91-e92a908c91f9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 26261f5f-7784-5943-9e0c-502c678934bf |  | note | Frequency - At completion of Lot
label | bf1072e0-d007-52af-b1e7-313347889819 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | 966f64d8-5bfa-550c-9258-25c8bd5cfad0 |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | bfa7950b-a82e-5e8e-9c24-b9198fa22823 |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 5: FINAL INSPECTION AND HANDOVER
checkpoint-status |  |  | checkpoint | 5.1 - Quality Assurance deliverables
label | 85680821-106c-5ad5-b2f1-c0dfabac1e00 |  | note | ACTION (Hold, Monitor, Witness) - W
label | bcc20ede-d4bb-5724-afa1-da6d53ffd737 |  | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 1a6c4c76-f022-57ea-b64d-961adac549bc |  | note | Frequency - At completion of Lot
label | fc90df9e-2dfa-5850-ad45-4e516892bd5c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 034f5d3b-3de3-56ed-9d17-38d29c4a2620 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 1112bc04-6f45-5d1c-a430-f29279f287a4 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 5.2 - Completion Sign Off From Fields Below
label | 6dff8cb4-a725-545c-b9a9-aff3fe9787fb |  | note | Records - Signatures