## Table 1
VIC CIVIL – Structural Concrete – VR
ITP Number: | [5 empty] | ITP007a-VC235- | [14 empty] | Revision Number: | [6 empty] | 2
| Author (Vic Civil) | [22 empty] | Client Approver (Multiplex)
| Name |  |  | Ben Thomas | [19 empty] | Name | [5 empty] | Jayden Campbell
| Position |  |  | Engineer | [19 empty] | Position | [5 empty] | Project Engineer
| Signature | [12 empty] | Date | [9 empty] | Signature | [18 empty] | Date
Authorisation (Vic Roads)
Name
[12 empty] | Position | [5 empty] | Vic Roads Site Representative
[12 empty] | Signature | [16 empty] | Date
| Work Lot Number: | [5 empty] | North Architectural Column | [8 empty] | Work Lot Description: | [6 empty] | Construction of architectural / structural column over Ballarat Road – Northern Section
| Design Package: | [5 empty] | 370_VU Bride | [15 empty] | Structural Engineer | [7 empty] | 4D Workshop
| INSPECTION CODES: |  |  | S: Surveillance Point W: Witness Point H: Hold Point R: Review | [7 empty] | INSPECTION ROLE TYPES*: | [7 empty] | SE: Site Engineer SF: Supervisor/Foreman ENV: Enviro Representative SU: Surveyor PE: Project Engineer QM: Quality Manager CR: Community Relations Advisor
Item No. |  | Operational Activities | [6 empty] | Verification | [22 empty] | Inspection | [11 empty] | Records & Comments
[9 empty] | Specification Reference | [7 empty] | Acceptance Criteria | [9 empty] | Test / Inspection Method & Frequency |  |  |  |  | Vic Civil | [6 empty] | Multiplex / Vic Roads |  |  |  |  | KEY:  = Applicable X = Not Applicable X and are to be initialled
[32 empty] | Key |  |  |  | Sign Date |  |  | Key |  | Sign Date
1 |  | PRELIMINARIES - Prior To Commencement of Work
1.1 |  | Work Lot Map | [6 empty] | N/A | [7 empty] | Work Lot Map attached to Work Lot | [9 empty] | Per work lot |  |  |  |  | PE (H) |  |  |  | = |  |  | PE (H) |  |  |  |  | [ ] Work Lot Map
2 |  | MATERIAL COMPLIANCE - Prior To Commencement of Work
2.1 |  | Calibration Certificates | [6 empty] | Process Control | [7 empty] | Confirm that external equipment calibration and testing facilities are registered External equipment calibration meets contract requirements for each item of test equipment | [9 empty] | Visual check with certificates, ITP, checklist or inspection report |  |  |  |  | PE (H) |  |  |  | = |  |  | PE (H) |  |  |  |  | [ ] Record of visual inspection [ ] Calibration Certificates
2.2 |  | Concrete Mix Design | [6 empty] | VicRoads 610.07 AS 3600 IFC Drawings | [7 empty] | Concrete mix design approved and in accordance with the IFC drawings | [9 empty] | Approved mix confirmation prior to commencing works |  |  |  |  | PE (H) |  |  |  | = |  |  | PE (H) |  |  |  |  | [ ] Approved VicRoads mix design registration
2.3 |  | Steel Reinforcement Certification | [6 empty] | VicRoads 611.05 AS 4671 IFC Drawings | [7 empty] | ACRS certificate provided for suppliers and manufacturers of steel | [9 empty] | ACRS certificate supplied within 14 days of contract award |  |  |  |  | PE (H) | [6 empty] | PE (H) |  |  |  |  | [ ] ACRS Certificate
2.5 |  | Bar chairs and spacer compliance | [6 empty] | VicRoads 610.26(a) AS/NZS 2425 IFC Drawings | [7 empty] | Reinforcement supports comply with AS/NZS 2425. Concrete bar chairs are tested in accordance with VicRoads 610.26(a) | [9 empty] | Review of certificates prior to ordering materials |  |  |  |  | PE (H) | [6 empty] | PE (H) |  |  |  |  | [ ] Compliance certificates
2.6 |  | Formwork / Falsework Design | [6 empty] | VicRoads 614.04 VicRoads 613.04 JHG Temp Works Design Procedure | [7 empty] | Approved Formwork Design Approved Falsework Design Design brief approved and verified | [9 empty] | Proof Eng’g Certificate or Design Verification forwarded to Client |  |  |  |  | PE (H) | [6 empty] | PE (H) |  |  |  |  | [ ] Temporary Works Design Ref No.
INSPECTION CODES: |  |  | S: Surveillance Point W: Witness Point H: Hold Point R: Review | [7 empty] | INSPECTION ROLE TYPES*: | [7 empty] | SE: Site Engineer SF: Supervisor/Foreman ENV: Enviro Representative SU: Surveyor PE: Project Engineer QM: Quality Manager CR: Community Relations Advisor
2.7 |  | Confirm approval of curing compound | [6 empty] | VicRoads 610.23 | [7 empty] | Curing compound approved and in accordance with VR IFC Design via RFI. | [9 empty] | All batches |  |  |  |  | PE (H) | [6 empty] | PE (H) |  |  |  |  | [ ] Curing compound Design Approval Ref:
3 |  | QUALIFICATION REQUIREMENTS - Prior To Commencement of Work
3.1 |  | Welding Requirements | [5 empty] | Approved Weld Procedures [ ] AS 1554.1 Clause 4.1 to 4.11 [ ] AS 1554.3 Clause 4.1 to 4.11 IFC Drawings Welder Qualifications. [ ] AS 1554.1 Clause 4.12 [ ] AS 1554.3 Clause 4.12 TGN-BC-01: Tack welding of reinforcement bar | [8 empty] | Weld Procedures have been reviewed and approved by Construction Team & Quality Team for all welding required- this includes Non Load Bearing tack welds Evidence that all welders are qualified with regards to the applicable welds Weld Supervisor has required qualifications | [9 empty] | Provided by subcontractor | [5 empty] | PE (H) | [5 empty] | PE (H) |  |  |  |  | [ ] Weld Procedures [ ] Weld Procedure Qualification Records [ ] Welder Qualifications [ ] Supervisor Qualifications Welding Procedures required for the works to be listed here Eg. Fillet welds/ splices, tack etc:
3.2 |  | Concrete Technical Specialist | [5 empty] | VicRoads 610.24 | [8 empty] | The assessment of the cracked concrete structure shall be undertaken by a technical specialist with a minimum of 5 years’ experience | [9 empty] | Prior to repair | [5 empty] | PE (H) | [5 empty] | PE (H) |  |  |  |  | [ ] Evidence of experience
NOTE: 1. All preliminary records have been reviewed and approved.
| Vic Civil Representative: | [17 empty] | Vic Civil Signature: | [18 empty] | Date:
| Multiplex Representative: | [17 empty] | Multiplex Signature: | [18 empty] | Date:
INSPECTION CODES: |  |  | S: Surveillance Point W: Witness Point H: Hold Point R: Review | [7 empty] | INSPECTION ROLE TYPES*: | [7 empty] | SE: Site Engineer SF: Supervisor/Foreman ENV: Enviro Representative SU: Surveyor PE: Project Engineer QM: Quality Manager CR: Community Relations Advisor
Item No. |  | Operational Activities | [7 empty] | Verification | [23 empty] | Inspection | [10 empty] | Records & Comments
[10 empty] | Specification Reference |  |  |  |  | Acceptance Criteria | [10 empty] | Test / Inspection Method & Frequency | [7 empty] | Vic Civil | [5 empty] | Multiplex / Vic Roads |  |  |  |  | KEY:  = Applicable X = Not Applicable X and are to be initialled
[34 empty] | Key |  |  | Sign Date |  |  | Key |  | Sign Date
4 |  | CONSTRUCTION ACTIVITIES - Prior To Commencement and During Works – Sub-lot Records (if applicable)
4.1 |  | Inspection of incoming materials: • All embedded Items cast into structural concrete | [7 empty] | Project Requirement Specification |  |  |  |  | Materials conform to IFC drawings and Specifications Free of defects, transportation damage and/or imperfections | [10 empty] | Visual check with written notes in Delivery docket, ITP, checklist or inspection report. Upon Delivery | [7 empty] | SE (W) | [5 empty] | PE (H) |  |  |  |  | [ ] Structural Concrete Checklist –
4.2 |  | Survey Set-out & Initial pour against ground | [7 empty] | IFC Drawings |  |  |  |  | Survey marks (levels and offsets) in place (where applicable) | [10 empty] | Visual Inspection / Spot Check – Prior to commencing works | [7 empty] | SE (W) | [5 empty] | SE (W) |  |  |  |  | [ ] Structural Concrete Checklist
4.3 |  | Pre-pour inspection: Reinforcement | [7 empty] | IFC Drawings VicRoads 611 AS 5100 AS 1554 |  |  |  |  | Concrete shall not be placed until: All reinforcement installed as per design | [10 empty] | Visual Inspection prior to concrete pour | [7 empty] | SE (W) | [5 empty] | PE (H) |  |  |  |  | [ ] Structural Concrete Checklist
4.4 |  | Pre-pour inspection: Formwork, falsework & scaffold | [7 empty] | VicRoads 610.18 VicRoads 614 IFC Drawings Temp Works Design & Procedure AS 3610 |  |  |  |  | On-site inspection and validation of Temporary Works Design Falsework erected in accordance with certified design Refer to checklist | [10 empty] | Visual inspection prior to concrete pour Inspection of falsework construction by Engineer | [7 empty] | SE (W) | [5 empty] | PE (H) |  |  |  |  | [ ] Structural Concrete Checklist
4.5 |  | Construction Joints | [7 empty] | IFC Drawings VicRoads 610.20 |  |  |  |  | Concrete cast against concrete to be clean and free of laitance with roughened and coarse aggregate exposed to depth of 3mm | [10 empty] | As required | [7 empty] | SE (W) | [5 empty] | SE (W) |  |  |  |  | [ ] Structural Concrete Checklist
4.6 |  | Cast in items, voids and block outs | [7 empty] | IFC Drawings Temp Work Drawings |  |  |  |  | All cast in items, voids and block outs installed as per design and given tolerances | [10 empty] | Visual Inspection prior to concrete pour | [7 empty] | SE (W) | [5 empty] | SE (W) |  |  |  |  | [ ] Structural Concrete Checklist
INSPECTION CODES: |  |  | S: Surveillance Point W: Witness Point H: Hold Point R: Review | [7 empty] | INSPECTION ROLE TYPES*: | [7 empty] | SE: Site Engineer SF: Supervisor/Foreman ENV: Enviro Representative SU: Surveyor PE: Project Engineer QM: Quality Manager CR: Community Relations Advisor
4.7 |  | Install thermocouples to monitor early age thermal cracking of large members >500mm. | [7 empty] | VicRoads 610.22 |  |  |  |  | Required for concrete members where: (a) The least dimension of a member exceeds 500mm; or (b) One or more faces of a concrete member is restrained by previously placed hardened concrete or by other external restraints. Thermocouples installed Temperature differential across concrete member is less than 20ºC during the period of curing. | [10 empty] | As required | [7 empty] | SE (W) | [5 empty] | SE (W) |  |  |  |  | [ ] Structural Concrete Checklist
4.8 |  | Concrete supply & testing | [7 empty] | VicRoads 610.16 Mix Design AS 1379 |  |  |  |  | Slump tests acceptable within limits of mix design If mix contains superplasticiser, slump testing shall be in accordance with VicRoads 610.16(c) Concrete samples taken in accordance with VicRoads 610.16 | [10 empty] | Complete the structural checklist for every pour Testing frequency as per VicRoads Table 610.161 | [7 empty] | SE (W) | [5 empty] | SE (W) |  |  |  |  | [ ] Structural Concrete Checklist
4.9 |  | Discharge of Concrete | [7 empty] | VicRoads 610.13 VicRoads 610.17 VicRoads 610.18 AS 1379 |  |  |  |  | Discharge completed within time limit approved on mix design No water added once discharge commenced Concrete temp between 10-32 °C and Air temp between 5-35 °C. | [10 empty] | Visual inspection – Each delivery | [7 empty] | SE (W) | [5 empty] | SE (W) |  |  |  |  | [ ] Structural Concrete Checklist
4.1 |  | Placement | [7 empty] | VicRoads 610.17 VicRoads 610.18 |  |  |  |  | Placed in near horizontal layers not more than 350mm thick Concrete shall not be dropped from a height exceeding 2m. Compacted with vibrators and power screeds as appropriate Needle vibrators to be used vertically to full depth plus 100mm into the lower layer. | [10 empty] | Visual inspection – Each pour | [7 empty] | SE (W) | [5 empty] | SE (W) |  |  |  |  | [ ] Structural Concrete Checklist
4.12 |  | Concrete Testing - Compressive Testing | [7 empty] | VicRoads 610.16 |  |  |  |  | Concrete shall be tested for compressive strength in accordance with VR 610 3 cylinders (1 x 7day, 2 x 28 Day) taken for each sample, minimum no. of samples: | [10 empty] | Each Pour | [7 empty] | SE (W) | [5 empty] | SE (W) |  |  |  |  | [ ] Structural Concrete Checklist
[15 empty] | Quantity, m3 | [5 empty] | # Samples
[15 empty] | 0-10 | [5 empty] | 1
INSPECTION CODES: |  |  | S: Surveillance Point W: Witness Point H: Hold Point R: Review | [7 empty] | INSPECTION ROLE TYPES*: | [7 empty] | SE: Site Engineer SF: Supervisor/Foreman ENV: Enviro Representative SU: Surveyor PE: Project Engineer QM: Quality Manager CR: Community Relations Advisor
[15 empty] | 10 to 25 | [5 empty] | 2
[15 empty] | 25 to 50 | [5 empty] | 3
[15 empty] | 50 to 100 | [5 empty] | 4
[15 empty] | >100 | [5 empty] | 1 sample for each 50m3 >100
4.13 |  | Formwork and Falsework Deformation check | [7 empty] | Temp Work Drawings |  |  |  |  | Ensure that no significant deformations have occurred during the pour | [10 empty] | Visual – Each Pour | [7 empty] | SE (W) | [5 empty] | SE (W) |  |  |  |  | [ ] Structural Concrete Checklist
4.14 |  | Surface Finishing | [7 empty] | VicRoads 610.31 VicRoads 610.18(d) |  |  |  |  | Surface finished as specified in drawings Joint surfaces left rough, set retardant applied where required | [10 empty] | Visual – Each Pour | [7 empty] | SE (W) | [5 empty] | SE (W) |  |  |  |  | [ ] Structural Concrete Checklist
4.15 |  | Curing | [7 empty] | VicRoads 610.23 BCRC REPORT |  |  |  |  | Approved methodology and application rate | [10 empty] | Where Required, after discharge | [7 empty] | SE (W) | [5 empty] | SE (W) |  |  |  |  | [ ] Structural Concrete Checklist
4.16 |  | Removal of Form / Falsework & Inspection of Stripped Surfaces | [7 empty] | VicRoads 610.24 VicRoads 610.25 VicRoads 610.31 VicRoads 610.34 |  |  |  |  | Falsework and formwork removed no earlier than specified in Table 610.251, unless otherwise approved Specified Surface finish class achieved. Specified cover achieved within tolerance | [10 empty] | Visual Inspection – Each Pour 10 cover checks in 3m2 test areas for every 25m2 surface area | [7 empty] | SE (W) | [5 empty] | PE (H) |  |  |  |  | [ ] Structural Concrete Checklist
4.17 |  | Patch repair (Where applicable) | [7 empty] | VicRoads 610.32 VicRoads 689 |  |  |  |  | Surfaces repaired using approved cementitious products achieving similar texture and colour to surrounds | [10 empty] | Review – Each Pour | [7 empty] | SE (W) | [5 empty] | SE (W) |  |  |  |  | [ ] Structural Concrete Checklist
4.18 |  | Crack Inspection and repair (Where applicable) | [7 empty] | VicRoads 610.24 VicRoads 687 |  |  |  |  | Structural cracks assessed by qualified professional Approved crack repair procedure | [10 empty] | Visual/measure– Each Pour | [7 empty] | PE (W) | [5 empty] | PE (H) |  |  |  |  | [ ] Structural Concrete Checklist
Item No. |  | Operational Activities | [5 empty] | Verification | [26 empty] | Inspection | [8 empty] | Records & Comments
[8 empty] | Specification Reference |  |  |  |  | Acceptance Criteria | [11 empty] | Test / Inspection Method & Frequency | [9 empty] | Vic Civil |  |  |  |  | Multiplex / Vic Roads |  |  |  | KEY:  = Applicable X = Not Applicable X and are to be initialled
[35 empty] | Key |  | Sign Date |  |  | Key | Sign Date
5 |  | TESTING AND COMMISSIONING REQUIREMENTS – Post Construction Works – Sub-lot Records (if applicable)
5.1 |  | As Built Survey | [5 empty] | IFC drawings |  |  |  |  | As-built survey is within tolerance when compared to Design & Specifications | [11 empty] | As-built vs Design Survey is within Tolerance | [9 empty] | SE (R) |  |  |  |  | SE (R) |  |  |  | [ ] Structural Concrete Checklist
5.2 |  | Maturity Testing | [5 empty] | VR610.16 |  |  |  |  | Confirm concrete has achieved minimum compressive strength required for demoulding/lifting | [11 empty] | As required | [9 empty] | SE (R) |  |  |  |  | SE (R) |  |  |  | [ ] Structural Concrete Checklist
5.3 |  | Concrete cover checks | [5 empty] | VR610.34 VR 610.41 AS5100.5, 4.14.3 |  |  |  |  | Minimum Cover measurements demonstrated that minimum concrete cover as per the drawings and the allowable dimensional tolerances as stated in Clause VR 610.41. | [11 empty] | Min. 10 concrete cover measurements carried out using a cover meter in a 3m2 test area for every 25 m2 or part thereof on a representative and randomly selected number of exterior surface areas. Record min. measurement. | [9 empty] | SE (R) |  |  |  |  | SE (R) |  |  |  | [ ] Structural Concrete Checklist
5.4 |  | Temperature Monitoring Report | [5 empty] | VR 610.22 |  |  |  |  | Monitor early age thermal cracking of concrete for large and restrained members to ensure temperature differential is not greater than 20°C during the period of Internal concrete temperature does not exceed 75⁰C. | [11 empty] | As required | [9 empty] | SE (R) |  |  |  |  | SE (R) |  |  |  | [ ] Structural Concrete Checklist
5.5 |  | Laboratory testing of concrete | [5 empty] | VicRoads 610.05 VicRoads 610.16 |  |  |  |  | Compressive strength testing Slump test results | [11 empty] | As per VicRoads Table 610.161 | [9 empty] | SE (R) |  |  |  |  | SE (R) |  |  |  | [ ] Structural Concrete Checklist
INSPECTION CODES: |  |  | S: Surveillance Point W: Witness Point H: Hold Point R: Review | [7 empty] | INSPECTION ROLE TYPES*: | [7 empty] | SE: Site Engineer SF: Supervisor/Foreman ENV: Enviro Representative SU: Surveyor PE: Project Engineer QM: Quality Manager CR: Community Relations Advisor
Item No. |  | Operational Activities | [6 empty] | Verification | [23 empty] | Inspection | [10 empty] | Records & Comments
[9 empty] | Specification Reference | [8 empty] | Acceptance Criteria | [9 empty] | Test / Inspection Method & Frequency |  |  |  |  | Vic Civil | [5 empty] | Multiplex / Vic Roads |  |  |  |  | KEY:  = Applicable X = Not Applicable X and are to be initialled
[33 empty] | Key |  |  | Sign Date |  |  | Key |  | Sign Date
6 |  | COMPLETION REQUIREMENTS – Post Construction Works – Sub-lot Records (if applicable)
6.2 |  | Close out NCR(s) | [6 empty] | Project Specification | [8 empty] | All out of tolerances notified via Site NCR reporting system | [9 empty] | Prior to closing and signing ITP |  |  |  |  | PE (H | [5 empty] | PE (H) |  |  |  |  | [ ] Structural Concrete Checklist
6.3 |  | Relevant RFI(s): | [6 empty] | Project Specification | [8 empty] | Design/Construction Queries or clarifications relating to this ITP are addressed and closed. All ‘parts’ of RFI are included All ‘supporting evidence’ is included | [9 empty] | RFIs closed and linked to NCRs where applicable |  |  |  |  | PE (H) | [5 empty] | PE (H) |  |  |  |  | [ ] Structural Concrete Checklist
INSPECTION CODES: |  |  | S: Surveillance Point W: Witness Point H: Hold Point R: Review | [7 empty] | INSPECTION ROLE TYPES*: | [7 empty] | SE: Site Engineer SF: Supervisor/Foreman ENV: Enviro Representative SU: Surveyor PE: Project Engineer QM: Quality Manager CR: Community Relations Advisor
Item No. |  | Operational Activities | [6 empty] | Verification | [23 empty] | Inspection | [10 empty] | Records & Comments
[9 empty] | Specification Reference | [8 empty] | Acceptance Criteria | [9 empty] | Test / Inspection Method & Frequency |  |  |  |  | Vic Civil | [5 empty] | Multiplex / Vic Roads |  |  |  |  | KEY:  = Applicable X = Not Applicable X and are to be initialled
[33 empty] | Key |  |  | Sign Date |  |  | Key |  | Sign Date
6.4 |  | Redline Marked-up Drawings | [6 empty] | Project Specification | [8 empty] | Redline drawing to be produced & maintained by engineers to include all changes made during construction Redline to use latest IFC version of the design drawings and be marked- up in red pen, to identify any variations RFI, DCR, ECW and Client Wavers to be referenced in redlines (as required) | [9 empty] | Completion of Works |  |  |  |  | PE (H) | [5 empty] | PE (H) |  |  |  |  | [ ] Structural Concrete Checklist
ITP CLOSE OUT 1. All applicable verification records must be legible, signed/ initialled and dated where required.
[5 empty] | Vic Civil Representative: | [16 empty] | Vic Civil Signature: | [22 empty] | Date:
| Multiplex Representative: | [17 empty] | Multiplex Signature: | [18 empty] | Date:
INSPECTION CODES: |  |  | S: Surveillance Point W: Witness Point H: Hold Point R: Review | [7 empty] | INSPECTION ROLE TYPES*: | [7 empty] | SE: Site Engineer SF: Supervisor/Foreman ENV: Enviro Representative SU: Surveyor PE: Project Engineer QM: Quality Manager CR: Community Relations Advisor