## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP007a-VC235-Structural Concrete Checklist | itp |  |  |  |  | ITP007a-VC235-Structural Concrete Checklist
section | 4.0 CONSTRUCTION ACTIVITIES – PREPOUR
checkpoint | 4.1 - Incoming Inspection of Materials
label | Acceptance Criteria - All materials conform to IFC drawings and specs- ferrules, galvanised dowels, drainage conduits etc.
button | Check Box | Yes,No,N/A
label | Verification Record - Delivery Dockets Compliance Certificates
holdpoint | Project Engineer (HP)
checkpoint | 4.6 - Reinforcement (1)
label | Acceptance Criteria - Type, size, position, chairs, cover all as specified & within tolerance; laps and splices as specified; tack welds not undercut
button | Check Box | Yes,No
label | Verification Record - Reinforcement Schedule
holdpoint | Project Engineer (HP)
checkpoint | 4.6 - Reinforcement (2)
label | Acceptance Criteria - Ensure starter bars match precast stitch bars (if applicable)
button | Check Box | Yes,No,N/A
label | Verification Record - Survey Report
checkpoint | 4.6 - Reinforcement (3)
label | Acceptance Criteria - Placement, size and configuration as per drawings ± 5mm position.
button | Check Box | Yes,No
checkpoint | 4.6 - Reinforcement (4)
label | Acceptance Criteria - Cover (including tire wire) specified in drawings 0mm, + 5mm. Cover checked to FSL.
button | Check Box | Yes,No
checkpoint | 4.6 - Reinforcement (5)
label | Acceptance Criteria - Surface condition free from thick rust, grease, mud etc
button | Check Box | Yes,No
checkpoint | 4.6 - Reinforcement (6)
label | Acceptance Criteria - Min lap lengths:
label | N12 – 300mm N24 – 1000mm N16 – 500mm
label | N28 – 1250mm N20 – 750mm N32 – 1500mm
button | Check Box | Yes,No
checkpoint | 4.6 - Reinforcement (7)
label | Acceptance Criteria - Tack Welding not within 50mm of bends
button | Check Box | Yes,No,N/A
checkpoint | 4.6 - Reinforcement (8)
label | Acceptance Criteria - Mechanical splices (couplers or similar) fully engaged and installed as per manufacturers recommendations.
button | Check Box | Yes,No,N/A
label | Verification Record - Coupler Delivery Docket, Compliance Certificates
checkpoint | 4.7 - Formwork/ falsework setup, alignment and integrity (1)
label | Acceptance Criteria - Installed as per temp design; design confirmed by survey; forms clean & release agent/oil applied.
button | Check Box | Yes,No,N/A
checkpoint | 4.7 - Formwork/ falsework setup, alignment and integrity (2)
label | Acceptance Criteria - Falsework/formwork over 1m high has a temporary design
button | Check Box | Yes,No,N/A
label | Verification Record - Temp Works Design
holdpoint | Project Engineer (HP)
checkpoint | 4.8 - Construction Joints
label | Acceptance Criteria - Concrete cast against concrete to be clean & free of laitance. Roughened and coarse aggregate exposed to depth of 3mm
button | Check Box | Yes,No,N/A
checkpoint | 4.11 - Cast-in items, void formers, block-outs and hold down bolts
label | Acceptance Criteria - Type, quantity and location as per design. Checked with survey and relevant stakeholder
button | Check Box | Yes,No,N/A
label | Verification Record - Delivery Dockets
checkpoint | 4.12 - Installation of thermocouples
label | Acceptance Criteria - Thermocouples installed as per VR610.22
button | Check Box | Yes,No,N/A
label | Verification Record - Install Photos
checkpoint-no-status | HOLD POINT
label | Concrete pre-pour checks completed in accordance with the applicable ITP, drawings, specifications and approved changes
textbox | PROJECT ENGINEER NAME (Vic Civil)
textbox | PROJECT ENGINEER NAME (Multiplex)
date | Date:
holdpoint | HOLD POINT
section | 4.0 CONSTRUCTION ACTIVITIES – CONCRETE PLACEMENT
checkpoint | 4.13 - Concrete Supply & Concrete Testing – Slump Test (1)
label | Acceptance Criteria - Concrete Mix on Docket Checked. Ensure delivery dockets. Tester onsite. Visual assessment of quality.
button | Check Box | Yes,No
label | Verification Record - Concrete Delivery Dockets, Field Test Docket, Concrete Pour Record (Refer pg 7)
checkpoint | 4.13 - Concrete Supply & Concrete Testing – Slump Test (2)
label | Acceptance Criteria - 1 slump test per strength test
label | ○ If mix contains superplasticiser, all batches shall be tested. If 5 consecutives batches comply, superintendent may reduce frequency to 1 per strength testing
label | ○ Test within 45 mins of adding cement to aggregates, or immediately prior to discharge when actual haul time is >45mins, or after addition of water. All other slumps to be estimated visually.
label | VR Tolerances:
label | – – – – – – – – – – – – – – – – – – –
label | Specified slump, mm ¦¦ Tolerance, mm
label | – – – – – – – – – – – – – – – – – – –
label | <60 ¦¦ ± 10mm
label | ≥60mm to ≤80mm ¦¦ ± 15mm
label | >80mm to ≤110mm ¦¦ ± 20mm
label | >110mm to ≤150mm ¦¦ ± 30mm
label | >150mm ¦¦ ± 40m
label | – – – – – – – – – – – – – – – – – – –
button | Check Box | Yes,No
label | Verification Record - Concrete Pour Record (Refer pg 7)
checkpoint | 4.14/4.15 - Discharge & Placement of Concrete (1)
label | Acceptance Criteria - Each load placed within 60mins of batching, unless approved otherwise
button | Check Box | Yes,No
label | Verification Record - Concrete Pour Record (Refer pg 7)
checkpoint | 4.14/4.15 - Discharge & Placement of Concrete (2)
label | Acceptance Criteria - No water added once discharge commenced
button | Check Box | Yes,No
label | Verification Record - Concrete Pour Record (Refer pg 7)
checkpoint | 4.14/4.15 - Discharge & Placement of Concrete (3)
label | Acceptance Criteria - Max and min temps:
label | – – – – – – – – – – – – – – – – – – –
label | MIN (ºC) ¦¦ MAX (ºC)
label | – – – – – – – – – – – – – – – – – – –
label | AMBIENT: 5 ¦¦ 35
label | CONCRETE: 10 ¦¦ 32
label | – – – – – – – – – – – – – – – – – – –
button | Check Box | Yes,No
label | Verification Record - Concrete Pour Record (Refer pg 7)
checkpoint | 4.14/4.15 - Discharge & Placement of Concrete (4)
label | Acceptance Criteria - Max. lag between trucks is <=25 mins. If > 25min aliphatic alcohol to be used. Interval between final discharge and start of discharge of next truck is <45 mins for a continuous pour.
button | Check Box | Yes,No
label | Verification Record - Concrete Pour Record (Refer pg 7)
checkpoint | 4.14/4.15 - Discharge & Placement of Concrete (5)
label | Acceptance Criteria - Vertical drop not exceeding 2.0m Placed in not more than 350mm layers.
button | Check Box | Yes,No
label | Verification Record - Concrete Pour Record (Refer pg 7)
checkpoint | 4.16 - Concrete Testing – Compressive Strength
label | Acceptance Criteria - Compressive Strength Testing => 28 days post-pour
label | ○ Refer VR 610
label | ○ 3 cylinders (1 x 7day, 2 x 28 Day) taken for each sample, minimum no. of samples:
label | – – – – – – – – – – – – – – – – – – –
label | Quantity, m3 ¦¦ # Samples
label | – – – – – – – – – – – – – – – – – – –
label | 0-10 ¦¦ 1
label | 10 to 25 ¦¦ 2
label | 25 to 50 ¦¦ 3
label | 50 to 100 ¦¦ 4
label | >100 ¦¦ 1 sample for each 50m3 >100
label | – – – – – – – – – – – – – – – – – – –
button | Check Box | Yes,No,N/A
label | Verification Record - Concrete Pour Record (Refer pg 7)
checkpoint | 4.19 - Visual check on formwork
label | Acceptance Criteria - Any significant deformation observed?
button | Check Box | Yes,No
checkpoint | 4.20 - Surface Finish
label | Acceptance Criteria - Surfaces finished to the class specified in the drawings.
button | Check Box | Yes,No
checkpoint | 4.22 - Curing of exposed surfaces
label | Acceptance Criteria - Curing in accordance with BCRC report recommendations
button | Check Box | Yes,No,N/A
label | Verification Record - Curing Methodology or Compound: BCRC Report (attached)
checkpoint | 4.23 - Removal of falsework and stripping of formwork
label | Acceptance Criteria - Falsework and formwork removed as per VR Table 610.251 (See Pg 5)
label | ○ If early removal or loading is required, relevant approvals and test results to be reviewed by design engineer
textbox | Days since pour
button | Check Box | Yes,No,N/A
textbox | Verification Record - RFI Reference #: Maturity Report
holdpoint | Project Engineer (HP)
checkpoint | 4.23 - Inspection of stripped surface
label | Acceptance Criteria - Stripped surface finish has been achieve in accordance with specifications (VR610.31) and design drawings?
button | Check Box | Yes,No
textbox | Verification Record - Surface Finish Class:
checkpoint | 4.25 - Patch Repair (where applicable)
label | Acceptance Criteria - Inactive crack and/or Patch repairs conducted as per approved procedure, where required
button | Check Box | Yes,No,N/A
textbox | Verification Record - Repair method approval- RFI-Repair Product TDS
checkpoint | 4.26 - Crack Repair & Monitoring (where applicable)
label | Acceptance Criteria - Cracks greater than acceptable widths as per VR Table 610.241 are mapped and repaired in accordance with VR 687 and approved methodology specific to location. Cracks requiring repairs monitored.
label | – – – – – – – – – – – – – – – – – – –
label | Exposure Classification ¦¦ Maximum Acceptable Crack Widths (mm)
label | – – – – – – – – – – – – – – – – – – –
label | A ¦¦ 0.20
label | B1 ¦¦ 0.20
label | B2 ¦¦ 0.15
label | C, U ¦¦ 0.10
label | – – – – – – – – – – – – – – – – – – –
button | Check Box | Yes,No,N/A
textbox | Verification Record - Repair method approval- RFI-Repair Product TDS
holdpoint | Project Engineer (HP)
section | 5.0 TESTING AND COMMISSIONING REQUIREMENTS – POST POUR CHECK & TESTING
checkpoint | 5.1 - As Built survey complete
label | Acceptance Criteria - As-built survey is within tolerance when compared to Design & Specifications
button | Check Box | Yes,No
label | Verification Record - As-Built Record – conformance report
label | Vic Civil - Site Engineer (R):
label | Multiplex - Site Engineer (R):
date | Date:
checkpoint | 5.2 - Maturity Testing
label | Acceptance Criteria - Concrete has achieved minimum strength prior to the removal of falsework/ formwork
button | Check Box | Yes,No,N/A
textbox | Verification Record - Strength Achieved: Maturity Report
label | Vic Civil - Site Engineer (R):
label | Multiplex - Site Engineer (R):
date | Date:
checkpoint | 5.3 - Concrete Cover
label | Acceptance Criteria - For every 25m2 of exterior surface area a 3m2 ‘Test Area’ will be selected. Within this ‘Test Area’ 10 concrete cover checks will be conducted.
button | Check Box | Yes,No
label | Verification Record - Cover Checks Record (Refer pg 6)
label | Vic Civil - Site Engineer (R):
label | Multiplex - Site Engineer (R):
date | Date:
checkpoint | 5.4 - Temperature Monitoring (VR610.22)
label | Acceptance Criteria - Ensure temperature differential across the concrete member being constructed is < 20°C during the period of curing, and internal concrete temperature doesn’t exceed 75°C
button | Check Box | Yes,No,N/A
label | Verification Record - Temperature Monitoring Report
label | Vic Civil - Site Engineer (R):
label | Multiplex - Site Engineer (R):
date | Date:
checkpoint | 5.5 - Compressive strength and slump results
label | Acceptance Criteria - 7 and 28 day strength results achieve min requirements as per VR table 610.051. Slump tests with tolerances.
button | Check Box | Yes,No
label | Verification Record - NATA Test Results
label | Vic Civil - Site Engineer (R):
label | Multiplex - Site Engineer (R):
date | Date:
section | 6.0 SUB-LOT – COMPLETION REQUIREMENTS
checkpoint | 6.1 - Works Completion Inspection
label | Acceptance Criteria - Ensure works completed in accordance with IFC Dwg & Specifications, Inspection completed & recorded prior to releasing activity
button | Check Box | Yes,No,N/A
label | Verification Record - Punch List Items
holdpoint | Project Engineer (HP)
checkpoint | 6.2 - Close out NCR(s)
label | Acceptance Criteria - NCR(s) raised & closed formally, All out of tolerances notified via Site NCR reporting system
button | Check Box | Yes,No,N/A
label | Verification Record - NCR/s related to lot:
holdpoint | Project Engineer (HP) / Quality Representative (HP)
checkpoint | 6.3 - RFI(s)
label | Acceptance Criteria - All RFIs have been closed-out prior to work lot submission
button | Check Box | Yes,No,N/A
label | Verification Record - RFI & DCN Register relevant to sub-lot only
holdpoint | Project Engineer (HP)
checkpoint | 6.4 - Red Line Mark Ups
label | Acceptance Criteria - Confirm redline drawings are being progressively marked up
button | Check Box | Yes,No,N/A
label | Verification Record - Redline Drawings / Summary of Material Quantities
holdpoint | Project Engineer (HP)
checkpoint-no-status | Check List Close Out
label | Concrete pre-pour checks completed in accordance with the applicable ITP, drawings, specifications and approved changes
textbox | PROJECT ENGINEER NAME (Vic Civil)
textbox | PROJECT ENGINEER NAME (Multiplex)
date | Date:
holdpoint | SIGN