## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP007a-VC235-Architectural Concrete Columns | itp |  |  |  |  | ITP007a-VC235-Architectural Concrete Columns Rev2
section | 1.0 PRELIMINARIES - Prior To Commencement of Work
checkpoint | 1.1 - Work Lot Map
label | Specification Reference - N/A
label | Acceptance Criteria - Work Lot Map attached to Work Lot
label | Test / Inspection Method & Frequency - Per work lot
label | Key - PE (H)
label | Multiplex / Vic Roads Key - PE (H)
bool | Records & Comments - Work Lot Map
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 MATERIAL COMPLIANCE - Prior To Commencement of Work
checkpoint | 2.1 - Calibration Certificates
label | Specification Reference - Process Control
label | Acceptance Criteria - Confirm that external equipment calibration and testing facilities are registered, External equipment calibration meets contract requirements for each item of test equipment
label | Test / Inspection Method & Frequency - Visual check with certificates, ITP, checklist or inspection report
label | Key - PE (H)
label | Multiplex / Vic Roads Key - PE (H)
label | Records & Comments -
bool | Record of visual inspection
bool | Calibration Certificates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Concrete Mix Design
label | Specification Reference - VicRoads 610.07 AS 3600 IFC Drawings
label | Acceptance Criteria - Concrete mix design approved and in accordance with the IFC drawings
label | Test / Inspection Method & Frequency - Approved mix confirmation prior to commencing works
label | Key - PE (H)
label | Multiplex / Vic Roads Key - PE (H)
bool | Records & Comments - Approved VicRoads mix design registration
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Steel Reinforcement Certification
label | Specification Reference - VicRoads 611.05 AS 4671 IFC Drawings
label | Acceptance Criteria - ACRS certificate provided for suppliers and manufacturers of steel
label | Test / Inspection Method & Frequency - ACRS certificate supplied within 14 days of contract award
label | Key - PE (H)
label | Multiplex / Vic Roads Key - PE (H)
bool | Records & Comments - ACRS Certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Bar chairs and spacer compliance
label | Specification Reference - VicRoads 610.26(a) AS/NZS 2425 IFC Drawings
label | Acceptance Criteria - Reinforcement supports comply with AS/NZS 2425. Concrete bar chairs are tested in accordance with VicRoads 610.26(a)
label | Test / Inspection Method & Frequency - Review of certificates prior to ordering materials
label | Key - PE (H)
label | Multiplex / Vic Roads Key - PE (H)
bool | Records & Comments - Compliance certificates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Formwork / Falsework Design
label | Specification Reference - VicRoads 614.04, VicRoads 613.04 JHG Temp Works Design Procedure
label | Acceptance Criteria - Approved Formwork Design, Approved Falsework Design, Design brief approved and verified
label | Test / Inspection Method & Frequency - Proof Eng’g Certificate or Design Verification forwarded to Client
label | Key - PE (H)
label | Multiplex / Vic Roads Key - PE (H)
bool | Records & Comments - Temporary Works Design
textbox | Ref No.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Confirm approval of curing compound
label | Specification Reference - VicRoads 610.23
label | Acceptance Criteria - Curing compound approved and in accordance with VR IFC Design via RFI.
label | Test / Inspection Method & Frequency - All batches
label | Key - PE (H)
label | Multiplex / Vic Roads Key - PE (H)
bool | Records & Comments - Curing compound Design Approval
textbox | Ref:
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 QUALIFICATION REQUIREMENTS - Prior To Commencement of Work
checkpoint | 3.1 - Welding Requirements
label | Specification Reference - Approved Weld Procedures
bool | AS 1554.1 Clause 4.1 to 4.11
bool | AS 1554.3 Clause 4.1 to 4.11
label | ○ IFC Drawings Welder Qualifications.
bool | AS 1554.1 Clause 4.12
bool | AS 1554.3 Clause 4.12
label | ○ TGN-BC-01: Tack welding of reinforcement bar
label | Acceptance Criteria - Weld Procedures have been reviewed and approved by Construction Team & Quality Team for all welding required- this includes Non Load Bearing tack welds, Evidence that all welders are qualified with regards to the applicable welds, Weld Supervisor has required qualifications
label | Test / Inspection Method & Frequency - Provided by subcontractor
label | Key - PE (H)
label | Multiplex / Vic Roads Key - PE (H)
label | Records & Comments -
bool | Weld Procedures
bool | Weld Procedure Qualification Records
bool | Welder Qualifications
bool | Supervisor Qualifications
label | Welding Procedures required for the works to be listed here
label | Eg. Fillet welds/ splices, tack etc:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Concrete Technical Specialist
label | Specification Reference - VicRoads 610.24
label | Acceptance Criteria - The assessment of the cracked concrete structure shall be undertaken by a technical specialist with a minimum of 5 years’ experience
label | Test / Inspection Method & Frequency - Prior to repair
label | Key - PE (H)
label | Multiplex / Vic Roads Key - PE (H)
bool | Records & Comments - Evidence of experience
section | 4.0 CONSTRUCTION ACTIVITIES - Prior To Commencement and During Works – Sub-lot Records (if applicable)
checkpoint | 4.1 - Inspection of incoming materials: All embedded Items cast into structural concrete
label | Specification Reference - Project Requirement Specification
label | Acceptance Criteria - Materials conform to IFC drawings and Specifications, Free of defects, transportation damage and/or imperfections
label | Test / Inspection Method & Frequency - Visual check with written notes in Delivery docket, ITP, checklist or inspection report. Upon Delivery
label | Key - SE (W)
label | Multiplex / Vic Roads Key - PE (H)
bool | Records & Comments - Structural Concrete Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Survey Set-out & Initial pour against ground
label | Specification Reference - IFC Drawings
label | Acceptance Criteria - Survey marks (levels and offsets) in place (where applicable)
label | Test / Inspection Method & Frequency - Visual Inspection / Spot Check – Prior to commencing works
label | Key - SE (W)
label | Multiplex / Vic Roads Key - SE (W)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 4.3 - Pre-pour inspection: Reinforcement
label | Specification Reference - IFC Drawings VicRoads 611 AS 5100 AS 1554
label | Acceptance Criteria - Concrete shall not be placed until: All reinforcement installed as per design
label | Test / Inspection Method & Frequency - Visual Inspection prior to concrete pour
label | Key - SE (W)
label | Multiplex / Vic Roads Key - PE (H)
bool | Records & Comments - Structural Concrete Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Pre-pour inspection: Formwork, falsework & scaffold
label | Specification Reference - VicRoads 610.18, VicRoads 614 IFC Drawings Temp Works Design & Procedure AS 3610
label | Acceptance Criteria - On-site inspection and validation of Temporary Works Design, Falsework erected in accordance with certified design, Refer to checklist
label | Test / Inspection Method & Frequency - Visual inspection prior to concrete pour, Inspection of falsework construction by Engineer
label | Key - SE (W)
label | Multiplex / Vic Roads Key - PE (H)
bool | Records & Comments - Structural Concrete Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Construction Joints
label | Specification Reference - IFC Drawings VicRoads 610.20
label | Acceptance Criteria - Concrete cast against concrete to be clean and free of laitance with roughened and coarse aggregate exposed to depth of 3mm
label | Test / Inspection Method & Frequency - As required
label | Key - SE (W)
label | Multiplex / Vic Roads Key - SE (W)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 4.6 - Cast in items, voids and block outs
label | Specification Reference - IFC Drawings Temp Work Drawings
label | Acceptance Criteria - All cast in items, voids and block outs installed as per design and given tolerances
label | Test / Inspection Method & Frequency - Visual Inspection prior to concrete pour
label | Key - SE (W)
label | Multiplex / Vic Roads Key - SE (W)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 4.7 - Install thermocouples to monitor early age thermal cracking of large members >500mm.
label | Specification Reference - VicRoads 610.22
label | Acceptance Criteria - Required for concrete members where:
label | (a) The least dimension of a member exceeds 500mm; or
label | (b) One or more faces of a concrete member is restrained by previously placed hardened concrete or by other external restraints.
label | ○ Thermocouples installed
label | ○ Temperature differential across concrete member is less than 20ºC during the period of curing.
label | Test / Inspection Method & Frequency - As required
label | Key - SE (W)
label | Multiplex / Vic Roads Key - SE (W)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 4.8 - Concrete supply & testing
label | Specification Reference - VicRoads 610.16 Mix Design AS 1379
label | Acceptance Criteria - Slump tests acceptable within limits of mix design, If mix contains superplasticiser, slump testing shall be in accordance with VicRoads 610.16(c), Concrete samples taken in accordance with VicRoads 610.16
label | Test / Inspection Method & Frequency - Complete the structural checklist for every pour, Testing frequency as per VicRoads Table 610.161
label | Key - SE (W)
label | Multiplex / Vic Roads Key - SE (W)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 4.9 - Discharge of Concrete
label | Specification Reference - VicRoads 610.13, VicRoads 610.17, VicRoads 610.18 AS 1379
label | Acceptance Criteria - Discharge completed within time limit approved on mix design, No water added once discharge commenced, Concrete temp between 10-32 °C and Air temp between 5-35 °C.
label | Test / Inspection Method & Frequency - Visual inspection – Each delivery
label | Key - SE (W)
label | Multiplex / Vic Roads Key - SE (W)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 4.10 - Placement
label | Specification Reference - VicRoads 610.17, VicRoads 610.18
label | Acceptance Criteria - Placed in near horizontal layers not more than 350mm thick, Concrete shall not be dropped from a height exceeding 2m. Compacted with vibrators and power screeds as appropriate, Needle vibrators to be used vertically to full depth plus 100mm into the lower layer.
label | Test / Inspection Method & Frequency - Visual inspection – Each pour
label | Key - SE (W)
label | Multiplex / Vic Roads Key - SE (W)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 4.12 - Concrete Testing - Compressive Testing
label | Specification Reference - VicRoads 610.16
label | Acceptance Criteria - Concrete shall be tested for compressive strength in accordance with VR 610, 3 cylinders (1 x 7day, 2 x 28 Day) taken for each sample, minimum no. of samples:
label | – – – – – – – – – – – – – – – – – – –
label | Quantity, m3 ¦¦ # Samples
label | – – – – – – – – – – – – – – – – – – –
label | 0-10 ¦¦ 1
label | 10 to 25 ¦¦ 2
label | 25 to 50 ¦¦ 3
label | 50 to 100 ¦¦ 4
label | >100 ¦¦ 1 sample for each 50m3 >100
label | – – – – – – – – – – – – – – – – – – –
label | Test / Inspection Method & Frequency - Each Pour
label | Key - SE (W)
label | Multiplex / Vic Roads Key - SE (W)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 4.13 - Formwork and Falsework Deformation check
label | Specification Reference - Temp Work Drawings
label | Acceptance Criteria - Ensure that no significant deformations have occurred during the pour
label | Test / Inspection Method & Frequency - Visual – Each Pour
label | Key - SE (W)
label | Multiplex / Vic Roads Key - SE (W)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 4.14 - Surface Finishing
label | Specification Reference - VicRoads 610.31, VicRoads 610.18(d)
label | Acceptance Criteria - Surface finished as specified in drawings, Joint surfaces left rough, set retardant applied where required
label | Test / Inspection Method & Frequency - Visual – Each Pour
label | Key - SE (W)
label | Multiplex / Vic Roads Key - SE (W)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 4.15 - Curing
label | Specification Reference - VicRoads 610.23 BCRC REPORT
label | Acceptance Criteria - Approved methodology and application rate
label | Test / Inspection Method & Frequency - Where Required, after discharge
label | Key - SE (W)
label | Multiplex / Vic Roads Key - SE (W)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 4.16 - Removal of Form / Falsework & Inspection of Stripped Surfaces
label | Specification Reference - VicRoads 610.24, VicRoads 610.25, VicRoads 610.31, VicRoads 610.34
label | Acceptance Criteria - Falsework and formwork removed no earlier than specified in Table 610.251, unless otherwise approved, Specified Surface finish class achieved. Specified cover achieved within tolerance
label | Test / Inspection Method & Frequency - Visual Inspection – Each Pour, 10 cover checks in 3m2 test areas for every 25m2 surface area
label | Key - SE (W)
label | Multiplex / Vic Roads Key - PE (H)
bool | Records & Comments - Structural Concrete Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.17 - Patch repair (Where applicable)
label | Specification Reference - VicRoads 610.32, VicRoads 689
label | Acceptance Criteria - Surfaces repaired using approved cementitious products achieving similar texture and colour to surrounds
label | Test / Inspection Method & Frequency - Review – Each Pour
label | Key - SE (W)
label | Multiplex / Vic Roads Key - SE (W)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 4.18 - Crack Inspection and repair (Where applicable)
label | Specification Reference - VicRoads 610.24, VicRoads 687
label | Acceptance Criteria - Structural cracks assessed by qualified professional, Approved crack repair procedure
label | Test / Inspection Method & Frequency - Visual/measure– Each Pour
label | Key - PE (W)
label | Multiplex / Vic Roads Key - PE (H)
bool | Records & Comments - Structural Concrete Checklist
holdpoint | AUTHORITY HOLDPOINT
section | 5.0 TESTING AND COMMISSIONING REQUIREMENTS – Post Construction Works – Sub-lot Records (if applicable)
checkpoint | 5.1 - As Built Survey
label | Specification Reference - IFC drawings
label | Acceptance Criteria - As-built survey is within tolerance when compared to Design & Specifications
label | Test / Inspection Method & Frequency - As-built vs Design Survey is within Tolerance
label | Key - SE (R)
label | Multiplex / Vic Roads Key - SE (R)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 5.2 - Maturity Testing
label | Specification Reference - VR610.16
label | Acceptance Criteria - Confirm concrete has achieved minimum compressive strength required for demoulding/lifting
label | Test / Inspection Method & Frequency - As required
label | Key - SE (R)
label | Multiplex / Vic Roads Key - SE (R)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 5.3 - Concrete cover checks
label | Specification Reference - VR610.34, VR 610.41 AS5100.5, 4.14.3
label | Acceptance Criteria - Minimum Cover measurements demonstrated that minimum concrete cover as per the drawings and the allowable dimensional tolerances as stated in Clause VR 610.41.
label | Test / Inspection Method & Frequency - Min. 10 concrete cover measurements carried out using a cover meter in a 3m2 test area for every 25 m2 or part thereof on a representative and randomly selected number of exterior surface areas. Record min. measurement.
label | Key - SE (R)
label | Multiplex / Vic Roads Key - SE (R)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 5.4 - Temperature Monitoring Report
label | Specification Reference - VR 610.22
label | Acceptance Criteria - Monitor early age thermal cracking of concrete for large and restrained members to ensure temperature differential is not greater than 20°C during the period of Internal concrete temperature does not exceed 75⁰C.
label | Test / Inspection Method & Frequency - As required
label | Key - SE (R)
label | Multiplex / Vic Roads Key - SE (R)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 5.5 - Laboratory testing of concrete
label | Specification Reference - VicRoads 610.05, VicRoads 610.16
label | Acceptance Criteria - Compressive strength testing, Slump test results
label | Test / Inspection Method & Frequency - As per VicRoads Table 610.161
label | Key - SE (R)
label | Multiplex / Vic Roads Key - SE (R)
bool | Records & Comments - Structural Concrete Checklist
section | 6.0 COMPLETION REQUIREMENTS – Post Construction Works – Sub-lot Records (if applicable)
checkpoint | 6.2 - Close out NCR(s)
label | Specification Reference - Project Specification
label | Acceptance Criteria - All out of tolerances notified via Site NCR reporting system
label | Test / Inspection Method & Frequency - Prior to closing and signing ITP
label | Key - PE (H)
label | Multiplex / Vic Roads Key - PE (H)
bool | Records & Comments - Structural Concrete Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - Relevant RFI(s):
label | Specification Reference - Project Specification
label | Acceptance Criteria - Design/Construction Queries or clarifications relating to this ITP are addressed and closed. All ‘parts’ of RFI are included. All ‘supporting evidence’ is included
label | Test / Inspection Method & Frequency - RFIs closed and linked to NCRs where applicable
label | Key - PE (H)
label | Multiplex / Vic Roads Key - PE (H)
bool | Records & Comments - Structural Concrete Checklist
checkpoint | 6.4 - Redline Marked-up Drawings
label | Specification Reference - Project Specification
label | Acceptance Criteria - Redline drawing to be produced & maintained by engineers to include all changes made during construction, Redline to use latest IFC version of the design drawings and be marked- up in red pen, to identify any variations, RFI, DCR, ECW and Client Wavers to be referenced in redlines (as required)
label | Test / Inspection Method & Frequency - Completion of Works
label | Key - PE (H)
label | Multiplex / Vic Roads Key - PE (H)
bool | Records & Comments - Structural Concrete Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | ITP CLOSE OUT
textbox | Vic Civil Representative:
textbox | Multiplex Representative:
date | Date:
holdpoint | Vic Civil/Multiplex Signature