## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Complete Assembly |  |  |  |  | Yes | Complete Assembly | 139de904-07e1-48c4-85e0-e4a56618802b
checkpoint-status |  |  | checkpoint | Sub Frame assembly, Sub frame mounted into folded panel.
label | da212e0c-0d33-5c30-896e-141d022b772d |  | note | Paper version Upload - 447-FAB-ITP-004
text | 474a6d19-94f0-5111-a7bb-e236c0d1bb0c |  | textbox | Date of silicon application
checklist-flat |  |  | checklist | Installation of Shelf panels |  |  |  |  | Yes | Installation of Shelf panels | 193bf87d-3327-4dfa-82fe-11d6688adf50
checkpoint-status |  |  | checkpoint | Installation of base framing in accordance with 447-SD- 4701
checkpoint-status |  |  | checkpoint | Fixing and fixtures are installed as documented by Fairlite / fixing schedule FX01 / FX02
checkpoint-status |  |  | checkpoint | Panel installed in accordance with the architectural documentation / project performance documents 447-SD-4701
checkpoint-status |  |  | checkpoint | Film Removed
checklist-flat |  |  | checklist | Fabrication |  |  |  |  | Yes | Fabrication | 2d5825c5-fa0b-41c6-bd1c-476efc9391ac
checkpoint-status |  |  | checkpoint | Extrusion delivery & material finish
label | 7c9ddd86-ebcd-55aa-a267-1939008135f3 |  | note | Paper version Uploaded - 447-FAB-ITP-001
checkpoint-status |  |  | checkpoint | Cutting flat sheet & Flat panel folding
label | b905c9d6-a956-57c3-83b2-9aed2e44bfc6 |  | note | Paper version Uploaded - 447-FAB-ITP-002
checkpoint-status |  |  | checkpoint | Extrusion Processing
label | 3f16d4aa-0e77-55c5-9460-7b73a3b1f063 |  | note | Paper version Upload - 447-FAB-ITP-003
checklist-flat |  |  | checklist | Dispatch Checklist |  |  |  |  | Yes | Dispatch Checklist | 6c05aaee-a6f1-4e0b-880b-01c61532a377
checkpoint-status |  |  | checkpoint | Paper version Uploaded - 447-FAB-ITP-004
label | 7ebdd4fd-58bf-5506-b940-dae32ea9714a |  | note | Photo's lodged to CONQA
checklist-flat |  |  | checklist | Out Of Tolerance Check |  |  |  |  | Yes | Out Of Tolerance Check | 75b7b273-84be-4860-bf5d-151b1d3cb1b7
checkpoint-status |  |  | checkpoint | Panel Tolerance
label | cd305e8d-7442-55ac-b48c-4b28f770c253 |  | note | Pass if in tolerance / Fail if out of tolerance
label | 9e0d3f83-55b5-5d6f-93ba-271cf5333bae |  | note | If Fail (out of tolerance), proceed to below steps. If Pass, move on.
button | 2c323a08-a160-5259-b2bc-5fed38c0157c |  | button | Out of tolerance panel drawing submitted | Yes,No
button | ac697ac9-4d28-5ac2-b2b1-61895e5301cf |  | button | Installation of base framing in accordance with 447-SD- 4701 | Yes,No
button | 976f6e8c-4bcd-5a46-95eb-6cb350090bad |  | button | Fixing and fixtures are installed as documented by Fairlite / fixing schedule FX01 / FX02 | Yes,No
button | 698ce261-ebe3-5dd9-8d9d-79631ca850c4 |  | button | Panel installed in accordance with the architectural documentation / project performance documents 447-SD-4701 | Yes,No
button | 1cb64078-cf8a-5474-9267-944f6c07d9b0 |  | button | Gasketing installed | Yes,No
button | d9674d19-d18e-561c-ad86-b29f2994b9ca |  | button | Check for damages / scratches | Yes,No
button | 1906b720-ba88-5c1c-90cc-ae26ac81dc9a |  | button | Film removed | Yes,No
label | 82bd46ee-31ab-5def-a035-8594ccea1bf0 |  | note | Once completed and new panel installed, change above status to pass
checklist-flat |  |  | checklist | Receival Of Panels Onsite |  |  |  |  | Yes | Receival Of Panels Onsite | 9dce2d66-5f89-4f0c-b810-d138aded9593
checkpoint-status |  |  | checkpoint | Check deliveries of materials for damage that may have occurred in transportation on truck prior to unloading
checkpoint-status |  |  | checkpoint | Delivered nose cone panels have protective film and are free of damage
checkpoint-status |  |  | checkpoint | Vertical stiffeners installed with maximum 350mm spacing
checkpoint-status |  |  | checkpoint | Horizontal stiffener installed between each vertical stiffener
checkpoint-status |  |  | checkpoint | structural silicone installed to all stiffeners and gaskets installed.
checkpoint-status |  |  | checkpoint | Delivery Docket provided
checklist-flat |  |  | checklist | Installation of Nose Cone panels |  |  |  |  | Yes | Installation of Nose Cone panels | d478ba0a-5ca7-45c0-9db4-192e5cd5310f
checkpoint-status |  |  | checkpoint | Gasketing installed
checkpoint-status |  |  | checkpoint | Final check "per level"
checkpoint-status |  |  | checkpoint | Panels are installed as documented and within tolerance
checkpoint-status |  |  | checkpoint | Check for damages / scratches
checklist-flat |  |  | checklist | Silicone Procedures |  |  |  |  | Yes | Silicone Procedures | f028a8b2-a299-48e7-80e5-1deb3f5e0ccf
checkpoint-status |  |  | checkpoint | Document type selected and uploaded below
select | f6d02d88-e19b-5bc2-a857-58f47a52846f |  | dropdown | document type uploaded | Butterfly Test Record,Sealant Inspection Record,Sealant Deglazing Checklist,Sealant Silicone Application Checklist
text | 384e77ff-9262-5231-bec3-3ac0be2791f2 |  | textbox | date
checklist-flat |  |  | checklist | Installation of base framing |  |  |  |  | Yes | Installation of base framing | f3f9777f-e58d-40f6-b546-251eac1e4897
checkpoint-status |  |  | checkpoint | Check Latent condition / Alignment of existing panel prior to installation of overclad panel
checkpoint-status |  |  | checkpoint | Adequate room to install Framing sections
checkpoint-status |  |  | checkpoint | Installation of base framing in accordance with 447-SD- 4851
checkpoint-status |  |  | checkpoint | Fixing and fixtures are installed as documented by Fairlite / fixing schedule FX01 / FX02