## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP007 – Pavement Grooving | itp |  |  |  | Yes | ITP007 – Pavement Grooving
section | 1. Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Current revision drawing is being used including the Subcontractor’s copy. Current revision to be obtained via Aconex.
label | Reference Documents - Drawings and drawing registers on Aconex
label | Inspection/ Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer
checkpoint | 1.3 - Definition of the work area
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Work area has been cleared and surveyed (marked on site). Limits of work clearly defined.
label | Reference Documents - Drawings
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer
checkpoint | 1.4 - Grooving Machine
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Details of proposed grooving machines to be submitted to Contract Administrator for approval.
label | Reference Documents - Cl 20.3
label | Inspection/ Test Method - Verify
label | Record of conformity - Aconex Correspondence
label | HP
label | Responsibility - Project Engineer Principal’s Representative
holdpoint | AUTHORITY HOLDPOINT
section | 2. Grooving
checkpoint | 2.1 - Pavement Conditions
label | Frequency - During grooving works
label | Acceptance Criteria - Pavement to be thoroughly inspected and in an acceptable and suitable condition for grooving prior to works commencing.
label | Reference Documents - Cl 20.2
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Site Engineer
checkpoint | 2.2 - Grooving Pattern – Trapezoidal
label | Frequency - During grooving works
label | Acceptance Criteria - Trapezoidal grooves must be:
label | – Nominally 6mm deep by 6mm wide at the bottom and 12mm wide at the top and spaced evenly at 57mm centre to centre
label | – Transverse and continuous
label | – At true 90 degree angle to runway and taxiway centrelines unless indicated otherwise
label | ○ Around in-pavement light fittings, grooving must cease maximum 450mm from centreline of light in all directions.
label | Reference Documents - Cl 20.4.1.1
label | Inspection/ Test Method - Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Site Engineer
checkpoint | 2.3 - Tolerances – Trapezoidal
label | Frequency - During grooving works
label | Acceptance Criteria - Grooving works must be as per the following allowable tolerances:
label | – Spacing to be evenly spaced, no less than 54mm and no more than 60mm centre to centre
label | – Width:
label | – At surface - must not be less than 11.5mm and not more than 15mm
label | – At bottom - must not be less than 4.5mm and not more than 8mm
label | – Depth must not be less than 4.5mm and no more than 8mm
label | Reference Documents - Cl 20.4.1.3
label | Inspection/ Test Method - Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Site Engineer
checkpoint | 2.4 - Grooving New Pavement Surface
label | Frequency - During grooving works
label | Acceptance Criteria - Contract Administrator to witness measurement of groove dimensions
label | Reference Documents - Cl 20.4.1
label | Inspection/ Test Method - Inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Site Engineer Principal’s Representative
section | 3. Slurry Removal
checkpoint | 3.1 - Removal of Slurry
label | Frequency - Progressively during works and after
label | Acceptance Criteria - Grooving machine must flush the grooves of all slurry during grooving process. Any residual slurry must be removed using high-pressure water in combination with hand or mechanical sweeping. Slurry must not be allowed to harden in the groove.
label | Reference Documents - Cl 20.4.2
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Site Engineer
checkpoint | 3.2 - Notification of Completion of Cleaning
label | Frequency - At each of each work period
label | Acceptance Criteria - Contract Administrator is notified of completion of cleaning of pavement surface
label | Reference Documents - Cl 20.4.2
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Site Engineer Principal’s Representative
checkpoint | Final Inspection
note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP