## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-CIV-SSB-Rail Delineation Temporary Fencing
ITP Description: |  | Rail Delineation Temporary Fencing for Camms Road
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2023-08-11
ITP created by: |  | Isaac El Zayat
ITP approved for use by: |  | Aldrin Guinchoma
Special Notes to ConQA Team : |  | ITP for SSB Rd only
Inspection & Test Plan - Rail Delineation Fencing
[9 empty] | Revision: | 0
[9 empty] | Date: | 2023-08-11
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings L1-CHE-STD-005 L1-CHE-STD-025 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries-Materials
2.1 | Concrete | IFC Drawings | 32MPa concrete to be used as per IFC drawings. | Document Review | Each Mix | HP | SE/Site Supervisor | Certificate of Compliance
2.2 | Steel components | IFC Drawings AS41000 AS1163 | All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250 | Document review Visual and Measure | All elements | IP | SE/Site Supervisor | Supplier Certificate of Compliance
3 | Preliminaries-Documentations
3.1 | Excavation works | IFC Drawings L1-CHE-STD-005 | Excavation for post foundation must not undermine track and comply with PTDT requirements. Follow asset owners guidelines for work around their service. Excavation must use Non Distructive Digging in the rail corridor | Visual |  | IP | SE/Site Supervisor | This ITP
4 | Pre-construction / Pre-installation Activities
4.1 | Survey Set-out | IFC Drawings | Survey to set out the following but not limited to: existing services, post locations, refuge bays Offset checked against the running edge prior to installation of posts. Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template) Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts) | Measure Visual inspect | Each element | IP | Surveyor SE/PE/SPE | This ITP
5 | Construction / Installation Activities
5.1 | Ground Conditions | IFC Drawings | All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. | Visual | Each post | IP | SE/Site Supervisor | This ITP
5.2 | Post Foundation | IFC Drawings | Concrete - 300mm Dia - 1000 mm Depth CHS Sleeve: - Depth 1400 - Other Dimensions as per IFC Direct Driven: - 88.9x4 CHS - Depth: 1500 Spacings: Typical: 2700 max Gates: 1350 Refuge: 1200 | Measure | Each footing | IP | SE/Site Supervisor | This ITP
5.3 | Post Installation | IFC Drawings L1-CHE-STD-005 | Up track: Minimum offset 3000mm from centreline of track. Down track: Minimum offset 2200mm from centreline of track. Maximum post spacing to be 3.1m Two spans at 1350CTRS at the end and at Refuge bays. Max. post height 1800mm above ground level. Vertical Tolerance: ±20mm from the design line. | Measure | Each post | IP | SE/Site Supervisor | This ITP
5.4 | Chain Wire Mesh Installation | IFC Drawings | Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire. Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire. | Visual | Each element | IP | SE/Site Supervisor | This ITP
5.5 | Bracing | IFC Drawings | 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps. Bracing to be installed on both sides of the fence at the fence corners | Visual | Each element | IP | SE/Site Supervisor | This ITP
5.6 | Refuge Installation | IFC Drawings | Refuge Access to only open from track side. No chain wire mesh to be installed at refuge access. Refuge Access to be located maximum 10m along down track and staggered from up track refuge. 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only. | Visual | Each element | IP | SE/Site Supervisor | This ITP
5.7 | Refuge Signage | IFC Drawings | Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX) | Visual | Each element | IP | SE/Site Supervisor | This ITP
6 | Post-construction / Post-installation Activities
6.1 | Fence Height and Track Clearance | IFC Drawings | Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings. | Measure | Each lot | IP | SE/Site Supervisor | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /