## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-057-CIV-SSB-Rail Delineation Temporary Fencing | itp |  |  |  |  | ITP-057-CIV-SSB-Rail Delineation Temporary Fencing Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-CIV-SSB-Rail Delineation Temporary Fencing
label | ITP Description: Rail Delineation Temporary Fencing for Camms Road
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 11/08/2023
label | ITP created by: Isaac El Zayat
label | ITP approved for use by: Aldrin Guinchoma
label | 1.1 Non Dependent
label | Reference: IFC Drawings L1-CHE-STD-005, L1-CHE-STD-025
section | Preliminaries-Materials
checkpoint | 2.1 Concrete
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 32MPa concrete to be used as per IFC drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Mix
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Certificate of Compliance
text | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Steel components
label | REFERENCE: IFC Drawings AS41000, AS1163
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
label | ○ Steel section sizes must be checked on site.
label | ○ Steel posts to be CHS with a grade of C250
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review, Visual and Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: All elements
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
text | Date Completed:
section | Preliminaries-Documentations
checkpoint | 3.1 Excavation works
label | REFERENCE: IFC Drawings L1-CHE-STD-005
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Excavation for post foundation must not undermine track and comply with PTDT requirements.
label | ○ Follow asset owners guidelines for work around their service.
label | ○ Excavation must use Non Distructive Digging in the rail corridor
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 4.1 Survey Set-out
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays
label | ○ Offset checked against the running edge prior to installation of posts.
label | ○ Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
label | ○ Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual inspect
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
section | Construction / Installation Activities
checkpoint | 5.1 Ground Conditions
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each post
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 5.2 Post Foundation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete
label | – 300mm Dia
label | – 1000 mm Depth
label | CHS Sleeve:
label | – Depth 1400
label | – Other Dimensions as per IFC
label | Direct Driven:
label | – 88.9x4 CHS
label | – Depth: 1500
label | Spacings:
label | ○ Typical: 2700 max
label | ○ Gates: 1350
label | ○ Refuge: 1200
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each footing
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 5.3 Post Installation
label | REFERENCE: IFC Drawings L1-CHE-STD-005
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Up track: Minimum offset 3000mm from centreline of track.
label | ○ Down track: Minimum offset 2200mm from centreline of track.
label | ○ Maximum post spacing to be 3.1m
label | ○ Two spans at 1350CTRS at the end and at Refuge bays.
label | ○ Max. post height 1800mm above ground level.
label | ○ Vertical Tolerance: ±20mm from the design line.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each post
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 5.4 Chain Wire Mesh Installation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire.
label | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 5.5 Bracing
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
label | ○ Bracing to be installed on both sides of the fence at the fence corners
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 5.6 Refuge Installation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Refuge Access to only open from track side.
label | ○ No chain wire mesh to be installed at refuge access.
label | ○ Refuge Access to be located maximum 10m along down track and staggered from up track refuge.
label | ○ 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 5.7 Refuge Signage
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 6.1 Fence Height and Track Clearance
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP