## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-029 ITP Pavement 7 | itp |  |  |  |  | DN1210-029 ITP Pavement 7 Rev 0
section | SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 3.1.1 - Subbase - (AP65-1): Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 130kN
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Subbase - (AP65-1): Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - ≥ 60%
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Subbase - (AP65-1): Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.1 - Subbase (AP65-1): Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 63.0mm ¦¦ 100% passing
label | 37.5mm ¦¦ 55-85% passing
label | 19.0mm ¦¦ 33-65% passing
label | 9.5mm ¦¦ 20-50% passing
label | 4.75mm ¦¦ 10-36% passing
label | 2.36mm ¦¦ 5-27% passing
label | 1.18mm ¦¦ 2-20% passing
label | 0.425mm ¦¦ 1-13% passing
label | 0.075mm ¦¦ 6% max passing
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - Subbase (AP65-1): Shape Control
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 34-50%
label | 19.0 – 4.75 ¦¦ 18-40%
label | 9.5 – 2.36 ¦¦ 12-32%
label | 4.75 – 1.18 ¦¦ 6-24%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 0-15%
label | 0.6 – 0.15 ¦¦ 0-12%
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.3 - Subbase (AP65-1): Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - ≥ 30
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.4 - Subbase (AP65-1): Cone Penetrometer Limit
label | Detail - NZS4407:2015, Test 3.2 Cone Penetration
label | Acceptance / Conformance Criteria - Cone Penetrometer ≤ 25
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.5 - Subbase (AP65-1): Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - Plasticity Index ≤ 8
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.6 - Subbase (AP65-1): Accelerated Weathering
label | Detail - NZTA T/20 Ethylene Glycol Accelerated Weathering Test
label | Acceptance / Conformance Criteria - ≤ 30% increase in fines
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.7 - Subbase (AP65-1): Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.1 - Basecourse (AP40-1): Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 130kN
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.2 - Basecourse (AP40-1): Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - ≥ 80%
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.3 - Basecourse (AP40-1): Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.1 - Basecourse (AP40-1): Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 37.5mm ¦¦ 100% passing
label | 19.0mm ¦¦ 60-75% passing
label | 9.5mm ¦¦ 37-50% passing
label | 4.75mm ¦¦ 20-35% passing
label | 2.36mm ¦¦ 12-28% passing
label | 1.18mm ¦¦ 9-20% passing
label | 0.600mm ¦¦ 7-12% passing
label | 0.300mm ¦¦ 3-10% passing
label | 0.150mm ¦¦ 0-5% passing
label | 0.075mm ¦¦ 0-5% passing
label | Standard / Specification - TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.2 - Basecourse (AP40-1): Shape Control
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 28-48%
label | 19.0 – 4.75 ¦¦ 14-34%
label | 9.5 – 2.36 ¦¦ 7-27%
label | 4.75 – 1.18 ¦¦ 6-22%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 5-19%
label | 0.6 – 0.15 ¦¦ 2-14%
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.3 - Basecourse (AP40-1): Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - ≥ 40
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.4 - Basecourse (AP40-1): Cone Penetrometer Limit
label | Detail - NZS4407:2015, Test 3.2 Cone Penetration
label | Acceptance / Conformance Criteria - Cone Penetrometer ≤ 30
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.5 - Basecourse (AP40-1): Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - Plasticity Index ≤ 8
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.6 - Basecourse (AP40-1): Clay Index
label | Detail - Clay Index NZS 4407 Test 3.5
label | Acceptance / Conformance Criteria - <5
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.7 - Basecourse (AP40-1): Accelerated Weathering
label | Detail - NZTA T/20 Ethylene Glycol Accelerated Weathering Test
label | Acceptance / Conformance Criteria - ≤ 30% increase in fines
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | — Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – CONSTRUCTION: Subbase Layer Construction (AP65-1)
checkpoint | 4.1 - Subbase - AP65-1 - Plateau Density Test
label | Detail - Using a 14T Roller carry out plateau density test to determine optimum rolling pattern using static and vibratory passes
label | Acceptance / Conformance Criteria - Plateau Density Report
label | Standard / Specification - NZTA B/02 7.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2 - Subbase - AP65-1 - 3m Straight Edge
label | Detail - Formation check to ensure surface is smooth
label | Acceptance / Conformance Criteria - +/- 10mm
label | Standard / Specification - TNZ B/2 7.7
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - Every 20m Centres, 1 each lane
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3 - Subbase - AP65-1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -15mm + 0mm
label | Standard / Specification - NZTA B/02 5.1
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres, 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.4 - Subbase - AP65-1 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - NZTA B/02 7.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.5 - Subbase - AP65-1 - Benkelmen Beam
label | Detail - As directed by Engineer 15m staggered by wheel path for each lane.
label | Acceptance / Conformance Criteria - 90th Percentile: 2.47mm
label | ○ Maximum: 2.92mm
label | Standard / Specification - PS 20.14.5, NTC0160
label | Verifying Document - Test Report
label | Testing Quantity Required (based from schedule qtys) - As directed by Engineer
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 – CONSTRUCTION: Basecourse Layer Construction (A40-1)
checkpoint | 5.1 - Basecourse - (AP40-1): Plateau Density Test
label | Detail - Using a 14T Roller carry out plateau density test to determine optimum rolling pattern using static and vibratory passes
label | Acceptance / Conformance Criteria - Plateau Density Report
label | Standard / Specification - NZTA B/02 7.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2 - Basecourse - (AP40-1): 3m Straight Edge
label | Detail - Formation check to ensure surface is smooth
label | Acceptance / Conformance Criteria - +/- 10mm
label | Standard / Specification - TNZ B/2 7.7
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - Every 20m Centres, 1 each lane
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3 - Basecourse - (AP40-1): Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -15mm + 0mm
label | Standard / Specification - NZTA B/02 5.1
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres, 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.4 - Basecourse - (AP40-1): Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >98% of MDD
label | ○ Min >95% of MDD
label | Standard / Specification - NZTA B/02 7.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.5 - Basecourse - (AP40-1): Benkelmen Beam test
label | Detail - As directed by Engineer 15m staggered by wheel path for each lane.
label | Acceptance / Conformance Criteria - 90th Percentile: 1.85mm
label | ○ Maximum: 2..24mm
label | Standard / Specification - PS 20.14.5, NTC0160
label | Verifying Document - Test Report
label | Testing Quantity Required (based from schedule qtys) - As directed by Engineer
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 6 – AS-BUILTS / REDPEN MARKUPS
checkpoint | 6.1 - As-Builts/ Red pen markup
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills,Any changes made on pavement layers
label | Acceptance / Conformance Criteria -
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Red pen markups
label | Testing Quantity Required (based from schedule qtys) - During Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV/SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature