## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | FHIMS-QA-6007 - PCP Network Drainage | itp |  |  |  |  | FHIMS-QA-6007 - PCP Network Drainage Rev 0
section | PCP Network Drainage
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Obtain Permits
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Control Checklist - Digging Checklist (incl. marking out & potholing existing services), PTW #2 - Trench Excavation Inspection, PTW #1 - Confined Space. Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | Records - Permit attached or permit number noted
checkpoint | 2 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, TMP is approved all personnel are inducted to site
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - All personnel inducted to site, TMP as required for sub-work area, any permits/approvals required for work area obtained
label | Records - As per conformance criteria
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Installation of Erosion and Sediment Controls (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set up Erosion and sediment controls as per ESCP and undertake pre & post rainfall checks
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Check ESCP and monitor weather for rainfall checks
label | Records - EMP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Installation of Erosion and Sediment Controls (2)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Monitor effectiveness of the ESCP Controls throughout the construction process
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Check EMP
checkpoint | 5 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Survey setout of pipeline of GPS design on excavation machinery as required by contractor to construct to design
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey/ Use of GPS design
label | Records - Survey receipt where used
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate existing services by hand digging (1)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | Conformance Criteria - All conflicts have been located. New services and/or conflicts recorded.
label | Records - Service Location & Potholing PCP
checkpoint | 6 - Locate existing services by hand digging (2)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Close approach permits in place
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Approved permits in place
checkpoint | 7 - Trenching and Excavation (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspect trench profile and ensure it is correct to lines and levels to design
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Line and level is correct
label | Records - Drainage Line Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching and Excavation (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure trench width meets the specification
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Trench width meets design cross sections - Detail B & C Church Rd Watermain and wastewate rising main shared trech details berm/access roads crossing & road crossing.
label | Records - Drainage Line Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching and Excavation (3)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Interface with existing services - UG Power & Telco
label | Frequency - CH 285, CH 280-1350, CH 875
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Interface with Aurora UG cable
label | ○ Close Approach permit in place and procedures followed.
label | ○ Item 6.
label | Records - This PCP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Undercut material for re-use as trench backfill in berm/access road detail
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Backfill Construction Material
label | Frequency - Excavated material for re-use as trench backfill
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Field testing
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Foundation Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test formation level on completion of excavation to check if undercut required
label | Frequency - One test per 10 linear metres
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer or Shear Vane as appropriate for soil type
label | Conformance Criteria - If scala is less than 2 blows per 100mm or shear strength less than 50Kpa, then the engineer shall be notified
label | Records - Drainage Line Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Pipe Bedding/Haunching Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Pipe bedding
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - MDD & PSD
label | Records - Lab Test Report, Pipe supplier letter
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Pipe Bedding/Haunching Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Backfill Construction Material
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - MDD & PSD
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Pipe Bedding/Haunching Material Compliance (3)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Backfill Construction Material (Road crossing)
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - MDD & PSD
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Bedding
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure bedding material is compacted
label | Frequency - Prior to laying pipe
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Testing undertaken to correlate Clegg hammer target (CIV) to MDD via NDM testing
label | Records - Clegg test results
checkpoint | 12 - Pipes, valves & fittings
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | Frequency - Each delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
label | Conformance Criteria - Pipe - Diameter & Class
label | Records - Material certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Pipe Welding (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Pipe welding meets specification requirements
label | Frequency - Each Weld
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Welding records
label | Conformance Criteria - Butt Welding to be completed as per specification
label | Records - Weld Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Pipe Welding (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Butt weld testing
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Test results
label | Conformance Criteria - Two welds undertaken to demonstrate the pipes have been successfully welded under the site conditions. Tensile strength of 95% with no brittle fracture.
label | Records - Test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Pipe Welding (3)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - EF weld testing
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Test results
label | Conformance Criteria - One test welds undetaken on thickest walled PE pipe to demonstrate the pipes can be successfully using equipment and methodology.Maximum brittle fracture is 33% of the fusion length.
label | Records - Test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Pipe Laying (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Notification to Engineer that pipe laying works are due to commence to allow Engineer opportunity to inspect as work proceeds
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Notification
label | Records - This PCP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Pipe Laying (2)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Pipe Laying -Variation between design invert level to as-laid invert level must meet specifications.
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Grade >1%: Invert 10mm or less from design (If pipe less than or equal to 1% grade, invert to be no more than 3mm from design levels)
label | Records - Photos & Drainage Line Record
checkpoint | 14 - Pipe Laying (3)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - DN 315 OD PE 100 PN 16 Watermain & DN 63 OD PE 100 Pressure Sewer
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Installed as per IFC drawings ad meets design cross sections - Detail B & C Church Rd Watermain and wastewate rising main shared trech details berm/access roads crossing & road crossing.
label | Records - Photos
checkpoint | 14 - Pipe Laying (4)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - No defects/ gaps / pipes are aligned correctly
label | ○ Pipes are clean nd free from dirt and debris.
label | Records - Photos
checkpoint | 14 - Pipe Laying (5)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - As-built survey of pipes installed
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - As per IFC drawings and as per specification.
label | Records - Survey Receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - AV installation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Installation as per IFC drawing detail
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - As per IFC drawings and as per specification.
label | Records - Photos/Inspections
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - Design Engineer Pre-backfill Inspection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Inspection of pipes prior to backfilling to ensure they have been installed correctly and that the joints are sealed. Check for any gaps.
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Compliance with the Specification
label | Records - Inspection Record
checkpoint | 17 - Haunching/Backfilling (berm/access road crossings)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Backfill in 200 mm loose lifts as per IFC detail B Chuch Rd WM & WW shared trenched detail. Noting that backfill will comprise of scalpings, and re-use of excavated material.
label | Frequency - Clegg testing every 50m along trenchline at 200 mm lifts
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - NDM testing will be undertaken at intervals of 1 in every 2km to correlate Clegg hammer target (CIV) to MDD
label | Records - Clegg test results
checkpoint | Haunching/Backfilling (trafficable areas)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Backfill in 200 mm loose lifts as per IFC detail C Chuch Rd WM & WW shared trenched detail. Noting that backfill will comprise of scalpings, 400 mm minimum of AP65 & 200 mm of M/4 AP40 and reinstated road surface in compliance with QLDC LDSC B1-3.
label | Frequency - NDM testing every 50 m linear metres along pipeline & Clegg testing in between
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - 95% of MDD
label | Records - Lab test results / Clegg test results
checkpoint | 18 - Pressure testing (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Notification to Engineer of at least 48 hours of testing and completion of pre-requisites
label | Frequency - Prior to Commissioning
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Notification
label | Records - This PCP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18 - Pressure testing (2)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Pressure pipelines to be pressure tested
label | Frequency - Prior to Commissioning
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Pressure Test Record Church Rd CH 40 - CH 1450.
label | ○ Compliance with QLDC CoP Appendix C criteria.
label | Records - Pressure Test Record
checkpoint | 19 - Disinfection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Disinfection & bacteriological testing
label | Frequency - Prior to Commissioning
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Disinfection as per approved methodoloy in accordance with QLDC CoP Appendix D aceptance criteria
label | Records - Bacteriological test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 20 - As-builts
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Asbuilt Drawing
checkpoint | 21 - Asset Capture
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Asset register to be completed
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Asset informtion to be entered to correct spreadsheets
label | Records - Asset register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 22 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all OFIs are closed and included within QA file, Delivery Dockets, Test Reports Surveys and Check Sheets to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded
label | Records - All lot QA
checkpoint | Final Inspection
label | QA Compiled By: Maddie Irving
label | QA checked By Discipline Manager: Andy Boyd
label | QA checked By Quality Manager: Kurt Beeton
textbox | Accepted By Design Engineer:
signoff | Sign ITP
checklist | FHIMS-QA-6007 - PCP Raw Water Pipeline | itp |  |  |  |  | FHIMS-QA-6007 - PCP Raw Water Pipeline Rev 0
section | PCP Raw Water Pipeline
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Obtain Permits
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Control Checklist - Digging Checklist (incl. marking out & potholing existing services), PTW #2 - Trench Excavation Inspection, PTW #1 - Confined Space. Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | Records - Permit attached or permit number noted
checkpoint | 2 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, TMP is approved all personnel are inducted to site
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - All personnel inducted to site, TMP as required for sub-work area, any permits/approvals required for work area obtained
label | Records - As per conformance criteria
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Installation of Erosion and Sediment Controls (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set up Erosion and sediment controls as per ESCP and undertake pre & post rainfall checks
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Check ESCP and monitor weather for rainfall checks
label | Records - EMP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Installation of Erosion and Sediment Controls (2)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Monitor effectiveness of the ESCP Controls throughout the construction process
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Check EMP
checkpoint | 5 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Survey setout of pipeline of GPS design on excavation machinery as required by contractor to construct to design
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey/ Use of GPS design
label | Records - Survey receipt where used
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate existing services by hand digging
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | Conformance Criteria - All conflicts have been located. New services and/or conflicts recorded.
label | Records - Service Location & Potholing PCP
checkpoint | 7 - Trenching and Excavation (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspect trench profile and ensure it is correct to lines and levels to design
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Line and level is correct
label | Records - Drainage Line Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching and Excavation (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure trench width meets the specification
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Trench width meets design cross sections - Detail A Raw water steep shared trench detail
label | Records - Drainage Line Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Undercut material for re-use as trench backfill in berm/access road
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Backfill Construction Material
label | Frequency - Excavated material for re-use as trench backfill (Excluding steep slope section CH 80-120)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Field testing
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Foundation Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test formation level on completion of excavation to check if undercut required
label | Frequency - One test per 10 linear metres (Excluding steep slope section CH 80-120)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer or Shear Vane as appropriate for soil type
label | Conformance Criteria - If scala is less than 2 blows per 100mm or shear strength less than 50Kpa, then the engineer shall be notified
label | Records - Drainage Line Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Pipe Bedding/Haunching Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Pipe bedding
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - MDD & PSD
label | Records - Lab Test Report, Pipe supplier letter
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Pipe Bedding/Haunching Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Backfill Construction Material
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - MDD & PSD
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Pipe Bedding/Haunching Material Compliance (3)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Backfill Construction Material (Road crossing)
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - MDD & PSD
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Bedding
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure bedding material is compacted
label | Frequency - Prior to laying pipe
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Testing undertaken to correlate Clegg hammer target (CIV) to MDD via NDM testing
label | Records - Clegg test results
checkpoint | 12 - Pipes, valves & fittings
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | Frequency - Each delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
label | Conformance Criteria - Pipe - Diameter & Class
label | Records - Material certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Pipe Welding (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Pipe welding meets specification requirements
label | Frequency - Each Weld
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Welding records
label | Conformance Criteria - Butt Welding to be completed as per specification
label | Records - Weld Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Pipe Welding (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Butt weld testing
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Test results
label | Conformance Criteria - Two welds undertaken to demonstrate the pipes have been successfully welded under the site conditions. Tensile strength of 95% with no brittle fracture.
label | Records - Test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Pipe Welding (3)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - EF weld testing
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Test results
label | Conformance Criteria - One test welds undetaken on thickest walled PE pipe to demonstrate the pipes can be successfully using equipment and methodology.Maximum brittle fracture is 33% of the fusion length.
label | Records - Test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Pipe Laying (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Notification to Engineer that pipe laying works are due to commence to allow Engineer opportunity to inspect as work proceeds
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Notification
label | Records - This PCP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Pipe Laying (2)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Pipe Laying -Variation between design invert level to as-laid invert level must meet specifications.
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Grade >1%: Invert 10mm or less from design (If pipe less than or equal to 1% grade, invert to be no more than 3mm from design levels)
label | Records - Photos & Drainage Line Record
checkpoint | 14 - Pipe Laying (3)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - DN 315 OD PE 100 PN 16 Watermain & shared trench services
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Installed as per IFC drawings ad meets design cross sections - Detail A Raw water steep shared trench detail
label | Records - Photos
checkpoint | 14 - Pipe Laying (4)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - No defects/ gaps / pipes are aligned correctly
label | ○ Pipes are clean nd free from dirt and debris.
label | Records - Photos
checkpoint | 14 - Pipe Laying (5)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - As-built survey of pipes installed
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - As per IFC drawings and as per specification.
label | Records - Survey Receipt
checkpoint | 15 - AV installation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Installation as per IFC drawing detail
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - As per IFC drawings and as per specification.
label | Records - Photos/Inspections
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - Design Engineer Pre-backfill Inspection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Inspection of pipes prior to backfilling to ensure they have been installed correctly and that the joints are sealed. Check for any gaps.
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Compliance with the Specification
label | Records - Inspection Record
checkpoint | 17 - Haunching/Backfilling (berm/access road crossings)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Backfill in 200 mm loose lifts. Noting that backfill will comprise of scalpings, and re-use of excavated material.
label | Frequency - Clegg testing every 50m along trenchline at 200 mm lifts
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - NDM testing will be undertaken at intervals of 1 in every 2km to correlate Clegg hammer target (CIV) to MDD
label | Records - Clegg test results
checkpoint | Haunching/Backfilling (Steep slope - CH 80-120)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Backfill with AP20 cement mixture as per IFC Detail A Raw water steep shared trench detail
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Batch report
label | Conformance Criteria - Supplier to provide batch report to confirm correct weightings of cement and AP20-
label | Records - Batch report
checkpoint | 18 - Pressure testing (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Notification to Engineer of at least 48 hours of testing and completion of pre-requisites
label | Frequency - Prior to Commissioning
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Notification
label | Records - This PCP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18 - Pressure testing (2)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Pressure pipelines to be pressure tested
label | Frequency - Prior to Commissioning
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Pressure Test Record
label | ○ Compliance with QLDC CoP Appendix C criteria.
label | Records - Pressure Test Record
checkpoint | 19 - Disinfection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Disinfection & bacteriological testing
label | Frequency - Prior to Commissioning
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Disinfection as per approved methodoloy in accordance with QLDC CoP Appendix D aceptance criteria
label | Records - Bacteriological test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 20 - As-builts
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Asbuilt Drawing
checkpoint | 21 - Asset Capture
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Asset register to be completed
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Asset informtion to be entered to correct spreadsheets
label | Records - Asset register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 22 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all OFIs are closed and included within QA file, Delivery Dockets, Test Reports Surveys and Check Sheets to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded
label | Records - All lot QA
checkpoint | Final Inspection
label | QA Compiled By: Maddie Irving
label | QA checked By Discipline Manager: Andy Boyd
label | QA checked By Quality Manager: Kurt Beeton
textbox | Accepted By Design Engineer:
signoff | Sign ITP