## Sheet1
NWPC Click & Collect ITP's
Type | Name | Values | Prompting Name | Postfix
checklist | Civil - Buildings Subgrade |  | Civil - Buildings Subgrade - CnC
section | Subgrade base
checkpoint | Geotech Eng inspection report received- and close-out
checkpoint | Geotech Eng Inspection of subgrade and proof rolling prior to filling
section | Building Subgrade build-up
checkpoint | GL and datum provided
checkpoint | Placement of hardfill layer compacted as per design
checkpoint | Drainage piping installed under foundation level
checkpoint | Platforms spot checks heights and location
section | Subgrade Sign-off
checkpoint | Subgrade QA and test results received
checkpoint | Geotech Eng Inspection of subgrade and proof rolling report received and close-out
checklist | Civil - Drainage Checklist |  | Civil - Drainage Checklist - CnC
section | Pre-start
checkpoint | Locates done on site – confirm no clash with pre-existing underground services
checkpoint | Appropriate permits in place
checkpoint | GL and datum provided
checkpoint | Upload drawings / check services depths, confirm location, filling/digging
checkpoint | Clear work area
section | Trenching
checkpoint | Delineation of area
checkpoint | Benching appropriate for ground conditions
checkpoint | Safety of trenching conditions and edge protection
checkpoint | Civil Eng inspection report received and close-out if unsuitable subgrade conditions exist
section | Installation
checkpoint | Confirm correct bedding material being used and spot check RL’s
checkpoint | Manhole installation
tickbox | Confirm MH diameter
tickbox | Joint sealing (if precast)
tickbox | Invert level
checkpoint | Pipes installed and correct junctions/connections
checkpoint | Civil Eng inspection report received and close-out for first pipe run
checkpoint | Council inspection report received and close-out
section | Backfilling
checkpoint | Appropriate backfill material
checkpoint | Backfill at 150mm lifts and compact as per Civil spec
section | Post Backfilling
checkpoint | Internal manhole works
tickbox | Benching completed
tickbox | Council inspection report received and close-out – as-built plan required
checkpoint | Drainage QA received and as built
checklist | ITP Civil - Bore Piling - Driveway Piles |  | ITP Civil - Bore Piling - Driveway Piles - CnC
section | Pile base (Pre drilling)
checkpoint | Check ground suitability for Piling Rig
checkpoint | Geotech Eng inspection report received- and close-out (Proof Drilling)
section | Set up and drilling
checkpoint | GL and datum provided
checkpoint | Boring/ casing installation /Diameter/ Plumbness / Depth check to RL
checkpoint | Inspection of reinforcement cages, connection, welding / placement of cages
checkpoint | Structural Eng inspection report received and close-out
checkpoint | Geotech Eng inspection report received and close-out
checkpoint | Council inspection report received and closed-out.
section | Access/Safety
checkpoint | Clear access for trucks/pump/workers
checkpoint | Sediment erosion controls in place
section | Pour |  |  |  |  | RFI
checkpoint | Confirm design mix
checkpoint | Confirm concrete is being tested (slump and cylinders samples)
checkpoint | Weather recorded
section | Post Pour
checkpoint | Check and confirm Pile as-built
checkpoint | Check and confirm Starter bars
checkpoint | Subcontractor QA received including dockets
checklist | Civil - In Ground Services |  | Civil - Footpath In Ground Services - CnC
section | Pre-start
checkpoint | Conduits in place running through/under footings to desired locations
checkpoint | Trench formed and sand bed completed
checkpoint | Conduits underslab completed
section | Services trench
checkpoint | Confirm heights and cover of Conduits (Tapes)
tickbox | Electrical
tickbox | Comms
tickbox | Hydraulics
tickbox | Gas
section | Post-services
checkpoint | Fines cover
checkpoint | Pits to final RL
checkpoint | Final backfill & compacted
checklist | Facade - Below Ground Waterproofing |  | Facade - Below Ground Waterproofing - CnC
section | Pre-start
checkpoint | Panel QA received
checkpoint | Panel joints grouted/sealed
checkpoint | GL and datum provided
checkpoint | Clean work area
checkpoint | Safe access
section | Installation
checkpoint | Waterproofing as per architectural drawings
checkpoint | Façade Engineer Report received and closed out
checkpoint | Council inspection report received and close-out
section | Post install
checkpoint | Protective layers
checkpoint | Tanking QA received
checklist | Structure - Footing |  | Structure - Footing - CnC
section | 1. Pre-start
checkpoint | QA for sub-grade and relevant services received
Tickbox | Site concrete allowed for in cut.
checkpoint | GL and datum provided
checkpoint | Clear work Area
checkpoint | Review construction drawings and set-out
checkpoint | Geotechnical Eng inspection report received and closed-out
section | 2. Pre-pour
checkpoint | Service trade sign off/QA
checkpoint | Waterproof sign off/QA (DPM)
checkpoint | Formwork signoff/QA
checkpoint | Check foundation width for propping
checkpoint | Reo sign off/QA
checkpoint | GN inspection
Tickbox | iv. Reinforcement size, spacing, supports.
Tickbox | ii. Starters, scabbling, cover checked
Tickbox | iii. Clean formwork and ready to pour
Tickbox | iv. Check RL levels
checkpoint | Structural Eng inspection report received and close-out
checkpoint | Council inspection report received and close-out
section | 3. Access/Safety
checkpoint | Clear access for trucks/pump
checkpoint | Exposed reo capped
checkpoint | Safe access to all areas of pour
section | 4. Pour
checkpoint | Confirm mix
checkpoint | Confirm concrete is being tested (slump and cylinders)
Tickbox | Weather recorded
section | 5. Post pour
checkpoint | Finish
checkpoint | Levels
checkpoint | Starters
checkpoint | Pour QA received including dockets
checklist | Structure - Toe Footings Checklist |  | Structure - Toe Footings Checklist - CnC
section | Pre-start
checkpoint | Panel QA received
checkpoint | GL and datum provided
checkpoint | Backfill to foundation level completed |  |  |  | Internal Rfi Confirm propping plan
checkpoint | Clean work area
section | Pre-Pour
checkpoint | Service trade sign off/QA
checkpoint | Formwork signoff/QA
checkpoint | Waterproof sign off/QA (DPM)
checkpoint | Reo sign off/QA
checkpoint | GN inspection
Tickbox | iv. Reinforcement size, spacing, supports.
Tickbox | ii. Starters, scabbling, cover checked
Tickbox | iii. Clean formwork and ready to pour
Tickbox | iv. Check RL Levels
checkpoint | Structural Eng inspection report received and close-out
checkpoint | Council inspection report received and close-out
section | Access/Safety
checkpoint | Clear access for trucks/pump
checkpoint | Exposed reo capped
checkpoint | Safe access to all areas of pour
section | Pour
checkpoint | Confirm mix
checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint | Weather recorded
section | Post Pour
checkpoint | Finish
checkpoint | Levels
checkpoint | Starters
checkpoint | Pour QA received including dockets
checklist | Structure - Pre-cast Panels |  | Structure - Pre-cast Panels - CnC
section | Pre-start
checkpoint | PrePour PCP inspection done
checkpoint | Timber guides installed – including spacers
checkpoint | Shore Loading and props onsite and in posiiton
checkpoint | Check for clashes on footing step
checkpoint | Confirm Propping plan and Engineer sign off
section | Delivery & Install
checkpoint | Check for damage/defects on arrival
checkpoint | Props & propping bolts onsite
checkpoint | Panels unloaded correctly
checkpoint | Measure internal dimensions
checkpoint | Panels Plumb & Flush
checkpoint | Props Installed
section | Grouting & Sealant
checkpoint | Drypacking done
checkpoint | Grouting pumped
checkpoint | Sealed between panels
section | Post Checks
checkpoint | PCP supplier QA received
checkpoint | Subs installation QA received
checkpoint | Grouting, Drypacking & Sealing QA received
checkpoint | Vertical check done
checklist | Structure - Slab on Grade |  | Structure - Slab on Grade - CnC
section | Pre-start
checkpoint | Services sign-off
tickbox | i. Electrical
tickbox | ii. Fire
tickbox | iii. Hydraulic
tickbox | iv. Comms and Fibre
checkpoint | Subgrade sign-off/QA received
tickbox | i. Backfill and blinding
checkpoint | GL and datum provided
checkpoint | Clean work area
section | Pre-Pour
checkpoint | Waterproofing sign-off/QA
tickbox | i. DPM including tapes and laps
checkpoint | Formwork signoff/QA
tickbox | i. Step down/ falls
tickbox | ii. Ties, propping, seal formworks
tickbox | iii. Seismic gap/expansion joints
checkpoint | Reo sign off/QA
checkpoint | GN inspection
tickbox | i. Details checked
tickbox | iii. Check starters, scabbling, cover checked, thickenings
tickbox | iv. Reinforcement size, spacing, supports.
tickbox | v. Clean formwork and ready to pour
checkpoint | Structural Eng inspection report received and close-out
checkpoint | Council inspection report received and close-out
section | Access/safety/protection
checkpoint | Clear access for trucks/pump
checkpoint | Safe access to all areas of pour
checkpoint | Panel and steel protection
checkpoint | Skip clean and ready
section | Pour
checkpoint | Confirm mix
checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint | Weather recorded
section | Post pour
checkpoint | Finish
checkpoint | Levels
checkpoint | Curing agent
checkpoint | Saw cuts within 24h of pour and slurry removed
checkpoint | Pour QA received including concrete dockets
checklist | Structure - Structural Steel |  | Structure - Structural Steel - CnC
section | Pre-Start
checkpoint | Panel sign-off/QA received
checkpoint | GL and datum provided
checkpoint | Area clean/clear for access equipment
section | Erection
checkpoint | GN inspection
tickbox | Welds, bolts, tensioning, pre drilled holes etc. as per design
checkpoint | Structural Eng inspection report received and close-out
checkpoint | Council inspection report received and close-out
section | Post Erection
checkpoint | Propping where required
checkpoint | Spot check RL’s and plumb
checkpoint | Primer touch-ups
checkpoint | Steel QA received
checkpoint | Grouting to connection plates
checklist | Facade - Eave and Roof |  | Facade - Eave and Roof
section | Pre-start
checkpoint | Steel QA received
checkpoint | ACP Shop Drawing Alignment
checkpoint | GL and datum provided
checkpoint | Clean work area
checkpoint | Safe access
section | Eaves
checkpoint | Framing
Tickbox | DPC & Fixings
Tickbox | Nogs for signage, Cladding & Services
Tickbox | Gutter falls confirmed/RL's Checked
section | Services
checkpoint | Services signoff/QA including nogs
section | RAB
checkpoint | GN Inspection
Tickbox | RAB signoff/QA
Tickbox | Check Fixings
Tickbox | Check Tape/Trade Seal
Tickbox | Confirm Proclima installed as per manual
checkpoint | RAB signoff/QA
section | ACP
checkpoint | ACP installed as per shop drawings
checkpoint | Services cables pulled through – check builders work
checkpoint | Sealants
checkpoint | ACP signoff/QA
section | Roof
checkpoint | Framing
Tickbox | DPC between timber and steel
Tickbox | Timber frame fixings to steel frame/purlins
Tickbox | Gutter falls/Check RL's
checkpoint | Mesh and underlay installed
Checkpoint | ILD Testing
checkpoint | Gutter waterproofing sign-off/QA
checkpoint | Install Roof Underlay
checkpoint | Check roof Sheet Fixings
checkpoint | Service penetrations installed
checkpoint | Proper septation
checkpoint | Roof finishes
checkpoint | Painting panels
checkpoint | Cap flashings
checkpoint | Apron flashings
checkpoint | Services penetrations
checkpoint | EPDM tape / termination bar and sealants installed
checkpoint | Gutter and downpipe installed
checkpoint | Roof signoff/QA
section | Roof safety anchors
checkpoint | Check layout (positioning)
checkpoint | Roof anchors tagged
checkpoint | Roof anchors signoff/QA