## Master List Templates
Id | Type | Name | Values | Prompting Name
8a4bfb74-04d2-47d1-9d9c-4e0e45c8e71f | checklist | Documents |  | Documents
d27e664b-b8db-4dae-8ce3-cc3995597fdf | section | Details
9483f8e0-de31-4f34-b59b-8778c5e33994 | checkpoint | Document attached
71311430-12af-4de5-b2e1-320343a3d7c5 | checklist | Test ITP | itp | Test ITP
20380797-825e-43d5-b636-1e28953acadd | section | Preliminary Works
107e3d9c-f945-48ad-a893-382139576ad3 | checkpoint | 3.1 Pre-construction Photos
955645e1-125c-52ac-a36d-9f7aaf64fd68 | note | Inspection Point: Quality Control Activity - Photos of worksite including vehicle access points.
de815be8-ff5b-5bbf-8fcf-b6a74f875d15 | note | ○ Photos of any existing defects/damage.
f629ba35-c6c9-5e84-afb6-f12afe19ba50 | note | Acceptance Criteria - Coverage of whole site
b343e756-6236-534e-a04c-adde741f9cf9 | note | Verifying Document - Photos saved
487d2c77-26c6-574d-9f8c-69197b900e60 | note | Reference: Contract Specs/Standards - D1.4
aa7dcc23-975c-5d3e-90f1-e46ecef13a8e | note | Inspection Point/Signature & Date - PM
441f8f47-9e59-4e93-af48-52ea9db74b4f | checkpoint | 3.2 Verify Construction Drawings
5979cb19-48d2-5a0f-8a4a-18a2495e019b | note | Inspection Point: Quality Control Activity - Verify Construction Drawings that are in the site folder are the latest revision.
77adfc3c-637c-5532-a2de-de99b4eb0801 | note | Acceptance Criteria - Latest drawings approved
2e7272cf-1b67-5992-8aea-1c720473b1e1 | note | Verifying Document - Drawings Register
91384230-7de8-55b8-b9f0-cf3094b4e632 | note | Reference: Contract Specs/Standards -
53f92b21-b0f6-50b0-9a66-65c339b74caa | note | Inspection Point/Signature & Date - PM
92a4d361-6a90-4261-aacc-b17a70c5ba02 | checkpoint | 3.3 Road Authority Notifications
a5905a4b-3c67-5ea9-9f5c-3f49ad93a559 | note | Inspection Point: Quality Control Activity - Corridor access Permit.
0158a33e-7ce3-58a8-babd-2c00a85ada9b | note | ○ Block by block Temporary Traffic Management Plans.
c980e384-1324-5a31-ad80-c5f42c7f2909 | note | Acceptance Criteria - Permit & Traffic Plan approved
670802ca-5daf-518d-ba40-b11f61b8bba8 | note | Verifying Document - Work Access Permit & TMP
ae04fd1d-8285-5e71-9dc0-6c451b22a24a | note | Reference: Contract Specs/Standards - C1.09, D1.4
afbe1801-0461-5ff9-9968-d71d709c4667 | note | Inspection Point/Signature & Date - PM
d39f31d1-9f41-49b3-8e2e-f1d32ae48a60 | checkpoint | 3.4 Management Plan
dacc70c9-2410-5db2-bd45-66d975547e52 | note | Inspection Point: Quality Control Activity - H&S Plan
c98cf114-7fba-5cd7-9f75-05f14d1dc0c4 | note | ○ Environmental Plan
ff8ca60d-7b07-570e-837e-2ea6f5924d22 | note | ○ Quality Assurances
6ad36c2d-187f-596a-87f1-b024ccfeeffd | note | Acceptance Criteria - Plans & Safety Measures in place
d5f70aa4-3aed-5da0-b07e-f5410907778d | note | Verifying Document - H&S Plan, Method Statement
79d6f9d4-a271-5202-907c-58e7835bcb83 | note | Reference: Contract Specs/Standards - D1.3
7f636cf1-81e6-5b8d-8b3a-e415c151f5d7 | note | Inspection Point/Signature & Date - PM, CR
5d595464-2779-423b-add8-0d8127f9cada | checkpoint | 3.5 Public Notification
3a84e0b1-0335-5dc4-bb53-a8236469f1e8 | note | Inspection Point: Quality Control Activity - Notice of works to properties in the construction zone in each block
111ac031-f06c-52e2-8d36-657040eef63d | note | ○ Notification to Rubbish collection contractor.
6425c7b3-a4a7-5fc9-b4d2-348fb03ae6aa | note | ○ Project Signage
1fb132d3-92db-5038-aa91-124209dd7f89 | note | Acceptance Criteria - 48 hours prior notification
6a28c857-a4f5-59ec-8a55-c083caf0c3a7 | note | Verifying Document - Letter to residents
c926fb82-add6-5d96-9893-e1996f955a14 | note | Reference: Contract Specs/Standards - D1.10
bdbcb526-3a1e-5e5d-86ef-0a808ab8369e | note | Inspection Point/Signature & Date - PM
83d17dff-2396-439e-955c-8f1f727f65ed | checkpoint | 3.6 Shutdown/Isolation
6ea865c2-ca78-5854-8fa3-2264bf699993 | note | Inspection Point: Quality Control Activity - Shutdown/Isolation process verified in each block closure
1555c1d5-29de-5a42-a7d4-8b3739287984 | note | Acceptance Criteria - Shutdown process verified
cd7f89f3-8fdf-5085-8c83-7bb9094c8b0a | note | Verifying Document - Notification letters
ef26b893-83e8-5557-854d-c80eb7263938 | note | Reference: Contract Specs/Standards - C1.16, D2.7.8
28d7be85-39af-58e3-9302-9376a974da67 | note | Inspection Point/Signature & Date - PS
d167c212-b415-420c-a15c-45c677294de6 | checkpoint | 3.7 Construction Set Out
742868c8-23f0-5452-9b92-ba186649d8d7 | note | Inspection Point: Quality Control Activity - Correctly mark out the position of the new pipelines for construction.
9e97b2cc-ba1a-5815-b8f9-fbfc1eb1d305 | note | Acceptance Criteria - Construction Plans checked
5b2e22e1-e5ff-5dc0-99bf-61f23b16df05 | note | Verifying Document - Construction Plans
62386f7d-45bf-5fb2-8ee5-5645b5fb6848 | note | Reference: Contract Specs/Standards - D2.7.1
d58502cb-242d-55dc-b860-3551207f6eba | note | Inspection Point/Signature & Date - PS, CR
a5600e25-383f-46d4-8512-0c264c1e449f | checkpoint | 3.8 Pre-Excavation Permits
dae1eccc-c23e-53c5-a82d-0efd94bccfeb | note | Inspection Point: Quality Control Activity - Permit to excavate for the location has been endorsed by an authorised person.
4086823b-a3b0-5514-bed4-f7f9e3b60915 | note | ○ Existing service plans & locates
c1e5fd2a-aef6-51bf-8cd0-bb993a96c4c9 | note | ○ Close approach permits
e9ebe2eb-6bb3-5920-af4f-3e5f51dc6ced | note | ○ Notifiable works
c0184131-3963-58e5-89ee-4c85ee5a746b | note | Acceptance Criteria - Permit to excavate endorsed
ef5bff12-f195-5b6f-aa81-cb8850c90580 | note | Verifying Document - Ground Disturbance Permit
64acb508-1d91-553b-8bd2-2bec3032ca97 | note | Reference: Contract Specs/Standards - D1.7
7835cccc-5334-5c60-a2d5-886aa9e0b519 | note | Inspection Point/Signature & Date - PS
02c8290d-79fe-4b01-a4f8-43e9d4c6e881 | signoff | HOLD POINT
abbb431d-e004-44ec-b738-fab1868140b8 | section | Incoming Goods Inspections
2aa07f2e-4aed-4158-88a0-e6abf1872ee1 | checkpoint | 4.1 Pipe & Fitting Inspections
335e2b85-3765-5d7c-823f-1a30f4f4c2cd | note | Inspection Point: Quality Control Activity - Visual check of materials delivered:
3c2f6b16-25d4-518b-a78c-50cd0381e2b9 | note | ○ Correct Material & dimensions
38ce9bbf-d35b-56d0-9094-6888dbbe0772 | note | ○ Condition & Quantity
e0aca729-1137-5fa6-a9c4-e65d8d4be14e | note | ○ Free of defects – surface abrasion, ovality, not kinked or crushed
c7813b84-576f-505d-b003-53fb30070daf | note | ○ Batch/serial numbers present
e60eb730-8b8d-5bbe-9001-2c575dd38607 | note | Acceptance Criteria - Correct material & no defects
775a2f60-1a0d-5a61-a840-33859f5f5380 | note | Verifying Document - Packing Slips
5523d66d-7eb8-57b7-8130-17f63b83eb86 | note | Reference: Contract Specs/Standards - D2.4,D3.3, D4.3, D5.3, D8.3
4815886f-d85b-584d-a8bf-54bb43596b4d | note | Inspection Point/Signature & Date - PS
18a89c7a-07fc-4278-9ab2-46bbdeed02f3 | checkpoint | 4.2 Pipe & Fitting Storage
736fc6ca-0587-58a7-aa66-1e6006900b05 | note | Inspection Point: Quality Control Activity - Stored as per manufacturers specifications including maximum height limits and safely chocked in place.
88679b02-09b0-5f6d-85d2-86abe8c910f1 | note | ○ All pipes are end capped.
ace5e548-9b68-55f8-acb6-13682245a6d3 | note | ○ No scoring of pipe more than 10% of thickness.
0f1df64d-4495-5578-a941-f201cb9bd702 | note | ○ No damage to epoxy coating on Ductile fittings.
1dbf0fff-4157-5283-af1b-f1fa245cb0fd | note | Acceptance Criteria - Stored as per manufacturer
c2c2afc7-5301-5e5c-ba67-ba552d116bc1 | note | Verifying Document - Manufacturer’s Storage Instructions
99bbba7a-beec-5223-939d-15034191d36d | note | Reference: Contract Specs/Standards -
1dbd7e86-bf3c-5e32-8b08-073e38069992 | note | Inspection Point/Signature & Date - PS, CR
6b2618a5-8d30-4b91-a333-0dfd3ca9cf5f | signoff | HOLD POINT
1f6a3545-531a-431b-8950-db0056c6a96e | section | Construction Inspections
5b9fc0f7-1004-4407-be8c-24b464b7f09e | checkpoint | 5.1 Trench Excavation
02e391fc-3a18-522d-9c19-e2a03e270cfb | note | Inspection Point: Quality Control Activity - Trench width to be sufficient to safely lay the pipe (including shoring if required) and compact the side support of the new pipe. Bedding details below;
a6f490ee-48df-5ce7-ad7c-e1ea3aa3e379 | note | ○ Sufficient room to enable the pipe, joint, bed, haunch or surround shown in the drawings to be accommodated.
eec54b15-5ecd-5436-96af-7f3f1ec2feb7 | note | ○ Trench depth to enable pipe to be laid with the designed cover as shown on construction plans.
8fd021a9-e8d2-5b4c-8b4b-5843892fc6d1 | note | ○ If trench bottom to be suitable to compact pipe bedding as support pipe.
fc3f41ae-94b6-572c-ac89-2a9ef6fb22bf | note | Acceptance Criteria - Trench dimensions correct
e3b19d68-be79-52b1-b552-b4069f08f057 | note | Verifying Document - Daily Site Diary
84a404dc-63b4-5583-b4db-f3add2e91694 | note | Reference: Contract Specs/Standards - D2.6, D2.7
5aa888e2-14d6-582f-9a52-d9c849c2397e | note | Inspection Point/Signature & Date - PS
27edf7a6-5c6f-40e4-b0c0-9ab61a806878 | checkpoint | 5.2 Encountered Services
da1255de-facf-5b78-9de0-40b88d5693d6 | note | Inspection Point: Quality Control Activity - Block by block ensure existing live services are not unnecessarily damaged by works.
5fc0b366-4852-5bfe-a581-cba57122ba03 | note | ○ Repair any services that are temporarily removed during construction.
c6c5167f-c5f2-5998-b8d3-01f5f3e9341c | note | ○ Record any services found.
0631e0d3-22a9-5d7c-8b37-c6cbd46c7c91 | note | Acceptance Criteria - Existing services not damaged
81f412b2-a38d-50f2-a598-84775c34f384 | note | Verifying Document - Encountered Services Record
90c9acea-6aa9-5d0a-b22b-e74a722eebd8 | note | Reference: Contract Specs/Standards - D1.7, D2.7.7
7d0df532-6775-5e02-87ef-5933b5113c19 | note | Inspection Point/Signature & Date - PS
0bb6eb81-7e4a-451f-830e-1b4ed2ca3ea2 | checkpoint | 5.3 Pipe Installation
e9a5264d-e34d-57c2-b251-70577ea28002 | note | Inspection Point: Quality Control Activity - Interior of each pipe visually inspected to ensure free of debris.
4de7eba6-7a52-508a-8f6f-3da7ba17c6ad | note | ○ Re-cap end of pipe after installation.
9fcd0740-534d-500d-8189-e0970be0fe0f | note | ○ Check pipe installed at correct depth.
97372ff6-7a61-5b54-b317-dc368cef403b | note | ○ Ensure all collars are free from contamination in McDougall St berm
d141a6e9-ce08-571e-8cfd-8a4080f2f31b | note | Acceptance Criteria - Pipes free of debris & correctly installed
6c48859f-43ee-519f-b185-e2757b35f5ef | note | Verifying Document - Daily Site Diary
d6e34e20-3287-5bb8-accf-914843f1e5ed | note | Reference: Contract Specs/Standards - D2.5, D2.7, D8.4.2
c344ad27-9a7c-5088-8578-ce9de1f06115 | note | Inspection Point/Signature & Date - PS
315ca360-db4e-4b0f-b047-bcd13a88803d | checkpoint | 5.4 Concrete Pre-Pour Inspection
a0c3ca9d-7c53-5f00-a910-1efc9d53070f | note | Inspection Point: Quality Control Activity - Check dimensions of formwork match details in the Construction Drawings.
63a3685f-631f-50f2-b45b-5b550dd42985 | note | ○ Check pipe fitting joints are clear of concrete pour.
23788df5-5f26-5f32-a93c-2b6f87bf050f | note | ○ Thrust blocks to be poured against good solid natural ground.
2e389bbc-ca69-56cc-991e-0c7ae5298cfb | note | Acceptance Criteria - Thrust blocks against solid ground
4630ea02-6452-5ef8-9df0-b7baf484a9ae | note | Verifying Document - Daily Site Diary & Photos
2a52135d-b44a-5d64-8c2f-594fcb8d9444 | note | Reference: Contract Specs/Standards - D5.1, D5.3.2, D5.7
270f8374-94d2-5ff4-afe3-a9f4d98bb457 | note | Inspection Point/Signature & Date - PS, CR
02e5fe15-a3d0-4117-9c59-df286de87b71 | checkpoint | 5.5 Hydrant Depth
c166f8ac-68a4-56d5-a714-45a77c232876 | note | Inspection Point: Quality Control Activity - Confirm depth requirements have been met;
2f2ace55-1dbf-557c-880b-7b6a3dd25264 | note | ○ Hydrant outlet: 200mm min. to 400mm max.
285e10aa-95d7-51d9-ab64-3b2072cdb2d5 | note | Acceptance Criteria - Hydrant depth verified
9803aeb2-9d90-54ba-9e49-df36b5629658 | note | Verifying Document - Daily Site Diary
f8c94654-15c9-51e9-8452-342e59ecae6e | note | Reference: Contract Specs/Standards - D5.5
cc256614-c42e-5f6e-a39f-f68a89b87155 | note | Inspection Point/Signature & Date - PS
a0e3fce6-d131-4d47-b2fa-1afd64dedf22 | checkpoint | 5.6 Compaction Testing
ba0f25db-c515-54bf-af10-241ef05a2184 | note | Inspection Point: Quality Control Activity - Confirm trenches in paved areas are compacted to standard block by block.
49e7f8fd-7c6b-5d23-b61b-854926d2d227 | note | Acceptance Criteria - Compaction confirmed
22f4308c-0c3d-5079-b554-738af731d09f | note | Verifying Document - Clegg Record Sheet
ea3ff20d-d289-5332-88c3-7d7ac37a937a | note | Reference: Contract Specs/Standards - D2.7.10
bb591b35-fe0b-530a-8cb7-36e77516390e | note | Inspection Point/Signature & Date - PS
cdecfdb6-ad87-453e-b692-8fb65eb5cbe7 | checkpoint | 5.7 Watermain Pressure Testing
1da5f833-284a-5b18-99a9-331354fad608 | note | Inspection Point: Quality Control Activity - Hydrostatic pressure test on new pipeline and fittings block by block.
2f9a2668-68c2-5f33-8c5e-ec33a157d16e | note | Acceptance Criteria - Pressure test passed
36849462-809a-58b1-a71f-40568e648c95 | note | Verifying Document - Pressure Test Record Sheet
a57df2e3-9168-58b3-8e23-04a24658c806 | note | Reference: Contract Specs/Standards - D2.9.1, AS/NSZ 2566.2:2002 Section 6
2d130f10-37f0-55a1-8d72-a460b1f28c32 | note | Inspection Point/Signature & Date - PS, CR
a1e1175c-838a-44d4-97e2-105d86a88295 | checkpoint | 5.8 Watermain Sterilization
ce10429c-a3e0-5c3c-b478-43bc65ee371b | note | Inspection Point: Quality Control Activity - Flushing and sterilizing full length of new pipeline and fittings block by block.
14828d25-390c-5376-8cc6-48d3ee750694 | note | Acceptance Criteria - Sterilization completed
72845af4-3a77-57b0-bfd3-8c8b00ad194a | note | Verifying Document - Sterilization Record Sheet
c67f69b9-5827-576d-aa4b-e05ef53cf735 | note | Reference: Contract Specs/Standards - D2.9.1, AS/NSZ 2566.2:2002 Section 6
99631707-3d31-5b31-aff4-efb8e8c21979 | note | Inspection Point/Signature & Date - PS, CR
ddf7462a-b76e-41eb-a36d-0de8b8dd2a87 | checkpoint | 5.9 As-built Information
517e67db-4033-58c1-a6ca-d3362f98ca30 | note | Inspection Point: Quality Control Activity - Capture data for all new construction work.
ba450391-5c8a-5c55-b1c4-c22f0833b96c | note | Acceptance Criteria - Redline mark-up plan submitted
3eb797e2-7275-5590-8fac-676aa04c793f | note | Verifying Document - Redline Mark-up Plan
b2cc15a1-1e88-5f06-9c50-d2d2827d97a5 | note | Reference: Contract Specs/Standards - C1.22
3c06f156-3b4e-51b2-91ab-48d5a7624304 | note | Inspection Point/Signature & Date - PM
6fda002d-0146-4403-8542-79c60a61f794 | signoff | HOLD POINT
8b2fb51e-3dea-4864-85cf-ea6c1f2099ae | section | Final Inspection and Handover
e1185f06-97ee-41c3-ba68-9fa87ec8f197 | checkpoint | 6.1 Final Inspection of Works
937e6486-743d-5157-8e7e-d97207a69798 | note | Inspection Point: Quality Control Activity - Work is inspected by the authorised person and complies with the nominated specification/standards
17149ea4-e39d-5a08-9b34-a5a55b8544b8 | note | Acceptance Criteria - Work inspected & complies with standards
69020570-efe6-5843-a2ad-9a102698555a | note | Verifying Document - Practical Completion Certificate
b28f2ad8-0f63-5340-9f55-310a0e29c35a | note | Reference: Contract Specs/Standards -
5422ff6f-c5f8-5de4-8a22-f168bf4f557c | note | Inspection Point/Signature & Date - PM
aca660fb-dc8b-43a6-b666-e84980ea511b | signoff | HOLD POINT

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
eb480729-b100-4b54-b419-4002b74afcce | checklist | ITP - Construction - FoulSewer Stage 1 - Sydney Street, Invercargill | itp | ITP - Construction - FoulSewer Stage 1 - Sydney Street, Invercargill
4ab81cce-f07e-4015-9edb-1fd6a75dc27c | section | Details
bf88fa65-c178-4b81-8508-3bdaed4ce569 | checkpoint | 1 - ITP sign off
2211bc66-f028-5db8-ba1e-e4420e2af382 | note | Inspection / Test Point - Sign off
847327ed-f6ae-5d2c-94bd-328751f689ed | note | ACTION - H
1a6b3ce9-89a4-590a-92b7-9a3ea3cc8a84 | note | Conformance Criteria (Whats Required) - Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed.
b77e1f74-40b5-53f1-83d0-ef300ed64899 | note | Frequency - Prior to commencement
d6542a4a-ee7a-5c83-864b-77adac1a44a8 | note | Inspection / Test Method - Review
3f3a085d-ad90-5465-9e4a-85fc8be653c8 | note | Verification Records - Sign This ITP
6f033b1a-7efd-5214-9109-d5784c3332e1 | note | Signatory - Divisional Manager
b61625b0-fcce-4550-8d0d-6d2729692c90 | signoff | HOLD POINT
b6d6ff3d-993d-4cb9-9910-9b4a3740bf0c | checkpoint | 2 - Materials to comply with contract specification
82f0f818-fdab-5353-b26c-388607937472 | note | Specification / Standard - SR10.103 SR10.105
f5133c16-c2e4-5ef5-abeb-2d1ee5ce46ae | note | Inspection / Test Point - Aggregate Certification
d140ded5-2277-5a35-b2ab-cab578155aaf | note | ACTION - W
61568f63-326c-5793-a885-435272a575e6 | note | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results
ce188f01-4419-5377-95d1-1897aacd0bae | note | Frequency - Prior to commencement
014d72a6-c137-5f14-83e5-2abfca39438e | note | Inspection / Test Method - Lab report
e1ffa5b2-d2f0-5e29-855f-4ffe35432c19 | note | Verification Records - Sign This ITP
aa4d282d-c746-57cd-b0b3-8f2b397af6ed | note | Signatory - Contract Manager
2e9dc207-9d42-4019-97f2-a3b5d96aa899 | checkpoint | 3 - Materials testing to be provided to Engineer for acceptance
d778aab4-702e-527e-a801-622bd8839891 | note | Specification / Standard - SR10.103 SR10.105
811f1bff-2b93-57d4-9385-8700714a005c | note | Inspection / Test Point - Aggregate Acceptance
c9d8f3e7-9367-5c9e-893f-fea5f0bc7f63 | note | ACTION - W
4f8eb5ac-3ac9-517e-ac59-407922fb6894 | note | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results
a26b8c3d-e8f9-5b9c-ae6e-1e6113808c98 | note | Frequency - Prior to commencement
4f760fab-2894-5bd3-aaec-68fc497ab1af | note | Inspection / Test Method - Lab report
78316bab-30b9-544f-bf70-f844f1b1f515 | note | Verification Records - Sign This ITP
dd258804-b52e-5224-b578-321d1d95c951 | note | Signatory - Contract Manager
97d70f61-5dd1-4dc3-b3e6-b1b2e543a0d5 | checkpoint | 4 - Ensure Approved Plans are on site. Safety/ Environmental/ Quality/ Asbestos/ TTMP/ Permits/ Consents/ Site Plans
d75aaaa9-1a58-5ecc-8c7e-191d58fcc871 | note | Inspection / Test Point - Review
37eedaab-939f-540e-afe0-b54fe088c2e9 | note | ACTION - W
dc4f0f48-e25f-50c5-b260-daa1692fec3d | note | Conformance Criteria (Whats Required) - All plans/ permits produced under pre construction avaiable on site al all times
cb2b91b1-43f6-54cd-9be4-7eb1fb2d3a1a | note | Frequency - Prior to commencement
f4bcd6e6-3e17-52bd-8cc8-b7c072fb3ab2 | note | Inspection / Test Method - Review
8cfec6a6-c4d8-513b-9ae7-b1f2945d9d7f | note | Verification Records - Sign This ITP
b1586c14-778f-551f-847c-fb11a6589379 | note | Signatory - Contract Manager
056ff938-4302-43ad-9be3-582074b70180 | checkpoint | 5 - Notice to Engineer Reveiewed by Divisional Manager
6385d127-68ee-5415-86e8-68354d731329 | note | Inspection / Test Point - Review
02d234cf-f899-59f1-8db8-abda27d64eca | note | ACTION - W
4f72c86b-3293-5e08-8f7b-7a602da0350e | note | Conformance Criteria (Whats Required) - All NTE's to be reviewed
07f7123b-616f-5173-bc6d-761bd78ee0ad | note | Frequency - Prior to submission to Engineer
c2248d02-c3fc-573f-aa85-0250e811ed22 | note | Inspection / Test Method - Review
b37a2193-ed90-5292-a80f-a9666cf7c09a | note | Verification Records - Sign This ITP
9cdfe47a-17a1-55d5-88bc-5553b5a6a4a4 | note | Signatory - Contract Manager
85d5b026-588d-4b8a-9f21-1131fc875c90 | checkpoint | 6 - Variations Reveiewed by Divisional Manager
2e9c6b48-857d-5363-859e-7f381e73d56c | note | Inspection / Test Point - Review
8f507ee7-c23a-513a-92fc-debacb153043 | note | ACTION - W
630bf15f-553a-5e8a-b286-a519a2ffcd39 | note | Conformance Criteria (Whats Required) - All Variations to be reviewed
8cc6d7a0-b21c-5cf6-adc9-2015de4319e9 | note | Frequency - Prior to submission to Engineer
e6bda6ab-ab23-5f70-915a-68af8ffadfd2 | note | Inspection / Test Method - Review
6d6c2225-80d5-5a0e-8839-83052bcc0739 | note | Verification Records - Sign This ITP
a671eca3-3a5c-51ff-bcd2-97471d42d50f | note | Signatory - Contract Manager
d2655f7f-cfab-43f4-b708-d9905dbbcb42 | checkpoint | 7 - Site Precondition Inspection
dda3cc14-c315-564c-b350-606f36d42710 | note | Inspection / Test Point - Review
218ebcc8-34d8-53f6-af5e-f1e5dddd5a60 | note | ACTION - W
47d215f5-8077-556a-823b-e4ddea162880 | note | Conformance Criteria (Whats Required) - Video record site walk over
33bd2b1a-71e0-5407-ac4b-6df447bcc4cc | note | Frequency - Prior to work starting on site
ccaca6b1-8bfb-58c7-91d1-8d221857b388 | note | Inspection / Test Method - Video
04d51206-6744-53f2-a61d-c17e8fea0aa0 | note | Verification Records - Sign This ITP
6a86546f-c958-5b79-ba86-4adec2a3d872 | note | Signatory - Contract Manager
ef6c9114-1ca4-4b6c-b820-c772cda557f5 | checkpoint | 8 - Pownet and Chorus loactes completed
021246e2-4b7a-59dc-a859-592cd0cc3078 | note | Inspection / Test Point - Inspection
cdcbcb61-3a76-51a0-8575-4c2863a00e72 | note | ACTION - H
4cfd5dd5-0551-5183-bd57-cfc0c94690c1 | note | Conformance Criteria (Whats Required) - PowerNet and Chorus has been located, refernce back to plans to ensure everthing has been located
5068bf52-9bae-551e-a235-ec1befedfa95 | note | Frequency - Prior to commencement
f1264c94-ad25-5d31-805d-8418fb595819 | note | Inspection / Test Method - Inspection
4186d090-c171-54a6-a0a3-8408fb715e14 | note | Verification Records - Sign This ITP
1b9a612b-20ae-573f-af82-209173571bed | note | Signatory - Supervisor / Forman
fd2eda84-2dd9-45b8-b0f9-58a60e340490 | signoff | HOLD POINT
3a068a53-7ddd-43cc-b813-b4dd6aafcb0a | checkpoint | 9 - Correct materials delivered to site in acceptable condition
d0f22686-63ad-5c1b-8127-ca4e533e074f | note | Inspection / Test Point - Material inspection
54e6740f-946a-58b7-82e4-6660532e926b | note | ACTION - W
7631a244-7742-56d4-a659-5cec7ea12f43 | note | Conformance Criteria (Whats Required) - Complete inspection of materials as they arrive to site (particularly the concrete pipe)
3f451ef0-ab4a-5ed3-9810-a7260636c8f2 | note | Frequency - Upon pipe delvery
92664a6e-eb0f-5b9f-afe8-a5baf76e99e2 | note | Inspection / Test Method - Inspection
3e7b1642-afcd-5ae7-858c-27a02e18fe41 | note | Verification Records - Sign This ITP
43d75eff-018b-5150-95d0-66938793a931 | note | Signatory - Supervisor / Forman
fa4d39aa-ef64-4ddd-8aef-df1e2a923019 | checkpoint | 10 - New FoulSewer Main Alignment
e64f4cec-fcf7-5c20-a609-9e33a6ac626c | note | Specification / Standard - Construciton drawings
ac477e8f-c851-534d-b835-81295199dbba | note | Inspection / Test Point - Inspection / Test Point
a0c746d8-629c-579b-8ae6-8fc9cb96fc62 | note | ACTION - H
fe5d486c-fb2e-5e9f-8228-03800b0aaf69 | note | Conformance Criteria (Whats Required) - Alignment to be setout and confirmed on site by Engineers Rep
9f9b802a-657b-5ad8-9a0c-cff8ba589e5c | note | Frequency - Prior to commencement
ebbe5c79-8495-5250-bc34-df25efdbb66a | note | Inspection / Test Method - Inspection
d5f953a3-3c4a-5a42-80a0-92ff9e9f9c33 | note | Verification Records - Sign This ITP
997d41c7-8805-5230-a96e-6336e9aeafb4 | note | Signatory - Engineers Rep
bf620b1c-31af-4831-83d9-ad70c4007eaf | signoff | HOLD POINT
e2f16350-a047-4381-ac7b-27df077f721d | checkpoint | 11 - Inspect subgrade
37e011d7-858b-527f-8d8c-d6b593393777 | note | Specification / Standard - AS/NZS 2566.2:2002
24e157cc-1844-550c-be20-3cd8f0db5718 | note | Inspection / Test Point - Inspection/Scala
9e02f924-57dd-56b3-9742-d5a5c42e2818 | note | ACTION - M
be801406-8047-5891-93e2-e20f8aa763d8 | note | Conformance Criteria (Whats Required) - Inspect subgrade as exposed and scala if required, contact manager for further instruction if deemed unsuitable
873e8255-c4c8-5977-866c-d3e1e1b40bbc | note | Frequency - During Construction
58ea7587-766a-53bf-a4ec-9c34c2839ddc | note | Inspection / Test Method - Inspection / Scala
cf58dd45-f0af-56d8-8a85-ceae495696e0 | note | Verification Records - Sign This ITP
1bddc031-642d-59d7-b0a6-4552c60c9094 | note | Signatory - Foreman
66d2cb47-42bf-4c9e-a27e-4ff7914defd2 | checkpoint | 12 - Pipe Laying
afdef103-e807-5118-b9f9-3d6083b27334 | note | Specification / Standard - AS/NZS 2566.2:2003 and Contract Doc
91a08fc9-3b11-5c6a-a87a-97ade117dba6 | note | Inspection / Test Point - Pipe Laying
f2306f17-f982-5086-b64b-28fabf70e444 | note | ACTION - M
6a0277d1-879c-5443-8071-9f8502cf0599 | note | Conformance Criteria (Whats Required) - Pipe to be laid as per spec, contract and plans.
4b59b380-0c6f-59d1-8315-ce5cf90c6ea7 | note | Frequency - During Construction
e20e3fc7-0137-5c8c-b1d0-4ad9c6971f0f | note | Inspection / Test Method - Spot checks
0fab28ca-ced4-5ee1-837e-63b352705017 | note | Verification Records - Sign This ITP
77bea28d-0332-5937-9d17-29a1ff43c75f | note | Signatory - Foreman/Supervisor
46f07355-150c-4d08-8b92-17259441dd64 | checkpoint | 13 - Saddles onto main for laterals and sumps
91dde30d-1c30-51d5-82b6-dcd527730b92 | note | Specification / Standard - Construciton drawings
464e1ebe-4dbd-5594-9abf-4932ab01ea44 | note | Inspection / Test Point - Sign off
daea9ad2-0977-529a-a448-d769925f735a | note | ACTION - W
cc55643a-52d9-5624-a986-455fd2ad5ccc | note | Conformance Criteria (Whats Required) - Instal as per construction plans
1da18dd9-e37a-53fa-9a2b-e997d11ab59b | note | Frequency - During Installation
a8bf7e16-89b7-57b0-a5f2-46227c18f0f2 | note | Inspection / Test Method - Photos
0b55e050-7711-5de3-ba25-b95619f8538e | note | Verification Records - Sign This ITP
09c553b0-4f6d-5e79-b659-3bbe3886a0e1 | note | Signatory - Foreman
9576b217-6426-4bb5-8b94-19f6b8f22d8b | checkpoint | 14 - Compaction of bedding
3868df0e-3f50-502f-9138-fc0c2ec943d4 | note | Specification / Standard - Contract Doc
009644bb-ecc5-500e-8a97-6dec89543c4f | note | Inspection / Test Point - Bedding
f005eba2-0ffc-5aac-b5cd-458caf194a6f | note | ACTION - M
93929a69-4403-54ec-8656-ea4a5ae4cbf3 | note | Conformance Criteria (Whats Required) - Compacted layers not exceeding 200mm or ⅓ the pipe OD (whichever is the least).
8ba6d4d3-cbc0-5c03-96b4-c6b80fc52990 | note | Frequency - During Construction
64416808-2e7c-54c4-9d44-883b5aa97995 | note | Inspection / Test Method - Monitor
6d32c829-1dd9-5d27-b63c-b90f0aff4c07 | note | Verification Records - Sign This ITP
2b17504f-3891-5251-810e-1ffe43dca821 | note | Signatory - Foreman
c9adf08f-774e-4ea5-8153-2a9108009388 | checkpoint | 15 - 1050dia. Manhole Installation F24669
8053a39d-0846-5967-9a19-ffa1bdf6f639 | note | Specification / Standard - Contract Doc
c3334408-ec76-577e-a5ff-895d0af195d4 | note | Inspection / Test Point - Inspection
ae229637-9983-5bb2-b079-c6ff026555e1 | note | ACTION - W
51aaf99b-2b24-5ac4-8c49-9f7d89fe97fd | note | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
cf14dab8-4dcb-5406-8236-8bd9f9be4667 | note | Frequency - During Construction
d21d38a0-6764-5238-a042-e88c8f259f31 | note | Inspection / Test Method - Inspection
68d15b01-5c48-5429-8f2c-87d644e5cc9a | note | Verification Records - Sign This ITP
90fffd73-14ce-5697-9de3-d6fe29c36a52 | note | Signatory - Foreman/Supervisor
eb50a639-8339-5e36-9c5f-1d9418992d59 | note | Comments - Complete SR Manhole checklist
8a63b302-59a5-4ae9-9ad6-0b9d661ee648 | checkpoint | 16 - 1050dia. Manhole Installation F21508
ae6123cf-0478-522d-a0bf-383f4cc1b744 | note | Specification / Standard - Contract Doc
321f5ee6-c659-54ba-a12a-df0beb9e8a3d | note | Inspection / Test Point - Inspection
7e8fed35-d5c5-501a-ac88-f01ef1181dbc | note | ACTION - W
5d70ddd3-f85c-5dd0-9c37-b98505b05752 | note | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
e14a44e8-024f-5baa-bb2e-bda84db8a99a | note | Frequency - During Construction
21c3a113-60f5-5080-a35c-e04130cd6d56 | note | Inspection / Test Method - Inspection
b9bda717-c817-5ebc-ba3e-1ec291d77959 | note | Verification Records - Sign This ITP
3511381f-be83-5986-9d3a-c8a547d62d21 | note | Signatory - Foreman/Supervisor
81dedc8a-cbd9-5d5d-a8d3-f7e397d76dd0 | note | Comments - Complete SR Manhole checklist
8387f96a-9e37-44ba-85c4-f38b7f0a869c | checkpoint | 17 - 1050dia. Manhole Installation F21500
ee2f5111-a66d-5775-8ddf-7219c01554fd | note | Specification / Standard - Contract Doc
4b364463-ee7e-5e77-8ca4-dbd2456a0732 | note | Inspection / Test Point - Inspection
bfd5f163-5af6-545b-972e-2094239433ad | note | ACTION - W
a8c259fd-0f7d-58a6-ae4b-f7d2d74277d9 | note | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
d06c0547-4804-5df9-821b-f7493e63eac2 | note | Frequency - During Construction
d9a9018c-92dd-58da-a727-cd3cb2dee960 | note | Inspection / Test Method - Inspection
eda9ddf5-a7cb-5116-a713-a32369d6cd42 | note | Verification Records - Sign This ITP
920d5cfe-05a4-5360-8ede-f545d80ec762 | note | Signatory - Foreman/Supervisor
8a59e4bb-8876-5ae2-9f4f-fb69d1786579 | note | Comments - Complete SR Manhole checklist
78793bf4-902a-452c-97d2-257fded8da74 | checkpoint | 18 - Concrete Placement
898988fa-4e59-5635-a7e7-16cd0d60eb34 | note | Inspection / Test Point - Inspection
fa3351ea-9c0f-5089-a2c7-952e78f13067 | note | ACTION - W
4a1cbea1-6275-5025-b9bb-946985421cba | note | Conformance Criteria (Whats Required) - Engineers Rep to have viewed / inspected concrete formwork
f5f8c572-520b-5163-8975-fbd0541bf7d0 | note | Frequency - During Construction
98b44e66-ea04-598e-bdd2-3552f56dd63d | note | Inspection / Test Method - Inspection
2acbc49d-a0a7-5faf-8bac-2d51a0003446 | note | Verification Records - Sign This ITP
35e267d1-5d8d-502e-be90-d03eb1f70d82 | note | Signatory - Foreman/Supervisor
4e0f595b-69ef-56c5-8ec9-46a4d24b08f8 | note | Comments - Photos & Concrete Dockets
1df451f0-a86d-4b16-adbc-2b00ae840a1d | checkpoint | 19 - Encountered Services
140a2374-1474-5250-86e9-140448da85d8 | note | Specification / Standard - Contract Doc Appendix X
9f98de4b-4665-5342-afd6-1353d9fce763 | note | Inspection / Test Point - Record
d924726b-4095-57d5-8e2a-835754304d3a | note | ACTION - W
f32076fa-4d79-5c00-a22b-818e64bc0135 | note | Conformance Criteria (Whats Required) - Record service on ICC encountered serives record sheet
2a9a1c27-ba5b-5258-905d-4a0c212cff38 | note | Frequency - During Construction
d53b8fe7-c119-5448-824d-431b05e4c453 | note | Inspection / Test Method - Record
0d4a6e97-baf3-5fb8-992f-28df7dc21496 | note | Verification Records - Sign This ITP
72f1b0f6-21f8-5380-85d7-d924dba28746 | note | Signatory - Foreman/Supervisor
d272ed24-3787-4b64-aae0-cc50baa1e94b | checkpoint | 20 - Drainage Connection
298e4d33-c7c0-5520-bd62-43dc1d3026c6 | note | Specification / Standard - Contract Doc Appendix XI
b8d27350-2cb7-5d2c-a17d-b98928d3b0b1 | note | Inspection / Test Point - Record
59207294-b989-5241-bac7-99bec6ee202b | note | ACTION - W
e44fb019-9189-5d4f-ad0f-d744bfaab11c | note | Conformance Criteria (Whats Required) - Record detail on ICC drainage connection sheet
a03f1dbd-897f-5fc4-af15-5fe29bf9125f | note | Frequency - During Construction
98c62072-d0d3-533f-a4aa-a57e3dab191e | note | Inspection / Test Method - Record
ec7501a3-624e-5430-9408-426d1d2e0520 | note | Verification Records - Sign This ITP
4c0b5cb7-f130-523f-a601-706c3624c3b5 | note | Signatory - Foreman/Supervisor
ace8fb9f-074a-5413-b285-a29e1d8b7821 | note | Comments - Complete ICC drainage sheet for each laterial
f04ea3c2-dd20-483c-9877-dec2f2bb5d1e | checkpoint | 21 - Plateau Testing
138f3e5f-4483-5b87-b1d4-3d06041b4630 | note | Inspection / Test Point - Test
3bfe5d3c-6678-591f-9100-1a50c09c96ec | note | ACTION - H
07a93256-42e0-57c1-86ff-78ab41db6d21 | note | Conformance Criteria (Whats Required) - Plateau test to be undertaken at start of backfill to calibrate compaction methodology
0d99e747-c71e-52a4-bd62-be891f3d8c65 | note | Frequency - Test to be carried out at the start of backfilling
46949fb3-7dd8-5a19-bc68-ab33e677c04b | note | Inspection / Test Method - Test
bb98ef34-926d-5d39-83f6-0b0c9795669c | note | Verification Records - Sign This ITP
eac53e85-10aa-5c1e-b5c4-3ba77a41bd30 | note | Signatory - Contract Manager
379c8517-abd8-5b73-a0b9-3189c655756b | note | Comments - NDM Test record
c791ce39-045f-43d7-bd01-0b29b53b9f9a | signoff | HOLD POINT
c0b97b41-fea4-43b3-96dc-554fa1999a01 | checkpoint | 22 - Compaction of AP65 - Clegg tests
b859c384-48e2-504c-b821-a5c8752f25f8 | note | Specification / Standard - Contract Doc Appendix XIII
84d3f32c-5d2d-5385-9f4a-a7377f967b82 | note | Inspection / Test Point - Rocord
3f5420f3-9489-519f-8b8b-783a5a7df7e7 | note | ACTION - W
012703e0-5546-5c6d-8806-63e42589b057 | note | Conformance Criteria (Whats Required) - AP65 shall be in compacted layers not exceeding 200mm depth. Clegg testing to be done at 6m intervals, Record on ICC Clegg testing results sheet
485d9ab3-1716-51b1-82b1-67def664c3df | note | Frequency - During Construction
e25f263f-59e3-5c03-8120-dcda850aa103 | note | Inspection / Test Method - Clegg Test
f8752e2e-0325-5bcc-b7ea-862ca77ca3df | note | Verification Records - Sign This ITP
3514b393-382d-538e-a4f8-54a30174e6d6 | note | Signatory - Foreman/Supervisor
9567712a-46c7-5d02-8611-63efe18d4c3c | note | Comments - Complete ICC Clegg record sheet
4dd9b1dd-4b4b-4534-9f31-82c0dcf1d37a | checkpoint | 23 - Compaction of AP65 - Test results to Engineer
bb03d3a1-7705-5c0f-9381-cd70e4889881 | note | Specification / Standard - Contract Doc
3ed1cf2c-7d1f-584a-aa86-92e2e8b2d418 | note | Inspection / Test Point - Test Point
4f46dd38-6794-5d7e-9ca3-c4ee82160447 | note | ACTION - W
43d9feda-126f-5eb8-9df8-a8f6bb83ddcc | note | Conformance Criteria (Whats Required) - AP65 shall be in compacted layers not exceeding 200mm depth. Ndm testing to 95% at 120m intervals where a Clegg is to be compared, Clegg testing to be done at 6m intervals
565a6b48-903d-5138-a602-9bd11c98c453 | note | Frequency - During Construction
4b49e9bf-8bd5-5a6e-8ae8-cbeb77d0b8e7 | note | Inspection / Test Method - NDM Test
0a4108dc-af23-5467-adac-6dff4b7088e4 | note | Verification Records - Sign This ITP
8698f18f-174f-5e84-bf0e-8c920330b61f | note | Signatory - Contract Manager
591bb261-f632-52e0-911f-a90165c533c0 | note | Comments - NDM Test record
ca2a1907-b969-4e08-8584-836a95bdf16c | checkpoint | 24 - Compaction of AP40 - Test results to Engineer
cdbaf574-1279-5f18-9b25-7d68910f8f3c | note | Specification / Standard - Contract Doc
5b058070-f9c5-54be-9e2d-4b2d2a129014 | note | Inspection / Test Point - Test Point
626a96af-c63e-53a1-bb39-fb12b20eb95d | note | ACTION - W
25fcb904-fea5-5c0a-be04-06b53d028db0 | note | Conformance Criteria (Whats Required) - The basecourse layer shall be a minimum depth of 150mm for all applications. Ndm testing to 98% at 20m intervals
6b1f47c1-6ddf-594a-8d44-5c5f66cbd055 | note | Frequency - During Construction
f2fdc693-a26d-5b50-8bbb-aa95cbdc9480 | note | Inspection / Test Method - NDM Test
fc0cdce8-e9e6-534d-a13c-d7689366b0b0 | note | Verification Records - Sign This ITP
a496c29c-c824-5c04-a7b6-f148f1da1205 | note | Signatory - Contract Manager
6ce86208-aba6-504e-b4b7-c69e0c45e48b | note | Comments - NDM Test record
2708f18d-a647-4e75-8736-7f1f3bca70d3 | checkpoint | 25 - Flush and CCTV line
534ca7dd-38c8-5466-a74c-dd37a38d2105 | note | Inspection / Test Point - Inspection
ccb4b630-7d13-5ae7-92a8-2e732da9092c | note | ACTION - H
46efcf9d-d6ae-5f95-abbc-4087eca8103c | note | Conformance Criteria (Whats Required) - Flush and CCTV line and pass footage back to engineer for review
f61f668c-4965-52d4-b764-8d688d1359e6 | note | Frequency - Prior to asphalt
991d8bb1-d152-57aa-87a2-bf30a92e8281 | note | Inspection / Test Method - Inspection
e5129d7c-6eaf-5e24-af7b-0d8fd5c399aa | note | Verification Records - Sign This ITP
f0a3a79f-68f5-590b-82ac-99f4797a57ea | note | Signatory - Contract Manager
1944f81c-1e35-413f-afb7-8a7a36164a95 | signoff | HOLD POINT
9b7cbbe0-e9c7-459f-9bc8-22832baba89e | checkpoint | 26 - Asphalt prep
33f060e4-ae37-51e7-ab43-2932a4091813 | note | Inspection / Test Point - Sign off
952ff9ea-c19c-5598-8872-f5c07b06af80 | note | ACTION - H
532be00a-95b6-531e-b1fb-54ae0f1d42dd | note | Conformance Criteria (Whats Required) - Engineer to approve area is ready for asphalt (including overcuts). Prep is 50mm and has fall and compaction results have been recived
ba867fcd-c960-534d-af5a-999c587435c4 | note | Frequency - Prior to asphalt
554ced54-1a0e-5ad8-bb5d-8a3ca9f74c4e | note | Inspection / Test Method - Inspection
d1a93a7d-296c-53a6-aa49-65453b2ede8c | note | Verification Records - Sign This ITP
aadffea0-470d-5a33-b3d7-f56dfdd2f2c2 | note | Signatory - Engineer
65265586-7ce7-4cac-9889-2703e7b95f00 | signoff | HOLD POINT
7896fdd4-beaf-433e-9e8e-04a2ed63ffdc | checklist | ITP - Construction - StormWater Stage 1 - Sydney Street, Invercargill | itp | ITP - Construction - StormWater Stage 1 - Sydney Street, Invercargill
e177da21-12c9-4a01-b406-c42a8cc61683 | section | Details
e9f86e3d-1b0e-4527-a228-a6831b3deedd | checkpoint | 1 - ITP sign off
acd95196-9a8c-5155-a92f-1ce60651dead | note | Inspection / Test Point - Sign off
2b7714fe-be76-5d49-9d53-30e9fa87042c | note | ACTION - H
fc3a5fac-87d2-562a-8f31-72ec37a2fddc | note | Conformance Criteria (Whats Required) - Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed.
99f1509e-1baa-5f3b-b6d4-64602cf3e0ee | note | Frequency - Prior to commencement
7e21ffb4-65c0-51e1-87a8-4e0badd88a79 | note | Inspection / Test Method - Review
835d0f1c-6591-5b4c-bc70-7a5d0088838a | note | Verification Records - Sign This ITP
269966de-9ab4-58dd-8ccc-c3f9a73558b1 | note | Signatory - Divisional Manager
4c894459-7326-43ce-b1e9-0f4bf05813e7 | signoff | HOLD POINT
af464a6e-71a8-41e6-b6f6-07a26691a97d | checkpoint | 2 - Materials to comply with contract specification
e66a4bbc-b580-5b7f-9d19-056f12d16a06 | note | Specification / Standard - SR10.103 SR10.105
4ede3326-bbee-5956-ae6a-a686385cbea7 | note | Inspection / Test Point - Aggregate Certification
a2bf3638-d29e-55bb-831a-7072b1071d5c | note | ACTION - W
3d5f5d3f-f51e-5ca0-8d35-04edb47f245b | note | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results
96fd3a66-9122-5df7-9d76-e888d248c624 | note | Frequency - Prior to commencement
b77c0cab-1cdd-54c7-9188-be27e640b5dd | note | Inspection / Test Method - Lab report
12ea48e9-c180-5b02-b0eb-da0ea3f5521d | note | Verification Records - Sign This ITP
bc5a6f1b-e353-5c03-8329-c90e4b7401aa | note | Signatory - Contract Manager
71f06574-4f12-4772-abff-0197ce6000d8 | checkpoint | 3 - Materials testing to be provided to Engineer for acceptance
c20a63d9-e08e-548d-a507-0199c65a6d4d | note | Specification / Standard - SR10.103 SR10.105
02a505b4-3fc5-5d98-a29c-d884b9147881 | note | Inspection / Test Point - Aggregate Acceptance
94ad979e-c24b-5cd7-8690-b1bbd45518db | note | ACTION - W
caae43c5-a10a-5cd8-b79b-db5d0c3a1ff5 | note | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results
7a9f2d34-306a-5e26-b245-42ea7b829f68 | note | Frequency - Prior to commencement
02ab8f07-cc78-55f3-81b4-ab9108120500 | note | Inspection / Test Method - Lab report
97914328-68ab-5c0f-bbcd-283d8b731f2f | note | Verification Records - Sign This ITP
77c38c2f-12dc-5205-8252-26b435b4be74 | note | Signatory - Contract Manager
cb10120b-c369-4c1d-add8-5d26b22a7b2c | checkpoint | 4 - Ensure Approved Plans are on site. Safety/ Environmental/ Quality/ Asbestos/ TTMP/ Permits/ Consents/ Site Plans
eba6472f-6343-5650-b3aa-5248fb0490a8 | note | Inspection / Test Point - Review
c49f08ab-4369-5b18-a957-fab87462bd3a | note | ACTION - W
407813bd-0793-5378-bd66-f91cd7d64c7a | note | Conformance Criteria (Whats Required) - All plans/ permits produced under pre construction avaiable on site al all times
935e5245-91ef-583a-8b59-0f017786d8ac | note | Frequency - Prior to commencement
fbe69ad4-7b6d-583e-9dd9-4f5a0eeb976a | note | Inspection / Test Method - Review
e102a28a-a82a-505c-9f3a-ffcecac8bcfd | note | Verification Records - Sign This ITP
18a28b96-2329-5b1f-a9e5-4328b89599b2 | note | Signatory - Contract Manager
42b3fcd4-d71c-4534-9aed-0b94467a8b41 | checkpoint | 5 - Notice to Engineer Reveiewed by Divisional Manager
03a8a9f2-faeb-531e-bc03-9dc60066d224 | note | Inspection / Test Point - Review
ae0a6746-d47b-55a5-8db6-0a8ea7a3d6cb | note | ACTION - W
b329e299-de43-5c43-89e6-478737ea9cce | note | Conformance Criteria (Whats Required) - All NTE's to be reviewed
300df561-366f-51f7-a59e-253b9714b32f | note | Frequency - Prior to submission to Engineer
e842f411-f7b7-5dff-bc23-9e01873b22a4 | note | Inspection / Test Method - Review
0eb2adaa-e804-5d49-9ea5-578f06a47add | note | Verification Records - Sign This ITP
7a195be4-2366-53b2-b348-091bf7e263be | note | Signatory - Contract Manager
3331cb06-806c-4700-96f7-e936af82b37e | checkpoint | 6 - Variations Reveiewed by Divisional Manager
be0f69d2-b939-5330-9e2f-486c03d3d3ee | note | Inspection / Test Point - Review
0f025f9b-ad60-5124-9a24-5f0915bf7d9b | note | ACTION - W
ecc1cb1a-2dd4-5f5a-83f7-150f865e0abe | note | Conformance Criteria (Whats Required) - All Variations to be reviewed
811d5aa0-a77c-537a-9212-bdb308142981 | note | Frequency - Prior to submission to Engineer
d1af25be-1376-5b07-b736-b2c9a1c77257 | note | Inspection / Test Method - Review
0508f9e3-afb8-500f-8c6c-c76f6231e51e | note | Verification Records - Sign This ITP
4d6259a6-b96b-58b2-a7e7-c7342b82378f | note | Signatory - Contract Manager
dc1f5597-19c9-4cd5-887a-0fd9a8f3c62e | checkpoint | 7 - Site Precondition Inspection
5f6e6ae9-0b28-5a99-8913-e9b7d7693439 | note | Inspection / Test Point - Review
aba03e82-995f-5bdd-a784-f01925fac2e8 | note | ACTION - W
018e5903-de97-5593-a3de-6b69c14a7d59 | note | Conformance Criteria (Whats Required) - Video record site walk over
3f1f88a3-43c7-5076-af06-cd5b47c76860 | note | Frequency - Prior to work starting on site
ad7d6ab0-cf49-5c28-82d0-7121be85424d | note | Inspection / Test Method - Video
a2a935ff-1252-5299-9ecb-033d2a8d4b58 | note | Verification Records - Sign This ITP
ea55641a-a466-50dd-8a8f-51d684fac9e0 | note | Signatory - Contract Manager
b4a59add-fc00-4935-8620-f069022e347e | checkpoint | 8 - Pownet and Chorus loactes completed
79460d8a-dbfd-581a-bc67-05e61fc53f06 | note | Inspection / Test Point - Inspection
05f2ad1d-7cfb-50be-aa89-73089c5a4f10 | note | ACTION - H
fabda33d-190c-524d-848d-27bdbc6e2d14 | note | Conformance Criteria (Whats Required) - PowerNet and Chorus has been located, refernce back to plans to ensure everthing has been located
767aacca-69bb-51b7-846b-f0127830235f | note | Frequency - Prior to commencement
766b5390-0746-5d09-879d-3b1779d8b852 | note | Inspection / Test Method - Inspection
070a93d0-5bc7-53d0-a2fd-5ce07728a492 | note | Verification Records - Sign This ITP
d9019b80-d64b-5115-82c1-549b2b518ee7 | note | Signatory - Supervisor / Forman
c0958809-fe09-4777-8d03-03eef67efe44 | signoff | HOLD POINT
457aa271-0715-4e06-a3d9-b761eeab11c5 | checkpoint | 9 - Correct materials delivered to site in acceptable condition
c7158623-476b-5d27-8e5c-e85e57da8a20 | note | Inspection / Test Point - Material inspection
60058bcd-e5ea-5ef6-a0d0-f436e3e832fd | note | ACTION - W
c4661ad2-1dcd-5693-af68-4644678bee2f | note | Conformance Criteria (Whats Required) - Complete inspection of materials as they arrive to site (particularly the concrete pipe) Engineers Rep to inspect materials
f5f92e4f-7e92-537e-8c03-ad7cde7ef95c | note | Frequency - Upon pipe delvery
02a6d6c1-e2bd-563f-9a13-4d08dc3c5e1a | note | Inspection / Test Method - Inspection
8a9f39c2-8fc8-5798-bc78-f819ee1bd8e5 | note | Verification Records - Sign This ITP
0a7961c1-339f-5864-a92d-b1171abae28b | note | Signatory - Supervisor / Forman
566d77ca-bb29-4ea3-a9ab-058f0ce4a741 | checkpoint | 10 - New StormWater Main Alignment
cf2e9133-cc3e-5e6e-9fb2-8604f528c5ea | note | Specification / Standard - Construciton drawings
693c31ae-f6be-5024-93f2-525ed75a0346 | note | Inspection / Test Point - Inspection / Test Point
f817278b-869b-575c-a275-699b0c5715ce | note | ACTION - H
4e6b6e49-0239-5b79-9ad3-2c8fb8c12919 | note | Conformance Criteria (Whats Required) - Alignment to be setout and confirmed on site by Engineers Rep
8f22b943-cac1-53d8-b326-9bce16b65644 | note | Frequency - Prior to commencement
935ed138-9b75-5782-963a-e279e2f52660 | note | Inspection / Test Method - Inspection
24012754-3fb2-5205-8310-8828a3ead3ec | note | Verification Records - Sign This ITP
ca99eb5e-2e32-59a7-9cc3-691e8336286d | note | Signatory - Engineers Rep
0bc91877-c973-4c85-a460-3435231b9595 | signoff | HOLD POINT
af4a8c4c-3e66-4f43-ab8d-89a45b81d514 | checkpoint | 11 - Inspect subgrade
5ed5e0eb-9916-5671-813d-9ed39b75a747 | note | Specification / Standard - AS/NZS 2566.2:2002
52b54931-44e3-553d-ab0a-01ae9c594964 | note | Inspection / Test Point - Inspection/Scala
0ece26b4-b0f4-5940-8407-9d0e493c8560 | note | ACTION - M
3e5adda3-cdc8-5af2-991d-43016d11d690 | note | Conformance Criteria (Whats Required) - Inspect subgrade as exposed and scala if required, contact manager for further instruction if deemed unsuitable
5ecdeb26-7e4f-5e0c-8acc-6602b5643e0e | note | Frequency - During Construction
f14b1e58-911b-5a28-b5bf-1d9274b9b9df | note | Inspection / Test Method - Inspection / Scala
a8ca8afc-d076-5012-b441-2681787acd2b | note | Verification Records - Sign This ITP
ab4df031-bde5-5580-ba3b-b0bc3cded5db | note | Signatory - Foreman
d601bdaa-12e9-48ac-9608-dc7d3aac155d | checkpoint | 12 - Pipe Laying
ca2ac4a2-323d-5c89-a9af-0cef4bd2d2f4 | note | Specification / Standard - AS/NZS 2566.2:2003 and Contract Doc
667db824-f066-5602-abf8-fb664e7a0e43 | note | Inspection / Test Point - Pipe Laying
85659e0a-36c9-5dd3-9f3b-bc5b2a40d3f4 | note | ACTION - M
b095b6fd-33e7-54e6-a003-9a0c1146211e | note | Conformance Criteria (Whats Required) - Pipe to be laid as per spec, contract and plans.
68ed6910-2948-547d-ba3e-512b3975f5f1 | note | Frequency - During Construction
36098da6-4418-5937-99c9-8262a4c9bcdd | note | Inspection / Test Method - Spot checks
15fbc827-dbf7-500d-8a32-fb24bfe555a9 | note | Verification Records - Sign This ITP
f19e8155-95d6-56ff-bfb6-712b60f8dc69 | note | Signatory - Foreman/Supervisor
fd6d76ba-21a9-46e2-82ae-1f4cd658c533 | checkpoint | 13 - Saddles onto main for laterals and sumps
9b2ca141-2d0a-50af-9dd1-20df49ba0907 | note | Specification / Standard - Construciton drawings
69a3c32b-3646-5dd0-8306-7efa8cc07302 | note | Inspection / Test Point - Sign off
689f2af5-967b-5add-8422-848be9b17076 | note | ACTION - W
f77cc2a8-79c4-5352-83e9-b0d2c3657067 | note | Conformance Criteria (Whats Required) - Instal as per construction plans
b70a98a8-ae98-5ce6-b648-923eedd5e851 | note | Frequency - During Installation
24d75d2d-4480-5531-b78a-5cc68adc124b | note | Inspection / Test Method - Photos
f628e14c-aef0-54cf-a13d-d1200c9c242f | note | Verification Records - Sign This ITP
79a28225-efc8-57e2-b355-40e368218afe | note | Signatory - Foreman
a043b434-ac7b-46b9-b8f3-9cf3f3dd8fd2 | checkpoint | 14 - Compaction of bedding
f266d454-377b-5009-8a92-aeecb628bab8 | note | Specification / Standard - Contract Doc
1479e882-2add-5d55-89ba-11ace77b8356 | note | Inspection / Test Point - Bedding
6fce72e3-aa62-51a6-b2ab-a41fc9487473 | note | ACTION - M
ea049218-9aae-55e1-b3b1-2d254880eeb2 | note | Conformance Criteria (Whats Required) - Compacted layers not exceeding 200mm or ⅓ the pipe OD (whichever is the least).
01c33214-2fab-5f3a-9eed-986ca505980c | note | Frequency - During Construction
7ee549e3-b2eb-53f5-b9f6-68d2b6c56e7f | note | Inspection / Test Method - Monitor
3c6bb226-d07c-5516-963e-78f58f8ab8d9 | note | Verification Records - Sign This ITP
44732343-411d-5fb1-ae40-253544d31d85 | note | Signatory - Foreman
85cc8430-4e5a-4842-9e7f-a5202cb4b79d | checkpoint | 15 - 2550dia. Manhole Installation 1A-01 (if required)
eaa5e9e4-de95-5087-b669-1fa0f4f0f8ab | note | Specification / Standard - Contract Doc
a1acfe03-055f-5e42-83c9-3411a441fee6 | note | Inspection / Test Point - Inspection
eac3778e-58bd-53eb-98d8-918a4a4139d9 | note | ACTION - W
93f01aa7-0492-506f-8446-912fffcb8bfb | note | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
684d0abe-fffc-5317-b138-bc1119d8f2f4 | note | Frequency - During Construction
06b7bd0e-b42e-59ef-b3b1-3561870dfd57 | note | Inspection / Test Method - Inspection
6329b7c1-34f4-5a99-a362-4c301ef9ce2d | note | Verification Records - Sign This ITP
79854f31-6672-56fd-b85f-2e3f2d06e96b | note | Signatory - Foreman/Supervisor
fea6d33d-b6d0-5cf0-bfca-b3c27d41d06d | note | Comments - Complete SR Manhole checklist
c4da6f1e-9e8a-446f-b45e-85d5d363a83b | checkpoint | 16 - 1500dia. Manhole Installation 1A-02
58e318ca-186c-52cc-8c91-a8c1a37581db | note | Specification / Standard - Contract Doc
4594e303-d685-5352-930d-6848b2ded05d | note | Inspection / Test Point - Inspection
0a40d577-9b32-5571-91d5-74089157ebcc | note | ACTION - W
325947b7-4924-5da7-9fbb-5eebd8c60469 | note | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
c592025a-2bdf-55a4-9b3f-9317048b6b9f | note | Frequency - During Construction
eab9348b-e047-5fcf-ad6a-e6d479ba1d9d | note | Inspection / Test Method - Inspection
e282da4a-312f-5586-bd16-b1e4de252385 | note | Verification Records - Sign This ITP
78a02d08-4de9-5902-9a8b-cb1380267265 | note | Signatory - Foreman/Supervisor
2c350cbf-ab24-59c9-9655-43940eec9202 | note | Comments - Complete SR Manhole checklist
312c0ba8-a9d2-4136-b341-4b027ed7e34c | checkpoint | 17 - 1050dia. Manhole Installation 1A-03
89a10585-c9e3-547b-8253-33d8b7a0717b | note | Specification / Standard - Contract Doc
0384c35e-93b8-595b-ad94-5891edeb7a10 | note | Inspection / Test Point - Inspection
489cd3b7-3443-53c5-b414-4218cd19592f | note | ACTION - W
60cf4541-9cef-5f2d-835d-e4ab60b52f67 | note | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
76228c2a-ef65-5520-88aa-0e985ce3a580 | note | Frequency - During Construction
887f5c6d-10d8-5996-a599-eb09fe0968a7 | note | Inspection / Test Method - Inspection
6d333daf-096a-5e2f-845a-9cec77310d05 | note | Verification Records - Sign This ITP
55600b2d-98ed-53dd-8865-ffed9cf1def5 | note | Signatory - Foreman/Supervisor
889f9e52-1b3e-5a97-a967-183bd7e51ba3 | note | Comments - Complete SR Manhole checklist
0194dd9f-92ae-407d-a535-d96223dfe88b | checkpoint | 18 - 1050dia. Manhole Installation 1A-04
af1401a9-2e18-53cd-b88e-7c2087bab92f | note | Specification / Standard - Contract Doc
050ea409-0f2a-5415-a480-a859556a6ccd | note | Inspection / Test Point - Inspection
0126eb8b-f7b9-55fb-a312-6cec0256f0e8 | note | ACTION - W
db222fc7-95a2-536e-ac4c-51328eedc64f | note | Conformance Criteria (Whats Required) - Complete Manhole Install Checklist
8ac12a10-b4c2-5adc-a87c-15e13b3f5198 | note | Frequency - During Construction
99eea185-233c-579a-8fab-ba2bed0bc018 | note | Inspection / Test Method - Inspection
cdfa5163-5221-5128-b033-06707999f643 | note | Verification Records - Sign This ITP
56fc2e15-1040-5786-8696-aa7ca4e9016d | note | Signatory - Foreman/Supervisor
61ce24ab-58b5-50d7-8518-186b2330878c | note | Comments - Complete SR Manhole checklist
8768ca51-a157-4624-ae9b-fc9343f1b08d | checkpoint | 19 - Road Sump Installation
2cbaae61-fedf-5f79-8404-77d0b98cc660 | note | Specification / Standard - Contract Doc
735bfe52-f95f-554a-aff0-c4bdf3171582 | note | Inspection / Test Point - Inspection
d3f86a8b-5525-5ac3-b2a2-4cd08b6a33da | note | ACTION - W
b69ef956-6f04-5608-b358-8215db2936c1 | note | Conformance Criteria (Whats Required) - Complete Sump Install Checklist
0c00a069-6fa3-54f5-acac-69e6534254f6 | note | Frequency - During Construction
31131f11-c1a6-534f-9527-712daefc59b0 | note | Inspection / Test Method - Inspection
971c8c02-918b-5a9d-b0e6-9d4cc11f9829 | note | Verification Records - Sign This ITP
f2af4a25-fd7c-5a00-a770-90850db7d0f7 | note | Signatory - Foreman/Supervisor
365bdc09-a9d5-5e93-badd-cd98e01119f8 | note | Comments - Complete SR Sump checklist for each sump
7e285dbc-5f00-4e4f-a3c7-d01400c1896e | checkpoint | 20 - Concrete Placement
d75884af-0f3b-5fc5-a281-93d5a9a215a5 | note | Inspection / Test Point - Inspection
9e1c3bce-5064-5a6d-b38b-a0065d56a591 | note | ACTION - W
6b6b9298-331b-5ddd-af43-e3975c454c3a | note | Conformance Criteria (Whats Required) - Engineers Rep to have viewed / inspected concrete formwork
6acd07ca-95f8-5bd6-ae12-78dae0030d62 | note | Frequency - During Construction
85a5425f-1d70-5750-955e-b541b7906995 | note | Inspection / Test Method - Inspection
8903f0f7-f4ae-5c7b-9857-523fa00dbf71 | note | Verification Records - Sign This ITP
84dbd382-0a48-55e8-81e1-710c94c10af9 | note | Signatory - Foreman/Supervisor
ddfc92dd-4c7c-505b-be69-1e254c3d4702 | note | Comments - Photos & Concrete Dockets
f946494e-8450-417d-9283-aa31b4fcd0a0 | checkpoint | 21 - Encountered Services
b82e4c57-4c25-5da2-bb34-b21009cdaedf | note | Specification / Standard - Contract Doc Appendix X
a239d827-4a80-546e-a848-d336c99357eb | note | Inspection / Test Point - Record
41191a7c-e054-58c2-86c3-a026eaccac9c | note | ACTION - W
6d42f241-222f-563e-8224-cc9744b9a308 | note | Conformance Criteria (Whats Required) - Record service on ICC encountered serives record sheet
fc89667c-c138-51ac-ab96-f85645882c65 | note | Frequency - During Construction
c20d62e2-9ef1-51cd-a7f3-8dc7682cfcd5 | note | Inspection / Test Method - Record
749dc235-2109-5234-9d0d-7a9fc9c2c7d6 | note | Verification Records - Sign This ITP
f80e8011-36e5-5411-9fa3-a5f440c848a6 | note | Signatory - Foreman/Supervisor
40c07e15-a20f-4e71-abfd-21463f0440f5 | checkpoint | 22 - Drainage Connection
990f116f-55d3-5f5a-b5b8-db5b32049070 | note | Specification / Standard - Contract Doc Appendix XI
f7207c86-26cb-5728-92da-59d0c6e5539c | note | Inspection / Test Point - Record
a6093e58-0c07-59cb-a276-d1ffaf35bf09 | note | ACTION - W
5af1d34d-fcf6-5f5a-a111-152e15f37b01 | note | Conformance Criteria (Whats Required) - Record detail on ICC drainage connection sheet
2cf8e49f-3ea1-5a21-9ae7-4a9085e1b287 | note | Frequency - During Construction
6ca6fa2b-b1cc-5ad9-8ad9-f0dc5f4af9d2 | note | Inspection / Test Method - Record
2be82e7f-edbc-5d2d-830a-9eb570cf2ec4 | note | Verification Records - Sign This ITP
88deebfd-4309-5fba-a3cc-2112291830a8 | note | Signatory - Foreman/Supervisor
84255dd1-43e8-529b-a2fc-680cf7195e4d | note | Comments - Complete ICC drainage sheet for each laterial
cd543bd7-a290-42b9-bda5-ff7888247d05 | checkpoint | 23 - Plateau Testing
c265781b-8e9f-5bf1-9ae6-df6bca037132 | note | Inspection / Test Point - Test
ab07a867-a112-5152-8487-2110f44b0a71 | note | ACTION - H
c29ae398-736b-5c5e-b6f1-67cf2df6420e | note | Conformance Criteria (Whats Required) - Plateau test to be undertaken at start of backfill to calibrate compaction methodology
36d39263-f5e7-56f6-b9cc-4d565166ab05 | note | Frequency - Test to be carried out at the start of backfilling
0cab342b-0f95-5853-805d-df8025d163d4 | note | Inspection / Test Method - Test
d2ec0b4b-7aa3-5274-afc3-d2d6d52819fa | note | Verification Records - Sign This ITP
01c58494-2fce-5f0e-a278-690a81141798 | note | Signatory - Contract Manager
f7351c8b-2f8c-53d0-9879-8ad9fae15bca | note | Comments - NDM test record
83018626-e917-4e55-be12-d45d53a18814 | signoff | HOLD POINT
54d72957-4e56-459b-a2bd-6ba80fa1d09c | checkpoint | 24 - Compaction of AP65 - Clegg tests
d1b91e16-bc16-5c13-9dbd-626f923cc8b2 | note | Specification / Standard - Contract Doc Appendix XIII
cb01e93d-f323-5079-8d7f-b06fb30ca970 | note | Inspection / Test Point - Rocord
5ce509a9-dc61-5eb4-a7f3-a2a671bc415e | note | ACTION - W
892a08ca-f286-583d-8e17-621469f5dfab | note | Conformance Criteria (Whats Required) - AP65 shall be in compacted layers not exceeding 200mm depth. Clegg testing to be done at 6m intervals, Record on ICC Clegg testing results sheet
67dff334-6445-5c7a-bae3-b5642be7f221 | note | Frequency - During Construction
0f4bdb3c-8933-5053-9a99-969aabf840e1 | note | Inspection / Test Method - Clegg Test
9c3412fc-c45e-5478-8df4-87d7a064b648 | note | Verification Records - Sign This ITP
4f9bd2dc-7ea4-5fa4-bb7c-188093239ca1 | note | Signatory - Foreman/Supervisor
0aa75e7c-1d05-5d17-9f38-ed0874379201 | note | Comments - Complete ICC Clegg record sheet
db678ead-8352-4feb-aadd-976a3f254cd2 | checkpoint | 25 - Compaction of AP65 - Test results to Engineer
f3e45e29-4fc4-50be-912b-1904520c3fc0 | note | Specification / Standard - Contract Doc
46a155ad-c32f-5a96-a1b5-5d8d17ecf811 | note | Inspection / Test Point - Test Point
6295c4e3-8d65-5cc3-88da-e6e079726a68 | note | ACTION - W
3828039d-74bd-5b5a-b906-ca1a325c2013 | note | Conformance Criteria (Whats Required) - AP65 shall be in compacted layers not exceeding 200mm depth. Ndm testing to 95% at 120m intervals where a Clegg is to be compared, Clegg testing to be done at 6m intervals
dd047f47-8cd4-5a8c-9e77-65349d64664c | note | Frequency - During Construction
4320e0ae-0d3f-5b09-99a4-a4e1910cc6fe | note | Inspection / Test Method - NDM Test
4d28a01f-abc7-52ba-bb9e-140962462ee2 | note | Verification Records - Sign This ITP
3126a524-da35-5fb0-ab70-b44a14b2dc37 | note | Signatory - Contract Manager
64451430-024f-53fd-a5be-8538a6abb7f0 | note | Comments - NDM test record
0e7c1e9d-c2e6-4ac0-85c5-5041e39d03c4 | checkpoint | 26 - Compaction of AP40 - Test results to Engineer
74fec4bc-3bb0-5f80-a034-f3ce1597b772 | note | Specification / Standard - Contract Doc
bba74b4d-8aa9-5c94-b828-cbc639cc38f9 | note | Inspection / Test Point - Test Point
e8cbb56f-06e4-5faa-bb40-d4882ab1a8d0 | note | ACTION - W
3ac22a6b-ce80-5895-97b0-03e1d61b2a5a | note | Conformance Criteria (Whats Required) - The basecourse layer shall be a minimum depth of 150mm for all applications. Ndm testing to 98% at 20m intervals
969de3a0-4c6d-52da-9389-cf8440167440 | note | Frequency - During Construction
5a9aa27e-edb3-5565-b786-265e70da6bdf | note | Inspection / Test Method - NDM Test
cb69c699-a89d-5c38-b424-0768134037e1 | note | Verification Records - Sign This ITP
a5b0b75a-7d87-5d8c-b03d-44a2e9113318 | note | Signatory - Contract Manager
0536f23b-0aa7-5e81-bcde-b19be7976709 | note | Comments - NDM test record
5f7abcec-51bd-4093-8fa5-a2e8daa27278 | checkpoint | 27 - Flush and CCTV line
d35fe13d-692c-53de-a0e8-15694fb62f52 | note | Inspection / Test Point - Inspection
d267de5b-9975-58c5-bdb7-8c2e91193939 | note | ACTION - H
dab65692-4e08-5c7c-acd4-1995ba9835a0 | note | Conformance Criteria (Whats Required) - Flush and CCTV line and pass footage back to engineer for review
fbea89df-046b-565a-8015-0c2b8c4b25e2 | note | Frequency - Prior to asphalt
d89868ec-0b7d-511b-ac24-02e72696be7f | note | Inspection / Test Method - Inspection
31a4eaac-08c3-5452-94de-c790e4961bd9 | note | Verification Records - Sign This ITP
5e25126a-0746-5041-8715-1c3ae35f6e90 | note | Signatory - Contract Manager
f65a33f3-236f-4b09-a9b6-74ea7523de01 | signoff | HOLD POINT
59e2c964-d536-43eb-9bb2-1140e3188e20 | checkpoint | 28 - Asphalt prep
46dc17b8-b9fc-5131-88e7-99f123308b16 | note | Inspection / Test Point - Sign off
da6ac8c2-4921-5e3b-bd8e-04cfa556a2eb | note | ACTION - H
af580eed-37f6-5ebd-9ce5-42a3faa2d497 | note | Conformance Criteria (Whats Required) - Engineer to approve area is ready for asphalt (including overcuts) . Prep is 50mm and has fall and compaction results have been recived
1a0e7b48-4a60-56f3-a0ee-1ac51933cc77 | note | Frequency - Prior to asphalt
79b37ccb-207e-5ec9-b376-48b165b907f5 | note | Inspection / Test Method - Inspection
b59e800c-bf4d-5263-b6e7-447836020edb | note | Verification Records - Sign This ITP
ed7751bf-eb5b-5a1e-aef0-7c736b9b0d6e | note | Signatory - Engineer
ed65b9a7-b9de-4c4b-aef9-01d653a4aca0 | signoff | HOLD POINT