## SWB1
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Scott Forbes |  | Action | Sydney Street Drainage Renewal
Manager |  | Alex Mattingly |  |  | W | Witness | StormWater Stage 2 - Sydney Street, Invercargill
Divisional/Regional/General Manager |  | Ed Palmer |  |  | H | Hold Point
Engineer |  | Rob Hayes |  |  | M | Monitor | Job Number: |  | 4530 | Version: | OO1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | ITP sign off | — | Sign off | H | Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed. | Prior to commencement | Review | Sign This ITP | Divisional Manager | —
2 | Ensure Approved Plans are on site. Safety/ Environmental/ Quality/ Asbestos/ TTMP/ Permits/ Consents/ Site Plans | — | Review | W | All plans/ permits produced under pre construction avaiable on site al all times | Prior to commencement | Review | Sign This ITP | Contract Manager | —
3 | Site Precondition Inspection | — | Review | W | Video record site walk over | Prior to work starting on site | Video | Sign This ITP | Contract Manager | —
4 | Pownet and Chorus loactes completed | — | Inspection | H | PowerNet and Chorus has been located, refernce back to plans to ensure everthing has been located | Prior to commencement | Inspection | Sign This ITP | Supervisor / Forman | —
5 | Correct materials delivered to site in acceptable condition | — | Material inspection | W | Complete inspection of materials as they arrive to site (particularly the concrete pipe) Engineers Rep to inspect materials | Upon pipe delvery | Inspection | Sign This ITP | Supervisor / Forman | —
6 | New StormWater Main Alignment | Construciton drawings | Inspection / Test Point | H | Alignment to be setout and confirmed on site by Engineers Rep | Prior to commencement | Inspection | Sign This ITP | Engineers Rep | —
7 | Inspect subgrade | AS/NZS 2566.2:2002 | Inspection/Scala | M | Inspect subgrade as exposed and scala if required, contact manager for further instruction if deemed unsuitable | During Construction | Inspection / Scala | Sign This ITP | Foreman | —
8 | SWMH2A-01 | — | Inpection | H | Complete Manhole Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | —
9 | Pipe Laying SWP2A-01 | — | Inspection | W | Engineers Rep to have viewed / inspected concrete formwork | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Photos & Concrete Dockets
10 | Pipe Laying SWP2A-01 | AS/NZS 2566.2:2003 and Contract Doc | Pipe Laying | M | Pipe to be laid as per spec, contract and plans. | During Construction | Spot checks | Sign This ITP | Foreman/Supervisor | —
11 | Complete pipe level Checklist | — | Record | M | Complete checklist at the beginning of every day | Daily | — | Sign This ITP | Foreman/Supervisor | —
12 | Saddles onto main for laterals and sumps | Construciton drawings | Sign off | W | Instal as per construction plans | During Installation | Photos | Sign This ITP | Foreman | —
13 | Compaction of bedding | Contract Doc | Bedding | M | Compacted layers not exceeding 200mm or ⅓ the pipe OD (whichever is the least). | During Construction | Monitor | Sign This ITP | Foreman | —
14 | Unkown Service | — | Record | M | Complete unkown Service Checklist | During Construction | Checklist | Sign This ITP | Foreman/Supervisor | Complete any time an unkonw service is encourtered
15 | Road Sump Installation (provinisal) | Contract Doc | Inspection | W | Complete Sump Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Sump checklist for each sump
16 | Compaction of AP65 - Clegg tests | Contract Doc Appendix XIII | Rocord | W | AP65 shall be in compacted layers not exceeding 200mm depth. Clegg testing to be done at 6m intervals, Record on ICC Clegg testing results sheet | During Construction | Clegg Test | Sign This ITP | Foreman/Supervisor | Complete ICC Clegg record sheet
17 | Compaction of AP65 - Test results to Engineer | Contract Doc | Test Point | W | AP65 shall be in compacted layers not exceeding 200mm depth. Ndm testing to 95% at 120m intervals where a Clegg is to be compared, Clegg testing to be done at 6m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM test record
18 | Compaction of AP40 - Test results to Engineer | Contract Doc | Test Point | W | The basecourse layer shall be a minimum depth of 150mm for all applications. Ndm testing to 98% at 20m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM test record
19 | Flush and CCTV line | — | Inspection | H | Flush and CCTV line and pass footage back to engineer for review | Prior to asphalt | Inspection | Sign This ITP | Contract Manager | —
20 | Pre Seal Inspection | — | Sign off | H | Engineer to approve area is ready for asphalt (including overcuts) . Prep is 50mm and has fall and compaction results have been recived | Prior to asphalt | Inspection | Sign This ITP | Engineer | —
21 | SWMH2A-02 | Contract Doc | Inspection | W | Complete Manhole Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Manhole checklist
22 | Concrete Placement | — | Inspection | W | Engineers Rep to have viewed / inspected concrete formwork | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Photos & Concrete Dockets
23 | Pipe Laying SWP2A-02 | AS/NZS 2566.2:2003 and Contract Doc | Pipe Laying | M | Pipe to be laid as per spec, contract and plans. | During Construction | Spot checks | Sign This ITP | Foreman/Supervisor | —
24 | Complete pipe level Checklist | — | Record | M | Complete checklist at the beginning of every day | Daily | — | Sign This ITP | Foreman/Supervisor | —
24 | Saddles onto main for laterals and sumps | Construciton drawings | Sign off | W | Instal as per construction plans | During Installation | Photos | Sign This ITP | Foreman | —
25 | Compaction of bedding | Contract Doc | Bedding | M | Compacted layers not exceeding 200mm or ⅓ the pipe OD (whichever is the least). | During Construction | Monitor | Sign This ITP | Foreman | —
26 | Road Sump Installation | Contract Doc | Inspection | W | Complete Sump Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Sump checklist for each sump
27 | Encountered Services | Contract Doc Appendix X | Record | W | Record service on ICC encountered serives record sheet | During Construction | Record | Sign This ITP | Foreman/Supervisor | —
28 | Drainage Connection | Contract Doc Appendix XI | Record | W | Record detail on ICC drainage connection sheet | During Construction | Record | Sign This ITP | Foreman/Supervisor | Complete ICC drainage sheet for each laterial
29 | Compaction of AP65 - Clegg tests | Contract Doc Appendix XIII | Rocord | W | AP65 shall be in compacted layers not exceeding 200mm depth. Clegg testing to be done at 6m intervals, Record on ICC Clegg testing results sheet | During Construction | Clegg Test | Sign This ITP | Foreman/Supervisor | Complete ICC Clegg record sheet
30 | Compaction of AP65 - Test results to Engineer | Contract Doc | Test Point | W | AP65 shall be in compacted layers not exceeding 200mm depth. Ndm testing to 95% at 120m intervals where a Clegg is to be compared, Clegg testing to be done at 6m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM test record
31 | Compaction of AP40 - Test results to Engineer | Contract Doc | Test Point | W | The basecourse layer shall be a minimum depth of 150mm for all applications. Ndm testing to 98% at 20m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM test record
32 | Flush and CCTV line | — | Inspection | H | Flush and CCTV line and pass footage back to engineer for review | Prior to asphalt | Inspection | Sign This ITP | Contract Manager | —
33 | Pre Seal Inspection | — | Sign off | H | Engineer to approve area is ready for asphalt (including overcuts) . Prep is 40mm and has fall and compaction results have been recived | Prior to asphalt | Inspection | Sign This ITP | Engineer | —

## FWB1 (hidden)
INSPECTION TEST PLAN
CONSTRUCTION
Foreman |  | Scott Forbes |  | Action | Sydney Street Drainage Renewal
Manager |  | Alex Mattingly |  |  | W | Witness | FoulSewer Stage 2 - Sydney Street, Invercargill
Divisional/Regional/General Manager |  | Ed Palmer |  |  | H | Hold Point
Engineer |  | Rob Hayes |  |  | M | Monitor | Job Number: |  | 4530 | Version: | OO1
No: | Detail | Specification / Standard | Inspection / Test Point | ACTION | Conformance Criteria (Whats Required) | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments | Date | Signature
1 | ITP sign off |  | Sign off | H | Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed. | Prior to commencement | Review | Sign This ITP | Divisional Manager
2 | Ensure Approved Plans are on site. Safety/ Environmental/ Quality/ Asbestos/ TTMP/ Permits/ Consents/ Site Plans |  | Review | W | All plans/ permits produced under pre construction avaiable on site al all times | Prior to commencement | Review | Sign This ITP | Contract Manager
3 | Site Precondition Inspection |  | Review | W | Video record site walk over | Prior to work starting on site | Video | Sign This ITP | Contract Manager
4 | Pownet and Chorus loactes completed |  | Inspection | H | PowerNet and Chorus has been located, refernce back to plans to ensure everthing has been located | Prior to commencement | Inspection | Sign This ITP | Supervisor / Forman
5 | Correct materials delivered to site in acceptable condition |  | Material inspection | W | Complete inspection of materials as they arrive to site (particularly the concrete pipe) Engineers Rep to inspect materials | Upon pipe delvery | Inspection | Sign This ITP | Supervisor / Forman
6 | Inspect subgrade | AS/NZS 2566.2:2002 | Inspection/Scala | M | Inspect subgrade as exposed and scala if required, contact manager for further instruction if deemed unsuitable | During Construction | Inspection / Scala | Sign This ITP | Foreman
7 | Pipe Laying F13890 | AS/NZS 2566.2:2003 and Contract Doc | Pipe Laying | M | Pipe to be laid as per spec, contract and plans.Check grades daily | During Construction | Spot checks | Sign This ITP | Foreman/Supervisor
8 | Junctions onto main for laterals and sumps | Construciton drawings | Sign off | W | Instal as per construction plans | During Installation | Photos | Sign This ITP | Foreman
9 | Compaction of bedding | Contract Doc | Bedding | M | Compacted layers not exceeding 200mm or ⅓ the pipe OD (whichever is the least). | During Construction | Monitor | Sign This ITP | Foreman
10 | Unkown Service |  | Record | M | Complete unkown Service Checklist | During Construction | Checklist | Sign This ITP | Foreman/Supervisor | Complete any time an unkonw service is encourtered
11 | Road Sump Installation | Contract Doc | Inspection | W | Complete Sump Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Sump checklist for each sump
12 | Compaction of AP65 - Clegg tests | Contract Doc Appendix XIII | Rocord | W | AP65 shall be in compacted layers not exceeding 200mm depth. Clegg testing to be done at 6m intervals, Record on ICC Clegg testing results sheet | During Construction | Clegg Test | Sign This ITP | Foreman/Supervisor | Complete ICC Clegg record sheet
13 | Compaction of AP65 - Test results to Engineer | Contract Doc | Test Point | W | AP65 shall be in compacted layers not exceeding 200mm depth. Ndm testing to 95% at 120m intervals where a Clegg is to be compared, Clegg testing to be done at 6m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM test record
14 | Compaction of AP40 - Test results to Engineer | Contract Doc | Test Point | W | The basecourse layer shall be a minimum depth of 150mm for all applications. Ndm testing to 98% at 20m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM test record
15 | Pre Seal Inspection |  | Sign off | H | Engineer to approve area is ready for asphalt (including overcuts) . Prep is 50mm and has fall and compaction results have been recived | Prior to asphalt | Inspection | Sign This ITP | Engineer
16 | F20889 | Contract Doc | Inspection | W | Complete Manhole Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Manhole checklist
17 | Concrete Placement |  | Inspection | W | Engineers Rep to have viewed / inspected concrete formwork | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Photos & Concrete Dockets
18 | Pipe Laying F11051 | AS/NZS 2566.2:2003 and Contract Doc | Pipe Laying | M | Pipe to be laid as per spec, contract and plans.Check grades daily | During Construction | Spot checks | Sign This ITP | Foreman/Supervisor
19 | Saddles onto main for laterals and sumps | Construciton drawings | Sign off | W | Instal as per construction plans | During Installation | Photos | Sign This ITP | Foreman
20 | Compaction of bedding | Contract Doc | Bedding | M | Compacted layers not exceeding 200mm or ⅓ the pipe OD (whichever is the least). | During Construction | Monitor | Sign This ITP | Foreman
21 | Road Sump Installation | Contract Doc | Inspection | W | Complete Sump Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Sump checklist for each sump
22 | Encountered Services | Contract Doc Appendix X | Record | W | Record service on ICC encountered serives record sheet | During Construction | Record | Sign This ITP | Foreman/Supervisor
23 | Unkown Service |  | Record | M | Complete unkown Service Checklist | During Construction | Checklist | Sign This ITP | Foreman/Supervisor | Complete any time an unkonw service is encourtered
24 | Drainage Connection | Contract Doc Appendix XI | Record | W | Record detail on ICC drainage connection sheet | During Construction | Record | Sign This ITP | Foreman/Supervisor | Complete ICC drainage sheet for each laterial
25 | Compaction of AP65 - Clegg tests | Contract Doc Appendix XIII | Rocord | W | AP65 shall be in compacted layers not exceeding 200mm depth. Clegg testing to be done at 6m intervals, Record on ICC Clegg testing results sheet | During Construction | Clegg Test | Sign This ITP | Foreman/Supervisor | Complete ICC Clegg record sheet
26 | Compaction of AP65 - Test results to Engineer | Contract Doc | Test Point | W | AP65 shall be in compacted layers not exceeding 200mm depth. Ndm testing to 95% at 120m intervals where a Clegg is to be compared, Clegg testing to be done at 6m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM test record
27 | Compaction of AP40 - Test results to Engineer | Contract Doc | Test Point | W | The basecourse layer shall be a minimum depth of 150mm for all applications. Ndm testing to 98% at 20m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM test record
28 | F20881 | Contract Doc | Inspection | W | Complete Manhole Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Manhole checklist
29 | Concrete Placement |  | Inspection | W | Engineers Rep to have viewed / inspected concrete formwork | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Photos & Concrete Dockets
30 | Pipe Laying F11031 | AS/NZS 2566.2:2003 and Contract Doc | Pipe Laying | M | Pipe to be laid as per spec, contract and plans.Check grades daily | During Construction | Spot checks | Sign This ITP | Foreman/Supervisor
31 | Saddles onto main for laterals and sumps | Construciton drawings | Sign off | W | Instal as per construction plans | During Installation | Photos | Sign This ITP | Foreman
32 | Compaction of bedding | Contract Doc | Bedding | M | Compacted layers not exceeding 200mm or ⅓ the pipe OD (whichever is the least). | During Construction | Monitor | Sign This ITP | Foreman
33 | Road Sump Installation | Contract Doc | Inspection | W | Complete Sump Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Sump checklist for each sump
34 | Unkown Service |  | Record | M | Complete unkown Service Checklist | During Construction | Checklist | Sign This ITP | Foreman/Supervisor | Complete any time an unkonw service is encourtered
35 | Encountered Services | Contract Doc Appendix X | Record | W | Record service on ICC encountered serives record sheet | During Construction | Record | Sign This ITP | Foreman/Supervisor
36 | Drainage Connection | Contract Doc Appendix XI | Record | W | Record detail on ICC drainage connection sheet | During Construction | Record | Sign This ITP | Foreman/Supervisor | Complete ICC drainage sheet for each laterial
37 | F20872 | Contract Doc | Inspection | W | Complete Manhole Install Checklist | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Complete SR Manhole checklist
38 | Concrete Placement |  | Inspection | W | Engineers Rep to have viewed / inspected concrete formwork | During Construction | Inspection | Sign This ITP | Foreman/Supervisor | Photos & Concrete Dockets
37 | Compaction of AP65 - Clegg tests | Contract Doc Appendix XIII | Rocord | W | AP65 shall be in compacted layers not exceeding 200mm depth. Clegg testing to be done at 6m intervals, Record on ICC Clegg testing results sheet | During Construction | Clegg Test | Sign This ITP | Foreman/Supervisor | Complete ICC Clegg record sheet
38 | Compaction of AP65 - Test results to Engineer | Contract Doc | Test Point | W | AP65 shall be in compacted layers not exceeding 200mm depth. Ndm testing to 95% at 120m intervals where a Clegg is to be compared, Clegg testing to be done at 6m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM test record
39 | Compaction of AP40 - Test results to Engineer | Contract Doc | Test Point | W | The basecourse layer shall be a minimum depth of 150mm for all applications. Ndm testing to 98% at 20m intervals | During Construction | NDM Test | Sign This ITP | Contract Manager | NDM test record
40 | Flush and CCTV line |  | Inspection | H | Flush and CCTV line and pass footage back to engineer for review | Prior to asphalt | Inspection | Sign This ITP | Contract Manager
41 | Pre Seal Inspection |  | Sign off | H | Engineer to approve area is ready for asphalt (including overcuts) . Prep is 40mm and has fall and compaction results have been recived | Prior to asphalt | Inspection | Sign This ITP | Engineer