## Master List Templates
Id | Type | Name | Values | Prompting Name
bf940eed-1583-444b-a88a-7fe6080bd2ec | checklist | Box Fins - Install Checklist |  | Box Fins - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
9f16cca4-1553-443a-9b99-2aed515f7a9b | checkpoint | Has the window/door installation been completed?
0984b153-3eaa-4813-9816-8eb9b589124f | checkpoint | Is interior sealant application neat and continuous.
8428e856-68d0-476c-b582-f186a11e4dc3 | checkpoint | Is exterior sealant application neat and continuous.
a1921991-582f-4986-b3aa-b91e0f734fa6 | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
20ab1926-e99d-4f35-8689-a94b9e691368 | checkpoint | Are all window and doors working?
a627108f-86fd-4cf8-b223-03c63b4326f8 | checkpoint | Is the joinery free of scratches?
24a7715a-c77c-4fc9-b782-f0d92bc3c5a6 | checkpoint | Is the joinery clean and tidy?
7bab1045-0600-4232-bc75-b94fab728abc | checkpoint | Proper spacing and clearances are maintained around the window units.
ca948369-328d-428b-a80c-d32bd72e81b9 | checkpoint | Fasteners used are correct in type, size, and spacing
e92e84b6-0b0a-4274-96a8-e7c951bbc9ff | checkpoint | End Caps Installed
4e3a18c8-06af-4143-b117-f6e0568067eb | checkpoint | Brackets installed to modules as per Shop Drawings
9ff05b47-9a6b-4526-97f7-1cf92d0e8033 | checkpoint | Brackets installed to Box fins as per Shop Drawings
8d8a2778-5d46-4364-9352-b5b0b2a0a01f | checkpoint | Box Fin Spacing as per Shop Drawings
1c1a3a6d-4406-438d-b6a0-25e3e6428484 | checkpoint | Box Fin Alignment completed
9769f69a-caaa-4d67-afc3-a7f9b27b4410 | checkpoint | Frames installed correctly?
dc75720c-baf6-4997-bc91-d99d9fde64f9 | checkpoint | Modules installed correctly?
23544eb9-37ca-40aa-81dd-3183db4adde2 | checkpoint | Drains are not blocked
c15efdd1-5fae-49d2-8965-28e54566368e | checkpoint-no-value | The correct consumables specified were used (Sealant) - Photo of Label Required
4a3f2adc-414e-4de3-9782-833bd2fbd759 | checkpoint-no-value | The correct consumables specified were used (Screws) - Photo of Label Required
48cfc9cd-4b73-4191-9cdc-452893427838 | checklist | Channel Glazing - Install Checklist |  | Channel Glazing - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
9decc434-3038-40b2-aea8-32661fbc4cac | checkpoint | Has the window/door installation been completed?
81ddc2c9-3817-4be3-8f4c-d4aef1e7ba87 | checkpoint | Is interior sealant application neat and continuous.
a7334be9-b596-4659-a4a3-972992977f6e | checkpoint | Is exterior sealant application neat and continuous.
edadd316-764b-4056-91b7-a8ba502c2e37 | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
24638af7-17d2-4d8e-85b2-33f20e93f3b0 | checkpoint | Are all window and doors working?
955f2234-6043-4577-a406-f35f142d1cb2 | checkpoint | Is the joinery free of scratches?
b3cd1466-56d8-4a03-919e-be47c2fb1bbe | checkpoint | Is the joinery clean and tidy?
25d38dbb-b2e2-496f-8374-f57649cd1367 | checkpoint | Proper spacing and clearances are maintained around the window units.
12b88cd7-66c9-4377-8c13-61dab7347f99 | checkpoint | Fasteners used are correct in type, size, and spacing
85c310de-970d-4b8c-9f5c-7f83dba150b4 | checkpoint | Frames installed correctly?
963bfe97-09b3-4ca2-abd2-3c351ffec7cc | checkpoint | Drains are not blocked?
a3735c3c-43ee-4cfe-a5b7-759e43d2a3a2 | checkpoint-no-value | The correct consumables specified were used (Sealant) - Photo of Label Required
c420144f-f907-4ec6-bd6d-11f00eda5268 | checkpoint-no-value | The correct consumables specified were used (Screws) - Photo of Label Required
e75fa9ec-9749-4c52-bf48-199f7aeab6c4 | checklist | General Manufacturing Template |  | General Manufacturing Template
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
83bd2d4e-0fe3-439f-86c2-c2768ee445a4 | checkpoint | Item free of defects and damages
5fd22b99-4780-43c6-ad4c-0fb51c1d1379 | checkpoint | Item is clean - No pencil marks / dirt / excessive sealant
022fbb6b-a0b9-4481-9874-92f58e3dab83 | checkpoint | Item is clearly labelled in accordance with fabrication sheets
7a8f9bfe-103e-430b-a0d6-1ab14ae785fc | checkpoint | Item is square - Frame / Sashes / Panels
5ffbc1b4-0ee6-46ed-be65-9bb4c0e10e5b | checkpoint | Sealant is correct colour
21ec308c-fb31-471c-92aa-52f970d6460e | checkpoint | Beads / Thresholds / Infills correct length
5d9c8513-2879-4860-af07-5d9448ce6e25 | checkpoint | Mitres flush
10f0cea4-e5c5-4f61-97e4-4e488cd6ccd1 | checkpoint | Drainage correct as per APL manufacturing pack and aligned
cde361a9-c03b-4620-9275-29b7d1968dac | checkpoint | Liners - TWT Measured / Correct Liner / Staples every 150 - 200mm
33435a04-bba7-4189-a3da-2e190ce103f3 | checkpoint | Rubbers continuous and free of damage - not pinched under glass / foam
bb930635-b662-42a3-8e10-43aee0db603b | checkpoint | Fin Mullions painted
4af25516-ce52-44de-a9e6-a11f4dcff239 | checkpoint | Sealant tidy on frame where sash is present
2f9938bd-984c-4b54-b40e-a20456f87fa4 | checkpoint | Glass inspection done - Clean / Correct type / No defects
ebb169bb-0cec-4538-b417-624da86a3561 | checkpoint | Glazing done correctly - No movement / correct glazing rubber
c08a92da-7e06-41f7-b6da-dee8b20a2f0b | checkpoint | Bungs / Caps fitted
5d151bf8-a07d-45b2-a6d2-eca2d09ceb32 | checkpoint | Support Blocks fitted
bc0b3aa1-cf30-4e61-9556-22604141c473 | checkpoint | Transport Blocks between panel and frame
dc1129a6-90bf-4989-933c-b196d783937e | checkpoint | Protective tape on bottom sill
41776750-e73b-470c-9bdc-9231296698b0 | checkpoint | Overall item dimensions correct
12e7851f-a3b7-40c8-9fa2-2d475a16abfd | checkpoint | Correct Windzone sticker applied
5de09a86-8ad8-4531-b97d-b6013a7edb63 | checkpoint | Item match drawing
0dfa618d-6ae0-4090-b4ec-e3ba60682f92 | checkpoint | Commenst on jobsheets followed
6dd88342-6059-408e-a00c-9c6dae71034a | checkpoint | Machining done as per assembly sheet
e251f8cc-536b-447c-b75b-499bdb6d90f9 | checkpoint | Correct Hardware fitted as per jobsheet
8ea8d0b6-ed98-443a-bf37-cc1da4bc96f6 | checkpoint | Soaker correctly fitted
e3533ec2-989b-4854-897c-cc71ec8b2715 | checkpoint | Sillsafe applied correctly
9bb04d30-a482-4f60-b67a-d8cd7f0bc0c2 | checkpoint | Soaker correctly fitted over sillsafe ends
b6fff5cf-485f-4e6f-8687-8e6e4304b090 | checkpoint | Foam tape fitted to sill fixed leg
5219d8fc-d186-4b0a-a4ac-89e322029edb | checkpoint | Top & Bottom Screws sealed
3b5a076b-c0c1-4226-bfab-d9c5b64aefb5 | checkpoint | Screws fitted to all hardware & components
a863823f-f9bf-4c1d-9177-bb3a38dfaf4b | checkpoint | Glazing Platform fitted (TH Frames)
487e8a8e-8278-43e7-b18f-34939b2203ad | checkpoint | Seal between liners - Correct application
3e60ef50-1a78-4c21-85ca-a6221847c57f | checkpoint | Tracks / Stoppers fitted correctly
7688e894-e64b-4515-a3e2-82b44ba24b50 | checkpoint | Sashes / Panels opening and closing correctly
fa453deb-b971-4e22-b80e-0113342e3c3b | checkpoint | Handles facing the right way and are not lose
263510fb-cf9c-4d6b-83e8-f4871799fba3 | checkpoint | Strikes fitted - Item locks / unlocks freely
034c87a7-8724-4c6d-8bf5-26010efc88a4 | checkpoint | All hardware operational
b2cba76e-bc18-4695-ab3b-13d9997eb5f4 | checkpoint | Protective tape on handle - Key taped to inside of handle
d900dd32-9eba-4297-b27f-6d98c6558780 | checklist | Glazing Checklist |  | Glazing Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b68e0248-2936-43d7-a39e-425796453601 | checkpoint | Frame installed securely
4bc74dd1-2c26-42fc-9240-efb1d4d8f31f | checkpoint | Correct glass installed
144ce542-9dd8-46db-a99b-ae5c872b169e | checkpoint | Glass installed with correct face to the outside
8c042754-d45b-443d-bc5b-2c4227aa0c59 | checkpoint | Setting/location blocks correctly installed
e8d93361-bb58-40fb-8648-db2f0fd7cc49 | checkpoint | Beads installed
e2f364df-c5f6-4d6b-91f5-e4a855a0b7dd | checkpoint | Wedge rubber complete
c710226e-2ed1-4c58-b052-4585b0c112f8 | checkpoint | Trade clean
93754c40-d751-4f62-8952-dbb6fe743baa | checklist | Handover Checklist |  | Handover Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f5319e7d-c1f3-4777-b3a2-6b94f57a4313 | checkpoint | All works completed as per specifications
7b05e090-6935-5526-a050-1202c0b658f4 | date | Date:
bcb80f05-b1a1-4cf1-9660-fa74a8d7790f | checkpoint | Company Signoff
6307ad26-9f46-4bae-a376-4475c7e744f8 | signoff | SIGN HERE
a79b18ad-d9c6-44cf-af9b-3a0634994635 | checkpoint | Client Signoff
3117845b-52e4-4056-b6ac-4dfcbd0ec98b | signoff | SIGN HERE
fabab1f4-499c-4d74-a3b4-74898b14a941 | checklist | Performance Tests |  | Performance Tests
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
02e033c7-3388-461a-9334-681086727aa0 | checkpoint | Water test (if applicable) performed and passed.
883761d8-e44d-4bec-a7e5-84ca8536b1c4 | checkpoint | Sealant Peel Test (if applicable) performed and passed
5a22953a-90a7-43f1-bf68-3ca12e772e78 | checklist | Pre Install Checklist |  | Pre-Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b00b5a77-ad76-45b6-b3ad-2731c8def02a | checkpoint | Openings are prepared and match the dimensions specified in the drawings
09275694-954a-46dc-87cb-d8c38a7c6214 | checkpoint | Openings are prepared and match the dimensions specified in the drawings
0f1896aa-38e6-449b-83dc-81b006266aa3 | checkpoint | Waterproofing has been prepared
498451fa-4c5c-4493-bf45-2aa8240fd71d | checklist | Structural Glaze - Install Checklist |  | Structural Glaze - Install Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a6202c1a-9c75-45da-a7c8-ccfc043b41f5 | checkpoint | Has the window/door installation been completed?
9fee5fee-7e56-46a6-88fd-b338d4c3ec96 | checkpoint | Is interior sealant application neat and continuous.
4cbb0e8d-4f4e-42e2-8ff3-bedbd52e203b | checkpoint | Is exterior sealant application neat and continuous.
0376e0c5-35ed-48bd-8f19-41fa56d3f04a | checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
05ad11a6-49e8-46a3-be38-348225650450 | checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
97243724-972f-4547-9c8e-7f73539e74ba | checkpoint | Are all window and doors working?
88435f8a-0f42-4cd3-ad70-8b3aa6902004 | checkpoint | All handles installed correctly?
894c7133-66a1-4306-85fe-6682a0e3a3f8 | checkpoint | Are all the hardware installed correctly?
d2bc6cb7-003b-489a-bd87-1c05e5b360a5 | checkpoint | Is the joinery free of scratches?
797af926-95d9-4274-8060-87005ff313bf | checkpoint | Is the joinery clean and tidy?
1084587b-8fe8-412c-9c62-dabdb51524f8 | checkpoint | Hinge doors strikes adjusted and locking easily
39f25609-dc9d-49de-9171-9a5ca9d832bb | checkpoint | Hinge doors 4 or 3 point lock operate easily
1f531f2c-debf-4f11-bd51-531b52f107a7 | checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
787bb37f-5f97-47d4-819c-3c66ea9cd595 | checkpoint | Sliding doors - panels are adjusted and locking easily
22f65642-8ba8-4803-b604-3ef3b34921d8 | checkpoint | Sliding doors - Strikes are adjusted
f7f999bc-7bbb-49d0-b610-b7de4afca181 | checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
3f174e56-5da8-4cc3-8ecc-45f6da79cc76 | checkpoint | Proper spacing and clearances are maintained around the window units.
b6805a9f-92bb-48bc-b931-fc0934f76ace | checkpoint | Fasteners used are correct in type, size, and spacing
afabb51f-106a-41fb-a75e-e2a166b56a26 | checkpoint | End Caps Installed
fa1811a2-5f98-416f-acbb-cae7e2184665 | checkpoint | Frames installed correctly?
6cfc2547-36f3-450b-963d-e9b0ddb415b4 | checkpoint | Modules installed correctly?
08848229-d398-4494-a945-75f3eab64de7 | checkpoint | Drains are not blocked
cd3dac97-f843-4108-90d4-d2f9b1a11fc8 | checkpoint-no-value | The correct consumables specified were used (Sealant) - Photo of Label Required
06be6f18-2455-4d2c-a5fe-fd795fcb83ef | checkpoint-no-value | The correct consumables specified were used (Screws) - Photo of Label Required

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
301b0803-9948-4260-9540-3c4ef7c8e57f | checklist | General Manufacturing Template - CBC |  | General Manufacturing Template - Test V2
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
71bc9155-72e0-4036-829a-74b82a1e260f | checkpoint | Lengths cut as per Jobsheet
952be6f0-0f91-47df-8002-cff0fac02608 | checkpoint | Prep & machining work completed as per Manufacturing pack & Shop Drawings (Photos)
7ed20bda-756d-4923-ad0e-c867aee69b65 | checkpoint | Sealant applied where required prior to assembly (Photos)
5adecd7e-14eb-4ea6-aaf8-3b57eb7674e9 | checkpoint | Assembled as per manufacture drawings (Photos)
ad552e7e-9ac8-468f-8733-814cd3d7e460 | checkpoint | Fixings and penetrations are as per the PS1
8b8442bf-a118-4474-b5e3-1971738e04d8 | checkpoint | Joints oversealed as per APL manufacturing pack (photos)
b3fd6ae7-fef2-410a-9e64-dd1621c47d71 | checkpoint | Fin Brackets installed as per manufacture pack (Photos)
4639cfd6-5a44-4f35-b24a-e00795617cba | checkpoint | Bracket machine flange oversealed prior to glazing
4c22c768-c99c-4c01-ba9a-46602e1ccba1 | checkpoint | Hook brackets installed as per manufacturing pack & shop drawings, bolts torqued as per specifications (photos)
daf18eaf-e8d8-4345-a3ee-db8f923d2bc1 | checkpoint | Hook Bracket Bolts are oversealed
58b38068-4c57-4de3-b61d-5177f304b160 | checkpoint | Backpans installed as per manufacture pack (photos)
38ac75ac-1c08-4297-a200-3921ee6bf362 | checkpoint | Fire Insulation installed as per supplier specifications (Photos)
c4faa141-27b3-4248-82dc-851b672e189e | checkpoint | Box Fins Installed as per panel drawings.
676ccc8e-e4d3-4106-a830-a3677db2e6c7 | checkpoint | Box Fin End Caps installed & Location are correct
815301b3-6cc6-446b-bb32-be8692a61a2d | checkpoint | Box Fin bolts torqued as per specification.
49a9428c-3040-5149-8ea7-278385d8a5f0 | tickbox | Each Module /Item labelled correctly
ee1f42a1-e66d-41ac-9256-7fd3a4f3c058 | checklist | General Manufacturing Template - CBC (STAGE #6) |  | General Manufacturing Template
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
71bc9155-72e0-4036-829a-74b82a1e260f | checkpoint | Lengths cut as per Jobsheet
952be6f0-0f91-47df-8002-cff0fac02608 | checkpoint | Prep & machining work completed as per Manufacturing pack & Shop Drawings (Photos)
7ed20bda-756d-4923-ad0e-c867aee69b65 | checkpoint | Sealant applied where required prior to assembly (Photos)
5adecd7e-14eb-4ea6-aaf8-3b57eb7674e9 | checkpoint | Assembled as per manufacture drawings (Photos)
ad552e7e-9ac8-468f-8733-814cd3d7e460 | checkpoint | Fixings and penetrations are as per the PS1
8b8442bf-a118-4474-b5e3-1971738e04d8 | checkpoint | Joints oversealed as per APL manufacturing pack (photos)
b3fd6ae7-fef2-410a-9e64-dd1621c47d71 | checkpoint | Fin Brackets installed as per manufacture pack (Photos)
4639cfd6-5a44-4f35-b24a-e00795617cba | checkpoint | Bracket machine flange oversealed prior to glazing
4c22c768-c99c-4c01-ba9a-46602e1ccba1 | checkpoint | Hook brackets installed as per manufacturing pack & shop drawings, bolts torqued as per specifications (photos)
daf18eaf-e8d8-4345-a3ee-db8f923d2bc1 | checkpoint | Hook Bracket Bolts are oversealed
c4faa141-27b3-4248-82dc-851b672e189e | checkpoint | Box Fins Installed as per panel drawings.
676ccc8e-e4d3-4106-a830-a3677db2e6c7 | checkpoint | Box Fin End Caps installed & Location are correct
815301b3-6cc6-446b-bb32-be8692a61a2d | checkpoint | Box Fin bolts torqued as per specification.
49a9428c-3040-5149-8ea7-278385d8a5f0 | tickbox | Each Module /Item labelled correctly
84e0208b-0bd5-4472-a934-e8749c5924cc | checklist | General Manufacturing Template - test |  | General Manufacturing Template - test
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f7e94752-8386-41c4-b486-ebd45bfa542c | checkpoint | Lengths cut as per Jobsheet
51c5863c-1ff6-46fd-af5f-2bfa9589c440 | checkpoint | Prep & machining work completed as per Manufacturing pack & Shop Drawings (Photos)
00acd5ea-29ae-499d-8def-36ba019b132d | checkpoint | Sealant applied where required prior to assembly (Photos)
0de1aaeb-6bc4-4e31-895f-c704fc5ccd1e | checkpoint | Assembled as per manufacture drawings (Photos)
7d53584d-2c6b-4732-97f5-1743a69b888a | checkpoint | Joints oversealed as per APL manufacturing pack (photos)
0536e217-628a-41d8-a2a8-c63ccf103277 | checkpoint | Fin Brackets installed as per manufacture pack (Photos)
3fbc2820-f63b-4dd9-9258-cf3c64dd4dbf | checkpoint | Hook brackets installed as per manufacturing pack & shop drawings, bolts torqued as per specifications (photos)
0d4e645e-4ef2-4e9b-bea7-0449c87204c0 | checkpoint | Backpans installed as per manufacture pack (photos)
0e1920e3-e9e0-477e-8ba8-304d9abc4941 | checkpoint | Fire Insulation installed as per supplier specifications (Photos)
7d2f6486-bd6a-4457-872f-f7deed43bb97 | checkpoint | Box Fins Installed as per panel drawings.
8dba0595-0c1a-4c8c-809b-89825bab693a | checkpoint | Box Fin bolts torqued as per specification.
fa275d4d-cd35-4f1e-be59-81acb365360a | checklist | General Manufacturing Template - Test V3 |  | General Manufacturing Template - Test V3
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
23d6895e-339d-48eb-92d5-02b4ab6c39aa | checkpoint | Lengths cut as per Jobsheet
62aee34e-4845-457b-84b3-a8da08d98ed3 | checkpoint | Prep & machining work completed as per Manufacturing pack & Shop Drawings (Photos)
6755883d-aaef-49dd-b058-888ee00b724b | checklist | Glazing Checklist - test |  | Glazing Checklist - test
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
fb532c10-184b-49e4-a6af-31ea4429fbab | checkpoint | All bonding surfaces cleaned with approved solvent
c09374e1-04cc-4710-9875-15c1975b57ae | checkpoint | No presence of dust, oil, oxidation, or contamination
4eb7cc59-63d8-4350-ad24-0d90d16e1197 | checkpoint | Primer applied to metal
297b258a-1e4b-46ed-a043-01c24b63b3a6 | checkpoint | Approved structural silicone sealant used (name & batch recorded) (Photos)
6d9861a7-e805-4cfb-8c62-daa294344e4e | checkpoint | PEF rod & setting blocks positioned correctly (Photos)
6b593be9-38a0-435e-bd44-e40c5fa859ea | checkpoint | Consistent silicone bead thickness & contact with glass and frame (Photos)
69c293f2-5e22-4b93-8577-27ac46a35361 | checkpoint | No air bubbles, voids, or skipped areas in silicone
40528dc9-cefb-40d5-b4d3-68a24679b1f8 | checkpoint | Tooling of sealant is neat and continuous (Photos)
c6586aff-b508-4bf8-a9e0-ad9dcd302c60 | checkpoint | Curing time/conditions meet manufacturer’s specification
97172e0c-ce98-4688-a155-8d6285f07b4e | checkpoint | Glass is free of defects, scratches, edge damage (Photos)
765e9212-61d3-4b73-8cda-37fa48657c07 | checkpoint | Sealant and glazing methods align with PS1 design
53cd2cc8-ce34-46ac-aaa0-1df42de5eeff | checklist | Handover Checklist - test |  | Handover Checklist - test
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
919a6618-447f-4816-b7ee-8c9d7da4ac68 | checkpoint | All works completed as per specifications
9774a590-ddbc-516a-b973-e8edc0bbc6ee | date | Date:
50fa1f69-e17d-4c16-9a95-8490551f09d0 | checkpoint | Company Signoff
7d8e4830-f71d-4219-895c-e774a8cf3fdf | signoff | SIGN HERE
e8d76db4-8c2e-41e5-9624-38a13e0a3d4b | checkpoint | Client Signoff
6d1646fc-a5da-43c2-93a3-0c7a64e48bd6 | signoff | SIGN HERE
92c9cc4b-8a20-415c-86fc-2e139be4c9c0 | checklist | Performance Tests - test |  | Performance Tests - test
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
4aa981c6-6376-4f00-ab32-93be11d85f65 | checkpoint | Water test (if applicable) performed and passed.
35f271c5-6f10-4829-9389-18862d415902 | checkpoint | Sealant Peel Test (if applicable) performed and passed
665abdb8-733d-4bba-80fa-390f0301b8af | checklist | Pre-Install Checklist - test |  | Pre-Install Checklist - test
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
02f10b28-53d5-4c07-923c-581cb7f6450a | checkpoint | Waterproofing prepared as per specifications
6abe64cf-411d-40f9-bf43-1a59017f193b | checkpoint | Sill & Jambs within tolerance specified
4e29d7ff-a06b-4504-9758-4ecf1ad52331 | checkpoint | Bracket Survey completed & within acceptable tolerance
a8e555cd-09d8-4f48-9773-7d9b96271b2b | checkpoint | Bracket Connections to building torqued to specifications
f1385286-2433-4ba2-bf7d-9fbacf05fe98 | checkpoint | Structural glazing sealant undamaged, fully cured
7e145a56-9941-494a-a52a-0f01d74a6fae | checkpoint | No glass damage, delamination, or edge chips
45489999-3c88-4215-902c-d4ce8a96dcfe | checkpoint | Frame and corner joints intact and not deformed
bc9eb26f-ac3d-424b-a66a-0f310a3a485b | checkpoint | Labels and module ID still present and legible
d0b1b792-eefc-4824-93fb-d4fb30c6e212 | checkpoint | No signs of contamination (grease, dust, water)
ca63136b-4e72-410c-99b3-f7ad37aa5adb/1 | checklist | Sill Tank Test - Test V2 |  | Sill Tank Test - Test V2
70613f33-1d2b-4783-b089-1f24534252a3 | section | Details
3523b992-d40c-488b-b5c0-8f92950b6eb1 | checkpoint-no-value | Start Time
6a193045-5af2-4fae-9f78-179769534b75 | checkpoint-no-value | End Time
a49294fc-b21a-45d7-8954-9c3dcb59170f | checkpoint | Sill Test
24f70791-b55a-4638-83f5-fc6c568551ef | checklist | Structural Glaze - Install Checklist - test |  | Structural Glaze - Install Checklist - test
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
87321fdf-ede9-4f51-bf89-36713e974b9a | checkpoint | All brackets/fixings installed as per PS1/shop drawings (Photos)
05491eb9-6276-4d67-92e1-22227e13ea30 | checkpoint | Fixings secure, correctly torqued, and not overtightened (Photos)
73f5e9c7-4cbf-4332-9691-f443250db67c | checkpoint | No signs of bracket deformation or stress
988447c1-bb00-4337-b0ad-8aedde9a77d4 | checkpoint | Modules installed square and level
ca6e76bd-1942-4c15-b364-263dd0681ed5 | checkpoint | Vertical and horizontal alignment consistent
405e78a1-a928-4dcc-84ed-6c084fe8e991 | checkpoint | Consistent reveal gaps between modules and substrate
f8157285-fbea-4c8c-8036-5ae923afecaa | checkpoint | Glass joints aligned uniformly across façade
a840d278-4c99-4ebe-8ddc-28b63266d264 | checkpoint | Spigots & Soakers Installed and oversealed (Photos)
910c1934-714c-4ad3-84a1-de3e0252c739 | checkpoint | Flood Tests to Split Transoms passed (Photos)
4e1434d6-e981-4329-9018-5c1a150a0984 | checkpoint | No visible frame damage or scratches
29fd9c41-43cf-427d-99f8-97b7018b438d | checkpoint | No chips, cracks, or scratches in glass
3eceb215-f04b-4ef7-96db-68f652455b48 | checklist | Structural Glaze - Install Checklist - Test V2 |  | Structural Glaze - Install Checklist - Test V2
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
cbc70714-128b-4b90-b9a3-f0a2eec3952c | checkpoint | All brackets/fixings installed as per PS1/shop drawings
8a724c90-09c0-4422-a8d4-1f9fda970722 | checkpoint | Fixings secure, correctly torqued, and not overtightened
2b7b215b-bcf3-4658-9d39-3acef279c8ba | checkpoint | Module has been wiped down before hoisting
13a8efa7-7554-437e-9ae4-554d12139054 | checkpoint | No signs of bracket deformation or stress
540b1736-2d68-456a-be2f-f71846d85c5b | checkpoint | Modules installed square and level
23985b1b-ad0c-41b5-a0a0-512961ef3670 | checkpoint | Vertical and horizontal alignment consistent
f314f1d0-6028-4e0c-ab38-d8307c3d42dc | checkpoint | Consistent reveal gaps between modules and substrate
b095e1a5-662a-4285-8e25-ed153b072521 | checkpoint | Glass joints aligned uniformly across façade
3fa561cf-9069-40c0-a6bb-dbab9e56ba3d | checkpoint | Spigots & Soakers Installed and oversealed
5616feaf-b25a-4b20-a09f-fea5c1b95668 | checkpoint | Jamb/End Dams sealed (over & under)
f38d0556-ce5b-48f8-b74a-7e75c1a99184 | checkpoint | Flood Tests to Split Transoms passed
ea5ff32f-ffae-4443-8ab5-446c5a557460 | checkpoint | No visible frame damage or scratches
12ca6e45-4261-492e-9aae-100d42a2ef96 | checkpoint | No chips, cracks, or scratches in glass
9d4d2bae-0101-4da9-b300-204b842df9e5 | checkpoint | All temporary packers are removed.
d29cdcde-fdbf-4d23-bd30-0d093dc03f73 | checkpoint | Ensure adjustment bolt lock nuts are securely fastened in place.
d41d765d-6eb4-44a6-bacc-dc6ceee2b2aa | checkpoint | All Protection tape and orange tape removed from joinery.