## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | General Manufacturing Template - CBC (STAGE #6) |  | General Manufacturing Template
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
71bc9155-72e0-4036-829a-74b82a1e260f | checkpoint | Lengths cut as per Jobsheet
952be6f0-0f91-47df-8002-cff0fac02608 | checkpoint | Prep & machining work completed as per Manufacturing pack & Shop Drawings (Photos)
7ed20bda-756d-4923-ad0e-c867aee69b65 | checkpoint | Sealant applied where required prior to assembly (Photos)
5adecd7e-14eb-4ea6-aaf8-3b57eb7674e9 | checkpoint | Assembled as per manufacture drawings (Photos)
ad552e7e-9ac8-468f-8733-814cd3d7e460 | checkpoint | Fixings and penetrations are as per the PS1
8b8442bf-a118-4474-b5e3-1971738e04d8 | checkpoint | Joints oversealed as per APL manufacturing pack (photos)
b3fd6ae7-fef2-410a-9e64-dd1621c47d71 | checkpoint | Fin Brackets installed as per manufacture pack (Photos)
4639cfd6-5a44-4f35-b24a-e00795617cba | checkpoint | Bracket machine flange oversealed prior to glazing
4c22c768-c99c-4c01-ba9a-46602e1ccba1 | checkpoint | Hook brackets installed as per manufacturing pack & shop drawings, bolts torqued as per specifications (photos)
daf18eaf-e8d8-4345-a3ee-db8f923d2bc1 | checkpoint | Hook Bracket Bolts are oversealed
c4faa141-27b3-4248-82dc-851b672e189e | checkpoint | Box Fins Installed as per panel drawings.
676ccc8e-e4d3-4106-a830-a3677db2e6c7 | checkpoint | Box Fin End Caps installed & Location are correct
815301b3-6cc6-446b-bb32-be8692a61a2d | checkpoint | Box Fin bolts torqued as per specification.
49a9428c-3040-5149-8ea7-278385d8a5f0 | tickbox | Each Module /Item labelled correctly