## Sheet1
1 | Design | H | IFC Drawings | Prior to commencement | Document Review | Ensure that Design is approved and Drawings are of the latest revision | Check Drawing Register | 1 - Design | ACTION (Hold, Monitor, Witness) - H | Detail - IFC Drawings | Frequency - Prior to commencement | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision | Records - Check Drawing Register | 1 - Design
ACTION (Hold, Monitor, Witness) - H
Detail - IFC Drawings
Frequency - Prior to commencement
Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision
Records - Check Drawing Register