## Sheet1
Taylormade ( 1-7 Boyle St Sutherland )
| Job | Panel No. | Area/m2 | Thickness mm | weight/t | m3/hr | Production Actual Date | Delivery Actual Date
1 | 348 | 201 | 16.96 | 150 / 250 | 8.64 | 0.4 | 2023-08-28 |  | urgent need 1st
2 | 348 | 202 | 13.56 | 150 / 250 | 6.2 | 0.4 | 2023-08-28 |  | urgent need 1st
3 | 348 | 203 | 3.73 | 150 | 1.4 | 0.4 | 2023-08-08 |  | urgent need 1st
4 | 348 | 204 | 8.59 | 150 / 250 | 3.95 | 0.4 |  |  | urgent need 1st
5 | 348 | 204-A | 9.72 | 150 / 250 | 4.33 | 0.4 |  |  | urgent need 1st
6 | 348 | 205 | 5.82 | 150 / 250 | 2.65 | 0.4 |  |  | urgent need 1st
7 | 348 | 206 | 16.3 | 150 / 250 | 7.6 | 0.4
8 | 348
9 | 348 | 208 | 19.05 | 150 / 250 | 8.77 | 0.4
10 | 348 | 209 | 2.94 | 150 | 1.1 | 0.4 | 2023-08-08
11 | 348 |  | 19.01 | 150 / 250 | 8.75 | 0.4
12 | 348
13 | 348 | 212 | 17.5 | 175 / 250 | 9.1 | 0.4
14 | 348 | 213 | 16.33 | 175 / 250 | 8.35 | 0.4
15 | 348
16 | 348 | 215 | 19.67 | 175 / 250 | 10.1 | 0.4
17 | 348
18 | 348 | 217 | x |  |  | 0.4 | 2023-08-25
19 | 348
20 | 348
21 | 348 | 220 | 25.9 | 150 / 250 | 12 | 0.4
22 | 348 | 221 | 15.06 | 150 / 250 | 5.65 | 0.4
23 | 348
24 | 348 | 223 | 26.41 | 175 / 250 | 13.47 | 0.4
25 | 348 | 224 | 5.82 | 150 / 250 | 2.65 | 0.4 |  |  | urgent need 1st
26 | 348 | 225 | 9.72 | 150 / 250 | 4.33 | 0.4 |  |  | urgent need 1st
27 | 348 | 225-A | 8.59 | 150 / 250 | 3.95 | 0.4 |  |  | urgent need 1st
28 | 348 | 226 | 3.73 | 150 | 1.4 | 0.4 | 2023-08-08 |  | urgent need 1st
29 | 348 | 227 | 13.56 | 150 / 250 | 6.2 | 0.4 |  |  | urgent need 1st
30 | 348 | 228 | 16.96 | 150 / 250 | 8.64 | 0.4 |  |  | urgent need 1st
31 | 348 | [7 empty] | urgent need 1st
32 | 348 | 230 | 20.44 | 150 / 250 | 8.7 | 0.4 |  |  | urgent need 1st
33 | 348 | [7 empty] | urgent need 1st
34 | 348 | 232 | 20.44 | 175 / 250 | 9.5 | 0.4 |  |  | urgent need 1st
35 | 348
36 | 348
37 | 348
38 | 348
39 | 348
40 | 348
41 | 348
|  | Total | Total Dwg | Produced | Delivered
|  | 24 | 25 | 6 | 0
|  | Taylormade ( 1-7 Boyle St Sutherland ) |  |  |  |  | area=1793.9 | 2.281%
[7 empty] | panels=198 | 3.03% | 0.12121
|  | Status | Incomplete |  |  |  | delivery | 0%
|  | Contracted Sq m | 1793.9
|  | Produced Sq m | 40.92
|  | Total Sq m | 335.81
$/m2
Sales Price
Labour
Transport
Note on C6: Marcel senior. Nassar: curved panel
Note on C7: Marcel senior. Nassar: curved panel
Note on C28: Marcel senior. Nassar: curved panel
Note on C29: Marcel senior. Nassar: curved panel