## Sheet1
1 |  | DASCO (Castle Hill)
2 | Job | Panel No. | Area/m2 | Thickness mm | weight/t | m3/hr | Production Actual Date | Delivery Actual Date
3 | 361 | W 01 | 13.46 | 200 | 6.73 | 0.6 | 2022-09-16 | 2022-10-28
4 | 361
5 | 361 | 1001 | 6.68 | 175 | 2.81 | 0.1 | 2023-07-27 | 2023-08-18
6 | 361
7 | 361 | 1003 | 3.06 | 175 | 1.4 | 0.1 | 2023-08-01 | 2023-08-18 | CURVE SHOULD RECEIVE ON 10TH
8 | 361 | 1004 | 9.38 | 175 | 3.94 | 0.6 | 2023-07-31 | 2023-08-18
9 | 361
10 | 361 | 1006 | 4.09 | 175 | 1.72 | 0.1 | 2023-07-27 | 2023-08-18
11 | 361 | 1007 | 1.56 | 175 | 0.91 | 0.1 | 2023-07-27 | 2023-08-18
12 | 361
13 | 361 | 2001 | 6.69 | 175 | 2.81 | 0.1 | 2023-08-08
14 | 361 | 2002 | 3.06 | 175 | 1.4 | 0.1 | 2023-08-01
15 | 361 | 2003 | 9.38 | 175 | 3.94 | 0.1 | 2023-08-04
16 | 361 | 2004 | 4.29 | 175 | 1.8 | 0.1 | 2023-07-31
17 | 361 | 2005 | 1.63 | 175 | 0.64 | 0.1 | 2023-07-31
18 | 361 | 2006 | 1.63 | 175 | 0.7 | 0.1 | 2023-08-02
19 | 361
20 | 361 | 3001 | 6.69 | 175 | 2.81 | 0.1 | 2023-08-08
21 | 361 | 3002 | 3.06 | 175 | 1.4 | 0.1 | 2023-08-03
22 | 361 | 3003 | 9.38 | 175 | 3.94 | 0.6 | 2023-08-04
23 | 361
24 | 361 | 4001 | 6.69 | 175 | 2.81 | 0.6 | 2023-08-25
25 | 361 | 4002 | 3.06 | 175 | 1.4 | 0.1 | 2023-08-21 |  | curve
26 | 361 | 4003 | 9.38 | 175 | 3.94 | 0.6 | 2023-08-22
27 | 361
28 | 361 | 4501 | 1.82 | 175 | 0.76 | 0.6 | 2023-08-28
29 | 361 | 4502 | 3.06 | 175 | 1.4 | 0.1 | 2023-08-23 |  | curve
30 | 361 | 4503 | 8.32 | 175 | 3.5 | 0.6 | 2023-08-25
31 | 361 | 4504 | 8.32 | 175 | 3.5 | 0.6 | 2023-08-22
32 | 361 | 4505 | 6.79 | 175 | 2.85 | 0.6
33 | 361 | 4506 | 3.06 | 175 | 1.4 | 0.1 | 2023-08-23 |  | curve
34 | 361 | 4507 | 2.71 | 175 | 1.14 | 0.6 | 2023-08-28
35 | 361 | 4508 | 5.33 | 175 | 2.24 | 0.6
36 | 361 | 4509 | 5.33 | 175 | 2.24 | 0.6
37 | 361 | 4510 | 3.06 | 175 | 1.4 | 0.6 | 2023-08-25 |  | curve
38 | 361 | 4511 | 2.78 | 175 | 1.17 | 0.6
39 | 361 | 4512 | 4.72 | 175 | 1.98 | 0.6
40 | 361 | 4513 | 3.06 | 175 | 1.4 | 0.6 | 2023-08-24 |  | curve
41 | 361 | 4514 | 8.7 | 175 | 3.65 | 0.6
42 | 361 | 4515 | 8.7 | 175 | 3.65 | 0.6
43 | 361 | 4516 | 3.06 | 175 | 1.4 | 0.6 | 2023-08-28 |  | curve
44 | 361 | 4517 | 4.69 | 175 | 1.97 | 0.6
45 | 361 | 4518 | 2.28 | 175 | 0.96 | 0.6
46 | 361 | 4519 | 3.06 | 175 | 1.4 | 0.6 | 2023-08-28 |  | curve
47 | 361 | 4520 | 7.88 | 175 | 3.31 | 0.6
48 | 361 | 4521 | 5.7 | 175 | 2.39 | 0.6
49 | 361 | 4522 | 3.06 | 175 | 1.4 | 0.6 | 2023-08-25 |  | curve
50 | 361 | 4523 | 4.26 | 175 | 1.79 | 0.6
51 | 361 | 4524 | 3.06 | 175 | 1.4 | 0.1 | 2023-08-21 |  | curve
52 | 361 | 4525 | 2.22 | 175 | 0.93 | 0.6
53 | 361 | 4526 | 7.72 | 175 | 3.24 | 0.6 | 2023-08-24
54 | 361 | 4527 | 7.72 | 175 | 3.24 | 0.6 | 2023-08-24
55 | 361 | 4528 | 3.06 | 175 | 1.4 | 0.6 | 2023-08-24 |  | curve
56 | 361 | 4529 | 1.82 | 175 | 0.76 | 0.6
57 | 361
58 | 361
59 | 361
60 | 361
61 | 361
62 | 361
63 | 361
64 | 361
65 | 361
66 | 361
67 | 361
68 | 361
69 | 361
70 | 361
71 | 361
72 | 361
73 | 361
74 | 361
75 | 361
76 | 361
77 | 361
78 | 361
79 | 361
80 | 361
81 | 361
82 | 361
83 | 361
84 | 361
85 | 361
86 | 361
87 | 361
88 | 361
89 | 361
90 | 361
91 | 361
92 | 361
93 | 361
94 | 361
95 | 361
96 | 361
97 | 361
98 | 361
99 | 361
100 | 361
101 | 361
102 | 361
|  | Total | Total Dwg | Produced | Delivered
|  | 47 | 47 | 33 | 6
|  | DASCO (Castle Hill) |  |  |  |  | area=2512 | 6.661%
[7 empty] | panels=522 | 6.322%
|  | Status | Incomplete |  |  |  | delivery | 12.77%
|  | Contracted Sq m | 2512
|  | Produced Sq m | 167.32
|  | Total Sq m | 238.52
$/m2
Sales Price
Labour
Transport
Note on C5: Marcel senior. Nassar: spandrel
Note on C7: Marcel senior. Nassar: spandrel
Note on C8: Marcel senior. Nassar: spandrel is green
Note on C10: Marcel senior. Nassar: panel on slab orange
Note on I10: Marcel senior. Nassar: delivered but not installed Yet
Note on C11: Marcel senior. Nassar: U-shaped panel is blue
Note on I11: Marcel senior. Nassar: delivered but not installed Yet