## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP - Great South Rd - Stormwater | itp |  |  |  | Yes | ITP - Great South Rd - Stormwater | 05807317-f0cd-462e-a864-954933b6cc25
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | c5067ef9-be49-5a79-92a1-ceeee44ba2bc |  | note | H
label | 2ffd7ec4-51d7-5836-937c-1b1f48c7cf99 |  | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | c897153d-3e20-56b4-b00a-3a2aa4366bf1 |  | note | Frequency - Prior to any construction commencing
label | 7c0586ca-bcc1-5e35-a926-1ada4f4ae046 |  | note | Inspection / Test Method - Document Review
label | 07ee5ce3-fa36-5895-a0c4-13526372519e |  | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | 818477f9-b7ef-5bf3-82e0-2f18bd392ccf |  | note | Records - Permit attached or permit number noted.
label | 614964fc-9fec-5611-9e11-c3f3d9ce38eb |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1 - Permits & Services
label | e768d2f5-be32-5796-8ba3-6930dcc6a04d |  | note | H
label | d4d0fb19-39f2-572b-8ca9-d2c48cdf3e5b |  | note | Detail - Locate and mark out all existing services
label | 48577eec-90fb-5f64-a9df-53d2bb0bfeb9 |  | note | Frequency - Prior to any construction commencing
label | f9fb7307-b688-5628-864d-1539fd007296 |  | note | Conformance Criteria - B4u dig procedure - follow utility protocols
label | 28003981-50d7-5c89-92e0-6fc1c324ac13 |  | note | Records - B4u dig plans & GPR report attached
label | 97ac85ea-91b2-590c-9800-6aed7fcee3ad |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | dde33f81-d3af-5e52-8a9f-4b61ed6fc250 |  | note | H
label | 1a09703d-d5fe-5ba9-9ffc-5086329b9bfd |  | note | Detail - Sub-Contract and Supplier Agreements
label | 32c5e375-395e-5efc-be29-45f7ccc4efa1 |  | note | Frequency - Prior to commencement.
label | 4672cb3c-d671-51da-9e4c-a3b2af35cd24 |  | note | Inspection / Test Method - Document Review
label | cd9fb1f8-2cb8-5f3c-b00d-8f864b7bff52 |  | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | 3bcf88f4-25b1-5b10-810a-944ca3938682 |  | note | Records - Subcontract and Supplier Agreements
label | 4fae1e9a-b41b-5ce4-974a-a8f5a378042a |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | f082222d-5835-5420-802b-c7dd1885cd63 |  | note | H
label | 44353dc3-21b0-518f-8c3b-e5c580bcb30d |  | note | Detail - Design is approved and Drawings are of the latest revision.
label | 7a25c8c3-d1f1-5631-9ac6-129a63641c4a |  | note | Frequency - Prior to commencement.
label | 4fd3888f-5c8e-58a6-83a1-9ded22ecc6d3 |  | note | Inspection / Test Method - Document Review
label | 382a5edc-2366-552b-ab6b-b3f124b7b7f2 |  | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 975b859f-b781-53a6-bd62-3b80c5e3ef4b |  | note | Records - Drawing Register.
label | f403a5d0-4741-5c62-94bc-139d384ea9f2 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Survey Setout
label | edf07bee-a88d-5d61-9a9e-ee8b122392f5 |  | note | H
label | ffd16b89-d8b9-5cec-b0a2-77cba2fbba28 |  | note | Detail - Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | 77679b99-ea02-5bb1-947a-a957d3d8a591 |  | note | Frequency - Prior to commencement.
label | 228f07eb-668d-5900-9f2b-0e2f8269e29c |  | note | Inspection / Test Method - Survey
label | 49a191f7-1759-578e-8324-903fe5f6b90a |  | note | Conformance Criteria - As per Blue Barn Consulting Engineering Drawings: 02188-T-400 & Setout files
label | 9c3da98d-cada-5584-bc9b-0fb9f4544783 |  | note | Records - Survey Receipt.
label | df3e730a-6b26-5098-8194-318605999820 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Pipe and Manhole Material Compliance
label | 69661c04-8a6e-58f2-876e-767664fb8e04 |  | note | H
label | 7134b16e-b8ef-5df3-9ef7-df58ed42254a |  | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | e7f4f295-66fd-50e8-bec3-03415e211cdc |  | note | Frequency - Prior to commencement.
label | 1097a9d7-e792-5049-aa61-2943e4e8f931 |  | note | Inspection / Test Method - Document Review, Visual Inspection
label | fd5e43f3-ddff-5533-a485-d4411a6fffe8 |  | note | Conformance Criteria - Pipe shall be Check for freshyly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | e451caf7-9551-517a-8956-2a572c0a9afb |  | note | Records - Manufacturers Data Sheets, Delivery Dockets
label | 4bf4cd33-d85a-5393-ad57-842a735c4ac1 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | 20693165-ce62-5855-bc20-cd68d4b57623 |  | note | H
label | 97bc53d2-73b5-5d94-b4ee-af6847eb748a |  | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | 93b16d05-e8d2-5216-98ea-cdf30a5da039 |  | note | Frequency - Prior to commencement.
label | 8066038a-a288-555c-911a-37f089c12d67 |  | note | Inspection / Test Method - Potholing / Survey
label | fd82a11c-713f-54dc-b708-c64179cee1b4 |  | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | 388445bd-bcd1-58a1-b3ac-ddef13e714ba |  | note | Records - As-built Drawings. Doc. Review
label | 7baeecc1-a789-535f-9164-e7f56a22ad05 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | 44f570d5-b629-5d24-8418-735f7f9d3b16 |  | note | H
label | 27122c98-abf2-5937-a2ec-d4991db8d8b4 |  | note | Detail - Excavation methodology
label | 57dc1a0d-8220-5441-9e0b-7ff352dac274 |  | note | Frequency - Daily
label | f3314c42-e56b-544c-8fb1-3effb17182b8 |  | note | Inspection / Test Method - Prestart review
label | 9f57b1f2-b199-57e3-93fc-93ee3e1daaab |  | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | c6a81bf5-bd15-5640-8f42-15fc2b84dd08 |  | note | Records - Prestart RCP
label | 803118b8-a15b-5cfa-ad7e-99c0a70b01fd |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1 - Trenching & Excavation
label | 3468451a-5fe5-506e-adc8-8dabc2768145 |  | note | M
label | 68f11d91-a23d-5dbc-ad1d-c4d70d1e0cf3 |  | note | Detail - Trench Profile - Width
label | 114892fd-2c23-502e-af87-c201aa042481 |  | note | Frequency - Daily / as trenching takes place. Different depth methodology
label | cd64d331-5b33-5427-bc2e-a738b6fae867 |  | note | Inspection / Test Method - Visual Inspection, Excavation methdology
label | 845026d6-5b84-5ce1-985c-f78a97d5b0f7 |  | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | 69197fd4-b089-5c2a-9b7d-60c142b3dd2e |  | note | Records - Construction Photos
label | be8016ea-e976-5303-a5cb-5fc6826a4a86 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 7.2 - Trenching & Excavation
label | 39b5ff3f-04ce-59e6-9202-b26acfc65cc2 |  | note | W
label | a486e986-602a-56d2-8d92-8a9c8345159a |  | note | Detail - Trench Profile - Depth
label | 79afbf11-3792-5514-aad4-ab8df1b3d05e |  | note | Frequency - Daily / as trenching takes place.
label | b0f5bd33-e839-5b35-a23a-8469f37d0b8f |  | note | Inspection / Test Method - Visual Inspection, Measurement
label | 55dd8611-a385-58c1-8fbf-edbb884978b6 |  | note | Conformance Criteria - Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | 0fe3b387-2cb2-5967-bb82-fb3c56f1dd0a |  | note | Records - FH Drainage Line Record / Construction Photos
label | 2158225e-641b-5323-a0dc-eb3a4ddaa41a |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | f93d3666-f1d4-569e-bbec-23db491d2827 |  | note | W
label | 6b4a9c33-3d6e-5db0-bb7f-4c0dffee211d |  | note | Detail - Placing and compaction of Bedding Material.
label | 260a51d5-89d9-5c63-b376-961e627b7466 |  | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
label | a5b5aef7-d4b3-5b11-84a9-38f7186fc623 |  | note | Inspection / Test Method - Visual Inspection
label | 8dcbc703-1afe-54a5-ab9c-8a79946abc93 |  | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | a8030bfa-964d-5121-8a3a-824074d1460b |  | note | Records - FH Drainage Line Record / Construction Photos
label | 233fd5f2-ae70-52a6-a219-4b8ced80ee1d |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 9 - Pipe Position Tolerance
label | 3e6b3e88-6d1e-5ded-ae76-7077132c51d9 |  | note | M
label | ff0c3c0e-1db4-5686-bb07-f8d84bb55ec1 |  | note | Frequency - At any point of pipe
label | eb5fa07b-83cc-5234-a87e-4ccaa14464e8 |  | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
label | cd57e1f6-4447-5f5f-9698-caa98fcce5ac |  | note | Records - FH Drainage Line Record, Survey Data.
label | 66064578-149d-5290-a1bf-0c7be22e5566 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 10 - Trench Backfill - Placing & Compacting
label | 664dd556-4acc-59d6-b31a-9bed92493af2 |  | note | M
label | f5aa13e0-6080-5e88-9435-91fed1c9e735 |  | note | Detail - Placing and compacting of Trench Backfill Material
label | 7ea5bad9-82b7-5ec7-b311-ca234096d086 |  | note | Frequency - Throughout Trench Backfilling operation.
label | 097d9da1-bc58-5e1c-877e-9c8a174416ee |  | note | Inspection / Test Method - Visual Inspection
label | a8f7a827-9968-5ec4-9aaa-cd7cc9c483a3 |  | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | 30ddc257-3a79-5374-9bbc-b13d70422d8c |  | note | Records - Construction Photos
label | 8b666aa4-e984-511b-b8eb-d80d7014b38c |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 11 - As-Built Drawings
label | dbb16b58-9546-5e87-8e26-60f8859157a0 |  | note | W
label | 255ed7d8-2093-56d6-abce-be23dc107bb4 |  | note | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
label | 8c89e7a7-3dca-5a43-857c-cbd34ab4d171 |  | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | eb1e678e-36c0-56e6-89b9-799924a8c756 |  | note | Inspection / Test Method - Drawings / Visual Inspection
label | 3f7b8500-c4cf-5d37-beef-f44ef1f54620 |  | note | Conformance Criteria - As Built and GIS Data
label | a54c8491-54f4-5661-89ba-ee7fc2380c47 |  | note | Records - Redline As-Built Drawings, scanned as .pdf files.
label | c8de229d-5177-5e67-acfb-549b8fb25fd5 |  | note | FH Initials - Site Engineer
checklist-flat |  |  | checklist | ITP - Willcott Street - Stormwater Drainage | itp |  |  |  | Yes | ITP - Willcott Street - Stormwater Drainage | 0938e20a-9b2e-4040-bebe-b54f8425f7e1
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | 9e1b1722-24ed-5f27-b99b-25ef6b7d34a5 |  | note | Inspection / Test Point - Permits & Services
label | bc7b8882-9ddb-55da-a406-be570fce41a4 |  | note | H
label | f7a337c2-b95a-5abd-9871-31fa3bc01c01 |  | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | e6df2b6d-2d68-5088-be5d-1e6047df8d39 |  | note | Frequency - Prior to any construction commencing
label | 6aa57308-ec1a-5d14-a816-f8e9ceffcdd4 |  | note | Inspection / Test Method - Document Review
label | c04286aa-1155-56cd-a13b-d4f8d746435b |  | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | 12eb20fe-6195-5b30-9bb0-60224ebe5d3b |  | note | Records - Permit attached or permit number noted.
label | be77751a-f2c8-5e4d-9aec-8bd8c68f8c40 |  | note | FH Initials - Site Engineer
label | d004627d-f6d1-5531-965f-efd5f4363c30 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 8f8ff762-8413-5e4d-be38-ea0e0fc0a3cf |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | c14d64d0-ddf8-52da-9bfa-d4ad7e234f19 |  | note | Inspection / Test Point - Permits & Services
label | e9a9c2ed-ac14-5c1b-a0e3-b42a0cd36a1a |  | note | H
label | 68abfa43-3bc7-540c-a9ce-720b66b808a5 |  | note | Detail - Locate and mark out all existing services
label | c16acfe2-f079-5cec-8023-8a17e59e9b14 |  | note | Frequency - Prior to any construction commencing
label | 899f65bc-4998-5bf3-a736-0cf6121eef44 |  | note | Inspection / Test Method -
label | f207972e-91a1-5ff2-9395-d455576263f1 |  | note | Conformance Criteria - B4u dig procedure - follow utility protocols
label | 573758af-4f73-54dc-b60c-4fb6635d750b |  | note | Records - B4u dig plans & GPR report attached
label | 4c6bccfd-a55f-5fd7-bacb-7779663cd2cb |  | note | FH Initials - Site Engineer
label | 6edffc4a-4c84-5ded-a983-d6aa8a135a1f |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | ad022c03-8347-5e72-94c4-05d8de1aeedc |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | adb38019-075f-5de3-af01-c036a7565b3e |  | note | Inspection / Test Point - Pre-Construction Sign Offs
label | 2c351b6c-2d9d-57a2-864f-a068eb358f58 |  | note | H
label | 3cf7088f-c1d1-5c62-91fc-ea6a220174d0 |  | note | Detail - Sub-Contract and Supplier Agreements
label | e5d922de-aba2-54d2-8fb1-c42bfc47ab15 |  | note | Frequency - Prior to commencement.
label | fd120b66-40e5-5847-81d6-028403edc031 |  | note | Inspection / Test Method - Document Review
label | ff5c9f64-4be3-53bf-83c0-f34a4b420159 |  | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | fccf0371-fcb5-5e06-8716-12b16370689c |  | note | Records - Subcontract and Supplier Agreements
label | 21a1de00-0bb4-5db4-a3c4-63586e11d99a |  | note | FH Initials - Site Engineer
label | 80f3d2eb-4852-5f10-970d-3c4d4793a622 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 98db86b0-e9c7-5e15-865a-f9f49baa5814 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | de2654f3-9828-5f58-877f-123abd60fa54 |  | note | Inspection / Test Point - Design
label | 3b1eeb65-7d27-5354-a139-0602d1f0a93a |  | note | H
label | c808960b-8a13-57d4-84f7-38573a545de5 |  | note | Detail - Design is approved and Drawings are of the latest revision.
label | de8c7b82-260f-5c8d-b2c1-05351205b8f4 |  | note | Frequency - Prior to commencement.
label | 79151b19-21ad-54e7-aeba-b9374768cfce |  | note | Inspection / Test Method - Document Review
label | 2e3f7b10-cb2d-5863-b74e-96e6aa3e7fc4 |  | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 9b21d522-91dc-5b43-8e3a-07a9f4c455de |  | note | Records - Drawing Register.
label | 452c6809-38ac-5337-8ba9-082d9dd22e80 |  | note | FH Initials - Site Engineer
label | cb74b01c-c04b-51ed-8911-b942ddbb4ace |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Engineers Rep.
text | 37a8ed8c-7867-5435-b0ba-0b9603f5e060 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Survey Setout
label | 7bff0a75-9c58-54c8-a9bb-004d7028c3f9 |  | note | Inspection / Test Point - Survey Setout
label | 7497921f-b1eb-590a-97f1-5c381f5fe365 |  | note | H
label | 994188ae-3c79-5b2b-a456-772eaf66b90c |  | note | Detail - Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | 36f4eba3-a495-5b0d-9759-ced13ff5d439 |  | note | Frequency - Prior to commencement.
label | f0047127-6078-5ec9-af65-e8158f54a961 |  | note | Inspection / Test Method - Survey
label | 39294bfc-8d20-5e2f-a398-ecddeaf14e1f |  | note | Conformance Criteria - As per Blue Barn Consulting Engineering Drawings: 02088.02-T-700 & Setout files
label | 5910ddc3-66bd-5a23-9243-ec4b68fd5175 |  | note | Records - Survey Receipt.
label | 6904b18f-28dd-5ada-9586-eb35cb389e83 |  | note | FH Initials - Site Engineer
label | 4cea45a0-0b26-5ee7-bd98-cb5f4be04b0e |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 84364298-f737-591d-a8e4-d203a0334180 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Pipe and Manhole Material Compliance
label | b0db6b6b-31e5-5aa7-8d8f-977fd256bddc |  | note | Inspection / Test Point - Pipe and Manhole Material Compliance
label | 74c5ea15-c65d-58e4-b882-0d0e12cc7fa2 |  | note | H
label | df9b84a8-41a1-518f-b677-7d76f8822085 |  | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | aee9cee3-3300-568b-8ab3-55c8823085e9 |  | note | Frequency - Prior to commencement.
label | a9f5da16-6260-5ebd-8a78-8e85934997c2 |  | note | Inspection / Test Method - Document Review, Visual Inspection
label | edd01d42-aca4-5ab1-aa86-a0097c8668ca |  | note | Conformance Criteria - Pipe shall be Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | cfebb0cb-33c4-5bff-ab21-5da568141b64 |  | note | Records - Manufacturers Data Sheets, Delivery Dockets
label | fddab239-2cff-5a91-b76f-1b7b7862026b |  | note | FH Initials - Site Engineer
label | 4db5a58e-63c6-50d3-9d84-f73c1965c8c6 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 7a9f285f-9b51-59c0-95af-aae7a3cfb98f |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | 0c68d250-088c-5a3a-9eb5-9febd73f9442 |  | note | Inspection / Test Point - Locate Existing Services by Hand Digging / Hydro Vac
label | b3feb558-013c-5357-af5e-4edb543208db |  | note | H
label | c7e28837-8ce8-56b8-88f7-23469c0de7ca |  | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | 54d159e8-2c47-5df1-aa74-71737121d72b |  | note | Frequency - Prior to commencement.
label | 999ac2d1-39f5-5d1d-98e8-4e54e5e285cf |  | note | Inspection / Test Method - Potholing / Survey
label | ba4e9290-12b3-5406-8b94-eb4d19e6d374 |  | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | 3c6ea454-6cb3-536f-af9d-215e34806586 |  | note | Records - As-built Drawings. Doc. Review
label | 14795dc3-c4e9-5345-befd-48c994b3882d |  | note | FH Initials - Site Engineer
label | 37f4944a-d285-5078-a72e-966506de9ba9 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 219fa8e5-7cdc-52b1-956c-de6c3e7ed603 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | e2600ae5-de24-5694-be2b-f7db8320a162 |  | note | Inspection / Test Point - Trenching & Excavation
label | 1b2295d3-56db-50c9-890c-b8df90039216 |  | note | H
label | bfc006ef-5652-5c26-8bdb-219920a00324 |  | note | Detail - Excavation methodology
label | 747002bf-f984-5059-96f4-d08564263abc |  | note | Frequency - Daily
label | 2eb5a53c-2f08-579f-ad6a-a99372538be0 |  | note | Inspection / Test Method - Prestart review
label | d6f773f0-90d7-5952-897d-02fa9a687ad0 |  | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | 0901d3dc-cadf-5243-afad-39d52c74ba3a |  | note | Records - Prestart RCP
label | b86fcab1-c562-518b-9e99-a66f2932a4c5 |  | note | FH Initials - Site Engineer
label | 201a30ac-25ac-5031-92e6-ebe95ddc76c2 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 2f73a44a-8708-5cec-aacf-1afec37ac514 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | cb62c4d4-1e8f-5293-ac55-d08cb2be1d3b |  | note | Inspection / Test Point - Trenching & Excavation
label | bd525f13-8654-58dd-bd9f-0ae22ec1f07b |  | note | M
label | af259e3a-746c-5cf6-8238-6e1a32647943 |  | note | Detail - Trench Profile - Width
label | acd705ad-6c22-50c3-87a8-bf41ed3133da |  | note | Frequency - Daily / as trenching takes place. Different depth methodology
label | 2275def1-fd64-5353-b640-c4c8cb6bdb76 |  | note | Inspection / Test Method - Visual Inspection, Excavation methodology
label | fc632835-60b8-5b11-917b-5ee784f2dcdb |  | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | 63c9b7e2-1b7e-534a-818f-057b03e6c56c |  | note | Records - Construction Photos
label | 270e581d-5a83-5614-b42d-3f846062410f |  | note | FH Initials - Site Engineer
label | f031ede9-f427-5e7c-bb4b-7d66ef3679c6 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 51dcf10a-ff44-5b2e-908d-fb0808aaccab |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | a08e2d36-92f8-5899-bd1c-b8d889837605 |  | note | Inspection / Test Point - Trenching & Excavation
label | f4ae7d03-c3a6-5281-aef6-dbb0a4b71f6f |  | note | W
label | 141a230e-cc34-5719-a166-9e5b9b3e867e |  | note | Detail - Trench Profile - Depth
label | f71e327d-dfd8-5c87-be68-d91016412e6f |  | note | Frequency - Daily / as trenching takes place.
label | 5fe27610-b649-5819-9a7f-d8231de1e6e1 |  | note | Inspection / Test Method - Visual Inspection, Measurement
label | 82ff9485-590d-542a-b2d1-bcd1af06761d |  | note | Conformance Criteria - Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | b4eb2a39-8c5a-5047-918c-6552079ed09e |  | note | Records - FH Drainage Line Record / Construction Photos
label | 6df3d911-8acc-58aa-891c-81d5882e7330 |  | note | FH Initials - Site Engineer
label | cf1e5fd4-8f1f-5b89-9367-1bf45236776d |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 51394ecd-a31e-5397-a377-82eacc1816f3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | 4c7c9272-eff1-5acd-84f8-db1fab8aa947 |  | note | Inspection / Test Point - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | bec162cc-0751-5cc4-9a68-73544d33bcc5 |  | note | W
label | 08e29c25-23bc-5a28-b4fe-15d8db09fd0e |  | note | Detail - Placing and compaction of Bedding Material.
label | 9caeaa7a-6924-514e-bb7e-b48fae0192cd |  | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
label | fad4dd50-05b1-5e65-8a6a-03cff0ce3c1b |  | note | Inspection / Test Method - Visual Inspection
label | 9c61de39-e419-5b43-b15e-c63285d694c0 |  | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | cc8471da-0b39-5a48-9cbb-e6b865962cd9 |  | note | Records - FH Drainage Line Record / Construction Photos
label | 9c7e7d83-9d37-5045-abf9-76ef3b218022 |  | note | FH Initials - Site Engineer
label | ea341e16-e689-524e-9ee3-d148e6d9c1e7 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | c5ce94ea-1031-5502-be30-2351bfe6dbc2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9 - Pipe Position Tolerance
label | b61c7a2f-5e32-5665-a911-198f7876c31c |  | note | Inspection / Test Point - Pipe Position Tolerance
label | 59498faa-a625-542c-a08b-7999ccfc363a |  | note | M
label | 717d24a3-77f6-5200-82a1-38fb4590ff17 |  | note | Detail -
label | c9f1f96c-ecc1-5387-99d9-eea95beea3c9 |  | note | Frequency - At any point of pipe
label | ec66905c-a760-5dd5-b416-f21827fe73be |  | note | Inspection / Test Method -
label | 097d8156-ada1-5903-aa8a-b0bc46549e5e |  | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
label | fb66ddee-e05d-509f-9951-e324590582ca |  | note | Records - FH Drainage Line Record, Survey Data.
label | c065e9fb-4d58-5379-b3ef-f0fac625ea4e |  | note | FH Initials - Site Engineer
label | 9ba6e7f1-eb57-5d12-9e8a-3fa7546d954c |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | e44ff11b-93f4-5ae2-8932-568bd3c2a0d1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10 - Trench Backfill - Placing & Compacting
label | 40279805-6db7-558b-863b-ef9ff4807984 |  | note | Inspection / Test Point - Trench Backfill - Placing & Compacting
label | 28595c35-e900-552b-bb71-190d647a3cf2 |  | note | M
label | 40e557b8-18cf-5ab7-8215-e6b0c59d89ab |  | note | Detail - Placing and compacting of Trench Backfill Material
label | 14c863ca-20ae-5c90-a282-1175340623e7 |  | note | Frequency - Throughout Trench Backfilling operation.
label | 956d83d2-e052-55c1-94e4-61f78de3f3d9 |  | note | Inspection / Test Method - Visual Inspection
label | 4b6d1b6a-11a8-5690-b01e-ba1c0b22f868 |  | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | e6f2295b-f1f5-5ded-a024-7e33dbea923d |  | note | Records - Construction Photos
label | eec58562-4eb4-5641-b724-d5fa69f0d3b4 |  | note | FH Initials - Site Engineer
label | 89f7a92a-0c58-541d-afa9-c7bf46340bc6 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 4a8196d3-f32e-5db3-8bda-6e9fb553b082 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 11 - As-Built Drawings
label | 153b3e07-d166-5b34-a090-21110f60896e |  | note | Inspection / Test Point - As-Built Drawings
label | 75b4f9ea-538c-5de6-9ee1-4b2de7e14a36 |  | note | W
label | 52200537-2aaf-531c-a32f-8f9b37561499 |  | note | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
label | a81ed0ad-6591-5a50-be47-28b2ac0ca206 |  | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | b3b19c22-5a72-550b-9173-c2c2052da737 |  | note | Inspection / Test Method - Drawings / Visual Inspection
label | a9eea2b3-842f-597a-8211-9519159d5d31 |  | note | Conformance Criteria - As Built and GIS Data
label | 421920d2-fbd9-5925-bf08-538ecd381de0 |  | note | Records - Redline As-Built Drawings, scanned as .pdf files.
label | 73de1352-3324-53da-9686-5b8e70c52ae6 |  | note | FH Initials - Site Engineer
label | d8de9881-1747-55dc-b4a5-5a662376d800 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Engineers Rep.
text | 03acaf1e-aca5-53c9-ba08-f3cc9a2968ea |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
text | 0c7fc7e2-33a0-5e85-9157-9b8548fa270c |  | textbox | QA checked By Quality Manager:
text | 5399ef2b-ceae-536f-b388-2c123bfdd8ae |  | textbox | Accepted By Engineers Rep:
checklist-sectioned |  |  | checklist | Drainage - Pipeline Installation - |  |  |  |  | Yes | Rogan Arunel - ITP - Enabling Works | 0aa34d49-8c64-43e0-8c3b-b526b2b13b1e
checkpoint-group |  |  | section | Pre Start & Area Acceptance
checkpoint-status |  |  | checkpoint | Latest consented drawings available, checked and referenced
text | becbf563-65cf-4d00-b2a6-e5a2cf94db78 |  | textbox | Relevant drawings & revisions for reference:
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Work area acceptable & approval to start work
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-group |  |  | section | Pipeline Installation
checkpoint-status |  |  | checkpoint | Setout Completed checked and accurate
checkpoint-status |  |  | checkpoint | Excavation Accurate - Location & Depth
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status |  |  | checkpoint | Bedding depth and material correct
checkpoint-status |  |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
holdpoint |  |  | signoff | Connections to manholes complete and approved
checkpoint-status |  |  | checkpoint | Air Test Complete (Sewer Only)
checkpoint-status |  |  | checkpoint | All Pipe install elements completed - Install Completed
checkpoint-group |  |  | section | Review & Handover
checkpoint-status |  |  | checkpoint | All Pipe Install works completed, checked and reviewed as per specification
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Area left clean & tidy
holdpoint |  |  | signoff | Raise Remedial / Request Review
checklist-sectioned |  |  | checklist | Pavement Construction |  |  |  |  | Yes | Halsey/Maich RAB - ITP - Pavement Construction | 0af5a3e1-3f76-4dc6-8b71-0b7d947a7748
checkpoint-group |  |  | section | Precom
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | ecd89b00-4258-5b71-8262-de5a7a11b732 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 89f7c429-787b-529b-b516-68d4685338b6 |  | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | 6a049b6f-a861-51b0-a1d5-082c8104cf57 |  | note | Frequency - Prior to any construction commencing
label | 5eb00e2a-a594-59fe-98ec-d91d2a28a15c |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 132ed97c-0c7f-54b3-a567-457ba9bdef0c |  | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | 09a3e30b-af06-5f19-b908-e05aebee5f59 |  | note | Records - Permit attached or permit number noted.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1 - Permits & Services (2)
label | f8c3108d-82cf-5ea7-a5fa-b7eb8dba6b28 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 60f1fe91-c3c9-578e-b814-bbe7d3723942 |  | note | Detail - Locate and mark out all existing services
label | 7227d345-7188-57df-bc7f-0c1aa0d5372b |  | note | Frequency - Prior to any construction commencing
label | 8ce0d899-3f46-5ec1-b531-23fbff7bc0e5 |  | note | Conformance Criteria - B4u dig procedure - follow utility protocols
label | 119b52a2-b0f2-5fa6-b0a1-023af403f48a |  | note | Records - B4u dig plans
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1 - Permits & Services (3)
label | 8c1b576b-1742-5f4a-8342-d615cb93eab4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2ff1f7b4-659f-5974-b2eb-0e6a9a585386 |  | note | Detail - Approved TMP
label | fd95ff3c-f793-588f-99af-cc473453ee01 |  | note | Frequency - Prior to any construction commencing
label | cf401228-b2fa-5c8b-867f-698320fd5948 |  | note | Conformance Criteria - Approved TMP and WAP onsite befor establishing traffic management
label | 0095a760-371c-5569-ba08-434880334fa2 |  | note | Records - TMP Plans
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | fa37090f-4999-520d-b7a3-65f1a1ee0af7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 12645261-e6d0-5885-90d2-4babb2e96cb8 |  | note | Detail - Sub-Contract and Supplier Agreements
label | a72d48a1-8d3f-5065-819c-c75e6fa5a4db |  | note | Frequency - Prior to commencement.
label | c666234b-668e-5a0c-a2a4-f445909d7936 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 93873cdb-82ea-5dbc-b118-0f45e7cd629e |  | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | 2424981f-fcc6-55ee-b9a6-c80cd77ef7da |  | note | Records - Subcontract and Supplier Agreements
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 8a2d55d2-8f7c-5292-b1e1-edf13b544dcd |  | note | ACTION (Hold, Monitor, Witness) - H
label | feabdd99-cd5c-5366-86c6-41df5fc750c2 |  | note | Detail - Design is approved and Drawings are of the latest revision.
label | 52a22fe0-934f-54bb-83a3-5929561712db |  | note | Frequency - Prior to commencement.
label | 3b65d6ff-a7fd-5a07-9553-6cdcf158451d |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 6fa45ab1-58d2-58bc-ab30-9c27a54de2e1 |  | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision.
label | 3201c9c3-bc7e-543d-8f91-c1dabc852cf7 |  | note | • Drawings to be 'ISSUED FOR CONSTRUCTION' status.
label | b434b04d-c8f6-595b-ae6e-a3f8def0acbe |  | note | • HOLD POINT of not issued to IFC.
label | 4509afa4-38da-5287-aed4-3855ffe07ad5 |  | note | Records - Drawing Register.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | SAC Pavement & Surfacing
checkpoint-status |  |  | checkpoint | 4 - Bitumen
label | 68f75255-0d13-5747-9629-e30c1ba6d645 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 066a918b-77a0-5390-9b41-ada03261d9ac |  | note | Detail - NZTA M/1
label | 9b25ff1e-7cbf-5116-a9be-aaaa8ca2f0d4 |  | note | Frequency - Passing all tests listed in Table 1 of NZTA M/1
label | b0ad2cad-3d53-5ebb-9e10-7540742609eb |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
label | 807f1016-43d9-53e6-b894-49d6874ef469 |  | note | Conformance Criteria - Passing all tests listed in Table 1 of NZTA M/1
label | 08cfd5f7-84c5-5625-a287-6854e7fb8fa0 |  | note | Records - IANZ Lab results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Asphalt Mix Design
label | 40a889a4-777a-51e1-bd81-2d80d14dfc7f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 10392982-aa0f-504c-8d62-39be0a0d03ac |  | note | Detail - JMF approved
label | 2b37eb51-1733-562b-8850-c2119663f3e1 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
label | 86c4c883-9754-585b-8ef0-3e08bc77cabb |  | note | Conformance Criteria - AUSTROADS
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Production Tests
label | cf88b822-b2ac-5f0e-a602-a5cbe44e1ab7 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 79c0d356-76d1-5f19-8788-b7cd3ada535e |  | note | Detail - NAS 2004 & TNZ sup to NAS 2006, TNZ P/9P (M/10 Table 5.1)/
label | fc951b28-ec63-5739-8dde-9c2cdb6d5af8 |  | note | Frequency - 1 set every 300t
label | 89418e5b-f53a-5ab7-bb1d-7f60f1c45396 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
label | e4f2a371-3132-5a41-a9aa-70ec96b79b7e |  | note | Conformance Criteria - NAS 2004 & TNZ sup to NAS 2006 TNZ P/9P or NZTA M/10 - Grading, Binder content, Max Density, Temprature
label | 8f4335ac-765c-5a53-b4a3-07fd618c4a00 |  | note | Records - IANZ Lab results
checkpoint-status |  |  | checkpoint | 7 - Check Weather Reports
label | 303dea3f-dd3c-58d4-88e1-b79462edcb54 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5a783ae4-516f-5cbe-81fe-448a95066d9b |  | note | Detail - No fog, rain or wet surface. Base temp greater or equal to 7 deg celcius
label | 3b55cffe-b45a-52df-b6d7-f26ffe1241cf |  | note | Frequency - Weather call the day before
label | 2e20e834-f7b6-5f9b-a33f-94164d643675 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual
label | 0705ea3d-ad5f-5a5d-8fde-f93b7098c50a |  | note | Conformance Criteria - Forecast and thermometer
label | 2c58e189-522a-5d93-82c0-862ef5b7fb53 |  | note | Records - Radar and Asphalt QA
checkpoint-status |  |  | checkpoint | 8 - Pre-Seal Inspection
label | db2c46e4-c016-53f3-b542-5d0c57a21106 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 479bf882-888c-59e1-a7c1-0ceee5dee59e |  | note | Detail - Surface finish
label | 16b70717-7336-5094-a2e6-2e5017d49c7e |  | note | Frequency - Continuous
label | 1176ec81-9d72-5642-ac96-ed5429836803 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual
label | dd285702-4bc3-5e08-a4b5-acb9658a83ec |  | note | Conformance Criteria - The surface must be clear of deleterious material and not chocked with fines. The basecourse surface must present a stone mosaic surface with larger aggregates protruding and not appear damp
label | 077d3198-2c5c-5ca2-856a-fe70d9d6eca4 |  | note | Records - Sealing QA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Tack Coat
label | f3084355-a482-58c2-bdaf-84ba853e7c02 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 90981153-416d-56d0-bfdc-04575ce2206a |  | note | Detail - Minimum residual binder application of 0.3l/m2
label | 3acc4ddd-f6ff-5743-a5c4-d5eb7e1d21d3 |  | note | Frequency - Each Run
label | 5a317f83-05b0-5896-ace1-d79c5b61a7e5 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing & Visual
label | 5eb5c51f-1116-5acd-a7b9-4f9bc6282fef |  | note | Conformance Criteria - Each spray of bitumen
label | 8bdb78aa-cc2d-531a-9c1a-0738c3e87ff9 |  | note | Records - Asphalt QA
checkpoint-status |  |  | checkpoint | 10 - Construct 50MM PMB AC14
label | 028a7cdc-2879-514f-9ea5-99b74ae8aae8 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 449cbcdd-b61e-52f0-bc60-4c8bd169109d |  | note | Detail - NZTA M/10, NDM and Stringline
label | eff235db-54f4-5629-8c87-ce8ee5693035 |  | note | Frequency - Each Run
label | 6877ed8c-4bf4-581e-a736-8ef2f86cf6d7 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing & Visual
label | 77381468-7fc4-5646-9539-911fb28762ff |  | note | Conformance Criteria - Construct 50mm PMB AC14 . - Design air voids 4% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
label | 7222640f-9a28-5b3c-952c-21422266c868 |  | note | Records - Asphalt QA
checkpoint-status |  |  | checkpoint | 11 - Construct 50MM HF AC14
label | 79e01922-37e4-5b3e-8253-4b972bcc232f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 6436c7eb-389e-5574-9996-0b8ca5d7201c |  | note | Detail - NZTA M/10, NDM and Stringline
label | 5eb44a66-c1d2-5b68-9357-93cf82bbf0a7 |  | note | Frequency - Each Run
label | c67fdcda-cddd-5db5-8518-9884a3bc7796 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual
label | f49d3a47-5d40-57d2-911d-37179193716f |  | note | Conformance Criteria - Construct 50mm PMB AC14 in 1layer
label | d6a63263-deae-5902-89aa-8115ce73768d |  | note | Records - Asphalt QA
checkpoint-status |  |  | checkpoint | 16 - Construct 80MM AC 20
label | 994c74f1-7d49-5914-8a30-9fb8bde6ac46 |  | note | ACTION (Hold, Monitor, Witness) - M
label | eb194b36-5944-595b-af77-9375dc739b7f |  | note | Detail - NZTA M/10, NDM and Stringline
label | ca6ec17a-234c-520b-8b98-342522e49581 |  | note | Frequency - Each Run
label | 762b3fa3-84ae-5a0e-9cb7-1a71853f8e39 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing & Visual
label | c76815e6-90da-52e1-a96e-7e016880f1ff |  | note | Conformance Criteria - Construct 80 MM AC20. - Design air voids 4% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
label | e6fa1d9f-040d-5fb7-8567-74f2391082a9 |  | note | Records - Asphalt QA
checkpoint-status |  |  | checkpoint | 17 - Surface Finish
label | 41637f97-2803-5167-9dd1-487bdf64affa |  | note | ACTION (Hold, Monitor, Witness) - W
label | 36901ebc-187a-5fd3-8dd0-07a43a5d4dd1 |  | note | Detail - TNZ P/9P
label | bd9396ba-c1bf-52a3-8a3d-85a2831fae8f |  | note | Frequency - Each Lot
label | da637903-4ba4-5056-9a07-6da8a9d1dab9 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual
label | e0cfd3d5-0cbd-54eb-befb-02432151ec71 |  | note | Conformance Criteria - Inspection: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate
label | 7c555031-ac4f-56fa-a48b-53c935299afc |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 18 - Reinstatement of Linemarking and RRPM's
label | 05a805c0-b782-514f-8e1e-605d100202d3 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 50799c3b-0a6e-58d8-8617-77115be01371 |  | note | Detail - NZTA M7 approved (Class B or C as required for anticipated traffic level)
label | 3b5a9a0d-75dc-57b2-99ad-babb08d7a929 |  | note | Frequency - Every site
label | 5699909c-d446-56ec-919a-6f727909e454 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual
label | e1dee3b5-170a-59a2-840d-777788379d90 |  | note | Conformance Criteria - Carried out within 12 hours of each shift completed and as per the existing markings
label | 78d4663d-ad3c-537a-8d30-336e457e8b08 |  | note | • Suitable Traffic Control to remain in place until pavement markings have been reinstated
label | 912ff5a7-f070-5c76-a08f-110c67ff9da4 |  | note | Records - Photos
checklist-sectioned |  |  | checklist | ITP - Motatau - Enabling Works - Footpath, Kerb and channel | itp |  |  |  | Yes | ITP - Motatau - Enabling Works - Footpath, Kerb and channel | 0b0ce88c-8bab-4293-adf8-2c22de0a6f78
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | b377bbe4-1ee8-5eb6-ab3c-205dd0796142 |  | note | VERIFICATION ACTIVITY - Surveyor
label | 308766d9-ca1c-5e7c-9816-f93d0afd4c1e |  | note | METHODS OR REFERENCE - Surveyor
label | bb7e148f-be2b-5479-b917-fd4bb50856ab |  | note | FREQUENCY - Everysite
label | fc7ecbb7-b9d0-5e64-a049-c1365b120a30 |  | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | 2383df50-53ba-5a50-953b-72cacea43cc9 |  | note | Mandatory HOLD POINT -
label | 543d658e-5384-5c8f-9e02-0097b4cea8a2 |  | note | Records - Onsite records/photos
label | 9aec90fd-c4fe-5af8-9ad1-c9098247dcee |  | note | Onsite Responsibility - Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Kerb & Channel
label | d34ff5f9-e226-5051-b97c-9ba6c8479f11 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 8bb928a6-d5b3-5cd8-96ac-cab585777b30 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | f752e9ae-58b4-5a46-b5af-b6020cce9228 |  | note | FREQUENCY - Everysite
label | 20166a57-eb46-5064-bdc2-b4bedcf590ce |  | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
label | 64f71289-335d-509e-8d97-b3a1cf7bfcc6 |  | note | In Process Inspection
label | f1c973f8-ba81-533b-864b-118f8fa8d6f0 |  | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
label | 43fa1f31-be3c-5b02-818b-14e09869272a |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Channel Level
label | 754a1258-81ed-5cb8-a092-bffe15405670 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 7e4ef6e8-e31c-568b-8ba7-f21f3ea64339 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | 1d23ad8c-6458-53db-9ccd-28bb1d084c31 |  | note | FREQUENCY - Everysite
label | 1566ff77-a5a5-56d7-8df8-002a4378bd33 |  | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | 1b3b6b2b-5d74-5b38-b957-07decf75ac5c |  | note | In Process Inspection
label | 2e6294fe-523d-5b8c-a3b3-08214c098fd4 |  | note | Records - FH concrete QA sheet
label | 9da16371-6826-52e5-9bc3-5751a3f7885a |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | CIVIL WORKS
checkpoint-status |  |  | checkpoint | 4 - Concrete Footpaths
label | 1fc25aef-45dd-5ab4-82f8-df31d09dc5d6 |  | note | VERIFICATION ACTIVITY - QA FORM
label | c34dbe4b-b211-5358-9f8e-5e380759664e |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
label | 84965f98-e752-542a-ba5c-21d6e109e047 |  | note | FREQUENCY - 10m Intervals
label | 2dc56669-6c77-54d0-864b-07a91e9b5ae9 |  | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 15 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
label | 92bed86c-4a2c-5e24-a8a8-d0299d74402a |  | note | In Process Inspection
label | dccb1358-e16c-5f18-83a9-027fc0adf27f |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | d8e35bdc-2d87-5c90-8b07-d33bb0ee4aea |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 -
label | 8da034d9-102c-5ce8-8493-873d5abc22e9 |  | note | VERIFICATION ACTIVITY -
label | f539d8f7-3f85-59bf-b84b-d1989fbbf679 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
label | bf7eac0a-96f6-516f-8e32-ef682384ef7a |  | note | FREQUENCY - Each PX
label | 4da1a97d-c24c-5d4e-b13d-aac396817f5f |  | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
label | 87b9d5dd-e4e3-597c-9f43-6e41dfc4cf90 |  | note | In Process Inspection, Measurement
label | b23bcc1f-4473-5bd1-a1af-9425dd2c7b42 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 35399437-f256-59ef-a706-b99eef92430d |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6 - Tactiles
label | e9a3e3a9-84b3-50ed-9e58-17dfba5be1dd |  | note | VERIFICATION ACTIVITY - Visual
label | 421276ff-4d6e-528d-b371-be5a73c38114 |  | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | f8302dff-b509-54c8-94b6-6f3c59017f73 |  | note | FREQUENCY - Everysite
label | c35678ab-dfc0-5743-881e-54a63b81fb17 |  | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | c23caff3-c4c0-5403-bcce-3390707d837f |  | note | In Process Inspection
label | 93e7e4d5-8394-55f2-b88e-bb5969f31250 |  | note | Records - Photos
label | 18fd543a-c4b0-5b90-92ee-e43139129ea6 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6.1
label | 75101633-9f5b-5f46-bda8-77ba0535712c |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 6875bdf5-12e1-5b80-909f-af78408d8748 |  | note | FREQUENCY - Everysite
label | e0d16ca4-aebe-5da8-b62e-59e0267d95c8 |  | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | 4d988dd7-5dca-587f-8d35-f6d81dd3330e |  | note | In Process Inspection
label | bcdaaf4a-5a6d-5e2e-bec6-25b66f08ef92 |  | note | Records - Photos
label | 8284e885-e0fa-58bc-8424-3b7f1df5fb57 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6.2 -
label | bf090a04-a7cb-5a69-a837-8b38c29bafda |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | fa56cfaa-9056-5a89-b921-a3c44bac908e |  | note | FREQUENCY - Everysite
label | dfc6f2f6-53c6-527d-b255-9d9224b4b9d0 |  | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | 785a813a-e0ce-5a25-a64f-26fb4e16d895 |  | note | In Process Inspection
label | 77a6e76e-bdce-5c8c-8e08-78a626847f68 |  | note | Records - Photos
label | b9347766-9233-5b7c-8240-e61aa340c94e |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | RAMM DATA
checkpoint-status |  |  | checkpoint | 7 - As built information
label | d3b20655-5388-5e4f-b885-6b11a4862ee4 |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | 11df1193-ef13-5d9e-b16d-39f78c05fc81 |  | note | FREQUENCY - Every Site
label | af13b132-00ae-5025-9ea5-0d948f70cc24 |  | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
label | b2f70539-e287-5e2d-a9bc-043d749a65cc |  | note | In Process Inspection
label | 2926804d-9776-5509-a0bf-7bfc9cfcd008 |  | note | Records - Asbuilt records
label | 5b68a23e-5e94-50d3-90a4-619860afe7b7 |  | note | Onsite Responsibility - Supervisor and Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 01553db6-4b5d-54aa-9914-30f60a4a7e59 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 7868b7ef-a43f-5546-b34a-0ebfbbf7c9d2 |  | textbox | Print Name:
text | 5fc66f33-411c-5880-88c1-644ddf5fbeb9 |  | textbox | Position:
text | c97a6e8c-0ef0-51b6-ba7c-373105f6ea19 |  | textbox | Date:
checklist-sectioned |  |  | checklist | Vehicle Crossings | itp |  |  |  | Yes | ITP - Griffen Park / Hillsborough Rd - Vehicle Crossings | 0b7de203-9895-4a01-9343-9f03cc04f07c
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | af67e904-1238-54a1-ae49-f4867c4d37a4 |  | note | Verification Activity - Surveyor
label | f2e73f34-fd1d-545d-a897-54e81048ab18 |  | note | Methods Or Reference - Surveyor
label | 12889f6b-0b3f-56a0-8741-8624fb40d738 |  | note | Frequency - Every Site
label | d7ac1cec-3747-5a45-9399-6fb3a4730dd5 |  | note | Acceptance Criteria - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like
label | 5c577395-adcf-5aed-9129-0e2bd1582c1f |  | note | Mandatory HOLD POINT -
label | 583cf055-2635-55c0-8bb7-5a898e1dad82 |  | note | Records - Survey Receipt
label | f041df5d-62c7-5d6a-a732-a1dafc56730e |  | note | Onsite Responsibility - Site Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Channel Level
label | f2b12434-e847-528a-ba16-2ab57e09e0aa |  | note | Verification Activity - QA FORM
label | a9aa1a43-599e-5fab-bf4d-2b8ed5ae774f |  | note | Methods Or Reference - TDM Technical Standards - VX0000
label | 1304c3c4-001a-530b-8bdc-e337fcdfac30 |  | note | Frequency - Every site
label | 696c545f-c1f2-56d3-96ca-0795e007a017 |  | note | Acceptance Criteria - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | 010dbbbb-f733-534e-90d8-0722fbe3a835 |  | note | Hold Point - In Process Inspection
label | b4c1101a-1a22-56cc-8703-0604fafbb66d |  | note | Records - FH concrete QA sheet
label | a2e93316-edac-53b3-b182-64c60e29a6d2 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Mesh & Steel
label | 0aa932e3-3f36-56de-9d4f-726daaa6422b |  | note | Verification Activity - QA FORM
label | b50007c6-ba7a-5108-adea-ba7289c68e6d |  | note | Methods Or Reference - TDM Technical Standards - VX0000
label | 23353034-23f6-58eb-b660-d4d38ab10631 |  | note | Frequency - Every site
label | 1387b935-54bf-55bf-a428-c3e9df5245ce |  | note | Acceptance Criteria - 661 Mesh and/or D12 Bars to be installed if 4> dwellings or commercial crossing
label | ef213588-dcf9-5f2a-a05c-302b82620e3f |  | note | Hold Point - Mandatory HOLD POINT -
label | 0a96cd9e-51d3-5b47-b4b4-606629696dd3 |  | note | Records - FH concrete QA sheet Photos
label | b91b322e-203c-5e27-93b8-0aed65b8d590 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 4a - Vehicle Crossing
label | b518d751-d7bf-5abc-9b2d-fbd51e4126e8 |  | note | Verification Activity - QA FORM
label | e915adfe-2508-5351-ab14-ba0a1a87f3e7 |  | note | Methods Or Reference - TDM Technical Standards - VX103
label | 8d79b3d7-da5a-5139-8796-a1e628d1ee30 |  | note | Frequency - Each VX
label | 376fd68a-e857-5d0c-993b-321637bd47ff |  | note | Acceptance Criteria - Subgrade -(CBR > 3) Base course - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 black oxide Exposed Finish
label | 7bbc2501-4d87-5f80-99fa-f74728c7e0d3 |  | note | Hold Point - In Process Inspection
label | 78082180-491f-596d-8345-62d0b405b665 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 8241a504-acd3-5528-93e9-392b3dc949dc |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4b - Commercial Crossing
label | ed62018e-c48b-5034-8ea8-e2b00c5ca58d |  | note | Verification Activity - QA FORM
label | ce868024-6dff-5927-a117-d9a360a970de |  | note | Methods Or Reference - TDM Technical Standards - VX0202
label | 1f6003d8-8254-5b4b-9b40-9e94fe123e4f |  | note | Frequency - Each VX
label | ad7e8893-59ec-5a97-92a5-ec1b10a42f11 |  | note | Acceptance Criteria - Subgrade -(CBR > 3) Base course - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 200mm and 20 MPa @ 28 days. 4kg/m3 black oxide Exposed Finish
label | 502f9d67-5977-5de6-b079-bc806bba367f |  | note | Hold Point - In Process Inspection
label | e0a59f75-47a6-51ef-aa30-25378f63e6fd |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | c0a47870-c702-513d-996e-4d873479cb3f |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Grass Berms
label | a85a5388-cd4a-5a7c-9561-b193fe0a2c3b |  | note | Verification Activity - Visual
label | 242b7ad1-301e-5d8a-b3c8-3a7cab642af8 |  | note | Methods Or Reference - ATCOP Section 12 Footpaths and Pedestrian Facilities
label | f3861b2a-0a39-5347-b0cc-067be61abb7d |  | note | Frequency - 10m Intervals
label | 6c38db2a-35bc-5d2f-abe7-5053f7cd73f0 |  | note | Acceptance Criteria - 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | 5769288c-b21f-5e8d-8a7e-02135b6f798b |  | note | Hold Point - In Process Inspection
label | e325eb99-fdd0-55a3-b7d1-7461493810dc |  | note | Records - Photos
label | 2e278576-c454-5a6f-9991-aa8899e8e38a |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | As Builts
checkpoint-status |  |  | checkpoint | 6 - As built information
label | c16bc260-e4e2-5a07-8910-688fe1792331 |  | note | Verification Activity - RAMM DATA SHEET
label | d2677c0f-ce22-54b7-99ef-d5e4f492004d |  | note | Methods Or Reference -
label | 7976a2c5-16a3-5c4b-a11c-f8e031af4ee1 |  | note | Frequency - Every Site
label | 20c10e26-532f-5904-8c97-f96d076a7a89 |  | note | Acceptance Criteria - As built drawings and Ramm Sheets Completed
label | b1b3ef4b-495d-5e0c-9af5-e8a036855444 |  | note | Hold Point - In Process Inspection
label | d842274f-b913-5585-8716-f426e22da32f |  | note | Records - As Built records
label | 493fdebb-7170-5548-af55-ffb8fd471ea3 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | f90d2067-54b5-5992-9c3b-6e4bd97228a7 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 60375904-1289-599d-a109-e941b0aa8e93 |  | textbox | Print Name:
text | 7499af58-b1e1-5840-a6d5-292a13d97374 |  | textbox | Position:
text | 9563a6e2-e91a-5d07-874c-273094bab3e5 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP - Enabling Works - Footpath, Kerb and channel and VX | itp |  |  |  | Yes | Triangle/Mokora - Enabling Works - Footpath, Kerb and channel and VX | 0dc1a437-30aa-4e0d-90f4-e306d6b6b684
checkpoint-group |  |  | section | Kerb and channel
checkpoint-status |  |  | checkpoint | 1 - Kerb & Channel
label | 02ed84c5-ff9f-5c9e-8714-622f44356f51 |  | note | VERIFICATION ACTIVITY - QA FORM
label | ae9dd399-3abf-5e6e-9bd1-ba33615b41f5 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001 Type of Kerb used as per Design drawings
label | 21f79190-0314-5c81-bd40-80bf0ed6bede |  | note | FREQUENCY - Every 10m for clegg Two point per 20m stretch for scalar where widening is occurring
label | 0e71126f-54ea-5257-a9c3-43a3ff8e04a1 |  | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
label | 721ed329-4576-5d97-9633-981580701eca |  | note | Hold Point - Inprocess Inspection
label | b652d509-c20d-5d47-abda-0df07b5f3682 |  | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
label | b821541d-f3cd-5049-8fbb-fcab11c667af |  | note | Onsite Responsibility - Site Engineer
label | 69c137f2-39f0-5740-9e85-f2ac81319445 |  | note | Designers comment - - Kerb height across the length pedestrian croswalk reduced to 75mm. - Kerb height reduces to 120mm along south side over the extent of existing culvert. - TDM KC0001 there is criteria for undercut if CBR <5. So CBR testing should be included in ITP. Please state frequency and minimum tests. - include ITP for Kassle kerb installation
label | b845ca0d-b740-57bb-b608-5ec1aa9cad71 |  | note | FH Comment - Noted on levels however this subject to site out information/walkover. The CBR testing has been added however please note that achieving CBR >5 on K&C is very unlikely and most likely designer needs to provide undercut detail
checkpoint-status |  |  | checkpoint | 2 - Channel Level
label | 6594b7e5-b363-5b5a-a4c0-3ed09900820e |  | note | VERIFICATION ACTIVITY - QA FORM
label | db64d69d-ccb5-5b36-a1da-395cc8f43287 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | cd3217ee-5e58-5f2d-abea-640455ac2930 |  | note | FREQUENCY - Every Site
label | 32ec4184-6115-5359-a48b-a17ac9ffd00c |  | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | 1b804106-44d1-5991-8473-7fd21acde6e1 |  | note | Hold Point - Inprocess Inspection
label | 507c6dd5-0c5c-5f71-8c37-9b00dc895b77 |  | note | Records - FH concrete QA sheet
label | c94bf256-ab39-54c7-906d-f41dc31d7996 |  | note | Onsite Responsibility - Site Engineer
label | 6f994013-06a8-58d9-8b4e-26b2b6b3c025 |  | note | Designers comment - Channel longfall to be as per IFC long section
label | 2430914e-a199-5066-8221-a5cee30169f5 |  | note | FH Comment - Noted
checkpoint-group |  |  | section | Footpath
checkpoint-status |  |  | checkpoint | 3 - Concrete Footpaths
label | 0cb55b7c-1b91-5343-905b-20ed18138f76 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 899fa758-d3f5-570f-adc8-adb5700f4a87 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
label | 28ba7025-0b46-5451-a956-9bb0214fa7fc |  | note | FREQUENCY - 5m Intervals - Eastern/Western 5m intervals - Southern
label | fa2f453a-93dc-57f1-9636-1c340c832463 |  | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Basecourse - 100mm min. thickness Clegg CIV > 12 Surfacing - Concrete 100mm and 20 Mpa @ 28 days. 4kg/m3 blackoxide with broom finish
label | 2d1c59f4-960e-5a8b-89b0-bf0d35e0a76f |  | note | Hold Point - Inprocess Inspection
label | 5408ebef-c145-56f7-ba01-92b4e90fbe3f |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 8aa1c1f5-56f6-5a47-95ab-59bcfe61a82c |  | note | Onsite Responsibility - Site Engineer, Engineer Rep/ MSQA
label | 361d4c82-5282-5c43-abda-773cef4c1f45 |  | note | Designers comment - 10m is okay for southern side, for eastern and western side reduce frequency of clegg it to 3-4m. Specify saw cut interval and depth of sawcut. Include prepore inspection as hold point
label | 2d4b4ff9-024d-55ab-b83b-aaef0fafe1fd |  | note | FH Comment - 5m for Easter/Western. Sawcut every 3m or more frequent at any service cover obstruction
checkpoint-status |  |  | checkpoint | 4 - Concrete Vehicle Crossings (VX)
label | a8a8cfd7-a658-57c4-aff3-6d07a8b6ad2b |  | note | VERIFICATION ACTIVITY - QA FORM
label | 9826d1c3-5347-597a-b516-3d99ba519d4c |  | note | METHODS OR REFERENCE - TDM Technical Standards - VX01202
label | 5af7a04e-f7cf-53dc-b9c1-f724b39a7d15 |  | note | FREQUENCY - At Least 4 clegg each crossing - one in each corner.
label | 94dbd622-55f5-5e9d-84bd-94923c677c75 |  | note | ACCEPTANCE CRITERIA - Subgrade - (CBR > 3) Basecourse - 100mm min. GAP40 thickness Clegg CIV > 12 Surfacing - Concrete 150mm and 20 Mpa @ 28 days. Oxide and finish as directed by engineer
label | e63175c1-ae6e-5496-9b3c-ea3fa4ba98d7 |  | note | Hold Point - Inprocess Inspection
label | fdf9a13a-4e91-5c91-9fad-4617007b4801 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 583c51d6-7780-5816-a9ef-f86df10d71e3 |  | note | Onsite Responsibility - Site Engineer
label | 2043663c-968e-595b-a8a2-0a0dfcd59c76 |  | note | Designers comment - frequency- At Least 4 clegg each crossing - one in each corner.
label | 78ccd57c-8fda-5b8a-be7c-67251a385e78 |  | note | FH Comment - Noted
checkpoint-status |  |  | checkpoint | 5 - Grass Berms
label | 899e02c9-a3c4-5880-9efa-3adc5ef2a967 |  | note | VERIFICATION ACTIVITY - Visual
label | 598b7140-a82e-5e08-8004-319fa2426c78 |  | note | METHODS OR REFERENCE - ATCOP Section 12 Footpaths and Pedestrian Facilities
label | 15c3c7a8-7498-526e-897d-ba92f2076fd2 |  | note | FREQUENCY - 10m Intervals
label | bb56568d-61e3-50cc-aaa9-2f20093b66e0 |  | note | ACCEPTANCE CRITERIA - 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | 270ef202-2f8b-5eb0-b0ec-5308a32332e0 |  | note | Hold Point - Inprocess Inspection
label | 2a284281-d48c-5935-b776-f336ad90bedd |  | note | Records - Photos
label | d084fd00-5622-5372-a0e6-879898cd7697 |  | note | Onsite Responsibility - Site Engineer
label | 4a5f2b31-1c13-516b-bc8d-b3986c0c986d |  | note | Designers comment - Change to TDM reference
label | 4f0379d1-c564-5af2-b20c-2d2a0df11b74 |  | note | FH Comment - Please provide TDM reference
checkpoint-status |  |  | checkpoint | 6 - Service Covers and Street Furniture
label | 63208345-5c8d-51d0-9e3a-35f7b68f0ee4 |  | note | VERIFICATION ACTIVITY - Visual
label | d6033dd8-04af-5b98-ab62-b2c0bc43484e |  | note | METHODS OR REFERENCE - AT Contract Specification 14000
label | 907108ee-032b-5a5b-8ad7-29035d3fda8c |  | note | FREQUENCY - Every Site
label | d7f21633-2cb8-54ef-9344-b725c0331410 |  | note | ACCEPTANCE CRITERIA - Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
label | 63415d13-ded7-558c-a676-cd3c909eefad |  | note | Hold Point - Inprocess Inspection
label | 7a1cd11b-d34b-562a-8aa8-fdeef8f5441e |  | note | Records - Nil
label | 3b7cd785-bfd3-5aaa-916b-578e4fb09913 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 7 - Tactiles /Pram crossing
label | 3eea9f33-6f6b-5ef6-823f-9045f9883254 |  | note | VERIFICATION ACTIVITY - Visual
label | 332b8abb-75f9-5713-9d24-e423dce0ad87 |  | note | METHODS OR REFERENCE - As per Design Plan
label | d2a592be-8149-544e-a1a8-2630bea7412f |  | note | FREQUENCY - Every Site
label | 52f653fb-356b-5d5b-b449-9fd9d7e6052a |  | note | ACCEPTANCE CRITERIA - Foreman to set out tactiles and agree location with ATOC and Engineer prior to concreting
label | 335b9dc4-10bb-5c4f-b2ee-499a2ad79e66 |  | note | Hold Point - Inprocess Inspection
label | f37a354a-1525-5dc0-a922-7b7a38f3ab32 |  | note | Records - Photos
label | 1452fac5-92af-52b9-ba44-1f6dd0ebe3e8 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 7.1 - Tactiles /Pram crossing
label | 97a1602b-7452-55f7-824f-11d0fac9ee48 |  | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | bd4f7720-6423-51c7-a139-b0a943ea4dcb |  | note | FREQUENCY - Every Site
label | d0a1bf03-c56d-53be-ab93-a71ac5e8bad1 |  | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | b5096317-dabe-51bc-a1ef-7c46b356e867 |  | note | Hold Point - Inprocess Inspection
label | ea0a6a72-9cc6-5676-a38a-0a90e671267e |  | note | Records - Photos
label | b516b6a5-97d4-5180-ac2a-8cc336b5544e |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 7.2 - Tactiles /Pram crossing
label | 4a02e45f-92ff-56b9-a98a-0e0d9c085f06 |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | bb94ad80-3e96-5911-afb8-f82acba0c586 |  | note | FREQUENCY - Every Site
label | 5cf2fd2b-8f86-546a-acfe-5e6d374a7004 |  | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | fab6bb23-7ba3-55b8-be01-b8fa7cd33213 |  | note | Hold Point - Inprocess Inspection
label | 5a6d02d4-2ad1-5343-aba7-f89a2cb69bdb |  | note | Records - Photos
label | 8d18ac8e-31ce-591e-b43a-e9d011b1207a |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 7.3 - Tactiles /Pram crossing
label | cab1e566-a994-5390-a963-67b30ec746d1 |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 8515fcf7-df20-5301-8163-2bea9ef26651 |  | note | FREQUENCY - Every Site
label | 230b7724-631c-527c-9510-3fa2f18b64de |  | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | cd0dfbb4-2dbc-58b0-a146-21b9bb703ca1 |  | note | Hold Point - Inprocess Inspection
label | 70d5113e-343e-5e58-8713-47ce2f7adf84 |  | note | Records - Photos
label | 0f649f1c-a858-56b5-bf12-6380032b890d |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 7 - As built information
label | 7e0667b5-6c93-51bc-8bd7-74a6c074ed88 |  | note | VERIFICATION ACTIVITY - Drawings
label | 115d1f91-f8ed-516f-ac88-e20cc3c58d4a |  | note | METHODS OR REFERENCE - - As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | abfa4467-be0d-5301-9e58-22bf83d1a26b |  | note | FREQUENCY - Every Site
label | 494507d0-2308-5a4c-adf6-eb5d2cbddef5 |  | note | ACCEPTANCE CRITERIA - As built drawings
label | ccd0a345-c07e-54a3-9f59-c58073d27648 |  | note | Hold Point - In Process Inspection
label | 845b7967-6019-540d-87ba-a3bcea2d428a |  | note | Records - Asbuilt records
label | 42537943-d96b-5b7d-b9fa-bc634730a732 |  | note | Onsite Responsibility - Supervisor and Engineer
label | 035a7de3-ce24-5209-8976-4dac5cbf86fa |  | note | Designers comment - - As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. - Provide a separate row for RAMM data sheets referencing the contract requirements
label | c61aa1c8-93c5-57ea-9bd5-da163e1e26ea |  | note | FH Comment - Noted
checkpoint-status |  |  | checkpoint | 7 - RAMM DATA
label | e187201c-1089-5572-8f73-ee42eac757b6 |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | 6ff99795-0430-5c04-8bff-2032e688acc0 |  | note | METHODS OR REFERENCE - - As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | df3ecc4a-fe26-5797-bd38-3f5c327d4a9c |  | note | FREQUENCY - Every Site
label | 6b99f1ea-1091-5d41-9d3c-ace31dd8e86d |  | note | ACCEPTANCE CRITERIA - RAMM SHEET
label | 840902aa-71d5-5416-8d54-9ba11fa3ad8c |  | note | Hold Point - In Process Inspection
label | ce3d5385-6afe-5709-a946-10eb7b823578 |  | note | Records - Asbuilt records
label | 97c03b7f-8195-5e2c-ae7e-f4676aaa8692 |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-flat |  |  | checklist | ITP - Motatau - Raised Pedestrian Crossing | itp |  |  |  | Yes | ITP - Motatau - Raised Pedestrian Crossing | 0f23c9f8-15f9-41a0-a1ab-04521a54f1cb
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 7b0028f9-3e88-52c6-9ff7-07dacd0ea8fb |  | note | Inspection / Test Point - Permits
label | 779a4841-5d06-5e1d-9ea4-5106b99b9bb4 |  | note | H
label | 9d885ca0-05b4-5599-a7ee-75223754da6e |  | note | Detail - Obtain Permits
label | 77a3a2fe-2aa3-511d-817d-46146158b4c0 |  | note | Frequency - As required
label | 2be1df03-1595-5220-b9cc-572acb82996a |  | note | Inspection / Test Method - Document Review
label | f20958d8-8694-5dd5-8208-3232a807bc9d |  | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 60ea0f57-c3da-5188-b6d5-b16a61ff918f |  | note | Records - Permit attached or permit number noted
label | 1a851cae-1ffd-5335-b5ca-ce2308338083 |  | note | FH Initials - Site Engineer
label | c070139d-c94b-511f-86eb-d1c8e5c1288c |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | b1f0963e-7831-551d-8e1b-87f716c57c0a |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-construction sign offs
label | 407f2b83-f048-5b75-a8b8-94a1c04cf32e |  | note | Inspection / Test Point - Pre-construction sign offs
label | 78642a49-91fe-5bd7-9186-b6bb97ac2501 |  | note | H
label | 2a6c575e-52aa-54c0-967a-6cce503b887d |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
label | a6baae4b-634c-5859-956f-335bdffba412 |  | note | Frequency - Prior to commencement
label | 74cccef6-ab2c-546d-b5df-2252526fc879 |  | note | Inspection / Test Method - Document Review
label | 70e2a45a-a7ce-5d22-b87b-edd22975ba61 |  | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
label | 89db8905-a845-5d87-acfb-c4ecc48c0fc0 |  | note | Records - Subcontract and Supplier Agreements
label | 42eac125-579e-5abd-83fa-dddb53217453 |  | note | FH Initials - Site Engineer
label | 1e7fca19-8eb6-563d-ac70-8d2fa9343bdf |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 48a16b1c-86fe-5675-a950-882fa39242dd |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1 -
label | 65926df1-2c30-52ae-9438-f71c370176fc |  | note | H
label | 325e1eea-32e3-5e5e-8e28-538fe80b815a |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | 60e1e170-7aea-59f4-b1d8-7d01c77a0b3f |  | note | Frequency - Prior to commencement
label | c58bc202-c3e1-5396-b91a-f1acf063e576 |  | note | Inspection / Test Method - Document Review
label | 7a68444f-6530-5d55-b2c8-4f780f543af8 |  | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | 75adb8ca-5d17-55e7-b240-aac2704b7dd8 |  | note | Records - TMP on MyWorksites/On Site
label | 1c0b88b7-ee0c-51e0-95f9-020282f8a6a7 |  | note | FH Initials - Site Engineer
label | 87fe1bf4-ebfb-55a9-851b-547aaa8e243a |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | f82b86ea-e9f7-57e9-af0c-c1505d07ad40 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 -
label | c37c1415-5a3f-59ed-ba80-5c081a611b02 |  | note | H
label | c604a69c-535a-56ef-a3d1-ba791a1462d4 |  | note | Detail - Ensure all Subcontractors and Suppliers go through FH induction
label | 39339d7e-da93-55af-beef-cd799c1fa305 |  | note | Frequency - On site daily
label | e9bfcd73-7050-5276-b8f9-55a5b0ca8721 |  | note | Inspection / Test Method - Induction
label | 72fe06a3-3a9e-53e3-ab2d-1e7f9672600a |  | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | 047c3a2b-c311-5a3c-9209-7f64f935bebf |  | note | Records - Hazard ID and Pre-starts to safety team
label | ce3bf458-666b-5816-a131-3811d6019f19 |  | note | FH Initials - Site Engineer
label | 1441fc49-b3d7-54ee-aca8-bfa9cf743de5 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | a492f091-740f-5dd1-a19d-f2b16cfd9fa0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 528d4ea3-eb59-512c-b03a-c8b6ebf9ba02 |  | note | Inspection / Test Point - Design
label | f4df5bbd-8a43-5516-ac8d-d99c4ac17a7a |  | note | H
label | 03732459-2203-54dc-8397-ba8ea8b3563c |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | b1a1f647-cf00-5f5c-9d7e-c274905b88a1 |  | note | Frequency - Prior to commencement
label | e3013bb4-f90e-532f-b80d-f5a64eff6793 |  | note | Inspection / Test Method - Document Review
label | f76f7085-9359-58d5-b788-742df513206d |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | 61517d27-31d1-5779-b003-8fb2d780b834 |  | note | Records - Check Drawing Register
label | 20d579b3-885a-5567-b1bf-b3ca7cb25d65 |  | note | FH Initials - Site Engineer
label | 7134e44b-03bc-5cb3-801b-dc9ce6281888 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
text | a170bb95-8e39-57ab-947c-e360512818e0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 151cdd9b-b7dd-5940-ae23-e5098ae9e8e6 |  | note | Inspection / Test Point - Design
label | 3560f4a6-df01-5b85-8e09-e86812155359 |  | note | H
label | bc757ac8-f99a-5d0f-880e-12625d015a33 |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 9b3bd54a-466a-5ba4-aaa6-7e7dd4961a0a |  | note | Frequency - Prior to commencement
label | 01c0ba29-d17d-5731-81fb-57e4e75f1d2c |  | note | Inspection / Test Method - Document Review
label | e9d32c82-5ab8-5260-bf91-c68764b701f2 |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | 24750298-2b49-503c-8ebe-2dabfaa5d0cb |  | note | Records - Check Drawing Register
label | c77c1ecb-23da-51a8-b0b7-594f0ae01be3 |  | note | FH Initials - Site Engineer
label | b3d73973-9558-59cf-86d3-f6171a7b1fde |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
text | a652c732-db4e-5922-b8e9-e039820f0aa8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1 -
label | fe2adb42-95bd-5747-8de5-ffb76d32b270 |  | note | H
label | bd83926c-8bfb-58da-afc8-ba8edf4f0641 |  | note | Detail - Crossing to comply with AT TDM chapter Traffic Calming and TDM TC0003
label | 86c14bde-f592-5cdc-81be-48924cbda74d |  | note | Frequency - Prior to commencement
label | b9ce5523-93d7-59f8-a30c-9c1060cf537e |  | note | Inspection / Test Method - Document Review
label | 8ec78370-9d4f-5b9a-a9d4-9eae2c74dd66 |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | 8a5be461-fd7c-5cdf-8ee4-6fd1dda3ee32 |  | note | Records - Check Drawing Register
label | ad92de46-38ac-5aeb-9ad8-afc4266c1263 |  | note | FH Initials - Site Engineer
label | f0044af3-5236-56af-b02b-8379c56ae6c5 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
text | 0008120a-a29b-5212-86ff-dd62f0f2ae85 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Installation of Erosion and Sediment Controls
label | b303f1f2-2998-5f22-ba19-16865a69032b |  | note | Inspection / Test Point - Installation of Erosion and Sediment Controls
label | cb9d9754-a963-560d-905e-1b3e93714df3 |  | note | H
label | c4bf12fa-254c-5aea-8bc8-008e32faa08e |  | note | Detail - Ensure that Erosion & Sediment Control in place
label | 1946020f-222a-5ecf-a450-8b1242d16bc0 |  | note | Frequency - Prior to commencement
label | ba6d9079-6dac-533d-a267-a6f21d755da9 |  | note | Inspection / Test Method - Visual Inspection
label | d53a6fa5-1a3a-5735-8773-6d087854c1e7 |  | note | Conformance Criteria - Cesspit Covered
label | 6db3cb39-4e63-5348-996f-a915442df182 |  | note | Records - Environmental Controls Audit
label | e27e41df-8892-56cb-8870-6a8aa66c54fc |  | note | FH Initials - Environmental Manager/Site Engineer
label | 19241d3d-ab31-52d4-84e2-82f49b96d52a |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 8ea0bd11-27da-5bb4-b6d6-9b0a69e1f958 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | 43df6592-f91a-58f1-82f6-13b9938c3897 |  | note | Inspection / Test Point - Survey Setout
label | 0fb802f5-9614-5f04-be5f-0a10c0318bfd |  | note | H
label | 28589810-13c3-5223-9650-2fd536cac406 |  | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | 4b96eeb5-aad0-5906-9b25-1c631192b28b |  | note | Frequency - Prior to commencement
label | 81082cc0-b4ca-5a64-9d36-b97d15748a4c |  | note | Inspection / Test Method - Survey + Smart Level
label | 5d050d99-999f-5373-9c9c-a3a87f93b408 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 8edbc766-3f7e-5134-afbd-247a99fbe083 |  | note | Records - Site Photos post surveying
label | be594eeb-4b64-50d4-997c-a6e1ffb479c3 |  | note | FH Initials - Site Engineer
label | f990ca2e-821f-509e-91ce-2abf0da248cd |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 9afa59d2-7789-5378-ace7-1ec374f7f355 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging
label | 3d4793b2-a88d-5af6-a77f-86ab740ecc39 |  | note | Inspection / Test Point - Locate Existing Services by Hand Digging
label | 7d139feb-31db-58e7-87d2-756137b7e3ce |  | note | H
label | 2ec100b2-4908-5bb8-b0aa-a057f8cc5460 |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | ee6452f0-53e3-5dee-8dee-51fd15b37763 |  | note | Frequency - Prior to commencement
label | 11598fe2-a8e5-5af0-9379-38928d55b681 |  | note | Inspection / Test Method - Potholing
label | 1eb1e037-2f0b-50dd-be29-f8e5789c1101 |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | 5c1ee194-23b2-5af7-861a-7ed3d8d16c36 |  | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
label | 70ce3867-b603-57fc-9cf4-aed9adbb2576 |  | note | FH Initials - Site Engineer
label | 161725cc-0b32-59db-a2a1-c45474a3ae00 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 2ac755d9-dc1a-5260-8f93-ddb3d8cc9a22 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Material Compliance
label | dcd177b2-9ff3-5163-bfa5-02a3c20e22c7 |  | note | Inspection / Test Point - Material Compliance
label | 444e0ec8-cdae-5814-b8c7-3e4c7590f1ba |  | note | H
label | fabd4cbd-692a-5d02-b8be-7e08d2e21d81 |  | note | Detail - LESA dowels to be used at all construction joints
label | c997abe2-7eaf-5ef7-adc3-7c7f359a5427 |  | note | Frequency - Prior to pouring concrete
label | d7b3acb3-c44f-53da-a6c3-73b6556881ae |  | note | Inspection / Test Method - Document Review
label | 41f76aef-2afb-570c-8309-2be405d733ce |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder , TDM Standards TC0003
label | 531af653-a678-5539-9d65-af84169e7c69 |  | note | Records - Delivery Dockets / Photos
label | 060677df-2fe0-5aec-880f-32f54c303597 |  | note | FH Initials - Site Engineer
label | 5af1dc6c-9cb4-51d4-9c51-0064c240217c |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | c43388a3-f145-5433-96a1-76a9df411053 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1 -
label | f56ecaee-bdfb-5841-ac25-e6eba30d4728 |  | note | Inspection / Test Point -
label | 05d1f89f-5842-5ab0-9e2c-9cdd5f024f10 |  | note | H
label | 0b9019c1-430d-547c-9d14-df63a5eb31bf |  | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
label | 6663da2c-ab9b-521b-bbd2-b53e64f58f89 |  | note | Frequency - Prior to pouring concrete
label | 79d40f8a-9a9e-52ce-b4e7-e0555d7b338e |  | note | Inspection / Test Method - Visual Inspection, Document Review
label | 80b2ede0-b184-5b9a-968c-2b0ada861c4e |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder , TDM Standards TC0003
label | 42092201-7554-5030-8ac7-4ac959cfcab8 |  | note | Records - Delivery Dockets / Photos
label | 83dd9617-0473-5da7-99eb-389d40a46a40 |  | note | FH Initials - Site Engineer
label | f4c52dce-b3e4-5372-8f80-bc92cf03dd68 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | ec7faec5-c724-5fe0-83d3-b7b9229483ce |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 -
label | 0da137b9-4a1c-5871-8e22-f2604c21346f |  | note | H
label | ba8eb469-e30a-5f10-87f3-adf945541fb3 |  | note | Detail - 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | eb122a44-4749-59cc-970f-2a08dc524009 |  | note | Frequency - Prior to pouring concrete
label | 09dd558d-919a-56db-ba6f-32beb36f2e00 |  | note | Inspection / Test Method - Visual Inspection
label | 5030378a-df49-5005-b3df-58ac9f758ade |  | note | Conformance Criteria - CIV >15
label | 91f3c11e-71de-5529-956c-d924c1cc9794 |  | note | Records - Delivery Dockets
label | 5aac750a-9762-5405-8d52-252476fef465 |  | note | FH Initials - Site Engineer
label | f76b6896-aa3c-5d74-a43d-2633e64b4b2b |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 7918ca64-8a5f-509b-b3bb-4c2e19bf1850 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3
label | 1efb58e0-5803-594d-832f-fdffe4a7e22c |  | note | H
label | edd13270-f03c-5278-bd43-53c3fa8778c7 |  | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs separating.
label | 3fa18440-a26a-59cd-a981-080a3a1a65ca |  | note | Frequency - Prior to pouring concrete
label | c992ac30-60f5-5bf1-8198-16cb3f502205 |  | note | Inspection / Test Method - Visual Inspection
label | 87207011-f40e-5b1e-bcc7-d9509f1bfaf8 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder , TDM Standards TC0003
label | 25881189-1d7d-5d0f-9a3a-6c0a928cdf3b |  | note | Records - Delivery Dockets / Photos
label | 2fbe5ae7-7721-5ad6-8037-a2857f554a21 |  | note | FH Initials -
label | 4377d169-fd95-59b2-b607-da9455bdcd52 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 24b313b5-f3b8-5fcd-98c0-2e66ccc881cd |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3
label | fef6426a-81de-5c35-9a74-a988cedb2910 |  | note | H
label | ca032549-e5a3-5a29-a74a-240a9a498cc7 |  | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs separating.
label | 00a1b008-2393-565d-b421-d5d785ca342a |  | note | Frequency - Prior to pouring concrete
label | aa611a5a-2ce3-5dad-865b-c59d08f74080 |  | note | Inspection / Test Method - Visual Inspection
label | 4c3d3890-c9a8-52b8-8272-c43803895aad |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder , TDM Standards TC0003
label | 986f8ce9-591c-5835-999c-de47c3d62753 |  | note | Records - Delivery Dockets / Photos
label | 60b5737d-ad90-5932-b4c0-c2a50fa35a1d |  | note | FH Initials -
label | da47d768-b521-51e5-9857-0359a5b68db8 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 3fcdc0d0-4b80-5f91-853d-a8e1fb83da42 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Temporary Works (Formwork)
label | 60bd759a-3919-5b5f-9a4c-a4cbfd5494ec |  | note | Inspection / Test Point - Temporary Works (Formwork)
label | 27d158e6-90dc-5bfe-ba97-84d05f0e4e91 |  | note | W
label | f1bdc64c-464d-5ded-a216-2feed55102a2 |  | note | Detail - Formwork to be set to correct line and level
label | ec5c1394-fac6-58a0-a8d4-bb06cb7e274b |  | note | Frequency - Prior to pouring concrete
label | 95d85476-ec59-5abb-bcda-d9c826294a8f |  | note | Inspection / Test Method - Visual inspection
label | 47dd4ee9-4c57-500c-9e7c-2357376de3c8 |  | note | Conformance Criteria - Concrete Inspection Record
label | 1e135c76-9b0c-58cb-9ba9-a6457de710b9 |  | note | Records - Concrete Formwork Checklist
label | d3ce7315-bb95-5d79-a842-15e24c244fff |  | note | FH Initials - Site Engineer
label | f6893d46-ccac-52f4-98f4-5c983977392f |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | 92775ebb-3437-52ce-9094-d279a35ea5a6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.1
label | b9924f3d-68d1-5d06-bb7b-e0215f0ef3fd |  | note | Inspection / Test Point -
label | cf8066a6-1fc1-5c44-9ab7-aa700d373615 |  | note | H
label | 921148c1-2bf2-5abd-8b7e-521eb10fdfa6 |  | note | Detail - Raised table formwork to be 100mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
label | fa8c73d5-956a-5571-8c2d-5157cac6e911 |  | note | Frequency - Prior to pouring concrete
label | 33591ce6-f905-5de4-b73f-845623079b49 |  | note | Inspection / Test Method - Measurement
label | fa32654b-7f5c-5db6-a42c-2a94f9a50f9f |  | note | Conformance Criteria - Designer to inspect formation level
label | fc4dd88a-d3cd-561f-b6cd-33dbc2f58d8c |  | note | Records - Site photos
label | 5f288949-8aef-541e-b11a-3aed608ed13e |  | note | FH Initials - Site Engineer
label | f190dacc-a35d-5d63-99f9-710c2651fae1 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | bf92e1c1-574a-51c6-8d1a-dc81de1921d3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2
label | 74bde3db-773e-5bc8-b2f5-07061534a3d2 |  | note | H
label | 8c4612ca-c6d5-50c7-946a-599befc41867 |  | note | Detail - Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
label | 6af6babb-347e-5d6d-ad59-b4d4e4fca80b |  | note | Frequency - Prior to pouring concrete
label | df679403-31b4-5d18-b17f-0dbecca84281 |  | note | Inspection / Test Method - Measurement
label | dd09a0ef-717b-5f91-a45f-4a9ff36d03ba |  | note | Conformance Criteria - Designer to inspect formation level
label | b16a992b-12f9-50ac-be62-927eb9d1dfe5 |  | note | Records - Site photos
label | 783f83a7-33dc-5d70-84fe-ba3172ed5961 |  | note | FH Initials - Site Engineer
label | 2bbcef77-63a7-5b95-9071-81490d6f536e |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | afd9b504-3d15-5a01-818e-1df45e61f1a2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.3
label | d056fc59-ca24-5bb6-b7fe-9f101a06df4d |  | note | H
label | 9fabc04c-83c2-5a52-adaa-8249825d5556 |  | note | Detail - Raised Table ramps to be 1m across for entry and 1m for departure ramp.Toe to be 1m across for both entry and departure.
label | d8f55c6f-1246-5e69-ac26-d15540ca63a2 |  | note | Frequency - Prior to pouring concrete
label | de444bdb-168e-5a4b-90e9-559569e4af7e |  | note | Inspection / Test Method - Measurement
label | 4394cace-1800-583d-bc40-6c978d7747e6 |  | note | Conformance Criteria - Designer to inspect formation level
label | affd67ba-9b3b-58b2-9ee8-29dd5855658e |  | note | Records - Site photos
label | 26395ba4-8d3a-53e9-bcb0-c8afb8eb3abe |  | note | FH Initials - Site Engineer
label | 66ee0879-ccdd-5870-806f-462fb412f7ad |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | 8c093768-f372-5851-9ff8-5fc1f54c8c78 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4
label | acf3b6a4-fd5c-55b6-87ce-cebd4eea3be8 |  | note | H
label | 6a7355e5-2e85-5145-a047-a3becaf596d2 |  | note | Detail - Raised Table ramps to be 1:10 gradient for ramps - As per Relative gradients provided in Construction drawing 1-A8258.07
label | 3d8fec77-6f40-564a-abc6-0bc3938eda67 |  | note | Frequency - Prior to pouring concrete
label | eade9d80-04f6-57af-8a54-3beaf0780080 |  | note | Inspection / Test Method - Measurement
label | 57b157d0-8714-55d9-bd26-75e33edaa2ff |  | note | Conformance Criteria - Designer to inspect gradient level
label | 16fe0f58-96ea-5ee8-bf7f-7201bbda62d0 |  | note | Records - Site photos / Concrete Formwork Checklist
label | b3ed132d-76b9-5306-b4d0-bf3443103152 |  | note | FH Initials - Site Engineer
label | 2ba40501-4ddb-581c-8991-b9b92ed0a514 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | 62409ff1-d603-5a7a-af34-3864f0fbe0ce |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5
label | f333a730-7a16-5767-8360-ccc162419485 |  | note | H
label | c504bf49-ba65-58bf-adb9-a64f800326cb |  | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | e137b390-2cd0-573a-bcec-bb030e53a6dd |  | note | Frequency - Prior to concrete pour
label | 05cf89cd-9bce-5275-9fe4-50f86973e6f1 |  | note | Inspection / Test Method - Visual inspection
label | f3813cb0-ecc5-54bf-9416-a895a35bf5e0 |  | note | Conformance Criteria - Concrete Inspection Record
label | d82a54fa-ed19-5cc0-9b0a-b1ed8ba1298f |  | note | Records - Concrete Formwork Checklist
label | 6f97ac8a-ee16-59e3-87b8-f27b56286dd2 |  | note | FH Initials - Site Engineer
label | 03c6a2eb-e6c8-5b06-b7e3-7d67daff3de2 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | b885a951-ae80-507d-95d8-f10813999598 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Reinforcing
label | 0dc0edad-7621-55b0-aac8-b4c11700d09f |  | note | Inspection / Test Point - Reinforcing
label | ad81cc7c-fa30-5cf7-bfa2-bf3e14bd423f |  | note | H
label | 6d5aebd3-79bc-5d95-97aa-9c4f04987227 |  | note | Detail - Construction joints on speed table to ramps are to contain 2 rows of LESA dowels or similar approved dowels . Dominator dowell system 50mm w/ Black 300*50*6mm plates @600 centres placed across the construction joint and for joints from ramps to toe slab @400mm centers
label | 20d845d3-2145-5ad7-82af-e5f3b0ad1a97 |  | note | Frequency - Prior to pouring concrete
label | 3d40cb4e-d15a-58b8-b1fd-81c9cca0e1b2 |  | note | Inspection / Test Method - Measurement
label | 6d10c05f-f6e4-5c65-b897-3b447213e04d |  | note | Conformance Criteria - Concrete Inspection Record
label | 0983b670-5972-5fb0-88cb-cf1082e0f5f6 |  | note | Records - Site photos/Concrete Formwork Checklist
label | e06c5097-9c85-5a9e-88f9-f0ebfb6f0282 |  | note | FH Initials - Site Engineer
label | 7a77ca76-b03b-577a-9735-97a3b0975e68 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | 863fb193-3818-534f-b62f-cca1b3b2840c |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Concreting
label | 412c4ca3-591b-516c-aef2-d14a5051d233 |  | note | Inspection / Test Point - Concreting
label | 600cd65b-5875-5473-9a1d-399167244e02 |  | note | H
label | 5884a2df-bb68-5c07-84cf-0e3e95782ad7 |  | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | 6d12c41c-ef8c-5564-b19e-ef92dd30f6c9 |  | note | Frequency - Prior to concrete pour
label | 201679b4-ae96-5815-82ce-9a04e8afb7d0 |  | note | Inspection / Test Method - Visual inspection
label | 3e9f2e75-627e-5384-9e85-9ae609902fd6 |  | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | 9e644737-b7c8-56f9-9c3b-aa0db27dfb21 |  | note | Records - Email / SMS
label | 1d4218d3-96ea-578a-8823-985050e3cea3 |  | note | FH Initials - Site Engineer
label | 882fc9a3-e619-5ac8-82ac-a3904d67634b |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | dca7f290-3232-59ad-b1e7-63c33505ac1d |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1
label | 9550175d-307f-5ee6-8902-f502cc72e3fe |  | note | Inspection / Test Point -
label | 6b352042-c179-55c8-bb6f-41769a53acfa |  | note | W
label | 1d6044b7-8439-5af1-9746-e77fc6911f48 |  | note | Detail - Vibrator to be used throughout concrete pour
label | bb4b9913-6606-5a69-8bd0-680430d2302c |  | note | Frequency - When pouring concrete
label | 1a3d39d2-a0ca-5797-ad99-966ad5a49e01 |  | note | Inspection / Test Method - Visual Inspection
label | cc46ad92-fe6f-55b8-8a4c-43c4cefa8c17 |  | note | Conformance Criteria - Concrete Inspection Record
label | b331fb4b-4287-5fd1-9f72-c5c4e388264b |  | note | Records - Concrete Formwork Checklist
label | 5a5d79d3-7d51-5485-b1c7-de934ef9094b |  | note | FH Initials - Site Engineer
label | 40c39c98-f973-5aed-9847-96e7229285fc |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 1ff04f3b-c77c-5470-8cc8-7b35f75816e0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10.2 -
label | 2cac6664-c634-5a44-ab5e-4fcaa8f123f9 |  | note | Inspection / Test Point -
label | d3242fe3-638b-5c5c-a1b8-968bfa1d9cc4 |  | note | H
label | 323c7d64-4a9b-54d9-88a3-95b8daacc33d |  | note | Detail - Concrete ramps surfaces shall be U5 broomed finish and speed table top exposed finish
label | 7ef7b2e9-35da-539d-8fed-1e4fd1f525df |  | note | Frequency - At completion of pour
label | 4b74c89b-4e84-55ed-af68-613579a34ab7 |  | note | Inspection / Test Method - Visual inspection
label | 6d731f1d-5571-5dd2-b89a-9cf193528ca5 |  | note | Conformance Criteria - Concrete Inspection Record
label | 98b23739-5375-52d1-96d0-c406aaa3b3d3 |  | note | Records - Concrete Formwork Checklist
label | 6e309454-545f-583c-8bd2-d3f4ae5674fe |  | note | FH Initials - Site Engineer
label | add512aa-3b7e-5744-9332-0fdbc3efa48a |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | db400842-8465-5d49-9b35-4eb884eab220 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Curing
label | 35ca422c-e3ec-5418-9e4d-ec95fe0c7783 |  | note | Inspection / Test Point - Curing
label | f8522d1e-9451-556f-a8d3-d78680e90a51 |  | note | M
label | 1bd7692b-9ea9-5d8e-8cd0-e743952bdba4 |  | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | 5196e70c-5421-56bd-945b-e0a4048ef8ee |  | note | Frequency - Post Pour
label | bc536d69-9a57-5ba5-bfa0-e253edc82859 |  | note | Inspection / Test Method - Monitoring the time allowed for curing
label | feb36d07-a3a6-55b0-bc1d-d8d0b2899c06 |  | note | Conformance Criteria - 48 hours minimum have passed
label | 3835f72c-04d3-5498-898e-ac061ac5203a |  | note | Records - Concrete Formwork Checklist
label | 0b4ef566-21ca-51dc-be0c-5f275458d466 |  | note | FH Initials - Site Engineer
label | f81834d6-ae7c-5ce2-a5cc-3d0e8fc835bb |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | ada61b36-7f6c-554f-b443-9730384d918a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 12 - Remove formwork
label | 8aa4d09b-987b-5d6d-b848-73e8015edbf2 |  | note | Inspection / Test Point - Remove formwork
label | 46397704-591c-5446-bfea-43d0972aa1ba |  | note | W
label | 7d9e5ca1-17e4-5635-8cb6-ae7923bffe3a |  | note | Detail - Remove formwork after 48 hours
label | 18127f48-dc3f-5edb-99b9-b2ecd6aa549b |  | note | Frequency - Post Curing
label | 85de1519-2ea7-5079-aaa0-1d7170eab871 |  | note | Inspection / Test Method - Visual inspection
label | b3913e40-4c8e-59e9-99e4-8c1ad41f743e |  | note | Conformance Criteria - Concrete Inspection Record
label | b45544b5-1a8c-5506-9ffd-2813c11b6384 |  | note | Records - Concrete Formwork Checklist
label | aea86b7c-c9e0-557a-935a-4c2081bf5131 |  | note | FH Initials - Site Engineer
label | cf5867c6-0874-5f6e-975e-f47368e755b8 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | fa8163f4-8480-51d8-ac41-a43dfa00a711 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
label | caeb0207-c280-5dfc-a568-a07a47889e24 |  | note | Inspection / Test Point - Asphalt- Concrete extension slab/ Toe
label | d90b40ba-4cf1-5d9e-97a5-5fdee49ecc3a |  | note | H
label | 4cdfc0ff-67dc-5041-9b23-044e5b40b715 |  | note | Detail - One row of Lesa diamond placed mid depth @400 C/C along construction joint placed at 75mm as per TDM TC0010
label | 3c02342a-7b8a-5307-89c7-6059162eb47c |  | note | Frequency - Prior to pouring concrete
label | e009f36e-a9dd-53c6-97c0-c916261791fb |  | note | Inspection / Test Method - Measurement
label | 9d6528be-9920-5663-aed4-7d05e26860f6 |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | a6a46e30-b715-5c6b-97db-c83c93e7f459 |  | note | Records - Site photos,delivery dockets
label | bcbe936b-9fb5-565c-aa9b-16b26eae5d08 |  | note | FH Initials - Site Engineer
label | 55fb5ff3-52cd-50f6-b97d-7104134dd93b |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 3015ef1f-2fb5-5baa-b92e-016c01c428eb |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.1 -
label | 920575b3-3f27-53d6-b0b2-d510a04aeb44 |  | note | H
label | c5b2e95f-dfd0-5159-978d-89dcdc1ac8ac |  | note | Detail - 250mm thick 40Mpa Concrete and 4kg/m3 Black Oxide with one layer of 663 mesh
label | d2d39d4f-7844-5ec3-95f9-05bf171196ee |  | note | Frequency - Prior to pouring concrete
label | 058e3602-90ff-5947-9190-de24d1ed325f |  | note | Inspection / Test Method - Measurement
label | 231d11c1-2358-5a31-8f92-ad11e8220a9b |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 98f1c7d5-b006-564c-9d9f-54b09cb11396 |  | note | Records - Site photos,delivery dockets
label | 8f1fb4f2-6913-55a8-9fe6-bf78b5f447d3 |  | note | FH Initials - Site Engineer
label | 573f7281-8d47-572b-ba95-ac05967eeca2 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 0ee28acb-5fad-5e7b-8b72-a31627958c2e |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.1 -
label | 261545a1-b6d0-5d1a-8073-054ecd0f74bb |  | note | W
label | 1a780835-a7dd-59e1-a3bc-11441c4c2891 |  | note | Detail - Ramp to have relative gradients as per Construction Drawing 1-A8258.07
label | 8370fa5a-a3ce-5e80-a371-7e7392439ff5 |  | note | Frequency - Post Curing
label | 4b54a290-a0d9-5c5d-8f08-a309113d88cc |  | note | Inspection / Test Method - Visual inspection
label | 4e9c4670-8296-50a4-86da-928d77534d42 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 96756de8-88f4-575f-8a6c-2de5a3270d98 |  | note | Records - Site photos
label | a1e48776-d1f8-51b1-bc73-a707cf5b3b2b |  | note | FH Initials - Site Engineer
label | 569aca92-803e-5ae8-9fe0-ccdd0dfb7d4e |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 5b76cacc-7c20-59ff-af3c-ed7e8d317aae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 13.1 -
label | 7cf7c597-6e88-5da6-a214-e9093b93d50e |  | note | W
label | c98d5799-3994-5665-a5e9-8796605ef962 |  | note | Detail - 50mm thick AC14 and 4kg/m3 Black Oxide
label | c505d1f8-72c9-5dfe-a6cf-d1e59c95727a |  | note | Frequency - Post Curing
label | 85a1042f-4d12-5d56-86fe-372896aab0d0 |  | note | Inspection / Test Method - Measurement
label | b1713d98-9966-5407-b4ab-ec7529b52ee1 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | f1c7eea3-0580-572f-8315-8525416ba75d |  | note | Records - Site photos,delivery dockets
label | 3bc5a1ff-4ffb-5eaf-8bba-5f2ffef21f59 |  | note | FH Initials - Site Engineer
label | 1372c979-a5a4-5b67-8b9e-f8cfadb534d2 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 56ba6b02-deff-5db7-9993-b435090dd752 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Lot Number QA File
label | 02610332-342c-5269-9e21-3c68062e589b |  | note | Inspection / Test Point - Lot Number QA File
label | cb19982c-9986-5cbb-9759-5f16dcadc0fa |  | note | W
label | 798ec3d1-2cfa-548d-81c0-879f7e796db3 |  | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | 5db34cc9-7570-5f0e-9f50-677ac471fede |  | note | Frequency - At completion of Lot
label | 41bad3ad-a86c-584d-944e-38e5bb24286b |  | note | Inspection / Test Method - Document Review
label | a5daeec2-3afc-5e1f-9a0b-aa3540a13dcf |  | note | Conformance Criteria - All QA files compiled and submitted to client
label | ca1482e2-6bac-5735-b41f-01ccc7758d8c |  | note | Records - QA records
label | b4d7292a-2c21-580a-b7e7-73455b91a4d6 |  | note | FH Initials - Site Engineer
label | 5875e69c-8cb5-5438-88e6-a6552bbe4b8d |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 7c9f2616-be92-5659-83ba-971d63cbdbfe |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 14.1
label | f4dd43b7-0008-5e36-8b40-6efd8e2522b2 |  | note | W
label | c7d2bf03-37f5-545f-aaec-a8efeb7c4159 |  | note | Detail - Delivery Dockets to be included in QA file
label | 3a98077e-6c7d-5f4c-b707-71546ac32aaa |  | note | Frequency - At completion of Lot
label | 129671b7-e192-52d3-82d8-70d84f73f759 |  | note | Inspection / Test Method - Document Review
label | f333395e-d16f-515d-9e5f-7310df566b55 |  | note | Conformance Criteria - Delivery Dockets to be included in QA file
label | 2717f42a-671e-56b2-8472-da0c97e822d8 |  | note | Records - QA records
label | a70eecd9-5ba6-5639-9130-93cbb12719e6 |  | note | FH Initials - Site Engineer
label | 243c232c-48fb-57e3-b2ff-936e3f07f3fb |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 78fa3861-3d95-5165-beb7-648bf410407e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | e59f09c2-47e7-5f43-80f9-3e3ffe863452 |  | note | Inspection / Test Point - As-builts
label | faf778dd-f549-5cc2-af47-22c265cc7176 |  | note | H
label | def1beea-bbaa-5a9d-b98e-64b032483b39 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 982a6d77-c086-57e1-859e-e608a1ae589b |  | note | Frequency - At the completion of the Lot of work
label | a75e807d-3c0a-560b-972f-94d9f2ae873e |  | note | Inspection / Test Method - Drawings
label | 22cb79d3-24b8-5c9d-8825-ecff615eea90 |  | note | Conformance Criteria -
label | 755eb350-f28e-5390-8272-51ac13674f6a |  | note | Records - Asbuilt Drawing
label | f79b3cd8-428b-5307-b9d9-ec841c99961b |  | note | FH Initials - Site Engineer
label | 64e936ef-56f7-5926-9227-82affd77b4e5 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | a8ab0bcb-0632-53f8-9715-905f832d71c2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
text | 148709b3-c6cf-5e80-affd-7d4867be5b8c |  | textbox | Comments:
text | adfed1dc-35c8-5de6-82a9-d8ead9ee78f2 |  | textbox | IFC Drawings used for Construction incl. Rev numbers:
text | 4cc48a11-c97d-5566-80de-0519de6b334e |  | textbox | Reference Documentation (Notices/OFIs etc.):
text | 7292e76d-58a4-57f5-aab8-7768f1cd74e5 |  | textbox | QA Compiled By :
text | 6e0fad8e-3c78-5479-a6ec-bc803393f3fe |  | textbox | QA checked By Discipline Manager:
text | 3b164237-452e-5f09-855f-f0a6f974a3c9 |  | textbox | QA checked By Quality Manager:
text | f2050995-ed85-588a-85c7-95d74c733f8a |  | textbox | Accepted By Design Engineer:
checklist-sectioned |  |  | checklist | Footpath, Kerb and channel | itp |  |  |  | Yes | ITP - Griffen Park / Hillsborough Rd - Footpath, Kerb and channel | 10588cb3-57b9-456a-b0fe-6fdb07b4d72c
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | 9cb7f9d0-f4fd-573f-bc43-9d65ce94de01 |  | note | Verification Activity - Surveyor
label | 07b38422-c2c4-5b64-b973-795a28a8f9a8 |  | note | Methods Or Reference - Surveyor
label | 2b7857c2-d1b4-5510-b4a5-8ceab34073d8 |  | note | Frequency - Every Site
label | 0ca28e5c-9b48-5f02-9f76-9171a2de072c |  | note | Acceptance Criteria - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | fc394b66-1e71-54fb-9b75-0b4d8eb7061f |  | note | Mandatory HOLD POINT -
label | 007458b3-e4ac-5419-a29e-487c93afbfe6 |  | note | Records - Survey Receipt
label | 91f3e4e0-cb79-50fc-ac40-29802c803daf |  | note | Onsite Responsibility - Site Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Kerb & Channel
label | f8100e9a-84fe-5c98-9d2c-46672f6dda7c |  | note | Verification Activity - QA FORM
label | d1dec625-c940-5264-a0ce-c2c27ffc6040 |  | note | Methods Or Reference - TDM Technical Standards - KC0001
label | b0f1c951-02ee-5ac1-baca-8d4f2b787ff5 |  | note | Frequency - Every site
label | 14c10331-f505-5098-be5e-f30a6281654d |  | note | Acceptance Criteria - Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min GAP 65 subbase in roads and 100mm GAP 40 in footpaths. (CBR>5).Concrete 20MPa @28 Days
label | 3ee46141-84be-5d60-a195-11cfe558c576 |  | note | Hold Point - In Process Inspection
label | 7949b657-d517-5834-b62b-a48b6469d661 |  | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
label | 65bbcca0-4bd1-56ee-92d4-87f34162c94e |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Channel Level
label | 0784d71c-0127-523c-a2a8-44fbe48f3255 |  | note | Verification Activity - QA FORM
label | de1f98b6-b3f6-53c2-91e2-dc6462a7a27b |  | note | Methods Or Reference - TDM Technical Standards - KC0001
label | 12eae072-ebee-5deb-b262-07bd87350c5a |  | note | Frequency - Every site
label | 37b02556-4af7-55d7-a2fa-84a3df63efb9 |  | note | Acceptance Criteria - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | ad9032f9-e4b5-54c4-ab2b-28db9cd5d1ad |  | note | Hold Point - In Process Inspection
label | 1baa0027-45a9-5d98-8410-27f0c934d089 |  | note | Records - FH concrete QA sheet
label | cc67d6d1-45f2-5dc8-a6f8-356e208dcfba |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 4 - Concrete Footpaths
label | f91f665b-0ce5-59a0-ac60-a1502ca11e63 |  | note | Verification Activity - QA FORM
label | 1cfca176-04ed-5f87-bf04-92ad4dba2b7b |  | note | Methods Or Reference - TDM Technical Standards - FP0001
label | 6fb2008e-3263-5ac8-bc3d-0cf294f644a3 |  | note | Frequency - 10m Intervals
label | c9bf13e6-b449-522e-8e0f-4b3acde7d83f |  | note | Acceptance Criteria - Subgrade -(CBR > 3) Base course - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide Exposed Finish
label | 3719710d-1554-525b-8784-3f46b3ce469b |  | note | Hold Point - In Process Inspection
label | 9e1ed6b3-cd63-57ed-be65-4e9f79c1302e |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | efd061dd-54ed-581f-810b-68c4ff5c662e |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Grass Berms
label | b59e9b8d-6589-5b5d-bbbe-5de0c5e8a31d |  | note | Verification Activity - Visual
label | 42897cd8-8a69-5629-a092-633a14c14b71 |  | note | Methods Or Reference - ATCOP Section 12 Footpaths and Pedestrian Facilities
label | ef4cc5b3-0032-518c-8446-27eb004e2368 |  | note | Frequency - 10m Intervals
label | 56e241c3-a765-5d13-a7c9-9e00b3866489 |  | note | Acceptance Criteria - 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | d911584f-6c03-54ec-9fb0-4209142d9a3d |  | note | Hold Point - In Process Inspection
label | 162bab1a-8c85-5ca3-83ad-9e5e3f8b7f03 |  | note | Records - Photos
label | 83fa8a0b-f0d3-53cd-8eef-1766fb73efdf |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6 - Tactiles
label | b37b7ab2-6a2f-5a7f-b3d5-3e9979a67ef3 |  | note | Verification Activity - Visual
label | 33c3bc13-0ccf-54ed-a048-a870f90eede6 |  | note | Methods Or Reference - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 3b5bc17b-d9e9-585e-b0ef-443502b7befb |  | note | Frequency - Every Site
label | 73c57123-5031-5db4-a187-e8e5ba91093b |  | note | Acceptance Criteria - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | aecab37d-f22c-55df-ad79-817ae19de02d |  | note | Hold Point - In Process Inspection
label | 5be76b05-3726-592e-90bc-facbc35a01c6 |  | note | Records - Photos
label | 4f3110e0-dfff-5d53-98a3-28715aa79da8 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | As Builts
checkpoint-status |  |  | checkpoint | 8 - As built information
label | 7b0808c8-c738-56e1-8545-4328cfa497b6 |  | note | Verification Activity - RAMM DATA SHEET
label | 4072d864-c50f-58d1-8698-cb54c98eeebe |  | note | Methods Or Reference -
label | 91581691-59c4-527c-b82b-ec96eea1934a |  | note | Frequency - Every Site
label | 0f721d55-721c-59c9-b982-3df05778cb22 |  | note | Acceptance Criteria - As built drawings and Ramm Sheets Completed
label | 4a50ee88-3f7f-5123-b0bd-54bcd33ebaa9 |  | note | In Process Inspection
label | 16d925e7-3018-5706-bf01-f3520daaa758 |  | note | Records - As Built records
label | a553d09a-a1b6-5a9f-8e5e-fb9366bc3db7 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 9211ba56-12b2-553d-9bb6-03f6938f65b0 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 53f6b9cb-5dec-5bd7-bf46-da070ca6195a |  | textbox | Print Name:
text | 143dc8dc-d53c-5636-b385-b5909073fd51 |  | textbox | Position:
text | ad1f1e6b-2fcf-53c6-9dd2-59ad4e7d8ead |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP - St Lukes Road/Morningside Drive intersection - Enabling Works |  |  |  |  | Yes | ITP - St Lukes Road/Morningside Drive intersection - Enabling Works | 1460a8bf-f3e5-4a2e-bfb1-541a875808c4
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | 3fa204e0-6c56-5877-9400-6981f4e56ed7 |  | note | VERIFICATION ACTIVITY - Surveyor
label | fa2cf24b-2206-50a9-854d-0355d47b59b1 |  | note | METHODS OR REFERENCE - Surveyor
label | a4ee13bf-c54e-5c91-a93c-2b959c623d12 |  | note | FREQUENCY - Everysite
label | 3c23fe9a-d52f-5a1e-b9ef-b1a8983317be |  | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
label | c6d039fc-799f-542f-b091-d4375d30bfce |  | note | Hold Point - Mandatory HOLD POINT -
label | e30ab4f6-b762-5b2a-96aa-b9a4fc408d45 |  | note | Records - Onsite records/photos
label | e62e4119-5a10-5238-a3cb-9283616c3785 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Kerb & Channel
label | 5f053929-d24b-5c23-b6ca-ebb8fda2a9ed |  | note | VERIFICATION ACTIVITY - QA FORM
label | d13d10c2-6076-5378-8a12-6da46bf23287 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | a77781df-f09f-57e4-87c8-320b79f86084 |  | note | FREQUENCY - Everysite
label | f45e0929-bfd6-569f-9122-e52f415ce019 |  | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40
label | abb888ef-42ea-5756-8d4a-55a28d1cba35 |  | note | Hold Point - Inprocess Inspection - Engineer to check the Stringline Set out
label | cff46914-789e-5f56-9fde-a43d5d31606e |  | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
label | 2f1c9aa4-e308-5a65-aa6f-b5386d987d22 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Channel Level
label | 9eec518c-b38e-59f8-b8fe-c416b4611c85 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 0284548a-0d7a-5857-9d25-92aee3802de5 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | 22bf52cc-f90c-5a06-b72a-15d27f56c1c2 |  | note | FREQUENCY - Everysite
label | 6e330781-23a3-5294-8d36-eab45ceac98c |  | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | 7c15a896-45b3-5a37-acdb-675d497fa611 |  | note | Hold Point - Inprocess Inspection
label | 2668baf6-b154-58ad-9727-e134f145e9ba |  | note | Records - FH concrete QA sheet, Photos
label | 70aa9bdd-6dbf-53d5-8c8c-488da2353a6d |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | CIVIL WORKS
checkpoint-status |  |  | checkpoint | 4 - Concrete Footpaths and Pram Crossings
label | 864a98f9-462c-5bac-8e44-89672107edae |  | note | VERIFICATION ACTIVITY - QA FORM
label | 9f389bbb-0b0d-5491-9ab2-212d3af4f9a6 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
label | 97385b6f-adfd-564d-8764-2d3a3d1b9992 |  | note | FREQUENCY - 10m Intervals
label | 948ae407-5a12-5a4f-a93c-eb0d9d7fe778 |  | note | ACCEPTANCE CRITERIA - Basecourse - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish Expansion Joint cut for every 3m interval Pram crossing to have 600mm flare from kerb; Minmum 1.5m deep and wide.
label | b413eff3-2d3f-5de0-bc7d-d12af3995c57 |  | note | Hold Point - Inprocess Inspection
label | f8930dd0-59b0-5f00-9258-fb4f29d2c49a |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | 3c199721-d082-59ca-9944-f5fc316fedde |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Tactiles
label | 163d1000-bc8f-52a7-be71-d8ba917be288 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
label | ea88d39f-6eb3-548f-ac4a-b86685337f3c |  | note | FREQUENCY - Each PX
label | 932b3af6-09a5-5e66-9ad9-f196f335fa07 |  | note | ACCEPTANCE CRITERIA - Tile set out position to be agreed with ATOC and Engineer. Warning TGSI tiles should have 100mm concrete slab underneath
label | 5fcffc9c-1bad-5580-a967-7b491af69e47 |  | note | Hold Point - Inprocess Inspection, Measurement
label | 2fe6e17d-e6f3-5376-9d54-d5a52a48a4a1 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | 7b434978-2a96-5b5a-9fbc-ecde381d6f05 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5.1 -
label | 776acee2-9c7c-555a-9fe7-926d2eeabd47 |  | note | VERIFICATION ACTIVITY - Visual
label | 9b3c791f-3755-5892-8a57-9c81578f3e3c |  | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | c5620cce-4395-5257-8098-38db602e0baf |  | note | FREQUENCY - Everysite
label | 96b8d901-cf51-53c1-81db-74379cf5062d |  | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | 0a54a911-3c20-5ebc-8350-b00df1967d2e |  | note | Hold Point - Inprocess Inspection
label | a68da3ad-5f9a-585a-a60d-c7becfc346dc |  | note | Records - Photos
label | cd539025-4d05-5062-9959-c32691c0e1c3 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5.2 -
label | 88e328ab-81ee-5b9b-adaf-36b9694c3fde |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 6f74d62d-d13e-5c4f-8e02-1472d5094404 |  | note | FREQUENCY - Everysite
label | 4408617a-d616-590a-80d4-8390714a98a4 |  | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane.
label | 28e8d335-f290-506b-8110-4480f9785656 |  | note | Hold Point - Inprocess Inspection
label | 6fd984a6-bf6f-5e28-9516-b8619cc48841 |  | note | Records - Photos
label | ce649c9e-3345-5843-b837-5b479c2fd783 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5.3 -
label | 8f9b4420-26fc-5f15-b3cb-84e8615feaa0 |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 43adbe42-d996-5289-8ab7-6beac5792a96 |  | note | FREQUENCY - Everysite
label | 98acf081-63d6-5d2d-a43e-81d8b11e4841 |  | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | e3ca0919-97d6-5680-a815-486641d28d19 |  | note | Hold Point - Inprocess Inspection
label | 9807626f-b33a-5a3d-94d8-083a631dba01 |  | note | Records - Materials Dockets
label | fac150d0-95fa-5726-9896-375842d5c91c |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | 6
checkpoint-status |  |  | checkpoint | 7 - As built information
label | 5d385da7-98ca-5c6b-9933-3adb3f05a002 |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | e6b4bced-337d-5015-95d4-fd4527ac114e |  | note | FREQUENCY - Every Site
label | 03f84d4f-faff-5484-9c44-499b5d27b8d1 |  | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
label | 0b0922af-956c-52b6-88f1-dc23c3323298 |  | note | Hold Point - In Process Inspection
label | 2ff9ae31-3d95-5960-a8c4-051d971f65d0 |  | note | Records - Asbuilt records
label | 0237d10f-c05c-55b6-beb4-2d8bca9c88b5 |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-sectioned |  |  | checklist | Enabling Works - Footpath, Kerb and channel |  |  |  |  | Yes | Halsey/Maich RAB - ITP - Enabling Works - Footpath, Kerb and channel | 1689d1b2-64fe-414b-bf85-4aec14562790
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | 10977638-1625-53c7-a92b-f12c815a330e |  | note | VERIFICATION ACTIVITY - Surveyor
label | 09313a9b-9f76-5da6-b129-078a3645311c |  | note | METHODS OR REFERENCE - Surveyor
label | c483eefd-fdf0-5a0f-86e3-e0f2dc71b491 |  | note | FREQUENCY - Everysite
label | a90c6f8e-c1be-5866-a999-02b4bc5c719b |  | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
label | dd166184-484a-55e9-9d20-f63c90921294 |  | note | Hold Point - Mandatory HOLD POINT -
label | 68dd43ff-15f6-5c3f-8b55-056da8dbe9bb |  | note | Records - Onsite records/photos
label | d801a316-09f4-5ec9-87ae-26043ffccc71 |  | note | Onsite Responsibility - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Kerb & Channel
label | ca6eaee4-7bd3-593f-9d3e-a273b3b91ac2 |  | note | VERIFICATION ACTIVITY - QA FORM
label | d366edc6-b6be-59f4-b8ce-af35db2d68f5 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | bdf1e016-f129-5d1a-aa4c-4b5fa6e20ccd |  | note | FREQUENCY - Everysite
label | 046c9637-dd20-5c60-8d05-e581c5a8de8f |  | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40
label | e741e130-ff47-5c8c-8738-4880a83f0c10 |  | note | Hold Point - Inprocess Inspection
label | 52335437-a63e-5bc6-beaa-9829b9a73f96 |  | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
label | 009a656e-8d39-507e-b37d-d282d381b535 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Channel Level
label | 6adb15c9-c5f2-52f5-ac7d-7f8474c73df0 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 5aa50664-cc06-5ab8-af9b-a05606d9bf6d |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | 6a14352a-403b-5e34-bc22-0b0531046a80 |  | note | FREQUENCY - Everysite
label | d1f3b24c-ad43-55ab-88fa-49553579193a |  | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | 3d83baa0-9d69-52de-8983-2d2c3943d47e |  | note | Hold Point - Inprocess Inspection
label | 68069259-77c0-5406-abe3-6ae8078e86ca |  | note | Records - FH concrete QA sheet, Photos
label | 6ab6d591-606e-5d6a-9a93-541accbb44bd |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | CIVIL WORKS
checkpoint-status |  |  | checkpoint | 4 - Concrete Footpaths
label | b2c975a0-89d7-55cb-88d1-8d117333c5b4 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 3b499e6d-4a29-536b-9408-81b23f050aa2 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
label | 2651e231-d7e6-5532-a86f-9f5b9f935c09 |  | note | FREQUENCY - 10m Intervals
label | c1baf555-71fa-5f4c-8e38-c1b1e256c186 |  | note | ACCEPTANCE CRITERIA - Basecourse - 100mm min. thickness GAP40
label | bea19ec4-d318-555c-9d99-73cd30d89c61 |  | note | • Clegg CIV > 12
label | 84fd2f33-50a4-54e9-85db-330b3c7a8d9b |  | note | • Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
label | eaad7a27-7c5d-5fa4-9d43-debbdb410b31 |  | note | Hold Point - Inprocess Inspection
label | 6024b409-0770-5247-8e16-719b0023db8c |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | 731c6be3-9123-5fe0-bd87-5c697eb67140 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Tactiles
label | 9fff2919-9a7c-540d-84ad-1ee144e471bf |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
label | 36c3f4eb-0a36-584a-b2a8-c03a74195e25 |  | note | FREQUENCY - Each PX
label | 0aff6bce-7bb4-538b-aaaa-4235a8219afe |  | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 150mm concrete slab underneath
label | 0640625e-ebc4-5b93-a639-aa31d2ca86b7 |  | note | Hold Point - Inprocess Inspection, Measurement
label | 1c9012b2-13ab-5679-ad0b-7a4b9ad205cb |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | ad8061db-8459-5dd1-9aed-641b5bee911d |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5.1 -
label | 372f1c53-6118-5e39-ba4e-8a30a3a67ef1 |  | note | VERIFICATION ACTIVITY - Visual
label | 5290af57-16d5-5725-92fb-97bb5f04188f |  | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impared pedestrians
label | 28d8fa26-d131-57d1-a7d3-aa2333495088 |  | note | • AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 941073b5-c32c-55f7-b74e-9eb6a4934afb |  | note | FREQUENCY - Everysite
label | e7dc2bfc-f856-54ca-8b66-85dcc711ced0 |  | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | 27a96295-4e8d-54f3-b820-3cafff56ad2a |  | note | Hold Point - Inprocess Inspection
label | aa1be699-d04c-512c-a13b-945dad3b27fd |  | note | Records - Photos
label | 5e6fb141-b461-5ba3-adbf-c0b3816c29ca |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5.2 -
label | 1ff3378e-677d-5ac0-9649-5356220f8f68 |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | bd32e448-c479-50ee-b303-278c2aff7065 |  | note | FREQUENCY - Everysite
label | ec3d296e-6a49-5a60-8886-30d8709e6f79 |  | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane.
label | 438858f8-09e4-5ff3-be5b-889ef694051a |  | note | Hold Point - Inprocess Inspection
label | e53dbca2-5155-5163-81bf-20b1cad37d6f |  | note | Records - Photos
label | 58f113aa-8ab2-5781-a7fe-ae699eb8d618 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5.3 -
label | dd2f8cba-9a93-585d-8358-a167ebcce95b |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | b1677563-b08f-55b8-87dc-5cd14e20c115 |  | note | FREQUENCY - Everysite
label | 9685bc67-fdb5-5608-84f5-a323822e9350 |  | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | d5667c7a-6fe5-558e-9574-383b933eac9b |  | note | Hold Point - Inprocess Inspection
label | 8ed95bf5-e22f-5bfa-a75d-88fb3750d022 |  | note | Records - Materials Dockets
label | 4f5d4930-53e8-5c92-b015-5276fd01a60d |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6 - Grass Berms
label | 5f3a7c0d-431e-5228-8a60-64ff02c7395f |  | note | VERIFICATION ACTIVITY - Visual
label | f3f9b0a7-97b3-5192-92b2-f20f18618f4d |  | note | METHODS OR REFERENCE - ATCOP Section 12 Footpaths and Pedestrian Facilities
label | 66e131e7-c2ac-58a0-9a54-63800d11ea6f |  | note | FREQUENCY - 10m Intervals
label | d424e7d1-0b1d-596c-afb8-398f354bbc2d |  | note | ACCEPTANCE CRITERIA - 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | 98b56cd8-2b7d-53d5-b63e-a51af7c2c9a6 |  | note | Hold Point - Inprocess Inspection
label | 11ef74ad-c380-50a4-b2cf-ba454bca07b0 |  | note | Records - Photos
label | 5db74583-91a2-5bff-88bc-ecc2e88052db |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | 6
checkpoint-status |  |  | checkpoint | 7 - As built information
label | a7f3d049-1305-5f6d-bf3d-5855b501303f |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | 1e01c51b-683a-5b15-833b-300ae727e0d8 |  | note | FREQUENCY - Every Site
label | ee5dd4f2-897d-5a5f-8d9a-b99fff79b2fb |  | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
label | 107d67c1-e87e-5f94-ae9a-854ac058c192 |  | note | Hold Point - In Process Inspection
label | c8493b55-b54c-590f-8d34-11222fe7ea9b |  | note | Records - Asbuilt records
label | 8cffca3b-1f5c-59d3-b96f-d1a6d5f81087 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-group |  |  | section | ITP APPROVAL
checkpoint-no-status |  |  | checkpoint | ITP Approval
label | b6413876-20e5-5e00-acaf-eb5b0c4b445f |  | note | Prepared by: Yeswanth Vemula (1/05/2023)
label | 2d92f182-766e-59e4-b92f-95e112b6b343 |  | note | Approving Delegate: Daniel Tat (27/01/2023)
checklist-flat |  |  | checklist | ITP - Mckenzie Road - Stormwater | itp |  |  |  | Yes | ITP - Mckenzie Road - Stormwater | 228a9126-e706-4432-b4f3-73509589e99a
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | b3c8c11d-0570-5b9a-837c-60829a365dc5 |  | note | H
label | db73867a-f690-5750-b776-c14f4305ca20 |  | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | 89c5c254-bf9a-53bb-a3e4-625c0b4175b4 |  | note | Frequency - Prior to any construction commencing
label | cfe8a350-2923-572e-bd99-28e6208aadb0 |  | note | Inspection / Test Method - Document Review
label | 3e2612ea-2c8c-556e-822c-d6f9dcf646e8 |  | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | 2a17082b-df4d-5c88-8122-df1ebe8a4d5c |  | note | Records - Permit attached or permit number noted.
label | 3c5f172b-bf02-586f-825b-5257cb7daadf |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1 - Permits & Services
label | 9b997897-d645-57b7-b383-776f1eb4e813 |  | note | H
label | 60118bbc-2173-5a6a-a038-b487c3c77f0e |  | note | Detail - Locate and mark out all existing services
label | 3ab37d60-93a5-5e5f-9305-b10ad3999254 |  | note | Frequency - Prior to any construction commencing
label | 20d63fd2-7e3f-5322-9d77-29125d7f8b38 |  | note | Conformance Criteria - B4u dig procedure - follow utility protocols
label | 18ec3010-c0e2-58e6-a287-b8929c909ddd |  | note | Records - B4u dig plans & GPR report attached
label | 3286740d-a263-564c-b94f-c383e39dc97e |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | a1ef1c96-6ee8-5e80-b035-9c6d293dc228 |  | note | H
label | 8a09eb05-7d57-5bab-afbd-44ecd6d987a4 |  | note | Detail - Sub-Contract and Supplier Agreements
label | 9c2233dc-f874-52b6-935e-46cd35a1f81d |  | note | Frequency - Prior to commencement.
label | abed3b43-cef6-5055-bbb2-c8e74fd7cd76 |  | note | Inspection / Test Method - Document Review
label | 7c94a290-8113-5232-8cb4-644bd2bd5afe |  | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | 4b27aa68-b2c9-5421-9e54-a71684018048 |  | note | Records - Subcontract and Supplier Agreements
label | 9930c7f1-67d9-5281-ba6c-bf7818318939 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 20eda8fa-b8e2-5e3d-a719-17130c053f00 |  | note | H
label | 98224550-804d-5e4c-ab9b-e32262e7097a |  | note | Detail - Design is approved and Drawings are of the latest revision.
label | 835b07c9-f854-59e7-a35e-ae41057ca6cb |  | note | Frequency - Prior to commencement.
label | 963be0fc-9b1b-50b0-8a5c-ec9646ac8391 |  | note | Inspection / Test Method - Document Review
label | e2310d52-ec02-5570-9c3e-a22b2dd5a76b |  | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | a6905315-b75d-5502-a8a6-ffa426610bb9 |  | note | Records - Drawing Register.
label | 3529bd02-3244-559f-819c-dc1da2bf89fa |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Survey Setout
label | 51e1e441-8166-5611-bc11-3c65ef834ef7 |  | note | H
label | 2acda9b6-c6f8-5ab0-9fa3-9dc59d9ed38b |  | note | Detail - Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | 3a136266-6231-5f31-a40d-8642240340d5 |  | note | Frequency - Prior to commencement.
label | 957b17c5-3498-5d7b-8983-f8253cc987c3 |  | note | Inspection / Test Method - Survey
label | b2309e1f-ca86-55ec-a022-1b06667e9a8b |  | note | Conformance Criteria - As per Blue Barn Consulting Engineering Drawings: 02188-T-400 & Setout files
label | 3669fc66-099c-593c-8736-4bed6e1b871d |  | note | Records - Survey Receipt.
label | 228a1ff9-9b00-5128-afc1-7682bb5d967f |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Pipe and Manhole Material Compliance
label | 796e578e-eac9-5671-9f1b-de28f2ecc630 |  | note | H
label | 6a27a81a-6f00-5e07-8871-f30c70186fae |  | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | 75d6bee9-b1ba-57cd-8a26-81d69c9fb226 |  | note | Frequency - Prior to commencement.
label | b941233e-dc6e-508e-a534-b04527352e0d |  | note | Inspection / Test Method - Document Review, Visual Inspection
label | 84508024-0b62-5970-bfde-0509fa68b040 |  | note | Conformance Criteria - Pipe shall be Check for freshyly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | ff1983f4-2ca6-5916-8f48-9431eaa22bfd |  | note | Records - Manufacturers Data Sheets, Delivery Dockets
label | a8fe8bff-3368-5179-b437-ed587662948c |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | c94fd055-dfd0-5250-923f-72545f2e85c3 |  | note | H
label | b95faa82-b611-596f-92fe-c7c912669ee1 |  | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | 59e7aa6c-1ca6-5e1b-a840-610807b21885 |  | note | Frequency - Prior to commencement.
label | 1417e805-474f-5731-8bad-dd1362924173 |  | note | Inspection / Test Method - Potholing / Survey
label | 4f504c55-31f7-5e66-8d6f-9baf25c53f02 |  | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | a1e3640d-8f6d-54b0-9025-3cb05f48c0fd |  | note | Records - As-built Drawings. Doc. Review
label | 38279db4-7839-5553-9aaf-4fd9d86a1cdd |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | b6c51101-8136-5a8e-8735-611ea4a63988 |  | note | H
label | 2ed85907-7923-5421-867d-350620c68275 |  | note | Detail - Excavation methodology
label | 8879aa28-9d0b-534f-b628-466fa0da1c6b |  | note | Frequency - Daily
label | b6b2a99a-fe52-5fe4-8e52-2b4ba131ae14 |  | note | Inspection / Test Method - Prestart review
label | 49d622ff-21e6-5b31-8c88-6e2a0abe5a0e |  | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | 5f66d6ca-a5bb-5a24-9b7b-7d4eb2771ea1 |  | note | Records - Prestart RCP
label | 3dbaddf2-d6c7-53d7-92d6-5722723b511d |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1 - Trenching & Excavation
label | d7d5b9be-c7cb-51d6-b906-f4c5f8840c88 |  | note | M
label | 694cb0b1-ebd9-5947-82e9-fe4632479f17 |  | note | Detail - Trench Profile - Width
label | fe218245-d419-582c-a087-2fdc73745bec |  | note | Frequency - Daily / as trenching takes place. Different depth methodology
label | 4d8bd7ac-a991-5378-a575-3e809af03fd3 |  | note | Inspection / Test Method - Visual Inspection, Excavation methdology
label | a473c00a-f888-5587-bd8b-cee7826fface |  | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | e1d12c95-b206-5fb2-82ea-b29eb70389f0 |  | note | Records - Construction Photos
label | ea155010-b14e-5b88-b8b4-403de875e7b8 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 7.2 - Trenching & Excavation
label | 4d06fddc-e0a2-5b29-97a3-1723b978088d |  | note | W
label | 2f27b1e0-5c67-5b68-91b6-0d8a39fd6bf9 |  | note | Detail - Trench Profile - Depth
label | a632fa0b-0dc8-514a-ab2f-d1f460513c37 |  | note | Frequency - Daily / as trenching takes place.
label | f1cef5ce-dd12-534b-b3cc-cce489d3ee65 |  | note | Inspection / Test Method - Visual Inspection, Measurement
label | 48c812b3-8043-519d-8df1-f8977e591406 |  | note | Conformance Criteria - Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | fda3b1b8-fd14-573c-8d3f-9688ee8fd41e |  | note | Records - FH Drainage Line Record / Construction Photos
label | 4c6d3097-136c-5736-9e5e-e27e39558b33 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | 2038fe24-220c-5810-a7b6-dc9328132959 |  | note | W
label | b915eb3c-ae78-56ba-b68e-e2aa56dd5f2a |  | note | Detail - Placing and compaction of Bedding Material.
label | 140e0023-edef-5086-aba5-34b6cd91e23f |  | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
label | ebd78c54-9c28-573b-9257-beb4423204f0 |  | note | Inspection / Test Method - Visual Inspection
label | e09085f3-03a9-53bf-b1d5-ee3bd8136d71 |  | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | cc02cdf2-c39b-5a37-99f8-3b8f00f24889 |  | note | Records - FH Drainage Line Record / Construction Photos
label | e5fa5ac4-57e9-58bd-822b-ed8206add4a2 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 9 - Pipe Position Tolerance
label | 9b7c8ea9-6bf2-5987-8cb7-871f673fbb3d |  | note | M
label | 432f1247-e98b-5f50-b7d1-a1502a72a068 |  | note | Frequency - At any point of pipe
label | d9f4b05f-c276-5d66-8772-6146bbd253f9 |  | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
label | 01ee827f-9432-5514-9dac-40a0d77bfe2a |  | note | Records - FH Drainage Line Record, Survey Data.
label | b3663a9b-5fca-5b14-b11c-78ab514ac727 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 10 - Trench Backfill - Placing & Compacting
label | 5b4cb190-0093-5f80-996d-3b5fa18f2195 |  | note | M
label | 71acf6a2-eb7a-5cdc-8ed8-161f527f7ad6 |  | note | Detail - Placing and compacting of Trench Backfill Material
label | 263c44f7-29d2-58bf-9ff7-4d8e5d90a22a |  | note | Frequency - Throughout Trench Backfilling operation.
label | 982c6878-5648-5397-80b0-799763d70957 |  | note | Inspection / Test Method - Visual Inspection
label | 9080e7de-b030-546f-9547-2b1b94f6cf7d |  | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | c638b0b8-b610-530b-adcb-4d4406877470 |  | note | Records - Construction Photos
label | eb982cfb-8c16-5c35-932c-36c31471c5a7 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 11 - As-Built Drawings
label | 71088f1a-0d93-5e59-926e-b28aac487268 |  | note | W
label | 5fb34dcb-d753-5fca-a2fd-970a57cf45dd |  | note | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
label | aa0638c4-cb64-5b0a-a16b-f16e10680d8a |  | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | d0873973-b02c-5d67-a93c-cb5cbcdc44e7 |  | note | Inspection / Test Method - Drawings / Visual Inspection
label | 599bab6e-07ab-549d-ab6e-d030f6440106 |  | note | Conformance Criteria - As Built and GIS Data
label | b4d4f1a2-ab46-59f8-be2f-c9b8008113b8 |  | note | Records - Redline As-Built Drawings, scanned as .pdf files.
label | 7a9cbf5d-f347-595b-b84c-e240e7dd24c2 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
text | 89a4ac5e-ee22-5437-9900-d6f530cb656d |  | textbox | Comments:
text | 12180c07-0d98-5697-853d-aaa77ea3c3cf |  | textbox | Position:
text | 29ef09ff-bf6d-5fe5-bbec-88883e8dc29a |  | textbox | Print Name:
text | af5a2481-1af1-50d0-8e45-6ec1eede196f |  | textbox | Date Completed:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Final Inspection
text | ad71bb4b-76ce-5ac5-9926-848383051b5a |  | textbox | Comments:
text | 89e79747-ba41-560a-99e3-03f13575c638 |  | textbox | Position:
text | c185dfa5-10c3-545b-8227-44e2ae39ece6 |  | textbox | Print Name:
text | b4dc7a17-8626-596a-8e23-25a43a0ef083 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | Asphalt Surfacing |  |  |  |  | Yes | Ponsonby - ITP - Asphalt Surfacing | 2552067b-c80c-4ee4-ba7d-c3e151fcf7ca
checkpoint-status |  |  | checkpoint | 1 - Traffic Management
label | dbc90c64-93f1-53f0-a950-115314bca50d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5aa0a1e3-bc53-5084-8bf1-49a074bb6ded |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | e1fa7c8f-a553-5dd0-9f88-63e2564235d2 |  | note | Frequency - Prior to commencement
label | 132d5f75-321a-5848-9bba-c3ee82bb96db |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 3decf82f-43fc-58dd-8adb-6ba19b88a24c |  | note | Conformance Criteria - TMP is approved by AT for the site and works are only completed within the approved dates
label | e493f906-5f3a-564f-9511-ef4d36fc9a87 |  | note | Records - TMP on MyWorksites/On Site
checkpoint-status |  |  | checkpoint | 2 - Pre-construction sign offs
label | 7b051d40-8545-512a-a90f-36d54c2b70c9 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 20f1373b-5788-5fd5-bdf8-1cf6f5a3f88f |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site
label | 58897358-b764-5c90-a354-2f659131a98e |  | note | Frequency - Prior to commencement
label | 88883261-7023-554d-aaa1-31945fb19168 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | b3ea49cc-99ad-536b-9e64-be3722abc1a8 |  | note | Conformance Criteria - Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated
label | c4b01467-7384-5a52-924a-183d3b3c8abf |  | note | Records - Subcontract and Supplier Agreements, A & Updated Induction Register
checkpoint-status |  |  | checkpoint | 3 - Base course sign off
label | 00c45050-ecb1-57d9-9898-536d3987989e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1df086a4-3c41-51f1-a027-8d32a5ed8919 |  | note | Detail - Ensure that base course checklist and QA records are signed by AT representative/Engineer
label | b681519c-825f-5b85-ab20-eb322636323d |  | note | Frequency - Prior to commencement
label | 0abfa7ec-c9ae-5ba1-a3fe-30e11aae70ac |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 7215bf1d-8688-5081-b29c-6070a93fd563 |  | note | Conformance Criteria - Completion approved as per Pavement ITP
label | 2be09cdf-3dde-5d63-8e55-2d283909ce03 |  | note | Records - Pavement Base course checklist signed
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Design
label | 6940ef37-647c-5f5e-b0b7-c1d5d38f202d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 879959e1-6174-5b2f-bbce-20364712045d |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | fc7e8172-7d75-55f4-b107-65edb8f988dc |  | note | Frequency - Prior to commencement
label | 4a2398eb-5dc7-5ca1-8a04-d8c215985999 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | b295be90-541f-5908-bcf6-0eb5ece86c02 |  | note | Conformance Criteria - IFC Label on drawings
label | df00f56c-b55f-50b3-86a1-6df01c61d0d2 |  | note | Records - Check Drawing Register
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Material testing and control - AC
label | 5970f11f-a64f-51ac-9a07-af31c30e6d53 |  | note | ACTION (Hold, Monitor, Witness) - H
label | fc0c08e1-98be-5f21-b13e-a591f47ddce0 |  | note | Detail - Asphalt mix design approval
label | 8657b03b-06ed-5ec2-a755-c345b6b1342b |  | note | Frequency - Prior to commencement
label | e2ab9abb-c723-5f98-9561-6bd1688dd228 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Submission and review
label | 9823fde0-666e-5d24-b065-75ea9bd9352e |  | note | Conformance Criteria - Accepted by AT representative/Engineer
label | 0a45217e-2e7e-5a5c-a9a3-7d90d4e47229 |  | note | Records - Approval evidence
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Construction
label | 6ac4cc56-6ffb-5bb2-9f0d-bbec87a13c7e |  | note | ACTION (Hold, Monitor, Witness) - M
label | 359e7e7b-4989-5442-bb16-fdee7611ea82 |  | note | Detail - Check weather forecast and record weather
label | ba7ea2e0-80d6-5dc1-acbd-cb5e3b616277 |  | note | Frequency - Prior and during application
label | 5b552ff5-ec73-5706-a6ae-45467666a9b7 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Monitor
label | bcc1d0a2-7f59-5b0b-83e4-0df9d3b3c1ba |  | note | Conformance Criteria - No foggy or raining or wet surface, base temperature > 7°
label | 606f8265-689e-55b8-9789-cd6ed44677ca |  | note | Records - NA
checkpoint-status |  |  | checkpoint | 6 - Construction (2)
label | 1492c763-3cc5-538e-a01a-e33beca85cc5 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 9c84bd0e-402d-5fb4-9684-214019425d45 |  | note | Detail - Joints
label | 9a91f0a6-47ff-53d8-9ba2-e715f22639fd |  | note | Frequency - Per joint of the road
label | 68248642-ad94-50d2-89e4-aeb105f84b79 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | 8215d42a-ff0d-54fb-ac2e-09e38f016934 |  | note | Conformance Criteria - Edges and joints to existing surfaces must be tapered to provide a smooth transition from the slurry to the adjacent surfaces
label | 1e94090f-bdad-5a02-a1cb-c8ed880b1b05 |  | note | Records - Visual inspection
checkpoint-status |  |  | checkpoint | 6 - Construction (3)
label | 2121e838-c1ce-5ea5-9beb-368df758ad34 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ccac6124-fffe-5cb2-ac4e-d8cefd1aac2a |  | note | Detail - Milling/surface preparation
label | 0ec970be-f526-59f9-9622-06e2c79c2a7c |  | note | Frequency - Prior to emulsion application
label | d2087586-b4fc-557a-9dcb-ac3a3084c420 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection, survey
label | c847e093-4a5f-5528-b869-e1f5b83964cd |  | note | Conformance Criteria - If the surface is being milled and filled, surface levels and condition are to be inspected by the Engineer and confirmed acceptable before proceeding.
label | 9b9008da-3691-597b-91d8-54f524a9cab4 |  | note | • Not applicable if pavement has been constructed under the Pavement ITP process.
label | b8db0ce7-1f72-5fa3-86c4-fa1c3551ccb9 |  | note | Records - Visual inspection, survey
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Construction (4)
label | b8791e45-6034-5d99-a850-5c6529f8314c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 71215991-b874-5faa-a546-913720111c43 |  | note | Detail - Surface finish
label | ba39af46-5c6a-5f58-957d-47400797f609 |  | note | Frequency - Per section of road
label | c5d9e00f-8420-5177-8b3d-afba886237ee |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inpsection
label | 46f701c5-0274-598a-920a-180a768468e5 |  | note | Conformance Criteria - Uniform texture, no roller marks no bleeding, cracking, no crushing of aggregate
label | 96ee411b-25e9-5fc9-97e5-9cdfe9faaf92 |  | note | Records - Visual inspection
checkpoint-status |  |  | checkpoint | 6 - Construction (5)
label | dfb51867-b302-54c3-bab7-003c5aee0827 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 2835578c-2fad-59e9-8c09-655cd2204317 |  | note | Detail - Level
label | 379de3e8-e0eb-5652-90e4-73f8b3591796 |  | note | Frequency - As required
label | 31e91975-9e0a-5bb7-b3a3-272988ea31cf |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inpsection
label | 4cc713d9-ff87-5cb7-82e1-a5d835b84fc3 |  | note | Conformance Criteria - Asphalt against kerb and channel, the surface of the edge shall be flush or no more than 5mm above the lip of channel
label | 5226ced0-82da-53aa-99d3-98ca7c175f99 |  | note | • Any irregularities which vary more than 5mm under straight edge, longitudinally or transversely shall be corrected
label | f28e0c10-5160-5715-83e0-018316aacbdc |  | note | Records - Visual inspection
checkpoint-status |  |  | checkpoint | 6 - Construction (6)
label | cba34c37-2624-5daf-8c32-e9b8e919f165 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5ba26452-5ed1-5576-8e33-3d44f7f2ef93 |  | note | Detail - Compaction
label | 2bc7c94d-de1f-505c-b899-43a04fea6fb9 |  | note | Frequency - As required
label | 2b215ee2-f2f4-5ce4-b621-511d5016b33b |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
label | 58dec33e-aa1d-5a8d-aeed-8eb85812a790 |  | note | Conformance Criteria - Nuclear Densometer tests meet specified density
label | 6bd0a1a0-ba5a-5e6f-b211-7907e1e3e7d3 |  | note | Records - Nuclear Densometer test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Post construction
label | 6bb61f5c-355c-5726-9a12-52d2b93a034c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5c9c51eb-be75-5cc1-bc11-412962eaf267 |  | note | Detail - Inspection/ joint inpsection
label | aa7fb47b-fb1b-5199-9221-1cc3bd8fb755 |  | note | Frequency - As required
label | 0e4600db-8b1f-51d8-ae95-cb76fff2384a |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | 7e28774e-fc0b-5e88-846d-55b873414f4d |  | note | Conformance Criteria - Asphalt joint sealing as per AT standard
label | 6f6a14c6-6df9-5e66-8d58-bf9c4de6b738 |  | note | • Accepted by AT representative/Engineer
label | 21487ba8-2621-5009-ad1c-3201f783bd3a |  | note | Records - Visual inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Linemarking
label | bd785911-42a7-514e-a41f-59fb8f09b29d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5149de9c-dfa8-52ee-9825-722d90884e5a |  | note | Detail - Ensure that linemarking is set out and applied in the correct location and to the level of quality expected
label | c6249d76-546f-5aad-b55a-acbd697cb4f6 |  | note | Frequency - Before & after linemarking
label | 67168a06-d2a9-572d-8549-d79c1ebbe88a |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection, survey
label | e3efafd2-012d-5ef7-984e-ca3fc146faf3 |  | note | Conformance Criteria - Linemarking adheres to design alignments and is of a good quality
label | a4b5ed61-731a-5fc7-994e-a5a4eb76014e |  | note | Records - Visual inspection, survey
checklist-sectioned |  |  | checklist | ITP - Enabling Works - Footpath, Kerb and channel | itp |  |  |  | Yes | Graeme Ave - ITP - Enabling Works - Footpath, Kerb and channel | 26de9b44-2721-45c2-890f-743eb66c5fa2
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 Site Set out
label | f2acdc02-3166-5ba5-993a-bd0c9dce52ea |  | note | VERIFICATION ACTIVITY: Surveyor
label | 03786190-b6f9-539d-8b4d-81df6e3c217f |  | note | METHODS OR REFERENCE: Surveyor
label | 2b63c981-c7c3-56aa-b0d2-70415e943bad |  | note | FREQUENCY: Everysite
label | cd523aef-4413-5bf8-ba1d-7a97ee7362b9 |  | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | cf954a8a-3e06-51e9-b5d1-2b5f36231808 |  | note | Hold Point: Mandatory HOLD POINT -
label | 6da3a5cc-59bc-55b0-a538-f86327aacc5c |  | note | Records: Onsite records/photos
label | 36c8c73f-5a8d-5d9f-8d48-f5c61bdc073a |  | note | Onsite Responsibility: Site Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 Kerb & Channel
label | e4ef2523-9d2e-547e-b615-44553508a81a |  | note | VERIFICATION ACTIVITY: QA FORM
label | a0b1bd11-6361-55e4-9f57-c5eb4ca409a6 |  | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | c32df728-ca88-5467-93f2-573972936a6b |  | note | FREQUENCY: Everysite
label | 12c86a17-a53d-5e21-b0c9-5524332fcc8e |  | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. . Kerbing laid on 300mm min Gap 65 subbase in roads and 100mm GAP 40 in footpaths (CBR>5).Concrete 20mpa @28 Days
label | daba7c95-2885-5fb3-92a7-2172ceeccda9 |  | note | Hold Point: In process Inspection
label | a7f092a5-6dc7-5efe-a8a4-b2ada733d014 |  | note | Records: FH concrete QA sheet, photos. Concrete Plant Docket
label | 58e62e1c-37bd-5ab1-8ed6-cb8ce8b3daed |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3 Channel Level
label | 04c75814-f1eb-5e74-a6bc-687979668806 |  | note | VERIFICATION ACTIVITY: QA FORM
label | 52cd32cc-bc2d-54a4-a8de-aa9253f929ed |  | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | 2ef4b251-dd04-596c-b3ca-32dcc791c375 |  | note | FREQUENCY: Everysite
label | 3d8f4d58-4ffd-50f4-a462-aa25b42ee3a6 |  | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | 61f789f1-7114-55d1-a9f4-12d9aef6f059 |  | note | Hold Point: In process Inspection
label | d132bfd3-9dd9-5f55-b52a-c04bda96c137 |  | note | Records: FH concrete QA sheet
label | 6616f82f-0a19-599d-a955-ac8d2b7389bd |  | note | Onsite Responsibility: Site Engineer
checkpoint-group |  |  | section | Civil Works
checkpoint-status |  |  | checkpoint | 4 Concrete Footpaths
label | 09108c75-652a-51ab-a457-c54194f2a4ae |  | note | VERIFICATION ACTIVITY: QA FORM
label | cb4b4db8-5d2f-5c15-9b51-df1545a110a3 |  | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | d8270b92-3ad0-5086-a878-227ee0191036 |  | note | FREQUENCY: 10m Intervals
label | 10d7632c-d34c-5ee7-ae20-3f2be0476f98 |  | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3); Basecourse - 100mm min. thickness GAP40; Clegg CIV > 13; Surfacing - Concrete 100mm and 20 Mpa @ 28 days. 4kg/m3 blackoxide with broom finish
label | 373d404a-891b-5298-be69-b19d8160ca95 |  | note | Hold Point: In process Inspection
label | d87c7183-3ade-599f-8cab-bb57c5a7168e |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 86a36192-9b35-5096-ad2e-df0b6420b880 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 5 Concrete Pram Crossings (PX)
label | 5649fcf2-b647-57f3-aa1c-78b529c73366 |  | note | VERIFICATION ACTIVITY: QA FORM
label | cdfa94c3-ad24-5927-a44c-1b6bc5456b77 |  | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006
label | d16216b9-3455-58f0-9153-6205e1a52302 |  | note | FREQUENCY: Each PX
label | 9ea4788e-35a7-55ff-9bde-649c9e4dbe06 |  | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3); Basecourse - 100mm min. GAP40 thickness; Clegg CIV > 15; Surfacing - Concrete 150mm and 20 Mpa @ 28 days. 4kg/m3 blackoxide with broom finish
label | 9845b809-bf91-5aeb-91b8-8e134331772d |  | note | Hold Point: In process Inspection
label | 4830c30a-4acd-5ead-852f-aaa896b96757 |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 9fdd09f9-cddb-5548-81cf-c6ba806d220b |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 5.1 Concrete Pram Crossings (PX)
label | 1926d4a1-a2ae-5c57-a300-a53e022be695 |  | note | VERIFICATION ACTIVITY: QA FORM
label | 7c83d6cf-9c44-57c2-afbb-9aa862635398 |  | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006
label | efc7a520-b3f1-5378-8ae8-f2c4057814f3 |  | note | FREQUENCY: Each PX
label | de3de784-3674-5e2d-bc62-e5efab923c4c |  | note | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 100mm concrete slab underneath
label | a5fa5a4a-56e9-5336-bcf0-2e8e3e7ae4af |  | note | Hold Point: In process Inspection, Measurement
label | 95bbdea2-769c-5f67-8d46-435be8fe06d9 |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 50d095f0-5385-5efd-ae41-5361aee526cf |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6 Grass Berms
label | 7d669ef3-518b-5076-86cd-4c4a880f9a3f |  | note | VERIFICATION ACTIVITY: Visual
label | 23b7915f-ad06-5010-80a7-bf0334546652 |  | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
label | 3ef6647e-5500-562e-bfff-7e5d99ffeb27 |  | note | FREQUENCY: 10m Intervals
label | 6c4daa15-f718-5bec-910f-012ff201b659 |  | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | 6024d63d-ba04-51e4-9681-78b0c3498e0e |  | note | Hold Point: In process Inspection
label | 88f46918-9fa3-5d77-99ca-1817c5282d71 |  | note | Records: Photos
label | 5b96d5ff-66bf-586d-8a47-fa766d549694 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 7 Tactiles
label | 3e7bf4e7-728a-5132-8710-ef5f750812b6 |  | note | VERIFICATION ACTIVITY: Visual
label | 31fdae54-7791-5ef0-96a5-fe62e94be9fe |  | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 0a62939f-426f-505d-9c74-9806dc8dcaa2 |  | note | FREQUENCY: Everysite
label | 29013c46-7669-53d2-8250-310c4d794073 |  | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | 82e1d73b-f91c-5263-8612-e0db02a60226 |  | note | Hold Point: In process Inspection
label | 3a19a80b-f778-560f-8937-266076f20a5c |  | note | Records: Photos
label | 10c84099-bedb-5702-8a3c-1cad3d46a7aa |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 7.1 Tactiles
label | d9f2b062-2bec-5690-9c6c-1cfab0dab920 |  | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | ed7a4d7c-6ebe-50e4-9183-26f9c3e3cd43 |  | note | FREQUENCY: Everysite
label | 4e0276f6-d22e-5b98-a4d5-b0538556cce9 |  | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | 6c9ba8c1-e233-51e2-ac5b-891dcbafa0f0 |  | note | Hold Point: In process Inspection
label | a3f40aa2-f5a8-545f-8882-0dd9c6c1ed92 |  | note | Records: Photos
label | d345bece-edfd-5f34-9243-db7d1369570e |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 7.2 Tactiles
label | 146e4317-08ad-538e-9b1e-51b1c0f87ba5 |  | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 1b83a998-b23b-554c-8c0c-3a7f88116149 |  | note | FREQUENCY: Everysite
label | 8be958b0-e5cb-5acf-a8f4-17120423cb68 |  | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | 172ebfa9-b0ea-5931-9951-01fa947fa53d |  | note | Hold Point: In process Inspection
label | 4cb61080-5852-5883-b26d-586ab07a1a8d |  | note | Records: Photos
label | fa34d376-3e38-5f5e-b42c-62f594a2c7fd |  | note | Onsite Responsibility: Site Engineer
checkpoint-group |  |  | section | RAMM Data
checkpoint-status |  |  | checkpoint | 8 As built information
label | 78516180-81cd-51cc-95b8-761f9639fc1a |  | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | 2a71c6eb-02be-500d-94da-3d1f69a7cfea |  | note | FREQUENCY: Every Site
label | 58154f07-ff0a-5019-adc4-a70034930c43 |  | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | c2f351da-a3aa-5af0-b126-95f90bed971a |  | note | Hold Point: In Process Inspection
label | 3e21d62c-5075-53af-ab4d-d8cf556fe061 |  | note | Records: Asbuilt records
label | 02dbc33b-f793-5498-90ba-1c992fdddd4e |  | note | Onsite Responsibility: Supervisor and Engineer
checklist-flat |  |  | checklist | QA Photos |  |  |  |  | Yes | QA Photos | 2f5e868a-dbe1-470b-a4fa-ea5658af03f4
checkpoint-status |  |  | checkpoint | Add photos here:
checklist-sectioned |  |  | checklist | Traffic Island |  |  |  |  | Yes | ITP - Griffen Park / Hillsborough Rd - Traffic Island | 2fa82182-47d7-4600-9547-6aabbf8ca275
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 1 - Kerb
label | 373d6f47-b2d6-5493-bb69-3b99ed8bc19b |  | note | Verification Activity - QA FORM
label | f703a319-4cd5-57e5-95d7-28a35bbfa150 |  | note | Methods Or Reference - TDM Technical Standards - IS0001 & IS0002
label | 70845417-82a4-59a8-beb0-297aef76ea36 |  | note | Frequency - Every Site
label | c1e81402-aa26-54ba-9388-5f77f3cf8930 |  | note | Acceptance Criteria - Kerb to be laid using precast hand-laid
label | 52c8c547-d598-55e3-ab2c-2d2e43d545d9 |  | note | Hold Point - In Process Inspection
label | 1cccfa9b-8cc0-5fb2-910f-a1055e285c09 |  | note | Records - FH concrete QA sheet, photos.
label | 3edb83b4-7039-528a-b9f1-967d99259681 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 5024cbb9-6d74-5d42-9ff2-0ecfeae152bd |  | note | Verification Activity - Survey
label | dcbc3bc8-e67a-536f-b49e-e654127c31a1 |  | note | Methods Or Reference - Setout Kerb Alignment required to construct to design
label | efe51fad-7610-533c-8e83-b1a620435569 |  | note | Frequency - Prior to commencement.
label | b113aebc-737b-56ae-a973-291027c2b7c8 |  | note | Acceptance Criteria - Survey
label | 99b056b9-ec59-538c-81dc-8e52d4785fc9 |  | note | Hold Point - As per Drawings 3822001-400-CA-1050
label | 1a612227-cb81-509f-9be0-3d0bc1a389b3 |  | note | Records - Survey Receipt.
label | 0474c193-7ec1-591b-bc9b-41bff48bacf0 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Concrete Island
label | 0600e1ac-d3b5-5319-bc05-29fb81ac0617 |  | note | Verification Activity - QA FORM
label | 743636b1-a550-5d0b-8d88-bd2d2167ac42 |  | note | Methods Or Reference - TDM Technical Standards - IS0001 & IS0002
label | 76f20424-37d3-5955-afb2-e1c8c3ae4bb7 |  | note | Frequency - Each Site
label | 53a1ddf2-f39d-5b73-b5b5-b408a2e7a09a |  | note | Acceptance Criteria - Kerb to be precast hand-laid. Kerbing laid on 150mm min GAP 65 subbase in roads. Concrete 20MPa @28 Days
label | 3e7dec68-0fd1-5d56-a6ab-6725de645232 |  | note | Hold Point - In Process Inspection
label | 0a3fed72-75b9-50a6-9753-71e617936935 |  | note | Records - Photos
label | 6e6fa14c-a61e-50e5-9480-b36a650d71f2 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4 - Concrete Infill
label | ea5ce623-459c-52b4-9907-df57a1ef6b1d |  | note | Verification Activity - QA FORM
label | 5a3d5614-6554-5706-b7a5-f184e637797a |  | note | Methods Or Reference - TDM Technical Standards - IS0002
label | dd0600b2-67fb-56b0-a93c-6bdd78a17749 |  | note | Frequency - Each Site
label | 390e57cd-8c76-5509-b804-81bbbc926740 |  | note | Acceptance Criteria - 180mm depth of 20MPa Broomed Concrete with 4kg/m3 red oxide Cross Fall of 2% or max rise in centre of 180mm
label | b207c490-6ff0-50d6-973b-00e186b58448 |  | note | Hold Point - In Process Inspection
label | 8af0e31a-5ea8-5b8e-89d1-53acf2bbe8c6 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | b9db5e3c-f48c-5003-bd44-96776279c46f |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | As Builts
checkpoint-status |  |  | checkpoint | 7 - As built information
label | b3588df0-c52a-58e7-bbc0-be58e5d7d653 |  | note | Verification Activity - Drawings
label | 2427f28e-1715-534b-8fb5-87d884ab1e70 |  | note | Frequency - Every Site
label | 86ebd991-66ea-5a54-b4eb-c90e77c4fc1c |  | note | Acceptance Criteria - As built drawings
label | 15f1f409-e46a-545a-97a9-f7a9b1407d03 |  | note | Hold Point - In Process Inspection
label | 830d56ee-38ee-537c-9073-51ab9baeb67e |  | note | Records - As Built records
label | c04db015-2e04-57c7-9e3c-2831b8091a47 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | 7 - RAMM DATA
label | e0bb4ad5-cbf4-52c2-824a-814846ed8756 |  | note | Verification Activity - RAMM DATA SHEET
label | a3e69262-bfd7-5ccc-b628-9123dd050833 |  | note | Frequency - Every Site
label | ea4df0ba-6d3c-5d6b-9da6-2d14751f8781 |  | note | Acceptance Criteria - RAMM SHEET
label | e8d1e7d4-3a77-5868-8b26-3cd8079a12d9 |  | note | Hold Point - In Process Inspection
label | ce962c3f-1538-542c-8f53-b68ab0faaf35 |  | note | Records - As Built records
label | 09d6fc07-1696-5e65-bca7-3db28e2d9587 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-group |  |  | section | ITP APPROVAL
checkpoint-status |  |  | checkpoint | Final Inspection
label | adba1a61-4a78-564a-a9a9-b2e6c8fc50d0 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | d702b6fd-9e97-5863-b09e-68220c0f6fc4 |  | textbox | Print Name:
text | 85eff86a-673c-5705-87e1-642af949356f |  | textbox | Position:
text | 66263dc0-9832-56fa-a5ec-1183b23b3f77 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP - Massey Road - Enabling Works |  |  |  |  | Yes | ITP - Massey Road - Enabling Works | 34998639-8d25-4621-8f2b-91be9c99aa88
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | 9155c6a7-5d09-5a73-b388-b9277c99c38e |  | note | VERIFICATION ACTIVITY - Surveyor
label | 9573b97c-6575-5bf0-a13e-ed2de3bf4a0d |  | note | METHODS OR REFERENCE - Surveyor
label | 1c9d9c11-fc82-5dcf-b2a7-899225e911ca |  | note | Frequency - Everysite
label | 2748bb4b-c7f1-58a6-bd05-e9d9fe1c20c6 |  | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
label | 18586efe-26e4-52dd-b89a-2f98a1e505b0 |  | note | Mandatory HOLD POINT -
label | a7b4269c-f329-5b0e-97c5-b74f1fee0ec6 |  | note | Records - Onsite records/photos
label | 4ce8fc28-313a-597e-ba50-b9dab4eab221 |  | note | Onsite Responsibility - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Kerb & Channel
label | c6637c69-bc79-5fb7-aac9-993e8c4921b8 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 1d93cb49-cb1d-5799-a49b-851dfc27ce05 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | 9e7939ce-e43b-57b9-a106-8fba8cb2c406 |  | note | Frequency - Everysite
label | aa4d25a1-e4ce-53da-9263-77f5bd60f6b5 |  | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
label | 05b62f31-d290-5536-832b-a067fccbede6 |  | note | Inprocess Inspection
label | 067c9b78-2f07-5e2d-bdb7-0d187b36e8ec |  | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
label | 08ef3b0b-5f36-5786-b928-ca559a08d4da |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Channel Level
label | 4a769b49-d3c6-5259-a255-343b0962fd0e |  | note | VERIFICATION ACTIVITY - QA FORM
label | e8a94b1b-19bc-52c4-9429-7ff10f48736d |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | e852a434-5ef6-5c2c-b9ac-47e830cb70b7 |  | note | Frequency - Everysite
label | 69d4dc2e-588a-53d8-aa4d-b4d3c3ce0b57 |  | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | b4ff52e3-a527-5d72-988c-46a3eec9bce1 |  | note | Inprocess Inspection
label | 775a7c5f-77b6-5235-a5e6-d617767f8af0 |  | note | Records - FH concrete QA sheet
label | 36700016-a72e-5763-899c-1eda087a07cc |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | CIVIL WORKS
checkpoint-status |  |  | checkpoint | 4 - Concrete Footpaths
label | d88ba717-52ee-51ca-95d4-f73496b55bb2 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 27166f9b-94a0-5d13-9cd7-2c55dc08a5db |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
label | 78e0f4ea-f6d3-53e2-a482-81100faae26b |  | note | Frequency - 10m Intervals
label | 6d004f96-7801-5f56-8d6a-f1f72242d959 |  | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 15 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
label | add7cb81-be84-519a-8274-65ff39858af1 |  | note | Inprocess Inspection
label | 187975e0-bea8-5d33-9fbb-953dff2e6c66 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | b683068e-72f4-51b1-9a2c-7ef3b9afabf1 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Concrete Footpaths
label | 7c564fcc-2eca-5773-bc3d-2dfd94dc7fb9 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
label | d857c43a-37b3-5548-bfd2-2382fc758695 |  | note | Frequency - Each PX
label | ec3db974-9dfa-5295-9662-5507b0e3ba8b |  | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
label | 5d41e326-85f5-5122-a13c-c8a265c8bb6d |  | note | Inprocess Inspection, Measurement
label | 0dff9dc3-f262-5bd6-8bed-0af2586228c3 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 1f2aa361-3b53-5a61-828b-5274c1973713 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6 - Tactiles
label | 29670cc4-3be3-567e-83de-83d2cc4c301c |  | note | VERIFICATION ACTIVITY - Visual
label | 92debe81-7eea-5dca-9886-7c401d0d3d37 |  | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | a25c3f13-fe63-599a-b031-a9bb35906ce9 |  | note | Frequency - Everysite
label | 20457c5a-0583-57e4-b61d-ed465b25cfc6 |  | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | a1df43b9-e925-5ab9-85fc-355b6b9e6664 |  | note | Inprocess Inspection
label | de0aadb3-bf94-529f-b18f-1d39f05614bd |  | note | Records - Photos
label | bf6b77f6-062f-5581-9e44-b1a26c96b35c |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6.1 - Tactiles
label | 8971a2f5-bb13-5d42-8aec-67031873b392 |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 4930a5d8-1504-58b5-a6ae-227b8a960e67 |  | note | Frequency - Everysite
label | a66bd602-c95b-5ebb-b09d-724b1ce8ec58 |  | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | e45a8bb6-b2e0-5c43-aa04-7044e66a093c |  | note | Inprocess Inspection
label | 91693cb8-1eb5-502c-983e-091ddf8cdd0f |  | note | Records - Photos
label | e5e4bdf4-e6ba-5c17-840e-a749075c3cdf |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6.2 - Tactiles
label | a79fd993-8fac-5734-81ed-2f67cacc3632 |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | fa0f7d15-68bb-521e-b451-2ccbb60ba758 |  | note | Frequency - Everysite
label | 3ff55ba9-3907-55f9-8aa6-489034704380 |  | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | ac99d625-3e52-5d04-99db-d6b1a4375a95 |  | note | Inprocess Inspection
label | 58402bbf-5419-5b1a-aa0f-9c05b8502954 |  | note | Records - Photos
label | 791c8c5e-72aa-57c0-84bc-41132ca47fbb |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | RAMM DATA
checkpoint-status |  |  | checkpoint | 7 - As built information
label | 8901cea0-5e11-5b6c-aeb6-6729ba0a34f4 |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | eeee5a1e-797e-5f84-932a-eb4062831349 |  | note | Frequency - Every Site
label | b0e274ce-ab14-5457-ad04-b050346328c4 |  | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
label | ea8d0b36-ad77-5706-bd4a-8a7b0f55de1c |  | note | In Process Inspection
label | 0932f658-5f19-5557-85b6-8f14d1794e80 |  | note | Records - Asbuilt records
label | 0dc5f6ba-3f18-5ae5-993c-b23bab282b33 |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-sectioned |  |  | checklist | ITP - Enabling Works - Footpath, Kerb and channel | itp |  |  |  | Yes | 246 Mt Smart Road - ITP - Enabling Works - Footpath, Kerb and channel | 34aea8a2-1fbd-4386-aab5-88fdc41f3678
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | 28af9067-3907-573c-b149-9e433af09fe3 |  | note | Verification Activity: Surveyor
label | 5bbe611c-dd9a-5ba4-a9bf-0c5349513c1b |  | note | Methods or Reference: Surveyor
label | a38833fa-8eaa-56ff-a785-0818981183fc |  | note | Frequency: Everysite
label | 90980f30-5aff-5489-abcb-ddb628d28b6b |  | note | Acceptance Criteria: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | 9016cb4e-fb45-5f1b-8676-e7deeb9cc31e |  | note | Hold Point: Mandatory HOLD POINT -
label | a3127981-4140-5ff4-b8f8-6c93a74c2b37 |  | note | Records: Onsite records/photos
label | f8557566-c692-572e-8618-629ce9ba60ec |  | note | Onsite Responsibility: Site Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Kerb & Channel
label | ae98441b-72f4-5d91-bf36-d263f68c546d |  | note | Verification Activity: QA FORM
label | e591172f-ce4a-50d0-a7c5-c572d8964e6d |  | note | Methods or Reference: TDM Technical Standards - KC0001
label | bd73ea22-8391-5ca7-9e54-818e367adaf6 |  | note | Frequency: Everysite
label | 599a7f43-a4e9-557f-ba49-7d9974865ac7 |  | note | Acceptance Criteria: Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
label | 63de1870-9256-5ea0-ae46-c72523d3c5a4 |  | note | Hold Point: Inprocess Inspection
label | 5a03c66b-a02d-556c-9dc0-ec7571047f5b |  | note | Records: FH concrete QA sheet, photos. Concrete Plant Docket
label | 4a693427-e21c-55f8-8ee6-867138c51f0e |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Channel Level
label | 69588501-1c81-5531-96a5-d0ef2b35fa45 |  | note | Verification Activity: QA FORM
label | 501a4de2-2ab8-5599-8a26-00db66daacf3 |  | note | Methods or Reference: TDM Technical Standards - KC0001
label | 2481e9ce-9467-5bf0-b749-85e5810b9be0 |  | note | Frequency: Everysite
label | 26eb411a-58b1-5395-bd4b-50d8731bf94a |  | note | Acceptance Criteria: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | dcf1d24c-ef92-5170-83ce-2fda9203bf55 |  | note | Hold Point: Inprocess Inspection
label | dcd48ffa-e8a6-5c0d-b47f-46a02c1e37ef |  | note | Records: FH concrete QA sheet
label | 470cffb4-c802-50c7-aaef-62b754a05df2 |  | note | Onsite Responsibility: Site Engineer
checkpoint-group |  |  | section | Civil Works
checkpoint-status |  |  | checkpoint | 4 - AC Footpaths
label | 360faaa3-58da-5716-b511-8c7f99a05809 |  | note | Verification Activity: QA FORM
label | 76df872c-3de4-5e44-813b-e6e45d79401f |  | note | Methods or Reference: TDM Technical Standards - FP0001
label | b87b6aeb-9adb-57c3-b344-864da35083de |  | note | Frequency: 10m Intervals
label | 4c926d4f-aea4-59c3-b98b-a57c25b98983 |  | note | Acceptance Criteria: Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 13 DG7/Fine asphalt mix used
label | 44be6f0b-5cb4-5463-b3cd-95a824f55bec |  | note | Hold Point: Inprocess Inspection
label | 648f5e7c-cc7c-5c48-ab10-b28ca423e01e |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 4fd3179f-cbcc-5636-9017-aa73c5ce366d |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 5
label | 1a4eeb7c-706d-5154-91b0-f1b863b9fc43 |  | note | Methods or Reference: TDM Technical Standards - FP0010
label | aa1c3723-0526-58cf-9602-33119ad96cbd |  | note | Frequency: Each PX
label | 9de28d85-3dbf-55d9-acc2-e45a1bcb1b7a |  | note | Acceptance Criteria: Warning TGSI tiles should have 100mm concrete slab underneath
label | 13ae3394-e7da-5d38-9c12-25b9cb87972f |  | note | Hold Point: Inprocess Inspection, Measurement
label | 51631c4f-75cb-5cbb-85e2-7297528f3cc7 |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 9e8bc478-a192-5d54-8e98-f8d2af7f4d28 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6 - Tactiles
label | 7a408965-998e-51d7-8c09-bfab333c63a3 |  | note | Verification Activity: Visual
label | 54b5acee-0b96-5195-ad4d-c66201c09bc6 |  | note | Methods or Reference: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 04fad576-b129-5785-8cd8-eff41bd93252 |  | note | Frequency: Everysite
label | 8f1783c7-09e0-56fe-8131-156a58a74435 |  | note | Acceptance Criteria: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | ed0bb9cd-2fa5-5926-9f3c-0c822e65221b |  | note | Hold Point: Inprocess Inspection
label | 88724539-c8a4-5d23-bb54-eaf00ed3c266 |  | note | Records: Photos
label | 7b2d7616-cb9a-53e3-a08d-79a29ec904df |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6.1
label | aaa81e67-21af-50b1-98fc-aaca7781a2b2 |  | note | Methods or Reference: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 2263b8af-4814-5bd4-89d0-fa12efb4eb15 |  | note | Frequency: Everysite
label | 57c3a1cd-b97a-5e3a-9df4-77241fc41c86 |  | note | Acceptance Criteria: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | 8c24a03a-e90f-505f-9945-37cc5df97aef |  | note | Hold Point: Inprocess Inspection
label | 33ff4d8e-93ed-593b-b419-2fab03c7189d |  | note | Records: Photos
label | d85ba369-1150-58de-be1d-465699e213bb |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6.2
label | 7f18ef1b-5c6d-59d2-87dd-476e3648dcbd |  | note | Methods or Reference: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 84e9fb5b-e95a-5dae-8e7a-bcd0ed955df7 |  | note | Frequency: Everysite
label | c0b22230-f005-58e0-8692-8e1ce4079496 |  | note | Acceptance Criteria: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | 20b62379-331e-5e75-9d03-1751e73fb35d |  | note | Hold Point: Inprocess Inspection
label | c38114f2-ef79-55fe-91f1-83ea0e287b91 |  | note | Records: Photos
label | 92f470ef-0879-52f9-82f2-b92735fd69ad |  | note | Onsite Responsibility: Site Engineer
checkpoint-group |  |  | section | RAMM Data
checkpoint-status |  |  | checkpoint | 7 - As built information
label | 381f7027-a38e-5552-8866-90e621159167 |  | note | Verification Activity: RAMM DATA SHEET
label | 11174d25-8cc1-5386-a032-616ab1e60de3 |  | note | Methods or Reference:
label | 493982f8-e13d-5495-92a0-66eb2fbbe661 |  | note | Frequency: Every Site
label | 09238ef7-8dcb-55ed-91f2-5b73764f6eab |  | note | Acceptance Criteria: As built drawings and Ramm Sheets Completed
label | c8c6ab3a-753d-5ce7-9acf-01954db369ff |  | note | Hold Point: In Process Inspection
label | af8f41a2-a384-5545-931b-b4681e7afe5e |  | note | Records: Asbuilt records
label | 26fa43cc-8986-5046-8076-83ace7b0e518 |  | note | Onsite Responsibility: Supervisor and Engineer
checkpoint-no-status |  |  | checkpoint | ITP Approval
label | 8593682a-9a1d-5656-affd-18e2fbb6a540 |  | note | Prepared by: Cimyona Vinbi (02/08/21)
label | a4278548-6457-585c-909b-682143522766 |  | note | Approving Delegate: Daniel Tat (25/08/21)
checklist-sectioned |  |  | checklist | ITP - Willcott Street - Enabling Works - Footpath, Kerb and channel | itp |  |  |  | Yes | ITP - Willcott Street - Enabling Works - Footpath, Kerb and channel | 36c9094f-0450-4503-8b62-8d08388d94a0
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | fe7669da-6274-5b82-9c62-da112ed2cd1c |  | note | VERIFICATION ACTIVITY - Surveyor
label | b37bfad9-b7ae-5023-a0a1-ff241dd63ff5 |  | note | METHODS OR REFERENCE - Surveyor
label | b859282d-955c-5bb8-834e-df34509706d7 |  | note | FREQUENCY - Everysite
label | 44fcf706-2d78-5cce-8d91-3b085b537954 |  | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | 0347124a-7096-55d9-80a8-7f3485c23eb4 |  | note | Mandatory HOLD POINT -
label | 16b60e06-4540-528a-aed2-f887ec671278 |  | note | Records - Onsite records/photos
label | f41ff7b4-6dd4-526c-917b-03c1bc96e0cb |  | note | Onsite Responsibility - Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2a - Kerb & Channel
label | 374f0fb0-b379-5942-9ad1-1633879aec82 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 6699c17b-e0ce-5e7e-a822-7424e4abfbb9 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | e1aa31e5-0229-50e2-851b-8929a596591d |  | note | FREQUENCY - Everysite
label | f7e9b4d2-bc6d-5b78-9c5e-f9ee8f173577 |  | note | ACCEPTANCE CRITERIA - Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min GAP65 sub base in roads and 100mm GAP 40 in footpaths (CBR>5).Concrete 20MPa @28 Days
label | b5530dcb-f3a7-56de-898f-c1eb31dce512 |  | note | In Process Inspection
label | d1810342-4360-505f-9885-8e438df2c2f4 |  | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
label | c621d01b-52a9-5474-a136-23fe513d4f37 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 2b - Traffic Island
label | bf9e3cda-f86b-53a2-b658-2f43111d2325 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 7c98590b-158f-5824-bdc3-f05030911108 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001
label | 3cca3033-6b1a-5a77-bdf0-da9d169efd76 |  | note | FREQUENCY - Everysite
label | 04ad4b2d-7a2d-5141-b3d9-091129e8ccfb |  | note | ACCEPTANCE CRITERIA - Kerb to be laid using precast hand-laid
label | 91896da4-e30d-5407-80f6-70f7f12e1ac1 |  | note | In Process Inspection
label | 05096f82-99bc-5a16-9a83-d58de7e4aa5f |  | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
label | 92cd9b5c-b94f-5f93-bc3a-530f20785de1 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Channel Level
label | b2964c88-8917-5e31-b1ad-2af80cc10e6a |  | note | VERIFICATION ACTIVITY - QA FORM
label | 6a479bc4-0271-5a30-9406-c7faf0e1da3c |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | 6431a47e-61e5-5541-9d87-7775c1c80228 |  | note | FREQUENCY - Everysite
label | 81cd2ddf-1ba3-54a7-98ce-d63418437641 |  | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | 56e4988f-a3eb-5a06-a37c-770e2928bdb4 |  | note | In Process Inspection
label | e5b15406-0b6d-534a-92ca-3faec902862d |  | note | Records - FH concrete QA sheet
label | ce38894e-0375-5344-94aa-523dc8fb02c0 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | CIVIL WORKS
checkpoint-status |  |  | checkpoint | 4 - Concrete Footpaths
label | 57312936-a7a2-5fc3-8bd9-1c8fea800aea |  | note | VERIFICATION ACTIVITY - QA FORM
label | 2eeaa6b8-cc05-5019-b8ae-d1daeca3288a |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
label | d336ba70-3021-5339-94aa-4c3a7729bbde |  | note | FREQUENCY - 10m Intervals
label | 2df84ce0-bb0f-526c-8d99-dcd780fc23e6 |  | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish
label | b18515c9-6d4e-5c7c-b12c-d4927f0b7340 |  | note | In Process Inspection
label | 54addf5a-7b35-5fec-8667-5d7c50d61409 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 15f89bef-2f4e-502c-8e04-40fe1bbc2f99 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4.1 -
label | 51a57011-fe8d-55c1-a34f-703f3b079c9c |  | note | VERIFICATION ACTIVITY - QA FORM
label | 0aa8ba4f-8375-5c02-a708-5c61255aa98b |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0006
label | 9d3496a9-856e-5818-b907-f2ea586c6d54 |  | note | FREQUENCY - Each PX
label | 2c4119e5-c627-5a88-abcb-5becec5aeb3a |  | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
label | 1210d743-66aa-5052-b06e-39b669a49666 |  | note | In Process Inspection, Measurement
label | 757f38b5-0119-5e83-8a9c-68e90d0ba88a |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 30bc6166-11f3-57c6-9069-ba3d7f2fd6ee |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Grass Berms
label | 2d5c6772-c905-5ee3-ac35-2577a0adb8fb |  | note | VERIFICATION ACTIVITY - Visual
label | fbf0e3b4-c563-5621-84c8-1791d715d3fc |  | note | METHODS OR REFERENCE - ATCOP Section 12 Footpaths and Pedestrian Facilities
label | ce134998-1dde-53f9-9bc2-68a983aeab69 |  | note | FREQUENCY - 10m Intervals
label | 19fd1c16-02a8-5905-b8d9-cd822ec8a296 |  | note | ACCEPTANCE CRITERIA - 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | 5d95e54f-2749-5d62-9b5a-aec69a571b7b |  | note | In Process Inspection
label | 8c78e1eb-6b54-57ac-bb5b-5126d97cafa8 |  | note | Records - Photos
label | ef27de54-2ac4-5973-a6b4-c7d1117c67b9 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6 - Tactiles
label | 716c917f-f1e5-5322-9c12-5be429857f5c |  | note | VERIFICATION ACTIVITY - Visual
label | 756dc9b4-7322-5818-bc1c-51ae959156c0 |  | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | f337673b-bac4-5254-9f81-dc9fb5e44ae0 |  | note | FREQUENCY - Everysite
label | 814be53f-3171-5d86-87b1-da5fbfd6770c |  | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | 41a5e299-d5d4-5264-a616-09530a05f7e8 |  | note | In Process Inspection
label | b504a74b-cb26-5dd5-8835-52d2b43037f0 |  | note | Records - Photos
label | 86f8ca93-5fa0-5ff5-8b0d-40da0536e334 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6.1
label | 0af71293-3ae1-54af-8957-0a090cf7df7c |  | note | VERIFICATION ACTIVITY -
label | f265ddc2-7b04-50f6-87ad-d3d8a4387f60 |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | dbdfcd9f-1798-57b4-b930-83c05b4fc39d |  | note | FREQUENCY - Everysite
label | 8e9b88f3-05f1-5758-baef-e47e98ac6a28 |  | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | 4925ed03-24db-5b74-8336-eae5cc486b57 |  | note | In Process Inspection
label | 6788a83b-1e90-56b2-b76b-3b5b4f441d86 |  | note | Records - Photos
label | 15dee8aa-6c0f-5996-ab4b-4bb3daf2a0b1 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6.2 -
label | 6453ad1c-e5c6-53b7-837f-d327e508a40a |  | note | VERIFICATION ACTIVITY -
label | a303a267-0c97-5719-b2f6-6664acd6cb8b |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 9b18d9a2-0f29-5661-bfd8-c981df3a3560 |  | note | FREQUENCY - Everysite
label | 62ef37da-3ee6-52f9-baa2-a6d869234368 |  | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | 5a1f6fe8-86d6-54e9-b66b-6a3ea8bfca94 |  | note | In Process Inspection
label | f9f7f835-702e-56f7-b9d1-f276a0d5c532 |  | note | Records - Photos
label | 92b4fd07-56ea-5657-8b31-99b5303f69d2 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 7 - Concrete Island
label | 74c08020-e07c-5f62-8374-b56bc6dc8195 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 442787e5-ce07-5e76-876e-584d8dd88a4f |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001
label | 55f93f04-e4f3-5fc6-b520-3a7341243cf9 |  | note | FREQUENCY - Each Site
label | 582b46ea-02b5-5a95-83fc-9988db55b7b4 |  | note | ACCEPTANCE CRITERIA - Kerb & Channel to be precast hand-laid. Kerbing laid on 150mm min GAP65 sub base in roads.Concrete 20MPa @28 Days
label | 6fc68b79-92e6-5fe2-8120-936b9897839f |  | note | In Process Inspection
label | 488c216e-56dd-505b-9254-ccd5894fd4b3 |  | note | Records - Photos
label | 1975d59c-a4c3-5ebe-9137-52e1ba163d31 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 8 - Concrete Infil
label | c25b34fe-8518-5bad-a761-c781f26f5d5f |  | note | VERIFICATION ACTIVITY - QA FORM
label | 81c3c65e-5e71-5323-a9a4-17ecf0e52b69 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | be5e38aa-6413-56c9-ba6e-0798ac37cc9c |  | note | FREQUENCY - Each Site
label | 52551102-77ab-52da-a816-ad7a6cef95d7 |  | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa McCallum Chip with 3kg/m3 Red Oxide - Exposed Cross Fall of 10% or max rise in centre of 150mm
label | 392c07ed-ad56-57a6-9e94-087241102cdf |  | note | In Process Inspection
label | 35479df3-c323-54ea-a7d2-e8c0b3b62860 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | f9e71482-ab9d-5528-866d-103941bb068b |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | RAMM DATA
checkpoint-status |  |  | checkpoint | 9 - As built information
label | 2344fac6-2d9c-5bcb-b718-5bef33a39292 |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | e628f297-c1b5-50d6-86f9-67f992a25af5 |  | note | METHODS OR REFERENCE -
label | 51799d8b-a6a6-5818-87d2-b017438d4d09 |  | note | FREQUENCY - Every Site
label | 11a3066f-7a6e-5a0b-8496-f570a1040c65 |  | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
label | 947d66f3-7cb8-5c2d-826b-2302bd07d551 |  | note | In Process Inspection
label | c5b931fe-0a03-52d3-b757-c1559d6e7676 |  | note | Records - Asbuilt records
label | 84aa7768-5818-5f99-bf55-546181072b89 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 7746dbb7-329e-55a1-818e-7b229836e9d7 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | c7dce318-b7c9-586b-a80a-020bd21926dd |  | textbox | Print Name:
text | 0250584b-af87-58a3-ad15-86fadd51163d |  | textbox | Position:
text | 5bbb851c-b915-5dc4-a979-034ca9aabdd3 |  | textbox | Date:
checklist-flat |  |  | checklist | ITP - St Lukes Road/Morningside Drive intersection - Concrete Speedtable |  |  |  |  | Yes | ITP - St Lukes Road/Morningside Drive intersection - Concrete Speedtable | 3af1a026-2d05-4b11-9b24-e1bc18bea14f
checkpoint-status |  |  | checkpoint | 1 - Permits
label | e6f3aff5-0470-5358-97c8-75890da90e52 |  | note | H
label | fd02a609-4748-5423-ba94-1a6b32646d70 |  | note | Detail - Obtain Permits
label | 41c4671b-bb58-5b70-aa26-e1a780c100b3 |  | note | Frequency - As required
label | 7db272a8-e8c4-5088-9f49-da3af3ecf3fe |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | aef79d54-2ba2-5701-a532-b6cf2877725c |  | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 2d1d7724-90d0-5e6e-b5a5-7bd51ee9c1fd |  | note | Records - Permit attached or permit number noted
label | 78448a1f-755e-58a6-8b1e-33e96a5413f0 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-construction sign offs
label | 7e1d353d-199b-57ee-8b0f-4e7a26094cf4 |  | note | H
label | 5956bcf0-ea6a-5c49-a143-79d31231b1e3 |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
label | f9fd521d-b8a0-5d3c-afe9-258481c68823 |  | note | Frequency - Prior to commencement
label | d10a92e7-412a-558c-a5c3-aec4cad342dc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | cfb16333-1272-509c-b8d5-b998d425500b |  | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
label | fb205010-5e0d-5dd3-b6f1-3f1cf8f0343d |  | note | Records - Subcontract and Supplier Agreements
label | 1648a4e1-9348-5fab-9592-71a9dee2914f |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1 -
label | acf1a44a-6857-51fd-98f0-7ac93157d55d |  | note | H
label | c30b5540-3280-5e88-9483-c305ece1a499 |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | d8e74fb9-d412-54a0-9a07-a5a4e3ea144b |  | note | Frequency - Prior to commencement
label | a5244250-5b36-5ef0-9353-52ceb8470648 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 5129e841-6de8-52aa-ac5e-4ee8b02a301b |  | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | b353e649-e78a-50f2-8f10-104adcf353e9 |  | note | Records - TMP on MyWorksites/On Site
label | 55d40d2d-7193-50ab-871d-cc94fb4664a8 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 -
label | aadab849-959b-5f46-9336-a7ada69d3a81 |  | note | H
label | 48927965-f30e-5139-909f-e17b8a07e769 |  | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
label | 65bf89c4-fc85-5746-905a-037e14adb4a4 |  | note | Frequency - On site daily
label | 8c1558f2-0bdc-5a20-9122-a5d273ddd1e5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Induction
label | d3be0450-fce1-56a1-96be-6d6a681057ef |  | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | 892b25f5-6d32-5c78-b567-b82c8134967a |  | note | Records - Hazard ID and Pre-starts to safety team
label | 99ceaf5d-5b06-5abe-8c20-3b32679e46e9 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 5c2baddc-bc2d-5ce8-acb9-9c0fdc5460c6 |  | note | H
label | af531e0f-36c0-5e7c-af68-f96bfab78a58 |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | b9724924-6cc8-553b-b0ff-44298cc90cee |  | note | Frequency - Prior to commencement
label | 1bbb7d5c-8dbc-5e20-b2a2-9ae2f95bf771 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | c3c15c7f-7c66-5650-b978-d77d94c5ae43 |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | 889a8405-bebc-5df6-8394-4c873d9c629c |  | note | Records - Check Drawing Register
label | dd80d9e4-7f37-56f2-951f-fdd807a08871 |  | note | FH Initials - Site Engineer
label | cc56dd9a-7d83-5ae4-b822-5bfd353ac45e |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Installation of Erosion and Sediment Controls
label | 8758f403-b4d7-566a-9ee2-e21b6edb2b2b |  | note | H
label | 55f4d2f3-1214-56bd-acd5-4ceb5b8a0dfb |  | note | Detail - Ensure that Erosion & Sediment Control in place
label | 3d4e8182-66a9-5fd6-bb4a-bc6e60cb6d06 |  | note | Frequency - Prior to commencement
label | 75fc6e28-9ac1-5286-a8fb-62380cc2e08c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 828d9487-4f43-58c1-bb63-e66771bbba79 |  | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | 2de43f08-14e6-5a4e-84a7-9f83c33a4132 |  | note | Records - Environmental Controls Audit
label | d61a3d8e-7042-5f82-a49a-7aed4a72a44e |  | note | FH Initials - Environmental Manager/Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | 4fe38ba4-17ce-5b8e-95a1-06caffc5e200 |  | note | H
label | f7726095-63be-5714-bee4-c3a99a88156a |  | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | 846065df-2d51-5384-a886-903b0b9eada3 |  | note | Frequency - Prior to commencement
label | de5c25bb-b83d-5cc8-a4ca-4dca07b288b6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey + Smart Level
label | 47caa804-391f-50a5-bae3-9f78cbb6fd1a |  | note | Conformance Criteria - Consistency with Construction Drawing
label | babb074b-ad66-5d8c-9121-ae0a15c77bcb |  | note | Records - Site Photos post surveying
label | 55b8d5b7-0749-5509-9fcb-f792d435ea49 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging
label | 0768858f-dd07-52ce-9583-50fa9cadd59a |  | note | H
label | 5399135f-2013-5aaf-b3cc-aba95f5f73d5 |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | 2c1ba671-5d31-59d0-b3a4-cc5de88a9a0c |  | note | Frequency - Prior to commencement
label | 2b147023-e2f8-5077-a138-09faa8f45313 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | 01ba10b2-5ef5-58ea-97de-8172cc73e709 |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | 9039067d-fd1b-5412-a5df-8f580b2fa6dc |  | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
label | 99a9ef7b-fa0a-5c74-a499-3770228c0bdc |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Material Compliance
label | 6aab4d36-20bd-5d9a-931a-a88ceb1e7a04 |  | note | H
label | 15301909-8be2-52ca-805f-6de5f31dfdf8 |  | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
label | 74747b08-34aa-52ed-bbb4-30f51eaeb748 |  | note | Frequency - Prior to pouring concrete
label | bcb0cf01-b73b-5bec-8afd-177c92e2afc9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | a98fa5e4-f3af-51e0-b147-a0620c2be4ce |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | dac2ce38-5301-5742-8989-2f28af4a3044 |  | note | Records - Delivery Dockets / Photos
label | 20825d9e-a563-5edb-914e-b237f168e543 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1 -
label | 9613c092-9e7b-54c2-8a6b-d09c6c30e099 |  | note | H
label | 8e81ee63-23e3-5a49-aefc-0fa9ff286568 |  | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
label | 20a79c14-bf80-56a5-a431-cc1f4844af3f |  | note | Frequency - Prior to pouring concrete
label | 2e05a09b-0f25-58cf-8c3d-69ec1ff45151 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
label | 5cc318d4-c501-5cdd-8886-b5b49e6baafc |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 2bd2f254-a3e2-54d0-8065-6496f9aff4fd |  | note | Records - Delivery Dockets / Photos
label | ec232d54-0057-55a8-9eaf-362920f33086 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 -
label | bf88917e-1075-50ff-85b0-51617eba3628 |  | note | H
label | 69ea281d-0d1c-5581-bc76-b47dae8d500e |  | note | Detail - 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | 2e88c977-22d6-50ba-807e-09a1822bc3b1 |  | note | Frequency - Prior to pouring concrete
label | fe1cbf54-e33b-5fc3-98fd-fde4731cc756 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 0e31f1b1-7dc1-5ffa-a9e0-5655349db1b4 |  | note | Conformance Criteria - CIV >15
label | 9ce8d69b-ed89-5653-aae1-60fd203091e8 |  | note | Records - Delivery Dockets
label | 8cf5391b-af65-5663-9bf1-31dd87ca1574 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 -
label | 32fb9b68-3c17-58dd-8d4d-b7c0bdce39af |  | note | H
label | 0f50a400-a0df-565f-8879-99ea41c2faba |  | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
label | 344c4a77-4136-59d9-b8d5-9812aaf329f4 |  | note | Frequency - Prior to pouring concrete
label | 6f1ecc3c-1309-5e25-a24b-4fab0c66f24a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 6fd498e0-dd39-5cb6-b1fc-cf6c52515808 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.4 -
label | c8e99f56-9bd0-5ccc-8fc2-82eb053ed0fc |  | note | H
label | 1ef8b20b-0ba0-5be8-b5cb-d8f711154344 |  | note | Detail - All concrete delivered to site shall have 40MPa 28 day compressive strength.
label | ac9eb8d2-f5fb-5c7f-8c92-8b4a32f5b31b |  | note | Frequency - Prior to pouring concrete
label | 90641c57-a546-54f4-8573-14cdce4be2ad |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
label | b826276c-75f4-522c-bed5-cb9318c25cad |  | note | Conformance Criteria - Delivery Docket added to QA folder
label | 48ffc458-5d15-522c-9410-95eed908b2eb |  | note | Records - Concrete Delivery Dockets
label | 62d8de6a-b2fb-522d-9a4a-3825a8891408 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Temporary Works (Formwork)
label | 19fb0c70-de13-56b5-881c-ebf509261ae3 |  | note | W
label | 4b0b7756-09f0-5a5e-9570-7dda8de66338 |  | note | Detail - Formwork to be set to correct line and level
label | 235b5018-8e92-510b-bf48-bc9a225c7c22 |  | note | Frequency - Prior to pouring concrete
label | 46e419be-1691-56d9-a7c8-fffa0bab293a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 618f5b3c-3620-5995-a816-a88e27392178 |  | note | Conformance Criteria - Concrete Inspection Record
label | 6458be77-4888-53cd-8f00-857591f5a1b8 |  | note | Records - Concrete Formwork Checklist
label | afc49c63-875f-58fa-a70d-15d60d073cb7 |  | note | FH Initials - Site Engineer
label | e73de57b-b4c6-543a-932e-906097bc8694 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
checkpoint-status |  |  | checkpoint | 8.1 -
label | b62795d2-5f19-5eb3-ba01-990f6c4142aa |  | note | H
label | 7e65f452-12a5-5d4c-bd9d-562056143ad7 |  | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:20)
label | 89384c74-ec92-5fa2-8a60-c7c1397078b4 |  | note | Frequency - Prior to pouring concrete
label | 611d3844-9b16-5174-a47c-8e0b9dc18f1f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | b33b2625-706e-5256-a533-3eb27149844b |  | note | Conformance Criteria - Designer to inspect formation level
label | acf8d60e-8452-5ce4-aed9-ff6f1f3a779f |  | note | Records - Site photos
label | a8b366d6-dc55-5068-b9d5-092edbea97f1 |  | note | FH Initials - Site Engineer
label | 5dc13e63-6ba7-5f09-802b-0f9150b5720a |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2 -
label | e088c2b2-93ae-5404-8227-c0fc00a45efa |  | note | H
label | 6bf786d1-f3be-59c9-9c55-fed1f7ca77a3 |  | note | Detail - Raised Table ramps to have 225mm depth at entry point and tie into 300mm depth to meet raised table
label | 925d3092-880d-5e9e-9643-229fd50dd7da |  | note | Frequency - Prior to pouring concrete
label | af01d05e-ac06-5efc-98b9-9c93f364a131 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 86d13bc5-f144-5fdf-b3fd-95a183c01d56 |  | note | Conformance Criteria - Designer to inspect formation level
label | 57e48085-dc26-51e8-99b8-7156bbdf8efe |  | note | Records - Site photos
label | 89282ea8-5565-5d21-9443-59a39f194aab |  | note | FH Initials - Site Engineer
label | c138f05c-b530-53be-a9bd-589e920b266c |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.3 -
label | 658c4e45-1ae8-5f60-ba65-ad5b739bea00 |  | note | H
label | ebed6b8b-9d91-5747-8278-7c2953074c09 |  | note | Detail - Raised Table ramps to be 1.125m across for entry and 1.5m for departure ramp.Toe to be 500mm across for both entry and departure with 50mm asphaltic wearing course
label | d53c5757-d3a5-5b5b-8241-0f0a3c138763 |  | note | Frequency - Prior to pouring concrete
label | fb23081c-1f45-55e6-af23-02df0db1bfcd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 1d153967-6f52-5523-adad-f6501c4a5c9a |  | note | Conformance Criteria - Designer to inspect formation level
label | 98138558-644d-52fe-9a40-aa2f29081a69 |  | note | Records - Site photos
label | b08af23a-c1f2-5231-98d5-a797430bfabf |  | note | FH Initials - Site Engineer
label | 3ee05bb4-24b3-52a8-a3da-7afc2838da01 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4 -
label | c3ec490e-e4d7-57ed-9972-c07366d35bf5 |  | note | H
label | 63255b5c-d8d9-54a7-b3f6-392f9fea4c8f |  | note | Detail - Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:20 relative to the road
label | 22b523f8-1727-5bb3-85c1-e0186e428fe1 |  | note | Frequency - Prior to pouring concrete
label | 18fc7162-42ce-5879-ac36-6977af3144cc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | cbc61997-42d6-5634-8145-22519694257c |  | note | Conformance Criteria - Designer to inspect gradient level
label | 15350c10-1822-53bc-b9aa-c320f697a964 |  | note | Records - Site photos / Concrete Formwork Checklist
label | 4d5f8669-9fd6-5893-b615-4280b0ead012 |  | note | FH Initials - Site Engineer
label | 9a7e44cb-a942-5641-b3a2-fcdce6571248 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5 -
label | 0c026ec0-6032-566a-8165-d9406a28c649 |  | note | H
label | f1f0c425-7173-5b93-8ece-9d929bead5a2 |  | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | c4461c77-8bf2-5b4d-bd0a-ade97502b11d |  | note | Frequency - Prior to concrete pour
label | fe2df19e-ff74-5e46-8a56-1859e647add9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 6e7ad922-b5c2-5b3a-a37b-d95fc5dac8c7 |  | note | Conformance Criteria - Concrete Inspection Record
label | cb2384eb-3300-5704-915e-8ccc2a9d074c |  | note | Records - Concrete Formwork Checklist
label | 3e09a072-0054-596a-a693-3ea8006974f6 |  | note | FH Initials - Site Engineer
label | b2d1615d-a442-51cf-8071-ca4e4ee6befa |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Reinforcing
label | ee7cb76e-0755-5508-aa1c-22772563fd2f |  | note | H
label | a7539c49-67f3-5e26-aeb5-98800590c9ad |  | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
label | 45b5f670-6e28-50d7-a29e-8f7cf4c5cfb5 |  | note | Frequency - Prior to pouring concrete
label | 71dc8be3-8949-55e9-ac63-25e50897a7d6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | a706aaef-4448-58fb-9f47-fd2f041e34d7 |  | note | Conformance Criteria - Concrete Inspection Record
label | 338d6aca-1efd-5d2f-8855-cce3d267d26f |  | note | Records - Site photos/Concrete Formwork Checklist
label | d3f8b6fc-2a16-5380-b2f2-91b44895b9f9 |  | note | FH Initials - Site Engineer
label | 33f82467-7e4d-5b86-9ae1-ada41f59e9a8 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Concreting
label | 4237f0ca-9fba-5299-a315-826db45fe10a |  | note | H
label | 07238b6a-bbd6-58f2-a5e0-1a311dfda13a |  | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | f7561ab4-76c1-522b-9ae6-8f88fdf68624 |  | note | Frequency - Prior to concrete pour
label | 67694c03-e3b3-5fd7-bab1-5ef7395adb96 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 1bb43b39-4a52-58e1-9f50-b6cddb67929e |  | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | 6aaa7dd5-b949-5f7d-b997-a7d791d72309 |  | note | Records - Email / SMS
label | d45ff984-706a-516d-84e2-5aa0ea7d0c11 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1 -
label | 08708b46-4ce6-5093-911a-3fff77e9b2bc |  | note | W
label | 15392a1d-20d7-5fa0-8a57-50b73e9cb5c1 |  | note | Detail - Vibrator to be used throughout concrete pour
label | e45c2447-5d21-5b6c-9b17-355c0ff633c4 |  | note | Frequency - When pouring concrete
label | 5123d0d9-b129-5ee7-8900-a0827975e273 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c9dfdd7e-0f47-5e6b-9f12-cfd5b08e5d42 |  | note | Conformance Criteria - Concrete Inspection Record
label | f6a2731e-1b7b-5e6b-b48c-d57925ced47e |  | note | Records - Concrete Formwork Checklist
label | 470562a4-ea32-518f-b87e-e9b09731e355 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 10.2 -
label | 0c7364dc-4740-52af-9f38-ccc88a98a805 |  | note | H
label | b1aa4c65-59cd-502e-9d69-98ce98fed5b2 |  | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and Broom finish for table top.
label | a3823129-0cb2-512a-a694-3c16cdbbc008 |  | note | Frequency - At completion of pour
label | cec0da1c-4f81-561c-b6d3-f83c7f7f986f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | d99d4e14-19c0-5b3a-9564-6dad85581a37 |  | note | Conformance Criteria - Concrete Inspection Record
label | 5d396126-f539-5fa0-817e-282145cb57d9 |  | note | Records - Concrete Formwork Checklist
label | 83566065-4aa0-5f65-9b52-90ba5b17c9e4 |  | note | FH Initials - Site Engineer
label | 3f5209d6-a04d-5cb0-bcbf-2209c14746f4 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Curing
label | 54bf2699-e56f-5300-99e3-abf4c4c44df6 |  | note | M
label | c628a77f-aac6-5149-ad95-380e0b24d733 |  | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | 185a26e4-2e29-52cf-87c5-27b1f04f9f3e |  | note | Frequency - Post Pour
label | 3e775228-a562-586a-ac6d-c8cef29beb42 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Monitoring the time allowed for curing
label | 45566ceb-329e-53c5-9e6b-8d95805d2db4 |  | note | Conformance Criteria - 48 hours minimum have passed
label | ff195f01-c20c-5007-b2ae-3a75b65d484c |  | note | Records - Concrete Formwork Checklist
label | 2803c909-ed76-5088-950e-9a319f20048d |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 12 - Remove formwork
label | cba53c53-3958-5503-a12b-750022c97f10 |  | note | W
label | c43720b2-1313-5970-b519-46f4375b16a5 |  | note | Detail - Remove formwork after 48 hours
label | e12a7676-81a8-56e5-8d5e-2f4f80bf32db |  | note | Frequency - Post Curing
label | ea2a5b97-3052-5f3d-a644-e6a7b3ca970c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 09a64a2b-de22-5141-b457-d6e4237c03db |  | note | Conformance Criteria - Concrete Inspection Record
label | 6d195efd-4c18-5e6d-9e6b-100a4b4f454b |  | note | Records - Concrete Formwork Checklist
label | 7ace8843-6191-559b-8ad6-3d9cd4a5717c |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
label | 728b3958-9730-513e-86bf-072e0745352c |  | note | H
label | 0007bfed-7a22-5dd1-8ec4-ca38c899f902 |  | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
label | 3a1b2b50-4d59-59aa-aefe-1aea13f71797 |  | note | Frequency - Prior to pouring concrete
label | 1c97043e-0b87-5dad-9f2e-7ee52fb2397f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | d191a1fc-6d3a-54f1-9f1b-0f3665f0c95a |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 04583b29-af3e-5cd3-b68d-c47d85fb5c5d |  | note | Records - Site photos,delivery dockets
label | faecba07-e2e3-5301-b81f-e875ee02320d |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.1 -
label | 4dd0113d-32b7-5bf8-af24-616ebbb4fc1b |  | note | H
label | be579026-2dbc-59a6-b588-0fa93285c761 |  | note | Detail - 200mm thick 40MPa Concrete with two layers of 663 mesh
label | f75fe17f-430e-5d4f-89b1-05988bf46faa |  | note | Frequency - Prior to pouring concrete
label | d27c2678-c1bc-566a-abde-933c21bdc8c1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 5b8f58cd-62b2-57ed-9d44-fdadb48b3f4d |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | f9c4a930-94ff-56bb-a2d8-093b466f5b19 |  | note | Records - Site photos,delivery dockets
label | b10c4419-fddd-5c09-9622-c8f1584d4ae8 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.2 -
label | b84b0889-635f-59c4-9e9b-b65e9d687c62 |  | note | W
label | 180ce1a1-f9fa-57dd-8dce-935d7fdd1ec2 |  | note | Detail - Tack Coat between AC and Concrete slab
label | 811f987c-29cb-5acb-bd4e-6f4480ca5d22 |  | note | Frequency - Post Curing
label | b982c650-16ef-5e11-9ace-71dc57b459e4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 788d8abe-28ab-572e-92e8-3c640d078b07 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | b9fa4499-f84a-519b-ac98-e5b6cbf46a76 |  | note | Records - Site photos
label | e8a9c97b-2542-59a7-8d23-16cadb754ddf |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 13.3 -
label | 736ecd61-052d-537f-bdbe-f897cc973e38 |  | note | W
label | d7d6a4b6-a53b-5e9a-9160-403386cb59d0 |  | note | Detail - 50mm thick DG10 / Mix 7
label | c5fe3ecf-7b0a-504c-ad89-08cafe555091 |  | note | Frequency - Post Curing
label | ced5b99a-c3f7-5b9a-b886-5b86d237b029 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 16365f84-6ba2-5534-99ad-aef348077c03 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 6ff5cb27-9172-5563-a314-281add39b653 |  | note | Records - Site photos,delivery dockets
label | 6466cb25-b9d7-5fce-8ecc-39dc57c296b5 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 14 - Lot Number QA File
label | e542647e-5a17-5bde-aa78-d7e59362697b |  | note | W
label | 6e62f79b-d4b0-5c6d-aed8-cdf6c62825d5 |  | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | f6f68ff5-c3f6-5d03-ba66-074b754b3f4c |  | note | Frequency - At completion of Lot
label | 9d19ff42-9c5c-5ac1-a77d-01e4ea481410 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 3867f0ff-7ab8-58aa-848b-8e9acfbc3dc0 |  | note | Conformance Criteria - All QA files compiled and sumbitted to client
label | 9b7fc674-e8dc-5429-aab9-14673b1b34e0 |  | note | Records - QA records
label | de1b14c8-618c-5638-bb2b-21fbb0d1b9a6 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 14.1 -
label | 3bab4240-c0e2-5d8f-a991-34657fb8dc9a |  | note | W
label | 6dd47010-c19d-5797-a343-adb8c706c5ab |  | note | Detail - Delivery Dockets to be included in QA file
label | 7f1dabf3-843e-50f3-948c-a94dff54319c |  | note | Frequency - At completion of Lot
label | 7f0f1af6-e4b3-5373-909f-f62dcf2eab9e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 901be100-0e14-5288-b6f9-b7a70b41052c |  | note | Conformance Criteria - Delivery Dockets to be included in QA file
label | d6dfa4e6-4e14-54c9-a1dc-3be456c0a9f6 |  | note | Records - QA records
label | 55b2c9ce-9030-5a6c-b8f5-c9251c401644 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | 645ac489-8462-5816-b897-a6644a947282 |  | note | H
label | 10f5a458-1da2-5967-a35b-04a912d9ac78 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 788cfc91-9402-51c0-91cb-f6699845b650 |  | note | Frequency - At the completion of the Lot of work
label | 885c344d-1b68-5582-be45-7c78ef12d7ec |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | c6acc0fd-8a1f-5ae7-b29f-29d5d532fac5 |  | note | Records - Asbuilt Drawing
label | f7e536f5-ef2c-5781-87d8-2ef8dee989bf |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | Raised Pedestrian Crossing |  |  |  |  | Yes | Tui Rd - ITP - Raised Pedestrian Crossing | 3e01324b-97bd-4304-a695-40a5afc03c19
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 27fec997-1f82-5310-a4cc-3f9691948a2b |  | note | ACTION (Hold, Monitor, Witness) - H
label | a2c20484-92b0-5cab-a6a3-d03a74dc4fb7 |  | note | Detail - Obtain Permits
label | d4b27eea-bd64-57a3-ae39-3ebbdb2fe6f1 |  | note | Frequency - As required
label | 7f910878-89d2-51db-b2fc-5f71824a2120 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | cba007e9-dee3-500a-bbdf-6c78285df40c |  | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 5cda6189-272a-54c8-9343-26d493350df0 |  | note | Records - Permit attached or permit number noted
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-construction sign offs
label | ba50fcd4-3675-5e7a-a113-e0a274676de4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 82160531-d395-5185-9442-e95248c6a068 |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
label | f8b58947-2fd3-5fcd-a022-a0315636a32f |  | note | Frequency - Prior to commencement
label | 05024f3f-3f15-5eb2-80e1-6d830cca0280 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | ab121d92-9fa0-50e5-b67d-4cd715289895 |  | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
label | bf8e1f66-bfa9-5009-bb87-878a6e656cbd |  | note | Records - Subcontract and Supplier Agreements
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1
label | 490b54d8-cee7-5a0d-b461-4ee5588d78cc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 10b73f78-e2aa-5c01-b948-cb06210857bd |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | 2d6817f0-3d5c-5707-b2e6-710e8d101630 |  | note | Frequency - Prior to commencement
label | c4fae244-28fa-5940-8b7d-ba856b892ffc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 2beb7e66-f246-5f81-b78d-3e9a02c78f71 |  | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | 30c6733f-bca0-53a6-8edc-44cecd16c7de |  | note | Records - TMP on MyWorksites/On Site
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2
label | 012826eb-b484-5c37-a7bf-64795adb6cdb |  | note | ACTION (Hold, Monitor, Witness) - H
label | b0bbf113-6700-5eb3-9efc-b7b615a18b9b |  | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
label | af959d9f-b841-5718-b712-271de5bd4e5b |  | note | Frequency - On site daily
label | 067e1182-c9ce-5fa0-a3d5-8b9749c1ace4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Induction
label | a620bf16-832d-5732-a10b-f63122d21cca |  | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | c94c1fa4-4ded-51d6-b54e-12044eaf5934 |  | note | Records - Hazard ID and Pre-starts to safety team
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | af37a7f9-2c6a-52ff-8b90-909bfd02d07e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2e8076e2-a0d5-5bb7-ae4d-7d0ec5b6306d |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 53b66ce6-bc5c-5f33-93ec-01e24a0f9106 |  | note | Frequency - Prior to commencement
label | c94cebb2-abbc-5020-adb0-17627839f839 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | fb971300-7f0f-5d04-90ab-502f2a32dce6 |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | c7993e25-9740-57df-9ac8-32e8b18ec4e2 |  | note | Records - Check Drawing Register
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Installation of Erosion and Sediment Controls
label | e5fb46a3-8771-53fb-9667-9e6734bf3e09 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c0431ac0-e406-5b79-ab8c-56fb3b0363ea |  | note | Detail - Ensure that Erosion & Sediment Control in place
label | ab73a007-3845-5cfe-93d3-753f7d4cb9ba |  | note | Frequency - Prior to commencement
label | 2c3af693-6dd0-5d2b-a723-00799acf837e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | bf4c223e-a5cc-5950-85ad-6b75cefaf7e7 |  | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | f4e9ee70-9473-52fd-9a5e-969cbbe57b14 |  | note | Records - Environmental Controls Audit
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | 815a3378-44d4-54df-8e16-4d6c3c6cefce |  | note | ACTION (Hold, Monitor, Witness) - H
label | 593a26be-1f05-5362-9506-766133abb7b9 |  | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | 8c29b851-2b47-5048-a8af-044146a4f6da |  | note | Frequency - Prior to commencement
label | 795013d8-3fd6-5bbe-b461-cd50fef67134 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey + Smart Level
label | 7e84dfb9-1526-5a4d-8540-5e2f80164207 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 72b42055-b6d9-5a27-ad36-b7190376faab |  | note | Records - Site Photos post surveying
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging
label | c856d8b7-357a-5203-99f5-31deade7ad26 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2ec4271b-00a1-556c-bf1e-126f33d791e4 |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | 2654617d-8eff-524a-af84-598f53ad8aca |  | note | Frequency - Prior to commencement
label | 3277c81e-d5c4-5c99-b1b7-958090c6aff1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | c614999f-8faf-51e6-bdcd-d48482767e51 |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | 5230a6cd-2373-52a7-ae05-ac9a18b557a4 |  | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Material Compliance
label | 0b40cfbc-833f-5d05-a151-2f4007b2d180 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e6c93ce3-581c-533e-b389-42b50db2837e |  | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
label | 51326119-fb06-56cc-8a9f-3ceb529edd06 |  | note | Frequency - Prior to pouring concrete
label | e89f17e8-3833-58dc-8ca2-50e7ecad1ec9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | b3eeddcf-c067-5bbc-99ea-a1329329a47d |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | f1892a36-aef6-5b9b-beef-3c4b9e773cb7 |  | note | Records - Delivery Dockets / Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1
label | 48b882b9-5650-5ffd-b95e-f1eec2830178 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 889f887b-3692-5ca0-918a-866a30299a37 |  | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
label | 50359d7c-5839-5b20-9bc5-d3d8ee586712 |  | note | Frequency - Prior to pouring concrete
label | 7430aedc-15a4-5911-9d6d-5936562d16d2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
label | add1d6bc-90ec-5128-9dbb-53a0d4f0f212 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 6531d092-9893-552e-9d4c-431af47713f3 |  | note | Records - Delivery Dockets / Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2
label | 47b5926c-e98d-5c36-8ecd-82e7847f4670 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f77521dc-e705-5eaf-bd98-84ed6ab85e65 |  | note | Detail - 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | 7cf6a455-319b-52de-8bb4-5c0624f06c5e |  | note | Frequency - Prior to pouring concrete
label | dbc8dc95-45a1-5fb1-b2a1-8999d8fe2ba5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 52840ab0-e0c1-5e69-a331-31a44a64a55f |  | note | Conformance Criteria - CIV >15
label | edb89037-6b6d-5877-817e-0b6c5f2924ea |  | note | Records - Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3
label | 59a05472-de83-5b1b-811e-1b663163b10c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7e33e390-6ced-571a-8ccf-22e49bbbcd6e |  | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs separating.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.4
label | 0ba35755-f9d6-593b-8cfd-b5b8915ac50a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7dac000e-cb7d-5434-98c6-691aaf3a25b8 |  | note | Detail - All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
label | 871477b2-c4b9-56d0-9dce-bbdb7e7c8bc7 |  | note | Frequency - Prior to pouring concrete
label | a5c08413-d741-5698-b848-2db4c9565c21 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
label | 30d097ea-1547-5f61-a6d0-b88edce8bb5d |  | note | Conformance Criteria - Delivery Docket added to QA folder
label | 52c5f6ec-e404-550d-a6ad-f78191c91d9a |  | note | Records - Concrete Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Temporary Works (Formwork)
label | bbf4a7ac-639e-54a4-92a3-be6aae7ac957 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 28c6005a-d6f6-5be2-b8c2-c78c9bdd9ac5 |  | note | Detail - Formwork to be set to correct line and level
label | 7db1a44d-138b-58f9-98d1-4bd677ba6241 |  | note | Frequency - Prior to pouring concrete
label | e00ef60f-7a88-5b22-9f8d-ee43da8d8dc7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 21bffa84-4409-5d4f-b0fb-42219375537a |  | note | Conformance Criteria - Concrete Inspection Record
label | 2e873039-432c-5a1a-9043-5175589eacfd |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 8.1
label | e757b3b5-b337-5965-85e3-54340712c0d5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 73319b19-0ff2-506c-bbce-711d4c186787 |  | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:15)
label | 478ac928-e26f-5909-90eb-acad76d70cbe |  | note | Frequency - Prior to pouring concrete
label | a72e45b0-4eda-5396-9ad0-9f2771da502d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | a462f941-cdb2-57d0-9f0a-e8b209444a13 |  | note | Conformance Criteria - Designer to inspect formation level
label | b6915d64-da34-5392-bd43-673942c091ae |  | note | Records - Site photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2
label | afa30351-bcbc-5dc4-8602-ebff08308d52 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d597cb87-06ba-5bb9-9093-3ccae6ac94fb |  | note | Detail - Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table
label | 84aec1bd-33c1-5c58-9786-5cd6d7ded30d |  | note | Frequency - Prior to pouring concrete
label | e25982b3-80d9-50d3-a436-3e733298eb3e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 9d935748-7ce1-5299-a5fd-d4a5916740b7 |  | note | Conformance Criteria - Designer to inspect formation level
label | 333b4c8b-37e1-5f98-bd3e-5b26e6548b6a |  | note | Records - Site photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.3
label | def772d5-d7d3-50ef-a721-8444f53c14f4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 25253775-40d1-5a4b-8a13-15ec440f6d1c |  | note | Detail - Raised Table ramps to be 1.125m across for entry and 1.125m for departure ramp.Toe to be 0.5 to 1m across for both entry and departure with 50mm asphaltic wearing course
label | 90bfdea5-90b7-5657-8d22-68d78803e614 |  | note | Frequency - Prior to pouring concrete
label | 6fd89d6a-1756-5e3e-a654-5d3b651c7592 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 85d79df7-de17-5e7d-bd89-b0d59fd44efe |  | note | Conformance Criteria - Designer to inspect formation level
label | aa6659c1-8018-5057-9b1a-aaf97974fb9c |  | note | Records - Site photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4
label | c5c20c4e-35b5-528b-a7ad-51046fbeb61b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 92c8a804-0a8b-5711-856a-a5c4de819972 |  | note | Detail - Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:15 relative to the road
label | 5416dafe-4bd5-5372-94c8-e5e1fe8dc175 |  | note | Frequency - Prior to pouring concrete
label | 77cb0788-79f4-56f0-a33d-3e45d46bdce8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 7ba57623-f318-5530-8a5c-9487a0e5b271 |  | note | Conformance Criteria - Designer to inspect gradient level
label | abbb0998-17d0-5efe-a368-fdcfb9a5c603 |  | note | Records - Site photos / Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5
label | 03b3871e-8b5d-579f-b624-600fab2edb4b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 14c1af3b-0a67-553d-96af-81e97e3ee855 |  | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | b8b72f22-3b69-5364-9042-2d91b0c6b7fc |  | note | Frequency - Prior to concrete pour
label | a947dc27-166f-5f9f-bf9c-52f2a217a8ee |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 89535c5e-fa95-5ff3-9d7e-60f66ba0f58a |  | note | Conformance Criteria - Concrete Inspection Record
label | d9df0870-7595-52f7-819f-052bc02233f7 |  | note | Records - Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Reinforcing
label | a483b9ca-69dd-5d0e-965a-9876b6d06dd8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f8562a44-3b70-5632-894e-17bb4af885eb |  | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
label | c65ab12b-6d56-5159-9d97-e6d403eee0e3 |  | note | Frequency - Prior to pouring concrete
label | c60057f7-1942-52f2-8def-a93f33fd5557 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | e46da85f-2479-5a14-a043-28a5437457a5 |  | note | Conformance Criteria - Concrete Inspection Record
label | 87b1e9f5-c841-57f2-88e8-6f2a0bf8e63d |  | note | Records - Site photos/Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Concreting
label | 97896867-eeaf-5669-bad0-933437fd437c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3e2fec61-c2dc-5909-98f3-3e43dd43a197 |  | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | dd91c8a3-aa9c-5d52-bdc6-e20ff79db6b1 |  | note | Frequency - Prior to concrete pour
label | 730251a8-99e1-5e3e-a425-18068f1a53c2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | adfc2b04-0311-5462-bc5e-42481609a712 |  | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | 141ddc00-758a-5c78-9ea1-99d96eb70498 |  | note | Records - Email / SMS
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1
label | 69a7e782-0f20-505a-98ec-b3e7c658a1ae |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1b882c26-2e89-5dee-863b-97b2323fbd0c |  | note | Detail - Vibrator to be used throughout concrete pour
label | e7fed74c-3981-525a-8fa7-3e521d430634 |  | note | Frequency - When pouring concrete
label | d917a995-e97b-51fd-93dc-904643423fec |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 0a0b4d49-5465-5fb2-8337-d0042d902169 |  | note | Conformance Criteria - Concrete Inspection Record
label | 137e8a40-f5dc-5c6d-85f8-487a576970ae |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 10.2
label | 55104ca2-1171-5c98-a807-caf5f5bdfdcc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 874da190-d784-5979-be8b-4dc692c0b4a1 |  | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
label | dc95e63c-d0ed-53fb-84e5-8cb6c1846885 |  | note | Frequency - At completion of pour
label | e0573e3c-88f3-5801-ab47-d79ac13a7ecc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 75ae0ee2-9b1f-5ff8-be6c-f0a0df9f82e0 |  | note | Conformance Criteria - Concrete Inspection Record
label | 7697fd61-0dca-59a9-b4d1-102d26a7a314 |  | note | Records - Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Curing
label | 227f88b0-defc-59a4-b352-961044a03245 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 6ee763f0-07d1-515d-836c-3fb9effb7d37 |  | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | f4dcc119-1795-5dc1-a2ef-79c4cfd1b896 |  | note | Frequency - Post Pour
label | 9b0383db-3e56-5781-bd64-3d095d90fd5d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Monitoring the time allowed for curing
label | 1b26a275-ef51-5599-8c30-2e780b200566 |  | note | Conformance Criteria - 48 hours minimum have passed
label | 0a7ebac8-54e0-5356-9e0b-7dcef3ce630d |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 12 - Remove formwork
label | 449818d5-a8fa-5432-901b-84273c1baf4f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8ba838c0-117d-54e9-a163-aafce54e32e3 |  | note | Detail - Remove formwork after 48 hours
label | 1b267b34-95bd-51ef-98c6-2213412ec75f |  | note | Frequency - Post Curing
label | 2720970a-a745-56b1-ab59-07e8eddb9a7f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | c9844558-aad9-5670-9261-bf04227f82bc |  | note | Conformance Criteria - Concrete Inspection Record
label | 380839cc-96a3-5bf7-bddd-d7d6f2a0f6ee |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
label | e4e6cb12-36cd-5be5-ad6c-d82e34f146d7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7406339c-6ea2-5b73-a93b-3a9a37d8085d |  | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
label | f52b5f74-874e-59f7-8b81-e297374b6e30 |  | note | Frequency - Prior to pouring concrete
label | 1fb52637-98a5-5d4c-a017-e2fdb27352e9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | afa15d5e-0f9f-5d32-8ccc-eb24fc92ad38 |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 033aec2b-ff3a-526e-a5a5-9dc1eef75402 |  | note | Records - Site photos,delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.1
label | 5b4601b9-3da8-5548-ab46-595494f86d5c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 61e36202-407b-58d6-ad9f-8481b35a1d40 |  | note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
label | 28ea4af2-0b57-5405-a810-be40ff73f3e2 |  | note | Frequency - Prior to pouring concrete
label | 186f1635-b6b6-525b-8fad-7dbd6a981c28 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 216ceaa9-74e6-50a8-8fd8-7f2e7d224541 |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | a528a1ce-ab92-54b0-85f5-82c41fd5f307 |  | note | Records - Site photos,delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.2
label | 424df050-ce1b-5d7f-bd0c-a6219fc685bb |  | note | ACTION (Hold, Monitor, Witness) - W
label | 019e82fa-e648-5f14-b981-eb8406cf8e9d |  | note | Detail - Tack Coat between AC and Concrete slab
label | 6fa81800-074b-591d-bc88-b0865b2cd700 |  | note | Frequency - Post Curing
label | aef84e74-7adc-50f0-ab2c-cce47a8feb6c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 12031c5e-62f6-5f52-9012-43b6d47ce676 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | a6725812-8963-53ed-8f3e-5b6739097eea |  | note | Records - Site photos
checkpoint-status |  |  | checkpoint | 13.3
label | 69a64a59-21c4-578a-962a-830c2dabb06d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6f6b6986-7281-5a94-ac09-6d6deb338865 |  | note | Detail - 50mm thick DG10 / Mix 7
label | 3e85a88a-fda3-5e82-ba42-5b3f025bb890 |  | note | Frequency - Post Curing
label | b8a364da-5b5e-552d-8629-883309a956b6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 09b600e8-603b-5b68-bbb9-7359aa74aac1 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 8f6fa0e8-02f3-5e72-80ec-e3395ef9f6ed |  | note | Records - Site photos,delivery dockets
checkpoint-status |  |  | checkpoint | 14 - Lot Number QA File
label | 66319e01-9a8e-5da4-9638-24ac676faf5d |  | note | ACTION (Hold, Monitor, Witness) - W
label | f1ac64d9-90f4-5d08-8288-892c1b229ced |  | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | 0adc26f3-d8c5-58ca-b6a8-1ed26b528fd6 |  | note | Frequency - At completion of Lot
label | a60ccfde-8c3c-577c-8a6c-a4671dc0bd0b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 008633e3-7f2a-539f-ae24-293654ffe57a |  | note | Conformance Criteria - All QA files compiled and submitted to client
label | f8cb7811-06b8-50ee-8538-5c3fa0184ff8 |  | note | Records - QA records
checkpoint-status |  |  | checkpoint | 14.1
label | 19c0fec5-a764-5d59-bc01-668d47d83585 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c112341e-37cc-55c2-9ca4-7a51cd0c288f |  | note | Detail - Delivery Dockets to be included in QA file
label | 4b44d7a0-d2ab-5adf-8d46-cc76328eceae |  | note | Frequency - At completion of Lot
label | b1ac1b10-9e79-5895-8c94-2156aed14103 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | d5a387e5-1cdf-56a7-8317-98d0ba782942 |  | note | Conformance Criteria - Delivery Dockets to be included in QA file
label | a0e1de13-b60d-5148-a8f8-be104e1450a4 |  | note | Records - QA records
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | 8a21c5a9-6a5f-54d6-8e30-8c3e17a96fb6 |  | note | ACTION (Hold, Monitor, Witness) - H
label | dbcfa9ea-b4ec-508c-8b77-d6f22736ee67 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 2e95b181-a164-54fb-93b3-fe14f66a0952 |  | note | Frequency - At the completion of the Lot of work
label | 1ca6fcea-f576-5c6f-9ff8-65089baf9549 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | df59df4b-91b4-5000-897e-646da754b63e |  | note | Records - Asbuilt Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | Drainage Checklist |  |  |  |  | Yes | Drainage Checklist | 400c3f10-644b-4774-8a10-9fcad652b2dc
checkpoint-status |  |  | checkpoint | Alignment set out by surveyor
checkpoint-status |  |  | checkpoint | All existing services identified before trenching
checkpoint-status |  |  | checkpoint | Trench must be made safe before any person may enter the trench
checkpoint-status |  |  | checkpoint | Base of trench is clean and inspected Scalar penetrometer testing
label | 337c4845-f58b-5f5e-88ca-305aa8898bb3 |  | note | Every 10m , >3 Blows/150mm [CBR 3.5] , >3 Blows/200mm [CBR 2]
checkpoint-status |  |  | checkpoint | Undercut Required
label | eb6fd978-ec14-53e4-bf36-15eef0127fa3 |  | note | Cleg > 25
checkpoint-status |  |  | checkpoint | Geotextile Required
label | 6e4d2364-70bf-54d9-a1e5-ff69a719ef52 |  | note | Cleg > 25
checkpoint-status |  |  | checkpoint | Clegg Impact Value
label | bc1a74e6-9859-52c4-b418-16d4fb6b36fe |  | note | Cleg > 25
checkpoint-status |  |  | checkpoint | Drainage pipes, M/H, C/P to be:
boolean | 4697cc2e-9114-5864-a359-3ffa1b1e1998 |  | tickbox | Inspected and shows no signs of “greening”
boolean | 1bd87336-6775-53d3-b56d-33ffbb61650f |  | tickbox | Rubber rings (pipes)
boolean | fc4bc9c5-434d-5d15-9f8f-6b5b1ecafadc |  | tickbox | Product certification
checkpoint-status |  |  | checkpoint | Trench width and depth to correct target
label | 49fa4f14-3e0b-5a89-9cb4-9b15fcc80caf |  | note | Photos – per 20m
checkpoint-status |  |  | checkpoint | Pipe alignment and laser level check
checkpoint-status |  |  | checkpoint | Bedding and Pipe surround to be placed at specified pipe diameter requirements 100mm bedding; 200mm wall; 150mm cover
label | 3321a537-9425-5cb6-b3a0-b6cfb6b2e16e |  | note | G/SAP <12 Pipe Photos – per 20m
checkpoint-status |  |  | checkpoint | Backfill in layers less than 200mm
label | e703a204-a4c6-513b-8919-0cf7da836ef9 |  | note | ITP requirements Photos – per 20m Clegg > 25
checkpoint-status |  |  | checkpoint | CCTV Inspection
checklist-flat |  |  | checklist | Road Pavement |  |  |  |  | Yes | Ponsonby - ITP - Road Pavement | 4b125756-4eca-4bf5-b9df-7aab35427020
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 650cb897-55e5-5744-ab2c-f95d3b8e85f6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d2fee65f-75f6-5fa2-b8b2-f8dcc508fdd3 |  | note | Detail - Obtain Permits
label | 4d001545-e484-5543-ba38-8293ad2325b5 |  | note | Frequency - As required
label | 2d06e13f-a177-5b70-94f5-0ab45aa7cead |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | be154133-028d-5a5b-8324-05e2af5a4e88 |  | note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services).
label | 092e0334-afa1-561e-a2f5-49b9016181de |  | note | • Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | cd1e8d5f-1332-5cf8-9eca-809f98ec4c7a |  | note | Records - Permit number noted
checkpoint-status |  |  | checkpoint | 2 - Traffic Management
label | fd97452c-476c-579b-9352-a69cd1366501 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f30925ac-1941-55b6-a1c6-5f722939121b |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | 1bebb46e-2998-5ed1-a5d4-67518d0c63e7 |  | note | Frequency - Prior to commencement
label | 89f73add-3d40-59a1-b8a3-9bca5b73a148 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | b14294ad-884f-5db8-a4fa-bdce7898388f |  | note | Conformance Criteria - TMP is approved by AT for the site and works are only completed within the approved dates
label | ecd235c3-756d-5580-9015-fb655736521a |  | note | Records - TMP on MyWorksites/OnSite
checkpoint-status |  |  | checkpoint | 3 - Pre-construction sign offs
label | f5506347-dd97-5a61-8a22-416c99a399e9 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 710eb364-3d46-5b39-bc0c-68fd955431f8 |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site
label | bc220d1e-ec4f-514a-b30a-16a79decbb1d |  | note | Frequency - Prior to commencement
label | 6fee3de2-4e96-57bd-aade-3df6d9fa3cd0 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | aa1cd132-dfec-5696-b665-1e71d01d2b23 |  | note | Conformance Criteria - Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated
label | 71e8aa6f-272b-554d-ae4a-15a2b2884a4a |  | note | Records - Subcontract and Supplier Agreements, A & Updated Induction Register
checkpoint-status |  |  | checkpoint | 4 - Design
label | e313c924-7ea7-534d-a83c-d7c3c2e73961 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 545f88ea-5c10-5785-a434-de95c1dace26 |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | 9b2d3b0e-f961-57cb-a88a-6fb8285e2539 |  | note | Frequency - Prior to commencement
label | d8c06c6f-27ff-5722-a606-2f288b0d7ac4 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 9ea6d8f7-7c20-50db-a3dc-78c45368209c |  | note | Conformance Criteria - IFC Label on drawings
label | d098c525-cf39-5777-9026-831d297dc82b |  | note | Records - Check Drawing Register
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Subgrade
label | 6f75d136-4e2b-534c-914b-ef1c2ddf6175 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 93341fe2-2662-51ac-adcf-ab976cf9b5f3 |  | note | Detail - Subgrade Scala Penetrometer Testing (CBR) at 10m intervals in each traffic lane-staggered and /or stitch section - unless directed otherwise by engineer
label | 8185976c-2e70-572a-8087-4135756eae64 |  | note | Frequency - 10m
label | 9530531f-158d-5280-b7ae-eb8ff57dbe66 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
label | 9080c388-0534-5b7e-b2b5-ef59878d79f1 |  | note | Conformance Criteria - Accepted by or subgrade improvement instruction received from AT representative/Engineer
label | 20e64fdb-67cd-5f99-8b7f-51dd05f860ae |  | note | Records - Testing records/ QA sheets if applicable
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Subgrade (2)
label | 5db491f9-67bc-527c-88c6-8078582275e8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7d01d9ac-9d37-5ab7-bd55-02b5fb3c14b8 |  | note | Detail - Subgrade undercutting/improvement inpsection
label | 4d851e2f-83b5-58a6-b325-40f34e0f56d7 |  | note | Frequency - Prior to commencement
label | 0af71473-ff2e-52f7-996b-fc0caa8c7ace |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | 952a6033-df89-5945-842c-9ed0f7409914 |  | note | Conformance Criteria - Accepted by or subgrade improvement instruction received from AT representative/Engineer
label | 4f87ba6d-2ae7-5938-900d-18a1cca61768 |  | note | Records - Testing records/ QA sheets if applicable
checkpoint-status |  |  | checkpoint | 5 - Subgrade (3)
label | bd8dea97-7c5c-542b-bc9b-5ef39de861d6 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 65568008-a85b-577b-89e9-cd2967d89e89 |  | note | Detail - Subgrade surfacing stringing
label | eebb6f52-6662-56a7-854a-79cd00185dd3 |  | note | Frequency - 1 in 10m
label | a8b01238-6d24-5bb6-a4fd-feec630336a7 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
label | f7341e31-288a-59c4-b035-76185ee12d08 |  | note | Conformance Criteria - Straight edge: ±30mm/3m
label | 2ae9c82b-bf30-58ed-b84c-76da29b82c27 |  | note | Records - QA sheets
checkpoint-status |  |  | checkpoint | 6 - Subbase-GAP65
label | 264f38dd-db2f-5076-b4b1-60860cf480d6 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1dc359b6-deb8-5648-bec5-73f8160b7fdd |  | note | Detail - Material source testing approved
label | 1f726534-305e-516d-ac56-a46cb7a2903d |  | note | Frequency - Prior to commencement
label | 18d72302-944d-59f3-bf55-feb37d652762 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Submission and review
label | b2da41a8-65b7-5889-ae1b-e8e005a9a530 |  | note | Conformance Criteria - Meets specified criteria and lab test report is recent within 6 months
label | 6b02ecec-0df9-5611-b7c4-f6c6ad002c83 |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 6 - Subbase-GAP65 (2)
label | c48ff0ac-464b-5542-9e5b-c704d95018b6 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 7f56ca0f-64a9-57e8-9e45-e76843382536 |  | note | Detail - Material delivery
label | fb7aa4bd-231e-5fdf-b3f6-8a455d333dba |  | note | Frequency - Prior to commencement
label | 62184562-ffa4-5a36-aa47-d0b8c7615f5a |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | 75611aed-e55a-556b-89ce-ec48dbde9d57 |  | note | Conformance Criteria - Check for quality of material
label | 7744a49c-2dfe-5a1b-91b6-40be56fa01bb |  | note | Records - Visual inspection
checkpoint-status |  |  | checkpoint | 6 - Subbase-GAP65 (3)
label | f7ef6801-17c0-58e8-aa58-1f8640c8737e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4d4d3477-664c-5a18-b878-9f7603606fac |  | note | Detail - Surface shape-stringing line check
label | 8b2f71fa-32f6-5cfd-97f0-9fa3f4a92ae9 |  | note | Frequency - 1 in 10m
label | 58147e05-cf63-550b-b82c-22d1bb3dfc41 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
label | 986b25dd-27d0-545d-8a72-53be8da10c79 |  | note | Conformance Criteria - Within tolerances, ±20mm
label | d05cf65a-4c36-543c-a9ad-8d9cd7341aee |  | note | • Crossfall no depart from exisitng crossfall or instruction from AT represenative/engineer
label | 3b3965c6-2332-504f-8f9c-408cbbd443d9 |  | note | Records - QA sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Subbase-GAP65 (4)
label | bbff3bf3-0a13-57ad-88a2-989063b00544 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 544cb04f-395c-58b4-9bbc-71eb7041956a |  | note | Detail - Compaction-NDM tests
label | 3cb76d59-408f-5515-bd3b-004dfabd6a27 |  | note | Frequency - 1 test per 30m of road per lane, staggered at 15m
label | f94adfc1-6b32-5fc5-966e-438c0ee2ad84 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
label | d9a970e4-0743-5cec-b780-8aaaa4df168a |  | note | Conformance Criteria - Mean >=95% of MDD
label | 11c3225b-cab7-5a3f-a71b-1e1e5acaad42 |  | note | • Minimum>=92% of MDD
label | 7f4a0e02-c70c-5f60-945b-ebcbd86d5d33 |  | note | Records - Testing records/
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Subbase-GAP65 (5)
label | a7371b43-1cd3-5660-871d-de3006091406 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 10226c7b-fe0f-5c8f-a1fe-b550a5b79679 |  | note | Detail - Benkelman Beam Deflection Test
label | 278c3961-121a-5a92-a654-71d1aac8cfcb |  | note | Frequency - at 10m intervals in each traffic lane-staggered
label | e6532d5f-146f-5dc8-9283-88aa872e61ad |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
label | 6f668a25-ebc6-5aaa-8082-88d32b38fbd9 |  | note | Conformance Criteria - <=1mm (or specified by AT representative/engineer)
label | 013fef3b-15b7-50db-b12c-23002d3b4dfd |  | note | • Not applicable to stitch section
label | d0515114-0583-5a17-8f74-e3a8cd5beff7 |  | note | Records - Testing records/
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Basecourse-NZTA M/4 AP40
label | 5b7e6249-28db-5369-a919-60b47724c437 |  | note | ACTION (Hold, Monitor, Witness) - M
label | ead9b31a-feaf-5328-9f16-7802e3d7971d |  | note | Detail - All chamfer to be 20mm, kerb joints to be 10mm min cement mortared
label | 57272d77-7cd0-5fb6-9257-d10b94020561 |  | note | Frequency - Prior installation
label | c5557798-a4be-5905-8f11-837f44889cd1 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection and Measurement
label | 7f95a97e-eebf-5c61-98c3-2928371972be |  | note | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
label | cce1e4de-6e72-5f88-a589-5ebd46a1825d |  | note | Records - ATCOP, Photos
checkpoint-status |  |  | checkpoint | 7 - Basecourse-NZTA M/4 AP40 (2)
label | 98830768-85f4-5f88-a82c-af97e1e13040 |  | note | ACTION (Hold, Monitor, Witness) - M
label | f7dc2b2e-021b-549b-9084-8e9eeaf494c4 |  | note | Detail - Material source testing approved
label | 30747b26-8ef2-51de-97fe-337ab0f30599 |  | note | Frequency - Prior to commencement
label | a927b3b1-d111-5b5e-8f90-d4f8896d9e4b |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Submission and review
label | 749c38ff-3d35-5340-93cf-9f0adadafd2b |  | note | Conformance Criteria - 1/ source and at least 1/6 months
label | 39fa9d32-f613-58b1-a18f-7a8dc7b7a49f |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 7 - Basecourse-NZTA M/4 AP40 (3)
label | 7f618ef9-5e4b-5d9c-8b9a-9e90290fbeec |  | note | ACTION (Hold, Monitor, Witness) - M
label | 53a5e55e-a29e-56ec-a8e2-7aa9a2dfd90a |  | note | Detail - Material delivery
label | 6d4e866b-f2a8-5638-a9b3-52fcd321e30e |  | note | Frequency - Prior to commencement
label | 99c88d04-f9be-5a7a-ad6d-9a79bfe789b6 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | d8813ca7-2614-588b-9d47-d512c2c8b035 |  | note | Conformance Criteria - Check for quality of material
label | f8caa4f6-6317-577f-a6db-2fbe1d734b83 |  | note | Records - Visual inspection
checkpoint-status |  |  | checkpoint | 7 - Basecourse-NZTA M/4 AP40 (4)
label | c7f54511-18cc-5e42-b490-c640ad6fbecd |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6ea58cba-2cf1-529e-b76a-2ae26d81faff |  | note | Detail - Surface shape-stringing line check
label | 12cb7e7f-f280-5013-9d15-82b910162b2a |  | note | Frequency - 1 in 10m
label | 227df80f-fbe1-5fab-beee-7c0b67440a0c |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
label | 66b53d96-2d7e-57ef-8fec-c4918152a999 |  | note | Conformance Criteria - Within tolerances, ±5mm
label | 5d036741-4146-54a7-b660-5b9faa9e8149 |  | note | • Crossfall no depart from exisitng crossfall
label | e140ff16-6ead-5c35-b021-e67186bd0820 |  | note | Records - QA sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Basecourse-NZTA M/4 AP40 (5)
label | aad2e241-03b8-5642-9e16-1064cb89852b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8fd9c2c4-a8cb-5c8d-a746-89621cc1c556 |  | note | Detail - Compaction-NDM tests
label | 8c7fff9c-b8da-599e-8b23-adf66cfca0ff |  | note | Frequency - 1 test per 30m of road per lane, staggered at 15m
label | 898be89c-7135-5e06-ae97-bb076251202d |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
label | 209827e9-4c8f-525b-b0e0-2aea11048302 |  | note | Conformance Criteria - Mean >=98% of MDD
label | 5d16cac5-529d-51ec-a21c-510471ed5202 |  | note | • Minimum>=95% of MDD
label | af5a1873-7014-55b4-be1f-539a33b6949e |  | note | Records - Testing records/
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Basecourse-NZTA M/4 AP40 (6)
label | 5829199f-a0d7-5b61-8000-4fbcdda0fca1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ebe0dcd8-7bcc-58d7-973e-9b3cdbf0029a |  | note | Detail - Benkelman Beam Deflection Test
label | 633514ab-1aaa-59a7-8256-9ab181cf6a90 |  | note | Frequency - at 10m intervals in each traffic lane-staggered
label | f11e1987-6fad-573c-af49-6230edaed7cb |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
label | d7a6d398-6814-5bb3-8979-97396726ba70 |  | note | Conformance Criteria - <=1mm (or specified by AT representative/engineer)
label | 818b12a4-f50c-529c-82e8-e98b33cfe897 |  | note | • Not applicable to stitch section
label | 60b60507-ab94-5802-9ea7-63c18078fa4d |  | note | Records - Testing records/
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - Raised Pedestrian Crossing | itp |  |  |  | Yes | Graeme Ave - ITP - Raised Pedestrian Crossing | 4c53c2e9-ffa0-412c-af33-09747135a1de
checkpoint-status |  |  | checkpoint | 1 Permits
label | e3772de8-9031-4f31-ac21-e75bea8b05ab |  | note | ACTION (Hold, Monitor, Witness): H
label | 0251b105-7c3e-404f-966c-4365ec6b0ccd |  | note | Detail: Obtain Permits
label | 423efb66-1cf7-461b-aa01-94ca7be9198e |  | note | Frequency: As required
label | 9fa73610-3bbb-45a0-9135-b8aab3924c81 |  | note | Inspection / Test Method: Document Review
label | 3ef3c21f-98b8-4994-b1f8-92b53affc7ed |  | note | Conformance Criteria: Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 2b797ee5-1f0c-467c-ade4-ba2ddfbb4fe7 |  | note | Records: Permit attached or permit number noted
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 Pre-construction sign offs
label | 54f2c045-9d7a-4375-aa56-28ea8db68f67 |  | note | ACTION (Hold, Monitor, Witness): H
label | 4e5698ab-f4ec-4936-b50d-607229e2fa1d |  | note | Detail: Ensure that Sub-Contract and Supplier Agreements are signed
label | 1c1c9e69-cd91-4794-96c8-dec58bea07d1 |  | note | Frequency: Prior to commencement
label | 6b26cea4-7921-4453-9522-722f6681793a |  | note | Inspection / Test Method: Document Review
label | 9db8ba76-81e0-4cc3-8961-318790cf01b8 |  | note | Conformance Criteria: Signed Subcontractor and Supplier Agreements
label | bcdf3872-9cb4-4366-9293-9c205b51047c |  | note | Records: Subcontract and Supplier Agreements
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.1 Pre-construction sign offs
label | aedbe013-d502-4dd9-ba71-54f22adc0572 |  | note | ACTION (Hold, Monitor, Witness): H
label | f866abf6-7db3-4ca9-84e7-bd24f8a19eb2 |  | note | Detail: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | c2abc95c-b900-4048-9f1e-11922f7a8609 |  | note | Frequency: Prior to commencement
label | 43d58893-ebe2-4a2a-9607-c3e0ff05b85d |  | note | Inspection / Test Method: Document Review
label | 529ff974-b64f-4b90-9bc3-619b1deef417 |  | note | Conformance Criteria: TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | 48f4c14d-b5b5-4627-96e7-63bda9508cb1 |  | note | Records: TMP on MyWorksites/On Site
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 Pre-construction sign offs
label | 9f2360f0-9874-4b1b-830d-e0d23b121eab |  | note | ACTION (Hold, Monitor, Witness): H
label | cd90c7b2-068a-401b-b99d-c8ea923f07f4 |  | note | Detail: Ensure all Sub-Contractors and Suppliers go through FH induction
label | 41cc387e-b077-4b0b-80f4-03711c8e9301 |  | note | Frequency: On site daily
label | b6be9723-5c9e-4d21-b32f-47f2def5ee42 |  | note | Inspection / Test Method: Induction
label | f6d28e7d-b7c9-40e1-943d-4b52e489e804 |  | note | Conformance Criteria: Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | ce0de8b2-0256-428f-81dc-3c1d627658a7 |  | note | Records: Hazard ID and Pre-starts to safety team
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 Design
label | 6803b7fb-3ae0-40f6-bf9c-0afbfb36c32e |  | note | ACTION (Hold, Monitor, Witness): H
label | 6b4910e2-d74a-4463-ae24-6606cdcf85f6 |  | note | Detail: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | db342fb6-fc2d-40c2-9836-bfb53c82b990 |  | note | Frequency: Prior to commencement
label | 08fc29ec-f214-4fae-a270-81dcf78be152 |  | note | Inspection / Test Method: Document Review
label | 36cb06a9-93f2-4f37-9415-57ddb5e47034 |  | note | Conformance Criteria: IFC drawings have been received by Contractor
label | 1a56bdcd-7bd0-4668-853f-70f531d59af5 |  | note | Records: Check Drawing Register
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.1 Design
label | c9181eae-ecb2-421a-9a51-e797628e3c20 |  | note | ACTION (Hold, Monitor, Witness): H
label | b8219358-95d3-4c86-ad73-58a874ef5f85 |  | note | Detail: Crossing to comply with AT TDM chapter Traffic Calming and TDM TC0010
label | e2e16105-fbb3-4b63-98a1-a95221c8bbbd |  | note | Frequency: Prior to commencement
label | fb733392-2074-4547-8937-eaebddb0d081 |  | note | Inspection / Test Method: Document Review
label | 304e3706-680f-464d-aa5e-2f3ea11fff01 |  | note | Conformance Criteria: IFC drawings have been received by Contractor
label | 501a2134-219c-461b-95ee-c4973a50429c |  | note | Records: Check Drawing Register
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4 Installation of Erosion and Sediment Controls
label | f41e9388-dd6d-4517-ade0-0d914ce0bfc0 |  | note | ACTION (Hold, Monitor, Witness): H
label | 851aa34b-41b9-4f99-b8ab-f41adf29e983 |  | note | Detail: Ensure that Erosion & Sediment Control in place
label | 556780fb-f2cc-4b54-a985-e01182ddfc10 |  | note | Frequency: Prior to commencement
label | 245ef2d2-545b-4940-9d03-db159543f963 |  | note | Inspection / Test Method: Visual Inspection
label | 05dcf38b-4fd5-4ef7-89a3-4e0b67c9955c |  | note | Conformance Criteria: Territorial Authority has approved the as-builts for the ESC controls constructed onsite and gives approval for construction to commence
label | 1246346c-8d3e-4f2b-a65b-468acd0a3cbe |  | note | Records: Environmental Controls Audit
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5 Survey Setout
label | 303a5f11-1b35-45bf-8615-91046d3cef0c |  | note | ACTION (Hold, Monitor, Witness): H
label | 9ce4ccb9-0c19-4d1c-adc2-308a118d44c9 |  | note | Detail: Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | f1c50ea2-c3a4-4b7f-8052-5a179e22e28c |  | note | Frequency: Prior to commencement
label | 8364b1d8-be60-4e87-9496-94ef7826cc3b |  | note | Inspection / Test Method: Survey + Smart Level
label | d6fb3aee-4c30-4e47-8727-3a3240cff503 |  | note | Conformance Criteria: Consistency with Construction Drawing
label | 8a8910df-2f5a-4435-a309-95f27bb0d4d9 |  | note | Records: Site Photos post surveying
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6 Locate Existing Services by Hand Digging
label | 82e95836-520f-4bec-88bd-322098aa4b12 |  | note | ACTION (Hold, Monitor, Witness): H
label | 13b57a33-92f1-49e5-ba65-4cf854547b4e |  | note | Detail: Ensure all services conflicting with the line of trench has been exposed by hand digging
label | 49396fdb-fa6c-4e6e-90b1-3c2dc434c8a3 |  | note | Frequency: Prior to commencement
label | 1967fa22-045f-4cd8-9e16-81a64e68d942 |  | note | Inspection / Test Method: Potholing
label | f52e67ea-fb62-47a6-bbf1-638412072063 |  | note | Conformance Criteria: All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services
label | 3f46b59f-245a-46c8-9338-2deb437a5042 |  | note | Records: Digging and excavation checklist, service planes, As-Built Drawings Doc. Review
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7 Material Compliance
label | 205effa0-49cc-4488-bbf0-8a1f66bb3055 |  | note | ACTION (Hold, Monitor, Witness): H
label | dfbdd436-e240-44a0-984b-8a5629fa6372 |  | note | Detail: LESA dowels to be used at all construction joints
label | 543af136-9426-4f7d-984d-292b4fa07692 |  | note | Frequency: Prior to pouring concrete
label | 41e028b0-47fd-4259-98ef-d6b7796df90e |  | note | Inspection / Test Method: Document Review
label | ecc6472d-3557-4a8c-8da6-8dbfbfc98b26 |  | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
label | bd4ec2d1-39d6-4fac-9e4d-e4b41213e6e2 |  | note | Records: Delivery Dockets / Photos
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.1 Material Compliance
label | 35005638-4a31-472c-aae4-4199a6f863c5 |  | note | ACTION (Hold, Monitor, Witness): H
label | 6763146f-d4ee-45a3-a339-e6636b0a19e1 |  | note | Detail: 0.25mm polythene layer placed across all surface area at bottom of raised table
label | a8a179fd-2ae9-4627-a0b9-5ea9b84aeeff |  | note | Frequency: Prior to pouring concrete
label | 1f136df4-3fb3-4fd8-afda-7e68c02be98a |  | note | Inspection / Test Method: Visual Inspection, Document Review
label | 19de9bff-3dc0-4d83-96a2-da243af2693c |  | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
label | 2cdaf490-caac-4ec1-bd9e-7054cdb7538c |  | note | Records: Delivery Dockets / Photos
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.2 Material Compliance
label | ebf621ac-0006-4446-a3c1-72d8387e0029 |  | note | ACTION (Hold, Monitor, Witness): H
label | 0ad11bd6-d228-441d-a7f8-6e49e5bf26dc |  | note | Detail: 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | 70162f9f-4d59-4974-ba7a-84c47d42f767 |  | note | Frequency: Prior to pouring concrete
label | 1bee1a06-8ba5-4971-96b0-2a07853ee701 |  | note | Inspection / Test Method: Visual Inspection
label | 12622c4b-0c31-4240-ab16-516fc8872a14 |  | note | Conformance Criteria: CIV >15
label | 1d41b38f-be2c-4736-8b24-f65f094057c8 |  | note | Records: Delivery Dockets
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.3 Material Compliance
label | e3098afa-5ce5-49ff-b5f9-4a55dc7e301d |  | note | ACTION (Hold, Monitor, Witness): H
label | 9156e99a-518e-4611-b2c1-c492eec2f2d5 |  | note | Detail: Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs separating.
label | b89e8fa7-79d3-4aee-a99b-fb82e49e51d3 |  | note | Frequency: Prior to pouring concrete
label | 30e51180-914c-4cc5-b45d-ea8f1ac1c72f |  | note | Inspection / Test Method: Visual Inspection
label | dbad7283-bac3-4267-b4d4-7cc169e3a8f2 |  | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
label | 3fb22059-fa4d-431f-857b-41352b65c77a |  | note | Records: Delivery Dockets / Photos
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.4 Material Compliance
label | ea54a2ff-1ac7-4581-aa6c-a6b2dbf2cf67 |  | note | ACTION (Hold, Monitor, Witness): H
label | 3dfc93ae-2cde-4c6a-90bb-6928502767ad |  | note | Detail: All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
label | 6c13f93d-c363-4795-8c5c-e9e59cc52835 |  | note | Frequency: Prior to pouring concrete
label | b5c5f05b-a7b1-4e0a-880f-647a988ec13c |  | note | Inspection / Test Method: Concrete Delivery Dockets
label | f427c388-666b-4149-8164-67d593c0c36c |  | note | Conformance Criteria: Delivery Docket added to QA folder
label | d05a7f31-f68b-40ff-96bf-fa7d162839fd |  | note | Records: Concrete Delivery Dockets
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 8 Temporary Works (Formwork)
label | dc656339-11fa-46ff-b168-73de4d130c5b |  | note | ACTION (Hold, Monitor, Witness): W
label | 4d389484-0982-4a3d-b3ce-ffbf4184f679 |  | note | Detail: Formwork to be set to correct line and level
label | 96ecffe6-da2d-4540-9d98-bc359eee7a5b |  | note | Frequency: Prior to pouring concrete
label | a7ba028f-2a32-4290-994e-48ad2eb1d2aa |  | note | Inspection / Test Method: Visual inspection
label | adc07e26-5741-4c2c-b432-4ef7367a0540 |  | note | Conformance Criteria: Concrete Inspection Record
label | 3d031b82-4046-4192-8661-0e211044dbe2 |  | note | Records: Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 8.1 Temporary Works (Formwork)
label | 9e5b4d31-5b12-473b-82ef-032867c7481d |  | note | ACTION (Hold, Monitor, Witness): H
label | f20f406e-1bf6-4efa-8b1f-5e0b487e7309 |  | note | Detail: Raised table formwork to be 100mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
label | 14458b4e-9ceb-4485-a48a-260911ff6464 |  | note | Frequency: Prior to pouring concrete
label | 60bafdad-c5b2-419b-886f-7019bd5c94a6 |  | note | Inspection / Test Method: Measurement
label | 63a734e9-7895-4cdc-9277-8e5a1213b4ec |  | note | Conformance Criteria: Designer to inspect formation level
label | 75e84d09-9195-4e1e-ae2e-6d007bb7a2df |  | note | Records: Site photos
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 8.2 Temporary Works (Formwork)
label | 49db2aa6-9c6a-4cec-bd39-2d5eb43bc2f6 |  | note | ACTION (Hold, Monitor, Witness): H
label | 691e2f56-14c0-494b-b0ab-68c5450ec12d |  | note | Detail: Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
label | d31a423d-e3e3-43ca-b1e7-9e5c0be3735d |  | note | Frequency: Prior to pouring concrete
label | 2c6ea28e-7dec-4c6f-93db-a49398f42575 |  | note | Inspection / Test Method: Measurement
label | 05c76cb8-0f22-432a-bba8-8f769eead7e2 |  | note | Conformance Criteria: Designer to inspect formation level
label | 846514d3-bd80-4522-b676-da0fba800447 |  | note | Records: Site photos
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 8.3 Temporary Works (Formwork)
label | 53daead9-9f52-4f09-8c53-4fa37bc833f6 |  | note | ACTION (Hold, Monitor, Witness): H
label | 24b12bb8-5921-414b-9b6e-f51de766e036 |  | note | Detail: Raised Table ramps to be 1m across for entry and 1m for departure ramp. Toe to be 0.5m across for both entry and departure.
label | b7d17358-c008-400d-a2b8-eba6034a3939 |  | note | Frequency: Prior to pouring concrete
label | ce0a294d-7f9b-4ce9-84c0-6d13fb14afe0 |  | note | Inspection / Test Method: Measurement
label | 644fc96f-69c8-4232-9e00-fff8d92371e8 |  | note | Conformance Criteria: Designer to inspect formation level
label | a92ca88b-5469-4a00-bef4-f927c8142885 |  | note | Records: Site photos
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 8.4 Temporary Works (Formwork)
label | 9a4315f5-a1e0-4657-a3a1-a543f69286c4 |  | note | ACTION (Hold, Monitor, Witness): H
label | 8641573b-fcf7-4aa1-9471-f102648c8ddb |  | note | Detail: Raised Table ramps to be 1:10 gradient for ramps - Relative gradient on North facing gradient -11% and opposite ramp to be 9% relative to the existing road.
label | d2b83539-83e2-464d-8a54-8e18c9e82c01 |  | note | Frequency: Prior to pouring concrete
label | b1b3d16b-91d9-4799-b509-5205c897030e |  | note | Inspection / Test Method: Measurement
label | f9c2fcf9-4a3e-4eb8-a24d-9c07e547928d |  | note | Conformance Criteria: Designer to inspect gradient level
label | 976efb25-ecde-4a15-b674-20624be064af |  | note | Records: Site photos / Concrete Formwork Checklist
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 8.5 Temporary Works (Formwork)
label | bc2f182d-4ec3-4bb7-b317-4aa9479e0521 |  | note | ACTION (Hold, Monitor, Witness): H
label | dc5af71c-2f45-413b-85df-d4506299fd9f |  | note | Detail: The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | ad3046ca-aafe-431c-b281-a5ce8628acd9 |  | note | Frequency: Prior to concrete pour
label | 646b30be-9d75-4093-8417-e2ade8be01b6 |  | note | Inspection / Test Method: Visual inspection
label | 4974acd6-027e-4e80-a93d-54757d3cc37f |  | note | Conformance Criteria: Concrete Inspection Record
label | 60d1ec7b-ce1f-4191-8e16-0e0906d8a1f3 |  | note | Records: Concrete Formwork Checklist
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 9 Reinforcing
label | 688176f1-51c0-4bb5-904f-59a05960f09f |  | note | ACTION (Hold, Monitor, Witness): H
label | d869eccd-24fe-4234-aa79-cb13785303b4 |  | note | Detail: All construction joints are to contain 2 rows of LESA dowels or similar approved dowels . Dominator dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
label | 74aac687-a812-44df-8f60-195960b45fbd |  | note | Frequency: Prior to pouring concrete
label | d46cb7bc-8c35-4b4f-b9e3-a2e40aae3304 |  | note | Inspection / Test Method: Measurement
label | eeb744b2-85ae-4603-9ca0-c883dbbac701 |  | note | Conformance Criteria: Concrete Inspection Record
label | e97488a1-061e-4a37-8ade-96d988610453 |  | note | Records: Site photos/Concrete Formwork Checklist
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 10 Concreting
label | 92296d26-548b-47d1-a9fc-4e45c5269423 |  | note | ACTION (Hold, Monitor, Witness): H
label | 621452c1-a58c-47d0-b88e-7f40bfef2011 |  | note | Detail: The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | 423166a3-ae0a-4ea2-aa34-ceadbc0fb0a9 |  | note | Frequency: Prior to concrete pour
label | 4816b1ab-9e47-442e-b19f-a16b125aad5c |  | note | Inspection / Test Method: Visual inspection
label | c5328e23-17ac-48fd-aaaa-e5d5f048572a |  | note | Conformance Criteria: Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | 5e65da80-89b4-4987-a4ea-e79fdd5d8722 |  | note | Records: Email / SMS
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 10.1 Concreting
label | 6b5990d4-a6be-40ea-b8ab-3ba919693c7d |  | note | ACTION (Hold, Monitor, Witness): W
label | a099c204-6efa-4b01-a54e-5412360ea47b |  | note | Detail: Vibrator to be used throughout concrete pour
label | bf912907-3791-4170-80e7-3e174309808b |  | note | Frequency: When pouring concrete
label | cbd80b98-b359-4317-ab3b-87d0f249eb61 |  | note | Inspection / Test Method: Visual Inspection
label | 8fb71db6-2c37-4288-befd-969173419ee7 |  | note | Conformance Criteria: Concrete Inspection Record
label | 9d0987ab-eba9-4a99-a907-24c644d306ae |  | note | Records: Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 10.2 Concreting
label | 95b75c4e-3f1d-47c2-97a4-316560b7dad3 |  | note | ACTION (Hold, Monitor, Witness): H
label | 01cf754e-257b-4c77-b687-4678938f7077 |  | note | Detail: Concrete surfaces shall be U5 broomed finish
label | 34852c3d-e42f-4d37-a485-518ea8b95dcf |  | note | Frequency: At completion of pour
label | 00cc8241-3856-4bd2-ad4a-8621321eab9a |  | note | Inspection / Test Method: Visual inspection
label | 65d8ae45-9383-4fe5-b08e-339181d3a295 |  | note | Conformance Criteria: Concrete Inspection Record
label | b64e8c26-e00b-4739-8b1f-9717152cb26e |  | note | Records: Concrete Formwork Checklist
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 11 Curing
label | 1d579aba-15a9-426e-9017-032775707ddb |  | note | ACTION (Hold, Monitor, Witness): M
label | 79bdda79-962c-463d-9fe6-a1de53120da3 |  | note | Detail: Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | da9fa3e0-57d7-4105-8f21-aa1da4c4bc27 |  | note | Frequency: Post Pour
label | f2f5cca0-37f1-4610-87f9-0f8b4832f497 |  | note | Inspection / Test Method: Monitoring the time allowed for curing
label | b5d1ea64-0230-4907-b63b-91d9b1584e2e |  | note | Conformance Criteria: 48 hours minimum have passed
label | b281e85b-779d-4602-8b19-69c752c36e8e |  | note | Records: Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 12 Remove formwork
label | c7e17704-1911-472b-bf2d-72ab46e0bc34 |  | note | ACTION (Hold, Monitor, Witness): W
label | a99c8fa1-db9a-4487-a517-462db717d5a0 |  | note | Detail: Remove formwork after 48 hours
label | 982a08b5-8213-45e2-af2a-1a7339cbfe6d |  | note | Frequency: Post Curing
label | 35757059-fe65-4249-b915-3c514cb2f8af |  | note | Inspection / Test Method: Visual inspection
label | ffcd7ec7-b38e-4c4d-880d-f8c10fa16179 |  | note | Conformance Criteria: Concrete Inspection Record
label | c8c5bac4-cf68-48ea-821a-368cf7501033 |  | note | Records: Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 13 Asphalt- Concrete extension slab/ Toe
label | 43586bb3-867a-4677-b5cd-5a839e099079 |  | note | ACTION (Hold, Monitor, Witness): H
label | 43cb51bb-2d7c-4528-b601-05b688a64cd0 |  | note | Detail: One row of Lesa diamond placed mid depth @400 C/C along construction joint as per TDM TC003
label | b7ac0039-f604-4b7e-9d56-6f90ed4af0c1 |  | note | Frequency: Prior to pouring concrete
label | e5e10ec4-dd3e-41b6-b941-f689ac1d2b2c |  | note | Inspection / Test Method: Measurement
label | 55aefa6c-c459-4be3-a649-53f69658823f |  | note | Conformance Criteria: Pre pour Inspection Checklist, Concrete Inspection records
label | 9be4cc19-fe38-41c2-bda6-a6a46695d68f |  | note | Records: Site photos, delivery dockets
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 13.1 Asphalt- Concrete extension slab/ Toe
label | 1e8e9c8f-ff77-444c-82ca-e11ad3c7e310 |  | note | ACTION (Hold, Monitor, Witness): H
label | 17efc7d1-240e-43bc-bd25-2ce607b8cd6e |  | note | Detail: 150mm thick 40Mpa Concrete with two layers of 663 mesh
label | 6236faba-0cb2-4904-9703-8cd99bb1e8a9 |  | note | Frequency: Prior to pouring concrete
label | 443a60eb-8b7b-4208-aa29-3e517c7c7d11 |  | note | Inspection / Test Method: Measurement
label | 79ccb58a-d29b-4b7e-9723-77ac0743f4b6 |  | note | Conformance Criteria: Pre pour Inspection Checklist, Concrete Inspection records
label | 04ba7ea4-3e2e-4258-96e5-60fffa099514 |  | note | Records: Site photos, delivery dockets
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 13.2 Asphalt- Concrete extension slab/ Toe
label | 3f97f870-9dfa-4b1b-8905-fc8109ccf122 |  | note | ACTION (Hold, Monitor, Witness): W
label | 0e7d8e53-8003-4faa-9f9e-8179d3d08951 |  | note | Detail: Tack Coat between AC14 and Concrete slab
label | eec9b916-d426-4b84-ade2-8223301fa27d |  | note | Frequency: Post Curing
label | c821f634-0221-454c-98bd-ab2bca8c7674 |  | note | Inspection / Test Method: Visual inspection
label | d217415a-f55d-4b01-b84e-c2cda00effba |  | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
label | 54245f5e-6e21-4a69-838b-b3cd2508045d |  | note | Records: Site photos
checkpoint-status |  |  | checkpoint | 13.3 Asphalt- Concrete extension slab/ Toe
label | 75ad1a49-5878-44ed-9c7d-6f034e1ed124 |  | note | ACTION (Hold, Monitor, Witness): W
label | 6e1c6461-446e-4261-b197-bb06a79ebabc |  | note | Detail: 50mm thick AC14
label | 5bfac21e-2be8-48b6-b60b-a89a490d6365 |  | note | Frequency: Post Curing
label | 9461ed70-067c-45b8-8808-5aa6307a050a |  | note | Inspection / Test Method: Measurement
label | 3b69f42d-d522-485d-8da0-2bb892a7fb10 |  | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
label | 19abf383-0807-4a83-abec-79b7c89b5e82 |  | note | Records: Site photos, delivery dockets
checkpoint-status |  |  | checkpoint | 14 Lot Number QA File
label | ebb9247f-383f-4bd2-ab35-d05926721d13 |  | note | ACTION (Hold, Monitor, Witness): W
label | ea8dd881-1efb-4a26-aebc-1c4e8c1bc332 |  | note | Detail: Ensure all QA Records, site photos and incident cases (OFIs) are closed and included within QA file
label | ca476484-9124-41ac-87ad-0fdbb154d40c |  | note | Frequency: At completion of Lot
label | 10fafd7c-8141-4a82-85d9-b322b0203545 |  | note | Inspection / Test Method: Document Review
label | 18d63bca-553e-4e20-99e8-a8c04b4f39e3 |  | note | Conformance Criteria: All QA files compiled and submitted to client
label | 524faa11-41fb-4519-9fce-858b7b8671f0 |  | note | Records: QA records
checkpoint-status |  |  | checkpoint | 14.1 Lot Number QA File
label | 5183a539-db39-4b55-aa6e-61eee979ce9d |  | note | ACTION (Hold, Monitor, Witness): W
label | e2ab51f0-3803-4347-a29a-14ed8988f494 |  | note | Detail: Delivery Dockets to be included in QA file
label | 1758994f-30b1-4745-8485-5bb173e6544b |  | note | Frequency: At completion of Lot
label | 910a31ee-01d0-4a4e-9b0c-33b34234c173 |  | note | Inspection / Test Method: Document Review
label | 477e50f3-f83e-4fdd-bdbf-57f52060909c |  | note | Conformance Criteria: Delivery Dockets to be included in QA file
label | 893befc3-a11f-48d2-b452-62f4e995fecb |  | note | Records: QA records
checkpoint-status |  |  | checkpoint | 15 As-builts
label | d13a786f-cd1c-49fd-9f62-dd1953e73d4a |  | note | ACTION (Hold, Monitor, Witness): H
label | 3ca04f16-a973-42e4-95a6-e106b9304d9d |  | note | Detail: Red pen mark up drawings to be included in QA file
label | 1261195d-7238-4003-8e8b-de43c68fe0e7 |  | note | Frequency: At the completion of the Lot of work
label | dbe918d8-2c0e-4bf5-88c4-6ba283af7360 |  | note | Inspection / Test Method: Drawings
label | 5e8a8923-360e-4793-87f0-985be527068d |  | note | Conformance Criteria:
label | 9b824be4-b391-4791-a14f-2db403414e5f |  | note | Records: As-built Drawing
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | ITP Completion
text | d0b6b882-7d12-4822-adab-c039b47f6bc0 |  | textbox | IFC Drawings used for Construction incl. Rev numbers:
text | bf7b73b4-fdd8-4b4e-aed8-509b589fc1f5 |  | textbox | Reference Documentation (Notices/OFIs etc.):
text | bcd61098-cc8c-42ed-bb37-fd6a838870ec |  | textbox | QA Compiled By :
text | 537633ea-3b54-4fec-92fe-3469f44420e2 |  | textbox | QA checked By Discipline Manager:
text | dff82a78-b78a-443e-b5d8-e85b264a354c |  | textbox | QA checked By Quality Manager:
text | 7c10f9d6-43b1-4856-8b13-4e941b195ae4 |  | textbox | Accepted By Design Engineer:
checklist-flat |  |  | checklist | Ducting and Streetlight Installation |  |  |  |  | Yes | Ponsonby - ITP - Ducting and Streetlight Installation | 4c8bde4b-c69c-40be-9389-9e0c16e478a1
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 4c4bfa8c-bdf0-5433-8691-c3c758442cca |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8ab709e9-bc11-5ec1-b9df-d7fbc4562260 |  | note | Detail - Obtain Permits
label | 33066390-a338-5362-a03b-2a1c9335deb1 |  | note | Frequency - As required
label | cdcd0065-bacd-5f77-a039-a3399aac271e |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | c7dc63a8-d4ed-5a4f-a915-90a6394fb660 |  | note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services).
label | 79294616-de4e-541f-aa7e-519fc97d7e82 |  | note | • Notify Worksafe NZ if required.
label | dba8751c-c3fd-52e4-a069-e2b245b7def7 |  | note | • Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 7c14ffa9-eb96-5dfc-8656-a55eff2eb5cf |  | note | Records - Permit attached or permit number noted
checkpoint-status |  |  | checkpoint | 2 - Traffic Management
label | bbf01c4a-b6cb-5e04-87f1-533cb13e9664 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d5cd10af-93cb-5541-99c2-dcd422289369 |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | 78afbded-87d0-5e7a-b6da-f2971fd8fb33 |  | note | Frequency - Prior to commencement
label | e7917019-df03-5d82-8f49-fb9f8a4c3d3c |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 770bb316-ce95-5ab3-9c8e-c080115ec537 |  | note | Conformance Criteria - TMP is approved by AT for the site and works are completed within the approved dates
label | 575c3b70-a85c-5adb-9d9d-f1147dc1c6f6 |  | note | Records - TMP on MyWorksites/ On Site
checkpoint-status |  |  | checkpoint | 3 - Pre-construction sign offs
label | cb720230-15ae-5076-b4f6-4be3c184ce38 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 33da9770-a163-574e-8459-7c7c41b0570b |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed and that personnel have gone through the NWBI induction.
label | a23e6d32-0810-5fed-b41c-857b918f32e6 |  | note | Frequency - Prior to commencement
label | ee5e1cf5-d35b-5bab-958c-4b2ed04abe43 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 0028c6cf-3b3f-56e1-8bb6-9804b425a075 |  | note | Conformance Criteria - Signed subcontract & Supplier agreements. Issued induction stickers and number
label | ca920c5a-61a4-50b9-8e43-60da319ce2b3 |  | note | Records - Signed Agreements, Updated Induction Register
checkpoint-status |  |  | checkpoint | 4 - Design
label | 674f39bb-aaa0-5fe6-ba6c-8c732846fe83 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f8b0a9c7-a592-5a8e-9c07-130448927477 |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | 48a7e1f3-0179-5062-b1dd-cb6ec302b0bb |  | note | Frequency - Prior to commencement
label | 232145dd-0717-5bc6-99de-6bf95415e751 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 552ba200-df94-5c44-a61a-af7a12c982fb |  | note | Conformance Criteria - IFC label on drawings
label | 007dfe12-9fad-5c0b-95e7-1fedf47013a7 |  | note | Records - Check Drawing Register
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | c816186d-6922-58a5-9561-22dda9f6b280 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a8b83947-4053-5306-9537-83769885e4aa |  | note | Detail - Setout ducting alignment and Street light locations.
label | 8ea6676c-d942-5716-a1e5-dff2d4a2ddcc |  | note | • Setout and mark all known services along the cable corridor.
label | 908a3e98-eab2-5ff8-a6b3-8675dbbcdc23 |  | note | Frequency - Prior to commencement
label | 215815d8-5084-536e-a69d-ec034782553b |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
label | 3d700e7d-1f8d-5791-a50c-3d1d952f34b3 |  | note | Records - Survey Records Services Ducting Checksheet
checkpoint-status |  |  | checkpoint | 6 - Locate existing services by hand digging/ hydrovac
label | f1b3edf4-e2c6-515e-913e-ce91aef18a97 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6dee9a57-f139-5fe7-b19b-fd7533cd91ae |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | 54ddf514-07b4-56de-8ffd-d0ec88e247c3 |  | note | Frequency - Prior to Installation
label | f7d0ec45-4b27-51bc-9559-d97bf659ea98 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Potholing
label | 7029ce9b-320d-53be-ba92-506bff65c320 |  | note | Conformance Criteria - All conflicts have been located
label | 89f845d5-0bab-5356-9b83-096076406693 |  | note | Records - Digging/Excavating Permit, Service Ducting Checksheet
checkpoint-status |  |  | checkpoint | 7 - Material Compliance
label | 6ae7a528-8b75-5f46-879e-9b4cde613623 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 002655ea-d6ba-588e-8d92-4eb3878e7b20 |  | note | Detail - Ensure bedding and cover material is as per vector specifications
label | 9194b1fd-e5d6-5af6-84df-0f8eb3cbfec0 |  | note | Frequency - Prior to commencement
label | a7bfcd51-c75a-5205-8fed-66ccf2a16cdd |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | fbdb80a5-30fd-5ad1-bba2-6e23c399273c |  | note | Conformance Criteria - Crushing Resistance not less than 100kN. Maximum percentage of weight passing 0.075mm sieve shall not exceed 10%
label | 40c4b3c8-5284-559e-9ae9-e322c6cc802b |  | note | Records - Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Material Compliance (2)
label | 4bd33d5c-caeb-5da4-8482-fe1e3891d350 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6f61357d-4078-5374-b827-214c6111e8f2 |  | note | Detail - Ensure duct pipes are as per drawings & spec.
label | 3618548c-f07c-551e-9e30-5ba0a4e7a812 |  | note | Frequency - Upon delivery to site
label | 0d189ce2-5b35-5177-b8a2-43eaa1bdd215 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Ensure delivery docket matches materials
label | a5c975f7-9d66-5092-804d-50b917af716d |  | note | Conformance Criteria - Vector requirements as per ESE303, EDE3020, EDE3024
label | 7cdc0f58-f40a-5c33-b1ee-92bb6c4c98d3 |  | note | Records - Delivery Docket, Vector Specifications, Services Ducting Checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Trenching
label | 7132db6a-9a9d-5c72-bad5-b51925f6b1a4 |  | note | ACTION (Hold, Monitor, Witness) - M
label | b84a7aee-984a-5385-815d-f8f35d6ae956 |  | note | Detail - Inspect trench profile to ensure vertical depth and trench widths as per vector specifications EDE 3024 and EC-21-ACIP4-304 (900mm min cover and 650mm min. trench width for two ducts and 350mm min. trench width for singular ducts)
label | d76e513a-e779-52fb-a21c-d7a98be1eb16 |  | note | Frequency - 10m Intervals
label | 40718bfe-0ca3-5ef6-8bbe-66b3fb0d6965 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | aca2f514-6d7d-5dd2-a7d8-84ca4fa67681 |  | note | Conformance Criteria - Ensure trench profiles conform with corresponding vector specifications EDE 3024 and EC-21-ACIP4-304
label | cc43fdfc-08ca-51a3-92e7-7fdf46289e7c |  | note | Records - Vector Specifications, Services Ducting Checksheet
checkpoint-status |  |  | checkpoint | 9 - Bedding
label | 8a41537e-a37d-5005-99e2-c300266bec46 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2b00404c-9b07-5fa9-a57b-d9405e2688f1 |  | note | Detail - Bedding depths for Ducting as per vector specifications EDE 3024 and EC-21-ACIP4-304.
label | 0e9ed09e-c47b-5859-a6a3-bab518252439 |  | note | Frequency - 10m Intervals
label | a30a0764-3caa-5e37-8a9a-83afe90def7a |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | 990a39c1-2c19-5563-a83f-6d3ba1028bd1 |  | note | Conformance Criteria - As per vector specifications EDE 3024 and EC-21-ACIP4-304
label | 615035cc-92a3-5a90-a352-8412d7efdf05 |  | note | Records - Vector Specifications, Site Photos, Services Ducting Checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Warning Tape and Polymeric Slab
label | 0b21826c-02c0-5b24-96db-e5eff8421dc4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 748046d7-6d53-5a82-aca0-8ca178edfdc5 |  | note | Detail - Install Marker tape at 50% depth of duct cover or as per utility owners specification.
label | 01c20d34-efd7-56f0-aada-d263e480e8cc |  | note | Frequency - 10m Intervals
label | 29e4ff2e-a7a2-5ddd-a16b-b4f3f236987b |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | fc400aad-cd5e-5290-87b6-fc696d3fe061 |  | note | Conformance Criteria - Vector specifications as per EDE3021
label | 7198a2ac-4049-5487-a87e-178d4b6dcc8b |  | note | Records - Vector Specifications, Site Photos, Services Ducting Checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Backfill/ Compaction (also refer to specific utility owners requirements)
label | 25d53a27-e696-54e5-9919-5d9c6ccdc2c1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 82167746-efb5-57c5-8fb3-be56bd9e2484 |  | note | Detail - Depth Range >1m
label | 6bfee957-4490-5897-a8fc-493334215d44 |  | note | ○ Carriageway
label | d78186e1-695c-540e-8779-de0afe0a6235 |  | note | • GAP40, max. compaction layer 200 mm, as per TNZ B/2 Specification, CIV >=30
label | db638118-d0ef-5976-b2d0-4d83e8ad69b0 |  | note | ○ Depth Range >1m - outside 1m from Kerb
label | 9053f45b-326d-5458-9761-ebaae2531097 |  | note | • Selected backfill, max. compaction layer 200mm, as per TNZ B/2 Specification, CIV >=20
label | aae1c49a-bdc4-55d5-9ec1-7cb02a12667b |  | note | Frequency - 10m Intervals
label | d50bb8b1-ac35-56d8-bd8f-3c64da0efba9 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab/ testing
label | 848d7064-eb4a-5dc0-bd13-7b0b51bc8052 |  | note | Conformance Criteria - Pass Test Results
label | 13e993a2-97b5-536a-a5c2-ffc974f7ebab |  | note | Records - Test Records/QA Sheets, Services Ducting Checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Assemble & Install Street Lighting Column
label | 59e594fd-b6c9-5655-b91e-a40ff249c278 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 76ae8c6d-15b7-5f20-9a30-97ce755190bb |  | note | Detail - Confirm column type, height and outreach arm correct for location as per AS/NZS 1158
label | 3ad8ea70-15df-54ac-8d54-5e30a250a921 |  | note | Frequency - Before Column Installed
label | 7c242151-dda6-5c04-ae0a-675d10154943 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 3358057a-5d9b-5e8b-81d6-1a72847ce60a |  | note | Conformance Criteria - As per vector ATCoP Street Lighting
label | e36b9dd7-4086-58f9-8d3f-f736bfc78a54 |  | note | Records - This ITP
checkpoint-status |  |  | checkpoint | 12 - Assemble & Install Street Lighting Column (2)
label | 81d4305c-838d-5594-b707-ec59c4734e6c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 766fb380-d2ca-5cf5-b894-ffd93bfb0ee1 |  | note | Detail - Luminaire types as detailed on drawings
label | 8cec5959-7dcf-519a-acb5-a028a9228050 |  | note | Frequency - Prior to supplying to site
label | f1310089-a463-5043-bb5e-744bfb937491 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document review
label | d59087b2-71c2-5eb6-957b-3c4663315798 |  | note | Conformance Criteria - Refer to IFC Streetlight Drawings
label | 0041096c-ae39-546d-97a2-65241e9dcf94 |  | note | Records - Delivery dockets
checkpoint-status |  |  | checkpoint | 12 - Assemble & Install Street Lighting Column (3)
label | aedd9018-404c-5f4d-a483-95ea6240a8a7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 72de33d2-7d6a-5863-a7ed-09d9798c76cc |  | note | Detail - Streetlighting to be position no more than 1m away from face of kerb to face of column
label | 075a6f41-f52a-5b4d-8406-1f296d55deee |  | note | Frequency - Column Installation
label | 690b2117-7d7a-51c8-955d-7877bd0c6ec3 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 290cc2de-4f63-57a9-a1f2-86da0c11f088 |  | note | Conformance Criteria - As per vector ATCoP Street Lighting
label | 4ad58473-070e-5e2e-a5f9-aead0f4d49ff |  | note | Records - This ITP
checkpoint-status |  |  | checkpoint | 12 - Assemble & Install Street Lighting Column (4)
label | 342b763e-d77d-5284-b61a-6368331d415b |  | note | ACTION (Hold, Monitor, Witness) - W
label | d87fc44e-527e-5e13-aacb-7f588295efae |  | note | Detail - Foundation to be excavated as per manufacturer specification for ground planted columns
label | 34874517-fb29-5c48-86b6-df9c9a30bd57 |  | note | Frequency - Column Installation
label | cf3bd50e-bdb3-5631-b0bc-0ff4d1a364c7 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 6dce01f8-1428-5f09-97ea-615359c53706 |  | note | Conformance Criteria - As per vector ATCoP Street Lighting
label | 85d73b4b-e7df-588e-aa35-28acb0bf01e9 |  | note | Records - This ITP
checkpoint-status |  |  | checkpoint | 12 - Assemble & Install Street Lighting Column (5)
label | 391d7d9c-704f-5496-bebe-65c29ba203e9 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5f1f994a-19b7-5c1e-88b4-fea10c216863 |  | note | Detail - Backfilling with granular or concrete as per manufacturer specs
label | fe1d8a65-c881-5267-b56a-348e3718c6b3 |  | note | Frequency - Column Installation
label | c95b2a08-88eb-51bb-af9c-60cfddde2231 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 518a0976-77dd-55c5-97a8-6f61033e013f |  | note | Conformance Criteria - Refer to IFC Streetlight Drawings
label | 22c27657-13a3-5b76-9471-3bd330edb70c |  | note | Records - This ITP
checkpoint-status |  |  | checkpoint | 12 - Assemble & Install Street Lighting Column (6)
label | 285c9d76-4395-5783-9b7e-4d94b100ca11 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f0513133-05d1-5fec-808a-a145ef4db291 |  | note | Detail - Confirm column is bolted to base stub as per Manufacturer's Instructions
label | ab7919a9-6d3e-5aa0-83ff-0c070b5adde6 |  | note | Frequency - Column Installation
label | 22e4afb7-f45b-5563-aa27-f70902185273 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 6e711e0b-035a-5a17-9fca-8750956e2e1c |  | note | Conformance Criteria - Refer to IFC Streetlight Drawings
label | 144973c2-0cc6-58c5-b77c-67767b0fb6c0 |  | note | Records - This ITP
checkpoint-status |  |  | checkpoint | 13 - Tud/Pit/Chamber Installation
label | 9bd51fa4-f160-5713-a037-303bd440218d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 11abbce4-2bf9-5c6d-9fe9-9483233c1498 |  | note | Detail - Where needed, Ensure TUDs/pits and chambers are installed in the correct locations at asset owner's instruction to manufacturer and asset owner specifications
label | 4063893c-78c9-563c-bc30-f0a19d8ba926 |  | note | Frequency - During Installation
label | 988e581c-951c-5872-a8ab-1b9d80539406 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Site Inspection/Design Review
label | 8716f0be-af8c-5bb7-962c-2907d25938ca |  | note | Conformance Criteria - Sign off and approval by asset owner/MSQA
label | f635b7eb-4dcc-5688-ba77-2fb1796ce1fd |  | note | Records - Site Photos/ Checksheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Commisioning
label | ae31cde9-b3cd-5912-bb12-80db065ad1ef |  | note | ACTION (Hold, Monitor, Witness) - H
label | dc4ec3ff-2ba7-500b-bb48-006514db7d81 |  | note | Detail - Ensure that certification, testing and commissioning undertaken according to Utility Service Provider's guidelines. After livening a test sheet recording the measured voltage at each light and each circuit current is required.
label | 3e2616ef-3e38-54c9-817e-4c09ce9369b7 |  | note | Frequency - Post Installation
label | 108bf2b6-4fd9-566c-a9ba-ed35708ab3de |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 0e5d2298-5ba0-5c99-94bf-41be10f301a1 |  | note | Conformance Criteria - Commisioning completed by vector authorities for Certificate of Compliance and Record of Inspection before operational sign off
label | 06b97400-d4e4-5c03-bf93-ae836731030e |  | note | Records - Test Certificates, COCs and ROIs
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Commisioning (2)
label | 326a8fb2-eaf8-5d4c-86d7-07b35c13d0dd |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0f4534f9-e2b5-57dd-9174-211c17092824 |  | note | Detail - Equipment labels for Poles, Lighting Supply Boxes and internal equipment installed
label | e09f3bae-5ee5-55a6-86fb-b612b058281e |  | note | Frequency - Post Installation
label | 9b9f4377-cff7-5648-b7e8-ab92a768f0ba |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | ed9db401-de8f-5464-ae73-16040d45e9fd |  | note | Conformance Criteria - All relevant labels placed
label | 290860b3-fe5f-5f83-82a3-38a8501480ee |  | note | Records - Photos,This ITP
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | 41dda943-c271-5513-b7d2-75577de67a16 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 274aa17f-c668-5088-9ebe-9bc2e993b86b |  | note | Detail - Cable installation records, Electrical test records, materials and equipment schedule, Survey As-Built
label | 3c44c916-868c-5e38-a093-7695024df409 |  | note | Frequency - At the completion of the Lot of work
label | 5cae95ab-4aa9-5bf3-84c2-35e29906cc3b |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings/Documents
label | 15ea2eda-c60f-5f05-b0e9-07112f0b54ea |  | note | Records - Survey Asbuilt Documents
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | Traffic Islands |  |  |  |  | Yes | Lincoln Rd - ITP - Traffic Islands | 4d35d55c-22a5-4e41-8a48-80fa4b5b784a
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 1 - Mountable Kerb
label | 50caf296-8759-5bea-a82b-d7a584404a52 |  | note | VERIFICATION ACTIVITY - QA FORM
label | ee2083b1-70ca-58e1-b8a8-889fdb308413 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | 72e99e2b-c9e9-504a-9eec-d6b2debe9d41 |  | note | FREQUENCY - Everysite
label | 0da700b3-5c76-519a-bcd5-ad2d62e16dd9 |  | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
label | 58c7329a-c872-55fd-bf8a-54e485e3b346 |  | note | Hold Point - Inprocess Inspection
label | dfc695aa-1661-5123-921d-af3f1093d3d4 |  | note | Records - FH concrete QA sheet, photos.
label | d977b9b6-6c79-5f72-939b-f51e7741fef0 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 9b342c7f-110f-53c4-942b-6cabff4ce6a4 |  | note | VERIFICATION ACTIVITY - Survey
label | 6958e2fa-d417-5dae-a07a-530090326b3e |  | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
label | d17ab768-db32-5747-a4dc-77c0e171f4d1 |  | note | FREQUENCY - Prior to commencement.
label | 18beed1b-d21e-530f-b877-e78109e8a824 |  | note | ACCEPTANCE CRITERIA - Survey
label | 15cc8603-760a-5b1d-b77f-61d3d7d35040 |  | note | Hold Point - As per Construction Drawings
label | 0846f4b7-be8c-55a0-be1e-233c48df96e2 |  | note | Records - Survey Receipt.
label | 3303d262-93f0-5f8c-915f-6a3b33899f39 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Concrete Island
label | 7ddd13a0-94fd-55a8-bc21-3a8467029078 |  | note | VERIFICATION ACTIVITY - QA FORM
label | fac71c91-9f54-5c20-93b7-809d401442f9 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002, TDM Technical Standards - IS0001 & IS0003
label | f61b9337-47f5-5733-b77b-90782d44b69a |  | note | FREQUENCY - Each Site
label | 0bc8c048-dd20-5f0b-8ed8-b415eb142c80 |  | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete, Basecourse to be 150mm min thickness of GAP65
label | 046be29f-ff30-562e-a2fb-d58f4f96bff6 |  | note | Hold Point - Inprocess Inspection
label | a18db03d-7cd2-5ed4-9fd3-5347f014daef |  | note | Records - Photos
label | 56cde3ef-6b41-5407-beea-3768ad7e6825 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4 - Concrete Infil
label | 323c9eda-5969-5d34-b3ae-e61d65539c15 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 30d4db14-864a-514a-afc4-e45ff0c86144 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | c7142697-39ee-50c8-95d3-8aab5e3635ab |  | note | FREQUENCY - Each Site
label | 428b11e7-e1b0-5d36-aa56-d0ecebaf5e55 |  | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 red oxide, Cross Fall of 2% or max rise in centre of 180mm
label | 57677d74-7fe4-56a5-9cbd-0cf50f13828d |  | note | Hold Point - Inprocess Inspection
label | 221214c3-23e5-5697-825b-56fbbcad711f |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ada237b8-32be-5d8b-8965-f2951a1d7e3f |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 5 - As built information
label | 73bbd57f-52b6-55fc-8f50-72881243a6cb |  | note | VERIFICATION ACTIVITY - Drawings
label | 96b057f4-0162-56bd-88f2-f80b07d204b0 |  | note | FREQUENCY - Every Site
label | 48713b47-11c4-5cf2-887c-4451532d0b6e |  | note | ACCEPTANCE CRITERIA - As built drawings
label | 9f6442ce-e2b7-5376-8e06-5f7c3668bfc8 |  | note | Hold Point - In Process Inspection
label | d58783dc-4ad0-5013-86b4-2e024bd2a602 |  | note | Records - Asbuilt records
label | 426a6f61-4b9f-547c-b485-ec6b5f86325f |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | 6 - RAMM DATA
label | b65eac69-ba43-530a-b70a-361908f2a03c |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | 4b31739e-1bb1-5577-955c-ced3e825bf69 |  | note | FREQUENCY - Every Site
label | ef406c0e-0a26-5e2d-92fd-4a4f16235686 |  | note | ACCEPTANCE CRITERIA - RAMM SHEET
label | 84c306af-adef-50ad-a1d1-69bd1855f07e |  | note | Hold Point - In Process Inspection
label | 390f8d25-2ca2-595e-b21f-6ce17abe6524 |  | note | Records - Asbuilt records
label | bcb4daf8-b2da-5c67-83d3-7008ad54d5f1 |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-sectioned |  |  | checklist | ITP - St Lukes Road/Morningside Drive intersection - Enabling Works - Vehicle Crossings |  |  |  |  | Yes | ITP - St Lukes Road/Morningside Drive intersection - Vehicle Crossings | 4ddffb21-af98-4ef7-a1b5-6cab60e93eb6
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | 13eede79-6a0c-5aff-b87e-5faacdb3149a |  | note | VERIFICATION ACTIVITY - Surveyor
label | d8e9600c-bc8e-59fa-9fa9-77ccd3b1d9f2 |  | note | METHODS OR REFERENCE - Surveyor
label | 7187d19f-9068-5ff6-a556-85ce9e1af59f |  | note | FREQUENCY - Everysite
label | 1ab46364-a64e-50b4-9caf-d66cc1e95f1e |  | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like
label | f159afb4-700d-5e75-9838-453cb51c5a68 |  | note | Hold Point - Mandatory HOLD POINT -
label | d5e4fbde-50bc-56ef-9984-26576b76e23d |  | note | Records - Survey Receipt
label | e0d5caf8-a243-54b2-980f-5e733fcfc4cd |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Channel Level
label | 262c860a-f654-5027-ad1f-7d3ee7b0a7fa |  | note | VERIFICATION ACTIVITY - QA FORM
label | 274b2ce0-facd-5a04-b893-b51f04497b17 |  | note | METHODS OR REFERENCE - TDM Technical Standards - VX0000
label | d1b8ac98-c28e-59a5-aaf4-e2e6fd9c5bfe |  | note | FREQUENCY - Every site
label | c87a5cc2-f087-5bca-b2a6-9a74ab7a08ad |  | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | dab6ec5f-6828-566b-93ad-4510ef6fdb45 |  | note | Hold Point - Inprocess Inspection
label | fe08b551-a53b-5468-ba8f-683f8710700c |  | note | Records - FH concrete QA sheet
label | 3e589c9a-b27c-5249-b701-9b8900790e85 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Mesh & Steel
label | 3eef1fd6-f7ae-5a95-ba1d-c95678433dd4 |  | note | VERIFICATION ACTIVITY - QA FORM
label | cd437d5f-5c8f-5b58-86d0-6d635f659287 |  | note | METHODS OR REFERENCE - TDM Technical Standards - VX0000
label | a981eab8-11d9-5149-b63a-5b98efcd56c6 |  | note | FREQUENCY - Every site
label | 05ad95ef-b26c-5ced-8ce0-8360d5a82e5a |  | note | ACCEPTANCE CRITERIA - 661 Mesh and/or D12 Bars to be installed if 4> dwellings or commercial crossing
label | 0f563cc1-6e42-51cb-855e-ba43c8335b70 |  | note | Hold Point - Mandatory HOLD POINT -
label | 60274585-ae52-5130-9b1e-213faaa080f0 |  | note | Records - FH concrete QA sheet Photos
label | 0b059164-504c-5c09-91d0-3f2041a6aa70 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 4a - Vehicle Crossing
label | 78169538-a5af-50e9-bc11-d6a0f4b2f927 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 66f1dd70-1f42-59a7-bdd5-ed9e7abf7993 |  | note | METHODS OR REFERENCE - TDM Technical Standards - VX103
label | bed0f8aa-b81a-522c-9105-6795ea02052f |  | note | FREQUENCY - Each VX
label | df23bae4-5919-5cdd-b929-c94d4c9c742b |  | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Base course - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 black oxide Exposed Finish
label | bca3cde6-5d1f-529b-a650-801d54777b89 |  | note | Hold Point - Inprocess Inspection
label | f8d1cbe6-c9d5-5c65-a704-32b438bcc038 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | a6a96826-7a07-5839-b494-e097ff4bd140 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4b - Commercial Crossing
label | 70b4a8b2-468d-5dbc-8237-ac90bb914735 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 3a530c93-085e-5b9d-a6d1-c261fa40faca |  | note | METHODS OR REFERENCE - TDM Technical Standards - VX0202
label | e5142beb-5eac-50a5-a842-7dd64eaacea9 |  | note | FREQUENCY - Each VX
label | c5d9ca11-6c44-526f-baea-8a7b3217e677 |  | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Base course - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 200mm and 20 MPa @ 28 days. 4kg/m3 black oxide Exposed Finish
label | 0df90ba2-967d-5346-b2ea-881123f4686a |  | note | Hold Point - Inprocess Inspection
label | 7679114a-9b63-5a0b-ba74-a5e4d1af0265 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | e5d1c2d4-a6d1-5f9d-9537-80c1ac8a7aae |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Grass Berms
label | 473bcd99-5e22-5768-8307-a2fc3681c087 |  | note | VERIFICATION ACTIVITY - Visual
label | 4b06b878-69bd-5c75-bc8b-503e25b0976e |  | note | METHODS OR REFERENCE - ATCOP Section 12 Footpaths and Pedestrian Facilities
label | 6e5d50db-f499-5443-bfd9-8ea70c5e9552 |  | note | FREQUENCY - 10m Intervals
label | c3cbb398-d719-5903-86fb-ddc7e1b55451 |  | note | ACCEPTANCE CRITERIA - 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | 34ae55ed-b856-5aca-a52c-803d5b5fc794 |  | note | Hold Point - Inprocess Inspection
label | 53687c47-15bd-52fc-80d8-191a1e1682f7 |  | note | Records - Photos
label | a41c9939-680e-5fc4-8205-3e39599fec16 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 6 - As built information
label | a19dbdc4-370f-5360-b30f-6c54126211fe |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | 7eaf69d3-90ad-50e5-a122-e5a9fa3dd33c |  | note | FREQUENCY - Every Site
label | 5e3dfe17-4ccb-5d4b-9574-e1b95fb15894 |  | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
label | f2dd2386-e211-5ebe-997b-adc8793361cf |  | note | Hold Point - In Process Inspection
label | e9bf6627-b87b-5a44-bca3-1b0bca90e99d |  | note | Records - Asbuilt records
label | 30370cd9-d9c0-5222-8040-b13ad1fee61f |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-group |  |  | section | ITP APPROVAL
checklist-flat |  |  | checklist | ITP - Willcott Street - Raised Pedestrian Crossing | itp |  |  |  | Yes | ITP - Willcott Street - Raised Pedestrian Crossing | 520c7346-591b-4b27-afba-93fabbfdd89f
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 9ea38b37-c7ef-5b00-8a4d-d03cc6f8a52b |  | note | Inspection / Test Point - Permits
label | c1282c63-1a12-5c37-8091-3a0cd6f3d073 |  | note | H
label | 44f66319-4d8c-57c3-9ab2-a646ff851a3e |  | note | Detail - Obtain Permits
label | fc29865d-bc61-5ffd-9437-30d1c06e62b2 |  | note | Frequency - As required
label | f775e562-d713-536e-975b-878a3113b865 |  | note | Inspection / Test Method - Document Review
label | 6df016c7-b87a-5e80-8ea3-d183614323c6 |  | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 82cea3bf-2195-57bc-a309-c97dc922ac67 |  | note | Records - Permit attached or permit number noted
label | a4b08d26-d7ae-599c-a016-59fe3a5cf9a1 |  | note | FH Initials - Site Engineer
label | 6112658b-3a92-5cfc-9e7a-44e89fa34e66 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 3468e892-fc3a-5a06-b367-d10281922fe7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-construction sign offs
label | 59d2a90e-6387-5a4b-8586-9a4a4e250581 |  | note | Inspection / Test Point - Pre-construction sign offs
label | d4ed20f1-39c6-54b8-93f2-0ddf9e0c4f1b |  | note | H
label | 4db320f3-9639-5ff1-9a81-b7356bee1be9 |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
label | 89527ba0-6f1d-5199-907b-d872b155e9be |  | note | Frequency - Prior to commencement
label | 5cd693e0-d923-5333-8d02-af06ed274345 |  | note | Inspection / Test Method - Document Review
label | 936253dd-5390-51b9-9ebf-de81facc22fa |  | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
label | e646a8d3-bd2c-55b8-848d-7295ddbbc433 |  | note | Records - Subcontract and Supplier Agreements
label | d6a13a52-961b-54d8-a3fb-1592ac701596 |  | note | FH Initials - Site Engineer
label | 1365bac9-c609-5f41-91a7-e0e8782bfe1f |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 63f1f980-6fa7-5222-ae43-11825f28d04d |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1 -
label | 3f1cb732-0bae-50a1-8e45-881afd257409 |  | note | Inspection / Test Point -
label | aa5f5a8a-a0f7-5d0f-8b34-208adbdbc1f4 |  | note | H
label | 5c0b95b5-f7cf-55a9-b22c-6c8347ccd15a |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | 917d92d1-144b-551e-a7b6-774616641e6e |  | note | Frequency - Prior to commencement
label | ecea1d3e-0e25-5016-909d-4f5a929b6b08 |  | note | Inspection / Test Method - Document Review
label | 69ae87f6-abb3-52bf-9d97-2973e8b85102 |  | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | eaf6a72c-9f7f-50dd-8994-35600d2de594 |  | note | Records - TMP on MyWorksites/On Site
label | 14835e87-acdc-5eab-afd4-0db5682a8d09 |  | note | FH Initials - Site Engineer
label | 1869d155-f1d9-523b-8ad3-a137859517e7 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 5ade7a0f-b6bb-5e90-b8bb-8db009d62236 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 -
label | d14f8c2a-25d6-5261-9838-cc4cdc481fc9 |  | note | Inspection / Test Point -
label | eca4b261-4e9a-587e-8c8b-7618378dd4de |  | note | H
label | 14b68c2a-072f-5305-9ccd-2e19bc916387 |  | note | Detail - Ensure all Subcontractors and Suppliers go through FH induction
label | 532b3327-b30b-5c05-9fd0-0934f886a21c |  | note | Frequency - On site daily
label | 85bc6572-bf47-5440-9c5a-46d18f6982d7 |  | note | Inspection / Test Method - Induction
label | f656664b-238d-5ea1-bb1e-8642043e8a6e |  | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | 7ac62e0f-6ad7-5335-85a3-5cb4ce49471a |  | note | Records - Hazard ID and Pre-starts to safety team
label | 2a058390-9804-5c31-8bce-dc05827b0c34 |  | note | FH Initials - Site Engineer
label | 2ad506a0-3256-5eb5-a414-5d93291c031e |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | d237988d-8210-55be-879c-166990837da8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 8b13ed0a-fb5b-56b2-95ad-1f14f03733be |  | note | Inspection / Test Point - Design
label | 09d7d22e-7a98-554d-a3d0-c3641530bd7c |  | note | H
label | 71c6a09c-ddff-5a6f-8902-5632303b9722 |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | cd83fa49-15d3-59a6-94e6-1845a83b1f4c |  | note | Frequency - Prior to commencement
label | 674b0b63-c0d5-5c1a-a6b3-88ddac033979 |  | note | Inspection / Test Method - Document Review
label | 67b827b4-f751-5067-9a84-9c27a7b837dc |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | 4b67b770-3f4c-5b37-beb0-b833fff180c9 |  | note | Records - Check Drawing Register
label | b17be013-5ff0-518c-99ad-a46648d33fa6 |  | note | FH Initials - Site Engineer
label | 4d573b27-e856-56de-9990-d802c2253f88 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
text | 87a4de41-33c7-5bc6-a2c1-cf8505521fb7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1 -
label | 05ce86e3-2acb-5765-9fd9-86f265c23c43 |  | note | Inspection / Test Point -
label | 4624fd9c-7a0d-5a1a-a07e-8f15eef1f6f4 |  | note | H
label | 1d910bf6-9d3d-5e13-9047-aaca99704b33 |  | note | Detail - Crossing to comply with AT TDM chapter Traffic Calming and TDM TC0010
label | 27c71579-2310-5dd9-b8ee-afde6a665bdc |  | note | Frequency - Prior to commencement
label | 930a2bd9-d32f-5c16-a4c1-9aad73b760a5 |  | note | Inspection / Test Method - Document Review
label | 67fdd431-c631-540e-84be-f93de36f9c32 |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | ae5ebfb0-6b4a-5244-a3ef-6be5476282ab |  | note | Records - Check Drawing Register
label | 3929c958-a50c-5b2c-be2c-47a0a6b35e7a |  | note | FH Initials - Site Engineer
label | cec81eda-d547-5bce-b054-2a80137c56de |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
text | 8d9a72bc-e746-5a19-83dc-05d3d5c7d1e1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Installation of Erosion and Sediment Controls
label | e7c40dd7-06ba-55ea-bdba-06684de2986e |  | note | Inspection / Test Point - Installation of Erosion and Sediment Controls
label | 376db85f-8b7d-58e7-a596-b04516412c78 |  | note | H
label | 2d617f52-1260-50fc-ae1c-040369cb95a3 |  | note | Detail - Ensure that Erosion & Sediment Control in place
label | c70f2fd4-2228-54ee-93d2-baf8a57a9ff6 |  | note | Frequency - Prior to commencement
label | 4b1745d3-3786-5afc-b013-0365429e6602 |  | note | Inspection / Test Method - Visual Inspection
label | b34a8589-7bc4-55e3-b93c-e7018df50ca1 |  | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | 99ce2d0c-cf64-5af5-97de-8a9023ed688a |  | note | Records - Environmental Controls Audit
label | 3d47b0b5-fde3-5645-ab61-af5862a0a233 |  | note | FH Initials - Environmental Manager/Site Engineer
label | daad7679-b347-5521-93fa-912031d2d05d |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 9222844a-320e-5ead-9d03-4ba1de2f56ce |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | 8456fde2-1b33-5301-8a9b-f0beb926574e |  | note | Inspection / Test Point - Survey Setout
label | b272d8d1-00b3-56c7-b1d8-4307d41caf1d |  | note | H
label | 20c801bf-d3fd-5a15-a456-8842c31d190c |  | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | 3bdb79c0-79fc-5e7e-8366-e862a1d26700 |  | note | Frequency - Prior to commencement
label | 74411f0e-9230-596a-87a9-5aa0911be762 |  | note | Inspection / Test Method - Survey + Smart Level
label | fedafeaa-35ff-589b-aef4-73c599dce925 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 4a95e150-11e4-54e4-bec6-c83b0eed9407 |  | note | Records - Site Photos post surveying
label | da16ea3b-b769-56af-a7de-c29f2067adab |  | note | FH Initials - Site Engineer
label | 5c48fea3-f199-5bb1-bba6-5c0f69d3e9fe |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | b9ac8eb5-8812-5fb6-97e8-f388e7a34251 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging
label | 75e159b3-5ad5-50cc-a765-148435bcf47f |  | note | Inspection / Test Point - Locate Existing Services by Hand Digging
label | 58604264-591d-5c4c-b6d5-6be8716f3a0e |  | note | H
label | 4f135f06-30e6-5f42-986b-87703aca7e03 |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | 695c5156-8b61-5db9-b6a5-8e46c59f019b |  | note | Frequency - Prior to commencement
label | 206062bb-d37b-55bc-abe7-cf311929a4e3 |  | note | Inspection / Test Method - Potholing
label | 49adf21d-84b8-5fd2-9f9f-56e7633a9439 |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | ee2c81da-7d4c-507b-9623-ae3f1fdf41d5 |  | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
label | 3eeefec4-ea41-5989-bf89-2064eb5632af |  | note | FH Initials - Site Engineer
label | 8dc86991-7992-5c30-baa3-9e964b137501 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 3da030e6-794e-5e2e-b2c5-64eb9b6b41e2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Material Compliance
label | 6e4ffa41-5d3e-58a9-bf2e-1dd2d8e8ca69 |  | note | Inspection / Test Point - Material Compliance
label | 45878f46-54f9-592a-8d5e-84acc8e8d96a |  | note | H
label | 549d120a-5358-5d4f-9de6-7f91cb813c0d |  | note | Detail - LESA dowels to be used at all construction joints
label | 75187c3b-d570-51e3-aa7b-6f04d5260f96 |  | note | Frequency - Prior to pouring concrete
label | a3d611b6-abae-5f15-b2cf-f0019c4e5160 |  | note | Inspection / Test Method - Document Review
label | a4118dc2-3f18-5710-96e0-9b66695edd8b |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 1b86b5a8-3c60-5960-a677-d7003e18c200 |  | note | Records - Delivery Dockets / Photos
label | b3f771d4-57b5-524c-a149-d3dcf13c7db0 |  | note | FH Initials - Site Engineer
label | c69a1d97-29a6-507f-b487-d4aedcc9ab72 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 30046c68-398d-589c-b16a-568b3ebaa9d2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1 -
label | cd4a5b63-c94a-56c5-bbd4-ac88d772f4b7 |  | note | Inspection / Test Point -
label | 0be2727e-f3a7-5133-9fe2-34171a5c8740 |  | note | H
label | 44a7bfce-9bd9-5fea-9c13-d4e2bb337294 |  | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
label | facb7868-465f-5f6f-8698-93bc8b726cdb |  | note | Frequency - Prior to pouring concrete
label | 2ca7fb6d-bbe1-5879-b3f4-70338ee98e00 |  | note | Inspection / Test Method - Visual Inspection, Document Review
label | eb1a9eb8-f541-5162-bd93-ea3fba46ccad |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 9e6efb6a-9e5a-5a99-b401-f9c47bcc7ed3 |  | note | Records - Delivery Dockets / Photos
label | 7a003432-d2f3-51f9-8366-701e2cd6b6dd |  | note | FH Initials - Site Engineer
label | 997b7511-50e6-540e-a0c3-9c92ccf06e83 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | ea957ec8-87e3-5c0b-bdef-4dd6651e93c5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 -
label | f3fd379d-54e5-5b77-8764-c331afbec601 |  | note | Inspection / Test Point -
label | 593945a4-251a-5fc5-a7e7-03a7d555335c |  | note | H
label | a7bf6b27-a829-5b3a-bad3-e409d803a09b |  | note | Detail - 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | 714afb87-54d0-5a95-acb8-59bfd2095085 |  | note | Frequency - Prior to pouring concrete
label | 2279228b-c556-5c62-9a20-479d2c098f77 |  | note | Inspection / Test Method - Visual Inspection
label | 975cca28-4c2e-52d2-9579-609c01342ec4 |  | note | Conformance Criteria - CIV >15
label | f6c97aab-4763-51f6-a96a-26f3d37efa75 |  | note | Records - Delivery Dockets
label | 64f9fc2c-b56f-5924-998b-62a62819d5e9 |  | note | FH Initials - Site Engineer
label | d8b6acd0-a333-5754-baff-8ff46da20878 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 3089dd91-f5e8-5157-9af9-d2c8811046aa |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 -
label | 6b1ad189-3faa-53e6-94de-f67672a43180 |  | note | Inspection / Test Point -
label | 1dad9646-e43c-5ef9-91bb-0e849b20b166 |  | note | H
label | 9b9c0685-0dc9-5c64-b2a0-d9929fa1f4d2 |  | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs separating.
label | a03d9bc6-8c1a-5a41-87e4-61d78bf922d8 |  | note | Frequency - Prior to pouring concrete
label | f374d99d-ec1f-593b-9c06-c1b77ddc5637 |  | note | Inspection / Test Method - Visual Inspection
label | 08589937-cd71-500e-9bb4-af4d977e7d12 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | cb8a2201-18d7-5a19-8d3d-e0f98e0fe983 |  | note | Records - Delivery Dockets / Photos
label | 18df4c89-ff9f-54e7-a275-90c32ebbe9a9 |  | note | FH Initials -
label | 7f0c02f4-326e-5c3b-b3c8-52f44c72773b |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | e2854453-e6a5-5e77-a2fb-c6c2e69ebf6d |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.4 -
label | 9cb7fd3b-7dd1-5021-860b-f2defd8753ad |  | note | Inspection / Test Point -
label | cae52284-9168-5b30-99d8-7964d328c731 |  | note | H
label | fd70d368-75c0-5cc0-82ea-6c9e5420a632 |  | note | Detail - All concrete delivered to site shall have 40MPa 28 day compressive strength
label | a62aed1e-962b-54d5-9ba5-fba7450856d2 |  | note | Frequency - Prior to pouring concrete
label | 43ab89a3-c02c-5f9f-bcd0-ca7265fe46df |  | note | Inspection / Test Method - Concrete Delivery Dockets
label | 9de14ebd-c0c8-5dd1-884e-2f9ab3612722 |  | note | Conformance Criteria - Delivery Docket added to QA folder
label | 45082129-c10e-50fd-8a58-092d9e939841 |  | note | Records - Concrete Delivery Dockets
label | e2f07ee1-1686-550b-8dc3-6d3002346e0a |  | note | FH Initials - Site Engineer
label | 9cc96a79-e3b3-54d3-a5ea-dc1d523a3f13 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | d987b4cc-01bd-53a3-a52d-d4821d777c62 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Temporary Works (Formwork)
label | e05cd40b-b69a-5e72-8b97-a722a7f45dc7 |  | note | Inspection / Test Point - Temporary Works (Formwork)
label | 1535e89c-39f6-5bf6-a1a1-c83c97800888 |  | note | W
label | 9efda194-fe7e-5378-b65b-7490fe9185ac |  | note | Detail - Formwork to be set to correct line and level
label | b2d0d512-aaba-538d-9076-b4ff85175357 |  | note | Frequency - Prior to pouring concrete
label | 4cf717ad-9baf-5820-a03f-8a90fdbf921b |  | note | Inspection / Test Method - Visual inspection
label | 467e43d6-ebd4-5537-840e-531972a7a626 |  | note | Conformance Criteria - Concrete Inspection Record
label | 111cd02b-c901-59a1-802a-54ade19a22ec |  | note | Records - Concrete Formwork Checklist
label | b42a47fb-789d-5442-abc0-1d9eec47ebcd |  | note | FH Initials - Site Engineer
label | 487b9350-5c1b-555c-ad13-c0dfc1e2554c |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | f3779bab-c2b3-56c3-a177-1f93ba93e190 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.1 -
label | 031fbb7f-dfed-54c5-a038-309455cbbee9 |  | note | Inspection / Test Point -
label | 144a1afc-e5af-5a21-beee-fa6df7ac1589 |  | note | H
label | f0c34de0-8e2b-5d63-9926-eeca1e103a65 |  | note | Detail - Raised table formwork to be 100mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
label | 98b2ca8d-0e06-5159-a094-5c172f9580eb |  | note | Frequency - Prior to pouring concrete
label | 773664dc-db51-5789-b6a1-3bb13cf7e2eb |  | note | Inspection / Test Method - Measurement
label | 4c50c8d7-653e-5557-b569-2e27f265685c |  | note | Conformance Criteria - Designer to inspect formation level
label | ad7a396a-1da2-5165-93a2-9fb39796c2f8 |  | note | Records - Site photos
label | 37993b71-4f34-5ba7-97ab-059553d5ebbb |  | note | FH Initials - Site Engineer
label | 15585d10-e077-5ef9-91d0-cdba3c32fea7 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | d82eac6d-6493-56f2-b2ae-6c12758f5b63 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2 -
label | 2ac73215-a42e-5a84-9684-704df57bc548 |  | note | Inspection / Test Point -
label | c8779a4e-71b9-558c-9520-aa91d331e2e7 |  | note | H
label | aef1fb3d-c743-5c5b-a1c0-5c9fafdb86f8 |  | note | Detail - Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
label | b4dd87b3-ebe3-5416-8620-0b1f5f1202dc |  | note | Frequency - Prior to pouring concrete
label | ac922763-ef41-5f6e-8ee4-52dc17366674 |  | note | Inspection / Test Method - Measurement
label | 06d10162-7262-50f6-ae5c-701b37d191ee |  | note | Conformance Criteria - Designer to inspect formation level
label | abee5aa0-5a97-545c-918d-9b6ddf8d7cd4 |  | note | Records - Site photos
label | 2ffb97bb-2f91-57c1-a373-09fd34b722b7 |  | note | FH Initials - Site Engineer
label | f1b9308b-0cd4-53e4-b5ea-0057de2ca304 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | 1cd91e7f-5280-550e-a9a8-08adc7a04cd8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.3 -
label | cf7259db-8817-55fd-b095-0c73cf5cb493 |  | note | Inspection / Test Point -
label | cffbf74e-43da-5af8-a685-a5e860e632a0 |  | note | H
label | a575462e-2e66-5df8-bada-406f187b6fef |  | note | Detail - Raised Table ramps to be 1m across for entry and 1m for departure ramp.Toe to be 1m across for both entry and departure.
label | f526e8a4-9c0a-567a-a0c7-caf9514f02db |  | note | Frequency - Prior to pouring concrete
label | e128c77f-ea8d-5369-95b0-ceb1b9e0ed8b |  | note | Inspection / Test Method - Measurement
label | f822ae59-18ab-5cbb-b183-b8fe7b124dfb |  | note | Conformance Criteria - Designer to inspect formation level
label | 5d841fad-5faf-5884-8201-a2f0339a0966 |  | note | Records - Site photos
label | 9c064ee0-4687-5858-9922-2d4625266b7b |  | note | FH Initials - Site Engineer
label | d7141896-6b2e-5795-9693-b970db5797c0 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | cc2fa409-6cc1-5933-bff9-004143a6ba00 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4 -
label | 809acc86-0179-5be2-91cd-08f87e20497f |  | note | Inspection / Test Point -
label | 523120a9-7eb7-51df-9210-803ce173b7b0 |  | note | H
label | a0103c76-e174-585b-9043-325f91d23e16 |  | note | Detail - Raised Table ramps to be 1:10 gradient for ramps - Relative gradient on West facing gradient -15.65% and opposite ramp to be 4.84% relative to the existing road.
label | 077027c6-ae79-5430-b4f1-7aef1da900b8 |  | note | Frequency - Prior to pouring concrete
label | 55794c87-4d91-5ecf-8f0b-2f7fd0a34cef |  | note | Inspection / Test Method - Measurement
label | ed27ac7c-8d27-5edc-b854-f921fe57af6a |  | note | Conformance Criteria - Designer to inspect gradient level
label | 93ed3f34-6123-5fd6-af30-bb86ad2190f9 |  | note | Records - Site photos / Concrete Formwork Checklist
label | d01d2aa2-8731-5056-9768-0eb4c8824f45 |  | note | FH Initials - Site Engineer
label | 6b177078-6788-5e8d-a3e7-c4f4661c50aa |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | 8e44186b-426a-55f0-aa88-196449d1a658 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5 -
label | bdfddb63-387c-50fc-a435-a4511a74d5b8 |  | note | Inspection / Test Point -
label | 2c2b992a-b38e-52ae-a5e8-464671df82a9 |  | note | H
label | ad24e90a-221f-580e-90f8-2e3580cc4e9c |  | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | b940f216-4dde-576e-91a9-623911d2a6a4 |  | note | Frequency - Prior to concrete pour
label | f61cdf8e-d567-56d5-a741-d9943ca867cc |  | note | Inspection / Test Method - Visual inspection
label | 880c62a5-966e-5007-94c9-cfba567e688f |  | note | Conformance Criteria - Concrete Inspection Record
label | fb5338e7-a6fa-5bbd-89a4-c5944f745e41 |  | note | Records - Concrete Formwork Checklist
label | 447fc002-64fe-5827-8871-2787a9669a94 |  | note | FH Initials - Site Engineer
label | 10d53eb2-184f-5965-b3ee-c0e14a0b7506 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | 16c4d265-229b-5b53-94d3-efa08ee35046 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Reinforcing
label | 43a8fea4-f4c4-5854-b81e-dad60b734755 |  | note | Inspection / Test Point - Reinforcing
label | b0f00231-d6c1-57d4-9502-84c23003faf1 |  | note | H
label | d3aab46e-c7d0-576f-b5e6-a34727f845e5 |  | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels . Dominator dowell system 50mm w/ Black 300*50*6mm plates @600 centres placed across the construction joint
label | e2de17f4-8f75-538e-a850-1afafcb35e47 |  | note | Frequency - Prior to pouring concrete
label | e41cfc49-bf99-5918-bcc0-e6fc4468f1d8 |  | note | Inspection / Test Method - Measurement
label | e7d69dd7-ab32-5288-b091-49f2a46c1fc3 |  | note | Conformance Criteria - Concrete Inspection Record
label | df22f3b1-b55b-5e31-8317-1e89b10ca79c |  | note | Records - Site photos/Concrete Formwork Checklist
label | 7a0cfa71-ae5e-546c-a063-7e4ddab9bcfe |  | note | FH Initials - Site Engineer
label | 0d7e1b33-0389-59de-8df9-e80285e541d0 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | 57af00e1-0fc1-5e33-ae4c-4eb013d1263c |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Concreting
label | 99da54a5-ec62-549c-ac4e-9bd1271d5fe3 |  | note | Inspection / Test Point - Concreting
label | 73c12378-9394-5cd4-9bd1-4be3829732ce |  | note | H
label | e9d24a95-a77f-5a9e-a65f-c2e22912bc74 |  | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | 134edb2b-a7ef-5e3b-ae1f-5cdb1e70445f |  | note | Frequency - Prior to concrete pour
label | ce6309c8-2325-53ba-9416-bd5637d1e8ba |  | note | Inspection / Test Method - Visual inspection
label | 8dbb4216-c585-520a-b1ed-f133873bf611 |  | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | f025e74b-00fc-5e79-8e74-6658c54f86fe |  | note | Records - Email / SMS
label | 59535eb1-f107-567e-8b14-7a460ccc54e3 |  | note | FH Initials - Site Engineer
label | 359cdf6b-8db2-5651-9c3c-6805b4198754 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | d3af23c8-12ba-5a51-b329-c55a201cdcd3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1 -
label | a5f5341d-e646-5023-8630-4bd95ff16993 |  | note | Inspection / Test Point -
label | 2067b1ae-48b8-59b0-950b-12e8ef3a7812 |  | note | W
label | 204abf4f-51d2-5807-9fc4-1467d743129f |  | note | Detail - Vibrator to be used throughout concrete pour
label | af0d849f-267e-5f66-98cc-964f5b2a0e95 |  | note | Frequency - When pouring concrete
label | 0e62d0f4-41b8-5bdb-9cfa-94cf33023419 |  | note | Inspection / Test Method - Visual Inspection
label | 7300680d-a550-5381-9e98-62f5d11ad4cc |  | note | Conformance Criteria - Concrete Inspection Record
label | c125c121-b1ae-5882-b8bc-35b894b643aa |  | note | Records - Concrete Formwork Checklist
label | a60f8b6d-7550-5d36-969e-5bb648a780bd |  | note | FH Initials - Site Engineer
label | 38981dc9-67d4-5f7a-8318-aefe6b58e73b |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | e73e3e8b-9112-5589-af1d-4762471f6cb9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10.2 -
label | 2cde7243-830a-5604-8f24-5471dbecd2f4 |  | note | Inspection / Test Point -
label | 03521f9f-8494-5cd5-b964-541c851ce8dd |  | note | H
label | 9d9931aa-a18c-5eed-8091-5c64bf67930b |  | note | Detail - Concrete surfaces shall be U5 broomed finish
label | c4ac6d3e-d75b-5d70-9ff5-149374df9d25 |  | note | Frequency - At completion of pour
label | 77891a4e-5cfd-5146-83e6-56465b56f6d8 |  | note | Inspection / Test Method - Visual inspection
label | b55ced94-ac42-5c64-9656-e53185787f1b |  | note | Conformance Criteria - Concrete Inspection Record
label | 93748e74-46f2-5479-a89e-eb2dc7269c66 |  | note | Records - Concrete Formwork Checklist
label | df8eec84-53af-54ab-9c4d-01656c537df8 |  | note | FH Initials - Site Engineer
label | 00f6ed37-2764-54ce-8ff6-56f63f77b18b |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | 48866e52-6cbb-5baf-858a-9a085dd06f7d |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Curing
label | 0cf6c877-d652-570d-bde2-b6a955ae191a |  | note | Inspection / Test Point - Curing
label | 83155ea5-85b9-5084-a84f-6cd5b2025025 |  | note | M
label | 0c46729c-f18a-50d9-b920-1466678f6725 |  | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | a8ec689c-89d3-5e9b-80be-3c9dd421e17e |  | note | Frequency - Post Pour
label | 5f4f41ec-56a8-5c1f-ad56-9d3d4700d47a |  | note | Inspection / Test Method - Monitoring the time allowed for curing
label | dfb8b72d-0231-5559-afc4-a029982a4a91 |  | note | Conformance Criteria - 48 hours minimum have passed
label | 025216c1-58fc-5dec-9453-05ca8d74f793 |  | note | Records - Concrete Formwork Checklist
label | 89383147-1a51-50d5-8e0e-1ebc842c9e1f |  | note | FH Initials - Site Engineer
label | b8f3d0c4-38dd-543d-a32d-2d9e47e9dfe9 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 9735d079-d9e2-54ab-8828-113e64145534 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 12 - Remove formwork
label | 8997c4b5-ce79-5b2c-8706-550d45bdf1ef |  | note | Inspection / Test Point - Remove formwork
label | 5b10b369-7e2b-5350-b421-8c30a03949ae |  | note | W
label | 21c383a5-e117-59fc-b67d-8fea001524a8 |  | note | Detail - Remove formwork after 48 hours
label | b1bde4c8-738e-5fe7-b8fe-dafafc69f807 |  | note | Frequency - Post Curing
label | 6dd9f1c0-7026-5835-af37-0157105f97d0 |  | note | Inspection / Test Method - Visual inspection
label | 769ce260-43cc-5dfd-a802-7cccdbd46424 |  | note | Conformance Criteria - Concrete Inspection Record
label | 5c53197b-cc78-56ef-9c70-f90dd46d2132 |  | note | Records - Concrete Formwork Checklist
label | 4dbe64e4-cf13-5ce7-93c6-31dc417c771d |  | note | FH Initials - Site Engineer
label | d0193b0a-a38e-57a0-9900-d181dacda300 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 5f73c89a-d94a-55e9-9297-78a7f793c90b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
label | 01f8a909-bccb-555e-85d3-906dfa160b5f |  | note | Inspection / Test Point - Asphalt- Concrete extension slab/ Toe
label | 0ae6706a-03d1-5965-a7be-81cafe7cbdeb |  | note | H
label | c13137fe-a397-5554-a158-be0cddb4a18c |  | note | Detail - One row of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
label | fcae4168-d4ca-5958-8f58-5c42cc892939 |  | note | Frequency - Prior to pouring concrete
label | 5452dcd8-9201-549d-808f-0aa7b71c723e |  | note | Inspection / Test Method - Measurement
label | a5ce4cec-9917-55d5-af40-5a3e6ab4129b |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 2db35800-8810-57fe-bcca-3cd50b0e3ead |  | note | Records - Site photos,delivery dockets
label | 52c750f0-f354-59c6-bc65-1d31779cbced |  | note | FH Initials - Site Engineer
label | 6195829e-3bc6-56c6-bb70-739efdb70717 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | bcd09e8f-2094-5fea-a996-aa182c59ed89 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.1 -
label | 46ed7292-aafc-5b62-9045-ca72934bfd36 |  | note | Inspection / Test Point -
label | df276c4e-9b95-5fe2-b7e8-f1caf7190594 |  | note | H
label | c72f2809-3f50-50ce-9af1-ca4e90cd443c |  | note | Detail - 150mm thick 40MPa Concrete with two layers of 663 mesh
label | 444dd07d-6582-5843-9d7f-42e82fe14ac5 |  | note | Frequency - Prior to pouring concrete
label | 62512584-4c5d-57f7-9fdb-97266230ee73 |  | note | Inspection / Test Method - Measurement
label | 5fad9981-1280-58d9-8a0f-27b496041cc5 |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | fd7ff8b7-11ae-5da1-9a65-1420cce51513 |  | note | Records - Site photos,delivery dockets
label | efa807c7-ed54-53fb-842a-600afdf13d69 |  | note | FH Initials - Site Engineer
label | 6f7aef7d-b1bb-5ab7-95dc-2ced99cfeb79 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 9fd187b3-353a-5030-85f0-5433f902bb5e |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.2 -
label | 4c482c4e-6c0e-52ad-9b35-4acc4c2dc3b6 |  | note | Inspection / Test Point -
label | 1c001d78-24c6-5945-bbb7-92edd9d696fb |  | note | W
label | 805ec9ba-938f-5d3f-ab5e-7ba5265bd01f |  | note | Detail - Tack Coat between DG10 and Concrete slab
label | 1702fbbf-db15-542e-8838-cc9a00c8e4c4 |  | note | Frequency - Post Curing
label | 295001fc-9922-50dd-937f-2bae9b21c80b |  | note | Inspection / Test Method - Visual inspection
label | 1b1fac60-481d-51fe-a6e7-43645c5da5a6 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | f23b5515-89cd-5aab-9db6-774798f094e1 |  | note | Records - Site photos
label | a30ef7a5-ed09-5767-ab67-171cb32e6fd9 |  | note | FH Initials - Site Engineer
label | 28ba0be8-1591-5ea5-b605-038cff3a9dd4 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 642734a8-6112-5f7a-b51b-da4305a6ea6f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 13.3 -
label | 49c18251-c39d-5b18-9b87-50cddd84fc24 |  | note | Inspection / Test Point -
label | fc68b62f-e706-537c-a215-d318f66dc9e3 |  | note | W
label | e5dd5797-3d6c-5c49-8bc5-7c6ae3b05800 |  | note | Detail - 50mm thick DG10
label | df15c467-be19-57ce-a8d8-f1fe75726e82 |  | note | Frequency - Post Curing
label | 8c636bba-4785-5a05-98d5-4353d4f060d9 |  | note | Inspection / Test Method - Measurement
label | a43f4b16-0be9-5bf4-a617-9a97d20980fd |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | d760ccf3-d609-5e9d-9c64-3d0d5545df39 |  | note | Records - Site photos,delivery dockets
label | 0bf0ecd2-330b-5c25-bf8c-a5e8205eebc3 |  | note | FH Initials - Site Engineer
label | 142394f6-9f2c-5279-a31b-133015d4e595 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 32fe33e9-e317-547a-b679-4e9ad0953c3c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 14 - Lot Number QA File
label | dbe15c1d-70a3-5ae3-b87e-93565ab8987b |  | note | Inspection / Test Point - Lot Number QA File
label | a0adf221-1b22-5f9d-95ae-ef8aeb9ebf74 |  | note | W
label | 9d64a391-3ecc-5efc-8559-993181bdeb86 |  | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | 9d5ccd2a-fe55-5a5d-a100-acbb27da1cd7 |  | note | Frequency - At completion of Lot
label | 144dafc4-468e-52a8-911b-e93e8f068d11 |  | note | Inspection / Test Method - Document Review
label | 065b6eb3-169a-5e3c-90c7-a07a8a46ab4e |  | note | Conformance Criteria - All QA files compiled and submitted to client
label | bb1c226c-5a41-5ecf-8e4d-28422ee7de28 |  | note | Records - QA records
label | b93f1afa-fdfc-52a1-9ca4-78c71b544e11 |  | note | FH Initials - Site Engineer
label | 8000dbb8-95e1-5401-873f-3b3e90c2b2d8 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 510655b2-9a09-5148-877d-5f2ed7e70f1a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 14.1 -
label | 40129fc6-1726-5dd2-afbe-2edc41785bd2 |  | note | Inspection / Test Point -
label | 961c54c5-5ff1-5247-824e-c463b184032b |  | note | W
label | 62e446ee-6ac0-5322-b916-9d40a597c238 |  | note | Detail - Delivery Dockets to be included in QA file
label | 106e14c7-a251-5289-a7ca-630ec9732850 |  | note | Frequency - At completion of Lot
label | c5e69c99-7864-5677-8621-c3aaf8276d01 |  | note | Inspection / Test Method - Document Review
label | e381093f-ab4b-54ff-8b2a-bfdaa2d89dff |  | note | Conformance Criteria - Delivery Dockets to be included in QA file
label | 2246a588-8c70-56d5-a3d4-8887b0391b49 |  | note | Records - QA records
label | 273dcf78-143a-55ff-8154-63cc1e2d5392 |  | note | FH Initials - Site Engineer
label | 0cbd7be6-8f05-53b6-a5d9-82a68da6ae93 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 590467c2-6871-5315-988b-8875742c4eb5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | a753e2fc-45f6-5401-a5bc-f172864e569e |  | note | Inspection / Test Point - As-builts
label | bac2e36b-6af5-5d91-adc5-68546ff8ebef |  | note | H
label | 1211bc1d-1c80-5927-b408-cd1f81eb2a99 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 404c61db-e3c6-5aac-bf68-151efb2da34c |  | note | Frequency - At the completion of the Lot of work
label | 38b682fc-8bbf-5dca-ab29-b8cbe6b3ef1a |  | note | Inspection / Test Method - Drawings
label | f6b819fd-9576-5e26-9285-954156e5ae44 |  | note | Conformance Criteria -
label | 7501d270-a329-5758-9c06-9385eedb66c6 |  | note | Records - Asbuilt Drawing
label | 05822c9c-686e-5907-99f2-711d555e8269 |  | note | FH Initials - Site Engineer
label | 053a1fbe-4bab-538f-ae38-ac5e4c21bef2 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | b33986f9-cd69-5b5d-862c-247aa2f96974 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
text | 3a3eca8a-5721-5ea2-9546-1a7cca8913e7 |  | textbox | Comments:
text | d639ff9d-2c96-5599-a916-90c7e6fd4e72 |  | textbox | IFC Drawings used for Construction incl. Rev numbers:
text | 95715a9b-39bc-5bba-a3cb-92c23a03d1a6 |  | textbox | Reference Documentation (Notices/OFIs etc.):
text | e4bb9c68-6ad4-5af3-a853-aad2f173ecbe |  | textbox | QA Compiled By :
text | b20552cc-9ba2-569f-ac38-9376080cb5c7 |  | textbox | QA checked By Discipline Manager:
text | 9b8f9114-0d47-5c5a-acc7-c95efe09a408 |  | textbox | QA checked By Quality Manager:
text | 48d3184c-b4cd-5834-bd0c-f6333f7bde91 |  | textbox | Accepted By Design Engineer:
checklist-sectioned |  |  | checklist | Traffic Islands |  |  |  |  | Yes | Halsey/Maich RAB - ITP - Traffic Islands | 5c82c55b-b7ff-42a9-ac1c-dc4f39c70863
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 1 - Mountable Kerb
label | c800d1b3-d6b7-5a63-8f4d-ff8be7169d06 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 9ad55792-fd4c-5db0-907b-00edea5fd5bf |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | bf76488c-644c-5c99-b68d-dfae56bba4b5 |  | note | FREQUENCY - Everysite
label | 105b9e84-4283-50ad-afbb-041109314578 |  | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
label | ea4df31f-72be-5167-b500-5d7d1db63997 |  | note | Hold Point - Inprocess Inspection
label | b50817ff-88a5-5036-9c2a-b893eb2938a8 |  | note | Records - FH concrete QA sheet, photos.
label | bb03e056-bc2c-5f21-a0a6-10f618f8ce1a |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | ebd64959-9b56-5039-84b7-bb0b090e41a7 |  | note | VERIFICATION ACTIVITY - Survey
label | a5958117-5afd-5308-94c1-aa3e32e41ea7 |  | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
label | 4f6d6d9c-c75b-51dd-8075-b0bcb19bb5ff |  | note | FREQUENCY - Prior to commencement.
label | 2e8ca6e2-8027-58ae-8bee-b328fd93f495 |  | note | ACCEPTANCE CRITERIA - Survey
label | ee5db7ce-2d1c-51d8-80a4-24717eb59984 |  | note | Hold Point - As per Construction Drawings
label | 1599448c-4a4d-5df3-9606-8c35b582aee4 |  | note | Records - Survey Receipt.
label | cfa86b15-ff20-5793-acdb-763bad36f832 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Concrete Island
label | e80c084f-8407-59ef-a970-08a744636a4c |  | note | VERIFICATION ACTIVITY - QA FORM
label | c27373b2-4d9a-57c3-ace5-d62ffe84a14f |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | 35a4b4cf-355c-5e6f-87d2-27a1a7ef7206 |  | note | • TDM Technical Standards - IS0001 & IS0003
label | 5681bce9-1608-5a86-afba-ddcac08ae41f |  | note | FREQUENCY - Each Site
label | 7db028da-fb63-5a81-8784-d96c4367e458 |  | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete
label | b5bbb022-57c7-5e15-a79e-f596edbd2d4e |  | note | • Basecourse to be 150mm min thickness of GAP65
label | 0bc2478c-8728-5eb7-8e92-00e4437c4bf5 |  | note | Hold Point - Inprocess Inspection
label | ed0003af-55a9-5c34-8a2c-d92f104ebac0 |  | note | Records - Photos
label | 9ea066d8-a16d-59c8-bce3-67247149ddfe |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4 - Concrete Infil
label | 3a9bc23e-58d3-50ec-85b2-181b1b581e21 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 96cf2507-1270-5163-9c7a-496729c5a94f |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | 468f7ad6-4b8f-5431-a729-61817e6c20e7 |  | note | FREQUENCY - Each Site
label | 417b37f5-2cfe-51da-b474-ef024ca060e6 |  | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 3 kg/m3 Red oxide
label | ebbba178-0c92-5e11-aec1-dc4733d0198c |  | note | • Cross Fall of 2% or max rise in centre of 180mm
label | fbb42999-6f18-5ed6-9afc-136a4e6fe96f |  | note | Hold Point - Inprocess Inspection
label | fe26499e-8dc8-5cd2-aa7d-35b720fece99 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | b3af4af1-badc-5cd3-8ea6-13d4d6798219 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 5 - As built information
label | 13e2a0c3-a849-5d40-b5ca-33f939f7106d |  | note | VERIFICATION ACTIVITY - Drawings
label | c6d437e7-44b1-55d7-98fd-e7c5c1345cc1 |  | note | FREQUENCY - Every Site
label | 0740e22c-2546-59e5-b169-a53a5c912ff8 |  | note | ACCEPTANCE CRITERIA - As built drawings
label | 3f220194-ec73-5843-8baa-8aa278f62bfe |  | note | Hold Point - In Process Inspection
label | 1dbf76aa-ee77-574b-8caa-243891df1abf |  | note | Records - Asbuilt records
label | c6223c7e-47ec-5384-8db6-8a48524efdf9 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | 6 - RAMM DATA
label | 11e6bf04-7fe7-5116-9715-8f393588c4cf |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | aaa7d0ee-862b-5c66-8e26-04fc524eb841 |  | note | FREQUENCY - Every Site
label | 4d6c1e78-c91e-5b57-91ce-d52a0777a4ed |  | note | ACCEPTANCE CRITERIA - RAMM SHEET
label | 446fafb5-dfbd-5840-8f45-878c481d6ed2 |  | note | Hold Point - In Process Inspection
label | 38ceca14-2a85-5022-acab-538b958a6554 |  | note | Records - Asbuilt records
label | c1b48114-920a-5323-a91a-b04d0a4e7f9e |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-group |  |  | section | ITP APPROVAL
checkpoint-no-status |  |  | checkpoint | ITP Approval
label | 3737207c-3f03-55a4-8a56-7cf0d06652a3 |  | note | Prepared by: Yeswanth Vemula (1/05/2023)
label | 812fed8c-d1d1-50c7-a222-3942c0ccac53 |  | note | Approving Delegate: Daniel Tat
checklist-sectioned |  |  | checklist | Roundabout | itp |  |  |  | Yes | ITP - Griffen Park / Hillsborough Rd - Roundabout | 5ca33d7b-bb25-40b7-b938-13194976a59c
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | fcaf3a0f-7a82-5c9c-9d50-6266cc92232e |  | note | Verification Activity - Survey
label | 49aa9515-cf7c-514d-a796-56913f95fb9c |  | note | Methods Or Reference - Setout Kerb Alignment required to construct to design
label | ab996802-d8b1-54ba-b84c-a73347024b5b |  | note | Frequency - Prior to commencement.
label | 2836b637-5fa6-53aa-9086-7eefb9948bfe |  | note | Acceptance Criteria - Survey
label | fb7b7838-7a06-5104-8fba-34da2f4a0d94 |  | note | Hold Point - As per Drawings 3822001-400-CA-1050
label | 365e1c18-221d-56ab-a59e-8ab82c661d07 |  | note | Records - Survey Receipt.
label | 7c008b5c-2a37-5943-bac1-4826ba2ebb11 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 2 - Concrete Roundabout - Central Island
label | 9abcb676-5610-5601-8e1f-4bde47d16575 |  | note | Verification Activity - QA FORM/ Drawings
label | aebd3161-928c-58da-9852-28e049c3fe78 |  | note | Methods Or Reference - Construction Drawings
label | 87a9aecf-ec0e-5f76-a57c-93988c8c2036 |  | note | Frequency - Each Site
label | 427adb12-b34a-538f-b929-1e675ef280ef |  | note | Acceptance Criteria - Standard precast kerb to be hand-laid with 100mm reveal. Diameter to varies across with 2% cross fall.Kerbs to be sitted on 300mm Min AP40 Sub Base Course , with CBR>5
label | efb934e4-bb41-5f1e-8db7-1d9466525385 |  | note | Hold Point - In Process Inspection
label | 4fa64fc3-6f06-5e77-a85e-f7f463bcded8 |  | note | Records - Photos
label | 98255a33-d5e1-5ad1-a1be-cc8ed88e2f18 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 2.1 - Concrete Roundabout - Central Island
label | db10050d-ffa6-5ef6-9ed8-ee1f7a950781 |  | note | Verification Activity - QA FORM/ Drawings
label | 9baf05a8-e1c3-5f4e-bd98-5ead105a5e0e |  | note | Methods Or Reference - Construction Drawings
label | 1ad0be1b-eb08-5c50-8206-1681728cd9fc |  | note | Frequency - Each Site
label | 712c4e87-c7c7-5a34-8e4b-1e05d9e8a493 |  | note | Acceptance Criteria - Central island to have 100mm GAP 65 Granular base course on removed pavement surface.
label | 9ba6979d-0856-582d-96fd-7624d571dbcc |  | note | Hold Point - In Process Inspection
label | 916d6a5f-692e-5f18-8f53-dca2bd2157e8 |  | note | Records - Photos
label | 3d1b3d31-6c49-5528-924e-aa485d65bb75 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Concrete Infill - Central Island
label | a99d5bde-26b3-53f5-bd11-a98c8f06379e |  | note | Verification Activity - QA FORM
label | 2743fe32-8578-5ca6-9674-3332dd4ff3f8 |  | note | Methods Or Reference - Construction Drawings
label | 99a9fc31-804f-5317-a1db-772a541f3d02 |  | note | Frequency - Each Site
label | df25a28f-3567-5b6e-9a23-2d414c25949b |  | note | Acceptance Criteria - 100mm depth of 20MPa Unreinforced exposed Mcacallum chip Concrete with 3kg/m3 red oxide
label | 41fc0a35-8098-507a-a603-9fa876a0b93f |  | note | Hold Point - In Process Inspection
label | f71a5dd3-b56b-5fbc-99f7-681e560a43d4 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 4a0c037b-28b9-525b-8a4a-288290930190 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4 - Apron
label | 49586d1e-fd76-5ab8-ad2b-b1e86a76c8ad |  | note | Verification Activity - QA FORM/ Drawings
label | 11cc5fb7-c793-586c-b09b-f7811a85bbb8 |  | note | Methods Or Reference - Construction Drawings
label | 27b1f82c-073f-5bb7-81e7-46ef4d9d3df4 |  | note | Frequency - Each Site
label | 4333d288-87b5-5a99-b000-0cfa3216824b |  | note | Acceptance Criteria - Slip formed 25Mpa fibre reinforced concrete for roundabout edging OR Mountable Precast kerb for corner overrun
label | d6b6681a-7d98-5687-ab88-dafb5effe8c5 |  | note | Hold Point - In Process Inspection
label | 809af522-0344-539b-82dd-f121e1b19c18 |  | note | Records - Photos
label | a478a2e6-065a-5bc8-af03-0d7e45054b73 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4.1 - Apron
label | 4455a0dd-9daf-5008-9434-d5df26afc02a |  | note | Verification Activity - QA FORM/ Drawings
label | 4e2d6d71-b0b9-5a98-a7f8-a97c4c551d6f |  | note | Methods Or Reference - TDM Technical Standards - IS0007
label | 2775bb03-93e3-53df-a658-fac9751d26b5 |  | note | Frequency - Each Site
label | b8d6c445-40a1-5ad7-9c5f-a712ce3e0833 |  | note | Acceptance Criteria - Kerbs to be sitted on 300mm Min AP40 Sub Base Course , with CBR>5
label | f40effac-566b-52c3-bd8a-f450597fff89 |  | note | Hold Point - In Process Inspection
label | d888e89e-47fe-59f3-aec9-2d26bb3ae1d3 |  | note | Records - Photos of smart level/ As Builts
label | 7c983d7a-fa14-5e52-8868-7f9ccb8cadd7 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4.2 - Apron
label | 5e122c1c-949c-50af-a672-90702a76f2f0 |  | note | Verification Activity - QA FORM/ Drawings
label | 5928d03a-cb24-5f9b-9ed5-36a13800d14f |  | note | Methods Or Reference - Construction Drawings
label | df83cc02-3e70-5328-81be-2bbce0023579 |  | note | Frequency - Each Site
label | 935036f8-facc-5462-a0c3-ac581a603620 |  | note | Acceptance Criteria - Apron to have 2% min fall towards the road and 2 m wide throughout.
label | 91e95d34-3d7e-57ee-84f3-dde7ad085070 |  | note | Hold Point - In Process Inspection
label | 9dc0f8cc-a918-5de5-8414-d543d2ffe693 |  | note | Records - Photos of smart level/ As Builts
label | 490b8934-0fe0-58e7-8179-a0962eaaebed |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4.3 - Apron
label | b1f1b013-d327-52ad-a82e-1efb832ca999 |  | note | Verification Activity - QA FORM/ Drawings
label | a57905c0-77f8-585e-8ea4-daa42d5589a1 |  | note | Methods Or Reference - TDM Technical Standards - IS0007
label | 306d3a2c-3d4b-57e4-87d3-03383ca1b5c5 |  | note | Frequency - Each Site
label | 758dbbee-5e55-5786-8ae7-9d758c716e11 |  | note | Acceptance Criteria - Apron to have 30mm thick AP20 layer with 0.25mm Polythene layer on top below concrete
label | 12231ef8-d1af-59ed-8447-b5ca61422260 |  | note | Hold Point - In Process Inspection
label | da6c7660-99f5-5a06-9597-92d3c92c6821 |  | note | Records - Photos of smart level/ As Builts
label | ac1624a9-dd94-5be8-939b-3abd5355a9fe |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4.4 - Apron
label | 206e1fc8-68aa-55da-b355-69e804219dc5 |  | note | Verification Activity - Concrete Dockets
label | b0be2bdb-31f0-53bc-920f-55974f3d8df0 |  | note | Methods Or Reference - Construction Drawings
label | 983d8468-b8f8-505e-9255-ed146023d643 |  | note | Frequency - Each Site
label | 865720d5-73b0-562f-b535-07b5b5054503 |  | note | Acceptance Criteria - 200mm depth of 40 Mpa concrete with exposed aggregate finish with 4kg/m3 Black oxide.
label | ec995946-d074-55c0-8fe4-dbfdb170d1db |  | note | Hold Point - In Process Inspection
label | 18c454ce-42fd-57ec-b76a-42b81edc1d1b |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | cbe98764-f37c-5310-9399-7905eae57de3 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | As Builts
checkpoint-status |  |  | checkpoint | 7 - As built information
label | 9b524f9f-1a99-5a94-9620-1301281da8c2 |  | note | Verification Activity - Drawings
label | 465f8f2c-3d20-5af1-a6b3-332e616ccbc1 |  | note | Frequency - Every Site
label | 0c38c801-19c3-5bc3-98b9-f0a5d51bb071 |  | note | Acceptance Criteria - As built drawings
label | 7e2bc475-b480-5999-bc18-68ddd06d58ff |  | note | Hold Point - In Process Inspection
label | 27535478-bcc5-5948-a698-bf587a96e4db |  | note | Records - As Built records
label | da7f5f4c-7d91-5039-8f48-cae42ccaf465 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | 7 - RAMM DATA
label | 3509ef01-2562-5b05-946f-c22901dd6eb0 |  | note | Verification Activity - RAMM DATA SHEET
label | 117cf0ee-aab0-5832-9dd1-f3d13956cdae |  | note | Frequency - Every Site
label | 287a85ab-772a-5213-a9f0-54812fc7121f |  | note | Acceptance Criteria - RAMM SHEET
label | c26f0c5e-2279-5f43-bc8c-b69bea107e7f |  | note | Hold Point - In Process Inspection
label | 495a5a04-8048-599c-9aa0-1bdf1fddaa5f |  | note | Records - As Built records
label | d5eb24af-fc48-5166-bc19-ec4d6ba98159 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-group |  |  | section | ITP APPROVAL
checkpoint-status |  |  | checkpoint | Final Inspection
label | 46597b5f-248a-5466-ad30-8f1578783769 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 1c4cf797-f1bf-55d0-897f-7d61774f27d4 |  | textbox | Print Name:
text | 3b11cb3b-16a5-5e89-b430-b5fb1f0442ad |  | textbox | Position:
text | 892da696-b29b-59ec-b3ca-9be69d71b31d |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP - St Lukes Road/Morningside Drive intersection - ACO Drain |  |  |  |  | Yes | ITP - St Lukes Road/Morningside Drive intersection - ACO Drain | 5efec312-69d8-4545-907a-61b438f80ebf
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | 8d2cb990-d643-54e4-81c7-2eb64701ec28 |  | note | VERIFICATION ACTIVITY - Surveyor
label | a163aa42-ee57-5a45-abf0-8f2a1086352e |  | note | METHODS OR REFERENCE - Surveyor
label | 4996eb01-0caf-560c-9622-5009cc71c06d |  | note | FREQUENCY - Everysite
label | b397f755-1e45-5a08-9c1d-f32aace6121a |  | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like
label | 3886774e-4365-539b-9db5-17c146df85b3 |  | note | Hold Point - Mandatory HOLD POINT -
label | c54b5da8-d6c3-55bc-8c9f-c157e186260b |  | note | Records - Survey Receipt
label | 8d354d04-0c52-529a-a231-b857b760b210 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Aco Drain K300
label | 2019d5e1-bab3-5546-83cb-6be0a19ab6b3 |  | note | VERIFICATION ACTIVITY - QA FORM
label | c0d24776-74b0-5e71-83c5-09c3e17f87cd |  | note | METHODS OR REFERENCE - TDM Technical Standards
label | be4ba5b2-db72-548f-9e0c-3ec3d3a71432 |  | note | FREQUENCY - Every site
label | a6b9e3f2-85b5-58e3-8621-541688a849c1 |  | note | ACCEPTANCE CRITERIA - All the block and the grate should be inspected before installation.
label | 1be8310b-7573-5f61-aac7-d9453064bf16 |  | note | Hold Point - Inprocess Inspection
label | 35aa8ee4-47ae-579d-a831-1647eb0af817 |  | note | Records - Dockets
label | 627935ab-00ec-5b5c-9449-a6ba764ed2e2 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 3 - Prep and Level Check
label | a24eccd3-6ecc-59ee-9df8-74a565d942e7 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 5c7aa7cf-6d79-52a0-9553-3ad91bf4caae |  | note | METHODS OR REFERENCE - TDM Technical Standards
label | 4a848d28-6759-5c4c-9e89-834e3c03650a |  | note | FREQUENCY - Each block
label | aa67d21f-b7fc-57ae-bac6-31090f0dc4d6 |  | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Base course - 100mm min. thickness GAP40 Clegg CIV > 12 water flow check
label | 8adbd7c8-cd7a-56de-be80-f2913bd283ea |  | note | Hold Point - Inprocess Inspection - Engnieer to check
label | b887f8ed-a852-5121-afbc-c3982d25dac1 |  | note | Records - Depth check photos, fall check photos
label | ac9d0316-9531-5036-9f5d-3f8c10802baa |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4 - Lay Kerb Drain
label | b5a4273d-16ed-5b80-b7a5-80f4cb40d546 |  | note | VERIFICATION ACTIVITY - QA FORM
label | d3cba88f-bbdc-5682-bb47-b388f081efc7 |  | note | METHODS OR REFERENCE - TDM Technical Standards
label | ff9a9474-cff4-5099-8b5d-5bd778101c14 |  | note | FREQUENCY - Each Block
label | b93716a8-ce3e-519c-85bc-41420a4b94a0 |  | note | ACCEPTANCE CRITERIA - Boxing to be done along the aco drain Surfacing - Concrete 150mm and 25 MPa @ 28 days. Side Haunching for 150mm thickness Vibrator to be used to avoid voids Finished level of concrete to match with the grate
label | c32f0af1-9101-51f0-9413-471bfda118f8 |  | note | Hold Point - Inprocess Inspection - Engnieer to check
label | d6e5fe0f-7387-5d68-9d48-42a42792a41b |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record Photos
label | 204999e8-7444-52f1-b72a-3cab8cd24521 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 5 - As built information
label | 4fb58146-3b2c-5539-b8db-ace20155720d |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | 6298cf22-5493-5cdb-bfbb-68fd43443ab0 |  | note | FREQUENCY - Every Site
label | 3d8aab18-82c0-5dad-bdaf-222d08a55cd1 |  | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
label | d002737a-0616-59e4-a872-4f70729a052c |  | note | Hold Point - In Process Inspection
label | 3467b14a-7435-5c5c-8593-1fe47caa147f |  | note | Records - Asbuilt records
label | 5063ca62-6a79-5008-8faa-a6057e59afdb |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-flat |  |  | checklist | ITP - Massey Road - Stormwater |  |  |  |  | Yes | ITP - Massey Road - Stormwater | 5f0cd92d-fc0a-4279-b9e8-4dd2f9d4b2cc
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | da9a1cdc-6c1f-5556-8907-38b6dc499e1a |  | note | H
label | 32f678d7-8096-5cc4-8017-6f3a433df101 |  | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | 79f687ae-cdf9-5201-b0e8-994997500e36 |  | note | Frequency - Prior to any construction commencing
label | e75c336f-e7da-511e-9cf6-0f6586a937a2 |  | note | Inspection / Test Method - Document Review
label | 9e4ba9e5-8c1f-5993-b368-0e9325d27b92 |  | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | 6bc12c23-1b02-562a-822c-322dc82d9154 |  | note | Records - Permit attached or permit number noted.
label | 41827695-8816-52ae-ab0d-f4c366d9ad06 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1 - Permits & Services
label | e22f5f41-3e42-5bd5-9b9d-ae8c85b29dcc |  | note | H
label | 445ee068-7598-551d-a1e2-2f4b93f94194 |  | note | Detail - Locate and mark out all existing services
label | c4a8c0bd-024c-5b56-9633-3a03855bbd7e |  | note | Frequency - Prior to any construction commencing
label | 5849b6e8-cccd-54a5-8439-2670e06b656b |  | note | Conformance Criteria - B4u dig procedure - follow utility protocols
label | ec2063f1-c7c1-5959-bf75-8f905ffaa973 |  | note | Records - B4u dig plans & GPR report attached
label | 3692e9a1-b90d-54ad-939f-4d7d5004e74b |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | 12e4bb6e-6fc1-5923-926b-8f33853e6b82 |  | note | H
label | 83bf1cdc-63e3-5564-8542-2d599b767638 |  | note | Detail - Sub-Contract and Supplier Agreements
label | c81ad7b2-a9c6-510f-a4ef-c6af7837f27f |  | note | Frequency - Prior to commencement.
label | c5a2a09a-48ce-55e5-8a41-e803155aa502 |  | note | Inspection / Test Method - Document Review
label | 459eab4c-6609-5990-8555-6f5231a9e345 |  | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | a79d8348-e84f-5a67-a40d-5db039cb2748 |  | note | Records - Subcontract and Supplier Agreements
label | b28ef0fe-7449-555f-a8d3-907f63f857a6 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | f4b9c151-f656-582a-9fc5-f26a5fb51169 |  | note | H
label | 70102531-642e-54bd-ad21-fc9d42797059 |  | note | Detail - Design is approved and Drawings are of the latest revision.
label | d1421314-c561-5268-842e-d774acab378e |  | note | Frequency - Prior to commencement.
label | 55ef32a0-c955-5f13-9310-aca13060c4a1 |  | note | Inspection / Test Method - Document Review
label | 418e5eb3-b440-563a-9232-ed15db2d5c18 |  | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 984024bc-22c8-5f9d-a4bd-189c9998c861 |  | note | Records - Drawing Register.
label | 0bdc89a4-279b-5dfb-89ae-dde27fe62c31 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Survey Setout
label | e29abc16-e4f5-52b1-83ea-4e9cb11f79ec |  | note | H
label | 1b096634-9eca-5c04-a10e-a97e981f13fb |  | note | Detail - Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | d6a29dbd-c225-5db6-808a-ea4bccde54a6 |  | note | Frequency - Prior to commencement.
label | 81c8331a-a98c-5a58-b468-d87283d9c42b |  | note | Inspection / Test Method - Survey
label | 3e039cb1-5c37-5b06-9617-65126cd5fae9 |  | note | Conformance Criteria - As per Blue Barn Consulting Engineering Drawings: 02188-T-400 & Setout files
label | 6f01aeb3-82b6-529f-a22c-dd0ebeca0363 |  | note | Records - Survey Receipt.
label | 8ad63546-a270-563b-bde3-6fbf3989a498 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Pipe and Manhole Material Compliance
label | ef5de62b-8dc8-5a86-9315-83cc55fa4f48 |  | note | H
label | 9f3a7e59-6d82-5d10-80b0-5fe658d0b729 |  | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | 0a7c9f94-c52e-54f6-b027-46a305d85a77 |  | note | Frequency - Prior to commencement.
label | a7b8120b-8cd3-523e-a8e9-260e3aae858d |  | note | Inspection / Test Method - Document Review, Visual Inspection
label | ec0600c4-dc7e-5fe0-9908-82a92e9d1837 |  | note | Conformance Criteria - Pipe shall be Check for freshyly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | 4d539b6d-1aca-5405-9e4c-a948f33c437e |  | note | Records - Manufacturers Data Sheets, Delivery Dockets
label | c7576ca6-5303-5814-9f59-27b8324ffdd9 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | 6d43233a-48b6-519c-b55c-26e6d8631a7e |  | note | H
label | abc5c343-ca8f-51d0-a5c5-a71693da004f |  | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | 8dc594d3-a8d2-5424-8740-b5318611380f |  | note | Frequency - Prior to commencement.
label | a6c075f1-d06a-53f9-bdb5-ddc3f413569f |  | note | Inspection / Test Method - Potholing / Survey
label | 5a241202-7d14-5fae-a7bb-cd3e77c55ae3 |  | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | fb64f3a4-0c76-51cd-90f6-8219e8499b8d |  | note | Records - As-built Drawings. Doc. Review
label | 789e265a-e607-5dac-b15c-0cb989b1f2d1 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | 2e5943f4-e991-5313-af71-6d879d83c872 |  | note | H
label | 7f07e75d-2bb9-50f7-8888-f12a389b90f6 |  | note | Detail - Excavation methodology
label | 6e7cba23-3af0-508d-bc79-80dcbf43ba45 |  | note | Frequency - Daily
label | 7afdc185-8e2b-54c6-9356-1cb2110604cd |  | note | Inspection / Test Method - Prestart review
label | 33a61db8-e1c9-58b8-8752-4e6f190f2ca9 |  | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | a1c53b32-c9e2-5421-9498-50f491240cc7 |  | note | Records - Prestart RCP
label | 92a7596a-c6b6-588e-8cfd-bdee3bf8dba3 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1 - Trenching & Excavation
label | 661699ba-1adf-55fb-9a1a-05796d65ba50 |  | note | M
label | df868bdc-d0d1-56c7-bf2b-8bbc37364056 |  | note | Detail - Trench Profile - Width
label | 86e8a564-c52b-51a4-9d2a-0957be7b4ee0 |  | note | Frequency - Daily / as trenching takes place. Different depth methodology
label | 873d4b1c-5275-5337-b360-8000b25f3919 |  | note | Inspection / Test Method - Visual Inspection, Excavation methdology
label | 31495fce-cc10-5f9e-9812-e3af3b838a47 |  | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | 932e14d9-e91c-5f60-a7e1-f18c19103f1a |  | note | Records - Construction Photos
label | 88c66b21-d027-5671-a4ed-a892f90f61c0 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 - Trenching & Excavation
label | a984476a-5fc5-51c3-8bfa-7087557b0dbf |  | note | W
label | 06b40d93-7b7f-53c4-98bc-c2ca7623d6b8 |  | note | Detail - Trench Profile - Depth
label | 1e72f5ab-4a8e-5020-91b8-bc43716a3912 |  | note | Frequency - Daily / as trenching takes place.
label | ba24aa2f-5cfa-5a87-ba21-23f060355329 |  | note | Inspection / Test Method - Visual Inspection, Measurement
label | 336e696d-0b54-50a3-be1a-e6c7ef780b9d |  | note | Conformance Criteria - Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | 14910930-9fb2-5012-bc5d-019e4c9b2d10 |  | note | Records - FH Drainage Line Record / Construction Photos
label | 72aede44-6995-558a-81c1-c7a30b31147b |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | a189bbaf-3ad4-5401-aa5a-f189666f315b |  | note | W
label | 126f28f3-7528-5991-a2c6-1ee65c9ccdad |  | note | Detail - Placing and compaction of Bedding Material.
label | f33a6db6-19e3-57b9-90b2-bb1d16164a5b |  | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
label | 5daa61ce-74ad-571c-8d1b-9690f7a8ecc2 |  | note | Inspection / Test Method - Visual Inspection
label | a132a581-5955-536a-a23f-768857fb121a |  | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | 55a80541-5b9e-58ef-be74-e8a22438a048 |  | note | Records - FH Drainage Line Record / Construction Photos
label | a3af7893-b0fd-52fa-bed8-29d9a246fd50 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 9 - Pipe Position Tolerance
label | 035709c7-774a-5914-8866-3c6fc76a9866 |  | note | M
label | 0295fc89-d9c1-5087-a48c-0c814780e03b |  | note | Frequency - At any point of pipe
label | 7ea57b09-786f-59f2-8916-0e0889654288 |  | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
label | ddf8df00-5c32-57ae-b7fa-136e7e859f4d |  | note | Records - FH Drainage Line Record, Survey Data.
label | 5e888913-294f-504a-bddd-36787dff78d4 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 10 - Trench Backfill - Placing & Compacting
label | a807fd23-591c-52ff-9db9-fc3c730a7a69 |  | note | M
label | bdfbe66d-22ef-5041-a2f9-d52f5aee2cf3 |  | note | Detail - Placing and compacting of Trench Backfill Material
label | ae56d4a2-5720-5014-8c48-7748944415f0 |  | note | Frequency - Throughout Trench Backfilling operation.
label | 99f8d3c4-9018-5f08-af77-bcdcb6d1a684 |  | note | Inspection / Test Method - Visual Inspection
label | 4f81b30f-5754-510e-b3de-807464567e2e |  | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | 03ade187-40b2-520f-8e63-ef97df61308f |  | note | Records - Construction Photos
label | 8b541cc4-f754-532e-8eeb-ad42689387a4 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 11 - As-Built Drawings
label | aa993bcd-8b99-5aab-a889-7eef9653cd97 |  | note | W
label | fc4a3097-3584-585f-9af4-7fadac94bb2d |  | note | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
label | f0aeb9a3-b78c-5db5-88f9-0d63755ce112 |  | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | 60ebce65-f69f-5dff-bf2f-ff1d3ac1d127 |  | note | Inspection / Test Method - Drawings / Visual Inspection
label | 7e94ad03-66dc-57be-8bb1-aed889b0a096 |  | note | Conformance Criteria - As Built and GIS Data
label | ac681d74-f676-5934-9b14-c6ed9ab17916 |  | note | Records - Redline As-Built Drawings, scanned as .pdf files.
label | 84d37e59-cd1b-5b40-86fd-93bce685688f |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | QA checked by Quality Manager
text | 37d7cd3c-582b-57b9-9103-0539a866bc50 |  | textbox | Comments:
text | ca801cb8-b363-5c45-8aa2-7081e108fba7 |  | textbox | Print Name
text | 7222339c-7d05-5969-9307-fb3e4dd78e2a |  | textbox | Position:
text | 9c500253-e438-5871-b91a-3c9a5acfd269 |  | textbox | Date Completed
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Accepted by Engineers Rep
text | 781938b3-8c7f-5e3a-93b5-246a8b3f5d7f |  | textbox | Comments:
text | 2ac0df82-909d-52b5-b0e0-248faaa5aa6b |  | textbox | Print Name
text | dc8bfc55-9c40-5198-8b96-3906d5dcc042 |  | textbox | Position:
text | 0edd4d1b-b6cc-5831-8fc0-8e2821617295 |  | textbox | Date Completed
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | Concrete Speedtable |  |  |  |  | Yes | Halsey/Maich RAB - ITP - Concrete Speedtable | 6029d447-1159-4b55-a3b7-e47cc77209a7
checkpoint-status |  |  | checkpoint | 1 - Permits
label | a3d7c0a2-faf8-5a2a-a369-747714b508f9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c00aed18-ec0b-57c0-98c0-5c4d6e5dde14 |  | note | Detail - Obtain Permits
label | 480e5eac-8004-508c-a94d-b7e15c0ad104 |  | note | Frequency - As required
label | d51529e7-420a-58f7-a01a-4724345c5b5a |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 222618c8-ef8e-55b8-8e17-a3192d18e7ea |  | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 5a22fc9c-1517-5a56-970a-2312c2bd4c33 |  | note | Records - Permit attached or permit number noted
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-construction sign offs
label | 050ab25f-2fab-5ee0-9eb4-b5cce4a452c4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 82316814-8337-5cf1-b036-430a95a6f6ae |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
label | 7ff2cc82-0f11-5c6b-aad7-9af62fa09b3a |  | note | Frequency - Prior to commencement
label | 830a0e51-d427-5ee3-bfc2-b87494867243 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 36f1f15c-1fe4-511a-8be6-b0983f168d84 |  | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
label | 70685f1c-711c-5dba-99a3-ce3f74fffe03 |  | note | Records - Subcontract and Supplier Agreements
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1 -
label | cb73371d-aa15-5fea-87bc-11c7d44cd2eb |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7972e538-3671-5791-bd8d-6fbb9b63203a |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | 569a30c5-776a-58b2-96d9-299dfc91aa1d |  | note | Frequency - Prior to commencement
label | 120a60f4-0f69-548f-9c64-f737f0321b53 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 0a144905-094a-54b0-859d-d9aaf3ad0875 |  | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | 0013b39d-782b-5528-b37b-0b314b085f4e |  | note | Records - TMP on MyWorksites/On Site
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 -
label | 0c640a71-6f2c-5360-beb3-c4851b9fcbd2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 454f1ea6-2c21-50eb-bcd4-29ab96be59c0 |  | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
label | c14f9eaa-25d4-5340-836e-d181565116e2 |  | note | Frequency - On site daily
label | be2716a4-acac-5e38-a77f-8aaaef78bb30 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Induction
label | 7d90da74-2531-54b4-9411-dfb2d0cbf5a6 |  | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | 088ba123-2fdc-5ae4-9347-65db801cf192 |  | note | Records - Hazard ID and Pre-starts to safety team
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | ac35ecbe-6d5f-50be-9c8a-6797979301c4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f8e1cc66-ada0-5853-9c9b-9b5fd4bb480b |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 1125f9b0-a763-5cb4-8efb-5e6084db9d87 |  | note | Frequency - Prior to commencement
label | e65dd631-a0dd-5e51-94f4-25a3f7fc6bcd |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | cd644869-5f75-5a21-a21f-20b6b6fb383a |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | 2c9ff25e-814e-5291-a277-e377730afbca |  | note | Records - Check Drawing Register
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Installation of Erosion and Sediment Controls
label | 6ccbc7c4-e14b-5c2c-a09f-d6e743623463 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b16a0287-1faf-545b-9fff-ea5eb326afda |  | note | Detail - Ensure that Erosion & Sediment Control in place
label | 4249f251-3f75-5aa5-8a54-97b7046cdd0e |  | note | Frequency - Prior to commencement
label | ff2a924f-b80e-5c9f-8529-bec72384fec6 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 0226af5f-4643-5506-9af4-b1ec7ff6c9fc |  | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | 7d5ba5cd-ee14-5b28-a5db-14dc23622a4d |  | note | Records - Environmental Controls Audit
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | efb3a1e2-9ce3-5c49-ad27-07a4b837843d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 59d2c2c5-a30f-596f-bd74-c9f05aa8de26 |  | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | 643cd3a2-3f83-543e-964f-46d411036c5b |  | note | Frequency - Prior to commencement
label | 7318be6c-010c-59aa-8106-0c2991fc800c |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey + Smart Level
label | eae06f90-42f3-57c4-9f7d-d3c9ec3ed7d1 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | d6b86a25-dba0-51d9-afc3-9b79b36fc722 |  | note | Records - Site Photos post surveying
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging
label | affc6c61-afa5-538e-9a17-f7ecdf794c12 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9421575e-7718-5f23-b55c-454a758d3fc5 |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | 05248dc5-80eb-57c6-a8c2-929756bf7aa7 |  | note | Frequency - Prior to commencement
label | 0acdb4db-1819-501e-96c0-5369eac37c9d |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Potholing
label | 3a317abe-fefc-5310-a774-f48e71d8b27a |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | e6751289-836e-55e7-b96b-7be8cfe68448 |  | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Material Compliance
label | e91b2830-c669-595b-ada9-9cb13cc0013b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4fe1c0c2-01c8-55ee-807d-67a7ca5e10c3 |  | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
label | 0e8e33f5-93b4-5a13-b6e6-e18366252af4 |  | note | Frequency - Prior to pouring concrete
label | 982ecc7a-fbe7-5802-8ac8-7c1591f6f42d |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 1020e2fc-dc6d-5d1f-aa3c-816b398f4583 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | f3cf4127-f77b-5ffd-8da6-a7f271a4bdb7 |  | note | Records - Delivery Dockets / Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1 -
label | a82641ee-7da5-5fd9-b752-f11927b5a114 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b1341c9d-e8f1-56c0-b9fc-07b5c2f9e576 |  | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
label | 2d6dc70c-e72b-5b8b-9f9d-e2a10a1b3e9c |  | note | Frequency - Prior to pouring concrete
label | a00b3ea0-78d0-5363-a817-ba8bb7dffbe3 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Document Review
label | a17d6bcf-344c-5d5b-af1a-d0ca32bb6a16 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 658a9f99-40f6-5b2d-9e4c-b8060f409fbb |  | note | Records - Delivery Dockets / Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 -
label | 91186963-1db8-593f-b86d-d324d9cbcb53 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6cea52ad-aa4f-53e5-b2aa-3aa4d9a73b03 |  | note | Detail - 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | 797ff7e6-16f8-5baf-b678-464d3c68859a |  | note | Frequency - Prior to pouring concrete
label | af66bc93-e2bc-5ebd-b001-8e13a1ffa0a9 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | b16faf2a-0f4c-58bf-ad37-9539da268f3f |  | note | Conformance Criteria - CIV >15
label | 8f0bfbf2-fc0d-585a-8fc5-50e1f2ecc053 |  | note | Records - Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 -
label | 1b246522-abc3-5516-b0c4-68c1dce7975e |  | note | ACTION (Hold, Monitor, Witness) - H
label | a9d778f4-6a66-5662-a5a9-d05d049ec396 |  | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.4 -
label | 31e5c64b-5cac-5384-a5b3-98635875abf7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 60dc3f6c-f881-5865-9dc4-a1759247f098 |  | note | Detail - All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
label | 35aa1bd5-2c5a-51ed-a295-d5c4d917f570 |  | note | Frequency - Prior to pouring concrete
label | 8adc2eb2-6ccf-531a-861a-a447f78c0b55 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Concrete Delivery Dockets
label | eca4d011-d1ee-5141-a639-8353b0b4928f |  | note | Conformance Criteria - Delivery Docket added to QA folder
label | 2c0fc66b-8746-5619-b0ba-aa4b6e8b32f4 |  | note | Records - Concrete Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Temporary Works (Formwork)
label | c82ac61c-5041-5b6b-8e92-5f177400d517 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ff651f64-e03a-5317-86f2-c2a3037de8e7 |  | note | Detail - Formwork to be set to correct line and level
label | 7ed0fb60-41e8-58d4-87df-76afa1dd79d7 |  | note | Frequency - Prior to pouring concrete
label | 676d2a27-0920-5908-a8f6-4b8b0bca7fbb |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | e18d9829-7bec-5f0e-acf2-f986c90a83bd |  | note | Conformance Criteria - Concrete Inspection Record
label | 9ab2522a-ce6c-5c98-a03a-4bba4fa2ae4a |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 8.1 -
label | af4108c6-ed0a-51e6-902b-14e95fbee5ae |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9f28e69b-6da0-52b5-839d-cc4edaf2b855 |  | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:15)
label | bf903985-e39c-513a-adf7-c5c7e525eeb3 |  | note | Frequency - Prior to pouring concrete
label | 5f3866e2-4095-5914-b2f8-a68d51a8b740 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
label | 0d41b2ff-ca8f-53d9-a366-e8452a3d384c |  | note | Conformance Criteria - Designer to inspect formation level
label | faa60b92-e214-5f3f-973f-4ea424fd47d1 |  | note | Records - Site photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2 -
label | 4b23fed0-7d31-5aed-a1cd-25ddf8e644c0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6d3094d0-1079-5263-a11a-0852e98c0091 |  | note | Detail - Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table
label | 751f0cd5-3c76-5667-91ad-ab9caf090c0c |  | note | Frequency - Prior to pouring concrete
label | bd80a18f-f2f7-5599-b007-9cedb5f60996 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
label | b34714bf-b66a-5201-a3d7-9c412ce24399 |  | note | Conformance Criteria - Designer to inspect formation level
label | 40e72d95-2a63-55c5-8b54-37184c7c4de9 |  | note | Records - Site photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.3 -
label | e6b43de1-3d5c-59d9-9ddc-18f3c6c89e68 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3b4920c2-1593-599c-b72c-277fc410ed24 |  | note | Detail - Raised Table ramps to be 1.125m across for entry and 1.125m for departure ramp.Toe to be 0.5 to 1m across for both entry and departure with 50mm asphaltic wearing course
label | b7c86849-840a-5ef3-a587-621e87600504 |  | note | Frequency - Prior to pouring concrete
label | e6184790-962d-54a1-9393-dd0380459a89 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
label | be3e373b-45dc-5f3c-ad0a-e60f295e6299 |  | note | Conformance Criteria - Designer to inspect formation level
label | 1e4d3a7d-2f63-5d0b-8425-831e59aeda71 |  | note | Records - Site photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4 -
label | a73f583e-7b41-5f46-98c6-e8d18a04e526 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 15ca70e7-39f5-51c3-b58d-c33fd0a997ef |  | note | Detail - Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:15 relative to the road
label | 6b705729-baa9-5ae0-93d2-9c48b329388e |  | note | Frequency - Prior to pouring concrete
label | 7c370c15-9d18-5a9e-8d9c-25ea31d5e8c4 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
label | 62fc1b18-6501-5284-8aed-413c566a50b5 |  | note | Conformance Criteria - Designer to inspect gradient level
label | b8513826-534b-5d49-9407-e80f828e6e51 |  | note | Records - Site photos / Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5 -
label | 92d91029-1dc0-5d71-b135-ba41d3835dfc |  | note | ACTION (Hold, Monitor, Witness) - H
label | fd1fd8c6-ccb6-5c5c-a00e-d88b8f9cb398 |  | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | 73a9a8e1-4ad1-5ad5-977f-24c938591846 |  | note | Frequency - Prior to concrete pour
label | 674bc715-e1c6-5d1b-91e9-57761f28f3c8 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | fa1130a4-bcfc-5acf-9e83-6f6554286044 |  | note | Conformance Criteria - Concrete Inspection Record
label | ed8f546b-a82c-5a40-9682-5b8c30bcd833 |  | note | Records - Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Reinforcing
label | a5d85161-2480-52cd-942f-775669f65757 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3bbf215f-0890-5d30-9ad7-c0840e6cb21a |  | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
label | 936f5505-a412-5685-9cd6-53bd3efd20ff |  | note | Frequency - Prior to pouring concrete
label | a3da9c24-8636-5aa1-b743-0402ea30671b |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
label | 24bb2e21-1af8-5901-a728-f3839a027996 |  | note | Conformance Criteria - Concrete Inspection Record
label | 779588f0-7ebc-54fe-80e1-cc789a1f2628 |  | note | Records - Site photos/Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Concreting
label | c831fb5f-9d01-5b16-8c26-e827eb54f0c6 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 40999f73-dd06-5ded-bd8c-9fef17eb611f |  | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | c8107520-f58d-5b07-858e-65f04287bbac |  | note | Frequency - Prior to concrete pour
label | d0cd7ccb-b762-5123-8d60-12b5ca357217 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | 0fd09365-802c-5c9f-84f9-517e5a8df5c8 |  | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | 134d4830-5ddc-53de-adca-ae2b48a9712a |  | note | Records - Email / SMS
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1 -
label | a758b7b9-3d0e-5717-87db-b76eab1ce3c2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4288441e-9910-5e81-833c-d4ac09813405 |  | note | Detail - Vibrator to be used throughout concrete pour
label | 9875c12a-6c7b-56bd-bc16-c4b01fad1aa5 |  | note | Frequency - When pouring concrete
label | b9693773-311e-5416-b232-d2b8b6c5fec7 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 85de7d14-7f49-50ea-b954-9e8d5f811147 |  | note | Conformance Criteria - Concrete Inspection Record
label | 7a56e556-4235-57d5-b23f-f04fee6c3060 |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 10.2 -
label | 9b64dad5-f1ff-5dc3-afe6-14940aae3de8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | efb64ee1-213d-5c1c-8844-e7c99b2c0512 |  | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
label | 7f957016-968e-5b4c-994c-8a4d2f210f34 |  | note | Frequency - At completion of pour
label | 7bad9dc3-aeec-55d8-9c67-2e9519a4991e |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | 66a2bb14-6374-5e95-a8dd-acd650072063 |  | note | Conformance Criteria - Concrete Inspection Record
label | 9a414280-a244-56dc-bb52-bdeaf548777c |  | note | Records - Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Curing
label | f07155d9-3dd9-55bb-a75e-e65f8a584daa |  | note | ACTION (Hold, Monitor, Witness) - M
label | 683af135-58f6-5243-85f4-e37bf84e4cf4 |  | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | b89a17ad-cfad-5db4-b8c9-823f9ad7ab35 |  | note | Frequency - Post Pour
label | 55ecc52d-00e4-5986-9bc6-1f615c5856c7 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Monitoring the time allowed for curing
label | fa9bd73f-2ba4-51bb-a59a-852a4ba0ff5c |  | note | Conformance Criteria - 48 hours minimum have passed
label | 9af66ba4-1e63-5972-93bb-c1d0d7377441 |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 12 - Remove formwork
label | 87d0bcbc-0c44-5855-8240-92a054f594fc |  | note | ACTION (Hold, Monitor, Witness) - W
label | ec7a7d83-c632-5a37-b636-c9bfb6d38d24 |  | note | Detail - Remove formwork after 48 hours
label | 485604c4-37fd-51c3-b4ef-482b75ed51b2 |  | note | Frequency - Post Curing
label | 27f97c77-faf3-5433-ae57-94d8cec25c06 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | 930a1a18-2f61-598d-8b89-884c4f2a8a33 |  | note | Conformance Criteria - Concrete Inspection Record
label | 076c7ba7-82ac-5c26-95ae-31152c548181 |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
label | d4ea41b1-fc75-5628-8160-74cd6582ab80 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8db1e2b6-e9f5-59e7-a03e-beabceaac8dd |  | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
label | e54bb9ca-3fe5-55c3-b3ab-f90091baccc4 |  | note | Frequency - Prior to pouring concrete
label | 182862ee-de73-5631-b1b2-4b9450f1e574 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
label | f7a17d43-f00f-5cff-b011-66c6ba5342b2 |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 5792b006-2ea2-5344-b3ca-dcca1a8aea9f |  | note | Records - Site photos,delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.1 -
label | 2e7dda5f-b8c3-5697-88b4-dad1098529ae |  | note | ACTION (Hold, Monitor, Witness) - H
label | 77a7b42d-dc1d-520a-8e75-7a45c99cb326 |  | note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
label | 8d21bd56-5d86-5e46-ba78-491d50889f2a |  | note | Frequency - Prior to pouring concrete
label | 481f7072-4581-5f56-8457-a12c0637187a |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
label | 498b9a88-a343-5cac-8ce4-7096d9d14a91 |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 9da8e39a-d98e-59ec-93e0-0b9fbccb4b51 |  | note | Records - Site photos,delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.2 -
label | 8fba5f04-b8b1-5d65-82a3-9ef61d8c74c7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1500b25f-15eb-5da0-a311-ec28b0b514c3 |  | note | Detail - Tack Coat between AC and Concrete slab
label | cdcb883d-cbe8-5a8a-966f-6c76cdb46ea6 |  | note | Frequency - Post Curing
label | 18c0776a-1245-5636-9487-dc96ecc2b341 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | 94380c4d-1e1d-597f-9fdc-33de80f50f6b |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 9f95b444-3930-5f23-be8e-1bdcb0447760 |  | note | Records - Site photos
checkpoint-status |  |  | checkpoint | 13.3 -
label | 2ba77e2a-9c1c-5c4e-9af3-35cfeeaa7d61 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 36e8857a-c4de-5b3b-8c9a-98adf2888815 |  | note | Detail - 50mm thick DG10 / Mix 7
label | fd94851a-0bd7-5256-a883-82fdfffe8dfe |  | note | Frequency - Post Curing
label | 10cf311d-281d-5069-b598-79affe56571d |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
label | bc9798bf-3d46-584e-b4c2-49d9c9d9c082 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 4c5d72da-19a5-54ee-8088-3947f9928c33 |  | note | Records - Site photos, delivery dockets
checkpoint-status |  |  | checkpoint | 14 - Lot Number QA File
label | 5eed5326-6250-5d35-bfa9-f0b01c64a29f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2b4b413f-d09d-5cfd-b10f-99d4c950d424 |  | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | fccb1b8d-9976-5d2c-8240-e7355f65cd87 |  | note | Frequency - At completion of Lot
label | 5309daaa-0683-504a-b555-8e0442918a94 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 30c953a6-2543-598b-8c4f-c0586c2d0a51 |  | note | Conformance Criteria - All QA files compiled and sumbitted to client
label | 17c32aff-a1d8-5831-a94a-fd4c2a277cb8 |  | note | Records - QA records
checkpoint-status |  |  | checkpoint | 14.1 -
label | 3fbd5cd0-a951-58cf-9d74-28584d422082 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 07844a6a-dc3e-5603-841b-2d0f2c19fe6f |  | note | Detail - Delivery Dockets to be included in QA file
label | 599230c4-ac3f-533a-aac2-d92c1752f036 |  | note | Frequency - At completion of Lot
label | 8bf0de6e-3214-5234-b798-a96c270df098 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 594d5961-99ae-5bdc-8c5f-375def337334 |  | note | Conformance Criteria - Delivery Dockets to be included in QA file
label | e2fba0a2-deb5-528c-b74b-eabae715a804 |  | note | Records - QA records
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | 55e8c4d5-b3c0-5385-8a53-9d1636f4ad3d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 87ab7f4d-8c10-5de5-a43c-2e009f588f7b |  | note | Detail - Red pen mark up drawings to be included in QA file
label | d9391bc5-a97c-59ed-b574-c804bf32551c |  | note | Frequency - At the completion of the Lot of work
label | 3f8fc941-160d-5e9c-b01d-f709cc6038f8 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings
label | 8d0846c4-6119-54d9-94f0-efdd38c159ba |  | note | Records - Asbuilt Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - Mckenzie Road - Concrete Speedtable | itp |  |  |  | Yes | ITP - Mckenzie Road - Concrete Speedtable | 64ea5210-3072-45cb-acfa-fc2ed7e956ce
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 22698320-e06a-5234-bff8-505f6cccc384 |  | note | H
label | a030f5ac-3fd0-58d8-bdfd-a6cf7753deec |  | note | Detail - Obtain Permits
label | d19a66ee-56c1-5b11-9e0b-bad8e7a7a193 |  | note | Frequency - As required
label | f1483c1e-5895-599f-a2a7-020b7801cb9d |  | note | Inspection / Test Method - Document Review
label | 8c53fcf4-7b0f-5ea0-a895-3be35a3bb048 |  | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 2d65f655-40ff-502a-93af-f59a559f51dd |  | note | Records - Permit attached or permit number noted
label | 2a9e3b6c-04a3-50c8-87c0-42bdd0972b2c |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-construction sign offs
label | 3cc88b9b-10d8-5efa-b386-55e87c9085b2 |  | note | H
label | 71c3aa7c-73a2-57c6-a5e8-ca347bf15f23 |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
label | 53927a1f-f372-5f6a-b8ac-72a5658a6ca9 |  | note | Frequency - Prior to commencement
label | 7cedbe9a-470e-5705-8947-95a2dc525e9b |  | note | Inspection / Test Method - Document Review
label | bbceb787-5d3f-5328-a281-4b257d7f3f36 |  | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
label | f2d3923b-a313-5a59-9774-1c18acdfe4aa |  | note | Records - Subcontract and Supplier Agreements
label | 923055be-7c22-5531-b244-322b2926e812 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1 - Pre-construction sign offs
label | 047448e5-ddc0-5f1e-964d-2bd9c03adf9d |  | note | H
label | 63a6e514-31c8-50be-a21c-e31b5024f663 |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | 23ca171e-5205-5852-8196-703a53115503 |  | note | Frequency - Prior to commencement
label | d6a3473d-2ad8-5e8c-929c-2dc1150478ac |  | note | Inspection / Test Method - Document Review
label | 327b2efb-9833-5fce-a1be-cd6b12ff14f0 |  | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | d64b9d18-ebd6-55f4-a3ea-c858fd2816e9 |  | note | Records - TMP on MyWorksites/On Site
label | f1b201ef-3559-59f2-8b32-5ba91180ee1f |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Pre-construction sign offs
label | 3232a107-1fa7-5d09-bb82-67ff20792531 |  | note | H
label | 017b1417-ace2-5af7-be75-75e914e95f7c |  | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
label | 8b1e106e-23aa-5976-9777-d90cead98d92 |  | note | Frequency - On site daily
label | 9a6345f8-fb9a-5b05-a60a-b18549a4aae2 |  | note | Inspection / Test Method - Induction
label | 5b300b8a-cee6-563d-9f0a-a40e38ef5f26 |  | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | 1bcb3b1c-803c-53df-ba85-69a14402e351 |  | note | Records - Hazard ID and Pre-starts to safety team
label | 3c7f8f51-7cc4-5426-9b4a-42ca86d89295 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | e82c77b9-276a-5985-b7de-34de01be03f2 |  | note | H
label | 9f2fc21e-dba2-5c13-a90e-977394cd1a35 |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 179a88e3-a9a2-5858-9ab0-20e412015632 |  | note | Frequency - Prior to commencement
label | 43c0b2e0-e71a-59d0-bc45-37a9783fe11e |  | note | Inspection / Test Method - Document Review
label | 75ac6eb8-a903-5661-ac86-5f316b2f727b |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | a383978e-4038-5e94-a830-e5db01034e97 |  | note | Records - Check Drawing Register
label | a56a7ebb-0d87-5d0d-949c-b26a7b436118 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Installation of Erosion and Sediment Controls
label | 775da63f-2017-5cce-b3fe-e75eb5739150 |  | note | H
label | 73be6a73-3bab-5ee1-b809-831b4e234906 |  | note | Detail - Ensure that Erosion & Sediment Control in place
label | fa9b1fe6-f8bd-580b-a058-11c77eb5db14 |  | note | Frequency - Prior to commencement
label | 43bafe5c-155f-57b3-9beb-790b23d7e4bf |  | note | Inspection / Test Method - Visual Inspection
label | 1c25607e-5234-5f27-8306-35b01fc0865f |  | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | ac97b141-107e-5e24-91ab-08b8c6986ba4 |  | note | Records - Environmental Controls Audit
label | 16b7ac13-7454-54a5-b0a3-83d649fa2db0 |  | note | FH Initials - Environmental Manager/Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | 7c037a27-df20-5b86-ac57-d404a87810b8 |  | note | H
label | d5205825-3c09-5026-90bb-20b046aeadd2 |  | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | eab338fc-de9b-56eb-9517-550e30e82d89 |  | note | Frequency - Prior to commencement
label | 5f102c93-53b0-5af3-a5e5-e92087c9f163 |  | note | Inspection / Test Method - Survey + Smart Level
label | f9d5107a-ff4d-5ec3-b3fa-b36de6125d42 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 39a12409-2707-5b28-8648-019d8bcdcf74 |  | note | Records - Site Photos post surveying
label | 46fbae8d-e477-5da2-a5f6-21f6b388d7d5 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging
label | 33872b73-a217-5ee6-a206-0fb702da9e89 |  | note | H
label | 7c59b55d-f534-5b75-92e5-748221d81c6d |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | c03c9a75-0ce9-58a0-804c-36962bbf53e6 |  | note | Frequency - Prior to commencement
label | 64a35a42-8da3-52b5-b58c-ad1616ec3cfa |  | note | Inspection / Test Method - Potholing
label | 9ca766b1-2d50-587c-acc2-32887c449f28 |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | 8c07dccc-0e1c-5949-b60f-473031170d5c |  | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
label | 8e6c6103-8e86-51f2-bbf5-9a44cb9ca7bb |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Material Compliance
label | 56cb89ef-7c4d-5d42-942a-c1601e9bd753 |  | note | H
label | 2fc4a401-b8b5-52f2-bfa9-eabb3a35913f |  | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
label | df376724-10ef-5926-93d8-3731dfd08071 |  | note | Frequency - Prior to pouring concrete
label | bad98a8e-ee93-5523-9fe3-7a0e56349036 |  | note | Inspection / Test Method - Document Review
label | 604a8015-533c-508c-9d10-5b5f04c16ddd |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | a8eb8ea0-e396-5037-950b-0c3184361f31 |  | note | Records - Delivery Dockets / Photos
label | 7cdc6a3f-fb52-5dd0-be67-010204d95d38 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1 - Material Compliance
label | cfe7971c-7039-5592-8800-198bbea291c2 |  | note | H
label | 8d8b874f-62d2-5798-9555-4aacaaeaa70f |  | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
label | 26b67a34-9fb8-53a4-a224-e684f74d4740 |  | note | Frequency - Prior to pouring concrete
label | f6d5cdaf-e549-5ef5-99d4-64123f7b3ceb |  | note | Inspection / Test Method - Visual Inspection, Document Review
label | 6d34aa3c-ff4d-5788-b984-27665e7ce67e |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 0404bd68-a9e9-5b4b-92a2-b6bdb4c77552 |  | note | Records - Delivery Dockets / Photos
label | 4e3663da-1863-5d30-be56-1e6209816b66 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 - Material Compliance
label | 9b36012d-0e96-59ca-8614-b7667836ea95 |  | note | H
label | 859f6bb6-37d9-5393-9039-bd046d8bff1e |  | note | Detail - 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | 3e5cc72c-c8bc-5813-b018-4ac12a6ac325 |  | note | Frequency - Prior to pouring concrete
label | a140d6e4-47be-54c4-99dd-061e047963cb |  | note | Inspection / Test Method - Visual Inspection
label | 86ba3ea2-97dc-571c-bb6e-1fd30946d9e9 |  | note | Conformance Criteria - CIV >15
label | a9861ba9-3647-597c-8615-c62cd6e02adb |  | note | Records - Delivery Dockets
label | 7c7b2c50-6d9b-5048-89ea-126228178d56 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 - Material Compliance
label | fe834df4-f64e-5110-821f-693b3a474d82 |  | note | H
label | 1f08c481-f55d-5a07-9ad8-c4880969af1d |  | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.4 - Material Compliance
label | 31fba32f-57fa-5519-a099-1f56dbad659c |  | note | H
label | 7caaee7d-4293-5728-a4e1-d3c1fd09b004 |  | note | Detail - All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
label | 7187f6a1-3645-5785-a762-6760f70f9fdb |  | note | Frequency - Prior to pouring concrete
label | 0989eef4-8c56-53b8-9ff2-7ddf766f35ca |  | note | Inspection / Test Method - Concrete Delivery Dockets
label | ecfc66a6-aae0-5699-8a18-a22bb40074a9 |  | note | Conformance Criteria - Delivery Docket added to QA folder
label | 05902d86-a74b-5207-aa15-4cde41bab402 |  | note | Records - Concrete Delivery Dockets
label | fd4db05c-2e39-50fa-b379-d7daaede18e0 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Temporary Works (Formwork)
label | 5f19daf8-8777-5755-a1ce-4eb1163efdfc |  | note | W
label | 1aa6e783-5aa1-5e8b-944e-349c94dd2bca |  | note | Detail - Formwork to be set to correct line and level
label | 2c3f7717-e470-595c-8002-b2df673f8b08 |  | note | Frequency - Prior to pouring concrete
label | abd5ad05-a806-5ba2-ad5b-6442a347f8dd |  | note | Inspection / Test Method - Visual inspection
label | 1ca79612-1178-5de6-ab4d-c96e04bed3dc |  | note | Conformance Criteria - Concrete Inspection Record
label | 62ce8cb4-6453-5513-a9ae-080ea4925ea8 |  | note | Records - Concrete Formwork Checklist
label | d43aa353-daff-5a62-bd28-f86cc906182a |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.1 - Temporary Works (Formwork)
label | 1d5c171b-55a6-50cd-b571-0bcda90b18bc |  | note | H
label | 0474cfca-3c76-543e-acb7-7c80e85bc0fe |  | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:40)
label | 2973174c-4e31-5328-807b-58e23c75470b |  | note | Frequency - Prior to pouring concrete
label | c518bce8-6c27-5b4c-afef-483a74e32d14 |  | note | Inspection / Test Method - Measurement
label | 89873118-2e8c-5eeb-a9cd-1fc115174e75 |  | note | Conformance Criteria - Designer to inspect formation level
label | c16c6ab1-b822-54a5-8372-2fa00d40c02d |  | note | Records - Site photos
label | 80df969f-539e-5bca-ab9a-d503f9d36cd7 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2 - Temporary Works (Formwork)
label | 3c616156-f5c2-5dc5-9027-9bea4f278238 |  | note | H
label | 05e3c8b5-9348-5eb6-a836-dbf11bece5ac |  | note | Detail - Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table
label | 3dd4652d-a71c-58ce-8392-b70544c1366c |  | note | Frequency - Prior to pouring concrete
label | 4f57c0c3-ff91-5adb-bd88-83ee3a0b1faf |  | note | Inspection / Test Method - Measurement
label | 4fba598d-221b-5845-8fcb-66fb81a628c1 |  | note | Conformance Criteria - Designer to inspect formation level
label | 3f21297c-61df-5647-894c-c165908a02d4 |  | note | Records - Site photos
label | 1ef5536d-cd3a-513f-a1fc-212262e4e392 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.3 - Temporary Works (Formwork)
label | 2687741b-ea0b-501d-9432-ec273ead52c4 |  | note | H
label | 887c0da3-3cba-5e0c-a755-f9d792ee45d2 |  | note | Detail - Raised Table ramps to be 1.125m across for entry and 3m for departure ramp.Toe to be 0.5 to 1m across for both entry and departure with 50mm asphaltic wearing course
label | 6540c282-1cc3-568e-8819-f427ff76eb6a |  | note | Frequency - Prior to pouring concrete
label | bc1b276b-bfd1-58fb-bc31-965d0dbf55c6 |  | note | Inspection / Test Method - Measurement
label | 117d5138-ee94-507c-b549-6cb0e551693d |  | note | Conformance Criteria - Designer to inspect formation level
label | 3d2ada5c-70bd-5005-b3b2-9dd8181ffbd6 |  | note | Records - Site photos
label | 5213b7a8-f356-5d0e-987a-9fefe61b30b6 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4 - Temporary Works (Formwork)
label | 2f20462c-f27a-57a3-a85c-3aef3517a7e5 |  | note | H
label | 17d64d8a-8c76-575e-8aba-f6dea60a1266 |  | note | Detail - Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:40 relative to the road
label | 6e2ea8ac-f689-58e6-8ad5-6da15b8f3cb9 |  | note | Frequency - Prior to pouring concrete
label | 0ed8dbd7-50ee-5bc5-9d6f-5b0768738bf2 |  | note | Inspection / Test Method - Measurement
label | 5dc30fd7-9f90-5b1e-b51e-361c83c8be9e |  | note | Conformance Criteria - Designer to inspect gradient level
label | 93a51531-f904-5f78-9826-85159da09eb2 |  | note | Records - Site photos / Concrete Formwork Checklist
label | f43e9928-8ee0-569d-ae53-e172d836275b |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5 - Temporary Works (Formwork)
label | 530f0b30-5a59-57e1-b5ee-018de1b7396c |  | note | H
label | 8cd975b7-4799-5065-9c12-4316c8c645fc |  | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | 0d8b83ec-302b-5987-bbb3-1b6151c01617 |  | note | Frequency - Prior to concrete pour
label | 62b43909-3616-5a3b-85cc-0d18d8090bf7 |  | note | Inspection / Test Method - Visual inspection
label | 0ba30b78-cd80-5a3c-a7a0-97e79270b562 |  | note | Conformance Criteria - Concrete Inspection Record
label | fb246751-aedd-51d4-9a09-965079bd337c |  | note | Records - Concrete Formwork Checklist
label | d23375a4-bb6a-5a3c-8c5a-6fa4caf30bb3 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Reinforcing
label | ecaacbc0-5602-52bb-984a-45d7509049d1 |  | note | H
label | 563333f1-b114-5b26-a586-c2a5f66dfcc2 |  | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
label | e39b84c1-e5c7-593a-9e32-7df9022046a2 |  | note | Frequency - Prior to pouring concrete
label | e69e8f91-5ec5-56a9-b0d3-7b36af3f1308 |  | note | Inspection / Test Method - Measurement
label | 18439974-c34a-58e9-be35-0021fac63b10 |  | note | Conformance Criteria - Concrete Inspection Record
label | 88914a87-dab8-5241-9b4b-e6003e0843ec |  | note | Records - Site photos/Concrete Formwork Checklist
label | 4753ab3b-b986-5534-93cf-ce0df4481400 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Concreting
label | 9eef57b5-fff9-52e1-bb74-004055b26a53 |  | note | H
label | c762f50d-12af-5868-bd76-ff633654371f |  | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | bd093200-27a0-57dd-9fee-41a4cf031567 |  | note | Frequency - Prior to concrete pour
label | d4fcff40-1773-549b-9cc3-2d024a801ae8 |  | note | Inspection / Test Method - Visual inspection
label | 9f2d581a-1b6a-5ffc-ae03-8aa8b7c45b7a |  | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | 6e94321b-2dd8-5a4f-8263-260442bd3110 |  | note | Records - Email / SMS
label | 810f95a1-ee53-5a0a-bbf8-139399a46297 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1 - Concreting
label | 3fe364f9-5404-5e29-9e83-6886ebe44305 |  | note | W
label | 7ca04055-171d-54c1-92c0-7d2b5be121bf |  | note | Detail - Vibrator to be used throughout concrete pour
label | f1ac0871-d453-57d1-a363-558f031dc187 |  | note | Frequency - When pouring concrete
label | 283e7d58-fa8a-553c-817f-37520e16f468 |  | note | Inspection / Test Method - Visual Inspection
label | 13ea0ecd-bdf6-5ffd-9c3e-05e25d650f50 |  | note | Conformance Criteria - Concrete Inspection Record
label | d00e4c0e-363e-5d55-aaf1-96ea21d9b554 |  | note | Records - Concrete Formwork Checklist
label | dc10ba80-f474-5e6a-8e4c-77051c6bbf2d |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 10.2 - Concreting
label | a5396a8c-d1ba-58b4-95ef-c49212e0e73e |  | note | H
label | dad2750f-757f-510a-a91b-8b8cc6c6fc09 |  | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
label | 26983dfe-e539-5f80-a0be-ba65b4c175de |  | note | Frequency - At completion of pour
label | a51d8be6-a4db-593d-b4bf-f39fc150d70e |  | note | Inspection / Test Method - Visual inspection
label | adb7c33e-693f-5d30-bb39-74bad1d1ab5d |  | note | Conformance Criteria - Concrete Inspection Record
label | a0abec19-a091-5c2e-b439-d3068d277114 |  | note | Records - Concrete Formwork Checklist
label | edaacbbb-8f48-5b50-93db-855c5f3e6cb8 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Curing
label | 4c36ab38-6662-529a-bafc-4b502306704c |  | note | M
label | 5121ebfd-26f1-597f-b5cd-0cc780f79b9d |  | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | e4609059-c7a3-523d-8a32-ff7fcde70184 |  | note | Frequency - Post Pour
label | 604a852d-2789-584a-9007-dce3ab40ded9 |  | note | Inspection / Test Method - Monitoring the time allowed for curing
label | da7007f0-3aac-5b36-9e72-a912cb8f14c0 |  | note | Conformance Criteria - 48 hours minimum have passed
label | 8bfdef14-030c-55a5-be8d-106bf6048329 |  | note | Records - Concrete Formwork Checklist
label | 25adbdbd-532e-5ad6-a1ad-ab1119824ea8 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 12 - Remove formwork
label | 05ed22ab-b8d4-5d6e-a2ea-236c34ec588f |  | note | W
label | fb2f12d2-ed34-5016-8498-eda86805d1aa |  | note | Detail - Remove formwork after 48 hours
label | 91f155b7-5eff-5be9-9255-0eb0ee81bcbb |  | note | Frequency - Post Curing
label | 5c922b1d-7725-5fc5-989c-01a00fa1c3d7 |  | note | Inspection / Test Method - Visual inspection
label | ed1c3af7-43f9-5fff-b2f1-9a00331c8b3a |  | note | Conformance Criteria - Concrete Inspection Record
label | 6d0eeb0c-4dfc-51fb-b474-af24a1e8a249 |  | note | Records - Concrete Formwork Checklist
label | 5f17a232-e162-5069-a0f4-d764cae2f6df |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
label | c53b3f68-e3c6-5fdb-aa8c-7b5f61343c11 |  | note | H
label | ecaffd08-ccae-5304-8d75-ea85fd8b8f57 |  | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
label | e7d2268c-502f-5afc-8985-54efeef22e67 |  | note | Frequency - Prior to pouring concrete
label | cbba3cbb-c80f-510d-b82a-4c94eb28ecb0 |  | note | Inspection / Test Method - Measurement
label | a599a3f5-c94f-5689-b5ab-0321db5ac16e |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 3efd0d4d-59d3-53d9-8570-619b6cb74066 |  | note | Records - Site photos,delivery dockets
label | 57612fe4-c988-55eb-afc5-e6bf64410152 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.1 - Asphalt- Concrete extension slab/ Toe
label | fc1607e3-3568-5b6e-b0f1-1ab6ab0575b0 |  | note | H
label | 8462da4b-af82-5f6d-bcc7-9f738333c861 |  | note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
label | 99bd7d39-e354-5419-b341-8907444cca02 |  | note | Frequency - Prior to pouring concrete
label | 44de4a56-5667-5620-9251-5b16e85c218f |  | note | Inspection / Test Method - Measurement
label | 9dce2d72-5a9b-5a5e-ac14-2a7b2d825092 |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | b7dee4a6-5d27-5662-8067-d756921de230 |  | note | Records - Site photos,delivery dockets
label | 03184c93-b85e-56fd-b50f-410c358dc0a6 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.2 - Asphalt- Concrete extension slab/ Toe
label | 8626adbc-7dfd-560d-b5cf-b98876c263f4 |  | note | W
label | 38c64070-ee61-589a-95f6-8285e1f0a22a |  | note | Detail - Tack Coat between AC and Concrete slab
label | 00b9535c-4b85-56ed-9728-6bbb661c98b3 |  | note | Frequency - Post Curing
label | 562995c1-b33a-5081-8931-0c3dc0463141 |  | note | Inspection / Test Method - Visual inspection
label | bd61c180-060c-5bb1-b5ed-681c3c03dc28 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 0af383f8-bcea-53c4-a461-6ac463eb7a29 |  | note | Records - Site photos
label | 9f11b011-31a0-5e24-9df4-e3a042315ea0 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 13.3 - Asphalt- Concrete extension slab/ Toe
label | a598124e-78cc-53ba-87f8-8d36f4989952 |  | note | W
label | 36047350-6030-5bd5-af15-0a65c957c255 |  | note | Detail - 50mm thick DG10 / Mix 7
label | 0d532fc9-18f7-5936-b91f-03f242f923cb |  | note | Frequency - Post Curing
label | 2400a4d2-aa0b-5f50-97d4-744956d818e3 |  | note | Inspection / Test Method - Measurement
label | 3e1de7f2-b2cc-5a8a-b32c-0cbe218f67c0 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 64355c9a-dda6-52ae-95d3-06a6f4c27ea5 |  | note | Records - Site photos,delivery dockets
label | 6061f092-edc1-5f37-aef3-886716e6e92a |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 14 - Lot Number QA File
label | 71445b41-0ca2-5f5f-9594-69a5a139146d |  | note | W
label | f9e28319-3137-5808-940c-27eef065e5dd |  | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | d5e078a2-059e-5504-accd-f9a82be54c64 |  | note | Frequency - At completion of Lot
label | 22a8247e-ba31-5128-acac-676287ca0fdb |  | note | Inspection / Test Method - Document Review
label | 2d81317d-2599-5129-9e5c-6ff7db3673a0 |  | note | Conformance Criteria - All QA files compiled and sumbitted to client
label | 37100ac3-58ff-560c-ac18-99abcf9b4e2d |  | note | Records - QA records
label | 89427e26-f47b-5fcc-b2f4-6d5421ddf84f |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 14.1 - Lot Number QA File
label | 92bc1807-8247-5dd2-a771-59d5b2bfe82f |  | note | W
label | fd755b33-ecbc-56c7-922b-8b0d3dd294f1 |  | note | Detail - Delivery Dockets to be included in QA file
label | 5f656f5d-feda-5cc8-9af7-bd7058b650a4 |  | note | Frequency - At completion of Lot
label | 592020fd-feda-5285-8d1a-4182fa9c2087 |  | note | Inspection / Test Method - Document Review
label | 05db922e-9f86-5e29-82be-524518c5c771 |  | note | Conformance Criteria - Delivery Dockets to be included in QA file
label | 7d2de638-3e65-5245-bf6d-37c4863de1bc |  | note | Records - QA records
label | ba9b0dc2-42e7-5092-889e-d77f38f14932 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | f877b04c-05b6-58b7-beb2-042e920bc1ce |  | note | H
label | 75fce9dd-efa9-581c-bb17-f087d5f42d59 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 4fc7c330-0557-5c4f-b0ca-1721af0cfc4b |  | note | Frequency - At the completion of the Lot of work
label | 5fcc970e-0623-50d5-9360-cefa1391583c |  | note | Inspection / Test Method - Drawings
label | 5cdf80d8-e8b6-5391-a4d9-3e2fe11b48f0 |  | note | Records - Asbuilt Drawing
label | 367e8532-69b5-5384-a190-e8ce0f21d499 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Traffic Islands | itp |  |  |  | Yes | Stancombe Road - ITP - Traffic Islands | 65da4271-09f8-47e3-b8de-aa73d109da04
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 1 Kerb
label | fa623a68-67cc-4a51-981b-5dffc9102a79 |  | note | VERIFICATION ACTIVITY: QA FORM
label | bd67a7cc-8a72-49b7-a7f2-e315a2db18db |  | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | 126aef28-de76-4ec2-9275-398ad15aa3e8 |  | note | FREQUENCY: Everysite
label | 6810be6d-5b4c-4fc0-8b72-3e02a0e275ce |  | note | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid
label | 7c19e72f-b8ba-4093-a80e-666f59b09847 |  | note | Hold Point: Inprocess Inspection
label | d51cf50a-4751-4889-af04-ba1be4aa4b11 |  | note | Records: FH concrete QA sheet, photos.
label | c6386a31-6307-41b2-b2ce-2c390ec87835 |  | note | Onsite Responsibility: Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 2 Survey Setout
label | be2c4477-adb2-4679-8e37-3fe9c8d443ff |  | note | VERIFICATION ACTIVITY: Survey
label | 646d13ac-c7cc-4260-ad68-c4ef7257e90d |  | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
label | 157c53e9-ebee-4e37-8fe6-70c8a34d5172 |  | note | FREQUENCY: Prior to commencement.
label | b786b4f9-c51f-4615-b2c2-ab76ab5e30a5 |  | note | ACCEPTANCE CRITERIA: Survey
label | d86352d0-1476-4e50-b773-36c9257c8306 |  | note | Hold Point: As per AT Drawings 2020-AT-006-SD-G105
label | 3042c3d5-c6a9-404b-8db2-7e7c93a259d4 |  | note | Records: Survey Receipt.
label | 13708467-655d-48b0-83bc-ba69c8652b6d |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3 Concrete Island
label | 592d45d5-64ff-4e89-8546-d7fb5eaa66d7 |  | note | VERIFICATION ACTIVITY: QA FORM
label | a41586b4-8349-4815-8f8e-dd5bcfda2fd2 |  | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | a65cde82-0537-4c10-bb87-f8816c89a0f8 |  | note | FREQUENCY: Each Site
label | 9f9a71a6-49c9-4661-bdbe-5b369d48c7bc |  | note | ACCEPTANCE CRITERIA: Bonding Agent to be applied on existing surface Mountable Kerbs to be sticked on to the existing road using suitable glue.
label | b09d4688-9916-4586-9838-67753cc99c2e |  | note | Hold Point: Inprocess Inspection
label | 5cf88927-1a6a-45da-a7a1-73d5eb5931f0 |  | note | Records: Photos
label | f46d324b-4fbf-45b0-b22f-e2f2c1394dcc |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 4 Concrete Infill
label | a7e0f38b-c66a-4eab-8ddd-27760c4d3179 |  | note | VERIFICATION ACTIVITY: QA FORM
label | 33a75ccb-85ac-4288-b6b8-2cf013d5b6d4 |  | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | 1c2d8eca-ec3e-47de-893e-38cdee4848c5 |  | note | FREQUENCY: Each Site
label | a0e0a413-adba-442d-ab59-64019bb06535 |  | note | ACCEPTANCE CRITERIA: 150mm depth of 20MPa Broom Finish Concrete with 8kg/m3 of black Cross Fall of 2% or max rise in centre of 150mm
label | bbd01586-1722-42c9-8adf-b7b7932c5406 |  | note | Hold Point: Inprocess Inspection
label | aba085be-501d-47f2-920e-26c44e2b9a39 |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 11e195af-e60c-4a6a-9369-4e0f65176c33 |  | note | Onsite Responsibility: Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 7 As built information
label | b80fb9f3-9273-4266-ab07-463bbb9388eb |  | note | VERIFICATION ACTIVITY: Drawings
label | 9aaba3c1-e6c7-4854-90dd-47eb39c679ce |  | note | FREQUENCY: Every Site
label | 7ddb194e-a972-4806-9087-350b39973b9b |  | note | ACCEPTANCE CRITERIA: As built drawings
label | a960a5fe-2cc1-47d7-8ecb-62f63514d7c3 |  | note | Hold Point: In Process Inspection
label | 39f5f16a-de1d-47a4-a51a-626e81adf860 |  | note | Records: Asbuilt records
label | 68295748-109a-4600-bd64-fb09de5e1137 |  | note | Onsite Responsibility: Supervisor and Engineer
checkpoint-status |  |  | checkpoint | 7 RAMM DATA
label | d3985ace-934b-45f7-b9b7-2b25a503f8ec |  | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | 6b9d2f00-d9d5-46e4-bea3-4158f1e36a29 |  | note | FREQUENCY: Every Site
label | ac49c353-9647-46cd-92af-34f4ff55cb7f |  | note | ACCEPTANCE CRITERIA: RAMM SHEET
label | 0fced6eb-a759-41cc-b79f-7d48d02a6604 |  | note | Hold Point: In Process Inspection
label | 29147546-8ff7-4ffb-a6f0-ac075234fbf1 |  | note | Records: Asbuilt records
label | db89d2e0-8beb-461d-a0dd-36e76f773300 |  | note | Onsite Responsibility: Supervisor and Engineer
checklist-flat |  |  | checklist | Storm Water Drainage |  |  |  |  | Yes | Tui Rd - ITP - Storm Water Drainage | 663f957f-e38a-466c-ac46-241b84567e9b
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | ce12ade3-cb7b-5499-bf6f-3ec7d4c22204 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c7094bd4-e1ea-59b3-b91c-514084d1284a |  | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | 8b21e22a-e211-57bf-9de3-10b5b6c3af3a |  | note | Frequency - Prior to any construction commencing
label | e7a1811a-2e40-5d7c-a613-e6991e8fbdb5 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | cfedb522-4cc7-5979-b0a4-23c3f86df132 |  | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | 813b0721-0c7d-5aae-9f58-f3da43ea6b92 |  | note | Records - Permit attached or permit number noted.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | 5a0421d9-9d2e-5c84-98da-a04eb8897c0c |  | note | ACTION (Hold, Monitor, Witness) - H
label | b209d238-0232-5932-8aa0-c652838ec883 |  | note | Detail - Locate and mark out all existing services
label | e8d7e0ad-4ef3-57cb-84db-96901d156852 |  | note | Frequency - Prior to any construction commencing
label | 43550723-4b57-5a79-a4ee-5721731ce73a |  | note | Conformance Criteria - B4u dig procedure - follow utility protocols
label | b7bc9add-d5d4-5b87-9cd3-7885ca2df1cf |  | note | Records - B4u dig plans & GPR report attached
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | 7ef7394b-4c0a-5184-bb04-e5dc144cea7d |  | note | ACTION (Hold, Monitor, Witness) - H
label | c72270f7-5022-5151-83b1-b93258e009b0 |  | note | Detail - Sub-Contract and Supplier Agreements
label | 9963b1df-256d-5332-977e-1e35461b8acc |  | note | Frequency - Prior to commencement.
label | 004ebe3c-8101-57b1-9490-53ef8eb4ca4c |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | f59ccbe0-0c02-5bc4-af05-9c1599c7b30b |  | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | 67b28206-1fad-5e9f-8111-bfc6206b15ab |  | note | Records - Subcontract and Supplier Agreements
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 1439bcb0-ff56-5e50-8eac-67c7cf8a7bdb |  | note | ACTION (Hold, Monitor, Witness) - H
label | 53ddcff0-f160-5431-af08-b292010ad49a |  | note | Detail - Design is approved and Drawings are of the latest revision.
label | 8335cee4-c84a-54aa-8077-f713c2a00eff |  | note | Frequency - Prior to commencement.
label | f919c81f-0a04-5c43-b50a-f3f985d27250 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 72203cdf-e3e8-564f-aa3d-84628ded8cae |  | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 0afb1d06-6010-5a16-aae4-e534e6acef14 |  | note | Records - Drawing Register.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Survey Set out
label | 695eeadb-21d8-520c-84a5-b815e9143c92 |  | note | ACTION (Hold, Monitor, Witness) - H
label | be0f5bc0-1f30-586c-b040-8ed1f07e35a1 |  | note | Detail - Set out Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | 51069b86-ef88-58b9-86d7-4ee1774bd8bc |  | note | Frequency - Prior to commencement.
label | 9b628672-dad7-51a1-98fa-0121b24a1215 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
label | 1bbc6cff-32f8-59ef-bb3a-5bba4b0536b2 |  | note | Conformance Criteria - As per BlueBarn Engineering Drawings: 02237.17-T-400 & Set out files
label | 8441ed82-e175-54db-922e-ee4ade78bafd |  | note | Records - Survey Receipt.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Pipe and Manhole Material Compliance
label | c9fa5ad7-ebe7-53a1-b38d-b89b9fa24373 |  | note | ACTION (Hold, Monitor, Witness) - H
label | fcfeb77e-56b2-53e8-a11d-ca331eea818a |  | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | 364e94e3-1a7f-5f1a-a33a-0572b34905eb |  | note | Frequency - Prior to commencement.
label | 6bf48cda-311b-5643-a54b-ea1526ee5920 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review, Visual Inspection
label | b14f76c5-4a15-5117-b379-e861ce40a03d |  | note | Conformance Criteria - Pipe shall be Check for freshly formed pipes and return if required 1) DN300 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | b206e6ea-7685-5ac4-b53f-7918812b0798 |  | note | Records - Manufacturers Data Sheets, Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | f44f8fe7-e799-5fce-b898-b1a983f26779 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3d36c2cc-cd07-5999-89cc-e82f5595ee0a |  | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | 9bb0c561-23b1-51c9-b09f-cce6d4479516 |  | note | Frequency - Prior to commencement.
label | 72f38939-0521-5e68-964a-84b336f4bfab |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Potholing / Survey
label | d57c16bc-8e3c-590b-803a-96a90fb90597 |  | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | da25078e-c472-5d7f-b8e0-e6d2ca32b5c3 |  | note | Records - As-built Drawings. Doc. Review
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | ca817a5f-ec33-5e78-a10c-faddd889872b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2f1b4bbb-1371-56bc-b001-c91590241d52 |  | note | Detail - Excavation methodology
label | c23b3876-2e6d-55e9-a4cb-1354c2e6bf68 |  | note | Frequency - Daily
label | d17c12be-f085-54f2-9aaf-7dcb36132d5e |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Prestart review
label | bc79b9e3-9b17-556f-860f-b2076a7751b7 |  | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | 05f33886-f526-5cb8-a173-639a8a88d2cf |  | note | Records - Prestart RCP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | 9c26b39e-6b6e-5a31-abdc-1e37a3e82be8 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 3c5780f5-f074-5200-a1cf-0b4ce3c3457a |  | note | Detail - Trench Profile - Width
label | dd00e04a-51b5-545a-86b5-169f52d07b78 |  | note | Frequency - Daily / as trenching takes place. Different depth methodology
label | de46a123-f3cc-5b44-bbf1-9b215b3f5e37 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Excavation methodology
label | 146b0783-00c8-5c6b-86bc-8f6b4f9b901a |  | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | 8dc0da60-6656-5335-a24a-717ffa1ea55c |  | note | Records - Construction Photos
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | e1b507b9-acd6-549b-b766-51bf826a8188 |  | note | ACTION (Hold, Monitor, Witness) - W
label | cbdaedc2-9529-547f-beab-f99b31a066b6 |  | note | Detail - Trench Profile - Depth
label | f55ee2bf-d821-50a7-8c69-bfb528371505 |  | note | Frequency - Daily / as trenching takes place.
label | 63a96001-621a-5c0d-8577-6e9acee93800 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Measurement
label | c908020b-e5ed-5ce0-b27a-a71ded00e5b9 |  | note | Conformance Criteria - Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | bf3da196-eed0-5ed7-8cc3-1f7575b69f44 |  | note | Records - FH Drainage Line Record / Construction Photos
checkpoint-status |  |  | checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | 2b4984e0-e464-5af1-b3f6-65dfb79e03cd |  | note | ACTION (Hold, Monitor, Witness) - W
label | 37e2d56f-faaa-5b15-bc0a-ef364b50b088 |  | note | Detail - Placing and compaction of Bedding Material.
label | 7b0db10e-d525-5e5d-b05f-934ac13facc6 |  | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
label | 3d88c325-430e-555a-9116-b4dcffc07fd9 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 7f167ad5-14d7-533d-bebf-97fa4baf9434 |  | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | 31a4f39e-4026-5c70-bd42-b201cf10ed37 |  | note | Records - FH Drainage Line Record / Construction Photos
checkpoint-status |  |  | checkpoint | 9 - Pipe Position Tolerance
label | cac18c6b-ea1b-56e6-8c32-4a83da7d0787 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 69c29f0f-2a49-5699-bc78-16db35a32f83 |  | note | Frequency - At any point of pipe
label | a35be04f-e8c4-5531-8d4c-b79675c7c016 |  | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
label | 5a63b9d7-fe06-5dd8-9809-b932614ceee6 |  | note | Records - FH Drainage Line Record, Survey Data.
checkpoint-status |  |  | checkpoint | 10 - Trench Backfill - Placing & Compacting
label | 78ad3be4-f2bd-554d-ad7b-b0c66d78819b |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1ea30a9b-ead1-53f1-b050-78ee41c5e9a5 |  | note | Detail - Placing and compacting of Trench Backfill Material
label | 2f862942-ca48-5d04-adce-9974ce20f575 |  | note | Frequency - Throughout Trench Backfilling operation.
label | e42a7896-fb0d-5427-8f5f-4eedade00d96 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 9ff021eb-8ec7-5510-9cb8-f9aad7645160 |  | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | 4171789b-8831-527b-8a39-2b33323aff76 |  | note | Records - Construction Photos
checkpoint-status |  |  | checkpoint | 11 - As-Built Drawings
label | b91c72a1-211f-5989-b3ee-198c8943c6f0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 57ccb85a-d32c-53cf-b96c-98deba6cae9c |  | note | Detail - Red pen marked-up As-Built of every 'Issued for Construction' AT drawings
label | c5e98eab-cc38-59f3-b681-a4d8b2b28339 |  | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | cc8e8e67-1400-5203-ac6f-d3fce4c21cb3 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings / Visual Inspection
label | 6a67a938-4f28-561e-a79e-338133464b25 |  | note | Conformance Criteria - As Built and GIS Data
label | 1e002b85-2907-53a2-a42e-b6bf254ca696 |  | note | Records - Redline As-Built Drawings, scanned as .pdf files.
checklist-flat |  |  | checklist | Raised Pedestrian Crossing | itp |  |  |  | Yes | ITP - Griffen Park / Hillsborough Rd - Raised Pedestrian Crossing | 675ee30c-c74a-4b2a-ab55-b8dcda36facf
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 743f394e-1f78-52f6-aec0-910b3b43ae95 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 998a48d4-e80b-5f20-b631-1aada1adee71 |  | note | Detail - Obtain Permits
label | 666a9c98-f835-5152-b5cd-3535630d0f3f |  | note | Frequency - As required
label | 08cc6d70-9440-5e20-be3f-858ef4791eb7 |  | note | Inspection / Test Method - Document Review
label | e3434a21-35cb-50b1-980c-1212617e96e4 |  | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 7f2b3bd0-3b89-50d0-9f59-85a0042830c9 |  | note | Records - Permit attached or permit number noted
label | 37be8491-7d5c-5783-ad10-a6613d94c74f |  | note | FH Initials - Site Engineer
label | 22c54d89-f7a7-51e0-a959-6bb77cf59392 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | b4233b3f-cccd-5ffd-81a3-01734d1e5cde |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-construction sign offs
label | bae3bc52-53bb-58c5-b721-e32484f3fcb1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e73a868a-5f84-5fbd-a302-4a01654cece4 |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
label | f4858514-89b9-5705-9826-62259ffa32f0 |  | note | Frequency - Prior to commencement
label | 7593d285-e993-5888-8f51-a48d1ce69fbd |  | note | Inspection / Test Method - Document Review
label | e9bc0ac2-6dea-58e5-a341-88b8f894db41 |  | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
label | e60ac412-5583-5ba8-bcda-9d47c699c761 |  | note | Records - Subcontract and Supplier Agreements
label | 155ddd22-b381-51ca-b2a0-b68de21f0c6b |  | note | FH Initials - Site Engineer
label | 1c295914-e24d-5149-8570-c70064bff2ed |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | ce13ab75-88c3-5e28-b262-6d2757d3c569 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1 -
label | f0e02900-ec89-5628-9463-fe3f66092844 |  | note | ACTION (Hold, Monitor, Witness) - H
label | fe1c8a81-835d-5c06-a045-5b3ce1d75a5a |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | a6ae0a51-5c98-5c0d-987d-10d83cb3adb2 |  | note | Frequency - Prior to commencement
label | 8ee6724a-715b-569e-b795-b327637b50e2 |  | note | Inspection / Test Method - Document Review
label | 5562b31c-ad0e-561c-a818-fb5a8b83a209 |  | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | 4bcd5265-2caf-5433-a334-e53ac3315d12 |  | note | Records - TMP on MyWorksites/On Site
label | f27849e2-bbfd-55f5-a961-412800913f1a |  | note | FH Initials - Site Engineer
label | 3cd47e45-27a5-5a2c-8e6f-e2567892c8fe |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 9716d3b4-c05e-56fc-906e-326d23fa1ab4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 -
label | e0b5672f-03f5-5293-ab99-7edfabcb79db |  | note | ACTION (Hold, Monitor, Witness) - H
label | fae9c712-bc53-512d-a687-21d76b1a4180 |  | note | Detail - Ensure all Subcontractors and Suppliers go through FH induction
label | 26d22db6-16be-5b70-8ab0-a17b466635e0 |  | note | Frequency - On site daily
label | 46fc0b1e-610f-5a5e-a455-90db7773cb94 |  | note | Inspection / Test Method - Induction
label | f90789be-4801-5635-add3-8229fffa2220 |  | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | e98a67d6-24f1-56cd-a776-e3f33797ba19 |  | note | Records - Hazard ID and Pre-starts to safety team
label | 67409f98-7cf2-567e-a6f0-68d33ce8690b |  | note | FH Initials - Site Engineer
label | d317fa52-7f67-597b-aa30-dc19fee6355a |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | d5accf4e-bf41-50ac-86b9-312907b1af66 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 63ed5a53-6cff-5f1b-9518-397d19daeda4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 10fdabf0-0457-5679-abb9-be76e4406cc9 |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | abe54447-b43f-512b-9e21-3d57c1c17862 |  | note | Frequency - Prior to commencement
label | 70c8fca8-976c-5afc-8a8f-c4b06bc34678 |  | note | Inspection / Test Method - Document Review
label | bf8e9e1b-3d9d-57ec-9494-ba83b1d7bb49 |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | ed1bb690-ba26-51a7-8dcd-96b9ba536a0d |  | note | Records - Check Drawing Register
label | de3cc23b-0627-564e-b3ba-9c5b22bf7ea8 |  | note | FH Initials - Site Engineer
label | 33676ce8-9858-5568-b52b-3d4d161870db |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
text | c0dc5b1b-c807-5e35-8be6-de9bfe818b75 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1 -
label | 25705437-c9bd-539a-bba9-9c41c2c2fc15 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d276058a-4003-5645-8f10-730da7af6688 |  | note | Detail - Crossing to comply with AT TDM chapter Traffic Calming and TDM TC0023
label | 5cdcdfa2-83b2-557a-8e63-2a2ae65b9346 |  | note | Frequency - Prior to commencement
label | 65365f6a-a024-549b-a37a-a16017974cfd |  | note | Inspection / Test Method - Document Review
label | bbec4002-7056-57e1-a5a9-4d8d9ac9214c |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | 79c1235f-3b66-5e8a-8cf0-3896e92727e3 |  | note | Records - Check Drawing Register
label | 55ccca84-e61c-566e-bd27-b1f431235e35 |  | note | FH Initials - Site Engineer
label | 1a21cdb2-3771-51b6-a43b-9be59677ce5a |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
text | 7dffd69e-c453-5a50-bcf9-4eb26cf779bf |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Installation of Erosion and Sediment Controls
label | 53972ef7-c899-558c-8397-dfd33197bc0c |  | note | ACTION (Hold, Monitor, Witness) - H
label | f8ec7f47-5847-5b6e-842e-7e8797d1a052 |  | note | Detail - Ensure that Erosion & Sediment Control in place
label | a38f7384-eb9e-5be1-88c1-afeaa5f70803 |  | note | Frequency - Prior to commencement
label | 0ebf44ac-9405-5e3b-8bba-1548b2b69542 |  | note | Inspection / Test Method - Visual Inspection
label | 7c66ad45-0c4a-5507-8258-eb5c320f9bef |  | note | Conformance Criteria - Cesspit Covered
label | dc991284-dfb7-59eb-9c18-464c37c3aeb4 |  | note | Records - Environmental Controls Audit
label | fd557d8d-b5a4-5a1f-9a10-eb75bfa9121a |  | note | FH Initials - Environmental Manager/Site Engineer
label | 6e9f03f2-b28d-5747-8c1e-5e45cdd8d75f |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 6fc3f89a-798c-537f-b545-1a2fa587f1fc |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | 305137f4-5c59-5b03-88ee-b856a54bfe25 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e640d3ce-1028-5076-9e03-c81e213a67ae |  | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | 377190c7-dd4e-5cc4-9f84-3b61f7a92b3d |  | note | Frequency - Prior to commencement
label | 2288be0c-7e60-5cf5-858c-1d4c4831a4ce |  | note | Inspection / Test Method - Survey + Smart Level
label | b2bee5c4-8611-533a-999f-1c130d740a8a |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 0282cf09-3fd1-5da4-b265-29152ed97b3a |  | note | Records - Site Photos post surveying
label | 5a887695-d842-51b8-9208-a8be1a9d4520 |  | note | FH Initials - Site Engineer
label | b973ab93-add5-5141-8167-998dba3f619f |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 75a5911f-2ba2-5602-aa5f-8bcac3138b41 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging
label | 191a74cb-5de3-5d42-845b-7dd535283257 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d0fad140-2a9b-5dd6-b9b8-a23332a5db20 |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | 384b1d8e-7fe3-552d-93a3-27ef3d6cffd3 |  | note | Frequency - Prior to commencement
label | a0e260cc-2e80-53a7-8e7e-54e4abe1ce9f |  | note | Inspection / Test Method - Potholing
label | e2f73abc-4c62-5a57-8632-bf21d785d311 |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As Built all services
label | 28088d3b-7fd7-525e-8bb7-cebeb569cfb9 |  | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
label | c68377d7-135b-5703-8e57-cc35ba2eb278 |  | note | FH Initials - Site Engineer
label | ae55524e-d959-5c7f-8b95-8e6e00dcdc55 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | f3e3c667-0585-5484-9333-d698758d938a |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Material Compliance
label | 0ff5e9ad-1521-591b-b50f-291a45260d02 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1bcdbf6a-0751-5061-be6b-15ab6d9c40d6 |  | note | Detail - LESA dowels to be used at all construction joints
label | 3dc19584-4eda-5c30-adcb-109a7350d7d9 |  | note | Frequency - Prior to pouring concrete
label | ca43555c-b3e0-5bb9-89f5-ea1e0c6c8621 |  | note | Inspection / Test Method - Document Review
label | bc1b6618-6779-55b4-9f8e-594ab61e2189 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder , TDM Standards TC0023
label | 13a10bf1-ab5d-52ca-8e37-ac475c72db9a |  | note | Records - Delivery Dockets / Photos
label | 6379e5ab-379a-5b1b-b5bd-376880d11d21 |  | note | FH Initials - Site Engineer
label | d2bcb7c2-30db-5388-b573-1cc3aea6b81b |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 948e68fb-6de6-581c-8193-29ab87a9bfe9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1 -
label | bd59d219-fa02-5776-8649-142c5e8a5789 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4a250757-3fd5-5ffc-b80a-3aa3b5a8d072 |  | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
label | a804a868-fce1-5d12-a726-bc08563986e4 |  | note | Frequency - Prior to pouring concrete
label | 19bf6d34-e8e9-5791-986f-1f9eb5187842 |  | note | Inspection / Test Method - Visual Inspection, Document Review
label | 17e7739d-43d0-5a34-b2b3-9f2d0c26267c |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder , TDM Standards TC0023
label | 29d1f7fa-c96f-548d-9fa5-bbb7995bc5be |  | note | Records - Delivery Dockets / Photos
label | f8b13bb7-086e-50a7-bee2-c5dc4418bc14 |  | note | FH Initials - Site Engineer
label | 110c62d9-c3b6-5047-b88d-1418975a325b |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 6ad95c36-1d7d-5f21-8606-e968d4fc47b0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 -
label | 71f92665-8b3a-533e-9618-e6448a2373df |  | note | ACTION (Hold, Monitor, Witness) - H
label | fd7dfe30-703c-58e9-9339-ac9f5d138ec1 |  | note | Detail - 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | 3a9e850c-4adb-5bdf-8f33-b7eda8d298e2 |  | note | Frequency - Prior to pouring concrete
label | 55bcfa59-608c-5b54-a5e4-0dc9e1763ab6 |  | note | Inspection / Test Method - Visual Inspection
label | 0582f9cd-308d-5e1b-8eee-417f712ae3a7 |  | note | Conformance Criteria - CIV >15
label | 0a0e7215-cb9c-5714-8025-c71a843532b6 |  | note | Records - Delivery Dockets
label | ec369f97-e4aa-5fb1-9b0d-d6ca2b8c7dd1 |  | note | FH Initials - Site Engineer
label | 91be0faa-dac3-5d95-bd2c-696c40fc1948 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | af6dbaba-36de-52f6-a7ad-49ad1c842c68 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 -
label | 1e5338d9-3bfa-5279-89a8-fe703970d03a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9c3ca01b-8f8f-59ca-9578-926110b2992a |  | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs separating.
label | fe4fa732-483b-53cb-97cc-a0406f431937 |  | note | Frequency - Prior to pouring concrete
label | dde606a0-2300-5938-8ed5-7b42d0133a07 |  | note | Inspection / Test Method - Visual Inspection
label | 1df720ab-e3dd-5cf3-a476-793a1181c593 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder , TDM Standards TC0023
label | 86856948-e7d7-57d9-99a2-c59f32954e00 |  | note | Records - Delivery Dockets / Photos
text | 8b1d09ab-8860-5673-878f-e60c6ed2e64d |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.4 -
label | 3f26db56-e3e5-595a-bc01-8c7ecfd7e630 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3009b2b9-7220-5e26-bfc5-2023896048d9 |  | note | Detail - All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
label | 91a1d8f6-eab9-5daf-aa48-513bb075f872 |  | note | Frequency - Prior to pouring concrete
label | ab2ac2cb-4ffb-5f28-87d4-4c6cb592e68e |  | note | Inspection / Test Method - Concrete Delivery Dockets
label | ec9c1931-d912-5069-bfb7-add9d74ae8cd |  | note | Conformance Criteria - Delivery Docket added to QA folder, TDM Standards TC0023
label | 3c35015f-79cf-509e-a794-3ed1670a4f35 |  | note | Records - Concrete Delivery Dockets
label | 1d28e43f-7eae-5b4b-affd-9e74959a0b4f |  | note | FH Initials - Site Engineer
label | 066a4953-90ab-5678-b3e9-22b4060d215e |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 1a97805a-0b49-5cd6-8dc3-b6e9a440d4b8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Temporary Works (Formwork)
label | 87c1b134-d5c9-5c3b-a42c-cd92ca3337b2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 71f242ab-1bbf-5b9c-854e-58ce58f7a011 |  | note | Detail - Formwork to be set to correct line and level
label | 1a38cd38-a690-5de6-bafb-c6366a2c8e52 |  | note | Frequency - Prior to pouring concrete
label | 49ff6c72-6b6e-5865-a9b2-750e07c42ad5 |  | note | Inspection / Test Method - Visual Inspection
label | 5a1f82a8-d4c6-5611-b00c-a78fdc793b26 |  | note | Conformance Criteria - Concrete Inspection Record
label | 06e3a4f4-79e0-5dc8-8eeb-c65117c42f52 |  | note | Records - Concrete Formwork Checklist
label | ddb5e725-f1cb-5aa7-8fa2-d98ab3b91d8b |  | note | FH Initials - Site Engineer
label | 8e0fa104-690e-55d7-be16-cee604a76bdc |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | 9c7152a8-697b-502c-9440-5971d9561e06 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.1 -
label | c62b26f2-d091-509c-b942-8616cd4eefb7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 22273b0c-c6f4-5422-9359-6405067ed7be |  | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
label | d0efd942-ce5a-5212-826a-70f3bcc4c164 |  | note | Frequency - Prior to pouring concrete
label | 6f3103a0-3e7c-5492-8d62-1b62032b0806 |  | note | Inspection / Test Method - Measurement
label | 19e3e988-cb4a-52a5-a6ed-b0789d5eaae4 |  | note | Conformance Criteria - Designer to inspect formation level
label | 269c91e7-9322-5b90-a6a3-f04a881cb1a4 |  | note | Records - Site photos
label | 3c577486-4b8f-546e-8b31-b3d1028560a5 |  | note | FH Initials - Site Engineer
label | b2e3e3b0-1b3c-51c1-9411-7bb1fffc5e99 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | 5c91497a-2cac-53db-94aa-dc21fa742b0d |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2 -
label | b1d12a44-ca5b-516c-a58c-a71f33bdc255 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9a3e3591-eb15-5cc1-bd92-990820b88704 |  | note | Detail - Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
label | 5c129969-97b0-5178-bd1b-cf149595f9b6 |  | note | Frequency - Prior to pouring concrete
label | 60750d07-dd68-50ed-bda4-f1104cf8462f |  | note | Inspection / Test Method - Measurement
label | d469926a-86e4-5e0b-888b-ada55a52fb02 |  | note | Conformance Criteria - Designer to inspect formation level
label | 4c616c76-c41d-5fd1-a115-03ff487cfe6b |  | note | Records - Site photos
label | 4b809eee-57f3-549c-95ae-2bba693d5d06 |  | note | FH Initials - Site Engineer
label | 2ee74086-09f8-5106-bf37-abf4eba01fe9 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | 07abe915-c43f-5e32-870f-c13c01994773 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.3 -
label | 44d50171-35a5-5695-993a-e00fb93f8f98 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e24e550e-20b4-52f6-bf3c-c6f260e10e60 |  | note | Detail - Raised Table ramps to be 0.75m across for entry and 0.75m for departure ramp.Toe to be 0.5m across for both entry and departure.
label | 70574e7a-9aae-5680-bd36-97ad03965059 |  | note | Frequency - Prior to pouring concrete
label | 1713efd0-8f10-5983-b2d4-563219ce1ed4 |  | note | Inspection / Test Method - Measurement
label | b601970d-15fa-5c93-9f00-00f8ac952aac |  | note | Conformance Criteria - Designer to inspect formation level
label | d2150279-31e9-5a8f-975b-58c669a43c86 |  | note | Records - Site photos
label | 820740d0-3aea-5e1e-b430-cedd5d5fb833 |  | note | FH Initials - Site Engineer
label | 0cd0c48c-5fc6-5842-b3c8-eff4084f3f4e |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | f95ebe8f-4aa7-57c5-89a2-7c2b916d2ad4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4 -
label | 1078e69c-6c7f-5d25-b5da-c6924faf4c92 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3979e85a-5acf-589b-b455-3720b9675e31 |  | note | Detail - Raised Table ramps to be 1:10 gradient for ramps
label | 1653c6c8-d44a-5c8d-91e2-a9194b76f3bf |  | note | Frequency - Prior to pouring concrete
label | 38fcc4c2-f175-5f49-b253-cef8d13e58d2 |  | note | Inspection / Test Method - Measurement
label | 6bf6ae18-a16f-5ec5-a92b-aed2544e163a |  | note | Conformance Criteria - Designer to inspect gradient level
label | 3f3ad05c-78ba-5370-b036-bb5a4046dbb0 |  | note | Records - Site photos / Concrete Formwork Checklist
label | e1e3a7d9-2dbd-54f0-babf-9252e8f24820 |  | note | FH Initials - Site Engineer
label | cd580057-d419-53c0-a1c5-370c940b25be |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | 2d7ce3d3-acc4-536a-b63d-4fc9d7b293d0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5 -
label | 1e56cbdf-b19c-54fe-a09c-c78dea2fa1e9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0e84f1d4-cf27-5a66-97ad-215e00dc6d81 |  | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | 216edd0e-b45c-58ef-8b6d-6eadd63de2c2 |  | note | Frequency - Prior to concrete pour
label | b376dae0-2cb8-5563-a525-fdb35d449609 |  | note | Inspection / Test Method - Visual Inspection
label | 97f60df9-ad87-5395-841c-f4577a648683 |  | note | Conformance Criteria - Concrete Inspection Record
label | 3d2c51af-fcd3-58d1-a3c4-e598b12c272a |  | note | Records - Concrete Formwork Checklist
label | dfd4d08f-8f5f-5760-85f0-fc3a17cfe282 |  | note | FH Initials - Site Engineer
label | f413907a-a41a-56f9-985c-59a00d51b851 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | 00841943-1307-5d0f-9a07-c7a916517572 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Reinforcing
label | d2358297-f736-567c-b800-e3e61f8dc0f1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9030bec8-48f9-5271-99b3-2dd72e17fc04 |  | note | Detail - Construction joints on speed table to ramps are to contain 2 rows of LESA dowels or similar approved dowels . Dominator dowell system 50mm w/ Black 300*50*6mm plates @600 centres placed across the construction joint and for joints from ramps to toe slab @400mm centers
label | 68bef280-9c04-5157-8ff4-6d6dcdcd3ee9 |  | note | Frequency - Prior to pouring concrete
label | b31272ac-1b6f-58b3-9d54-371b280dfc1a |  | note | Inspection / Test Method - Measurement
label | e52acfd2-93fc-5164-9dca-d1b4c2bbc951 |  | note | Conformance Criteria - Concrete Inspection Record
label | 75cb88dc-06b6-51b9-b3b0-ea6d87546b4f |  | note | Records - Site photos/Concrete Formwork Checklist
label | 4baabccb-becb-5fba-ae6c-5f696f625138 |  | note | FH Initials - Site Engineer
label | fe9c1b92-4bb6-567a-acfe-a491697f85fd |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | aa60d608-cb15-5521-a5af-840729d038fa |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Concreting
label | a8654745-5d38-50fa-83a2-9e0dc1b49650 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9190573e-f479-50b7-ad2e-f50099aa57a6 |  | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | ab3ddc60-e747-56ca-8f7b-acf067cc2722 |  | note | Frequency - Prior to concrete pour
label | c9aec916-bff7-52e2-bf69-7d814c7a4e5c |  | note | Inspection / Test Method - Visual Inspection
label | 446a8326-24a1-542a-8b2b-1ca8d8a72110 |  | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | fc2b2a4c-3c50-5c32-a635-d188fab8536a |  | note | Records - Email / SMS
label | 37ed9620-c762-5f0d-b3e1-0a3830e4eaa2 |  | note | FH Initials - Site Engineer
label | 3234fc09-7b3f-552b-a378-3b3724343547 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | fb028f1a-c1ad-5626-9711-85974414290c |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1 -
label | c8672506-cfca-5ea9-b353-353334e80701 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9cd26314-2106-5e19-9467-f6050175eac8 |  | note | Detail - Vibrator to be used throughout concrete pour
label | 096aa3cc-eb79-5079-9821-a68b2b2f4099 |  | note | Frequency - When pouring concrete
label | 730b24fd-9284-5354-bdc0-43944e0c0a7c |  | note | Inspection / Test Method - Visual Inspection
label | 72b00502-e1e4-543b-b61b-20d39ee4f847 |  | note | Conformance Criteria - Concrete Inspection Record
label | 0c77912a-9c6b-52ea-8c27-e76dd689d861 |  | note | Records - Concrete Formwork Checklist
label | 244197ee-d62a-5310-8b6c-e8ecc44b856d |  | note | FH Initials - Site Engineer
label | deaecb95-7aab-53cf-8593-e44dca6a7dcd |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 147e47b6-dca5-5368-8106-03b8933bceaf |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.2 -
label | 0c7d36d6-128f-5db7-9c77-e0b12ca3adcf |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1e5f49a7-5b3b-5468-9a14-9dd7d0c698b9 |  | note | Detail - Concrete ramps surfaces shall be U5 broomed finish and speed table top exposed finish
label | dcdd8eb1-3830-515f-b7f2-8aa2b5b1efd3 |  | note | Frequency - At completion of pour
label | 6472bda0-73c5-5a22-9420-6707de200973 |  | note | Inspection / Test Method - Visual Inspection
label | 0b0d6e42-a3e1-59fd-88b7-7038053c0c88 |  | note | Conformance Criteria - Concrete Inspection Record
label | e4f39354-9f56-52b5-90ad-a2e9a09bd14e |  | note | Records - Concrete Formwork Checklist
label | bf66e0ca-dad5-5507-b9d0-0534bd1d8db6 |  | note | FH Initials - Site Engineer
label | c3f42d56-86c8-58f6-b44e-caea1f600b62 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
text | 08f0bbcc-2a33-56eb-96d0-3cb7655e2589 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 11 - Curing
label | fe16bba1-2860-58f8-a181-0a1eee75562d |  | note | ACTION (Hold, Monitor, Witness) - M
label | effc93a3-b19e-53c2-9fd5-7c30ebbb0e31 |  | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | 4d0dd5b8-3b3b-57e1-a824-2ed54d7e8140 |  | note | Frequency - Post Pour
label | 90a65e24-6cb0-5074-a10a-bacdc616e4a7 |  | note | Inspection / Test Method - Monitoring the time allowed for curing
label | 0282aeb9-e2f3-5660-b8fc-413ed3ee36a2 |  | note | Conformance Criteria - 48 hours minimum have passed
label | 1f19ed44-c2f8-5d93-9a81-3780ce585553 |  | note | Records - Concrete Formwork Checklist
label | ba39398e-d06c-5c2b-9f7c-f10f8722593f |  | note | FH Initials - Site Engineer
label | e819dcd7-b8e9-5bdd-84cd-a329578c0267 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | c0c7d883-a40d-5b09-9886-6971187305ca |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 12 - Remove formwork
label | 7342e5be-5981-5e25-9afb-c0090b3891d6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1feef54b-6fc7-5dfe-9d70-fe4774e60ca9 |  | note | Detail - Remove formwork after 48 hours
label | 669e77e1-1c5a-572c-a1e8-6cef521b83c8 |  | note | Frequency - Post Curing
label | 35371291-d25d-5848-9001-fa1de1e8841c |  | note | Inspection / Test Method - Visual Inspection
label | f3dbefd4-6da7-5e80-85fb-73b67f28a3d9 |  | note | Conformance Criteria - Concrete Inspection Record
label | 77f2201c-4d6d-5863-b661-06204ee0eae0 |  | note | Records - Concrete Formwork Checklist
label | dd0988de-7bcc-5fda-9ace-4aff4c865b7d |  | note | FH Initials - Site Engineer
label | e3d05c8c-a136-54f3-b7ca-5cd2f991fe3f |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 3d0ec4f1-33d8-5a6c-8d2a-26126422e13e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
label | cb545052-c194-5378-8677-b04cceced7ce |  | note | ACTION (Hold, Monitor, Witness) - H
label | cd118236-9a0a-5031-b7a2-59748e2f2196 |  | note | Detail - One row of Lesa diamond placed mid depth @600 C/C along construction joint placed at 75mm as per TDM TC0023
label | 6e4a2f94-df33-520e-80ab-a64caaf336b2 |  | note | Frequency - Prior to pouring concrete
label | 07fb6e8a-3964-56b3-aeb2-db3733193f02 |  | note | Inspection / Test Method - Measurement
label | f02f57b3-66e5-57b1-89c2-dda55b64b823 |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 5fac1a7c-9f96-559b-8490-62dfc7917cb0 |  | note | Records - Site photos,delivery dockets
label | fd11530e-0d8c-5e4e-8488-93cc068df69f |  | note | FH Initials - Site Engineer
label | 285e6ee3-84b7-5950-bf50-58c1380fc6a2 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 7a97f842-4040-5928-ae7c-39890324c605 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.1 -
label | 5d2e404f-b8a3-5c55-9766-d1007f71e03e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7277d1c6-60c4-5d5d-b3ae-db0f64757e69 |  | note | Detail - 200mm thick 40Mpa Concrete and 4kg/m3 Black Oxide with one layer of 663 mesh
label | 137f4a50-b9ad-5141-89cc-96d75afb2e84 |  | note | Frequency - Prior to pouring concrete
label | 4a896d15-7e27-54ba-bdfb-1966c0d7efe2 |  | note | Inspection / Test Method - Measurement
label | 72e37624-e501-50fa-b637-85b2048f91d9 |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 3fd06662-caef-540b-8eea-585541a30d43 |  | note | Records - Site photos,delivery dockets
label | d21710af-3659-5464-84f5-6128e69a40c4 |  | note | FH Initials - Site Engineer
label | 6888c2de-2607-5310-82bd-2784ee400071 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | e3e0b89c-49ad-5b9d-a7b2-48b542c26d5d |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.2
label | a97fbcce-0c97-5d9d-a209-9cdaad391d62 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5d03ff69-2148-5de1-b299-45d23bfec7db |  | note | Detail - Ramp to have relative gradients
label | c52fc280-0c01-573e-bf2a-cb935c8a9897 |  | note | Frequency - Post Curing
label | 3e0d71d5-0727-5c35-81e1-c04c358c44aa |  | note | Inspection / Test Method - Visual Inspection
label | 28c97675-b76a-5ae3-ab7c-54561c6becf4 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | f6292383-7e01-5466-923d-7cb5127dc48e |  | note | Records - Site photos
label | e9944dc6-66f3-51ca-92bf-cb7901cde027 |  | note | FH Initials - Site Engineer
label | c27ca429-1c60-59e4-a67f-293ae8c36f71 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 779978f2-ebcf-5ed6-b8cd-e8d95d6e84c3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 13.3
label | f42206af-07ce-5009-b3ca-744e358661f1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8722b95a-9725-5026-8348-6aadb781790b |  | note | Detail - 150mm thick AC14 and 4kg/m3 Black Oxide
label | 5fdf6db8-12ec-5634-bcc3-2e8e0c12fe37 |  | note | Frequency - Post Curing
label | 4b542863-e36e-5910-9895-ad570d2a020b |  | note | Inspection / Test Method - Measurement
label | 74f77d05-8c77-563a-ad64-27ba0b1c6711 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | c0389ace-417b-5ba0-a88d-ed79428a6c99 |  | note | Records - Site photos,delivery dockets
label | b3aa290e-57b7-57b0-a063-1ed4ba453c32 |  | note | FH Initials - Site Engineer
label | e50fe992-bfa7-5a4f-bcd4-3c326a284d65 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 2f3d17d9-7057-5f97-8419-cd9aae59a9d6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 14 - Lot Number QA File
label | d8206635-15f1-5fe1-be38-c33177ad0bf8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 17d37a13-bed5-5a49-8f51-55af8bb34fe1 |  | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | 37598047-d5d3-5a04-82eb-976d5987ec3f |  | note | Frequency - At completion of Lot
label | aaacd99f-6c10-59fb-b67a-65cbc9b9d6e3 |  | note | Inspection / Test Method - Document Review
label | e7bc4a3d-a565-52f1-b26f-a4a3eb5d801b |  | note | Conformance Criteria - All QA files compiled and submitted to client
label | 056004df-1dc6-5f77-b9fd-96c7ff834cdf |  | note | Records - QA records
label | d1d66302-67ca-5fe7-b6e4-b45d2808d7c0 |  | note | FH Initials - Site Engineer
label | 71befdb4-af2d-5925-982f-1ea4a7c45d66 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | a484d16f-0cf5-5195-99c9-526787af5ae5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 14.1 -
label | 84adbfc3-ea0a-56ab-aead-f7be0cc86217 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e692b458-926a-5aba-98ae-aabcfc3d66db |  | note | Detail - Delivery Dockets to be included in QA file
label | 9cee4bfd-3efe-585f-b51c-d2db46395277 |  | note | Frequency - At completion of Lot
label | c33034f1-7934-58ae-8910-cb59493e9012 |  | note | Inspection / Test Method - Document Review
label | ec9da1f2-4be9-5c53-9e9e-f3c5515636a0 |  | note | Conformance Criteria - Delivery Dockets to be included in QA file
label | 9a645740-c1d9-50af-ad47-de2010f4f5b0 |  | note | Records - QA records
label | 3fbae257-baf9-5678-9783-aeaa40890809 |  | note | FH Initials - Site Engineer
label | 20a587ca-87f5-51f6-90cd-0697306be048 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | dc2a0fa9-a27c-52b6-ab94-8187ff40303b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | 88653977-ca8b-5572-bcd4-ff8fc95dfa62 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 28fed422-7123-58f1-abbf-583ca78ab54b |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 916aa532-76c8-5135-b090-f49291c6d24e |  | note | Frequency - At the completion of the Lot of work
label | 4c6b9d25-2fa6-5543-b4bb-4dabdcc84ac8 |  | note | Inspection / Test Method - Drawings
label | 468f919f-0e6e-5ff3-982a-b0f0627d4196 |  | note | Conformance Criteria -
label | 10032ae9-f60f-546c-b430-7c5f76330637 |  | note | Records - As Built Drawing
label | 8bff1634-7746-5dd6-8d68-53c42a7d0832 |  | note | FH Initials - Site Engineer
label | 94f967fa-4b74-522f-9544-531392d18048 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | e8f2286d-9859-5b75-b74b-c8d41f4a2956 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | e5e49220-39c1-5777-a54f-9de73d26a9db |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 5a5f3dc0-763c-5527-a5b2-db9d8c094daa |  | textbox | Print Name:
text | 97ce6320-1154-5bc9-9412-de09a9e40e6b |  | textbox | Position:
text | b8bb8922-6702-5b8f-98f6-e85f4dfe4774 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP - Great South Rd - Enabling Works | itp |  |  |  | Yes | ITP - Great South Rd - Enabling Works | 73bbe34e-4ece-4ad8-8628-f2a61c715d41
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | 5eae14dc-b408-5d3c-9d2c-b04b0835e9ae |  | note | VERIFICATION ACTIVITY - Surveyor
label | fcc9d8f1-1a4f-5bcd-b233-428c6c248e47 |  | note | METHODS OR REFERENCE - Surveyor
label | 2b2ca28c-629e-516a-9e39-8ef050ddd25a |  | note | Frequency - Everysite
label | d5e440ff-ec77-563b-afec-6ec2393cd3b5 |  | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
label | bb92998a-b0a9-5848-a17b-60caaa00fffb |  | note | Hold Point - Mandatory HOLD POINT -
label | 531f5f41-471d-5c9d-a251-fec63c643b57 |  | note | Records - Onsite records/photos
label | 1ad67a61-d3d3-5692-9ddd-ec07b356873d |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Kerb & Channel
label | cbc1db41-ca55-59ca-ba45-7dd9ca57ec81 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 49ee2e6d-176b-56b6-b987-6bfb579fbf24 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | 0776bfc8-d86e-5345-bb7a-c5b20fce8c81 |  | note | Frequency - Everysite
label | dde84042-4251-536b-8d76-058adb03a8d4 |  | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
label | c41c85e2-1379-5476-b063-5bb5b82d0839 |  | note | Hold Point - Inprocess Inspection
label | c0a79302-d6e1-5d67-ae1b-3e44eeb71d91 |  | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
label | 57c98571-6344-5a7d-a679-7820b9bc28fc |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Channel Level
label | 5871bb79-a7e4-5d3b-9dc2-22921f6059d6 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 8d4c4059-6b43-521e-ab35-3ae738e371b9 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | 939f4117-d970-55eb-9acf-df6d6935b7f5 |  | note | Frequency - Everysite
label | 535731cb-d647-5f8a-9330-65c897f8a8b3 |  | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | e86eca70-04d2-53ad-8d1b-a5e14b30695a |  | note | Hold Point - Inprocess Inspection
label | 3b6679f5-2349-5cb8-8d84-3d7483afa4e1 |  | note | Records - FH concrete QA sheet
label | a8f174b2-b0f8-598e-aee3-8f9bf4c99dd7 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | CIVIL WORKS
checkpoint-status |  |  | checkpoint | 4 - Concrete Footpaths
label | 8a4bcf08-ca80-52f6-994e-e9482aa0f1f0 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 9d2faa96-57d3-59d4-9620-c06f1764a7ed |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
label | c5327c34-0bc1-583e-b44e-5840fb5dedce |  | note | Frequency - 10m Intervals
label | 1c685a2b-a1d0-54a6-8403-00c988eb99db |  | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with exposed finish
label | b9be1382-d072-5557-bf6e-7d51ba4ce5a0 |  | note | Hold Point - Inprocess Inspection
label | 25e828ca-4aad-5da4-a74a-815947b46c65 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | d0a92fe3-0f03-5d93-a837-ad605dcffcba |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - AC Footpaths
label | d53706f3-3d09-5793-beca-162635fbfa09 |  | note | VERIFICATION ACTIVITY - QA FORM
label | ec6e4f43-654c-5a0a-9b0a-eecafac5bbd1 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
label | 4f94c76a-22a1-5429-bc79-63361d4bb1c8 |  | note | Frequency - 10m Intervals
label | c45bf35a-588b-5b24-9c6e-dd051c8789d6 |  | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 13 DG10/Fine asphalt mix used
label | 4f175555-1a0a-5280-bb80-dca2e0e5f9f1 |  | note | Hold Point - Inprocess Inspection
label | c0ac7a74-7321-5e35-83cf-998206145654 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | b866075f-e6f1-5af9-83ea-ded97134782b |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6 -
label | 6e4705e6-1824-5ba3-a4ba-0c430f604ed0 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
label | ed4619d5-4f99-53f3-960d-fd1a4a702446 |  | note | Frequency - Each PX
label | 75a93ecc-bc7b-5038-8551-c41fac0f2907 |  | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
label | d0690f84-c7cb-5a1c-b3b3-41d5e981a199 |  | note | Hold Point - Inprocess Inspection, Measurement
label | ff597f46-653a-5233-9602-4f09f8c6a466 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 7b9f3ae3-d055-56cc-955e-c6078ff4f423 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 7 - Tactiles
label | 2baee133-ea73-587d-a324-ee0396645350 |  | note | VERIFICATION ACTIVITY - Visual
label | 178b44f3-02f7-5d62-86a6-ce0496b3fe1b |  | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 6d70b911-560c-572c-866a-8df57bfed342 |  | note | Frequency - Everysite
label | a803ae83-70be-5b65-8f6f-058832fe7038 |  | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | d65f5680-9f93-5983-a672-72ca69162597 |  | note | Hold Point - Inprocess Inspection
label | aa2ff71d-be75-5563-a721-08cfca9eda13 |  | note | Records - Photos
label | 1f6d4121-5380-5ad4-b498-120b2417372f |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 7.1 -
label | 8a9c9608-bba5-5faf-88e2-a789a7167b34 |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | a87bd221-3d19-501f-8048-b97f9ba2d4c4 |  | note | Frequency - Everysite
label | 6c5bd917-0deb-5494-8724-30dcd6851f25 |  | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | 132c87e6-2e47-5174-8cd0-2b2752391708 |  | note | Hold Point - Inprocess Inspection
label | 4a20fbac-7dc9-581a-8276-4e2347e1ebf7 |  | note | Records - Photos
label | 2c26aa0b-e8d9-5e50-bb13-63a02e74c2b7 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 7.2 -
label | 826a9828-498a-5842-a593-3ddb15171199 |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | c3e8bbcd-f6ff-5762-ac87-8d82c860fda2 |  | note | Frequency - Everysite
label | 55b9be87-0372-5f88-b522-f780febcfbd8 |  | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | 872a1646-c388-5ed6-a347-d06cc248d430 |  | note | Hold Point - Inprocess Inspection
label | 0489acb6-328d-58bb-b4cd-8e075dee6b04 |  | note | Records - Photos
label | f7c66119-bbfb-57df-93b0-be29b74d89e1 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | RAMM DATA
checkpoint-status |  |  | checkpoint | 8 - As built information
label | e12c6822-2530-5655-aecf-b10e6f65ede0 |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | ff03c488-d36e-59ad-8b8a-6e8a333c5d5f |  | note | Frequency - Every Site
label | 4c817798-9502-5586-8a18-139e6fba70b5 |  | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
label | 42a54f78-dd74-5e88-b23e-bc427e2ee48a |  | note | Hold Point - In Process Inspection
label | afa39854-d253-5f67-99ca-1d118f6d2f6a |  | note | Records - Asbuilt records
label | 0e28baef-e3b5-5ae6-aa76-4c33a5411650 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
text | 4abdb529-5cdf-5b89-8c43-8e26d2a557ca |  | textbox | Comments:
text | 3ad6746b-9d7b-5957-aba6-1b9780c60945 |  | textbox | Position:
text | 28e07d81-9442-5203-ac63-9dbd3948e535 |  | textbox | Print Name:
text | 29c1bbe1-4e6a-5b7d-b03e-1c0bd97927b7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Final Inspection
text | aad2ef4c-df2f-5e83-a15a-014d83d11c82 |  | textbox | Comments:
text | 5f90d200-dfad-5450-8f5b-fc76b676254e |  | textbox | Position:
text | 96b4d151-5422-5f35-96d4-e8724d626816 |  | textbox | Print Name:
text | 34c833ef-eaff-5384-befd-3845f1d23bf0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - VRU Projects - AC Speed Table Rev 1 |  |  |  |  | Yes | ITP - VRU Projects - AC Speed Table Rev 1 | 73d3fd4d-6284-426e-9c84-e5e6f334532b
checkpoint-group |  |  | section | Precom
checkpoint-status |  |  | checkpoint | 1.1 - Permits & Services
label | f810c70d-383f-5c79-b4eb-ed507da167d2 |  | note | H
label | e01fa1bb-4740-50be-98bf-4405e7bcafdf |  | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | af4743af-c6e9-56ab-8e62-14cfd7f0d8f4 |  | note | Frequency - Prior to any construction commencing
label | 7931c006-c0f2-5d29-a35f-9474e8456576 |  | note | Inspection / Test Method - Document Review,PHOTOS
label | 1cec9040-bd14-5695-8ce1-8d217c65878f |  | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | c81e036b-01c5-55b3-8fb8-35eacadd3888 |  | note | Records - Permit attached or permit number noted.
label | 61582d24-42f0-5956-9c47-e6463ea9ca38 |  | note | FH Initials - Site Engineer
text | e1855dc7-490c-5d2b-a611-71c40cdd0bad |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Permits & Services
label | 715f2083-9c93-52a4-8578-45a9c786f121 |  | note | H
label | 9343482e-a27c-5b8e-9299-af61b8e8e8d8 |  | note | Detail - Locate and mark out all existing services
label | 82c15ecb-3eab-54c9-975e-a6d5c0a87509 |  | note | Frequency - Prior to any construction commencing
label | 875ac0c7-c1a5-5953-8f05-d15570f751a1 |  | note | Inspection / Test Method - photos
label | 7a518056-4059-5d3c-b72b-4573160dbf5b |  | note | Conformance Criteria - B4u dig procedure - follow utility protocols
label | b8ff000b-7d5d-58f7-8cbc-52c412a8709f |  | note | Records - B4u dig plans
label | 7b439283-9a05-5e66-be22-b47bd2405d2f |  | note | FH Initials - Site Engineer
text | 6bd5fce5-168e-5b75-8aff-ec393c308478 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Permits & Services
label | 8c14ef8a-d718-5b90-8127-32e3c4d4866e |  | note | H
label | a9292593-16ea-5ae9-a495-08a28099cff8 |  | note | Detail - Approved TMP
label | dc7cb66e-825f-5eaa-baac-1eaf51923d0b |  | note | Frequency - Prior to any construction commencing
label | 76e95adb-5755-58a7-8b47-d64c7b8c1c0a |  | note | Conformance Criteria - Approved TMP and WAP onsite before establishing traffic management
label | ff97444d-8aa6-5da2-ac05-4ba62ef18d9b |  | note | Records - TMP Plans
label | 3a334f0b-53f5-5a75-853b-291f89874d3d |  | note | FH Initials - Site Engineer
text | 2a6b1789-8b4b-596c-b8aa-a1408d64d1ee |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | 0cf46d1b-4925-5695-9bb5-b00259710eb9 |  | note | H
label | 41109273-9e95-5dc1-8838-f143c78646e6 |  | note | Detail - Sub-Contract and Supplier Agreements
label | e3932fd1-afee-5ebc-9ff5-b17c6eed4728 |  | note | Frequency - Prior to commencement.
label | d7908b34-42ba-503b-84e5-9f9343e92ff0 |  | note | Inspection / Test Method - Document Review
label | 7d97ec24-b128-583b-833b-cba52586598b |  | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | e1a01ff3-c151-5c47-9889-efc10d5aa92a |  | note | Records - Subcontract and Supplier Agreements
label | dcae9d4d-56a9-5ba9-b8d4-340fcb9bcd3c |  | note | FH Initials - Site Engineer
text | ee74770d-fee3-5286-bd9d-adb617f39b8a |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 99a81368-3d67-541f-8fa3-93280ce0d4d4 |  | note | H
label | 234eed94-df98-51d7-b43f-3d269491501d |  | note | Detail - Design is approved and Drawings are of the latest revision.
label | db6c7262-4551-5ba5-8624-68f54bbda07e |  | note | Frequency - Prior to commencement.
label | 898e62b4-ce2a-5295-9f83-715a1215005a |  | note | Inspection / Test Method - Document Review
label | 2dc639c7-f9a4-5f5a-9337-17a74a6d8f9c |  | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 2945188f-f1e9-527f-882f-526ae364977b |  | note | Records - Drawing Register.
label | f9f027df-ab6e-5905-bf46-067298a39dda |  | note | FH Initials - Site Engineer
text | c155c062-c9ae-58c4-a1a8-b3660f46afd7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Milling
checkpoint-status |  |  | checkpoint | 4 - Milling Depth (up to 75mm)
label | bab6a5f0-fbdb-5388-9417-80d06c3f7265 |  | note | M
label | 5bd39387-54a5-5870-b031-70956ca53d36 |  | note | Detail - AT Contract Specification 4414
label | 93df934c-62cc-5359-9ae5-4009368e2bbb |  | note | Frequency - Every site
label | d27956da-053f-557b-bb65-fc6bb5803281 |  | note | Inspection / Test Method - Review,photos
label | 9f81e6fb-7c97-5b17-836b-939a2aa083b2 |  | note | Conformance Criteria - Surface preparation shall be in accordance with NZTA Specification M10,The Contractor shall mill the existing surface to the minimum depth required to place the specified AC surfacing layer and provide a “key in” between the new and existing surfacing.The milling depth shall be carefully controlled to ensure that the finished milled depth and level within + / - 5mm of the specified levels or specified layer depths.
label | 15c74856-6864-5826-969b-794eb91102cc |  | note | Records - Milling Records
label | a829c803-ddde-5885-9878-86c46704af7e |  | note | FH Initials - Supervisor
text | 680b6623-54cd-5386-87d9-143e2b05384f |  | textbox | Date Completed:
checkpoint-group |  |  | section | Aggregate Quality and Lab Test
checkpoint-status |  |  | checkpoint | 4 - Temperature Limitation
label | 5fe81162-d0de-5472-914f-18a3fcbe72ce |  | note | W
label | 0e17273b-9a30-5816-8a96-e5759a2f8861 |  | note | Detail - Contract Spec /M10 Spec
label | fa6779c1-e9f0-5782-ad73-c2f4d4da202f |  | note | Frequency - Every site
label | aeb0652f-42a5-5e4d-a8d7-278f10e9414d |  | note | Inspection / Test Method - Review
label | 95b02ea1-8594-5931-bb7f-44a66b8ebc70 |  | note | Conformance Criteria - Asphalt not to be paved when foggy or raining, or placed on a wet surface or when Temperature is below 120 degree
label | c868cd98-11df-55ae-b14e-69185ee7d88c |  | note | Records - Asphalt QA
label | 98fd74a5-dd6e-5d13-a5e2-78e29ca2003a |  | note | FH Initials - Site Engineer
text | 4df05634-fe9d-58f7-970e-d194d121fcdb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Check Weather Reports
label | ff12a44d-762c-5bfd-aef6-184a940d13ca |  | note | W
label | 6c0fac29-29d2-5e71-a651-ccda63bec5dc |  | note | Detail - No fog, rain or wet surface. Base temp greater or equal to 7 degrees celsius
label | 989a9580-cd1a-57ea-bc98-fc43f24f08cc |  | note | Frequency - Weather call 2pm on the day
label | 9b537c69-3a39-52cf-9a6a-740fe37b769e |  | note | Inspection / Test Method - Visual
label | 158b46c5-a4ee-5d48-8177-76df831ad14a |  | note | Conformance Criteria - Forecast and thermometer
label | d9112deb-c138-5d49-a7c6-1a4ec51a371b |  | note | Records - Radar and Asphalt QA
label | b0b3d147-c445-5720-bd48-1b446057e7f6 |  | note | FH Initials - Site Engineer
text | 8922a259-8c80-51cb-86ed-c48e4a18429e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.1 - Pre-Seal Inspection
label | fa5c15ed-8f6e-5c07-b955-09b166d9e12e |  | note | H
label | 903dac4c-5b8e-5768-a3e1-7fe371c6d01e |  | note | Detail - Surface finish
label | ddd39124-2820-58aa-b08e-5e8aa1c02922 |  | note | Frequency - Continuous
label | f8ae0ac5-75f4-593a-b1f5-db2ac85624ff |  | note | Inspection / Test Method - Visual
label | b04ba2f6-a928-542a-b58a-649ddc69afac |  | note | Conformance Criteria - The surface must be clear of deleterious material and not choked with fines. The basecourse surface must present a stone mosaic surface with larger aggregates protruding and not appear damp
label | cb8a2f50-7003-5610-885b-0c93a641f18a |  | note | Records - Sealing QA
label | 387f7c4a-5918-511e-9ef9-79c7f95615f6 |  | note | FH Initials - Site Engineer
text | d49f77d8-2cd6-5315-9f47-0472b8edf8cc |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 - Pre-Seal Inspection
label | f956227b-c039-558d-baa4-d363f8fa783c |  | note | H
label | c63c135b-0da5-5dd5-b4ca-fb3ce8685744 |  | note | Detail - Basecourse Compaction
label | 22173927-6692-5782-b97a-0c93aabb6b95 |  | note | Frequency - Everysite
label | 8d24a420-0274-59c4-ad01-ac016f9f0797 |  | note | Inspection / Test Method - Testing
label | d506f472-9dd3-53b4-8030-6128bba69c2b |  | note | Conformance Criteria - Clegg CIV >25
label | 295fda93-f502-513b-b25c-ae9a1d27c1f6 |  | note | Records - Asphalt QA
label | 285fe3ee-e905-59d7-bb69-dedfd17fee34 |  | note | FH Initials - Site Engineer
text | 5690eeb3-b576-5a4f-8234-4b69df3f9bb1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Tack Coat
label | 70fd73d5-70f4-5fce-9e56-52135e808977 |  | note | M
label | a2a1f383-2eeb-5ea0-ac15-d7318e149623 |  | note | Detail - NZTA M10 Spec
label | 4c0cb561-2dd6-5dc1-adda-56601a5ef652 |  | note | Frequency - Ensure heavy coat of emulsion is applied before on each layer of Asphalt mix
label | 1f69e86a-34ab-5d08-a7a2-d9494fe15133 |  | note | Inspection / Test Method - Testing
label | 4d024a5e-1fe9-5445-a454-44bf081a5e8c |  | note | Conformance Criteria - minimum of 1 L/m2 is required on each spray run
label | 7a32a474-e345-59c7-9540-aa23d6e30a55 |  | note | Records - Asphalt QA
label | ff0c5328-d215-5bdf-8810-0051fb68a96c |  | note | FH Initials - Site Engineer
text | 3afa390c-5961-5e64-a579-d73d7c075f9d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8 - Construct AC20 Layer
label | 0da78d0d-a935-5529-94d9-c8b9181de200 |  | note | M
label | eecf9bea-e75a-5c08-865d-7afc25babe4b |  | note | Detail - NZTA M/10 NDM and Stringline
label | bcafed82-4555-5dfb-b918-9c067201a9f4 |  | note | Frequency - Each Run
label | f439dcdc-a827-55eb-b6e4-7ce179f30b0e |  | note | Inspection / Test Method - Testing & Visual
label | 8b6b133b-e047-56df-99f5-f00aeba65fd4 |  | note | Conformance Criteria - Construct 100mm AC20 layer. Design air voids 2-7% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
label | 9f4570af-a551-526b-8903-d479fb8fbef1 |  | note | Records - Asphalt QA
label | a1a55677-af5c-596a-a3c0-cf876045039d |  | note | FH Initials - Site Engineer
text | 977b964c-eaa6-59ea-a504-cc2eca9660b1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9 - Construct DG10 Layer
label | 078da525-2ebb-50f6-84e8-415f6a221a51 |  | note | M
label | 2d2a83d0-26cb-5687-a3d7-f45e81ac1676 |  | note | Detail - NZTA M/10 NDM and Stringline
label | cf735ece-d592-59a8-a833-1c3e2faf5c82 |  | note | Frequency - Each Run
label | 36fb9fc7-684c-5566-b64d-3676cca4f8ab |  | note | Inspection / Test Method - Testing & Visual
label | 70df0424-2a63-5d46-8b8a-db106f989fd7 |  | note | Conformance Criteria - Construct 50mm DG10 surface layer. - Design air voids 2-7% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
label | c67583ef-7023-5a84-b9bf-048ec0f65806 |  | note | Records - Asphalt QA
label | 86bed40f-fb31-57f7-9168-de6e3208e734 |  | note | FH Initials - Site Engineer
text | b393ce11-4fe7-55bb-80ff-345fe5f77070 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10 - Surface Finish
label | 88ee9c94-57cb-5cf4-ac3b-89bb22481229 |  | note | W
label | 203b7687-caf0-5ba5-b25e-b52169c05264 |  | note | Detail - TNZ P/9P
label | e99d5bf1-792d-512d-a835-c95dce141b72 |  | note | Frequency - Each Lot
label | b0490845-c6ab-5a43-9b8d-50b78c559dbb |  | note | Inspection / Test Method - Visual
label | 3db640fe-d615-5d84-bfd2-b065dbdac024 |  | note | Conformance Criteria - Inspection: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate
label | 76279bac-640d-57f4-90b3-84aef2816eee |  | note | Records - Photos
label | 701ae4c4-6027-5b43-a97c-a9fa49e6d7eb |  | note | FH Initials - Site Engineer
text | 31668c14-82a8-59b3-b629-79c2bc8a45ff |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 11 - Reinstatement of Linemarking
label | 3d089f52-7e7e-5756-b8ed-1055adab1937 |  | note | M
label | fa38301c-c63d-509b-a004-f78086b62735 |  | note | Detail - NZTA M7 approved (Class B or C as required for anticipated traffic level)
label | 6f181389-fa5f-5957-b886-7fa0358604db |  | note | Frequency - Every site
label | 85e85662-0339-559c-82ec-af27d28e26f1 |  | note | Inspection / Test Method - Visual
label | 2fdcfc60-c0b0-554f-bcc0-6ad51817fd91 |  | note | Conformance Criteria - *Carried out within 12 hours of each shift completed and as per the existing markings * Suitable Traffic Control to remain in place until pavement markings have been reinstated
label | 8d02b67f-b3c4-557f-9bd2-fad1e6c3e5e3 |  | note | Records - Photos
label | d177a20f-fb3d-5c66-ae8b-f70e46bda120 |  | note | FH Initials - Site Engineer
text | a534f0e4-d219-5496-b8a5-df64d116c089 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
text | 23cec3eb-e1aa-5c8b-84a8-ef9725a2a2dc |  | textbox | QA checked By Quality Manager:
text | 0a95429b-3091-5333-ab1e-258d0a3e0e4d |  | textbox | Accepted By Engineers Rep:
checklist-sectioned |  |  | checklist | Vulnerability Users Package 13 |  |  |  |  | Yes | Tui Rd - ITP - Vulnerability Users Package 13 | 75434e9c-041b-4cf4-894f-88f23485bffa
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 1 - Mountable Kerb
label | 94c29683-000e-5ad4-baa7-381d30a63125 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 38b77392-6d8a-5669-9bf2-4b2286d099e0 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | 38bf7a47-02cd-571c-b2a6-96bc01455ea9 |  | note | FREQUENCY - Every Site
label | bd4f7313-e3ba-54a7-937e-79978ceb53e2 |  | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
label | 03564ad4-0295-5594-b61a-de9d6fdde1f7 |  | note | Hold Point - In Process Inspection
label | 15c7dc6c-1098-5087-b503-10e99190ede4 |  | note | Records - FH concrete QA sheet, photos.
label | 2933e632-e6aa-59e5-84e5-4aef10b68ef5 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | ed391fcb-a866-56b7-93e4-e000060df3d3 |  | note | VERIFICATION ACTIVITY - Survey
label | f4c4c86c-7cc3-5ab4-a324-b94a772fcdb5 |  | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
label | c551bc75-c040-5570-a643-f43c3840cb2e |  | note | FREQUENCY - Prior to commencement.
label | d7226633-2898-5063-942b-4523db21108e |  | note | ACCEPTANCE CRITERIA - Survey
label | a2bea14c-64b0-5c5d-afec-f40c0341b7d7 |  | note | Hold Point - As per Construction Drawings
label | d21a34d8-ec14-5fdc-a8ab-a56ac3ad66e0 |  | note | Records - Survey Receipt.
label | c5f988be-dcfc-5446-9166-c6fc43bb40fd |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Concrete Island
label | 9482d2ec-5678-56e2-920b-afd3f4d1bb7a |  | note | VERIFICATION ACTIVITY - QA FORM
label | b2480276-0192-5a19-967b-cd97340fe315 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | c34c0bfb-2210-5a2f-9092-376ce938fab4 |  | note | FREQUENCY - Each Site
label | f1eb70e5-24bf-596e-ae0b-743f12a50d83 |  | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete
label | b5b98a1d-99b9-557f-a382-d196dc140631 |  | note | Hold Point - In Process Inspection
label | 77293155-9995-599f-8e5e-a46ed25637c4 |  | note | Records - Photos
label | 47f2e84e-b7b4-50d0-b769-66311c61bbe3 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3.1
label | 60d3b457-c9f0-5a03-ae39-a6bc1fbcff18 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 206df951-7b57-5537-9f9c-ab13e5f1dcaa |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0003
label | 9f1bf784-5774-5ee0-8430-6b9e88cc8aed |  | note | FREQUENCY - Each Site
label | 18e194e2-71c1-5f7b-95c4-366dcafd22de |  | note | ACCEPTANCE CRITERIA - Basecourse to be 150mm min thickness of GAP65
label | 1f76bb0d-f2c9-57ba-8903-7fe44c8ca105 |  | note | Hold Point - In Process Inspection
label | 26349673-7af0-5578-b5db-4a0b9e79bbda |  | note | Records - Photos
label | e97f7af5-1318-5c81-93a2-6cce5c5baf2e |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4 - Concrete Infill
label | c83ed801-4fcb-5608-a4f0-ba0c73e8ab78 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 43f75fb0-9a72-53d1-bafe-7de3bf90c7a9 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | e354e8c0-11b3-58fd-96a8-66da32c1f76b |  | note | FREQUENCY - Each Site
label | 4442734f-9a30-591b-bda3-317d02657947 |  | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 black oxide Cross Fall of 2% or max rise in centre of 180mm
label | df61d890-2f3d-5c13-821d-43d77c948fe5 |  | note | Hold Point - In Process Inspection
label | 9789fcd8-140c-50c9-b4ce-ef6eaf7e0eee |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | aff2f3c6-59f8-5b68-83af-950a1ab48c1f |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 5 - As built information
label | 99a6f738-ab02-5e58-ae8b-0f0d2245799a |  | note | VERIFICATION ACTIVITY - Drawings
label | 9a3f6f03-183b-5d15-b777-047cac93bee1 |  | note | FREQUENCY - Every Site
label | f3ff6937-51ac-5a91-8867-c745b903bdf8 |  | note | ACCEPTANCE CRITERIA - As built drawings
label | a07961c4-9679-55e0-a098-9d182e37301d |  | note | Hold Point - In Process Inspection
label | 96727ea3-028a-55a3-88dd-baa946fbd8f8 |  | note | Records - Asbuilt records
label | 102c410c-a20b-52c0-8caf-2361f9081784 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | 6 - RAMM DATA
label | 6adaa422-0fc6-5c48-a24f-a245fee2fcae |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | 05069357-aa84-5f7a-accd-74102c0b3ac1 |  | note | FREQUENCY - Every Site
label | e3eb42c7-a885-5d9f-9c76-2edd5cdb49a3 |  | note | ACCEPTANCE CRITERIA - RAMM SHEET
label | eb26769c-bd32-5db0-82c9-423f27719af5 |  | note | Hold Point - In Process Inspection
label | fdf070a9-7a57-54b4-906a-725a84d4c257 |  | note | Records - Asbuilt records
label | 6dd51130-6780-5762-8bac-1efbbe660b6e |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-sectioned |  |  | checklist | ITP - Enabling Works - Footpath, Kerb and channel | itp |  |  |  | Yes | SYS - Graeme Ave - ITP - Enabling Works - Footpath, Kerb and channel | 75776e96-50e6-481b-bbb8-9579de41a6da
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 Site Set out
label | ddbf4851-6782-4dc9-8ecf-7cb0af29712b |  | note | VERIFICATION ACTIVITY: Surveyor
label | 6fa8e851-a74d-4306-8ab9-d8969e9a99b3 |  | note | METHODS OR REFERENCE: Surveyor
label | f71bce22-cd4b-4766-93d7-261cc7365384 |  | note | FREQUENCY: Everysite
label | b7c44e7d-ead7-4fd3-af6b-ea7e6c9e462a |  | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | 3dc83e1d-9971-4985-bde4-f6415d4aeb7f |  | note | Hold Point: Mandatory HOLD POINT -
label | 10c4a63e-2fde-4ad5-bc99-6cd54ac5dbfa |  | note | Records: Onsite records/photos
label | 93e0a440-ec9e-4f87-b1d6-8ceee24dc4e8 |  | note | Onsite Responsibility: Site Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 Kerb & Channel
label | 3051cf60-9bf9-4f3d-b5e8-6ef645de3eb0 |  | note | VERIFICATION ACTIVITY: QA FORM
label | da2443c6-a486-4bae-b1e5-15ea16b99ad4 |  | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | 3906b831-e219-458b-b1cb-862957801317 |  | note | FREQUENCY: Everysite
label | 5d675dcf-167d-4688-a464-5b0af8371e00 |  | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. . Kerbing laid on 300mm min Gap 65 subbase in roads and 100mm GAP 40 in footpaths (CBR>5).Concrete 20mpa @28 Days
label | a6f84927-d4cb-4998-b797-908fe82e4687 |  | note | Hold Point: In process Inspection
label | b91f6fc9-78cf-47bd-a2d8-1cd50cbeb400 |  | note | Records: FH concrete QA sheet, photos. Concrete Plant Docket
label | 678c03ed-1a5b-4e95-b9a8-bd6fc0b8fce3 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3 Channel Level
label | 3aebc5bb-25f4-4e66-bd27-a34048026469 |  | note | VERIFICATION ACTIVITY: QA FORM
label | c4a60afa-39a2-4e17-9889-66180d561fe1 |  | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | 5b3a5b37-20e9-4e71-8152-de720bb14854 |  | note | FREQUENCY: Everysite
label | 207479d4-92d1-40f3-a869-254316bda6b8 |  | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | 94936304-4b47-4273-8836-f1f12aec761d |  | note | Hold Point: In process Inspection
label | c3a1770f-cd18-498b-a9e3-7c4a34440310 |  | note | Records: FH concrete QA sheet
label | 9fdd6928-3013-4ded-b2c4-c58df62ea723 |  | note | Onsite Responsibility: Site Engineer
checkpoint-group |  |  | section | Civil Works
checkpoint-status |  |  | checkpoint | 4 Concrete Footpaths
label | 010e1387-dadd-4216-9ff9-642d398a00c1 |  | note | VERIFICATION ACTIVITY: QA FORM
label | d8c2ea60-b237-4230-bb55-57e4401cb2f3 |  | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | 9248cc05-a8dd-41ba-8d35-8e9971453fd6 |  | note | FREQUENCY: 10m Intervals
label | 7d2c4c52-9d4f-40d7-83cf-1b1c7df5ebf9 |  | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3); Basecourse - 100mm min. thickness GAP40; Clegg CIV > 15; Surfacing - Concrete 100mm and 20 Mpa @ 28 days. 4kg/m3 blackoxide with broom finish
label | 74d6d778-6510-4711-8374-87e59e9ce6a6 |  | note | Hold Point: In process Inspection
label | 28a9afce-e62c-452b-9d5b-5fb830043984 |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | b0b71762-6ef5-4c66-8dfc-b0dea9026224 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 5 Concrete Pram Crossings (PX)
label | 16dcf99c-0395-40a6-8a84-2afe711c3c63 |  | note | VERIFICATION ACTIVITY: QA FORM
label | 057e0743-6dc6-414d-8f21-5692bd316bfd |  | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006
label | 623f714f-8be4-40bb-99ae-ce74b691c59e |  | note | FREQUENCY: Each PX
label | 33c0504f-d69c-408c-940f-3debc779ffeb |  | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3); Basecourse - 100mm min. GAP40 thickness; Clegg CIV > 15; Surfacing - Concrete 150mm and 20 Mpa @ 28 days. 4kg/m3 blackoxide with broom finish
label | ac4f4091-574e-4b28-98ae-0a5ca90f8e7e |  | note | Hold Point: In process Inspection
label | c1eb0736-e609-4916-aea2-9d954b899f09 |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 58e717d9-deaf-4455-a1d1-03552c77b92c |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 5.1 Concrete Pram Crossings (PX)
label | 181bda09-b388-4b3f-b64d-a9abca2aba43 |  | note | VERIFICATION ACTIVITY: QA FORM
label | 2b5ef084-00c8-493c-8b0c-d2cbe4cbe316 |  | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006
label | 0d0d1deb-b9a7-4f3e-9c27-647f2f0150e3 |  | note | FREQUENCY: Each PX
label | d6754625-c053-412d-a990-ce7bb9d73ca6 |  | note | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 100mm concrete slab underneath
label | 317e18fd-d229-47da-8cf1-06f9bbb92ab9 |  | note | Hold Point: In process Inspection, Measurement
label | 3d1f43c8-af21-450d-a702-16363ef8d8d2 |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 13a830d4-1d9d-46af-ab44-4abcc86dd002 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6 Grass Berms
label | 5ed909d1-6421-432d-97fa-e40f8b197e30 |  | note | VERIFICATION ACTIVITY: Visual
label | eec16ba6-01f4-448a-94eb-d70671cada8e |  | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
label | 07972f8d-5755-49ac-a778-01ba62350c97 |  | note | FREQUENCY: 10m Intervals
label | 7b6e382e-bbf4-4ed6-a9a8-95f06a8b60d3 |  | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | 426ff477-f0d3-46d8-9178-9c9fc8169851 |  | note | Hold Point: In process Inspection
label | 5881e416-4a14-4d95-9638-5b26da8aa368 |  | note | Records: Photos
label | f1ba3078-6532-4e18-a9eb-0eb84d299407 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 7 Tactiles
label | 6e9c1805-8995-4c17-a6ab-a5ab7c859305 |  | note | VERIFICATION ACTIVITY: Visual
label | dd20db48-d7e8-4680-b441-aa0f0f59ea0c |  | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 9d023a4a-9b72-445b-b87e-0c6beaed1220 |  | note | FREQUENCY: Everysite
label | 5b13c535-81f6-4142-ba49-540e7d8cc331 |  | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | 5e3e9c5e-12b8-40f1-accf-ce7e0ff09409 |  | note | Hold Point: In process Inspection
label | 096eba49-1b3e-4620-9d1f-0e8fe29577a7 |  | note | Records: Photos
label | 23844e89-d32c-4fb5-81cf-a13f3e81659b |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 7.1 Tactiles
label | 5cf1303e-4296-4491-9e88-1e2625f0a4e3 |  | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 7022b0d9-bdb1-4cc2-aa96-4ca80f7b6813 |  | note | FREQUENCY: Everysite
label | 0c27c4ca-bf10-4b3a-a3ea-aa4eab1ce7a0 |  | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | 18d525e5-8b26-4d23-86a1-cea15270c694 |  | note | Hold Point: In process Inspection
label | b322d525-0c8e-4eb9-983b-8fcfe44ff606 |  | note | Records: Photos
label | 6a3a35dd-4c51-4802-bd72-798d0626da08 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 7.2 Tactiles
label | 58f5320f-c67b-44e3-aa22-30f1cb154f23 |  | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 9601367f-19d8-4e96-a8c6-64c06f940bdf |  | note | FREQUENCY: Everysite
label | 0d5443f5-fbca-4009-85af-8adce1a4d635 |  | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | 537cba37-c0c0-4533-91da-16f836f683d5 |  | note | Hold Point: In process Inspection
label | 21226592-d23c-4a1b-8ab1-0591d16790db |  | note | Records: Photos
label | 3249939c-3092-4e0e-b444-b8845885a66a |  | note | Onsite Responsibility: Site Engineer
checkpoint-group |  |  | section | RAMM Data
checkpoint-status |  |  | checkpoint | 8 As built information
label | fc411406-d276-49dd-ad73-9e2bb9dfd3b0 |  | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | 369deb07-0a8f-499b-8072-c41c501f2057 |  | note | FREQUENCY: Every Site
label | b820da13-b4e7-4679-972d-71e2cbb739b1 |  | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | d7f1a98e-1e0e-432c-a835-e371dd9ac6a5 |  | note | Hold Point: In Process Inspection
label | 529fc5bb-0c9f-490d-a82a-5b1da48159d4 |  | note | Records: Asbuilt records
label | 1b327156-63b5-41b4-9b22-3035f55cc755 |  | note | Onsite Responsibility: Supervisor and Engineer
checklist-flat |  |  | checklist | ITP - St Lukes Road/Morningside Drive intersection - Ducting and Traffic Signals |  |  |  |  | Yes | ITP - St Lukes Road/Morningside Drive intersection - Ducting and Traffic Signals | 7bb84262-77d7-4f23-aed7-583aede981cb
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 0dbda8ec-8192-5215-913d-b2dea554d575 |  | note | H
label | b385fa9a-c611-5c5c-b79c-fdc0ae82e288 |  | note | Detail - Obtain Permits
label | 68690731-2a9d-583c-9058-9ecd4043bb5e |  | note | Frequency - As required
label | 78b2f275-1b97-5882-a67c-b112e9494344 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 891fc5e6-1853-5976-827c-a7bd3eff8419 |  | note | Conformance Criteria - Authorisation to work, dig permit and service provider permits
label | 6a375b8d-b99e-567f-89e2-6a00bfd03e31 |  | note | Records - This ITP signed
label | fb4bec80-553f-5a97-a895-c702a37be096 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Design
label | 02a5dd1e-c5f8-5789-8306-c77147ec4825 |  | note | H
label | aa82a5ad-8d52-5a09-80ca-b138bbcfd62e |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | 80293d04-49eb-503b-a9c8-abfec31e792c |  | note | Frequency - Prior to commencement
label | 3f7670a4-666f-51fe-bc0b-0b92bbd68de2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | d5d38af4-0a72-5ac4-b567-354d4a0e3057 |  | note | Records - Check Drawing Register
label | 1c7ab305-0bbd-564f-9fa5-7c8eaaae2fa7 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Survey Setout
label | 99d325ec-88b7-5599-b676-e622bec21978 |  | note | H
label | 94d5caf0-824f-5fa9-9051-9ca0ef722246 |  | note | Detail - Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
label | 2abb7ac6-5030-545e-a04e-5877e6cf2bb0 |  | note | Frequency - Prior to commencement
label | b7d825d1-4b7a-5982-9db8-84c5034c3bc6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 02ca3c88-a356-5606-bd3c-f7f36a5185c2 |  | note | Conformance Criteria - Consistency with Drawings and Specifiactions
label | 20355a79-bbfc-5cb7-a2e8-96ab3ca9a3cc |  | note | Records - Survey Records
label | 2924250c-646e-5ac3-aae8-4e7bee3c51db |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1 -
label | 20325858-977a-501e-bdb4-4cd7c869b4b6 |  | note | H
label | 695870cb-c805-5368-bc5a-dd1491b1682e |  | note | Detail - Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
label | 24fcabb1-a922-53ac-b5dd-9bcf841e6d82 |  | note | Frequency - Prior to commencement
label | c326c170-0753-5a5c-9734-2e794f23a912 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 57fda63f-1953-5796-b9df-1e45f38c2c16 |  | note | Conformance Criteria - Consistency with Drawings and Specifiactions
label | 4b818b60-434a-5226-8fb2-2e655626c9e3 |  | note | Records - Photos / Engineers approval documentation
label | c871b1ee-344d-5d8e-8e62-9ce755478635 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Locate existing services by hand digging/ hydrovac
label | 0a928b5d-3461-5110-943d-293395412c5d |  | note | W
label | faab604f-bb8c-5459-93fc-1a78b15e8efe |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
label | 8b1e7543-bd00-59f5-add9-a7f307322aee |  | note | Frequency - Prior to Installation
label | 84510f17-f227-5c84-8085-2ae932111367 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | 9c0a1073-36b1-5418-9b8d-9f899c6caad6 |  | note | Conformance Criteria - All conflicts have been located and survey as built recorded
label | 10955384-6f2b-5535-9628-09b4392bee73 |  | note | Records - Digging/Excavating Control Checklist
label | 18618755-ee21-5fb0-9d15-775d5ca2535b |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Material Compliance
label | 53708f7d-4c93-526c-bd4b-e78dd708ad4a |  | note | H
label | acbd41b5-92b3-5b25-b911-4f5b6d7f02dd |  | note | Detail - Ensure duct pipes and poles are as per drawings and specification
label | 91defa86-d48c-5068-bd74-03d6956850d6 |  | note | Frequency - Upon delivery to site
label | 73530c3a-1b22-59c0-afca-d04eef59c057 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials
label | d5290b6c-0fde-5bb6-b931-9a88ba743b25 |  | note | Records - Delivery Docket
label | d00ed5ee-5442-59fc-a8d7-16e61f8f78da |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.1 -
label | 441083b6-5402-59f4-9a53-106b2a1bbbd2 |  | note | H
label | e9447a42-5991-5d6d-8008-2bcfc3395bef |  | note | Detail - Ensure all concrete used is 20MPa mix
label | e2726646-bafb-5014-a763-8dba6d96b7fe |  | note | Frequency - Upon delivery to site
label | 81bcfe7a-3622-5812-beaa-b1134903bfb6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials
label | 77c52bc8-229e-5ef0-8f59-7a5127b261ed |  | note | Records - Delivery Docket
label | 4075b066-21de-5167-b8a7-483ff51e4d31 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Trenching
label | 97233f15-208a-5f50-86a9-6f76d73dc11f |  | note | H
label | 6e3e5e2b-515b-5eb9-8865-86b11a9c42cd |  | note | Detail - Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm (900mm cover when under road crossing)
label | b0a1b664-1148-5f04-ac37-4d5851c033f9 |  | note | Frequency - 10m Intervals
label | dffd4d4a-63ae-5b43-ba2a-a97f5eef3fe8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 10498978-e958-545a-9d14-beb51fe2bb6b |  | note | Conformance Criteria - Consistency with Drawings and Specifiactions
label | c5df66b6-2f3e-5594-822d-848ecb1acaf7 |  | note | Records - Photos
label | 6e48c9b9-d33a-5ab8-8560-aa91a77ba4a8 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.1 -
label | 0ecd6be6-f6bf-51c0-9dc8-56934f33c95e |  | note | H
label | 8c0324ad-468f-5c23-adab-314f8c057828 |  | note | Detail - Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
label | 742c37d1-786f-5a8e-bbb2-4e3ffde4a6e5 |  | note | Frequency - 10m Intervals
label | edc45adb-b844-5732-82e6-c62b3247e0e0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | e3556d84-cbdc-5a9e-9f02-83dec1d281d5 |  | note | Conformance Criteria - Ensure trench alignment and levels match the design drawings
label | 2aa853bc-4c50-5a53-870a-b3240425f69e |  | note | Records - Dipsheet & Photos
label | 9dfbb667-d2cd-5327-8ae7-7fa08f14af8f |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Duct Installation
label | c788c966-6897-522c-8575-7b1921841d07 |  | note | W
label | d9480362-043e-5a8a-8457-9deb67bd2da8 |  | note | Detail - Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
label | 16c5f36e-c8fa-56cd-b456-adb6c934161b |  | note | Frequency - Prior to Installation
label | 4bcc660d-a596-590a-ac56-d8edda325a9f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 42436d63-791b-59da-aea3-6380ebd338b2 |  | note | Conformance Criteria - Consistency with Drawings and Specifiactions
label | d1a03167-e434-537f-91e0-e8c9f9bdc4c3 |  | note | Records - Photos
label | 6e6ba1e1-6001-555b-95b3-5a6e9e91ba7b |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 7.1 -
label | 1fa27fe2-7669-50c5-ad73-4ce9595b7d98 |  | note | H
label | 8455aec0-a705-50f3-a7f6-5f43783b29eb |  | note | Detail - Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
label | 037b6608-45b9-5844-8749-d97a9c387da6 |  | note | Frequency - 10m Intervals
label | 26678e06-1e3e-50ba-9147-8b27688b0f58 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | e136b7f4-b080-55bb-8f62-d8b56fe1b138 |  | note | Conformance Criteria - Consistency with Drawings and Specifiactions
label | 1db0b8a1-3ab5-575c-9eb0-7ff6cdf4b5cc |  | note | Records - Photos
label | d00afd94-d63f-5482-bc47-bea95e19d1f5 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 -
label | 6ad6f9c6-f2dd-5c2e-98ac-75e20eafc936 |  | note | H
label | 01afd926-d1be-5fdc-84c1-3caf89939a98 |  | note | Detail - Asbuilt Survey
label | cad4082c-81f4-56ec-81ea-8b2a4ef8b50f |  | note | Frequency - 20m Intervals
label | c63976c1-f2f8-5e7e-8ff7-b500e89c9a0b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 9ea0b595-c52c-521f-8c3e-1a1bb1ce9c9e |  | note | Conformance Criteria - Consistency with Drawings and Specifiactions
label | 2e2960ed-5a66-5656-b5f9-8de97971e125 |  | note | Records - Survey Records
label | 189b5593-1207-5ceb-93d3-88063dafdcb0 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Bedding
label | c5c740b5-e620-5234-bfa8-28707170c705 |  | note | H
label | be263c04-482e-5896-b91d-fc9122ae790e |  | note | Detail - Lay min. 150mm gap20 or finer for bedding and haunching
label | 045bc1fa-3977-530f-9225-662f1b7ba8d8 |  | note | Frequency - 10m Intervals
label | 66bc4061-758b-5391-9ceb-d98da839ea9f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | f88fc1a8-bc4c-5865-bd21-c5c461111724 |  | note | Conformance Criteria - Consistency with Drawings and Specifiactions
label | cf11a8d2-c31b-57d6-b8ba-dec15bd2cf5e |  | note | Records - Photos
label | d189f4ac-6313-5f2b-89ef-ff464856595b |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Warning Tape
label | 28403db6-f2f5-5e3d-86a3-035fdb55ef13 |  | note | H
label | 4326c4df-9f80-5971-8dac-12a1a8d2b2f2 |  | note | Detail - Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
label | fc432140-7c43-5604-a166-746b565b28a1 |  | note | Frequency - 10m Intervals
label | 0426047f-bbe0-513c-a339-c8e110ab1a99 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 6020c0e9-4ad8-5bf6-9544-279b9db6038a |  | note | Conformance Criteria - Consistency with Drawings and Specifiactions
label | 4b0ef066-a9d5-5c4c-ab8e-2bda22065ddd |  | note | Records - Photos
label | 7b0bc941-5255-5bda-ac20-efda5affa614 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Traffic signal pole erection
label | ac6fc405-2865-5d5d-8182-1671017bfb39 |  | note | H
label | 3b4ad816-7431-54d2-a5b3-92b3e4d85762 |  | note | Detail - Ensure Design engineer as inspected pole locations prior to proceeding
label | 5ff7ec55-bc40-568f-b7a9-d0f37ac8c2ee |  | note | Frequency - Per pole
label | c38cd927-0563-5bf8-b415-944188af6241 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 6a45c387-1ca8-588e-ad36-fa213d1abb07 |  | note | Conformance Criteria - Sign off by design engineer
label | 60283c80-0612-5945-be7d-7ffabec025f3 |  | note | Records - Engineer sign off
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1 -
label | 9f96e30f-7133-5c2a-997f-27e77de316c2 |  | note | H
label | e3cfc64c-b759-556a-ad8a-e8ce7674f335 |  | note | Detail - Ensure Pot hole is as per design with required depths and widths
label | 7a35eb44-0d81-541d-be9c-a6630cd77f4a |  | note | Frequency - Per pole
label | 1d0bfd7b-b75b-5ca4-8f65-80ad0530b7ba |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 5db37a51-b02d-5d6c-b051-671f6836dbf0 |  | note | Conformance Criteria - Consistency with Drawings and Specifiactions
label | 433837d3-8c12-5287-9cb8-e93b0b7ac5d9 |  | note | Records - Dipsheet & Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.2 -
label | 316e6476-a885-5aa7-bab9-5076466ca6e2 |  | note | H
label | c49c61a7-3640-5d20-ba2e-0d02aa657d59 |  | note | Detail - Ensure Poles are plumb and within design tolerances
label | e3d3f04b-c3a2-51c2-9f8e-2975e197a6bf |  | note | Frequency - Per pole
label | fd72661f-b5eb-57d6-9a8f-70a05e113a22 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 57901caf-e71a-508b-a57a-9a403798ba6a |  | note | Conformance Criteria - Consistency with Drawings and Specifiactions
label | 1b0f928e-1dd0-5220-b295-91b2db20bb5f |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - As-builts & C&I Diagram
label | 45f04c27-e8fd-5a8e-a64f-26ff8f5f7972 |  | note | H
label | 2dc01e22-3aa3-5c99-a5ba-6fc1960192e9 |  | note | Detail - As-built as per ATOC requirements
label | 8bc56203-117e-511a-a888-3b5e975eaa4f |  | note | Frequency - At the completion of the Lot of work
label | 8c27b4a1-0b65-5169-845b-781fb167bf5c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | abbd5240-3101-5870-bae7-95897eebc7a5 |  | note | Conformance Criteria - As-built as per ATOC requirements
label | 19d8f7d3-36a0-5e7d-a92a-5f29bf052e6d |  | note | Records - Asbuilt Drawing
label | c66c393e-e81c-5de1-b3b2-fecca0254e5d |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
text | 9fac1df9-b2f9-5f4f-b5a4-1f98694af7ab |  | textbox | Comments:
text | 9421a839-f1b0-54be-bc74-97d37fa7c410 |  | textbox | Drawings used for Construction incl. Rev numbers:
text | 96abca97-e999-5cd1-8923-a7820740b09a |  | textbox | Reference Documentation (Notices/OFIs etc):
checkpoint-status |  |  | checkpoint | QA Compiled By :
text | 5d3a407e-bc23-5b3e-a620-b53a7af6986d |  | textbox | Name:
text | 389ef883-2d6d-5325-88e9-20e2aa49f3af |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | QA checked By Project manager
text | 4837ea63-d4d1-5053-942b-ba1f12497949 |  | textbox | Name:
text | b029d27d-d608-5cdc-a6bd-c428e0b637d7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | QA checked By Contract Manager:
text | b803dfe0-f7be-552f-936d-623ce882784f |  | textbox | Name:
text | 57a56fc1-ad6b-57d5-8cf5-b31cea92f292 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Accepted By Design/AT Engineer:
text | e8b948ab-81ab-5927-b527-831cb17e8b5f |  | textbox | Name:
text | 4bf0dfa5-7030-5f97-b0ec-109ae6a6aae6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP - Stormwater Drainage (Atkinson Ave) |  |  |  |  | Yes | Atkinson Ave - ITP - Stormwater Drainage | 7e146bcd-0c2e-4f2d-8faa-99ff1cce41dc
checkpoint-group |  |  | section | Stormwater Drainage
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | 54a8b32a-a081-5df2-acc8-ae705735776d |  | note | H
label | cb11189f-87eb-52a7-a742-56fb0b0e6c3d |  | note | Detail: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | e179bcb7-9380-5ac7-92df-59ccd65bc847 |  | note | Frequency: Prior to any construction commencing
label | 2720ca53-6ba2-5aa6-9680-63babc04ba1f |  | note | Inspection / Test Method: Document Review
label | 793ebc32-34f4-51f2-8e9f-877457565c63 |  | note | Conformance Criteria: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | aa57d955-8f54-5b0a-abc8-efb8cf8f4747 |  | note | Records: Permit attached or permit number noted.
text | 6c7f5c6e-a285-5019-a759-4d87d1027355 |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1 - Permits & Services
label | 32d1352e-9e8a-501c-8d4f-9e62835b9d2a |  | note | H
label | dce47360-e661-53da-8054-32537684441e |  | note | Detail: Locate and mark out all existing services
label | 72e066a3-49a9-53b6-b687-f7b7a6e4ae6a |  | note | Frequency: Prior to any construction commencing
label | 556736ed-b010-597e-9018-58ddeeafa267 |  | note | Inspection / Test Method:
label | 67903b7b-97a5-5efb-bbfc-1feaf71eb4b2 |  | note | Conformance Criteria: B4u dig procedure - follow utility protocols
label | 9f78abde-4c5c-5d29-a631-6d89e8180da9 |  | note | Records: B4u dig plans & GPR report attached
text | e5a598a3-9a9c-578e-aceb-f30f5d863f67 |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | 89f66310-ff3f-56f1-9804-fd2d001aae13 |  | note | H
label | 59211db5-188f-5742-824e-4dbef1096fc4 |  | note | Detail: Sub-Contract and Supplier Agreements
label | 435274b0-9a98-513f-b6d9-77f57d357352 |  | note | Frequency: Prior to commencement.
label | 2ae07466-e0de-582b-92c4-4b549e9d5c86 |  | note | Inspection / Test Method: Document Review
label | 2ad7695a-637a-559c-8697-236a7ab8eeca |  | note | Conformance Criteria: Sub-Contract and Supplier Agreements to be agreed and signed
label | 91f229a9-c755-5933-b850-89b8e8eddbab |  | note | Records: Subcontract and Supplier Agreements
text | 4c989ba1-6169-5aa6-8749-d0bdc4d46d93 |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | ded785e6-f901-5e3b-bf55-5c815d321ca0 |  | note | H
label | 1e5309aa-73c2-5ded-904c-8ccf23657d74 |  | note | Detail: Design is approved and Drawings are of the latest revision.
label | a3b1e17d-360e-5f68-ab5b-a48f08334b8c |  | note | Frequency: Prior to commencement.
label | ee3e26f7-2847-55fd-8cff-91904cce0f3a |  | note | Inspection / Test Method: Document Review
label | 31bb8f07-b542-58c2-895d-db959f758cd9 |  | note | Conformance Criteria: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | bae788a2-3cb5-549f-8439-51576b235bcc |  | note | Records: Drawing Register.
text | ac21f9f3-2088-586f-b534-62ead8893116 |  | textbox | FH Initials - Site Engineer:
text | 2d8f346e-b80d-5c5d-806b-f7ffbf330b4b |  | textbox | Design Engineer Initials:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4 - Survey Setout
label | 9b0a5f26-480d-5447-92ac-fc59af5a12a1 |  | note | H
label | df6374d1-3ca0-5d7b-8554-8508e0528890 |  | note | Detail: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | a22bb920-5a20-5120-992e-414a10df2184 |  | note | Frequency: Prior to commencement.
label | 85ce5f45-de35-5d6f-bcb4-978f4bf4bc78 |  | note | Inspection / Test Method: Survey
label | fa8d1e34-dcf5-5b1a-9488-6c106b7cd247 |  | note | Conformance Criteria: As per GHD Drawings & Setout files
label | b96af3a9-9ada-5f83-b183-7082558d0531 |  | note | Records: Survey Receipt.
text | 9aac3cd7-de91-5894-83e6-e1db3ea9a853 |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5 - Pipe and Manhole Material Compliance
label | 2d8362b2-4dda-5b68-ac07-5ea1022e7fb1 |  | note | H
label | b67d4bf6-c5e4-59f2-b588-07e3e333e066 |  | note | Detail: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | 15faa754-9ac8-50cb-9f15-3ffe2abb8155 |  | note | Frequency: Prior to commencement.
label | b46630c6-9a87-50a6-aa27-43eb090b5fb7 |  | note | Inspection / Test Method: Document Review, Visual Inspection
label | 34088e69-117d-5a04-a2a5-1ccf9acb3987 |  | note | Conformance Criteria: Pipe shall be
label | 484942a4-9b9f-5d1c-a0f8-46a43de46837 |  | note | Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | 365b710d-d314-5861-8f18-ee6afb4fb1e2 |  | note | Records: Manufacturers Data Sheets, Delivery Dockets
text | 1b994bca-41d8-5056-b94a-9c5aec899ee8 |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | f44ee40e-2d71-5841-8382-dff171350909 |  | note | H
label | 83cc5819-c3f5-5fa4-9b73-18bfa3e0746b |  | note | Detail: Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | a59ac2fe-0bf0-5ab8-b2b9-9b12aad2f7eb |  | note | Frequency: Prior to commencement.
label | 4204c881-b9ac-5bf6-8c5c-9fa0d265c093 |  | note | Inspection / Test Method: Potholing / Survey
label | 867b9177-fb8d-5a31-aa5b-e40c73992123 |  | note | Conformance Criteria: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | 256a835d-f3b1-5b01-8192-3a20ddc4d4fc |  | note | Records: As-built Drawings. Doc. Review
text | 7616d9b1-2646-5180-9ab2-f69b3d25401b |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | c5016120-35e3-5e5e-b8d5-a5c887260488 |  | note | H
label | 9d123b79-4ebb-5493-92ed-3f91b5995206 |  | note | Detail: Excavation methodology
label | 8924745b-6cf3-5bc5-a7e5-26f1363a0cae |  | note | Frequency: Daily
label | e842cb53-3070-5554-a8cb-5ee4d5bdd907 |  | note | Inspection / Test Method: Prestart review
label | f1b1ac81-dbcb-57c1-bee7-1383b8204077 |  | note | Conformance Criteria: The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | c463a754-9d02-5206-ad20-49c051514451 |  | note | Records: Prestart RCP
text | 6db03f94-c94f-55da-a726-1703b67268a7 |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.1 - Trenching & Excavation
label | 8daa23bf-5d66-5d52-82b1-3d889b296e72 |  | note | H
label | fa497f14-8a7b-5fba-82d8-80667fc1f7f6 |  | note | Detail: Trench Profile - Width
label | 7f0789f7-f2db-503e-824c-417906bc114e |  | note | Frequency: Daily / as trenching takes place. Different depth methodology
label | 0ac317fd-4373-54fa-9e82-55039c601cde |  | note | Inspection / Test Method: Visual Inspection, Excavation methodology
label | 67a1462d-0760-5a7e-9119-972ca4812a60 |  | note | Conformance Criteria: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | 02c86a70-f5a5-5eac-9937-d287b9c7b7dd |  | note | Records: Construction Photos
text | 17f60569-a1ac-5e81-884a-3e70865f5dfa |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.2 - Trenching & Excavation
label | bbe58c03-9c6e-5442-803e-e79fdcc39f0a |  | note | H
label | 0a11977d-20a1-58a7-a9b4-c7e7c020106a |  | note | Detail: Trench Profile - Depth
label | 943699d8-e7e5-5b3f-b3da-49f4e0194eb8 |  | note | Frequency: Daily / as trenching takes place.
label | b60c0841-48c7-5e0c-a9a6-acc3c3250e49 |  | note | Inspection / Test Method: Visual Inspection, Measurement
label | c6772970-5a49-5d24-aefd-dbe37340df1b |  | note | Conformance Criteria: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | b1a192a6-5bb6-5e8b-b43f-ecd3c3408919 |  | note | Records: FH Drainage Line Record / Construction Photos
text | fdd1c438-35aa-5c4c-81a2-449e48d4b1c8 |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | a22af2cd-a2e9-543a-80b1-03e2ac3c507e |  | note | H
label | 353f8791-76c8-55c7-b644-ed7d2d3f6df8 |  | note | Detail: Placing and compaction of Bedding Material.
label | 6e2f4b7c-6ee6-5805-b384-f6fc616986e6 |  | note | Frequency: Inspected continuously during placing and compaction of Bedding Material.
label | 180f5009-96a1-5c41-8f19-7b164220681f |  | note | Inspection / Test Method: Visual Inspection
label | cff6e18b-b58a-508e-a3fe-c07b9727eb98 |  | note | Conformance Criteria: Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | e864d4da-99c1-5bed-bb77-5c2609721c2a |  | note | Records: FH Drainage Line Record / Construction Photos
text | d5913f1f-d80a-5200-9608-558fb31bc63f |  | textbox | FH Initials - Site Engineer:
checkpoint-status |  |  | checkpoint | 9 - Pipe Position Tolerance
label | 89318e59-41a7-5f4e-83c4-10ed1eb1aefe |  | note | H
label | d15950e4-c671-5adb-b308-0bc844c37a33 |  | note | Detail:
label | be340e94-946e-57b6-869c-20aac1ebef77 |  | note | Frequency: At any point of pipe
label | 92ef161e-7a75-59a8-8aae-6ebfc066fa21 |  | note | Inspection / Test Method:
label | 870b6c26-c968-5a8d-87a6-7da7f45880ab |  | note | Conformance Criteria: Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
label | b84746b8-557e-5ae3-93ed-9e83d37f1d5d |  | note | Records: FH Drainage Line Record, Survey Data.
text | 585b18f9-c71b-5d91-b6b1-f488c19a0a8d |  | textbox | FH Initials - Site Engineer:
checkpoint-status |  |  | checkpoint | 10 - Trench Backfill - Placing & Compacting
label | 76fd93c5-53f4-5518-9cfa-c780bf246ac6 |  | note | H
label | 55d5fcde-3cd5-5e66-b62d-aa2147e1a137 |  | note | Detail: Placing and compacting of Trench Backfill Material
label | 658980b5-7acf-57f4-b7da-6d40f1feab4d |  | note | Frequency: Throughout Trench Backfilling operation.
label | 1dcf8d66-25bf-5cc0-b63b-8775253391ad |  | note | Inspection / Test Method: Visual Inspection
label | 7fa2ef7e-f73a-50fd-b9e5-1efd6eac22de |  | note | Conformance Criteria: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | 5f964fb1-53bd-5912-b8a4-47ba07ec339c |  | note | Records: Construction Photos
text | dabc42bc-b195-5c16-936e-accba4cf2aed |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Subsoil Construction
checkpoint-status |  |  | checkpoint | 11 - As-Built Drawings
label | 85ba14c0-393b-513f-9774-4aaaa6e4f138 |  | note | H
label | 0477eda2-2e6d-5a12-b4cd-b94862dcbf54 |  | note | Detail: Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
label | 9393a182-6b79-5c0f-b5a6-4466c058b531 |  | note | Frequency: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | b661066f-02fd-565a-bb9a-5a957a1de29e |  | note | Inspection / Test Method: Drawings / Visual Inspection
label | 0d2cb6ad-5646-51e9-bcba-1ccf499f53b9 |  | note | Conformance Criteria: As Built and GIS Data
label | c05690f3-491d-57c7-8bee-1e2021cf8815 |  | note | Records: Redline As-Built Drawings, scanned as .pdf files.
text | 702c9bf4-3cab-5195-a819-b3f3e8e5ea2e |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checklist-sectioned |  |  | checklist | Enabling Works - Footpath, Kerb and Channel |  |  |  |  | Yes | Lincoln Rd - ITP - Enabling Works - Footpath, Kerb and Channel | 7e5e2b31-8cdd-4039-9ad9-967092ba3af4
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | 2e35f882-56e7-54d1-9283-1563f8f1a17e |  | note | VERIFICATION ACTIVITY - Surveyor
label | 475c69c9-d1e7-531f-91f7-89ae2ce9c946 |  | note | METHODS OR REFERENCE - Surveyor
label | 774cde07-75d5-5655-839a-0abe5b16602e |  | note | FREQUENCY - Every site
label | 89a654c9-b2bf-5ffc-b1be-754d3a233c06 |  | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | 0a50718b-be03-569c-967f-0f6510111d68 |  | note | Hold Point - Mandatory HOLD POINT -
label | 72d885d4-a3bc-5904-8af7-f3e927a9d6f2 |  | note | Records - Onsite records/photos
label | fdc3dff4-ac01-5d41-9a50-961d4f2637dd |  | note | Onsite Responsibility - Site Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Kerb & Channel
label | f54ce2cc-8018-58b7-8832-2894068104b6 |  | note | VERIFICATION ACTIVITY - QA FORM
label | dbda9fbf-c76a-57d6-a542-f523b8677ce0 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | a71a8742-f013-5247-aa8f-491163de8a7c |  | note | FREQUENCY - Every site
label | fdf10c90-4d18-5423-bd55-c18f850a5767 |  | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
label | e76866bb-4bd3-50d8-95c1-a717aed8c0b1 |  | note | Hold Point - In process Inspection
label | 5f1a26a0-adcf-517b-86ec-4b29c7ab1bf7 |  | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
label | fce78c38-e944-579b-8c15-a2ea3d02f1f2 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Channel Level
label | 7bf3b462-9e64-5978-a921-85e50f5d32e7 |  | note | VERIFICATION ACTIVITY - QA FORM
label | d40016a3-7248-5713-bbb8-0cc4cfd8f441 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | 76269370-a26d-5295-b50d-2800bdcb860e |  | note | FREQUENCY - Every site
label | 30f23f60-7e85-5ed4-8e25-e169f0a12ed1 |  | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | 2bf76ca8-0280-546f-94e7-d654e7331c54 |  | note | Hold Point - In process Inspection
label | 680fa24d-2def-52c4-baab-da6da7821303 |  | note | Records - FH concrete QA sheet
label | 875b48d8-c840-50f2-b2f2-d085c748288e |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | CIVIL WORKS
checkpoint-status |  |  | checkpoint | 4 - Concrete Footpaths
label | 3f5a8f75-0b64-5139-a5ea-f5d956933882 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 333a8c8c-528f-5c98-8bf8-4cca8c8b6313 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
label | 6b586cc8-55eb-514a-94cf-78c429dd3343 |  | note | FREQUENCY - 10m Intervals
label | 12009b88-c0c1-5840-9e9f-55dc28c3514b |  | note | ACCEPTANCE CRITERIA - Basecourse - 100mm min. thickness GAP40. Clegg CIV > 12. Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with room finish.
label | 4156c2a8-2d4b-5e8d-a110-97923af4b26c |  | note | Hold Point - Inprocess Inspection
label | f2689e85-d22d-53d5-aad5-d4bedd4b07f2 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | c533b5bd-65f9-5e34-9982-9348a8b92652 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Tactiles
label | 919de33d-ec03-5810-8956-d3e86354eddf |  | note | VERIFICATION ACTIVITY - Visual
label | a83cefbd-85f6-59d3-ba3c-94641c0f1284 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
label | 0eeeb774-f3f9-5b76-9859-7259a87bd06e |  | note | FREQUENCY - Each PX
label | 6bf5bd5f-2fba-5aea-b57b-1909abbdc082 |  | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
label | 7a623e1a-a0f0-5874-91b4-e7507d573a96 |  | note | Hold Point - Inprocess Inspection, Measurement
label | 0b2ca55a-45c6-5ff1-9fea-f4038deb8018 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | 61769e94-1325-5007-9dfe-640dc9e5fbc4 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5.1 - Tactiles
label | d1f30e31-a30e-530f-aaca-04c63430cf84 |  | note | VERIFICATION ACTIVITY - Visual
label | bcd181ab-e97b-56e2-b081-89a2c1acbeba |  | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians. AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY.
label | 5434909d-55f3-5b56-b012-dffa4cdf8846 |  | note | FREQUENCY - Every site
label | 9742fa7d-a25c-55a9-84b4-35c5d67f47eb |  | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | 6d697790-5d69-50f8-9e0b-44bb62b212fe |  | note | Hold Point - In process Inspection
label | 670e1200-869a-59e0-9a59-6dc52e015eb9 |  | note | Records - Photos
label | e2867df0-79b5-503f-a665-77e9ee8deca0 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5.2 - Tactiles
label | 6b488549-ff15-558e-a289-0b4a44de211c |  | note | VERIFICATION ACTIVITY - Visual
label | 3377e19a-f09a-5cb4-9ad7-fe622accd60f |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 323b8586-7f27-5ab8-a547-052eae92afc2 |  | note | FREQUENCY - Every site
label | 21356fe3-bc81-535e-8427-3c53fbf0e0fe |  | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | 0f718fca-7a1b-51b9-8487-7d654d685127 |  | note | Hold Point - In process Inspection
label | 038aed7e-ea8b-5743-a239-3a863c84cac4 |  | note | Records - Photos
label | 7a3efa74-8cce-54e9-8005-7fe4edd1bdc5 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5.3 - Tactiles
label | 448a340f-1899-5b0c-ba55-abbd522ed064 |  | note | VERIFICATION ACTIVITY - Visual
label | 83fb59de-015c-540c-9fd1-79d4e645de02 |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 252564de-a286-50b3-95ce-58e955fb4a1d |  | note | FREQUENCY - Every site
label | 00284487-ff6a-59aa-868b-45e7b3ea16c5 |  | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | f2938a32-06ec-5ce6-9790-55e6afd0424f |  | note | Hold Point - In process Inspection
label | 0e6e4058-9a21-588c-bf55-7b2e29584532 |  | note | Records - Photos
label | ce2ebc47-b760-5992-8d64-2909694c78cd |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | RAMM DATA
checkpoint-status |  |  | checkpoint | 6 - As built information
label | 6078c959-809c-501b-82c2-1208ec6ccbf1 |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | 9f0cec53-2afc-5cd3-8bc0-981779ad92d2 |  | note | FREQUENCY - Every Site
label | 1751543c-2052-56a4-991e-a570a9163edc |  | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
label | 256049e7-17df-512d-a207-2d62d9059873 |  | note | Hold Point - In Process Inspection
label | 8c41a3a3-3e54-5881-ba4b-46513078b97e |  | note | Records - As built records
label | bb1b74b7-607b-5cc6-bdad-64d0303628d1 |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-flat |  |  | checklist | ITP - Raised AC Table & Intersection | itp |  |  |  | Yes | Atkinson Ave - ITP - Raised AC Table & Intersection | 7e7cfc68-a499-49e2-9350-d80d5af84f23
checkpoint-status |  |  | checkpoint | 1 - Permits
label | af21b676-d32e-58d4-9ecf-a6a29451ce96 |  | note | H
label | 3964272c-2e2e-5484-8394-36d20d5abe70 |  | note | Detail: Obtain Permits
label | 34d0409b-feae-5f33-8c70-f9c7971b95c9 |  | note | Frequency: As required
label | dd29353f-e4b6-57af-a6d5-6862ddd9a2a8 |  | note | Inspection / Test Method: Document Review
label | 2ea5a2bb-438b-505b-865a-b50edc1c42d1 |  | note | Conformance Criteria: Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 5cb2201f-8aad-579b-bcfb-20d8f704b6a4 |  | note | Records: Permit attached or permit number noted
text | 3a093025-6d25-52bb-8996-05ec4648636e |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Pre-construction sign offs
label | f3db8d0c-8c4c-5a3e-b054-433dd18f2074 |  | note | H
label | 1d3874ef-ec93-5661-b529-e8fae6b2f55f |  | note | Detail: Ensure that Sub-Contract and Supplier Agreements are signed
label | 8bfb4edf-fcec-52b8-8701-90b53f04c77e |  | note | Frequency: Prior to commencement
label | 8892e96a-d75f-5c15-90e6-a1d5b6f4a4df |  | note | Inspection / Test Method: Document Review
label | c109d9cd-863f-5c27-8da6-35ff049b78fd |  | note | Conformance Criteria: Signed Subcontractor and Supplier Agreements
label | 1ae1a34b-03dc-5557-806f-10526686233b |  | note | Records: Subcontract and Supplier Agreements
text | 21c50b37-0cf9-581d-854f-4d07656510d6 |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.1 - Pre-construction sign offs
label | f6026cdd-80e2-50bd-815b-d9cfb32fb575 |  | note | H
label | 9998b4cf-37be-5327-802e-da2999a69acf |  | note | Detail: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | 1dc46e8c-c76c-575a-9d9d-5f99e3211dbd |  | note | Frequency: Prior to commencement
label | 79e16082-52cc-5b0f-9f8c-38d524e90f12 |  | note | Inspection / Test Method: Document Review
label | b0239f68-0f08-59d8-b6aa-990d3c961727 |  | note | Conformance Criteria: TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | 2c921d2d-008a-5bae-838c-5f2c97edd94d |  | note | Records: TMP on MyWorksites/On Site
text | 2c713837-f71b-5886-8ce4-9a64c9cb55be |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 - Pre-construction sign offs
label | fc0f1c40-4a8b-501d-91e8-82d32c418d16 |  | note | H
label | d62fd30c-0580-5fac-8eae-d28dab6cb43a |  | note | Detail: Ensure all Sub-Contractors and Suppliers go through FH induction
label | 70cd0c92-9432-5d94-9f23-39285688515e |  | note | Frequency: On site daily
label | b1a58794-01c4-5863-9936-645cb02514ff |  | note | Inspection / Test Method: Induction
label | 4b46b496-1f42-5249-9131-aa58010ed731 |  | note | Conformance Criteria: Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | 6bf2b116-8843-534e-86e7-4b25b5b61694 |  | note | Records: Hazard ID and Pre-starts to safety team
text | b30e912b-6c44-50b0-b341-6385dcb71bb2 |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | d6994a8f-6cff-567a-ba9b-63127b4aa4b5 |  | note | H
label | 8a94ae40-2601-52e6-80dd-517efdc9b76a |  | note | Detail: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | deb263ed-7822-5586-8ee9-b0cbbd59afe0 |  | note | Frequency: Prior to commencement
label | 8c0f7813-8b50-5c49-8678-d574feacf828 |  | note | Inspection / Test Method: Document Review
label | 93ac07f7-f9fa-501a-9545-1f33dc8a6b51 |  | note | Conformance Criteria: IFC drawings have been received by Contractor
label | 7bed29bd-9f42-58fa-8dd5-7eb666f77673 |  | note | Records: Check Drawing Register
text | 74dcc125-206c-5272-adc9-fe421ecce6bf |  | textbox | FH Initials - Site Engineer:
text | 98bf0ac9-ade3-5da6-9cbc-493e3f25ca33 |  | textbox | Design Engineer Initials:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.1 - Design
label | 75bb0303-fa07-59fd-8d14-c73a460f7b61 |  | note | H
label | f96da6f1-414f-569c-a7ec-4c79c049ecf4 |  | note | Detail: Crossing to comply with AT TDM chapter Traffic Calming and TDM TC0003
label | 247524fb-8d66-5be5-b90f-e1072a163f38 |  | note | Frequency: Prior to commencement
label | 7b3fdbf0-9617-5868-88c4-90268c00c1a8 |  | note | Inspection / Test Method: Document Review
label | e57ca0fc-7727-5e9c-b5be-0937654d4cbb |  | note | Conformance Criteria: IFC drawings have been received by Contractor
label | c6719590-9e62-5861-ba98-a885c6bd2639 |  | note | Records: Check Drawing Register
text | c81ecd67-fd15-5854-b186-82f38423fd1d |  | textbox | FH Initials - Site Engineer:
text | f87149e4-c1d6-5dda-a789-c4e515bdd5b8 |  | textbox | Design Engineer Initials:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4 - Installation of Erosion and Sediment Controls
label | 3889f520-5e18-5cdb-b348-10395dfb86b5 |  | note | H
label | 671a1dd8-e3b1-500e-8f80-cb6b67bb4063 |  | note | Detail: Ensure that Erosion & Sediment Control in place
label | 055f4159-1486-5989-9430-90da90d22a16 |  | note | Frequency: Prior to commencement
label | e1f97454-fb2e-5a19-acf9-699d2855356f |  | note | Inspection / Test Method: Visual Inspection
label | 823a320e-57ed-5bec-9e57-c6f60ea484da |  | note | Conformance Criteria: Cesspit Covered
label | c6a58ada-d553-582f-9689-63dbdabd0b9f |  | note | Records: Environmental Controls Audit
text | db35af76-cf99-567c-8168-a08c66809297 |  | textbox | FH Initials - Environmental Manager/Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | 47b0e8dc-2f79-5ae1-85fe-ad6cf3580330 |  | note | H
label | 54201b03-b721-52e7-85d1-d50482845c35 |  | note | Detail: Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | 00be5d2b-6c03-5ce0-b5cf-fc5b9f28e7ab |  | note | Frequency: Prior to commencement
label | d0f271e7-f646-51cc-b91b-9ef0817be526 |  | note | Inspection / Test Method: Survey + Smart Level
label | 877fe557-dabc-5935-8a6b-c9cb35b8d819 |  | note | Conformance Criteria: Consistency with Construction Drawing
label | b370ef01-8675-5ea1-ac29-29249d34a730 |  | note | Records: Site Photos post surveying
text | f4f9731a-52c0-500d-96d4-77f7e094dd6b |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging
label | 40f66042-9cb1-54c9-b6b7-5641526083d0 |  | note | H
label | cd204d1e-0d3e-5e2f-91b0-2aa350c82a1b |  | note | Detail: Ensure all services conflicting with the line of trench has been exposed by hand digging
label | 3cdd2053-606c-5071-9abe-7a31cac3911d |  | note | Frequency: Prior to commencement
label | 51127c67-48c3-51d4-81d2-2fe394898a0b |  | note | Inspection / Test Method: Potholing
label | 521bd02c-1410-5818-be1a-f88679c90134 |  | note | Conformance Criteria: All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | 32236c30-f260-5a0e-a00b-2be9396f8910 |  | note | Records: Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
text | 2e23e88d-bf94-517c-ab11-6191d52aceba |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7 - Asphalt laying
label | f70787d0-fb3b-52f8-87be-0994c75fbb36 |  | note | W
label | 5c32750f-d250-5b13-a1a9-f18f5aeca447 |  | note | Detail: Raised table and raised intersection formwork to be 75mm above existing road level and be 175mm in depth and gradients respectively of entry and exit ramps
label | 69cf4635-7c5b-58fb-a966-f5fa5fb036d8 |  | note | Frequency: Grade on ramps
label | 0397eae5-accd-5a42-b950-3c7f332c009f |  | note | Inspection / Test Method: Measurement
label | 5962cf4e-013b-5c72-bc22-25da14c324fd |  | note | Conformance Criteria: Designer to inspect formation level
label | 03502a03-59e6-5ec7-8c89-3d68ce91ca27 |  | note | Records: Site photos
text | 8ccfb68e-2fa9-5dda-92db-9e22f58b2502 |  | textbox | FH Initials - Site Engineer:
text | eaafdf36-a574-5504-877a-ef314b0d6f6a |  | textbox | MSQA Engineer Initials:
checkpoint-status |  |  | checkpoint | 7.1 - Asphalt laying
label | 4441b4e8-0e29-54d2-944c-bb24c7eb8f96 |  | note | H
label | e463eb7f-6642-53ec-84cb-d4c0cfc27f98 |  | note | Detail: Raised table and raised intersection ramps to have 100mm depth at entry point and tie into 175mm depth to meet raised table
label | b62d31db-f44e-5452-9e93-b5d499fc135b |  | note | Frequency: Grade on ramps
label | fd4482b1-25b5-5e99-91de-d6447d4b1a1c |  | note | Inspection / Test Method: Measurement
label | f5c344d6-d6fc-57b1-b304-7208e760607c |  | note | Conformance Criteria: Designer to inspect formation level
label | 87a77715-548d-532b-8a71-be5e995f8ef2 |  | note | Records: Site photos
text | bf92aad0-3db2-5dad-adcb-816fca76b145 |  | textbox | MSQA Engineer Initials:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.2 - Asphalt laying
label | 6fa401b5-c6b5-507d-9c7d-fd2e742a96f6 |  | note | H
label | 030a34ca-4728-56fa-91af-729f65dc231a |  | note | Detail: Raised table ramps to be 750mm across for entry and 750mm for departure ramp. Raised intersection ramps to be 1125mm across for entry and 1125mm for departure ramp.
label | 7e1f2984-ef16-5bbd-9362-23f964559279 |  | note | Frequency: Grade on ramps
label | 87a98649-9bc3-53b3-aac1-ea9b9d6599bf |  | note | Inspection / Test Method: Measurement
label | cfdb0b5f-6af4-5930-a12b-8a8280eda813 |  | note | Conformance Criteria: Designer to inspect formation level
label | 70e8817d-2f1a-5de3-8faa-a652fc172b3a |  | note | Records: Site photos
text | 26d75f00-255b-5aed-b7fc-11ace349dba2 |  | textbox | MSQA Engineer Initials:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 8 - Asphalt laying
label | c3b3f8b2-9e7b-5e3e-9e3e-c746283dab4e |  | note | H
label | 666ac5ad-c715-57b5-b205-2f2b1cd3e923 |  | note | Detail: Raised Table ramps to be 1:10 gradient for ramps - As per Relative gradients provided in IFC drawing No. 12544375-C151. Raised Intersection ramps to be 1:15 gradient for ramps - As per Relative gradients provided in IFC drawing No. 12544375-C152.
label | 92776ce6-8fe1-516d-be79-73d75adb4672 |  | note | Frequency: Grade on ramps
label | 36e0aa76-aeaa-58f9-97f5-a98254aa944d |  | note | Inspection / Test Method: Measurement
label | 4f443e6f-7630-5313-9b8d-71698a755f50 |  | note | Conformance Criteria: Designer to inspect gradient level
label | 4fca9d47-fa75-533f-9bf4-2494a647ff09 |  | note | Records: Site photos / Concrete Formwork Checklist
text | 6fb16e5e-c924-50f7-b63a-7051c9f0e745 |  | textbox | MSQA Engineer Initials:
holdpoint |  |  | signoff | HOLD POINT
checklist-sectioned |  |  | checklist | ITP - Pavement | itp |  |  |  | Yes | Triangle/Mokora - Pavement | 93d1607f-1626-4a32-8620-51d2d01a97f2
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 1 - Aggregate - AT AP40
label | 5fb106e1-6a59-506c-bed4-89ba210b987f |  | note | ACTIVITY DESCRIPTION - Aggregate - AT AP40
label | 8c60f304-0d1b-5f04-829a-a2b316154afe |  | note | VERIFICATION ACTIVITY - M
label | 8c2b0d33-4582-594a-833f-4411d9a76682 |  | note | METHODS OR REFERENCE - Meets Contract Auckland Transport Project Spec Section 2.9 - Table 3
label | 431f4cff-c0fb-5911-83ba-65be54f58b91 |  | note | FREQUENCY - Lot
label | 7981ad80-2f0e-56b8-a4a5-1417ed0dd443 |  | note | ACCEPTANCE CRITERIA - A Grading as per NZS 4407 Test 3.8.1 crushing resistance - Less than 10% fines passing 2.36mm sieve size under 130 KN or greater weathering resistance - CA or better SE > 40 PI < 5 or NP
label | cbcba214-9c4a-556d-9a8f-dee71776ec55 |  | note | TYPE - Testing/Visual
label | f0268cc9-e40f-54c5-9465-9cfa4932482e |  | note | RECORDS - IANZ Lab results
label | da661d73-e122-5b31-a8df-671822e51fda |  | note | On Site Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 2 - Concrete Sub Base - 20 Mpa
label | 8ab2952e-ae00-5944-b339-3517eb560a29 |  | note | ACTIVITY DESCRIPTION - Concrete Sub Base - 20 Mpa
label | 60215f45-bf2f-58f6-a08d-e2a6a8474cde |  | note | VERIFICATION ACTIVITY - M
label | 1bdd1432-fe00-58a9-8a5b-f389d93931a9 |  | note | METHODS OR REFERENCE - As per Design
label | 2aee49d2-c1ff-5a2c-8832-758948268ddb |  | note | FREQUENCY - Two cylinders per day
label | 1b1cfa12-4c08-5a79-834c-1c9dcf9aad0c |  | note | ACCEPTANCE CRITERIA - 20MPa Concrete (slump test < 120 and 28 Day UCS test from supplier)
label | 8af74fc6-78d5-580f-973d-ccc349b9f127 |  | note | TYPE - Testing/Visual
label | acdc9e2b-46a2-5117-8ccb-f7d57a90c937 |  | note | RECORDS - Supplier report
label | 79b4f832-342d-5d42-99c7-5b1edf9d3bbb |  | note | On Site Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Bitumen
label | f386b7c5-a86d-5f91-8207-606205dc0b7c |  | note | ACTIVITY DESCRIPTION - Bitumen
label | f6eff29f-94c8-590d-b0c7-6b8dd5f8f8b4 |  | note | VERIFICATION ACTIVITY - M
label | 55076713-35bd-5e4f-9925-19415bb0b9c0 |  | note | METHODS OR REFERENCE - As per Design
label | 40b59efa-5a91-5ce0-8059-33e26c188ff3 |  | note | FREQUENCY - Passing all tests listed in Table 1 of NZTA M/1
label | 55342081-72f8-5fda-b5db-8b3517623233 |  | note | ACCEPTANCE CRITERIA - Passing all tests listed in Table 1 of NZTA M/1
label | 2a314a14-5299-5cd7-afe3-94e160a3cb3b |  | note | TYPE - Testing/Visual
label | b9d863cd-0b2f-5bae-9b7c-5b9e467e974e |  | note | RECORDS - IANZ Lab results
label | 4b89bb39-7067-5999-a931-cd8a8e8d2e15 |  | note | On Site Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4 - Asphalt Mix Design
label | 444ef31e-2a32-5358-8e72-b6ffc0821ad1 |  | note | ACTIVITY DESCRIPTION - Asphalt Mix Design
label | 323a5ede-33df-5498-80b4-65f858a92e29 |  | note | VERIFICATION ACTIVITY - M
label | 54c93776-59c9-5f3b-8b0d-0cbb4dffd430 |  | note | METHODS OR REFERENCE - JMF approved
label | 2c3ed9bc-2215-5b8d-8313-b062f53192ac |  | note | FREQUENCY - JMF approved
label | 55ceab41-daa3-547b-bc7d-01b9d0d4ea0b |  | note | ACCEPTANCE CRITERIA - AUSTROADS - AC20 & PMB AC14
label | 862b13af-3e31-5900-afc4-464c0990fed2 |  | note | TYPE - Testing/Visual
label | 583bbe7a-40d7-5080-beb7-f4dafb09963e |  | note | RECORDS - IANZ Lab results
label | 0eca303d-50ff-5bd0-ae22-d23699f14f67 |  | note | On Site Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Production Tests
label | d694ef90-a411-5cdd-a938-eb4a8e7b3ed5 |  | note | ACTIVITY DESCRIPTION - Production Tests
label | bd0f279d-bc55-5023-a2b6-d2d7a9d2ec23 |  | note | VERIFICATION ACTIVITY - M
label | 1e947690-d85e-5885-b043-0d3ffd5b8180 |  | note | METHODS OR REFERENCE - NZTA M/10 spec
label | 0160e8ab-7ea9-51ad-a0d9-083a39c04a93 |  | note | FREQUENCY - 1 set every 300t
label | f4282e5b-998a-5bed-af11-88a6eea6acfa |  | note | ACCEPTANCE CRITERIA - NZTA M/10
label | ed7c2744-b66e-5c89-ba66-fd324e626dba |  | note | TYPE - Testing/Visual
label | b0e39435-6ee2-5828-91e6-2508194e6a1d |  | note | RECORDS - IANZ Lab results
label | 83d1eb9c-a82c-5729-91ef-a8120e6aa09c |  | note | On Site Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6 - MDD & OMC for AT AP40
label | 67d16356-1703-5ecf-891d-6d19c82a5bef |  | note | ACTIVITY DESCRIPTION - MDD & OMC for AT AP40
label | 9b4b82a1-6379-5750-8113-21b06382469f |  | note | VERIFICATION ACTIVITY - H
label | fbc136f3-c6f9-598d-8382-b7e5f9c56475 |  | note | METHODS OR REFERENCE - Laboratory MDD and OMC tests undertaken prior to construction confirming site targets
label | cda76e43-f511-5066-b373-44e5d178a10a |  | note | FREQUENCY - Once per material type
label | 4aaef332-3358-517d-abc8-af609353abf0 |  | note | ACCEPTANCE CRITERIA - NZS 4402 Test 4.1.1 - MDD and OMC determined in accordance with applicable specification.
label | 84267e69-cbd1-5533-ab28-59ac23f22aa5 |  | note | TYPE - Testing/Visual
label | 7ddaeab4-9f07-50a1-a579-871fa36b347a |  | note | RECORDS - IANZ Lab results
label | 0ec730d9-0f6f-5af0-861c-267f07025a9b |  | note | On Site Responsibility - Site Engineer
checkpoint-group |  |  | section | Excavation/Undercut
checkpoint-status |  |  | checkpoint | 7 - Milling / Cut to Waste (350mm)
label | c3d5dde1-5cb7-5992-bccc-b432340891ea |  | note | ACTIVITY DESCRIPTION - Milling / Cut to Waste (350mm)
label | 88895d05-d1ab-5d88-968d-8f546a7960d6 |  | note | VERIFICATION ACTIVITY - Stringline
label | bb5f14eb-4d2c-5ac7-be47-284c6eaf9a54 |  | note | METHODS OR REFERENCE - Dip from stringline or survey as-built
label | 40373c65-ce9b-5f8b-b146-c3ced3e6e2f5 |  | note | FREQUENCY - 10m each lane
label | 4d6c3d56-3a76-50d7-9c46-a430dff9afa1 |  | note | ACCEPTANCE CRITERIA - +0 / -20mm to design level
label | a85344ee-efef-58e1-966b-d35c15367e90 |  | note | TYPE - Mandatory HOLD POINT
label | c00b04d9-c504-5170-b67a-1d635e49483f |  | note | RECORDS - Stringline Sheet
label | c2bf61c4-12f7-54e0-9cc9-5a13d8ebdc6a |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-status |  |  | checkpoint | 8 - Proof Roll
label | e8a3fe1e-b452-5b1b-9aa8-aca2dd129f31 |  | note | ACTIVITY DESCRIPTION - Proof Roll
label | 3b32d7a1-92ea-5ffa-ba7f-491357f4f5d0 |  | note | VERIFICATION ACTIVITY - Deformation testing of existing Sub Base
label | fc36742f-ea1d-5445-a345-9735ff8b6992 |  | note | METHODS OR REFERENCE - Visual Inspection
label | efae24ed-519b-512e-ab39-522e4f21ed23 |  | note | FREQUENCY - Existing milled Sub Base
label | 303e1a3f-1aad-556e-87e7-fad01332b64a |  | note | ACCEPTANCE CRITERIA - No physical deformation or springing observed
label | 19cde30b-16d3-59f6-a4c5-104f08ae1e25 |  | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
label | f4ac722c-51c3-56bd-95ac-4cf0b3dfb1d6 |  | note | RECORDS - QA Record
label | 82487793-a39c-59a0-b4fd-15604bdc4105 |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-status |  |  | checkpoint | 9 - Contingency Undercut
label | a36b2588-40b3-55d6-89a1-73a1a42e7ae1 |  | note | ACTIVITY DESCRIPTION - Contingency Undercut
label | 1090b6e2-e99d-5bed-9ed7-bc0de53090e2 |  | note | VERIFICATION ACTIVITY - Contingency
label | 82f45a3e-2fcf-5fa1-a1c4-7090346f0f6d |  | note | METHODS OR REFERENCE - Contingency Undercut
label | 32e3e565-c514-5ca6-b540-2dff93fea37b |  | note | FREQUENCY - Areas with deformation under proof roll
label | e9ac61ff-5668-5d39-a579-d5716a5ea4ce |  | note | ACCEPTANCE CRITERIA - If significant deformation or springing is witnessed under the proof roll or the subgrade is encountered at 350mm then undercut by 180mm and replace with static compacted AT AP40.
label | b46b30b8-7483-5b16-894b-abbedbadd811 |  | note | TYPE - Inprocess Inspection
label | bfc4c3cd-cff0-5d61-8f87-d9167b84c62d |  | note | RECORDS - Site diary
label | 934db33a-05f3-543a-a88f-46e469dad545 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 10 - Widening Area - Milling / Cut to Waste (530mm)
label | a04696a0-27df-5e39-b063-591acb2ba581 |  | note | ACTIVITY DESCRIPTION - Widening Area - Milling / Cut to Waste (530mm)
label | 3a42640f-be29-57ee-a48e-e744d3223b8c |  | note | VERIFICATION ACTIVITY - Stringline
label | 99dc0315-e4fa-59c7-a0aa-b29a08cea398 |  | note | METHODS OR REFERENCE - Dip from stringline or survey as-built
label | b61ec14d-dee6-5215-ab3c-7b34e1f90e94 |  | note | FREQUENCY - 10m each lane
label | 2e678695-5d93-5dfd-af14-d19fee242717 |  | note | ACCEPTANCE CRITERIA - +0 / -20mm to design level
label | 22faccae-e41a-532f-90f8-89ee7f78164e |  | note | TYPE - Mandatory HOLD POINT
label | 190a24cf-87c5-52f4-be7b-8fe5c076d73e |  | note | RECORDS - Stringline Sheet
label | e757d3a0-842d-5f01-aeda-c2af3182cd63 |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-status |  |  | checkpoint | 11 - Subgrade
label | 35561225-607a-52aa-834c-61b19443bd60 |  | note | ACTIVITY DESCRIPTION - Subgrade
label | dadb8d8d-9007-5af7-aa01-91b168070146 |  | note | VERIFICATION ACTIVITY - No unacceptable subgrade materials after excavation
label | 04781f27-5c95-58b2-85dd-f2a7af2d317b |  | note | METHODS OR REFERENCE - Visual Inspection
label | 05dfcd5c-8886-5460-9006-e97f2effe0e3 |  | note | FREQUENCY - NA
label | ae02edae-43ea-50eb-a57f-021371c5622f |  | note | ACCEPTANCE CRITERIA - Free of detritus and loose material
label | df24b2f3-049f-5082-a734-5e914e4969d0 |  | note | TYPE - Inprocess Inspection
label | 61b4d4ff-10e3-5afd-8caf-c475c7b7dd99 |  | note | RECORDS - Site diary
label | 68ef4bc3-d651-5c7f-926f-bc16adf01f8d |  | note | On Site Responsibility - Project Engineer
checkpoint-group |  |  | section | AT AP 40 Sub Base (Widening Area)
checkpoint-status |  |  | checkpoint | 12 - NDM & Plateau Test
label | b911417a-6600-5d09-917e-3d1969b9bbe2 |  | note | ACTIVITY DESCRIPTION - NDM & Plateau Test
label | 7a77f141-18e0-5e45-a9ea-eb40fdbbff4b |  | note | VERIFICATION ACTIVITY - Testing
label | bd89d62b-e50a-533c-9738-ed5a410e1b5d |  | note | METHODS OR REFERENCE - Dip from stringline or survey as-built
label | 2c8615db-d26b-528f-a00e-972653102948 |  | note | FREQUENCY - 1 test per 10m in each traffic lane (alternating wheel path)
label | 9c282f43-6206-5942-8fb6-4b6f7c995506 |  | note | ACCEPTANCE CRITERIA - Clegg Test > or equal to CVI 35
label | 36b28e27-92bf-59b0-8c07-c375f0c54869 |  | note | TYPE - Inprocess Inspection
label | 4185b9ee-681e-5ee9-bd11-4da024b00937 |  | note | RECORDS - IANZ Lab results
label | afd1444f-21d9-5ac4-ac19-b0d2c4ff1473 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 13 - Stringline & Level
label | bac86b29-ae15-529f-a9f1-1afeacb18efe |  | note | ACTIVITY DESCRIPTION - Stringline & Level
label | 8db6abb2-98df-50e3-bbb5-d7897b9af6ca |  | note | VERIFICATION ACTIVITY - Testing
label | 599384b4-2a8f-5f2e-8c44-764ec66f13ec |  | note | METHODS OR REFERENCE - Dip from stringline or survey as-built
label | fb201861-ff7c-59a0-9a91-943aea678d2a |  | note | FREQUENCY - 1 test per 10m in each traffic lane (alternating wheel path)
label | f53d4a49-f4dd-53bb-a597-c2df1838e01f |  | note | ACCEPTANCE CRITERIA - Constructed as per TNZ B/2, minimum compacted layer depth to not be less than 100mm. Finished surface of Sub Base 180mm thick. Tolerances (-25mm, +5mm).
label | 56d13ce5-03ae-59be-b1ad-1505de3a9d58 |  | note | TYPE - Inprocess Inspection
label | 785d974c-f1d6-50c8-ac9f-dbfb96c31bba |  | note | RECORDS - Stringline checks Photos
label | dc161eb9-8a7f-5745-8622-d728a7b0d6ed |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 14 - Proof Roll
label | c0f948d9-5bd6-5267-a3ed-f00f86633995 |  | note | ACTIVITY DESCRIPTION - Proof Roll
label | 19a27645-be37-5b9a-987a-92eec20a3741 |  | note | VERIFICATION ACTIVITY - Visual Inspection
label | b867647b-1f0f-54a1-b044-c2abfc8f28e9 |  | note | METHODS OR REFERENCE - Visual Inspection
label | 82b1e45a-8964-551e-95c8-32aebe68c710 |  | note | FREQUENCY - Continuous
label | a0847a71-cca0-5124-831b-b2b9b72a36f6 |  | note | ACCEPTANCE CRITERIA - Undertake proof roll of the Sub Base 12T static smooth drum roller - No springing or deformation under the roller
label | 2178c4fe-a4ac-54c8-abf2-9ffefbdbae5e |  | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
label | 6846b3a2-9bbc-5392-8cdc-949cd1a3f450 |  | note | RECORDS - Visual Inspection Photos
label | 7514a015-ccf0-5cc5-83f5-5448807092b2 |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-group |  |  | section | Undercutting Contingency
checkpoint-status |  |  | checkpoint | 15 - Contingency Weak / Soft Spot
label | ffd0a696-eb85-5c28-bf61-7f7bd1b11e4f |  | note | ACTIVITY DESCRIPTION - Contingency Weak / Soft Spot
label | 0d3efabd-c897-51b2-86f5-0e8a7ca49626 |  | note | VERIFICATION ACTIVITY - Scala Penetrometer tests
label | d53537d8-7051-5312-864a-59d692db31fb |  | note | METHODS OR REFERENCE - Design Report
label | 6116cc42-9486-5219-8318-e65a78c81201 |  | note | FREQUENCY - At 10m intervals in each lane
label | 4d0f99cb-c788-54f9-98be-4d401deb479e |  | note | ACCEPTANCE CRITERIA - Subgrade CBR ≥ 1
label | 15d57923-4d98-5729-aa91-02442dd2e05c |  | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
label | ebc01f80-485a-5661-830a-3ed9c5ffdaaa |  | note | RECORDS - Marked up drawing
label | 7395566c-d946-5088-9567-dafca75e2063 |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-status |  |  | checkpoint | 16 - Contingency Undercut to be Confirmed by Designer following review of Scala and site conditions.
label | 15fa8d52-2883-541c-9bab-fcadb9536554 |  | note | ACTIVITY DESCRIPTION - Contingency Undercut to be Confirmed by Designer following review of Scala and site conditions.
label | 8b416f79-30eb-5ff7-9283-5ea1aed7229a |  | note | VERIFICATION ACTIVITY - Design
label | a7a5f90d-ac7c-52de-addb-169ca09071f1 |  | note | METHODS OR REFERENCE - Pavement Design
label | 202897e3-b42e-583a-9bc5-e9905c2a384a |  | note | FREQUENCY - As required
label | 02b28f3a-3ab2-5c13-a244-1c8f851782fa |  | note | ACCEPTANCE CRITERIA - As required based on Scala tests and site conditions. To be confirmed by Designer.
label | 8548ca3d-8c3e-512c-b4ab-ae8075e30df9 |  | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
label | c132ed3a-239a-58ff-b3c8-d00bf9039a9a |  | note | RECORDS - Stringline Sheet
label | 24c12f8d-c79f-5537-b623-8256950d6d66 |  | note | On Site Responsibility - Design Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-group |  |  | section | Concrete Sub Base (150mm)
checkpoint-status |  |  | checkpoint | 17 - Concrete Sub Base
label | 1f6b5c08-8bdb-5340-987c-b1416a156a13 |  | note | ACTIVITY DESCRIPTION - Concrete Sub Base
label | fbd078cc-ecf8-53b8-a4be-3d8fbf24a732 |  | note | VERIFICATION ACTIVITY - Strength and slump
label | 6182034d-16da-5706-86a9-bbb15c961428 |  | note | METHODS OR REFERENCE - Concrete dockets
label | 68da7196-8e2e-510c-a5ff-4de11f43842a |  | note | FREQUENCY - each pour
label | ae0f0a4d-2a39-5947-9ae1-fd3233234d82 |  | note | ACCEPTANCE CRITERIA - Strength = 20MPa Supplier to send through cylinder strength report
label | 3f6ee998-fe17-5d30-862f-caa42695c3eb |  | note | TYPE - Inprocess Testing
label | b3cd85cd-0766-5422-bb8f-b8ec9fda79c2 |  | note | RECORDS - Docket
label | 95f96316-d0f8-5892-9ad0-e95158c57b2f |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 18 - Concrete Sub Base
label | c6beca4d-3406-5625-80cb-ce06a28918bf |  | note | ACTIVITY DESCRIPTION - Concrete Sub Base
label | aa0124ad-664f-50f6-92a8-ddbcfe4ba3bf |  | note | VERIFICATION ACTIVITY - Levels / thickness
label | 659ebfad-c03c-59cd-b47d-a2a303df255b |  | note | METHODS OR REFERENCE - Dip from stringline
label | 970e6387-f800-5006-be85-0af47da3c4c9 |  | note | FREQUENCY - 10m each lane
label | f0f16eb9-5547-5f8f-9aa9-3757fc598de6 |  | note | ACCEPTANCE CRITERIA - Target Depth = 150mm -10 / +10mm, 200mm from design surface level
label | fe1533a8-b38c-502d-8b1f-2759474fb766 |  | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
label | 21456177-efc6-5d23-88ab-4408572942c2 |  | note | RECORDS - Stringline Sheet
label | db596ac4-854d-5c23-8494-8e2ca6f44033 |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-status |  |  | checkpoint | 19 - Concrete Sub Base
label | 66fa5a54-1125-5451-9c81-813306d1bd7b |  | note | ACTIVITY DESCRIPTION - Concrete Sub Base
label | da8448d6-dcb7-5525-a6b8-906b9d869707 |  | note | VERIFICATION ACTIVITY - Rake finish
label | 2752e18c-b2a2-563a-8b1d-5e4900cdef98 |  | note | METHODS OR REFERENCE - Visual Inspection
label | cff42de8-7905-5476-be36-7ba11f7e8717 |  | note | FREQUENCY - NA
label | 0ab5832d-57be-5c0e-9c43-b82f7dbebf31 |  | note | ACCEPTANCE CRITERIA - U5 rough finish or rake rough surface verified over 100% of surface area
label | 188f120d-03cf-58aa-9c7f-19fa35a9ae8b |  | note | TYPE - Inprocess Inspection
label | 19b59f3b-60a7-52c5-93e7-66b3cb16b228 |  | note | RECORDS - Site Records
label | 709e571c-8cf1-5e8c-a504-281a2155df03 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 20 - Concrete Joint
label | c58bf444-4a98-5947-bf21-896366cee9bd |  | note | ACTIVITY DESCRIPTION - Concrete Joint
label | a1a72775-b1b1-53ec-9cb9-8e4fb9481929 |  | note | VERIFICATION ACTIVITY - Roughened / Keyed Joint
label | 9834edcf-0bf2-5b3c-8581-40f3f0e93ffd |  | note | METHODS OR REFERENCE - Visual Inspection
label | 7596968c-28a2-56ae-ad45-a4ba9ea983b9 |  | note | FREQUENCY - Each Subsection
label | ab4080af-a1d0-5f1a-a9d6-b71f1ee7b447 |  | note | ACCEPTANCE CRITERIA - Roughened or keyed joint confirmed over full depth of concrete
label | 2b43bb17-a588-5d9f-90ed-a80fbc6ab56f |  | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
label | cae897f3-90ac-5b56-9410-35105c7b0b35 |  | note | RECORDS - Site Records
label | 3ba4f1c0-e5a4-5eb4-bcc8-5e6e7e81fff7 |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-status |  |  | checkpoint | 21 - Concrete Curing
label | dd08c654-3d2a-52ba-ba3c-321266fd631a |  | note | ACTIVITY DESCRIPTION - Concrete Curing
label | e2d3c8e9-9be6-5ef0-b8f3-44afcfa6cc05 |  | note | VERIFICATION ACTIVITY - Visual Inspection
label | 2299b1c7-3cad-5c88-98c2-ee34b0213ea3 |  | note | METHODS OR REFERENCE - Construction
label | 9770fe27-208c-5a23-8800-898362feaf84 |  | note | FREQUENCY - Concrete Area
label | 9a31068f-d8af-5965-b771-d5d38e076da3 |  | note | ACCEPTANCE CRITERIA - The concrete Sub Base requires a 48 Hr moist cure period to minimise cracking where traffic is not permitted. For cracking witnessed after the 48 hr period the following mitigation measures shall be undertaken: Cracking <1mm - Heavy Tack Coat Cracking 1 to 3mm - Heavy tack and reinforcement grid Cracking >3mm - Engineer Decision
label | 7482ebb4-cb8d-579c-a3b4-1c6bad29ff53 |  | note | TYPE - Mandatory HOLD POINT AT Sign Off Required
label | 6e8c638e-63ed-551e-aff1-66ef6cecc006 |  | note | RECORDS - Visual Inspection Photos
label | 2689d729-d236-59bd-850a-8836b198a88f |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-group |  |  | section | Emulsion (Concrete, AC layer, and on top of existing pavement)
checkpoint-status |  |  | checkpoint | 22 - Emulsion tack coat
label | dc8176f5-fb71-5532-bd75-328489aa0255 |  | note | ACTIVITY DESCRIPTION - Emulsion tack coat
label | 0693dec0-120b-5aa5-bf94-bd064f68439e |  | note | VERIFICATION ACTIVITY - CAT60 cationic emulsion or approved alternative
label | c85bd797-a6a7-58a2-899c-65c313759a3f |  | note | METHODS OR REFERENCE - Dip emulsion tank
label | d51fc9cc-546b-5fb1-804a-ba2e6cb7c7f6 |  | note | FREQUENCY - each lot
label | 678bfa5f-d989-56d3-824d-4e51478243ac |  | note | ACCEPTANCE CRITERIA - 0.3 to 0.6 lt/m2 (minimum residual) based on requirements from design drawings.
label | 44abc0b9-7db4-56a3-80ee-5b7c1fb8534d |  | note | TYPE - Inprocess Testing
label | 2038168a-0ccf-588e-8334-264b7638f690 |  | note | RECORDS - Spray sheet
label | 8185a284-f427-56fa-8630-7744bce649c5 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 23 - Blinding
label | 7f80f009-3402-511e-ad3c-e12b27e32061 |  | note | ACTIVITY DESCRIPTION - Blinding
label | ac87cbff-d2b2-5f87-8136-86f64d21944f |  | note | VERIFICATION ACTIVITY - Grade 5 chip
label | d9970d56-4739-5207-adad-addad435d9bb |  | note | METHODS OR REFERENCE - Aggregate Supply
label | 8e0fd961-cdaf-5be2-b0df-4380130dc9a1 |  | note | FREQUENCY - each lot
label | 6a780453-1523-5fce-bdca-7f86bb929a6a |  | note | ACCEPTANCE CRITERIA - Even application of blinding where required in accordance with the design drawings.
label | 7a5842fc-52be-5731-9a32-85f7993041d5 |  | note | TYPE - Inprocess Testing
label | f093dc16-b80e-5089-841e-d3ef0dca808a |  | note | RECORDS - Spray sheet
label | 5a32299d-8f67-5c0f-9fbd-5c0f218c4239 |  | note | On Site Responsibility - Project Engineer
checkpoint-group |  |  | section | AC20 (160mm in two lifts)
checkpoint-status |  |  | checkpoint | 24 - AC20
label | 5b0a7da9-1a4a-5652-9781-6605b7ffc015 |  | note | ACTIVITY DESCRIPTION - AC20
label | 67f1e15c-ecb9-560a-bc7b-395ad8318cd1 |  | note | VERIFICATION ACTIVITY - Check weather reports
label | 70a727d7-cf29-5f8a-9f36-2fbcec61657f |  | note | METHODS OR REFERENCE - Forecast and thermometer
label | eeb61da5-9a3c-5104-8cb1-e05e23130051 |  | note | FREQUENCY - Daily
label | 0c7ba1ba-45c2-5e4f-b955-818b1c46161d |  | note | ACCEPTANCE CRITERIA - No fog, rain or wet surface. Base temp ≥ 5o C
label | f80e3899-eb2f-59d5-87db-158b468163c4 |  | note | TYPE - Inprocess Testing
label | ff2267b7-5648-5d3e-b3a2-e6aea869b8c2 |  | note | RECORDS - AC check sheet
label | beedfa8d-f00e-5269-8987-343b5b27ad6d |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 25 - AC20
label | 8c555dae-ef0c-5e3f-8868-e54a1dfb5d51 |  | note | ACTIVITY DESCRIPTION - AC20
label | b8feae65-6572-5306-adb4-f52961692d23 |  | note | VERIFICATION ACTIVITY - Ensure previous layer is broomed clean
label | a39c54e5-e0ce-5435-ab9e-86e86493115f |  | note | METHODS OR REFERENCE - Visual
label | 84b16ba8-e1fc-52be-aa2b-daaccf1ff43b |  | note | FREQUENCY - Prior to starting
label | 84e2aaed-73ad-59cb-9a5f-74c09e90b36e |  | note | ACCEPTANCE CRITERIA - Free of detritus and loose material
label | 43bd6451-138b-54a9-928b-a2061965bf2c |  | note | TYPE - Inprocess Testing
label | f2df7383-fdae-59d7-8cd4-3e76272f3dfe |  | note | RECORDS - AC check sheet
label | 05708904-a696-5b5f-bd49-9ad1485dd043 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 26 - AC20
label | 87c4faf2-1524-5ac2-8d56-7b89c2d2fe17 |  | note | ACTIVITY DESCRIPTION - AC20
label | fd45f815-9ef1-5832-89b8-7e80d47d47b1 |  | note | VERIFICATION ACTIVITY - Production tests
label | 46204d37-d4d0-5df7-83ff-3f45d66f6149 |  | note | METHODS OR REFERENCE - Grading, binder content, max density, temp
label | b5e933c0-7243-550b-adc9-6a8800b5a0e1 |  | note | FREQUENCY - 1/300t
label | 067d3294-e49f-52a5-bdc3-13ec1a7532d0 |  | note | ACCEPTANCE CRITERIA - NZTA M/10
label | 066b938f-de55-5940-b4d1-9df72035c4f5 |  | note | TYPE - Inprocess Testing
label | b9143706-04e5-5826-8055-e4a58321dabc |  | note | RECORDS - Lab test
label | 1e969a64-7a9d-5a12-bbd7-408167f3af3f |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 27 - AC20
label | ce3a6b42-4937-51ff-b199-e96523ad3600 |  | note | ACTIVITY DESCRIPTION - AC20
label | 1407ea6f-bde9-5ddd-93e3-ed6da2df643f |  | note | VERIFICATION ACTIVITY - Surface finish inspection
label | 1505ebec-0a70-5ce1-80c6-089bc448ce53 |  | note | METHODS OR REFERENCE - Visual inspection by the Engineer
label | 40aeeb65-6dc5-576a-9de0-e4833e8e39c3 |  | note | FREQUENCY - Each lot
label | 367bef8d-5183-5737-9cf5-aaea179e60be |  | note | ACCEPTANCE CRITERIA - Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
label | e9d24c77-d8e5-5b99-9a97-f8fc544c1dc5 |  | note | TYPE - Inprocess Testing
label | 41215e09-97de-5218-a299-917092977238 |  | note | RECORDS - Inspection sheet
label | 2eaa7d9b-e6bb-5081-b525-cfc195033b6f |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 28 - AC20
label | 35c78fed-39f4-55c7-8213-c983b1a54af1 |  | note | ACTIVITY DESCRIPTION - AC20
label | d690d8ea-6f4a-5130-8555-916bae4c52eb |  | note | VERIFICATION ACTIVITY - Density testing
label | a865d8bb-2325-5b90-912d-99c3e36d8ec7 |  | note | METHODS OR REFERENCE - NDM
label | 4eb4c5b1-7322-5f07-9e32-39d429a23356 |  | note | FREQUENCY - Every 30m2
label | 5e91fad4-faec-5e5a-889d-f4a9523c82cf |  | note | ACCEPTANCE CRITERIA - Air voids (2% - 7%), in accordance with NZTA M/10 (2020)
label | 6347f87a-b97e-55c9-b807-42b71ceaa2eb |  | note | TYPE - Inprocess Testing
label | 806b7728-a524-5bc5-9ae2-01be8c505a8e |  | note | RECORDS - Inspection sheet
label | 442fd436-d11a-51ff-8c07-8ed7054ac164 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 29 - AC20
label | b9164f88-b5a0-500e-8c81-fc7f96670126 |  | note | ACTIVITY DESCRIPTION - AC20
label | a8e4251b-2a19-5548-b3c1-dcaf9a0f5756 |  | note | VERIFICATION ACTIVITY - As-built layer
label | d92486ab-81fd-531e-80ee-5316d9e02ede |  | note | METHODS OR REFERENCE - Stringline
label | adaf41d0-5498-569d-a69e-01accc7f3ecf |  | note | FREQUENCY - Each lot
label | 2fa5e8f5-aa3c-5519-89ac-a8dbbb5938d7 |  | note | ACCEPTANCE CRITERIA - 160mm (+10 / -10mm), Constructed in two 80mm lifts.
label | 07a4f282-43e3-50a4-80f4-8171908f441f |  | note | TYPE - Inprocess Testing
label | 804fa204-2975-5c40-ab9e-67c8449e80c7 |  | note | RECORDS - As-built drawings & stringline measures
label | 30ce4b71-6472-5ac7-be5e-f80ff4baee67 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 30 - Joint Inspection
label | e5731c55-462b-542c-a0d3-96123146b61f |  | note | ACTIVITY DESCRIPTION - Joint Inspection
label | dc614178-e47e-5c84-90d3-9b6c8b303403 |  | note | VERIFICATION ACTIVITY - Visual
label | fc4cdeb0-f049-5c62-9863-203360feed18 |  | note | METHODS OR REFERENCE - Design Report
label | b8c8ddda-12c3-5921-ad1c-d9c193c7afb6 |  | note | FREQUENCY - Each Subsection
label | ce36886e-17d1-5b60-a51a-9e9190fa2595 |  | note | ACCEPTANCE CRITERIA - Transverse layer joints to be offset by 500mm and longitudinal layer joints to be offset by 150mm, as per the design drawings.
label | fc13b8e6-5009-57d4-977f-eaedb7f1af91 |  | note | TYPE - Mandatory HOLD POINT Auckland Transport Sign Off Required
label | c00a3bca-1e09-5330-8ebc-cfbdf43e3c12 |  | note | RECORDS - Site Records
label | 430f3257-d557-5537-be5f-bf719d16dbea |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-status |  |  | checkpoint | 31 - AC20
label | c9782328-e14d-5bf6-ae6f-725c8028b749 |  | note | ACTIVITY DESCRIPTION - AC20
label | ea3db3a9-6231-5c12-a9c5-91b51331477c |  | note | VERIFICATION ACTIVITY - Density testing
label | ff705d60-08da-5120-ae09-02c7179ed8a9 |  | note | METHODS OR REFERENCE - Cores (Random testing plan to be agreed with client)
label | dd81cc53-503c-5f19-b4e1-cd2078b65a2c |  | note | FREQUENCY - 1/300m2 or min 4 no.
label | 318cc172-7d02-5c80-94d3-b8b7aeb85b00 |  | note | ACCEPTANCE CRITERIA - Air voids to meet NZTA M/10:2020
label | bc1ccded-4ce9-5ae2-9375-23afde794c20 |  | note | TYPE - Mandatory HOLD POINT Auckland Transport Sign Off Required
label | a098c08f-1ff1-5cc9-a102-0691be9d42cb |  | note | RECORDS - RFI response
label | 45dd016c-e50d-5d2e-a77d-979e4605c724 |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-status |  |  | checkpoint | 32 - AC20
label | 16c11065-ee87-56a5-ab72-4b90344913aa |  | note | ACTIVITY DESCRIPTION - AC20
label | 2fd4914b-b196-5447-9174-1303920ae251 |  | note | VERIFICATION ACTIVITY - Thickness (80mm layers with geogrid in between)
label | 20553ed2-492c-5c90-aaf8-4b2b9c6a3390 |  | note | METHODS OR REFERENCE - Cores depth (Random testing standard)
label | b04cf9e5-8849-531e-8694-88687fcca2d1 |  | note | FREQUENCY - 1/300m2 or min 4 no.
label | cbadb86e-8939-5a20-89e3-48753b4390d8 |  | note | ACCEPTANCE CRITERIA - - Target depth 160mm
label | e6ab2bde-db47-5f2c-8ea7-80fec97df5e1 |  | note | TYPE - Mandatory HOLD POINT Auckland Transport Sign Off Required
label | 80e41e31-a2d4-511f-abc6-980b472d2160 |  | note | RECORDS - Core test report
label | c76bcf90-995f-5de0-a444-d34e2d091dea |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-group |  |  | section | Hatelit grid
checkpoint-status |  |  | checkpoint | 33 - Hatelit
label | bb0bf400-1f46-5d39-9d61-89b3601f9a2b |  | note | ACTIVITY DESCRIPTION - Hatelit
label | e96e9174-116f-570f-adec-6e762be6ccfc |  | note | VERIFICATION ACTIVITY - Length direction grid overlap
label | 0ea9535d-dec7-5123-a62d-6da1b3e84ec0 |  | note | METHODS OR REFERENCE - Visual inspection
label | 8a94cbad-69f1-5776-962a-3b5ebab8432e |  | note | FREQUENCY - Ongoing during install
label | f017a3e7-074b-560f-9c73-d8f0df492a61 |  | note | ACCEPTANCE CRITERIA - Min. 250mm
label | 85b63e4c-9695-5fb0-a030-7a3b1abd537f |  | note | TYPE - Inprocess Testing
label | d0d395ec-a3c9-5433-946b-5b428efae9f7 |  | note | RECORDS - Photo / diary note / check sheet
label | bb58e055-b09e-5664-8733-21b2eafbd75d |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 34 - Hatelit
label | ef7c3b87-534d-5d7e-a132-74193a3b73d0 |  | note | ACTIVITY DESCRIPTION - Hatelit
label | 732d3764-7cd2-5098-b5d3-980063c2fe96 |  | note | VERIFICATION ACTIVITY - Cross direction grid overlap
label | 1ea33caf-355b-56ba-813f-d16063b48213 |  | note | METHODS OR REFERENCE - Visual inspection
label | a86fd457-d2f4-5ab3-8252-1771b0c3e638 |  | note | FREQUENCY - Ongoing during install
label | 13557e09-df12-516d-a402-46ec32826a23 |  | note | ACCEPTANCE CRITERIA - Min. 150mm
label | 3768e4ff-4800-554e-8977-98a722cf7d81 |  | note | TYPE - Inprocess Testing
label | 0d54ac33-85ce-52a3-afa0-e5482399bc77 |  | note | RECORDS - Photo / diary note / check sheet
label | 93482be0-614a-5154-a812-9e8d602cead5 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 35 - Hatelit
label | dfad841a-298b-53ec-95bd-e49bf505caec |  | note | ACTIVITY DESCRIPTION - Hatelit
label | 8b71f3a2-99e4-57bb-ab6f-74c58aeb653d |  | note | VERIFICATION ACTIVITY - Tack coat
label | 24f7c40f-f2cc-5521-806b-21b1165ec523 |  | note | METHODS OR REFERENCE - Visual inspection
label | 186fd887-e18f-590a-8636-e3fe6c330bf7 |  | note | FREQUENCY - Ongoing during install
label | 7d447eab-6064-57ff-b56c-9cc11c960536 |  | note | ACCEPTANCE CRITERIA - 0.4 lt / m2 - 0.8 lt/m2, residual bitumen emulsion (depending on surface condition)
label | 2daf9bba-2add-5f03-9b5b-2aa56a71133c |  | note | TYPE - Inprocess Testing
label | 658bd94b-d5f8-5909-8a50-39bd61993b30 |  | note | RECORDS - Photo / diary note / check sheet
label | 798a1e4a-a85f-5193-9215-7b3e54840c80 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 36 - Hatelit
label | a3b6465f-37e2-5ab3-a08b-1c5e809c407a |  | note | ACTIVITY DESCRIPTION - Hatelit
label | 1f41af5e-1842-53ae-a49d-1ac3954abb46 |  | note | VERIFICATION ACTIVITY - Emulsion on overlaps
label | ab09cd2b-da20-5133-9a43-790bf256118c |  | note | METHODS OR REFERENCE - Visual inspection
label | d0f0ae2e-0027-5383-b215-67f7e6f77494 |  | note | FREQUENCY - Ongoing during install
label | 7b9e0caf-4eea-5a0a-b963-6ece713e3e85 |  | note | ACCEPTANCE CRITERIA - 0.3 lt / m2 if required
label | 47e481b8-0567-5e2e-ae93-5fccc345d3da |  | note | TYPE - Inprocess Testing
label | ad313587-956f-54d1-8d64-3449a41eecc1 |  | note | RECORDS - Photo / diary note / check sheet
label | 4dcb76bd-4355-5712-9162-47e5852700b7 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 37 - Hatelit
label | 7a0a5eb2-684c-54ad-88df-87e5a22929fb |  | note | ACTIVITY DESCRIPTION - Hatelit
label | 948d22aa-1106-5faa-8d20-aac411200adc |  | note | VERIFICATION ACTIVITY - Evenly laid grid
label | 3a1a42a4-9c5a-543f-8915-132516c1385a |  | note | METHODS OR REFERENCE - Visual inspection
label | 6e019a1b-5dc2-56bd-a1ff-d80aa9dfbdf3 |  | note | FREQUENCY - Ongoing during install
label | 3d8b1d01-f2a1-5347-9480-4ddac92cac9f |  | note | ACCEPTANCE CRITERIA - Minimal air voids in grid, grid pulled tight
label | b4730571-554b-55d7-8b78-64948619541a |  | note | TYPE - Inprocess Testing
label | a6d96661-3d3b-559a-a40c-471e229d773d |  | note | RECORDS - Photo / diary note / check sheet
label | 9a695813-6e6d-5cec-883b-e83064d2e801 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 38 - Hatelit Blinding
label | 08eeecb3-2124-569b-a3c7-936e556cbca5 |  | note | ACTIVITY DESCRIPTION - Hatelit Blinding
label | a62f28cb-6e58-57cb-8b97-373485deed22 |  | note | VERIFICATION ACTIVITY - Blinding Mix
label | 396dafb1-ed6b-53d1-96a7-91f76936132b |  | note | METHODS OR REFERENCE - Even Spread of Blinding
label | 686819e6-4e4c-5f95-a751-a9bac4adfd59 |  | note | FREQUENCY - Ongoing during install
label | fe223b27-0524-51e2-9934-38d8bfc200f7 |  | note | ACCEPTANCE CRITERIA - Blinding mix applied to the Hatelit prior to paving next AC lift
label | 5d8cf60b-2079-5156-b507-3923125792b1 |  | note | TYPE - Inprocess Testing
label | 7d742359-a5c8-5d5e-9481-d41bfeaf03c8 |  | note | RECORDS - Photo / diary note / check sheet
label | 209709b4-2e5f-5d2a-9b95-c9fd842157e8 |  | note | On Site Responsibility - Project Engineer
checkpoint-group |  |  | section | PMB AC14 Raised Table
checkpoint-status |  |  | checkpoint | 39 - Visual Inspection for existing failures at intersection
label | de96a2bc-33ec-5eab-9fda-752edd3f7810 |  | note | ACTIVITY DESCRIPTION - Visual Inspection for existing failures at intersection
label | 205f4797-884e-5ab6-a8a8-ddf005ad6d50 |  | note | VERIFICATION ACTIVITY - Visual
label | 1f5197c2-6059-5a60-8c04-158a08704b7b |  | note | METHODS OR REFERENCE - Site Walkover
label | 6be34b1a-ad75-578f-84b4-26d0d3a9a102 |  | note | FREQUENCY - Intersection Area
label | 67c1e3e7-4d12-5bec-a839-975077d3de6c |  | note | ACCEPTANCE CRITERIA - Joint visual inspection undertaken to identify areas of pavement distress at the intersection that require undercut prior to the overlay. Undercut depth to be confirmed by Designer on-site following review of failure mechanism.
label | 20849ad0-1bc0-5478-b223-8dc043cf564a |  | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
label | c04fcd4b-82e5-51db-af10-4ebc2d8e6fdd |  | note | RECORDS - Visual Inspection Photos
label | 3966b529-74ff-5e50-a4a7-992386d9a872 |  | note | On Site Responsibility - Project Engineer/Designer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-status |  |  | checkpoint | 40 - PMB AC14
label | 0b58efa5-5b35-58c1-852d-6b44e798e02e |  | note | ACTIVITY DESCRIPTION - PMB AC14
label | d53eb549-279b-5371-809f-196f3387c6e8 |  | note | VERIFICATION ACTIVITY - Check weather reports
label | 2f16104f-6c99-53d6-952d-8d23e24a86d6 |  | note | METHODS OR REFERENCE - Forecast and thermometer
label | 72288880-de50-516e-822a-39e633c2d9b6 |  | note | FREQUENCY - Daily
label | e8083ba2-ffef-5f98-ba09-1bd2c3639050 |  | note | ACCEPTANCE CRITERIA - No fog, rain or wet surface. Base temp ≥ 5o C
label | a78ce373-faee-5ba9-90ec-cd2f98bcd2d3 |  | note | TYPE - Inprocess Testing
label | b2aaea26-2d83-54f1-a29b-2902b14905da |  | note | RECORDS - AC check sheet
label | 02a31ebb-c3ae-5e1b-9637-a7faea1d5620 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 41 - PMB AC14
label | 2a7c85c3-8d4a-5b67-b4aa-ae7f4921aa78 |  | note | ACTIVITY DESCRIPTION - PMB AC14
label | c0ad877a-0e59-5bc2-b9f0-3e0fdd398853 |  | note | VERIFICATION ACTIVITY - Ensure previous layer is broomed clean
label | 979a5bb5-afcf-5377-9300-16ecf040e847 |  | note | METHODS OR REFERENCE - Visual
label | 48c36c3c-37b2-52e2-b9aa-6ae8b3473648 |  | note | FREQUENCY - Prior to starting
label | c4716437-d4cb-56e0-ba80-91fd96dbc366 |  | note | ACCEPTANCE CRITERIA - Free of detritus and loose material
label | 2420a03e-986c-5b22-a1b4-46e89d10d8b4 |  | note | TYPE - Inprocess Testing
label | e50cd3b7-9dff-5ba2-b3a3-979620ab7708 |  | note | RECORDS - AC check sheet
label | 20baa21b-702b-5e79-b205-7ab7118bc76f |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 42 - PMB AC14
label | 73d6930b-eea8-58a0-8d62-d1eabc936395 |  | note | ACTIVITY DESCRIPTION - PMB AC14
label | d80dc83c-7c60-58b5-918d-dc73f7953f57 |  | note | VERIFICATION ACTIVITY - Production tests
label | 156142d2-cb85-5dd9-8b91-0283c40cacac |  | note | METHODS OR REFERENCE - Grading, binder content, max density, temp
label | 361c7302-5675-5f53-924e-b76b1ffcd769 |  | note | FREQUENCY - 1/300t
label | d5a97775-fd26-5d5c-92c7-8fb2ee1d36cc |  | note | ACCEPTANCE CRITERIA - NZTA M/10
label | fd29a0e5-eeef-58d9-9611-4983a3ae0313 |  | note | TYPE - Inprocess Testing
label | cb1fad01-c9e8-5b94-bc16-a1a9aaf3b7ad |  | note | RECORDS - Lab test
label | 8b8dd48d-8330-5d2c-8ac6-5097bb4a0df6 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 43 - PMB AC14
label | 56c1d178-5d13-55e6-b9b0-a3ddc577a368 |  | note | ACTIVITY DESCRIPTION - PMB AC14
label | fb209df9-076a-537e-aa85-39e95acd73c8 |  | note | VERIFICATION ACTIVITY - Surface finish inspection
label | 30c784cd-0538-5439-95b1-5e630b8f1950 |  | note | METHODS OR REFERENCE - Visual inspection by the Engineer
label | fee720a0-0df0-503e-9949-47f486201aa2 |  | note | FREQUENCY - Each lot
label | 9c47f145-c4c5-59de-a641-e62eab307239 |  | note | ACCEPTANCE CRITERIA - Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
label | c849c1de-50e4-5b30-bf46-0460361acc81 |  | note | TYPE - Inprocess Testing
label | e7432b47-b29c-52ae-83a3-e3f6c6135ef4 |  | note | RECORDS - Inspection sheet
label | e7d49f9c-31d8-5750-9dc0-c557e0090e77 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 44 - PMB AC14
label | 9ba4bc27-afbf-577b-ae7b-29ceff2c3aee |  | note | ACTIVITY DESCRIPTION - PMB AC14
label | 1c6b24de-27c3-5abc-854e-bbdc531e641d |  | note | VERIFICATION ACTIVITY - Plateau Testing
label | ac513f18-11dd-5fc1-8547-1c0980c0a0e9 |  | note | METHODS OR REFERENCE - Plateau Testing of PMB AC14 hand-laid areas in accordance with NZTA M/10
label | 34f072cf-20b2-5773-ae6d-e290bb994428 |  | note | FREQUENCY - Once for a hand laid area
label | ba8ec917-eead-5c3c-a6f6-f47b3c9acc90 |  | note | ACCEPTANCE CRITERIA - Plateau testing undertaken in hand laid area to determine the maximum achievable air voids target for NDM compliance
label | 6a3b5aac-eb9d-50b8-b952-ef15bd857f48 |  | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
label | 988a2d1f-6f5a-526b-8a92-48b91a392e5b |  | note | RECORDS - IANZ Lab results
label | 953b2697-2223-5798-919b-2b50ba0a44cb |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-status |  |  | checkpoint | 45 - PMB AC14
label | f0b712ca-333b-5f37-b04e-adc002e769cd |  | note | ACTIVITY DESCRIPTION - PMB AC14
label | a941d962-59c4-5f9e-a49f-e30a110eb03a |  | note | VERIFICATION ACTIVITY - Density testing
label | a33b97f5-c679-51fe-8a37-84ab46d66e74 |  | note | METHODS OR REFERENCE - NDM
label | 0abf9fc6-ace7-59c9-9cb6-58cb71cb9513 |  | note | FREQUENCY - 1/10m staggered between wheel paths in each lane.
label | 642ef2b5-0def-5ea6-a974-0bc36f92a671 |  | note | ACCEPTANCE CRITERIA - Paved Area: Air voids (2.2% - 7.2%), in accordance with NZTA M/10 (2020) Hand Laid Area: Within 2% of the plateau air voids
label | 51e310df-4a6f-5563-9c04-f1433e980d37 |  | note | TYPE - Mandatory HOLD POINT Auckland Transport Sign Off Required
label | d8d2f28c-217c-585e-b02a-41d57a72ed9c |  | note | RECORDS - Inspection sheet
label | a2fd4ec8-eee8-5d52-9756-778f09bd4707 |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-status |  |  | checkpoint | 46 - PMB AC14
label | 8d6553c1-091a-5467-a66e-5a7bb0f45408 |  | note | ACTIVITY DESCRIPTION - PMB AC14
label | 88405121-5d86-5da6-8de6-df21ab14bc12 |  | note | VERIFICATION ACTIVITY - As-built layer
label | a5a5d766-d617-52d7-9311-08ae82db248f |  | note | METHODS OR REFERENCE - Stringline
label | 368eeb49-214d-5c4e-8b48-921b0fe423fd |  | note | FREQUENCY - Each lot
label | afadf1d6-9dc6-589b-8bb5-ba237721eccc |  | note | ACCEPTANCE CRITERIA - 60mm to 100mm lifts for undercut areas and 75mm overlay over the raised intersection area, based on the design drawings. Slope of ramp to be 1:20, as per design drawings.
label | 1b7c5367-8121-5a59-a017-e927b910a3bd |  | note | TYPE - Inprocess Testing
label | 9f5800a7-0671-5488-8e74-c4d64963ff3e |  | note | RECORDS - As-built drawings & stringline measures
label | 2624d96a-e204-50a2-8456-661e941c40e3 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 47 - Joint Inspection
label | d9830bcf-bd92-506e-8a38-da66b15191a3 |  | note | ACTIVITY DESCRIPTION - Joint Inspection
label | d00c9bef-3d1c-5401-a6c1-4dc7c4afbe17 |  | note | VERIFICATION ACTIVITY - Visual
label | 9d8bbe1c-3b6f-5f06-b9e3-87f7180c0358 |  | note | METHODS OR REFERENCE - Design Report
label | c3b680ba-fe39-5efa-a90c-2b22b2cf2174 |  | note | FREQUENCY - Each Subsection
label | c80dbd76-9180-5ea7-bab7-38856c79e26a |  | note | ACCEPTANCE CRITERIA - Transverse layer joints to be offset by 500mm and longitudinal layer joints to be offset by 150mm, as per the design drawings.
label | a7038b4c-8ec7-5eac-b819-5a9c1b1523eb |  | note | TYPE - Mandatory HOLD POINT Auckland Transport Sign Off Required
label | 1d678fe6-ad92-539c-86ea-a59eb750e800 |  | note | RECORDS - Site Records
label | 2b088864-2674-5421-90c9-470b5187d415 |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-group |  |  | section | Asphalt Surfacing
checkpoint-status |  |  | checkpoint | 48 - Shape of road
label | ed2d119b-1370-563a-b51e-b20411d710a1 |  | note | ACTIVITY DESCRIPTION - Shape of road
label | cdce96bd-eba4-5691-acf5-ea7fbba5703c |  | note | VERIFICATION ACTIVITY - 3m straight edge
label | 95c498ca-5b84-5532-a7c2-aebdcadb8ee7 |  | note | METHODS OR REFERENCE - NZTA M/10 spec
label | 2bc248b5-e93b-5d6d-a462-221fae0a25ff |  | note | FREQUENCY - At joints and any other areas of concern
label | 0b6ec332-a23a-563b-a1f3-3643600597d3 |  | note | ACCEPTANCE CRITERIA - Irregularities < 5mm under straight edge
label | 495fa7e1-5f48-517e-b849-07c9d739f594 |  | note | TYPE - Inprocess Inspection
label | 2e8dd431-1fdb-5d7b-8649-ee65ca65fff3 |  | note | RECORDS - Check sheet
label | 3b248349-a2c7-5c18-836a-b56cf3789401 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 49 - Temperature Limitations
label | 9310f4af-041f-5e28-9dc3-a232656f131a |  | note | ACTIVITY DESCRIPTION - Temperature Limitations
label | 8aacb685-0b8c-5403-9565-2fdffff0b1f3 |  | note | VERIFICATION ACTIVITY - Temperature
label | ef1528e1-7dce-5ef8-b7d5-83df6a8a3f6e |  | note | METHODS OR REFERENCE - Contract Spec / M10 Spec
label | 24fe952a-2fcc-50cc-9e6a-ebc0be3ac4e4 |  | note | FREQUENCY - Every Site
label | 48934214-fd00-5f93-8b06-f92e5917eb35 |  | note | ACCEPTANCE CRITERIA - Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 10 Degrees Celsius
label | 370ddf82-99bf-5e01-ad72-a9f099d5925e |  | note | TYPE - Inprocess Inspection
label | 8b7d5076-2924-53d0-88cc-603326344925 |  | note | RECORDS - Asphalt QA
label | a8da6a82-5429-506f-9731-6c8f73985a3b |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 50 - Surface Preparation
label | fefc662e-cefa-5db5-90cd-8cd920bab1c9 |  | note | ACTIVITY DESCRIPTION - Surface Preparation
label | 16b11dac-e418-5447-a064-7cb781815a83 |  | note | VERIFICATION ACTIVITY - Visual
label | d9b25a6f-ee67-52e5-8056-943ab87424bd |  | note | METHODS OR REFERENCE - NZTA M/10 spec
label | 4227a9ec-bd46-5e00-9021-a5f47d3be552 |  | note | FREQUENCY - Every Site
label | 3994d4d5-df98-5795-86d1-e8048ee1a5db |  | note | ACCEPTANCE CRITERIA - Swept clean; all necessary measures to prevent ponding prior to any surfacing
label | 7d9955a8-eb0d-5f70-9f65-1885db8a740d |  | note | TYPE - Inprocess Inspection
label | 7eed7f1f-1717-58e6-a35d-43ff11bcab6e |  | note | RECORDS - Visual
label | 8364a6a5-c911-584f-b210-d345fc52cbde |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 51 - Joint Placement
label | 4da82245-b644-5cab-940b-396e9e9f69fe |  | note | ACTIVITY DESCRIPTION - Joint Placement
label | e1e8a8f4-d4b7-5422-87dd-eb05abbdc110 |  | note | VERIFICATION ACTIVITY - Paving Plan
label | 348e28e6-3818-5260-9ea5-b0665a83cd0a |  | note | FREQUENCY - Every Site
label | 784f7a0e-7b3e-512a-9349-8b3c0d5adc89 |  | note | ACCEPTANCE CRITERIA - Paving Plan to be completed for every site with dimensions. Joint sealing shall be applied between new and existing surfacing. Joints off-set 150mm longitudinally, and 500mm transversely, as per the design drawings.
label | a804db0c-34d3-5b34-8450-50725c03219a |  | note | TYPE - Inprocess Inspection
label | 6ac9cc33-1014-5776-9152-552355e0e0c7 |  | note | RECORDS - Nil
label | d75b1e75-80c5-5684-b133-e8e719b2a933 |  | note | On Site Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 52 - PMB AC14 - Layer thickness - 40mm compacted depth
label | e04ea6fc-e256-5bee-b415-325b78efac88 |  | note | ACTIVITY DESCRIPTION - PMB AC14 - Layer thickness - 40mm compacted depth
label | 48370b6c-3aef-5d51-8010-3676b5bfef34 |  | note | VERIFICATION ACTIVITY - In Situ
label | 0f76cd33-4aa9-5f46-ad4e-95bfdd39987d |  | note | METHODS OR REFERENCE - Contract Spec / NZTA M10 Spec
label | c15c703b-e839-5b8b-843e-15eec15c5854 |  | note | FREQUENCY - Continuous
label | affd5c56-acf1-5c6d-b341-121a1aeaf7ec |  | note | ACCEPTANCE CRITERIA - 40 mm minimum and 45 mm maximum compacted depth
label | 473f2ba9-ee87-5d21-bfdf-e162ebf01044 |  | note | TYPE - Mandatory HOLD POINT Auckland Transport Sign Off Required
label | 5f1bc6cf-a715-587c-ae91-a0ce0299f69f |  | note | RECORDS - Asphalt QA
label | 85905d5b-fd31-585c-8242-34ec95a2d9c7 |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-status |  |  | checkpoint | 53 - PMB AC14
label | 87dae3d4-a4bc-5a48-8c45-dc8cd4a370b4 |  | note | ACTIVITY DESCRIPTION - PMB AC14
label | 3dedb12e-322b-5e48-9901-2b7ee3f3966b |  | note | VERIFICATION ACTIVITY - Density testing
label | 5e68bfbc-3071-59d1-87f1-83b01c7b79a0 |  | note | METHODS OR REFERENCE - NDM
label | 126587ef-24ee-5e40-adad-e5eabf2a270a |  | note | FREQUENCY - 1/10m staggered between wheel paths in each lane.
label | ec41375b-a5ae-50ff-80f3-63acbe0b63ce |  | note | ACCEPTANCE CRITERIA - NZTA M/10
label | 6cec7123-51f7-5e02-96fe-1a3aa32eda01 |  | note | TYPE - Mandatory HOLD POINT Auckland Transport Sign Off Required
label | 5078e1dc-f8e8-5baa-a88b-47b6c4de07a6 |  | note | RECORDS - RFI response
label | 82b13bc1-4187-5770-a0fa-347c72549165 |  | note | On Site Responsibility - Project Engineer
holdpoint |  |  | signoff | Mandatory HOLD POINT
checkpoint-status |  |  | checkpoint | 54 - Reinstatement of Linemarking and RRPM's
label | 19eb69db-5756-5999-9fd3-9dc9a2b43964 |  | note | ACTIVITY DESCRIPTION - Reinstatement of Linemarking and RRPM's
label | 308e71b0-0715-56d3-a077-7443acc4a5fb |  | note | VERIFICATION ACTIVITY - Visual
label | c038f634-f6bf-5f0a-a13f-511d6afd4f4f |  | note | METHODS OR REFERENCE - NZTA M7 approved (Class B or C as required for anticipated traffic level)
label | 74c20a98-366b-5446-9cbf-2d0157c3134a |  | note | FREQUENCY - Every site
label | 6d922c12-9ba6-5aeb-b8ec-199b73c30498 |  | note | ACCEPTANCE CRITERIA - *Carried out within 12 hours of each shift completed and as per the existing markings * Suitable Traffic Control to remain in place until pavement markings have been reinstated
label | a5f0775e-2576-53f3-a5f0-24bf7fdfdbaa |  | note | TYPE - Inprocess Inspection
label | 64e8e07d-755c-5078-93d4-a8bcbc047572 |  | note | RECORDS - Linemarking Records
label | fe11e12f-e138-55aa-bed2-7137ccb58031 |  | note | On Site Responsibility - Project Engineer
checklist-sectioned |  |  | checklist | ITP - St Lukes Road/Morningside Drive intersection - Traffic Islands |  |  |  |  | Yes | ITP - St Lukes Road/Morningside Drive intersection - Traffic Islands | 95a5edbe-bdc8-4d84-af64-42178e0cf019
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 1 - Mountable Kerb
label | 79509ee2-9992-5080-95a1-907ecd75694d |  | note | VERIFICATION ACTIVITY - QA FORM
label | 3602ea0e-9ef8-53a9-9eac-a72e641a2bf0 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | c9d1d70c-bf93-59eb-98e6-38c9bf6a58d9 |  | note | FREQUENCY - Everysite
label | 94aa37df-99e5-576e-9c64-9bc1eb19b8ef |  | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
label | aaebfe9a-f55d-5647-a2e1-bf1f007859d9 |  | note | Hold Point - Inprocess Inspection - Engineer to check kerb stringline before laying
label | 730c90b1-7485-5e90-9f07-8c214fdeba91 |  | note | Records - FH concrete QA sheet, photos.
label | 9b7e2630-30f4-5190-9157-fffb9372b3c5 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 2e7db3d3-7814-5a50-b38a-416ed385fc90 |  | note | VERIFICATION ACTIVITY - Survey
label | 95f8b96c-d70b-5471-99c3-2f2fc68021b7 |  | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
label | d4b55126-122e-54be-a806-21034e672beb |  | note | FREQUENCY - Prior to commencement.
label | d0ec2e42-0dad-53b4-ab5d-45b65dd894b0 |  | note | ACCEPTANCE CRITERIA - Survey
label | 75443599-c0b1-5b86-85b5-1de4cb8c3252 |  | note | Hold Point - As per Construction Drawings
label | 6626cc67-0344-5547-819a-b4ec4ce93ae3 |  | note | Records - Survey Receipt.
label | e519d6fc-90c4-5625-8484-ca2a05f1cd85 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Concrete Island
label | 286affee-7fbf-5888-b545-864fee92c437 |  | note | VERIFICATION ACTIVITY - QA FORM
label | e40e4b9c-fc71-542c-9647-1cb869d8a408 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | 1dcd3e4a-77c6-555c-af7a-ea12b1baf50f |  | note | FREQUENCY - Each Site
label | a0251d64-0393-5bea-a716-2238774e67ad |  | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete
label | 3c970695-aa2d-51c2-9c03-1a6d45e6854d |  | note | Hold Point - Inprocess Inspection
label | f0b8de19-b198-5f55-bbc2-b832a69c982b |  | note | Records - Photos
label | 619a0e3a-a3eb-5ae4-818f-bd72fb8724bd |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3.1 -
label | 18f55fb2-aa0e-53b3-b05b-03abbbf26614 |  | note | VERIFICATION ACTIVITY - QA FORM
label | e963e0d0-792c-51ae-a37b-19ff10654ec8 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0003
label | 09b0b187-e57f-5000-8cc2-b02dc84ae33c |  | note | FREQUENCY - Each Site
label | 3887ef26-29d1-5dbc-a571-4060571eb320 |  | note | ACCEPTANCE CRITERIA - Basecourse to be 150mm min thickness of GAP65
label | d7df43de-59d8-5125-a6b1-d9ac672b51e5 |  | note | Hold Point - Inprocess Inspection
label | 07eae6eb-6038-5136-8aa5-73eb4409083f |  | note | Records - Photos
label | f1ed8115-436c-5cbc-bcb4-1b36bb8ceae5 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4 - Concrete Infil
label | dc18fc34-884f-59b6-90bb-3623ecd85405 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 18b8e3b8-ba7c-5036-9b8d-17a487828fef |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | e7a98d69-8265-58e5-95fe-6ac24118d4ec |  | note | FREQUENCY - Each Site
label | f76df45e-b219-5b14-bad6-39030ac6776a |  | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa Broom finish, unreinforced Concrete with 6kg/m3 Red oxide Cross Fall of 2% or max rise in centre of 180mm
label | 31fe5456-aea6-5147-8d68-c88df289eb4e |  | note | Hold Point - Inprocess Inspection
label | 0a45d5f3-cd67-5ec3-a6cf-6df5181f6d1d |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 69bfb2af-be34-5321-a558-5f791bf28f51 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 5 - As built information
label | 2ee5eddc-52fb-5a9b-b1ca-746f8bbd450c |  | note | VERIFICATION ACTIVITY - Drawings
label | c0db60f3-7796-53dd-997e-19c98e33daf7 |  | note | FREQUENCY - Every Site
label | 9e11fc4e-9ca1-5e9e-be5e-b3c134676ca0 |  | note | ACCEPTANCE CRITERIA - As built drawings
label | 9407cab5-f376-5c3d-b329-2f8493c0706b |  | note | Hold Point - In Process Inspection
label | aa9f5964-32bd-51dc-90ee-5fb9bd05f644 |  | note | Records - Asbuilt records
label | 26b4dc9a-afc2-5270-b766-270414ec5115 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | 6 - RAMM DATA
label | 4ed14ebd-905e-5026-801e-def4d49d1e12 |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | 28f985bd-7c76-5a30-af99-14a5099ba274 |  | note | FREQUENCY - Every Site
label | 433a0e2e-c73a-53dd-8b64-256bd0b859d1 |  | note | ACCEPTANCE CRITERIA - RAMM SHEET
label | d712ddad-76e5-5228-8d7e-63afe95676f0 |  | note | Hold Point - In Process Inspection
label | bbb2d025-167f-564d-912b-80c59b454ff3 |  | note | Records - Asbuilt records
label | 20ec48ef-b6c3-5b0a-ba21-27465a70a18c |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-flat |  |  | checklist | Raised Speed Table |  |  |  |  | Yes | Sheehan Ave - ITP - Raised Speed Table | 96ac93e1-8978-4948-8d52-c81c3563cc2a
checkpoint-status |  |  | checkpoint | 1 - Permits
label | eb353c99-b79f-53e9-8372-f53c4e530f9f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8b0fbe2b-c5fa-5958-844f-41481128a0ea |  | note | Detail - Obtain Permits
label | 5722a16d-5cb0-55d0-852b-9ee4046e61e4 |  | note | Frequency - As required
label | 4c00a638-4cc6-51e3-9011-72eb8977bf0d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 07e22cd5-1626-51ee-a123-eb5bab3cfe42 |  | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 60fff5d0-a63a-5fa4-b489-86fcac351aa7 |  | note | Records - Permit attached or permit number noted
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-construction sign offs
label | f7b8f8d5-d020-5dde-913b-959f2f4efbfa |  | note | ACTION (Hold, Monitor, Witness) - H
label | 77e88c12-aa2c-54ea-95e7-b6e6d2c3a633 |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
label | 420e1703-7176-5955-917d-59d8034dbbb6 |  | note | Frequency - Prior to commencement
label | 316de513-ca26-5f08-9f18-86fbcd5dc222 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | fdda940f-d38b-5932-a788-08e2c35469d1 |  | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
label | 16e3b644-c278-5f33-92f2-d55657d53663 |  | note | Records - Subcontract and Supplier Agreements
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1 -
label | 5bdd831f-f788-5cf4-afa6-9dfcd9c3426f |  | note | ACTION (Hold, Monitor, Witness) - H
label | a1b157cc-087c-5a45-9b69-67dd1a600347 |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | f9651d82-09a1-5830-bc72-0fc233686527 |  | note | Frequency - Prior to commencement
label | 5094ad6f-9f99-5c50-869e-ced636e424ee |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 680120c9-896b-54d3-9eda-1afd18def524 |  | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | 4be9bbf6-0c8d-523f-b4cb-aaedc8c28965 |  | note | Records - TMP on MyWorksites/On Site
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 -
label | 50bd5eba-9021-53c8-97cb-04e4d7f6cb34 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2428ebdb-20e6-5f31-9222-57159cfff580 |  | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
label | 8a2c7869-5f0b-5392-9da3-8b314b5ed13c |  | note | Frequency - On site daily
label | 09d22ac4-7c37-572d-979f-dd146c426aa0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Induction
label | 0ece3c94-cd43-5739-acb7-c11bd92be9a7 |  | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | 9066934a-ade9-5c5b-9413-05d06e29b808 |  | note | Records - Hazard ID and Pre-starts to safety team
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | ee2fcab3-e72a-5807-9762-2071323964fc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7c8219a3-c3ee-575e-9210-a3fe58f59c78 |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 1c8c184c-42b2-539d-b1de-55820438c2f9 |  | note | Frequency - Prior to commencement
label | c45971f7-25e0-5fb1-a17b-f1924c2141a2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | c7fc1f86-a821-5997-8a91-adec90a957b7 |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | fca7ca7c-f5a2-5f7e-a536-1235500a92e4 |  | note | Records - Check Drawing Register
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Installation of Erosion and Sediment Controls
label | 0bcfd015-1f45-5e5d-a4cd-f93e7e03c059 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 60e4fc2b-335d-52c6-8efa-1f46a715bc8f |  | note | Detail - Ensure that Erosion & Sediment Control in place
label | 8476e748-4967-57d7-a702-68f1c01fe5b8 |  | note | Frequency - Prior to commencement
label | 5a3be1de-0858-50ce-91ee-10ef8ea40af3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 23651467-32fa-5f50-9ac5-b4d5b13411b8 |  | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | b1ae53fa-a298-51c7-a2c7-d837e1ddbd36 |  | note | Records - Environmental Controls Audit
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | a0290439-103d-5cd3-8978-6e11e191334e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 689f3de1-5c3c-59b4-b416-687b42fe359a |  | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | bcaa693e-dab6-5184-9303-7d634432db02 |  | note | Frequency - Prior to commencement
label | 53c3c73e-1751-59d0-bd1e-bb56c0e79d9c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey + Smart Level
label | c71ae9bb-2aa6-5b30-a051-007ff81b86a6 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 58445448-204b-5932-be79-f8b53de9a633 |  | note | Records - Site Photos post surveying
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging
label | 2fbc3663-7938-5d26-908a-d15e3ffb42c8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2096601e-8b76-5dbf-9704-f27b83b7e8ed |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | abab33d3-a40f-524e-b860-72cacbd25e80 |  | note | Frequency - Prior to commencement
label | d2b1a41b-28bc-5950-8857-e081cbcd2b23 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | 11f56dc7-d223-5999-8528-e3c9b4b1e71d |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | 51be112e-50f4-5295-8019-5543670ebd2b |  | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Material Compliance
label | 485f5cb3-d713-5a23-b758-59c8aacbd9da |  | note | ACTION (Hold, Monitor, Witness) - H
label | 70b640b8-0580-551c-adf0-92e7535d44c2 |  | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
label | 93d81f7f-aa15-558e-a62d-8610ce70383d |  | note | Frequency - Prior to pouring concrete
label | 807d4275-ba18-5077-b671-5aeb91957b38 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | a4f89933-f739-5ab6-a699-9fec9ebceb33 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | e35e1ea4-3b87-5650-b217-4d2d4a6cb37b |  | note | Records - Delivery Dockets / Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1 -
label | e49c7070-449a-5245-992e-7eb1073ec0ee |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1b7718fe-cb88-5d6e-a721-aa448cfc10df |  | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
label | a7c5c65e-4f51-51c0-a056-3b32e4f4deb3 |  | note | Frequency - Prior to pouring concrete
label | 005b9f89-df65-55a1-adba-aecdf7a4adf5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
label | 636ee06a-7ea7-56fc-99cf-5245e14ab933 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 63c090a7-025a-5061-a207-6eb82817167f |  | note | Records - Delivery Dockets / Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 -
label | 302c6591-44b7-598a-9e42-ee917079f369 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c169ff04-8e56-564b-8f31-5e9cc5b145bf |  | note | Detail - 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | 03894d99-773e-52b1-b122-b8405ff4b098 |  | note | Frequency - Prior to pouring concrete
label | 713fab28-ee60-50fd-8c7e-2e9adaef651e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d1efa73a-98cf-50ac-8a8b-20400b296af2 |  | note | Conformance Criteria - CIV >15
label | 56f34088-0233-5d63-be43-0256b59d88a0 |  | note | Records - Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 -
label | 0c6c055c-4eff-59c5-9669-98a28069f465 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 32bc91a0-2921-5294-8643-b1368ee131ae |  | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
label | 640d71a2-002a-5e35-b0a9-d54b83d27fe1 |  | note | Frequency - Prior to pouring concrete
label | cb9ac078-b717-56c5-8a38-865a92fd2967 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 012e7a33-4996-59fc-8d4c-f8a5bd9abc5c |  | note | Conformance Criteria - Photos
label | 37cee42f-80e0-52eb-a5dc-0c50835005ef |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.4 -
label | ec3978f3-d249-5c5b-ac64-9af0e277b38f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2e061309-06a0-5890-a2b8-14b5f1074a1b |  | note | Detail - All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
label | d7ed725f-3041-5641-a6e6-6fb664c3eecf |  | note | Frequency - Prior to pouring concrete
label | 18ef0795-4d1d-5d15-9592-0d0f73fb949e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
label | 6c59fb44-6268-53f0-aa57-7331d769a34e |  | note | Conformance Criteria - Delivery Docket added to QA folder
label | 200379a3-337f-5556-8e2a-8a25535c0b36 |  | note | Records - Concrete Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Temporary Works (Formwork)
label | 4986958f-2726-5fa9-aa76-0d6567c42e5c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9ed30b2e-8c28-53d8-b79c-95cfa16efaa6 |  | note | Detail - Formwork to be set to correct line and level
label | 1fd52606-1279-5971-bbcc-5da278b65b0c |  | note | Frequency - Prior to pouring concrete
label | fb063cb4-1186-51bb-87fc-03897a3335f0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | e2877f10-0d00-5ab8-be45-f96b94d8c77e |  | note | Conformance Criteria - Concrete Inspection Record
label | f018bc91-36a1-530d-8112-5be280c4c915 |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 8.1 -
label | 8f402bca-2813-5e9a-929a-8161f250f734 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 417cfeaa-064e-5480-9250-4b7590ae2ed1 |  | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:15)
label | cc09e993-a7d8-5274-b430-6d9c0f7489b2 |  | note | Frequency - Prior to pouring concrete
label | 160486a0-54f0-5394-a2db-b2ea70e96daa |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 065228ce-014c-5e5b-91c0-f8df382d588d |  | note | Conformance Criteria - Designer to inspect formation level
label | b7fae449-a98c-5c68-ba0c-53c31dd44c83 |  | note | Records - Site photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2 -
label | 870adcd9-0590-52d6-a738-4e92576a0409 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 27a7b9fa-6706-5bab-bf5d-7e0d48f4ddd5 |  | note | Detail - Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table
label | f463e475-fcc7-5add-a803-26ba3182e4c1 |  | note | Frequency - Prior to pouring concrete
label | 9f95f583-457b-5bc0-bd2f-4795cda13bae |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 74c43a30-a90c-567e-828f-b07c7e936cfd |  | note | Conformance Criteria - Designer to inspect formation level
label | ac69172d-41b2-5259-9f12-1672ab01ff43 |  | note | Records - Site photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.3 -
label | c959049c-fde7-5827-99d4-4c0476ce8150 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7735c2eb-ee1d-5d8c-91dd-3411503d7472 |  | note | Detail - Raised Table ramps to be 1.125m across for entry and 1.125m for departure ramp.Toe to be 0.5m to 1m across for both entry and departure with 50mm asphaltic wearing course
label | 2387bdba-5bb0-59e3-bdb0-5ffc64d56aa0 |  | note | Frequency - Prior to pouring concrete
label | d7ffd7fe-96aa-55d3-8e43-962dc86c9a1f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 00607f3b-7add-5d0c-b354-adc4cb49ffa6 |  | note | Conformance Criteria - Designer to inspect formation level
label | 62c6c662-e66e-5620-bf32-d2ef4c51ccae |  | note | Records - Site photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4 -
label | 1dacbc18-0aa8-5ad1-bbd6-d5c351f8bc23 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 06d5e058-99be-537d-916b-f5c0f9831a73 |  | note | Detail - Raised Table ramps to be 1:10 gradient for ramps at entry and exit ramps to be 1:10 relative to the road
label | dd7610af-ee2c-58cf-bbdb-6b2cfaec60ca |  | note | Frequency - Prior to pouring concrete
label | 87103b25-8b32-5599-8bb9-f37f649a204e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | a9df64c5-e5c2-5c85-9229-49be131bf352 |  | note | Conformance Criteria - Designer to inspect gradient level
label | e99fda58-9bd2-531c-86a2-86915e76d727 |  | note | Records - Site photos / Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5 -
label | cf396161-d014-5dc1-b356-5b38d04dde65 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 73a1ad95-98bc-5a40-aacd-e88f29944312 |  | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | 75f59b6d-906f-5462-9329-59cd9005e0f9 |  | note | Frequency - Prior to concrete pour
label | d4226173-49a7-5bbd-9f71-b051e92dd48c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 30ec5ada-4872-5781-a896-38e1ad829f7f |  | note | Conformance Criteria - Concrete Inspection Record
label | 254b0b43-1095-558e-972e-ca7d57fabfbb |  | note | Records - Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Reinforcing
label | 3b6ee58c-729b-575c-90e1-2f2b82b0abec |  | note | ACTION (Hold, Monitor, Witness) - H
label | 46f71afe-9193-5415-8b1c-9a4e953e87e6 |  | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @600mm centres placed across the construction joint
label | 80ab89e5-1f3c-58bb-910b-36a7b4ba2e1d |  | note | Frequency - Prior to pouring concrete
label | 2a3d7ab4-ad87-5805-8bcd-aff571155512 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 56fcd899-1cdd-5e8d-8775-4f6accc268ae |  | note | Conformance Criteria - Concrete Inspection Record
label | 3dc72349-dc3f-564e-81b6-f0382e9da733 |  | note | Records - Site photos/Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Concreting
label | 6c36ddfb-de8f-569a-96c8-2fdd81bbdc58 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b9578acc-8363-5f1f-ad3f-b62aa3c58a44 |  | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | 71879ea3-476e-57f3-b13d-770835ae2e66 |  | note | Frequency - Prior to concrete pour
label | 9b066fd6-292c-5843-ba1a-78379a922a59 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 27df3622-f7bb-5fe0-a83b-99db6327dddf |  | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | dcfec44c-1786-513c-895c-2b1487c55478 |  | note | Records - Email / SMS
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1 -
label | ef32e2bd-1be1-5c48-a6e2-efc9ab21e7ae |  | note | ACTION (Hold, Monitor, Witness) - W
label | b46c2efa-03f0-5bc1-84d3-137efa622416 |  | note | Detail - Vibrator to be used throughout concrete pour
label | 3fc17083-78a2-5365-901e-81667a0bdc9c |  | note | Frequency - When pouring concrete
label | 53169be6-60df-587f-898d-5be32868b702 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 0a3b6d1e-6dc3-5b74-a3ab-4167d75f7fcd |  | note | Conformance Criteria - Concrete Inspection Record
label | d5d5d152-53bf-5d0b-bc94-79b9390c6bda |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 10.2 -
label | 7e5b93cd-c260-5805-b7bc-1ee093a3e591 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 267af595-37da-57c9-8f1a-d4d5f0be45db |  | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
label | e315b397-f7e0-5e8e-9c4c-164c15e38774 |  | note | Frequency - At completion of pour
label | dd686742-c28b-5662-8d0b-92915acf38d4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | ee407f88-59e9-54f6-a370-9c3c382bbb0e |  | note | Conformance Criteria - Concrete Inspection Record
label | 88c8f855-8561-554c-8050-77fa4745d3d3 |  | note | Records - Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Curing
label | 94dacb7a-b156-5419-bd9c-24eefd3ce719 |  | note | ACTION (Hold, Monitor, Witness) - M
label | b45a0cab-8278-53f4-a325-be2fa35cece2 |  | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | 87f4be58-d0a3-5541-af6c-ac3c1db90716 |  | note | Frequency - Post Pour
label | 58b14dcd-adf4-5487-9d0e-1f58252330f4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Monitoring the time allowed for curing
label | c2e157fd-081b-575d-b02e-dad5de41aabe |  | note | Conformance Criteria - 48 hours minimum have passed
label | b9534dd2-199d-52c4-9333-34a27c0345cc |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 12 - Remove formwork
label | a556e20f-501a-5454-a902-c662ba3f0f1b |  | note | ACTION (Hold, Monitor, Witness) - W
label | fa1e5768-bd21-5ba4-a774-d6f9d7b8f67f |  | note | Detail - Remove formwork after 48 hours
label | 716e3c96-9fb6-51f1-a9c2-0e2e5d5ae689 |  | note | Frequency - Post Curing
label | 1c146922-3e16-5834-b6e1-94803acd724b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | ef5db697-5156-522b-a698-468f282fae61 |  | note | Conformance Criteria - Concrete Inspection Record
label | 083a30ab-9709-55da-8d6f-7e99c5b65b26 |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
label | 7aa906b3-50ee-5b7b-9613-ed97099d2020 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c41ddf57-475d-5c8e-a700-6224a971c041 |  | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC0022
label | 3ce763e6-51e8-5b78-8894-efacdfbb7088 |  | note | Frequency - Prior to pouring concrete
label | 7601d627-2d13-5af4-84a3-f2dcfafaa85e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 8e72520b-9163-5646-9607-777809c579a9 |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 4490e65d-738c-5ee7-b4a7-8d9d74f683f0 |  | note | Records - Site photos, delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.1 -
label | ccc62176-3f63-5909-9bee-1a96dde4ebf1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | cfef0e9f-2b0e-5ce9-936a-2b3e9e0eff66 |  | note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
label | 58ddd2d7-6909-52ea-b1cc-e2e332e01e95 |  | note | Frequency - Prior to pouring concrete
label | e5350613-88b6-52b1-93ed-edba1210ae05 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | a94f182f-f35d-5660-b791-eacd2a4e3960 |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 74597500-7539-54b9-81c8-6646c5393d01 |  | note | Records - Site photos, delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.2 -
label | 134fba75-4f49-552b-8336-67b1cc305b38 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9c106721-383c-5829-9021-b19d2b8b778e |  | note | Detail - Tack Coat between AC and Concrete slab
label | e7c01fdd-e094-5a75-927d-f91ce573f88c |  | note | Frequency - Post Curing
label | 09b43418-fe8f-5a59-8ffc-d418d44a05e0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 511aaee8-8b4f-5551-a51c-33945b600bb5 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 845ebd63-4a59-5852-b253-9a63a4a876aa |  | note | Records - Site photos
checkpoint-status |  |  | checkpoint | 13.3 -
label | 8e9e6b52-6442-54dc-9b4a-3ff730ec8074 |  | note | ACTION (Hold, Monitor, Witness) - W
label | afafa5f8-1fee-51e4-bdec-80122deb471b |  | note | Detail - 50mm thick DG10 / Mix 7
label | ff9b75dd-9a61-502f-a476-1b27c8da22cd |  | note | Frequency - Post Curing
label | dc27394a-ccbe-5827-b0f1-07808cd7c193 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 8a6141e0-e2e7-530e-849e-cdcf2cc51da0 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 13252ec1-2859-5b17-bb17-b58e8b1c70e5 |  | note | Records - Site photos, delivery dockets
checkpoint-status |  |  | checkpoint | 14 - Lot Number QA File
label | 59a8eca1-0148-5088-b53c-2315038ac121 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2d8b98e1-e8e3-5921-9598-ef5380171ded |  | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | ea70c2e3-9b5c-5d5c-8f28-809c0267d99d |  | note | Frequency - At completion of Lot
label | e06c87ee-0186-587c-8b36-d98e7e8cc312 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | c9aad2f7-ddee-5cc0-b884-454957686ced |  | note | Conformance Criteria - All QA files compiled and sumbitted to client
label | d772611e-3019-5e8a-b256-3f3b3fe58ea0 |  | note | Records - QA records
checkpoint-status |  |  | checkpoint | 14.1 -
label | ab712974-099e-53cb-8e70-6f66be7fa04f |  | note | ACTION (Hold, Monitor, Witness) - W
label | ee32b7f1-6906-5f91-bb72-6e1e594934e2 |  | note | Detail - Delivery Dockets to be included in QA file
label | 02ea7d99-d5cd-55e9-90ee-2a93647772c6 |  | note | Frequency - At completion of Lot
label | 656015b2-3e6c-5b84-b487-dcd2004900e4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 669721fa-467f-5a96-a515-ebe5435f9c05 |  | note | Conformance Criteria - Delivery Dockets to be included in QA file
label | 71fe37e9-8d22-5b05-bb96-26b8ebfdf734 |  | note | Records - QA records
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | b08f14aa-1af7-5671-8e6c-4ffa85fa3ecd |  | note | ACTION (Hold, Monitor, Witness) - H
label | 01e44315-2907-5341-a8ba-b6ed06bea9d8 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 552b17cb-7ad5-5239-819f-c9f8893ebc51 |  | note | Frequency - At the completion of the Lot of work
label | edc3894e-f120-52f0-802c-23d87d6d548f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | a1cc0218-4a51-5a10-8cbf-8916d126d7b3 |  | note | Records - Asbuilt Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Enabling Works - Footpath, Kerb and channel | itp |  |  |  | Yes | White Swan Road - ITP - Enabling Works | 9d455e5b-818c-43a7-b9d1-4d9974122c06
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | 0aae5897-5811-52d6-b99f-29734b66f84c |  | note | Verification Activity: Surveyor
label | b12d1d36-d2af-51f5-b067-2872c23b98e9 |  | note | Methods or Reference: Surveyor
label | a8792956-6eda-575c-924b-50bd998dd41d |  | note | Frequency: Everysite
label | 136d5b3b-ccc8-59aa-ae53-f1f3c0a75ee1 |  | note | Acceptance Criteria: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | ed31d76a-26b3-5395-b763-2711fec7c61b |  | note | Hold Point: Mandatory HOLD POINT -
label | 81f37a40-e143-508f-91ad-1b60c6ac8c93 |  | note | Records: Onsite records/photos
label | 0b323bc5-be2f-5a99-8abd-2df986c8bfc7 |  | note | Onsite Responsibility: Site Engineer
holdpoint |  |  | signoff | Hold Point
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Kerb & Channel
label | 71a1af8a-433d-50b1-9369-b155396a6752 |  | note | Verification Activity: QA FORM
label | 22c42fd2-39f9-52fc-a74b-dcd54b8bc764 |  | note | Methods or Reference: TDM Technical Standards - KC0001
label | 18cc8839-afc7-574d-b088-f36e8d9fcc6e |  | note | Frequency: Everysite
label | 837713d8-7696-5f5d-85de-f8a29087ea85 |  | note | Acceptance Criteria: Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
label | eb28a6bb-cc26-504b-8089-0cdf5023115f |  | note | Hold Point: Inprocess Inspection
label | 03a34348-d5a2-584c-8f2f-3b07c2334b84 |  | note | Records: FH concrete QA sheet, photos. Concrete Plant Docket
label | bfe3f346-c471-528f-b61a-c77e9fc0709f |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Channel Level
label | d69d4120-a636-5ce7-937d-a9cec0137707 |  | note | Verification Activity: QA FORM
label | 416dae5e-1a90-5a87-98e5-a99651599f4c |  | note | Methods or Reference: TDM Technical Standards - KC0001
label | 0b818f4f-6441-52c7-9880-9b4aa9e7138e |  | note | Frequency: Everysite
label | d8d3ab91-1960-595e-8f43-1294dcd08a96 |  | note | Acceptance Criteria: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | 35454415-2d54-52bd-88e5-2f604921a923 |  | note | Hold Point: Inprocess Inspection
label | a2c47a03-6621-5943-855b-caf2a7b36088 |  | note | Records: FH concrete QA sheet
label | ea6af2fa-cc9d-52b3-87ed-801e92407c00 |  | note | Onsite Responsibility: Site Set Out
checkpoint-group |  |  | section | Civil Works
checkpoint-status |  |  | checkpoint | 4 - Concrete Footpaths
label | 5e13389b-535b-54a6-8fb5-ca876101ea05 |  | note | Verification Activity: QA FORM
label | 8326a15a-b381-5074-9596-79bead8726f8 |  | note | Methods or Reference: TDM Technical Standards - FP0001
label | de3281d3-e1f1-5c97-aa1e-6e0bd9db691a |  | note | Frequency: 10m Intervals
label | 6b14b2dd-36f7-55f0-a9bf-32c92d54aa54 |  | note | Acceptance Criteria: Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with EXPOSED finish
label | 58ee572f-6506-50a7-a16e-c809dca08488 |  | note | Hold Point: Inprocess Inspection
label | c86fd46e-0a44-5b14-8744-c74190fe41a9 |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 2f1462db-54fc-5a18-9072-a18ae7923e52 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 5
label | a7471bbe-b80b-5090-b221-b0165c0714aa |  | note | Methods or Reference: TDM Technical Standards - FP0010
label | 82925fcf-36f9-55db-8dcf-4f821988e4fa |  | note | Frequency: Each PX
label | d21e8dd2-0426-552b-9897-222ef0602303 |  | note | Acceptance Criteria: Warning TGSI tiles should have 100mm concrete slab underneath
label | 5a6abe93-0a37-59ab-8594-c8fbd89a5416 |  | note | Hold Point: Inprocess Inspection, Measurement
label | f9a7d82c-08e5-5c98-b543-9b6193780a44 |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | facddef4-97af-5240-8e5f-bcba80e60b08 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6 - Tactiles
label | f5c69796-e779-570c-b87c-74a774d831e7 |  | note | Verification Activity: Visual
label | 04a06c68-b92e-5755-a1bd-5151c2989515 |  | note | Methods or Reference: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 72341d07-de64-57f7-807b-93469053c40a |  | note | Frequency: Everysite
label | 55781b57-ac06-5835-9dcd-6d3ac36f75ec |  | note | Acceptance Criteria: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | dc435dc8-6bba-56a8-988b-65e58dc6bb4b |  | note | Hold Point: Inprocess Inspection
label | 26ffd1d4-6661-5797-bc1f-bee77bdfc59c |  | note | Records: Photos
label | d0793ea9-20ad-5250-82b8-2dd2d6b00c42 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6.1
label | e0c77b29-2196-5e69-9684-dbb5d4a8c3a0 |  | note | Methods or Reference: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | a0d0dc57-6713-58fa-9df2-40b17e62b6f9 |  | note | Frequency: Everysite
label | 6cbeddef-fc0a-5f6b-9b4c-05c8bd19b812 |  | note | Acceptance Criteria: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | 759c0270-b7c6-5735-8b44-e3c983b9e401 |  | note | Hold Point: Inprocess Inspection
label | 6e5b1467-d145-53f3-9646-29580ab85b25 |  | note | Records: Photos
label | 537199b8-1283-545b-b6fc-8a346d15c9e2 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6.2
label | 589af09c-f603-5ad7-97d3-a63afd34b7c0 |  | note | Methods or Reference: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 492b8288-93a5-567d-a2d8-adeebd72e912 |  | note | Frequency: Everysite
label | a3861ca2-14ed-5887-8361-282a6e37e94c |  | note | Acceptance Criteria: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | bcb5da55-0a93-5aed-b7eb-476b6f2d2090 |  | note | Hold Point: Inprocess Inspection
label | 3fc1faad-22c4-5567-82a5-dd4ac52206c8 |  | note | Records: Photos
label | 6e748668-28f0-5f7b-bf8f-05345cc6fb5f |  | note | Onsite Responsibility: Site Engineer
checkpoint-group |  |  | section | RAMM Data
checkpoint-status |  |  | checkpoint | 7 - As built information
label | ef92e8be-8cfc-53df-8f78-100374d1694f |  | note | Verification Activity: RAMM DATA SHEET
label | 60ee0ed4-9da3-5523-a3d1-5f57af753c9d |  | note | Frequency: Every Site
label | 51d8cfb9-e487-5df7-93b5-2009283911ff |  | note | Acceptance Criteria: As built drawings and Ramm Sheets Completed
label | 2a8de693-1eb4-5978-9532-f98dedc917dd |  | note | Hold Point: In Process Inspection
label | 3ad10fd8-a7ea-52ba-9c9b-91bc99a946d5 |  | note | Records: Asbuilt records
label | c5819110-a2a4-5181-9bf0-b186bd615f90 |  | note | Onsite Responsibility: Supervisor and Engineer
checkpoint-no-status |  |  | checkpoint | ITP Approval
label | 025945a9-36ab-56ca-93b0-494536be30de |  | note | Prepared by: Cimyona Vinbi (21/02/22)
label | 14c2f6f3-a240-55b1-9c53-2fee05c736ca |  | note | Approving Delegate: Daniel Tat (15/03/22)
checklist-flat |  |  | checklist | ITP - Great South Rd - Concrete Speedtable | itp |  |  |  | Yes | ITP - Great South Rd - Concrete Speedtable | 9de6de66-3314-4919-aaf1-0f72fc601e0c
checkpoint-status |  |  | checkpoint | 1 - Permits
label | f550ff1f-5636-5bfd-b932-89b6fc3f36e0 |  | note | H
label | 55432e5c-1e49-5c0d-a79d-c3d0f429e448 |  | note | Detail - Obtain Permits
label | da3ca0af-24b6-5009-9e1a-ab006379ddf4 |  | note | Frequency - As required
label | db524c0f-33af-5c43-ab7c-f251798cad17 |  | note | Inspection / Test Method - Document Review
label | 9b7630c2-2d09-5daf-ab2e-41bc86619b68 |  | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 44c8eaa9-a80e-5db9-a77d-c121ab9f2ee5 |  | note | Records - Permit attached or permit number noted
label | e1b20a5e-957e-5cd8-9d38-53bd747be466 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-construction sign offs
label | be18408b-f6d0-55ce-8801-5be60d297841 |  | note | H
label | 7772559b-7c17-54bd-a829-2740251e1bca |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
label | bec1b30b-6ed0-5795-9dd1-8e723eaca179 |  | note | Frequency - Prior to commencement
label | 314e7942-6b62-523c-a798-3c20d09f59dd |  | note | Inspection / Test Method - Document Review
label | 79940248-5602-5717-ac09-0204e75ac143 |  | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
label | 212ed970-bfd4-5add-8561-a07935c76fe4 |  | note | Records - Subcontract and Supplier Agreements
label | b131f942-1eb9-5e7f-8906-10b78b833776 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1 -
label | 502e8ed8-619c-5e55-9694-a183679719b0 |  | note | H
label | 1e7a7476-7ba7-5ddd-8b89-b65184daa2bd |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | b42a1666-13d4-5d42-a5a1-b4e3a1573406 |  | note | Frequency - Prior to commencement
label | b62f6491-8344-5628-a388-0dd4dafd2b2e |  | note | Inspection / Test Method - Document Review
label | 74ecc02c-2e8a-519b-9efd-76d7225b2f1d |  | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | 3b6487f3-1394-5e3b-abff-de3e9c69993c |  | note | Records - TMP on MyWorksites/On Site
label | b7615ef7-67bb-5355-984a-0940c696fe4b |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 -
label | 0f693450-b78f-54dd-bc7c-f6bd9e77b811 |  | note | H
label | b6d854fd-d232-52ec-af3a-5269817379ba |  | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
label | 32a7805d-9f39-55a9-b8d8-41323fb3e9fc |  | note | Frequency - On site daily
label | a0010d4b-a293-53f1-a66e-b8740a2fb7b9 |  | note | Inspection / Test Method - Induction
label | 4337bdd9-f0e3-5f2b-9252-a6407c22ad07 |  | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | 4713a8e0-94ac-5414-a8ca-ec496b78c40c |  | note | Records - Hazard ID and Pre-starts to safety team
label | e4fbaf1d-ebb2-556c-90d8-edf3386e83df |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | dd0ebb54-23fe-5915-b8a6-ca1eff5a6734 |  | note | H
label | 2ad6cd11-665f-5c51-a15a-eb8a5b3979e3 |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | f2efb68c-492b-5480-ade6-1ed97026def1 |  | note | Frequency - Prior to commencement
label | 2220deab-5e51-5945-810b-99a30587574f |  | note | Inspection / Test Method - Document Review
label | 98ae35d8-c221-5ad6-afe9-569bebf5213b |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | 19d6f32e-dd8b-5127-a89d-442a8da70290 |  | note | Records - Check Drawing Register
label | 26a240e1-abe0-5747-bb78-67fded30b6dc |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Installation of Erosion and Sediment Controls
label | e817a21f-7220-5142-8120-3e679dde8563 |  | note | H
label | e0b78d21-20ac-5b17-8ee9-083fd72f8f03 |  | note | Detail - Ensure that Erosion & Sediment Control in place
label | b8827f1a-c85c-5600-a705-188c88fbdabd |  | note | Frequency - Prior to commencement
label | 0eac7c1a-dd21-5c88-b944-cae6b6f5d05c |  | note | Inspection / Test Method - Visual Inspection
label | 988d4d11-5c17-5810-a898-ed09a5bf2807 |  | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | 5241572a-3375-5efb-b3cb-7a83f291270f |  | note | Records - Environmental Controls Audit
label | 78006230-50ac-57cb-ba62-a4ce37535feb |  | note | FH Initials - Environmental Manager/Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | 83e0c40a-a1fc-5df7-9c63-8d7e3317a037 |  | note | H
label | 86f8c966-0f5e-5eec-b858-97cf9a652111 |  | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | 8623b793-d01c-593a-8ce1-d0f400fcd87a |  | note | Frequency - Prior to commencement
label | c0303fd4-41bc-5eeb-8222-47dbfdf54b77 |  | note | Inspection / Test Method - Survey + Smart Level
label | afebe1eb-66f7-5a60-a130-03c2de302020 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 65b0385f-85f9-5408-af14-a1820f83714c |  | note | Records - Site Photos post surveying
label | 7cace66d-7599-55c0-aa97-843972986b7c |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging
label | bba2684e-d959-5f2f-b936-181f372b1cd2 |  | note | H
label | c835b629-de21-5571-8aa7-9f44d710717d |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | bac79441-06c0-5619-bb9f-3d2602927f35 |  | note | Frequency - Prior to commencement
label | 0423c433-eead-5ae2-b483-66ef776ce4aa |  | note | Inspection / Test Method - Potholing
label | 5e1e106c-ae9b-50ce-bb2d-dc152a53e3ec |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | 5c78ed4d-3e22-5ced-8e06-c149e59cc7cf |  | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
label | bd9bfbe4-0310-5d8e-b469-c953a5a93c2e |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Material Compliance
label | e1c353cd-cd02-56a4-aa03-55d8156b05db |  | note | H
label | c17b9b84-4eab-5921-b224-3309284b2e92 |  | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
label | 73524019-394e-53c6-a520-3307eae607c2 |  | note | Frequency - Prior to pouring concrete
label | 764b285a-baa1-538c-9f2b-a9c498d62e67 |  | note | Inspection / Test Method - Document Review
label | 6a39ffe8-99b3-553c-a343-98168b9e5efb |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 15704476-1951-5d8f-9340-bed65b7df9f7 |  | note | Records - Delivery Dockets / Photos
label | 6858fb57-94e3-5656-9c26-5ac54f52bfcd |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1 -
label | 90cbbc93-bc48-5bd7-8696-157ba0af59e9 |  | note | H
label | fb7d9d66-3926-5f0d-b605-48d00d4d38fd |  | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
label | a311ca4d-6889-5f0e-ae41-a211cc3fd537 |  | note | Frequency - Prior to pouring concrete
label | ccdf5bfd-654f-5f12-83ca-668a1d58f826 |  | note | Inspection / Test Method - Visual Inspection, Document Review
label | 4aa8183b-71b7-5859-b072-8a1968ae9f55 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 2f78eaaa-77e8-5eb5-870f-05ef29f1e678 |  | note | Records - Delivery Dockets / Photos
label | d4a8dd91-1e97-542e-9034-769faf632585 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 -
label | 0a9edd1e-78be-5a9f-a3fc-96f2a6b14b74 |  | note | H
label | 2a0a7625-8ae1-5fe3-92f7-e04794342435 |  | note | Detail - 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | fa272419-2c9a-5840-a310-5e361b633795 |  | note | Frequency - Prior to pouring concrete
label | 314b65e2-ed68-5000-ac22-d8eb3662c5a7 |  | note | Inspection / Test Method - Visual Inspection
label | f791a781-8859-5330-9342-1be946494503 |  | note | Conformance Criteria - CIV >15
label | 68791d72-efa9-51e1-9acf-8eaa3cdc29e4 |  | note | Records - Delivery Dockets
label | c0dd1a70-eb85-50b9-9f45-90f5e5e4489e |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 -
label | c2f6b355-f9c7-569c-9f9b-9b922a2da859 |  | note | H
label | 0e941f4f-7f6c-5e0d-b36d-7c2abd15cbae |  | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.4 -
label | c2c44325-19b0-5d93-aad5-5bc61e7c5faf |  | note | H
label | 91037283-f5d1-592a-8465-a7fe402ddbc1 |  | note | Detail - All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
label | f164bf24-450e-5b96-b724-7670bec583c3 |  | note | Frequency - Prior to pouring concrete
label | f253dc2d-b2be-5a04-b205-57bbb4b17aa9 |  | note | Inspection / Test Method - Concrete Delivery Dockets
label | 68270bb5-1ab5-588d-b5e8-a996ae98141c |  | note | Conformance Criteria - Delivery Docket added to QA folder
label | ed99c571-1d37-5701-8675-75bdbe95ab3a |  | note | Records - Concrete Delivery Dockets
label | be92b6ff-c327-5f5f-aaa8-72657b23c488 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Temporary Works (Formwork)
label | 29468734-bab6-527f-96a1-5080dc879c58 |  | note | W
label | 6014d553-b2f4-57b2-91fe-36809b45de68 |  | note | Detail - Formwork to be set to correct line and level
label | 93e1c190-80d6-5ce7-a514-ec8e02906609 |  | note | Frequency - Prior to pouring concrete
label | 3aa05717-349d-576c-85fb-397ce006540d |  | note | Inspection / Test Method - Visual inspection
label | cba5360e-e2e2-5e76-8248-7b5801c6fb33 |  | note | Conformance Criteria - Concrete Inspection Record
label | cec06d44-19c2-5f2a-b1f8-087d9e6603ea |  | note | Records - Concrete Formwork Checklist
label | 02c7e0e3-a322-551c-866d-ab6d1f026bd2 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 8.1 -
label | fe640a5b-d601-57c4-82b0-81fcdb907191 |  | note | H
label | 86803252-f5d5-592a-a2f5-ba24f334a5bc |  | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:40)
label | b722e98e-642a-51dd-bb23-d9f9d428361f |  | note | Frequency - Prior to pouring concrete
label | b55b6ab0-6eb7-5652-a1bf-1e3adc976791 |  | note | Inspection / Test Method - Measurement
label | 3d3789d5-4421-5302-b590-5944f9025bc4 |  | note | Conformance Criteria - Designer to inspect formation level
label | 15b4100a-8a87-5243-9446-c6107cdb7df1 |  | note | Records - Site photos
label | 78854638-40f0-532f-b2b7-6b5684cd478f |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2 -
label | 57289f7a-87c1-5fc1-81f9-8aedc070c624 |  | note | H
label | 58313634-f754-5c8e-b6e7-48b071eeb139 |  | note | Detail - Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table
label | a16e078c-89af-5eea-8293-8d1b878458b8 |  | note | Frequency - Prior to pouring concrete
label | 93fa93b6-7060-5a8f-90fe-70a67f94418c |  | note | Inspection / Test Method - Measurement
label | 532a59e5-8362-5eed-b1e5-a1976397fd76 |  | note | Conformance Criteria - Designer to inspect formation level
label | 0b86215c-7aa6-5641-b433-dfbff10f1235 |  | note | Records - Site photos
label | ebc69f63-2baa-5e16-9bfd-25f50f32d259 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.3 -
label | 2e77ae31-5ecd-5668-9f1d-97411698b01e |  | note | H
label | 5c73dd18-dcd7-5928-8bc8-72b3d41a3aaf |  | note | Detail - Raised Table ramps to be 1.125m across for entry and 3m for departure ramp.Toe to be 0.5 to 1m across for both entry and departure with 50mm asphaltic wearing course
label | 6fe25786-1945-59ea-b964-3d50ab56761b |  | note | Frequency - Prior to pouring concrete
label | a28b96c6-b118-54d6-a5c0-aa1b4b9893f9 |  | note | Inspection / Test Method - Measurement
label | 34aad87c-5903-5a16-9499-750ab7f5f8a2 |  | note | Conformance Criteria - Designer to inspect formation level
label | d1295208-20b7-5db5-af38-6fea9e36687c |  | note | Records - Site photos
label | 5dee4285-9188-5d87-bfc3-d45984b0b10b |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4 -
label | 95a58e27-70d8-5003-9e7c-f3e25c005ec3 |  | note | H
label | c53bf86b-e5fe-50af-9615-8f977d560d6c |  | note | Detail - Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:40 relative to the road
label | bb1ebdb2-b673-5265-a52c-a87b498bc7e3 |  | note | Frequency - Prior to pouring concrete
label | bf57b67a-0886-5726-b00e-a321ea4265bc |  | note | Inspection / Test Method - Measurement
label | 43bcb80e-10cb-53ff-bda6-ff6e0f0c8888 |  | note | Conformance Criteria - Designer to inspect gradient level
label | 0cd93cb1-fcb0-518f-9f32-adc5d2678116 |  | note | Records - Site photos / Concrete Formwork Checklist
label | 6032cc10-10cc-5db6-8316-aefb2fcc5100 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5 -
label | d6618948-0274-5da4-8dba-4dc7ac441ca9 |  | note | H
label | 135b7bad-efea-5396-a589-d25b3c7a8f1b |  | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | 6af60905-e0f8-5e1d-94d4-58bc71d2c715 |  | note | Frequency - Prior to concrete pour
label | 73849a83-5059-5e2f-a130-1ce2a1c8a862 |  | note | Inspection / Test Method - Visual inspection
label | 9a5d0a34-cfdb-5d9b-b11c-8bbd30a1d5c3 |  | note | Conformance Criteria - Concrete Inspection Record
label | e972cd11-9936-5e8e-9118-e003c9f76a77 |  | note | Records - Concrete Formwork Checklist
label | e4545aa3-8d88-5b6b-8ae3-fb5d3038d5c6 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Reinforcing
label | a6e771d1-ab0a-5a78-9b4d-7ec3ba700581 |  | note | H
label | 9ed10509-ee75-5b84-b2f0-0fd9f1085045 |  | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
label | 48c76fef-c4a0-52d7-87a5-a4f2b6fee84a |  | note | Frequency - Prior to pouring concrete
label | b27a8e2d-cb36-54da-ba87-4c6968f25bab |  | note | Inspection / Test Method - Measurement
label | 0229bfd1-51dd-5b5c-baf0-0c112e8f5436 |  | note | Conformance Criteria - Concrete Inspection Record
label | 8db99e67-5bda-5730-b47e-afd173587bb9 |  | note | Records - Site photos/Concrete Formwork Checklist
label | b56f0592-33d8-5976-b32c-480a21d0d4e5 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Concreting
label | a36de7b9-d1ba-5186-b983-210bfdec3e7f |  | note | H
label | 900de51f-0202-55e8-b1f2-94f4728642d6 |  | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | 8b78756b-e33d-52e9-88f4-e04da799626e |  | note | Frequency - Prior to concrete pour
label | 82ea2631-841d-5612-9c68-cd36511b1178 |  | note | Inspection / Test Method - Visual inspection
label | 2b636ec4-c39c-562d-b922-188dd662f530 |  | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | f2ead7bc-4eae-5ab5-b32e-2633c3a6227b |  | note | Records - Email / SMS
label | 1a72009e-0dd3-5d0f-b741-b4d5ad439fa5 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1 -
label | 615c8e02-5d0f-58d9-bf26-9e108b896ee5 |  | note | W
label | 80e0b8a4-2f3f-5d1e-bba9-482ac03c08fc |  | note | Detail - Vibrator to be used throughout concrete pour
label | 430d67a7-81f2-561d-bfc2-d450eaa37e30 |  | note | Frequency - When pouring concrete
label | 9df060c1-7b9d-5bfb-af77-46c2a287aa72 |  | note | Inspection / Test Method - Visual Inspection
label | 21e47812-cef7-5b81-ab7b-93470a7f172d |  | note | Conformance Criteria - Concrete Inspection Record
label | bf18c7e5-61b6-57e0-a32d-f7149b175978 |  | note | Records - Concrete Formwork Checklist
label | 1645865d-f29c-561d-9723-b46b8fdfc31d |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 10.2 -
label | 95809d09-74b6-5ccd-baa9-0c95c5caf7c9 |  | note | H
label | 98459f51-3d10-5761-afd4-d1c5873fe5a0 |  | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
label | cf131987-3cab-5d79-b048-cd087e2a20ea |  | note | Frequency - At completion of pour
label | 9f00c831-1d6d-5a03-9e8f-1c023fed1803 |  | note | Inspection / Test Method - Visual inspection
label | af8e2339-22fe-5711-a8da-f86a7395d9ef |  | note | Conformance Criteria - Concrete Inspection Record
label | 01012ef3-a448-55dd-b809-87261ed2bcc0 |  | note | Records - Concrete Formwork Checklist
label | f84d5fdb-c097-568b-9280-bd5e4fcfbd67 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Curing
label | 35f35d0d-8c33-504e-848f-fe9693e520e9 |  | note | M
label | 5003a2b4-6951-5c0d-9ba4-264ebbc585b3 |  | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | 8a999cfb-6b30-5119-ae71-f1e255744e3e |  | note | Frequency - Post Pour
label | 40aff075-3f19-5820-8f1a-04a0dda011f7 |  | note | Inspection / Test Method - Monitoring the time allowed for curing
label | 52db9a40-bc9d-5551-8493-22a41f31a1f7 |  | note | Conformance Criteria - 48 hours minimum have passed
label | 65ddc714-4034-595f-97b0-de6f267bc241 |  | note | Records - Concrete Formwork Checklist
label | 2fb03544-1107-5d29-a1b9-284445ce33ca |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 12 - Remove formwork
label | 45401c47-cb40-5c07-a5c6-00a9dc594510 |  | note | W
label | 8530b4a1-288e-5526-8ff1-8a3e553f6dfe |  | note | Detail - Remove formwork after 48 hours
label | 9efa64fb-7576-5f03-ae8f-0ef80d9df9fd |  | note | Frequency - Post Curing
label | 83a55c1b-1da7-57bf-88b1-c53e440a09df |  | note | Inspection / Test Method - Visual inspection
label | e7c2eb5c-842b-5976-aa8f-4266befb3791 |  | note | Conformance Criteria - Concrete Inspection Record
label | e3a6e09b-6661-5c24-b86c-2601b7f58b40 |  | note | Records - Concrete Formwork Checklist
label | 07fe5c54-472d-57b8-9bac-50de2c10dd2e |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
label | 54879025-7f69-5326-95e4-8ec528024d15 |  | note | H
label | 23124509-de8f-5148-8749-2e67923666f0 |  | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
label | c3355572-63e3-5e9c-a4de-f52ce4d2151b |  | note | Frequency - Prior to pouring concrete
label | f71c9af4-3362-5681-8328-06d3c4bb9ede |  | note | Inspection / Test Method - Measurement
label | 09751505-1a51-5210-a33b-a02b4485aa61 |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 4b237c44-752b-5e5a-b387-fbb7abb70c79 |  | note | Records - Site photos,delivery dockets
label | 28095584-a74f-5bae-a7b3-2297aec07415 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.1 -
label | afa18491-b7e0-5719-b36d-cbd8f59f69df |  | note | H
label | 20a7b738-608f-5f9d-9632-98df6e543caf |  | note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
label | c2768067-45a7-5b9f-ab0d-daa39f761546 |  | note | Frequency - Prior to pouring concrete
label | 7a0ee243-72e5-5ee9-ae75-c01a62fc9de4 |  | note | Inspection / Test Method - Measurement
label | f39f06d2-267f-5716-a8f5-191e12b1a3e0 |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 37d7e1cf-9377-5798-a68b-ccf2c4693ae8 |  | note | Records - Site photos,delivery dockets
label | 0534d447-4c43-5fb9-bbc7-a94dab98a138 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.2 -
label | 37c4f5e4-a465-54df-952a-df12c318136e |  | note | W
label | 07380a0c-053c-5ee7-9fc1-41397891df5a |  | note | Detail - Tack Coat between AC and Concrete slab
label | fef25fa0-30f2-5f2f-a0cd-6b15aee63a43 |  | note | Frequency - Post Curing
label | ac3c293b-9d5b-568d-a821-a4a7c1ce382f |  | note | Inspection / Test Method - Visual inspection
label | 5c07aa33-4efc-5276-a41b-7a9abbbdf585 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 2c25aab5-ab74-5976-9c39-d1fa42bd4129 |  | note | Records - Site photos
label | 3e6fcd94-ec9f-5392-9bc5-1d93a027e58c |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 13.3 -
label | fb1ef56a-f633-54f9-891c-7d2cbd03e933 |  | note | W
label | 47754c52-94db-5258-8124-a632902ea59f |  | note | Detail - 50mm thick DG10 / Mix 7
label | 5bcef5de-9018-50ff-bc13-298756792a0e |  | note | Frequency - Post Curing
label | c39ddf49-60c2-5875-9d78-eb4a1abe4449 |  | note | Inspection / Test Method - Measurement
label | e0ef947c-e240-59bb-8cfe-6cbc3105f10a |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | eb92afce-9816-5f2c-be4c-34142c0517a7 |  | note | Records - Site photos,delivery dockets
label | d8bf6787-2a29-52cf-9ab4-ef3b671fb3b5 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 14 - Lot Number QA File
label | 94f29e45-ad09-59ad-b949-8ca267d684ca |  | note | W
label | 025cfff7-fc69-5722-86e5-9edce0e61232 |  | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | 40bca27a-d6d1-5fc5-9309-5b2f428b5687 |  | note | Frequency - At completion of Lot
label | 02ddce0f-0a4c-5807-a1cd-d12bc1ff5984 |  | note | Inspection / Test Method - Document Review
label | 7cbf1c74-8997-55cf-822b-6b4470f63456 |  | note | Conformance Criteria - All QA files compiled and sumbitted to client
label | 6851c9f1-1e88-5904-91d5-115165ad2d44 |  | note | Records - QA records
label | f788bce2-80fa-56db-8926-65e7f3d6b70f |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 14.1 -
label | 229b56a6-56b5-5c18-b9a6-c480e96f10bd |  | note | W
label | 25ec0b22-65d4-57d5-95fa-de55a6b2bc0a |  | note | Detail - Delivery Dockets to be included in QA file
label | e557213c-69ea-5002-8f45-16ea2b72814c |  | note | Frequency - At completion of Lot
label | a9f08bd8-715b-5bca-91db-598019d9f202 |  | note | Inspection / Test Method - Document Review
label | 2df827b5-1b4c-549d-ab1a-d6bff0dd1688 |  | note | Conformance Criteria - Delivery Dockets to be included in QA file
label | e495b6ab-2801-5773-bc9e-a3ff4af105df |  | note | Records - QA records
label | 7acd9509-bf18-5b79-ba36-a93695bcec55 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | 7b6e4dd9-19f8-514a-9fb8-6c796ee25070 |  | note | H
label | e318cb7a-0dae-54bf-993a-cf3298fe3b29 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 2eb36e88-989f-56a1-8e7d-6981eac96808 |  | note | Frequency - At the completion of the Lot of work
label | 0f53729b-5b06-5eaa-a35c-f10858f1fc82 |  | note | Inspection / Test Method - Drawings
label | ac2666b8-c45d-5a96-8117-59ce3f5d416f |  | note | Records - Asbuilt Drawing
label | 0cadf6f9-6688-53f0-8e5e-db38a9646429 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - St Lukes Road/Morningside Drive intersection - Pavement |  |  |  |  | Yes | ITP - St Lukes Road/Morningside Drive intersection - Pavement | 9e03a0ba-1bce-444d-8169-d1e6269bbf49
checkpoint-group |  |  | section | Precom
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | a547c869-ceb8-542e-9edf-c0d7ed364856 |  | note | H
label | dc480b7e-b99a-5963-a02a-b5f91eaaae7a |  | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | 681346b3-043d-5396-b56f-b3473eba2002 |  | note | Frequency - Prior to any construction commencing
label | cc359c74-6ea6-50cc-bdb0-db6a42a4ab16 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 58cf89eb-2c11-5243-a61d-bfbb337f556a |  | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | 09590a3b-fa80-596d-a1d7-6e2dae62aa83 |  | note | Records - Permit attached or permit number noted.
label | e537a223-010e-5140-9da8-a1e78ebc90d5 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1 -
label | 88b44506-5613-581b-97a3-6216f7ed0642 |  | note | H
label | 8f30a418-1fc6-59b5-bbc0-2b50ef72ed42 |  | note | Detail - Locate and mark out all existing services
label | a5ef34af-37f2-53d9-944a-678627a17b2e |  | note | Frequency - Prior to any construction commencing
label | 93cfede8-3a5d-59a6-b7d4-b8056c994f9b |  | note | Conformance Criteria - B4u dig procedure - follow utility protocols
label | 6f211677-54d6-5fc0-9ae7-52f817a4e67f |  | note | Records - B4u dig plans
label | be404e9c-1fb7-5e23-b454-016b251ceec0 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 -
label | 076db791-04ab-5fa5-bbbb-3c8ae18f7887 |  | note | H
label | 45ac6910-2532-5000-b721-ac49d289fb2f |  | note | Detail - Approved TMP
label | 745c753d-ef27-5086-9022-0b286df9d2d1 |  | note | Frequency - Prior to any construction commencing
label | b5987be0-8a76-53df-b85a-9cb93290954d |  | note | Conformance Criteria - Approved TMP and WAP onsite befor establishing traffic management
label | fb9e5311-4dc8-58a3-a792-b3bf16d2f632 |  | note | Records - TMP Plans
label | 391bd7d2-ff6f-5ea4-886b-d001c75014a6 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | 5d874ee6-a728-530c-85aa-91fe5b9c2c9b |  | note | H
label | 675276f7-766e-5743-bb09-8f062a2be5ac |  | note | Detail - Sub-Contract and Supplier Agreements
label | 0a826bf0-5358-5c25-a5e0-96ce267dd5ba |  | note | Frequency - Prior to commencement.
label | 5a0c6ce0-82ce-523a-b02a-27cce1774fa6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | c2e1ab0a-b4b3-542a-b37d-0912522951d4 |  | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | b168b648-2456-524b-9776-ce6c09d8e4f2 |  | note | Records - Subcontract and Supplier Agreements
label | 98e15ee1-4260-55fc-856d-83b5d0b72c2e |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | e8747c0b-f85a-5039-bce3-60fde721f191 |  | note | H
label | 1cb99e0e-66c7-56ac-be04-4fbe72ec45ba |  | note | Detail - Design is approved and Drawings are of the latest revision.
label | f24f5c0f-144f-57b9-a0d8-31cd761b7ebb |  | note | Frequency - Prior to commencement.
label | bb4e2128-5be0-58ff-966b-c39be4614acd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 2815ce56-72a6-5e6a-9a6f-743abce12dff |  | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 2114bbec-1442-540d-8b75-6a07377ace68 |  | note | Records - Drawing Register.
label | 36ab87ce-3ca4-5fa9-8802-7f548e3338ef |  | note | FH Initials - Site Engineer
label | 38ff6649-e6f3-5120-8ac6-fdb4e011c817 |  | note | Design Engineer Initials - Engineers Rep.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | SAC Pavement & Surfacing
checkpoint-status |  |  | checkpoint | 4 - Bitumen
label | 4242ce10-a054-5d14-9ca5-729ac11b8879 |  | note | H
label | 4e468300-c7ae-5e87-822d-84b7b86f0127 |  | note | Detail - NZTA M/1
label | 87ecb1ca-12a6-520f-99e5-9dc7b17f70af |  | note | Frequency - Passing all tests listed in Table 1 of NZTA M/1
label | e1dcaa23-fb4b-531c-8eab-50fd539d0996 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | f3db14b1-57bc-58d0-9a34-f35ad83c6093 |  | note | Conformance Criteria - Passing all tests listed in Table 1 of NZTA M/1
label | d8aceb28-de29-5eeb-9577-86b561f310d8 |  | note | Records - IANZ Lab results
label | f89b700d-cb0f-5867-9ed9-e59fe477b71a |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Asphalt Mix Design
label | 20de2d57-7b10-5de0-8a7d-6f726a04db26 |  | note | H
label | d16d7cd4-df14-5091-938d-d3bcb3b075e3 |  | note | Detail - JMF approved
label | d056816a-cc32-57f5-9464-a339cf1b2d8d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | b9fa35c7-47ba-5885-afbf-42984e0ef2a3 |  | note | Conformance Criteria - AUSTROADS
label | 4d7f9ad0-efe2-58d5-922e-d65a9031fdb4 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Production Tests
label | 4c2426f2-e8bf-5e0e-beaf-c629002f9261 |  | note | M
label | 1c6f0ea0-03e9-5c99-b28d-355de3132b04 |  | note | Detail - NAS 2004 & TNZ sup to NAS 2006 TNZ P/9P (M/10 Table 5.1)/
label | 38772f34-8d43-586c-bf09-1b131a17ad7d |  | note | Frequency - 1 set every 300t
label | 37f82546-0958-5a6d-ba3f-047312842f95 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | ea1ddd11-3f99-5a07-981f-31a99d9af8f7 |  | note | Conformance Criteria - NAS 2004 & TNZ sup to NAS 2006 TNZ P/9P or NZTA M/10 - Grading, Binder content, Max Density, Temprature
label | 2748c3a4-c90b-5b3b-8d03-16b60d624c5d |  | note | Records - IANZ Lab results
label | 610f0729-db76-5c6f-b48f-b0ed3144cb6c |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 7 - Check Weather Reports
label | 7f4469b9-32fb-52e8-bf6e-a0e46593ddbe |  | note | W
label | 4ea8865f-77fd-574e-b0b4-408bfc05a723 |  | note | Detail - No fog, rain or wet surface. Base temp greater or equal to 7 deg celcius
label | aa63bfa6-adf5-508e-9819-0e17cbb6507b |  | note | Frequency - Weather call the day before
label | 907949a0-89cb-57d1-8f83-58f55b4031bd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 5eb42e2d-8a7c-55a4-a0f4-468d7d935407 |  | note | Conformance Criteria - Forecast and thermometer
label | 1ccb75cc-8694-52fd-9d96-e2742242f405 |  | note | Records - Radar and Asphalt QA
label | e29270eb-b9b5-52bc-ae4d-c192ada7cb65 |  | note | FH Initials - Site Engineer
label | 2792df9b-3d8e-584e-a4c1-a879cb8c624e |  | note | Design Engineer Initials - Design Engineer
checkpoint-status |  |  | checkpoint | 9 - Tack Coat
label | 4b453fc3-0edc-531a-b939-c709fe0a1bcb |  | note | M
label | 30161253-a269-5f93-8da9-384641f8c229 |  | note | Detail - Minimum residual binder application of 0.3l/m2
label | c7984740-7b1d-5647-bfaf-12bbe2ca7569 |  | note | Frequency - Each Run
label | 7a3910d3-a0d1-5bd4-a90a-e49b04453f72 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing & Visual
label | 4e3583ef-d0e1-5b1c-a990-9c9e278cc4ce |  | note | Conformance Criteria - Each spray of bitumen
label | 409ee545-cb7a-511c-9ff1-5da2207225be |  | note | Records - Asphalt QA
label | 56b36e0f-268f-5e35-906f-d9deee90ef3b |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 10 - Construct 70mm AC14
label | d5e597bf-a946-5555-b452-328c0b2b5f9a |  | note | M
label | 975d3ae3-e586-540d-b195-76ce37dc0300 |  | note | Detail - NZTA M/10 NDM and Stringline
label | 8cd26b3c-f6fd-58a2-87ab-f45bd3a743db |  | note | Frequency - Each Run
label | 22e0b6f8-ffd0-5683-a04a-1b1533dbd481 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | f4ef0af4-6f0d-5dbd-825f-4882042807e6 |  | note | Conformance Criteria - Construct 55mm AC14, Depth check and Stringline check
label | 484489bb-3ca2-5b1c-9c66-9a1e97d23301 |  | note | Records - Asphalt QA
label | 9239ae94-24bc-5f80-ad10-668a54f35bc4 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 11 - Construct 70mm AC14
label | 35f70a70-b427-52a0-95dc-c6a9cf6d0cd0 |  | note | M
label | f7afbc3b-5019-51b1-8915-329c88dfaca8 |  | note | Detail - NZTA M/10 NDM and Stringline
label | 3e880c48-cbc3-5af4-970e-72861617e426 |  | note | Frequency - Each Run
label | 433a936a-dfac-5565-85fe-0acc037c8b66 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | abb33e3e-f185-5283-9418-86b9a69123f0 |  | note | Conformance Criteria - Construct 55mm AC14, Paving and compaction using roller. Well compacted to avoid air voids.
label | 13993704-ab14-5c97-8dc8-08ce86bf42cc |  | note | Records - Asphalt QA
label | bada7d06-c4b9-5975-b00b-212ea7baa81c |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 17 - Surface Finish - 3mm Calcined Bauxite
label | aafdd697-bd49-5084-95c3-d12a30b1155e |  | note | W
label | 0a6787f7-f33a-54ad-b4cc-2641c35fa83f |  | note | Detail - TNZ P/9P
label | 0f91cb44-986d-5dbf-9abd-b5810f50ec83 |  | note | Frequency - Each Lot
label | d3f691ce-de14-541b-bc1d-af2eba6fdb2a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | dbb0a957-e55c-50a3-a465-2a56761c5da5 |  | note | Conformance Criteria - Inspection: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate
label | 7a9dd9af-1b77-5bd6-81ba-dd27a0e62430 |  | note | Records - Photos
label | 8d10667e-c3d3-5292-85ab-09d86aa9f916 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 18 - Reinstatement of Linemarking and RRPM's
label | 48aa1e25-2713-5e5c-abb0-dbf4cfdf2dff |  | note | M
label | 2bce6e8b-f6c0-5fdc-8ac2-6902bbc0483c |  | note | Detail - NZTA M7 approved (Class B or C as required for anticipated traffic level)
label | 4b2f4a1a-d99f-52bf-9b4b-3e5f96aae92f |  | note | Frequency - Every site
label | c95738cb-2a37-5a9e-8df1-9e579d6e30cc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 5aa6c52a-c929-50c5-afdc-5cf6f28dbe2c |  | note | Conformance Criteria - *Carried out within 12 hours of each shift completed and as per the existing markings * Suitable Traffic Control to remain in place until pavement markings have been reinstated
label | 17b5dac9-d3a8-5c98-9347-0530e6eac927 |  | note | Records - Photos
label | 4e755823-1e2d-5a7c-8c0a-87707ff6605e |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
text | 75b69a99-87eb-5963-8437-19ee5652aeb2 |  | textbox | Comments:
checkpoint-status |  |  | checkpoint | QA checked By Quality Manager:
text | 8f8e6c32-0169-575d-a9e2-23b038112694 |  | textbox | Name:
text | b5e8b4b2-3c4a-5eb1-a6e7-f779e52c37cf |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Accepted By Engineers Rep:
text | 70cbfec6-2158-5867-a0c9-b2469ff4cec2 |  | textbox | Name:
text | 16948960-0071-5bd5-a54d-6047294a3c76 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP - Massey Road - Traffic Islands |  |  |  |  | Yes | ITP - Massey Road - Traffic Islands | a2d3282b-ee56-4b2f-b7ba-274e815f50df
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 1 - Mountable Kerb
label | f09e6aab-0a80-533e-8ad6-dc496370ea2d |  | note | VERIFICATION ACTIVITY - QA FORM
label | 32836d5a-eb3a-5e5d-b021-99094e68eaeb |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | 0b942c98-0f1e-5e08-84a9-5ac8c3fde6a4 |  | note | Frequency - Everysite
label | adc61bf7-a6ff-582f-831a-ff67bd5364ba |  | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
label | 61c7cfbc-c2ee-59f5-b76e-0f3838974132 |  | note | Inprocess Inspection
label | 691dcf5b-6d5c-5958-9bed-0efd108989bd |  | note | Records - FH concrete QA sheet, photos.
label | 68d4399e-9170-522a-b380-a052f3e97d74 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 9a3066b6-a122-56f7-b3f5-6b25b42f9d03 |  | note | VERIFICATION ACTIVITY - Survey
label | e8101845-2cc8-5995-8ea1-b4bd52277eb9 |  | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
label | 1d1ae9b7-ded4-52bc-9c6b-7c1d5c83ac27 |  | note | Frequency - Prior to commencement.
label | e317a022-12c0-5948-a1eb-64f82b4db154 |  | note | ACCEPTANCE CRITERIA - Survey
label | 61838f99-c3f5-5e16-90f5-bcbfa445ffca |  | note | As per Construction Drawings
label | 2b96f036-2cf5-58a8-bc26-36d616b912d7 |  | note | Records - Survey Receipt.
label | 942b1a30-235e-5435-bf85-829ee438863d |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Concrete Island
label | 0c8aafa9-435b-5e44-94bd-a55a47f01d43 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 8c41222c-5c2d-5e86-9f04-77a7f00894eb |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | 32467ee5-62b2-594d-9ea2-6dc2213765cd |  | note | Frequency - Each Site
label | bda3af89-2d99-5002-a7b1-75403c2afc86 |  | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete
label | e46ca91f-3ca3-52cc-8220-c769689c268f |  | note | Inprocess Inspection
label | f07cd934-989f-582f-84ea-4e98e4f7373c |  | note | Records - Photos
label | a9a5780d-9f86-5153-92e7-033d16bedde6 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3.1 - Concrete Island
label | 73c1c391-38ac-5421-aa8d-7b2866686b7f |  | note | VERIFICATION ACTIVITY - QA FORM
label | ded2b8ee-e273-5acd-9ce2-19d96888c6cb |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0003
label | 64668834-faa6-5641-b382-3df0227e5145 |  | note | Frequency - Each Site
label | e3744d99-6c06-59a6-ba4b-42cd3d052faf |  | note | ACCEPTANCE CRITERIA - Basecourse to be 150mm min thickness of GAP65
label | 2ce6deb1-7ab9-5984-a994-3d7536fc33bf |  | note | Inprocess Inspection
label | c4be895d-f36b-5eff-b988-4c77a134cb87 |  | note | Records - Photos
label | bec1a210-c2bc-511d-b44e-f7a6a9b75a24 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4 - Concrete Infil
label | f543ee26-4356-5560-b3a8-12f683bedfcc |  | note | VERIFICATION ACTIVITY - QA FORM
label | 771e3a36-bc99-541b-a14c-dcbfd8098a3d |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | ab887746-b6af-55da-8656-8430cf4f97d1 |  | note | Frequency - Each Site
label | 2b05d846-e6e1-56ae-ba04-29bd2ae8030c |  | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 black oxide Cross Fall of 2% or max rise in centre of 180mm
label | c89dcf6c-6c90-5937-b319-0b0675c304a8 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 959defd7-c866-547c-bc44-44563ee6347d |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 5 - As built information
label | 0c5f9250-04b6-551a-854a-e04f0255c0df |  | note | VERIFICATION ACTIVITY - Drawings
label | 2c4d402b-5d0c-55d1-b6a9-2816c7216811 |  | note | Frequency - Every Site
label | 760cd9d8-1fc7-508f-b5c9-37bfb57cadbb |  | note | ACCEPTANCE CRITERIA - As built drawings
label | f8d213c5-72c3-54f0-ad75-193f76ce826f |  | note | Inprocess Inspection
label | 9e525868-0b18-5696-80d6-d352ffc4ca51 |  | note | Records - Asbuilt records
label | 790cb7d3-2c64-577f-99f0-41ccc21dd6dd |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | 6 - RAMM DATA
label | 997d90b1-6615-50d1-a51e-509a66fddc73 |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | b657d427-30b9-5d2a-b145-0e2418c98123 |  | note | Frequency - Every Site
label | 110252e8-e8e9-5b02-afa1-90afc3d2c249 |  | note | ACCEPTANCE CRITERIA - RAMM SHEET
label | 1462f469-0207-52f4-8fd5-bbfe29650d20 |  | note | In Process Inspection
label | 42c08529-40aa-562e-a80b-c9c658ae6b53 |  | note | Records - Asbuilt records
label | c7f0b99e-e486-541e-9d50-fa849aca33c5 |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-sectioned |  |  | checklist | Drainage - Pipeline Installation - |  |  |  |  | Yes | Rogan Arunel - ITP - Stormwater Drainage | a62a6240-7857-4f1d-a174-d73064348a8f
checkpoint-group |  |  | section | Pre Start & Area Acceptance
checkpoint-status |  |  | checkpoint | Latest consented drawings available, checked and referenced
text | becbf563-65cf-4d00-b2a6-e5a2cf94db78 |  | textbox | Relevant drawings & revisions for reference:
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Work area acceptable & approval to start work
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-group |  |  | section | Pipeline Installation
checkpoint-status |  |  | checkpoint | Setout Completed checked and accurate
checkpoint-status |  |  | checkpoint | Excavation Accurate - Location & Depth
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status |  |  | checkpoint | Bedding depth and material correct
checkpoint-status |  |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
holdpoint |  |  | signoff | Connections to manholes complete and approved
checkpoint-status |  |  | checkpoint | Air Test Complete (Sewer Only)
checkpoint-status |  |  | checkpoint | All Pipe install elements completed - Install Completed
checkpoint-group |  |  | section | Review & Handover
checkpoint-status |  |  | checkpoint | All Pipe Install works completed, checked and reviewed as per specification
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Area left clean & tidy
holdpoint |  |  | signoff | Raise Remedial / Request Review
checklist-sectioned |  |  | checklist | ITP - Great South Rd - Island | itp |  |  |  | Yes | ITP - Great South Rd - Island | a8450d00-925d-40cf-92cf-4539f1147269
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 1 - Mountable Kerb
label | db1594cb-b2b2-5aba-954a-bc73713241a7 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 7edffe87-ffc0-579e-a668-74b55d1161aa |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | 127ae372-3bb2-5ba8-a0d8-0bd5656bfb3f |  | note | Frequency - Everysite
label | 4ee5251e-eb99-585e-9412-d9199e20569d |  | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
label | d2b5af73-db1b-5743-a231-660b03a5c70b |  | note | Inprocess Inspection
label | b738d43f-afd4-521d-adf2-a9a6c4f74040 |  | note | Records - FH concrete QA sheet, photos.
label | 2598351d-f11e-5de1-b1a0-5b9207037174 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | f9041311-7a29-5aae-ac87-c37e4f2929ad |  | note | VERIFICATION ACTIVITY - Survey
label | 88ebbd61-6c55-5593-9415-6f661d08cdc8 |  | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
label | 01e4ad39-2bb7-5738-a82e-95f185ff0690 |  | note | Frequency - Prior to commencement.
label | 589ba7d6-7b95-5a85-8fdc-91fef9334af5 |  | note | ACCEPTANCE CRITERIA - Survey
label | 6aba0267-4f64-52e9-8f17-acfd1b4c2fdc |  | note | As per Construction Drawings
label | 6274f45a-5fe6-52d7-ab85-db6194c04f30 |  | note | Records - Survey Receipt.
label | fd4e524d-c0d4-5e2c-ac2b-75a078c5a1a1 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Concrete Island
label | 36cccbdc-9747-5800-b9d8-f233ae0593b7 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 9dbcd368-9760-5261-b39d-d4d8f3f30e31 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | 411956a7-7786-5eb3-9597-9c392944993d |  | note | Frequency - Each Site
label | 5ee9a501-9c28-54de-8edc-016232809ad5 |  | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete
label | 80d8fd09-4b7d-5d7b-9870-1377e7be4c8e |  | note | Inprocess Inspection
label | df60216d-21cd-55bd-893f-e7f26118cf67 |  | note | Records - Photos
label | f91a5272-aed2-5f60-8985-04f3ba2ccf9d |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3.1 - Concrete Island
label | 6dd0d13d-8e86-5c63-990e-bff9fc209265 |  | note | VERIFICATION ACTIVITY - QA FORM
label | e26ac361-91fd-5ae5-a0de-98f6ab5fcd7b |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0003
label | af5b0b74-5ffb-5497-8bca-4843ba324dac |  | note | Frequency - Each Site
label | d6267ee1-bea8-5acf-ac88-fd52434260b6 |  | note | ACCEPTANCE CRITERIA - Basecourse to be 150mm min thickness of GAP65
label | e53f3794-562c-55e8-a3b3-6f16d8c8310b |  | note | Inprocess Inspection
label | e829f4fb-3a4c-56f8-9f8e-5b72121eaf32 |  | note | Records - Photos
label | c2bbf2d3-f770-586d-93b3-44f929fbdb40 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4 - Concrete Infil
label | 6b9c21e4-107d-55d6-b9e2-313b513a0b09 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 9e5a42cc-9598-5c21-aa05-a74da3d351b7 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | b5f98983-cc73-5b20-87da-c9fd8f196840 |  | note | Frequency - Each Site
label | 0468b890-335d-5167-933d-2ce2e63376b6 |  | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 black oxide Cross Fall of 2% or max rise in centre of 180mm
label | 473a759b-a07a-54c1-b90e-7f7c64575922 |  | note | Inprocess Inspection
label | 68e76f9a-841e-5bd3-bfbf-64001d19371f |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 29750445-7275-55d1-9d81-861b3ecbe81d |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 5 - As built information
label | e00fc8b6-7b70-5d49-a43b-1dc5706f04e4 |  | note | VERIFICATION ACTIVITY - Drawings
label | 275b9df0-24df-5a4a-8093-a7af650db9fb |  | note | Frequency - Every Site
label | 3dc114e7-d466-5005-8512-eb19febc0b82 |  | note | ACCEPTANCE CRITERIA - As built drawings
label | 43528038-24af-5fd0-bf72-d8d38bdd000e |  | note | In Process Inspection
label | 3d52557a-d596-54cf-a973-ee585d939ab1 |  | note | Records - Asbuilt records
label | 03558890-0b5e-5e6e-bcd3-218f5c083fa0 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | 6 - RAMM DATA
label | 836c2205-4bfc-5535-9efa-e4b96e179e26 |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | 5ac8c17c-dc9a-504a-9ad3-5b545cbd1b85 |  | note | Frequency - Every Site
label | 2c227797-4e9a-5d40-bcd6-89690b5ba871 |  | note | ACCEPTANCE CRITERIA - RAMM SHEET
label | 51b5a1b3-b243-5cb3-80ba-237dec6a095a |  | note | In Process Inspection
label | 3702f566-787a-5d58-b7a0-5a1dd32def8b |  | note | Records - Asbuilt records
label | 6c64faba-aef5-506a-b837-891164715a41 |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-flat |  |  | checklist | Stormwater Drainage |  |  |  |  | Yes | Lincoln Rd - ITP - Stormwater Drainage | a9e8a0df-bfb2-4dae-9c04-463c9e72ce96
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | 040ed495-8f6d-5b8d-b19f-dd9a1dd54ec0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c0615b2a-2e3d-5af7-847f-11c57d6c3f66 |  | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | 6fe946f6-9ed6-536d-8fc3-1a01eacfc7f6 |  | note | Frequency - Prior to any construction commencing
label | d48b5fb1-ece5-5472-b789-43beab4ac787 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 252d30d1-e742-5b5e-abe6-cff7095bd569 |  | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority.
label | 44e54988-97d4-50f4-af93-384e5dd8ee14 |  | note | Records - Permit attached or permit number noted.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1 - Permits & Services (2)
label | d9652ce1-28ea-50a6-bdee-252d63be39ac |  | note | ACTION (Hold, Monitor, Witness) - H
label | cde4b71d-caa2-5e6d-83c5-92b8fb3d4734 |  | note | Detail - Excavation methodology, Trench Profile - Width, Trench Profile - Locate and mark out all existing services
label | 68b5ce5e-0a73-5e09-89cb-ae6c1d39f8aa |  | note | Frequency - Prior to any construction commencing
label | d20baaa5-a7aa-5075-8adb-63f9eee03bc8 |  | note | Conformance Criteria - B4u dig procedure - follow utility protocols
label | a65ff0d2-e7e6-5aff-8ecb-18e38f0bde18 |  | note | Records - B4u dig plans & GPR report attached
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | 4b4cda06-67fd-548f-852c-ef2e75b33f92 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 15f13df4-c3af-58ae-a87a-e303e23f59aa |  | note | Detail - Sub-Contract and Supplier Agreements
label | 97f9d318-26f2-53ff-8bb0-46ff0189ec36 |  | note | Frequency - Prior to commencement.
label | 150ccf96-d639-5600-a460-f4f88f4a3098 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 456745ca-3110-5c9d-b17f-0ffb4d048dd1 |  | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | 797b04b8-4d59-5f71-a5f8-3b38cec49144 |  | note | Records - Subcontract and Supplier Agreements
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 22eb0b82-d397-5191-9cbc-9854dc4cdac0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f33aded7-4185-5577-90cd-abb985e38c2a |  | note | Detail - Design is approved and Drawings are of the latest revision.
label | 30eb8138-586f-584d-b5c1-30c0f67195b4 |  | note | Frequency - Prior to commencement.
label | e5d307b6-6dfc-5302-a028-f696bc9bbad4 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | e29f5dbc-4bfd-5f35-8be1-242ea1e87fc2 |  | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 5f0be9bf-8339-5cca-bff8-ae7255769236 |  | note | Records - Drawing Register.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Survey Set out
label | 775f75fb-712c-53bb-ad47-6372b550ab12 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0c4c5a5c-107c-573b-b944-140be5722fdf |  | note | Detail - Set out Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | f0f5aff5-8cb5-5be2-b6b4-eb74b09b6629 |  | note | Frequency - Prior to commencement.
label | 979c4fe2-9103-5a7c-931d-c2c422441f0b |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
label | d5c22d21-0318-5d4b-accf-bd4d18bd0746 |  | note | Conformance Criteria - As per HARRISON GRIERSON ENGINEERING DRAWING: 1040-A2110796 & Set out files
label | f8d70d44-f94d-5db7-8966-7865a20498d1 |  | note | Records - Survey Receipt.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Pipe and Manhole Material Compliance
label | 60edd31a-6b92-5ec9-8034-74ea9c619298 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a7917a46-098d-5a58-97f8-30cbd5a087a3 |  | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | c2fae21e-baea-52d5-a36f-09347dedcdb9 |  | note | Frequency - Prior to commencement.
label | 6819accb-2bba-55e2-ba34-d245d5dc8cf7 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review, Visual Inspection
label | ec010da9-e0a9-52ac-9213-3a34e733aa11 |  | note | Conformance Criteria - Pipe shall be
label | 0202043b-2174-563a-a6df-5eec02188e84 |  | note | • Check for freshly formed pipes and return if required
label | 898cbf2a-9934-5093-ac8d-f61a2cea55af |  | note | 1) DN300 Class 4 RCRRJ pipes AS/NZS 4058
label | 091eb62f-601a-50e1-b67e-16db5dd107a5 |  | note | 2) All Concrete RCRRJ pipes to be fitted with Rubber rings
label | 1dcec963-97ef-55cd-9ae4-72e3d55120c4 |  | note | 3) Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
label | ed8b428d-fa6f-5b00-ac46-75a5d677b186 |  | note | • Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | 408f7a9c-d0cd-5631-9d10-be51c9a193b4 |  | note | Records - Manufacturers Data Sheets, Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | c095967e-0964-5906-9a98-1b2266674ca7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d7dfcf29-56f2-598e-b0fe-8f1550788b3c |  | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | ac623e15-243b-5413-831a-2f756f36baec |  | note | Frequency - Prior to commencement.
label | 880537fb-3f45-592b-8123-90f7dd325b73 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Potholing / Survey
label | f5584e0a-b512-5198-ad8a-e03bb5fb8aad |  | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | 1dd64751-9487-5c5d-900b-e4275dc12265 |  | note | Records - As-built Drawings. Doc. Review
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | 7f3c4fc1-d21f-542b-8f81-b6b623fe2f4d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 54b3aa15-9c83-50c8-80ef-1a26c1adab62 |  | note | Detail - Excavation methodology
label | 2af1f5b2-db59-5b2e-a387-4c7d8bc5e3e4 |  | note | Frequency - Daily
label | 54e48f66-0f10-5a92-b180-82a373f49a4f |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Prestart review
label | 6e967ab8-54d4-5426-9fcf-52dfe8597992 |  | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | cd0ab290-c424-528b-b10e-28d4b7b9a131 |  | note | Records - Prestart RCP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation (2)
label | d42d7dd3-d573-5cc0-8da0-8a14c07f10e0 |  | note | ACTION (Hold, Monitor, Witness) - M
label | c44810ba-de20-5e67-b1db-de8264d94a81 |  | note | Detail - Trench Profile - Width
label | 4560a46d-eddf-52a8-a841-ec825e2387ca |  | note | Frequency - Daily / as trenching takes place. Different depth methodology
label | 07fd1a89-c83d-576c-ad27-5727f3983cd7 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Excavation methodology
label | d70c624e-cd0b-55f8-aad5-89a69ffee236 |  | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | 4684cb7a-dadd-58fc-9add-04e61136531c |  | note | Records - Construction Photos
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation (3)
label | aeed73ec-7774-5a18-93e1-d168330ea022 |  | note | ACTION (Hold, Monitor, Witness) - W
label | dc495293-4f75-5ddb-857b-29062e8e509a |  | note | Detail - Trench Profile - Depth
label | 4ba3a1a5-f53d-55ae-8d1c-0eff7ada1e6c |  | note | Frequency - Daily / as trenching takes place.
label | a254387a-d7b0-50a4-9e34-94787e8fd41c |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Measurement
label | a4892c9c-586f-5041-aebf-f494feefdfc6 |  | note | Conformance Criteria - Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | ba38ec53-1aa5-5d07-9599-b5fcf9a723f2 |  | note | Records - FH Drainage Line Record / Construction Photos
checkpoint-status |  |  | checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | fdb6d4c2-3c6a-5a71-9aa7-690d44cf7fb2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1fe62f1d-0132-53a7-83ed-45dfbb13f93d |  | note | Detail - Placing and compaction of Bedding Material.
label | 39dc9489-98e4-5f26-9e10-f79f7f62f06b |  | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
label | 3b28e1f2-d0cf-5a41-8885-0bc7e94ec8c4 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 9e1ae739-d3ce-5af9-bc73-9e64a4323ada |  | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | 77247505-20de-50f3-baaa-4af7bc29a49c |  | note | Records - FH Drainage Line Record / Construction Photos
checkpoint-status |  |  | checkpoint | 9 - Pipe Position Tolerance
label | 4225e651-21d5-56fb-95b9-f9ce3835ba22 |  | note | ACTION (Hold, Monitor, Witness) - M
label | a579fb61-d8a8-53d6-af6d-8df2fe64d23f |  | note | Frequency - At any point of pipe
label | e08525bb-a760-5a7b-9805-eeece2cd6d01 |  | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
label | 040f570f-dfb7-5f4f-af75-4d14e60723e7 |  | note | Records - FH Drainage Line Record, Survey Data.
checkpoint-status |  |  | checkpoint | 10 - Trench Backfill - Placing & Compacting
label | f28e99ef-8d6a-5908-af85-041dd4f55c3f |  | note | ACTION (Hold, Monitor, Witness) - M
label | b34e2209-45c6-55c0-8038-02253f0a3cb0 |  | note | Detail - Placing and compacting of Trench Backfill Material
label | af4e311e-5415-5167-823b-5475e89276c5 |  | note | Frequency - Throughout Trench Backfilling operation.
label | 75410ce5-9df6-5575-9c1a-f3859571117c |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 2ebe445c-c6e6-5ff6-85f5-ddbd2b80b5a8 |  | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | 9d70c2ee-dd3f-51e8-bb47-6799be65a5c8 |  | note | Records - Construction Photos
checkpoint-status |  |  | checkpoint | 11 - As-Built Drawings
label | 13ef79d4-e96c-5163-af6b-b0d1ca392e5c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 92042e1f-5436-527c-8e38-45e012449abe |  | note | Detail - Red pen marked-up As-Built of every 'Issued for Construction' AT drawings
label | c8425110-bad9-5c23-99ed-36ee1ec32ca7 |  | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | ecbc9e13-96da-5b31-9073-af65d4794cfe |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings / Visual Inspection
label | e652bb46-485d-5a8f-8dc7-c0093eb4b757 |  | note | Conformance Criteria - As Built and GIS Data
label | ff1183cd-7fa3-5945-a022-89ceddd9dca6 |  | note | Records - Redline As-Built Drawings, scanned as .pdf files.
checklist-flat |  |  | checklist | Earthworks and Retaining Wall |  |  |  |  | Yes | Ponsonby - ITP - Earthworks and Retaining Wall | aa87a800-7060-4dfd-8977-fcfec0f414de
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 476d18aa-e843-587e-bcb0-f4418e889dd2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4566bcfc-537a-55c2-8d6d-dc7199a38e4e |  | note | Detail - Obtain Permits
label | 6ee160e2-2a1f-5b00-bd9d-3e0e0156598a |  | note | Frequency - As required
label | 2e3c6da8-01e3-5e86-8b25-3dcee36cb066 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 662205c4-1987-59fb-be6c-859643243e27 |  | note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services).
label | 22f177fc-e14c-5fa4-8cf5-73e9722e7f34 |  | note | • Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 1f2473e7-3d3e-50a3-8c4d-6a7d737353b3 |  | note | Records - Permit attached or permit number noted
checkpoint-status |  |  | checkpoint | 2 - Traffic Management
label | f5f0ca04-2bb6-50e0-aaf0-6f8e2bc43cf4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7cca0307-63e7-5572-9ca3-9f2f3fe77352 |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | f3238d81-33e1-5a6b-b6a7-01d0b78c23b8 |  | note | Frequency - Prior to commencement
label | debc195f-3b57-563b-a879-836cd2f123be |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 46bdb85d-f3f6-5e81-a4d8-e8c77411ecd4 |  | note | Conformance Criteria - TMP is approved by AT for the site and works are only completed within the approved dates
label | eecebabc-07c0-54c0-9861-3cf2e0528470 |  | note | Records - TMP on MyWorksites/OnSite
checkpoint-status |  |  | checkpoint | 3 - Pre-construction sign offs
label | bb078642-d4cc-56e0-8545-a233ad5795ab |  | note | ACTION (Hold, Monitor, Witness) - W
label | 48692666-8b2c-5489-8282-52ecac10e587 |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site
label | 123fd141-b838-5599-bd82-bf72526f4272 |  | note | Frequency - Prior to commencement
label | cc8ffa1e-bc5b-50bd-9b5b-6adfec2acd3f |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 2a3ce4eb-a142-5c29-8814-51c65f3af1d2 |  | note | Conformance Criteria - Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated
label | c5c24693-e350-55f9-966b-05e8400d4cb3 |  | note | Records - Subcontract and Supplier Agreements, A & Updated Induction Register
checkpoint-status |  |  | checkpoint | 4 - Design
label | 40b9684f-402c-52cf-bc87-b6497bc5afea |  | note | ACTION (Hold, Monitor, Witness) - H
label | ac847999-83da-5e3c-829f-4c37847bc125 |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | bc3cb441-955d-5baa-94db-5ba8f1d02dd9 |  | note | Frequency - Prior to commencement
label | 7e8134ff-ff40-5e1e-ab9a-9554dfe92639 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | b87bb4ac-df66-582f-ad17-88c7296d04af |  | note | Conformance Criteria - IFC Label on drawings
label | 809ed49b-da43-5bbb-8e32-9255711deb79 |  | note | Records - Check Drawing Register
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Material Compliance
label | fb997be0-0624-5660-908d-5a287068ab52 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a606e9e7-dce8-5424-b709-a41c94d92069 |  | note | Detail - Granular Fill Material requirements
label | cb8dcd42-f59a-574c-af90-d094d036d6e2 |  | note | Frequency - Prior to commencement
label | 8cde9b74-9036-5c71-ba94-4e6651440a64 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - As per TNZ F/1:1997
label | 19939408-1e3c-5beb-93c2-8814bd8e29ab |  | note | Conformance Criteria - Maximum percenetage of weight passing 35% 0.0075m sieve shall not exceed 35% and has a sand equivalent greater than 20.
label | 78ad7de1-5dc3-5bef-8379-67ca35533831 |  | note | Records - Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Survey Setout
label | 2121ab9c-9de4-5d47-a08a-585bff3151f4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b1a8002a-e62a-587e-adb4-7ea9f6541732 |  | note | Detail - Setout cut/fill areas as required by to construct to design. Topographical surveys to be completed prior to starting, monthly and upon completion
label | 3c724079-19f8-577f-80c6-3add44e2df15 |  | note | Frequency - Prior to commencement, monthly and at completion
label | f3ae3b25-7f23-5da2-8a76-0733efb12bd6 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
label | 619fd688-7c90-5646-ac83-c851815c0c21 |  | note | Records - Check Drawing Register
checkpoint-status |  |  | checkpoint | 7 - Installation of Erosion and Sediment Controls where required
label | 169cf02f-edc8-51a9-a2a5-4e9469f1b7d5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2087b8ee-ad62-54cb-a5ea-494620e109cf |  | note | Detail - Setout Environmental Controls and confirm location with Environmental Manager
label | d8298e1b-b3b5-583e-934b-6f579940a147 |  | note | Frequency - Prior to commencement
label | 52aaf298-2e10-5738-9170-39817d18a1c4 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
label | 219f31ce-6816-5bca-9c8a-082e4db691b0 |  | note | Conformance Criteria - Correct volume for area and setup to TP90: 1999
label | e5f4e055-0568-51e7-9adc-6aa0a30947fc |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Installation of Erosion and Sediment Controls where required (2)
label | 7f1794de-c384-5bc8-8de6-74619711043d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9e9e9791-d9d3-53c5-8800-a0a8810aea9c |  | note | Detail - Design Engineer Rep/ Client Rep to inspect controls after implementation
label | 46026937-c312-5a49-afe4-b5a6dbb6bf31 |  | note | Frequency - Prior to commencement
label | 286dc184-b0cb-5e02-97a4-7a5f49ed8c92 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Submission
label | 7401e037-d2be-5d2d-92d3-305453e4e0b5 |  | note | Conformance Criteria - Correct volume for area and setup to TP90: 1999
label | c0691931-f29e-5b2f-ab0e-c76b5f4bcdc1 |  | note | Records - As-built
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Installation of Erosion and Sediment Controls where required (3)
label | 58a815d7-f682-50a1-9281-c94cc845e825 |  | note | ACTION (Hold, Monitor, Witness) - M
label | b425ab10-1df2-5c30-b19c-bf48e6e0299c |  | note | Detail - Monitor sediments tracked out onto any roads and the generation of any Foreign objects and debris as well as dust generated
label | 1bf68b71-1741-5bff-8030-34d8b1d06a7c |  | note | Frequency - Continuous monitoring
label | 2334103c-63a8-580a-b26a-cdd71cf705cf |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 9c39b137-316a-5212-a5fe-cb597a2374aa |  | note | Conformance Criteria - Roads free of debris using watercart where required to minimise dust generation
label | d2396f7b-2684-5d3b-8ee9-5c65c090b254 |  | note | Records - This ITP
checkpoint-status |  |  | checkpoint | 7 - Installation of Erosion and Sediment Controls where required (4)
label | 1db8bc20-2042-5f22-bbde-1b66eeed6c3c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 86c476e8-9a66-50f9-9420-9949f808f304 |  | note | Detail - Monitor effectiveness of the ESCP Controls throughout the work
label | deb2f2a9-a4a9-5bb7-8609-637491f48a82 |  | note | Frequency - Continuous monitoring
label | 63cc1d2a-4709-5bfb-9f20-14ed9a518fe9 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measure
label | 117cb6de-7977-5ddf-a89d-862ea2d74ec3 |  | note | Conformance Criteria - In accordance with Auckland Council TP90:1999
label | b1db12f3-2503-5a26-b983-92093395b14e |  | note | Records - Audits
checkpoint-status |  |  | checkpoint | 8 - Site Clearing
label | 89299c72-2c10-502b-9a52-4a2c5e27a292 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 548609c0-1c06-5eaa-863e-f81a1337d468 |  | note | Detail - Removal of pavement layers, vegetation, services and other objects
label | 3302c992-bb5c-5ac6-9e61-e5541b03a261 |  | note | Frequency - During Physical Works
label | d5f2c338-8866-5ed9-99c6-fbf335a2d9cb |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 1ddb3baf-290d-569e-b10c-8dbd0352d5ad |  | note | Records - Photographic / Videography
checkpoint-status |  |  | checkpoint | 9 - Stripping
label | d58fa683-6287-542c-abf8-08c57da9c9b6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 08695874-4619-5375-8ac5-581eae4abed3 |  | note | Detail - Determine if topsoil suitable for respread after earthworks are complete
label | 34663f0c-9cad-57fb-b4e8-d4fc7d508329 |  | note | Frequency - As required
label | 3b5e2658-f08c-5104-8262-f1c39e55be04 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 3c988cd4-8f91-53f3-ae61-02107d8f8778 |  | note | Conformance Criteria - Stripping in accordance with TNZ F/1:1997
label | 8e930301-2aaa-5c5d-b37e-1a1bf93cfa4d |  | note | Records - Photographic / Videography/ Checksheets
checkpoint-status |  |  | checkpoint | 9 - Stripping (2)
label | fdee69fb-ff13-5991-a7d0-608b4ac578b1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a931da39-cb49-50f2-9bab-caec835b0b47 |  | note | Detail - Joint inspection with Engineers Rep and carry out topo survey
label | 514e62ca-15b0-59b2-a7ba-030a4974105c |  | note | Frequency - On completion of stripping
label | 19712ca7-f5fa-591e-9686-2c1c7b0752a3 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 9749bcff-bf08-56eb-89f2-d02c8942db1d |  | note | Conformance Criteria - Ensure topsoil stripping is complete and area is clear of organic material
label | 7c57c59e-9510-58f9-a9af-ea39a85c4a68 |  | note | Records - Photographic / Videography/ Checksheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Stockpiling
label | 1c80f65c-0716-561f-aead-4a7ddb08e0ed |  | note | ACTION (Hold, Monitor, Witness) - M
label | ad4a6a45-ae2e-5c73-9eca-69fe74f87e9b |  | note | Detail - Ensure stockpiles are separately stockpiled, exposed surfaces to be compacted sufficiently and away from runway, inlets and coastline
label | 375496d8-8f44-55bb-a81d-8689b59221aa |  | note | Frequency - As required
label | 64b5ade0-fc47-56ad-aa65-9edfe54edf95 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 9fb2e8b4-da15-5fd4-8458-0ee966107376 |  | note | Conformance Criteria - Stockpiling in accordance with TNZ F/1:1997. Stockpiles to be minimum 50m away from watercourses.
label | 1ee528f7-0c9e-525f-8ec1-b46a4705ad1a |  | note | Records - Photographic / Videography
checkpoint-status |  |  | checkpoint | 11 - Retaining Wall Foundations
label | be3c4f83-df40-5f7b-adef-9493cc67304a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9ba376f0-67ce-5ffe-a834-fd5b661be6bc |  | note | Detail - Shear vane Strength
label | bdfa4193-9535-592f-8e63-c32a1570dfde |  | note | Frequency - 1 tests per 4m2
label | a2b040b3-ca19-5c31-b67a-3984443f044f |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
label | 8e403517-ffb9-52f5-87ec-5b73fcacdb11 |  | note | Conformance Criteria - Shear vane to exceed 80 Kpa or otherwise subgrade to be undercut and repalced by specfieid granular material at Deign Engineer's discretion
label | 76d0a0e8-ffc0-58a5-a3ef-8952956ce36f |  | note | Records - Lab Test reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Cut Subgrade testing
label | a33ea9e2-fd91-5964-9fd2-e857e2a474a5 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 58d1a100-754e-5c9a-a96f-6f83c2c0978f |  | note | Detail - Subgrade Surface - Straight Edge
label | 1aa63d75-6c9a-5706-b159-6ae571d3e698 |  | note | Frequency - During Construction
label | 455d7ec5-b78c-5482-9f13-4ef63a8aa05e |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
label | a094d7cb-96f5-5d4a-a3bf-a22f0bd1df27 |  | note | Conformance Criteria - As per TNZ F/1 clause 11.2.2 - All points within 30mm of true from a 3m straight edge laid parallel to centreline of road.
label | 53689f3b-c483-5268-80c2-eb562d7516d6 |  | note | • The subgrade surface shall not pond water, where the design slope of the subgrade is 2% or steeper.
label | 30795fb8-2205-5f54-860c-436a6590839a |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 12 - Cut Subgrade testing (2)
label | d9e210e4-8c07-549e-9f96-2cefd204dcd1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8caeb890-0d5d-5e4f-975f-c6f14f58d697 |  | note | Detail - Scala Penetrometer Testing
label | f4663ab3-af2e-5e7c-8eaa-f553c1ea458a |  | note | Frequency - 20m intervals to a depth of 1m at alternating wheel tracks
label | d72fd032-ac04-541f-a119-18750c899067 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab Testing
label | 29e9dfa4-e569-50d1-ac00-3cc487a3995b |  | note | Conformance Criteria - Scala Penetrometer to a minimum depth of 1m and shall have no reading less than specified CBR of 3.5%, where Subgrade is gravel, Clegg hammer shall have no reading less than CIV 7.
label | 3074eec4-f3eb-5141-87f9-2ba13bc490da |  | note | Records - QA Sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - Bulk Fill Material Testing
label | 3a9d98e1-8fc6-5f5d-99d9-cfd3f7daf4f6 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a0974e03-dfd1-5253-8a2a-a4b6931d6b35 |  | note | Detail - Compaction shall be to TNZ F/1 with maximum layer thickness to not exceed 200mm
label | 6c627c1c-9eb8-5480-ab12-7203e3471889 |  | note | Frequency - Every 200mm lift at/ 1 test per 4m2
label | 7b4d85d5-b1e3-58d4-a1c5-f2ab3d6b2cff |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab Testing
label | 5188d2e9-a5ea-503b-aa98-bf98b70ff500 |  | note | Conformance Criteria - CIV >= 25
label | 8eb885bd-ac8c-594c-83ca-4c23144c0bf1 |  | note | Records - QA Sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Final Inspection
label | 46b67b5d-a6a9-5e78-b95c-86cb7793efac |  | note | ACTION (Hold, Monitor, Witness) - H
label | bccebad1-97ae-5d51-a0e9-9a61a2445ca3 |  | note | Detail - Subgrade inspection by Engineer
label | 16b5f509-817b-5152-860d-35beeeffacd4 |  | note | Frequency - Once per area
label | 1847039a-7287-5ebe-a4a3-c27275061d24 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 3e0e175d-7f59-5986-9c96-dcc18d606e73 |  | note | Conformance Criteria - Final sign off of subgrade by Engineer.
label | e6bdfce6-e124-5dc9-8844-76aa510a5f5b |  | note | Records - Photographic / Videography
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 15 - Retaining Wall Construction
label | b6d40f0d-6585-55e1-9eac-daf9fe478b86 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 21547ee8-a77a-5267-b308-318985d6fc6a |  | note | Detail - Material Compliance
label | 474e277b-7732-5c47-8b17-c69fd9f21937 |  | note | Frequency - During Construction
label | 38145a09-9f9d-5e04-8ce8-fa7c3b33daa3 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document review
label | aa203fd7-7ef8-5bc7-9ceb-229c6ccceb73 |  | note | Conformance Criteria - High Density H6 treated Radiata poles to be used for construction unless specified other wise by Design Engineer H5 treated timber to be used as railings unless specified otherwise by Design Engineer
label | 3477cd22-105e-537a-b919-ed7c08eabde4 |  | note | Records - Delivery Dockets/ Design Engineer Correspondence
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 15 - Retaining Wall Construction (2)
label | f358bbd1-7a76-51ed-bb67-795457ce4e05 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 5831e637-bcde-5567-9154-37b5d44e090d |  | note | Detail - Concrete Encasement
label | 626a032c-27f4-5691-9d3c-9516f26aefe6 |  | note | Frequency - During Construction
label | 3be9f0bc-616d-5e89-b9c2-66e1f9c68470 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 77f0f17d-a0ad-563a-95ed-0c62afce4f6e |  | note | Conformance Criteria - Concrete mix to be a minimum 17.5 Mpa, high slump mix, 10mm chip.
label | 069fa1ca-1941-50d0-b023-90eaa6063fc7 |  | note | • Minimum of 100mm cover below timber poles
label | 4cf00c01-e14a-5ec3-a51d-92dabcbf4250 |  | note | Records - Photgraphic / Videography / Delivery Dockets
checkpoint-status |  |  | checkpoint | 15 - Retaining Wall Construction (3)
label | b0c5c961-2e22-5a88-9717-04192e320f5e |  | note | ACTION (Hold, Monitor, Witness) - H
label | c808ce02-3461-5051-8aff-b32a86b292b9 |  | note | Detail - Subsoil drainage
label | 93fe06c5-3dc7-5959-8154-2e91a901710b |  | note | Frequency - During Construction
label | f1e3c1be-f28a-57f5-92bf-f66056771886 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | da30bc0f-b137-580c-8b8f-1918894bd4ca |  | note | Conformance Criteria - Subsoils to be 110mm preforated pipe with filter sleeve sock.
label | ffa7bd89-21a2-5f45-b3d9-510cd985cd5e |  | note | • Bidim A29 or approved geofabric to be placed between drainage material and surrounding ground.
label | 6b39060c-b959-5b7e-b772-014f5f43e0d7 |  | note | • Drainage 40/20 freeflowing aggregate to be used as bedding and cover.
label | 0b4c9fdc-b97f-5ba2-ad0c-1cbcd1165ae9 |  | note | Records - Photgraphic / Videography / Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 16 - As-builts
label | 79bd9c47-9108-59b0-a673-4f9f61c85575 |  | note | ACTION (Hold, Monitor, Witness) - H
label | db76e515-414a-57de-9199-548645c72530 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 16e6d93c-8247-5c97-a95c-983937afeb1c |  | note | Frequency - At the completion of the Lot of work
label | 1f1f476c-851c-543f-8522-35dc9bcebdcc |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings
label | eb25bc3d-c6ef-551d-b157-afcc02d9bc3f |  | note | Records - Asbuilt Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Massey Road - Aspalt Speedtable |  |  |  |  | Yes | ITP - Massey Road - Aspalt Speedtable | ad987a36-0b4f-4ff8-a4e6-8c12b1f3529a
checkpoint-group |  |  | section | Precom
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | 59069545-4c38-5a14-8e0a-81d0d8f289c5 |  | note | H
label | 45d52460-a8e4-5398-a265-ba7d8854df30 |  | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | 2c14ff3b-fd83-5d2d-b20f-d69aba5742ce |  | note | Frequency - Prior to any construction commencing
label | d8c24edf-3d98-537a-88c2-3a130e929d64 |  | note | Inspection / Test Method - Document Review,PHOTOS
label | 1ae97dac-f938-50f3-ad78-d381cc7d11e2 |  | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | a8603eca-8ca9-50a6-b1d0-ed9df083d3f6 |  | note | Records - Permit attached or permit number noted.
label | e2bffd4b-937b-5a69-9ea2-fa9c1bfdf225 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1 - Permits & Services
label | 6b14a192-d944-5b54-81be-48e1a28eb891 |  | note | H
label | bf871c2c-b797-5188-b0b5-6d1f0032efcd |  | note | Detail - Locate and mark out all existing services
label | dc8bef5a-47fe-54df-9ad0-2791d8c4e99d |  | note | Frequency - Prior to any construction commencing
label | 31aa8a2f-e4ea-57c0-b0f6-24d1a833675c |  | note | Inspection / Test Method - photos
label | b74436f8-4be4-5501-9cbf-bc298ccff63e |  | note | Conformance Criteria - B4u dig procedure - follow utility protocols
label | f5401272-f202-532e-b597-e7014b157eac |  | note | Records - B4u dig plans
label | cc96ffdc-5b19-5128-894c-6c09cccc2b99 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Permits & Services
label | 9d0c4c69-f3ca-5f23-933b-fbe6182c7588 |  | note | H
label | a30d0324-6fd3-552d-8209-155db7118f96 |  | note | Detail - Approved TMP
label | 5e2a6120-5e6a-51b2-aeae-ff13a4f59426 |  | note | Frequency - Prior to any construction commencing
label | 0b095af5-73e7-5cc6-86ec-bce24b04ad77 |  | note | Conformance Criteria - Approved TMP and WAP onsite befor establishing traffic management
label | 06ebe721-b161-546c-9a57-d242f4439616 |  | note | Records - TMP Plans
label | 21eab813-e89e-5a26-abe6-54f1e31196c3 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | b97d409a-b449-5b3c-88b0-b0bc68899561 |  | note | H
label | 4bc8b001-9b07-5d9c-9bac-766ebcf2bc02 |  | note | Detail - Sub-Contract and Supplier Agreements
label | 2a87847b-0f0f-50f1-82d1-214babb0b5a4 |  | note | Frequency - Prior to commencement.
label | 036afda7-3dac-5b33-b895-fa8d04d8ba47 |  | note | Inspection / Test Method - Document Review
label | 2445047c-438b-54ec-9366-ed77d77f4f70 |  | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | fa07fb0e-1172-529a-8c83-472f798c5dfe |  | note | Records - Subcontract and Supplier Agreements
label | 47467cac-6e65-51b1-bb28-4f5e91b00ce1 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 1a870aaa-1d78-5a7d-9c04-4db8b05369ac |  | note | H
label | 97ca1ae9-612e-51e4-9dde-87fa51e7826a |  | note | Detail - Design is approved and Drawings are of the latest revision.
label | 5770a4d9-2101-5a57-9f6c-56c3c75f8ad5 |  | note | Frequency - Prior to commencement.
label | 9febaf9a-88d2-5d86-a8fe-05b87ff995d1 |  | note | Inspection / Test Method - Document Review
label | 6be31ac1-2cb2-5a05-aa89-5550d9672132 |  | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | dee80fea-2d7d-5fbf-8a60-3d5355ed74c3 |  | note | Records - Drawing Register.
label | 85bbeb92-674c-5fdb-9b15-e82d19d294b0 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Milling
checkpoint-status |  |  | checkpoint | 4 - Milling Depth (up to 75mm)
label | 09367b90-7f09-55dd-b54d-96564c8efe44 |  | note | M
label | 9d72e033-5f5a-54b2-9125-6a5ae24e2238 |  | note | Detail - AT Contract Specification 4414
label | 03a438ef-203a-550f-9f4a-11bc4a75a0d6 |  | note | Frequency - Every site
label | 8cad0830-5586-5bea-81da-fcdbdf9a5261 |  | note | Inspection / Test Method - Review,photos
label | 0ef2b8c5-7439-52e8-870c-2c3f09da05e0 |  | note | Conformance Criteria - Surface preparation shall be in accordance with NZTA Specification M10,The Contractor shall mill the existing surface to the minimum depth required to place the specified AC surfacing layer and provide a “key in” between the new and existing surfacing.The milling depth shall be carefully controlled to ensure that the finished milled depth and level within + / - 5mm of the specified levels or specified layer depths.
label | c341a132-2add-5817-94d6-e83896bde448 |  | note | Records - Milling Records
label | f712b2e4-07b4-5dd4-a067-f96b477fd149 |  | note | FH Initials - Supervisor
checkpoint-group |  |  | section | Aggregate Quality and Lab Test
checkpoint-status |  |  | checkpoint | 5 - Temprature Limitation
label | 1a6e15f9-cd5b-5b03-be74-9486476872b9 |  | note | W
label | 39f2c928-60d2-5ce9-9b42-e1f91e7073fc |  | note | Detail - Contract Spec /M10 Spec
label | b1884833-6c1b-51d4-8802-3630b1a225e4 |  | note | Frequency - Every site
label | ae5d66da-4734-5e0b-9fa6-006bfaa17e1b |  | note | Inspection / Test Method - Review
label | 9cebe2a0-719b-5160-aa96-1edcfa40e84b |  | note | Conformance Criteria - Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temprature is below 120 degree
label | be3dde64-bab7-5d4a-9d49-4f16d6072f6c |  | note | Records - Asphalt QA
label | 05f30679-934e-56db-8b98-343c0693ac96 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 6 - Check Weather Reports
label | 1e9f9b70-259e-5dd0-b175-cd5358f51496 |  | note | W
label | 75ab4ad7-5bc0-5625-ab67-cb12004dc112 |  | note | Detail - No fog, rain or wet surface. Base temp greater or equal to 7 degrees celcius
label | cf005d22-5b31-5895-b81e-4be20b24f2ac |  | note | Frequency - Weather call 2pm on the day
label | 3207d280-67b0-5146-9e78-17dd62510128 |  | note | Inspection / Test Method - Visual
label | dbdcc902-b6be-5119-a462-19c76b42c9e3 |  | note | Conformance Criteria - Forecast and thermometer
label | aaa5a6ff-fcd4-5789-9cd1-9c74c45eb45a |  | note | Records - Radar and Asphalt QA
label | 1049f3d9-090b-5a2c-94ef-8e88536f8b67 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 7 - Pre-Seal Inspection
label | 1f84140b-33d3-506c-94a3-97ef26976a57 |  | note | H
label | 25c01a0c-af9c-544f-8976-b3816a203a01 |  | note | Detail - Surface finish
label | b228d666-821f-5e35-938c-50b92ad11fc7 |  | note | Frequency - Continuous
label | 3ae23385-b83a-542a-bebd-6466d57ed21d |  | note | Inspection / Test Method - Visual
label | e963b703-d375-5143-a93e-313f5161ae9d |  | note | Conformance Criteria - The surface must be clear of deleterious material and not chocked with fines. The basecourse surface must present a stone mosaic surface with larger aggregates protruding and not appear damp
label | ba64602d-1dcf-54e1-a587-6d92ae37e099 |  | note | Records - Sealing QA
label | 1e1d8213-25e0-5b7d-baaa-17d859467911 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1 - Pre-Seal Inspection
label | c1761e91-5c39-5aef-a48c-3cb7fb378d08 |  | note | H
label | c175b68c-147e-5e23-bb23-d0721640115a |  | note | Detail - Basecourse Compaction
label | 701a2626-b311-5d40-9920-bce8150bfe34 |  | note | Frequency - Everysite
label | 72311480-4b4f-5b0e-8bc6-98b049748c6a |  | note | Inspection / Test Method - Testing
label | d2fb85ae-0226-5f7b-83ab-7ffc7b3670ef |  | note | Conformance Criteria - Clegg CIV >25
label | e7aaaa61-1c21-5ab7-b44c-7897275940ee |  | note | Records - Asphalt QA
label | 6fec3f62-048d-5b46-8a1f-dfaef6b4564c |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Tack Coat
label | 1630dd84-550f-568e-92d9-773033dfbe52 |  | note | M
label | 47934fa4-36c2-5468-924c-257f22b28b8f |  | note | Detail - NZTA M10 Spec
label | 02954c30-5aaa-5a26-9281-58d1aebd83a2 |  | note | Frequency - Ensure heavy coat of emulsion is applied before on each layer of Asphalt mix
label | 5b4aed35-2416-5095-b734-920af9f1777c |  | note | Inspection / Test Method - Testing
label | f0fefc06-5cf1-569f-a0a5-8574855bbf6b |  | note | Conformance Criteria - minimum of 1 L/m2 is required on each spray run
label | 1dcfe227-f1d8-5835-8549-ed98d269b065 |  | note | Records - Asphalt QA
label | 573360fe-1e68-506f-ace2-1032e55082ad |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 9 - Construct AC20 Layer
label | 73b96cd3-ef51-5e6f-abd8-c9e615b26260 |  | note | M
label | 18c1575c-49b9-5a2c-9d69-75038fdc0d9d |  | note | Detail - NZTA M/10 NDM and Stringline
label | 9c1db619-6e02-537d-a880-6157fde56a45 |  | note | Frequency - Each Run
label | 20904000-a523-565f-8a42-b421df14b263 |  | note | Inspection / Test Method - Testing & Visual
label | b44a4918-0d2c-5273-8861-2df7d8637855 |  | note | Conformance Criteria - Construct 100mm AC20 layer. Design air voids 2-7% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
label | c16a08df-8229-5880-aec5-b13ac2a723ab |  | note | Records - Asphalt QA
label | 394953ab-596a-57bb-bbcc-1976825ef9f6 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 10 - Construct DG10 Layer
label | 3c4147d1-b282-5749-b437-df7ca33f1e56 |  | note | M
label | 3a17168f-7d79-5748-b6b9-c7930b03e3f5 |  | note | Detail - NZTA M/10 NDM and Stringline
label | 0042b6a8-cf25-5b6e-adfc-cfcd9143b0e3 |  | note | Frequency - Each Run
label | 227f8c9c-a6ee-5d1e-89d2-cc1c3b13231e |  | note | Inspection / Test Method - Testing & Visual
label | 617b0d51-04e0-5ace-a9aa-3d8d1074b9a6 |  | note | Conformance Criteria - Construct 50mm DG10 surface layer. - Design air voids 2-7% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
label | 3fa5f0e4-2bd7-5961-b330-3fd5c8f25ab9 |  | note | Records - Asphalt QA
label | 6085f4f2-0702-5e09-8e72-773a68dfb648 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 11 - Surface Finish
label | 23364588-2fd5-5e97-8e3c-6c8f718eb909 |  | note | W
label | f70d5763-f69b-5bba-8b3c-0232d63d03c1 |  | note | Detail - TNZ P/9P
label | a4bf1fc3-1528-5f4e-ae29-ef26096ecf8a |  | note | Frequency - Each Lot
label | 131a01d3-9697-52bd-9517-8c264b90937c |  | note | Inspection / Test Method - Visual
label | 25c8909c-d448-523d-b3c6-7e64d5559436 |  | note | Conformance Criteria - Inspection: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate
label | bb0d450d-3c16-5203-be7a-f9977a8d91cc |  | note | Records - Photos
label | 03aa2b48-5f31-50d0-9355-49654607ff31 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 12 - Reinstatement of Linemarking
label | 0073652f-19a7-51b3-9562-5300a677cc42 |  | note | M
label | 531113cf-7ecc-5a17-a5cd-463f22f82bc4 |  | note | Detail - NZTA M7 approved (Class B or C as required for anticipated traffic level)
label | c0d1dec3-b198-5d9c-8362-7cf24023e073 |  | note | Frequency - Every site
label | cb49703b-8f45-5224-ad8b-8dd94be4a0e4 |  | note | Inspection / Test Method - Visual
label | 3375d22e-5cb7-5a7b-a75e-e12b2b123b1d |  | note | Conformance Criteria - *Carried out within 12 hours of each shift completed and as per the existing markings * Suitable Traffic Control to remain in place until pavement markings have been reinstated
label | c8145bdc-1c83-55ae-94cd-41e244cfe75e |  | note | Records - Photos
label | 26c6987d-067c-54c4-a5b3-1b01873371c1 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | QA checked by Quality Manager
text | fb8d1bf3-4839-5bbb-ab8b-e6b769f8a1ec |  | textbox | Comments:
text | 3850712d-5b1f-5e34-baad-a5d340160bec |  | textbox | Print Name
text | cd75fbf3-caca-53f9-80d2-036a74e8ea65 |  | textbox | Position:
text | 0cb41a6c-0bb3-5537-b0c9-0a06e00e2237 |  | textbox | Date Completed
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Accepted by Engineers Rep
text | 8bfc4a94-278b-54e4-9d0a-dfad7cc8c737 |  | textbox | Comments:
text | 75c8f285-1237-5298-810a-ca3e5ad75e85 |  | textbox | Print Name
text | c9db85b3-d509-5863-883a-1589e775f94e |  | textbox | Position:
text | f33040d5-bc9b-56ab-b662-8bb18186bdce |  | textbox | Date Completed
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | Raised Speed Table |  |  |  |  | Yes | Lincoln Rd - ITP - Raised Speed Table | adde6438-a4bc-480d-80f6-ca9b1311a5aa
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 0b17c15a-e2fc-58fd-a090-405db2507f13 |  | note | ACTION (Hold, Monitor, Witness) - H
label | cb22230f-f5a9-5448-9cfb-b534867dd34e |  | note | Detail - Obtain Permits
label | e0cd0d3d-31cc-5bb6-8bcd-51e586a60731 |  | note | Frequency - As required
label | 00848616-cd65-5091-aca5-db4e1b5a8ebe |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | d8826d91-8afe-5f46-90bb-1cfd6f9943f4 |  | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 001624fc-314d-5e45-8b76-eb37161a2d15 |  | note | Records - Permit attached or permit number noted
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-construction sign offs
label | 99b559fd-e190-5130-817b-e903441f75af |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5335d82f-28c6-52a1-a790-46f76e278370 |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
label | a579be57-93c0-59e9-b086-2b18f831438a |  | note | Frequency - Prior to commencement
label | c0e5dc7a-b0f4-5fff-af74-d41794a0e1f8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | a6aa690a-7979-5ab6-9fc9-4d96e04dd34c |  | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
label | f1598841-5355-5913-bcf7-bc5f1d9802cb |  | note | Records - Subcontract and Supplier Agreements
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1 -
label | a3487056-cbd1-5fa9-9d7d-472fb18a3774 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ae5cd449-0910-5d48-93ab-9eab6880b5ca |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | 7d3582e3-c492-5404-aeb5-eb2c54344b68 |  | note | Frequency - Prior to commencement
label | 30df5552-d8fa-5bdf-beef-058987533ed3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 59bbd26d-4ff3-50d3-9843-bdd9a8d57ee6 |  | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | 08d4e121-0811-582a-8579-6db3c4176092 |  | note | Records - TMP on MyWorksites/On Site
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 -
label | 8936fd45-7179-5600-a5e3-86ffd06631bb |  | note | ACTION (Hold, Monitor, Witness) - H
label | fe990939-c4d0-5e45-a351-2595c3f6f812 |  | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
label | c5fdcd37-3db1-50ae-b297-52b9eb84e7eb |  | note | Frequency - On site daily
label | 60a458bf-01fa-5b8d-b748-3bdca79e96c3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Induction
label | f82d215e-da02-5f07-9c60-d11774d8c18e |  | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | 6e74de83-65dc-5ff4-9731-fcabcda039f5 |  | note | Records - Hazard ID and Pre-starts to safety team
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 2e5e053b-3a02-54c4-820d-79bc51558ca3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 928d7937-21e5-5b98-841c-3d7cdf65e49d |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | d51a6327-8c29-5fcb-b6f8-2be5b9222ba4 |  | note | Frequency - Prior to commencement
label | 33717db3-d0c8-5e55-816f-be3bc07a5321 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 1c69df19-1e49-50f1-807d-7fa7a063dbb0 |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | c5695ee8-1008-5024-b346-239c1d7a2979 |  | note | Records - Check Drawing Register
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Installation of Erosion and Sediment Controls
label | 1b8f0b41-84b3-5d37-8072-df2e0edac0c7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f344a6aa-e41b-57aa-b1c5-c6bc96c9f261 |  | note | Detail - Ensure that Erosion & Sediment Control in place
label | 945cf361-5867-5a18-8f00-9d56c0d52213 |  | note | Frequency - Prior to commencement
label | 9c26580d-5060-5371-86ce-029659e66bfd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | a275bece-a054-50fc-886c-7d7c17126efa |  | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | 541bbe28-af1f-5099-a959-dce30697c0f8 |  | note | Records - Environmental Controls Audit
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | fe31c89d-2041-57c4-95d7-544325d55135 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3927b6cd-5368-50b3-8043-62448b1b8378 |  | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | f9373efe-7200-5932-84bb-3b6e5a6e7857 |  | note | Frequency - Prior to commencement
label | 536edf3b-309e-544c-824c-1600586bd8a9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey + Smart Level
label | aa9c15ca-8dea-5a32-b8c4-e23c9bdddddb |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 99f47c4d-f6a5-5ad7-9a8a-9d27b3687922 |  | note | Records - Site Photos post surveying
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging
label | bc2ff83e-1c66-5b4d-ad1b-8314c2d3f7b4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0362dae0-cf58-5d1c-b46d-01c6f2fa9b4a |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | 6fe85a17-d167-5155-9362-4b9775ffd918 |  | note | Frequency - Prior to commencement
label | 620ad2cb-2e4a-5efd-a96a-0003485dc27d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | 589912da-6a1d-53a9-893f-806ffc42aad6 |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | 4959e6b8-b668-53b3-9272-a502bff8fb56 |  | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Material Compliance
label | e304e9f5-2f9c-53de-bb2e-8f8cdcfd32b6 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 40cad960-2f48-58c0-bf6a-dcd40bd4226f |  | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
label | 50e0b6b2-10c3-5685-8eba-585c3dbc3c7d |  | note | Frequency - Prior to pouring concrete
label | ff80a3a8-293e-50bc-935b-056a47e4220e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | a397d2f9-ddba-56ef-b635-de77d6f97559 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 580ccee6-7a14-5d5b-8808-2acb7bce19e5 |  | note | Records - Delivery Dockets / Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1 -
label | eae10ba9-c12f-5f9c-be54-093311958968 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ab050cec-a525-57d2-bcd1-b030337d3bba |  | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
label | 1738a058-ea8e-5752-98ec-233084efb0c8 |  | note | Frequency - Prior to pouring concrete
label | aaacfc3d-4a77-5dc0-a15d-354e35383e12 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
label | da64c509-f578-594d-b27d-e5501d25e79c |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | e415cbae-11cf-509f-8bcb-3b86e35bd5c3 |  | note | Records - Delivery Dockets / Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 -
label | 9472d0bc-5136-5c8a-b738-269b871c3a22 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 524ef8e0-bd8e-5be8-af5c-fea4283a251e |  | note | Detail - 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | 9dd97ed7-6104-5b91-a744-d274edfa907c |  | note | Frequency - Prior to pouring concrete
label | 1e10b23b-9857-58b3-a836-5fd973a9f906 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b54d129d-b926-5874-b8c1-ee35f63d050e |  | note | Conformance Criteria - CIV >15
label | dcbc5cf1-6b92-571d-9ccd-846dccd47850 |  | note | Records - Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 -
label | 077d82f9-89c1-52ab-a56a-377fbcde6b4c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 778c7e92-52aa-5d7d-8dc7-393b2a715f76 |  | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
label | b8fee512-448a-5e64-bd81-45d3b085e277 |  | note | Frequency - Prior to pouring concrete
label | 36051e0b-d396-534a-aebf-c63f272a046e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 9ce92d6e-299f-57ee-836a-4f9457ab1b83 |  | note | Conformance Criteria - Photos
label | ab546afc-0a5f-5fce-b76b-e225b0d73cb6 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.4 -
label | b95f88cf-cf7c-5366-aa54-7fbd39eace45 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6357d308-c43f-5e35-ace0-e37f0fa37e07 |  | note | Detail - All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
label | c9f286c2-61ff-5a8e-b570-0c8954162c52 |  | note | Frequency - Prior to pouring concrete
label | 07c46df9-83a1-5f36-b6b0-86e151675a08 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
label | fc4e426b-2fd1-5a23-920c-49cb385c1b4d |  | note | Conformance Criteria - Delivery Docket added to QA folder
label | fe78e50d-f723-5571-9d3b-304f28920fe3 |  | note | Records - Concrete Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Temporary Works (Formwork)
label | fa4d64b6-4982-544c-9a2e-f9c866c2749b |  | note | ACTION (Hold, Monitor, Witness) - W
label | d5bf2c64-1340-5dec-bf64-9ee5ca00e0e4 |  | note | Detail - Formwork to be set to correct line and level
label | 8cedd9f8-279a-5d78-8a10-640fcfd0309b |  | note | Frequency - Prior to pouring concrete
label | 8220bc1b-674d-58c9-a1d9-f34e756bc099 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | c4f78bbf-9611-50e0-9781-eb22fcbfe503 |  | note | Conformance Criteria - Concrete Inspection Record
label | 8f554579-85f0-5fb0-93b6-e4467bc0850e |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 8.1 -
label | 349b9296-4100-5467-8d2c-1498632cb7b2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 602af4c5-9e45-5dea-b5fd-fc0b5b8d3597 |  | note | Detail - Raised table formwork to be 100mm above existing road level and be 300mm in depth and gradients respectively of entry (1:10) and exit ramps (1:40)
label | ba67efa2-76d6-57d1-909b-9a43288afa47 |  | note | Frequency - Prior to pouring concrete
label | 5185db27-a933-5033-b200-41d7893b4e3d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | d9783b0e-111d-56d1-a09c-d4dfdbccc026 |  | note | Conformance Criteria - Designer to inspect formation level
label | 948996b5-9653-5ca9-938c-db49745bcf08 |  | note | Records - Site photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2 -
label | cb07691e-470b-5964-87ff-517880b04733 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 42e2b67a-a817-52b5-b696-81f2acb921ea |  | note | Detail - Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
label | 6999890c-ecb9-5480-8e31-9e5a38c98a53 |  | note | Frequency - Prior to pouring concrete
label | 03577304-a901-587e-a258-99d2cbfe6a2e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 30bba654-c0cb-56fb-aa4c-861b9b5289c4 |  | note | Conformance Criteria - Designer to inspect formation level
label | fed24be2-4704-52b1-bff3-439270e9f5b2 |  | note | Records - Site photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.3 -
label | 4e139e0f-0ef4-5b28-9cc7-6570a50d3bb6 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5a489d07-18b0-5cd8-8a84-fd020f65d7b7 |  | note | Detail - Raised Table ramps to be 1m across for entry and 4m for departure ramp.Toe to be 0.5m to 1m across for both entry and departure with 50mm asphaltic wearing course
label | c054ba66-e3cb-58da-86a1-5b1eba7ce6a2 |  | note | Frequency - Prior to pouring concrete
label | b2458f32-4c3d-5421-b2e1-db099e31c2a6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 8c687849-5762-57e6-a487-50f4f71f2aaa |  | note | Conformance Criteria - Designer to inspect formation level
label | b31d6af8-ca43-5643-a220-832cac1ae422 |  | note | Records - Site photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4 -
label | b134c657-7717-5851-867f-f45b206b1907 |  | note | ACTION (Hold, Monitor, Witness) - H
label | eab0721e-118d-5a9c-ac0d-dfab4979bd7b |  | note | Detail - Raised Table ramps to be 1:10 gradient for ramps at entry and exit ramps to be 1:40 relative to the road
label | 902c03bf-a44a-5235-8339-d8de080aecc0 |  | note | Frequency - Prior to pouring concrete
label | 115165af-5a9c-541f-a566-cc12c1f23876 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | ac60535a-7a4d-583f-9845-805c63caa3b0 |  | note | Conformance Criteria - Designer to inspect gradient level
label | f0aba105-32b2-55af-afad-c2a77709d942 |  | note | Records - Site photos / Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5 -
label | 35e35051-7199-50ff-9698-42df90a235e7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 819630de-18cc-5709-b96c-826ffe5d6ba7 |  | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | b28586e4-be01-590d-8c23-4d15b566df26 |  | note | Frequency - Prior to concrete pour
label | 6b43fe12-d10b-51fe-96cf-26e7dc4c58f6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | b5ce0672-523c-5bc6-8bb0-fbfb2d5d04ac |  | note | Conformance Criteria - Concrete Inspection Record
label | 5819468f-12df-58ff-b52b-3f5f45010024 |  | note | Records - Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Reinforcing
label | 766d95be-e9a1-5137-87e3-029d412ec425 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a2dcd3e8-9175-5256-9df6-095ec20e4c32 |  | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @600mm centres placed across the construction joint
label | c69badd4-2590-5fa2-93df-b1109434daea |  | note | Frequency - Prior to pouring concrete
label | de0ad842-7737-53b0-b908-d367229e6f14 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 95439931-f1da-566d-8ddf-5226a8ff6303 |  | note | Conformance Criteria - Concrete Inspection Record
label | e363a1a0-3e0f-5fd2-9641-3abda7bbcb60 |  | note | Records - Site photos/Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Concreting
label | c6dfbace-89ad-5ebd-b722-aa815c974d2a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2a9f864b-a1be-5223-8572-5622a2ac641e |  | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | 85fa27fe-bd2f-56f2-b9c1-d2a2612ec538 |  | note | Frequency - Prior to concrete pour
label | 6b5c799b-844b-536e-9dd6-c0fe055a5cae |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | e8d7de7e-d322-5633-9291-da8b0aa13aa2 |  | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | 17df2213-b693-5a54-b4a8-70847ff82e82 |  | note | Records - Email / SMS
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1 -
label | 2876db22-7207-5207-a0f4-dd18720172b0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 76b31725-9411-5f78-93e9-6be1aaa8899e |  | note | Detail - Vibrator to be used throughout concrete pour
label | f136b8d4-530b-5fd1-b532-3a9f5bea14ce |  | note | Frequency - When pouring concrete
label | 12f15384-432c-5b68-bdbb-8b5504da6eb4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 5cc74d85-fb7d-5c1d-8631-e77de3f4dcec |  | note | Conformance Criteria - Concrete Inspection Record
label | aaa0e6e1-b613-521b-967b-41b3efb1fa29 |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 10.2 -
label | da901c74-4707-5edc-a5ad-be9cd43edfed |  | note | ACTION (Hold, Monitor, Witness) - H
label | ab3dff82-7468-5bc8-bd26-d21282ff0642 |  | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
label | ef263e41-4304-5ad0-9701-871a9df794b2 |  | note | Frequency - At completion of pour
label | 761e83c2-2789-532e-b5a3-52f35c0a5b0b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 209479ad-bd6b-5b3c-a820-747e3b0db236 |  | note | Conformance Criteria - Concrete Inspection Record
label | 1e84ca6d-73a3-5264-9b40-395642ca10a6 |  | note | Records - Concrete Formwork Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Curing
label | 91551e83-7794-57b5-bbbe-ed42c2b38aef |  | note | ACTION (Hold, Monitor, Witness) - M
label | 4e380a02-4dd7-5001-a4c6-0a8a9e7c2f21 |  | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | 7a587172-77c4-5d85-b18c-4ae749755a42 |  | note | Frequency - Post Pour
label | d5b12ba9-d7bf-553c-9ed7-eb24bbbb5711 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Monitoring the time allowed for curing
label | f431c284-d266-563a-87f7-65944c279098 |  | note | Conformance Criteria - 48 hours minimum have passed
label | 966946b8-80c0-508c-9b5a-0c097ddede68 |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 12 - Remove formwork
label | b064d902-bae0-5134-9fdb-9497e648d4fe |  | note | ACTION (Hold, Monitor, Witness) - W
label | 727bb6d0-33f1-540f-87ca-eb18f8e37fa6 |  | note | Detail - Remove formwork after 48 hours
label | 790b8afe-0f3f-599b-89ac-45b82a558337 |  | note | Frequency - Post Curing
label | 09797a3c-d43d-5d43-96b6-0ed4c4dfa3c2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 78f234ee-0c62-5fa9-b1c3-7bc1f52e23b1 |  | note | Conformance Criteria - Concrete Inspection Record
label | c183d5a9-ff42-51b2-95ef-88586a0bb70e |  | note | Records - Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
label | 2682085b-ba7a-569e-bf69-753755f4ff80 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e8cc5ef1-4540-5053-b4b2-5f9e745e09e7 |  | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC0022
label | c1c99226-cb01-57a5-b981-c7f5e0bd75a4 |  | note | Frequency - Prior to pouring concrete
label | 1ba707f4-6bac-5710-b845-198b118594d8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | d895fe6e-89bf-540b-aebb-48813b6584dd |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 48adff46-1088-5751-a781-9979f59d456f |  | note | Records - Site photos, delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.1 -
label | 0dd0d5f4-fe33-5e2f-8449-6a82e42fc102 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 378d778b-bd5a-5583-ad7b-422458a70f10 |  | note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
label | 33b687a7-54f6-5774-ae82-38e86e51d32c |  | note | Frequency - Prior to pouring concrete
label | 708c47b6-a355-5e2a-8931-c34e5c12294a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 8e129a86-0e9a-5f56-bc58-afc74cd1718a |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 2247b6f4-2e98-542b-97e6-d3446f5d0f0d |  | note | Records - Site photos, delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.2 -
label | 16034f66-5eb8-59db-bc31-4203a308b5b8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 860d29bf-26a3-55c5-81cd-d55cc1480cb7 |  | note | Detail - Tack Coat between AC and Concrete slab
label | 51c0afb7-c9cc-5128-bbd1-ac705c17ea9f |  | note | Frequency - Post Curing
label | 356e61c8-3eb4-520a-b02e-2e8c4c8ff0ac |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 7b8e326b-7e64-5455-becb-b8195cb22075 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 1f1c3d3d-e71e-51ca-8720-c32d91f752ee |  | note | Records - Site photos
checkpoint-status |  |  | checkpoint | 13.3 -
label | 70846590-b134-5b15-9352-8200f5f3ddd5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ea9b1939-d759-540c-a0f9-b80066c15f81 |  | note | Detail - 50mm thick DG10 / Mix 7
label | 729c5d5a-4e72-5554-ae66-3b621e408635 |  | note | Frequency - Post Curing
label | fd54ced5-edf9-5ad5-ad78-770467be417c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 5c3ff950-4209-5c6c-8c7b-136f9a78ad4d |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | ce02f1c0-f11e-5150-a495-308543ddfbd3 |  | note | Records - Site photos, delivery dockets
checkpoint-status |  |  | checkpoint | 14 - Lot Number QA File
label | 2d7094d3-0f96-5952-8bc3-984db2446349 |  | note | ACTION (Hold, Monitor, Witness) - W
label | fae0a722-817d-54c4-a9f0-e0363db0ec0c |  | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | 16c941e6-5829-57a0-ae1f-5e401f9fdfbe |  | note | Frequency - At completion of Lot
label | f47357db-2d5d-5281-bd14-d888dd3b1653 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 053f3057-0a38-53ff-a1fe-3b071ee236f8 |  | note | Conformance Criteria - All QA files compiled and sumbitted to client
label | 1b5b54a9-765d-55c8-85fd-e6bb2f04bcf3 |  | note | Records - QA records
checkpoint-status |  |  | checkpoint | 14.1 -
label | f75ac87c-5afb-5420-ba1d-30cfa801cbaa |  | note | ACTION (Hold, Monitor, Witness) - W
label | 39e4ce73-c6c0-5b76-89f2-9c8df58fdb66 |  | note | Detail - Delivery Dockets to be included in QA file
label | 750b30bb-d7de-5f9d-ad82-2cdbf31d86e4 |  | note | Frequency - At completion of Lot
label | 3187deeb-2712-5707-8251-3d72bece79c1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 99266f15-62e7-5603-9111-9d34a7901362 |  | note | Conformance Criteria - Delivery Dockets to be included in QA file
label | 76f1dbfa-add7-504b-a494-511ba2544b79 |  | note | Records - QA records
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | b20f41b4-845c-5c25-8fb5-15887e29d2c4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f5f7f782-604d-5534-afdc-607e8cd15b22 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 152b8f2a-395c-5bd4-a1ba-e235f85f5ed1 |  | note | Frequency - At the completion of the Lot of work
label | 0e025228-5d0d-5ad2-92fd-4f607b1e9b8f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 90a2a424-8589-5001-94aa-f13311069fb4 |  | note | Records - Asbuilt Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | Stormwater Drainage |  |  |  |  | Yes | Ponsonby - ITP - Stormwater Drainage | af8a69a2-59b8-4331-8fb0-ff09ead039ac
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 726ed22a-0265-5046-acfc-949718f2dc70 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 28575627-8e6c-554a-a62d-40d83fb15cec |  | note | Detail - Obtain Permits
label | 02841cfc-e126-569a-b643-ef59fec31734 |  | note | Frequency - As required
label | 0d187424-db09-5ece-980e-f51da078396e |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 35523236-36c1-5178-900a-1c5b7ae740aa |  | note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services). Notify Worksafe NZ if required.
label | d9f61189-f6de-5384-ab9b-245329c84f29 |  | note | • Ensure all necessary Permit to Works & Controlled Checklists are in place
label | ece9c29c-c98a-595b-93d5-c694234de7ae |  | note | Records - Permit attached or permit number noted
checkpoint-status |  |  | checkpoint | 2 - Traffic Management
label | c9682f06-c5f7-5b21-959a-3543e2f5f7ed |  | note | ACTION (Hold, Monitor, Witness) - W
label | 81f35a0f-50a4-5a79-ba37-d09ba1d9b423 |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | 1810fb46-0df8-5070-afe9-ffdfd49a5057 |  | note | Frequency - Prior to commencement
label | b4eff5fb-55fa-5b34-bf6c-6f898a7e12c2 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | b7c1d525-26d2-54b2-b490-7f149f3494e3 |  | note | Conformance Criteria - TMP is approved by AT for the site and works are completed within the approved dates
label | 3237be67-4881-56c6-9d91-02e3232f58b9 |  | note | Records - TMP on MyWorksites/ On Site
checkpoint-status |  |  | checkpoint | 3 - Pre-construction sign offs
label | 3860a3bf-88d5-5aeb-8d0e-dfdb735a954a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4af12cb4-505b-54f3-ab85-e829fa100b2c |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed and that personnel have gone through the NWBI induction.
label | fd18da35-4bad-5f54-9f66-1d0f43ccb002 |  | note | Frequency - Prior to commencement
label | f28a843e-897c-5c69-9b4a-705bba0ac9e7 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 0f7c5f82-e8b6-580c-a388-b780accd8b05 |  | note | Conformance Criteria - Signed subcontract & Supplier agreements. Issued induction stickers and number
label | 484f7217-8448-5fbd-9f52-08d0dd7aeaed |  | note | Records - Signed Agreements, Updated Induction Register
checkpoint-status |  |  | checkpoint | 4 - Design
label | 7ff3cc8b-6b24-5884-bece-c50e78b98859 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a9992d1e-0d8a-5e12-acf4-ca8d1d77fe3a |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | c7a9f118-18b4-52f3-9b79-17fa8bc2e786 |  | note | Frequency - Prior to commencement
label | 967b3415-8c9a-5841-a521-54ed76654166 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | bffdf83c-e20f-54d9-9d91-68503f957094 |  | note | Conformance Criteria - IFC label on drawings
label | bc8462d7-9a0f-583f-814c-cf075538f770 |  | note | Records - Check Drawing Register
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | 1c35d076-2b1a-5dc6-80ff-3da6adb04492 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 3633c25f-6285-5e4c-be08-f6807485f658 |  | note | Detail - Set out pegs installed every 10m of the footpath showing the FL.
label | 2204aceb-edde-527f-b739-ff54ffc83f51 |  | note | Frequency - Prior to commencement
label | e055f37a-fe9b-58ec-b735-23039e6dfa0c |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
label | b5c4e1c0-1dc4-5157-ad5b-f6decc3f85ef |  | note | Records - Visual Inspection
checkpoint-status |  |  | checkpoint | 6 - Material Compliance
label | 785d41be-f89f-53ae-8519-0a53e9567a20 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 480c9ccb-c11b-5e5e-ba54-5fea0f317aef |  | note | Detail - Bedding, Haunching and Backfill Material
label | ca09e1f1-ba23-5b53-b5a7-df8f796e6c7d |  | note | Frequency - Prior to commencement
label | 6d08d101-05eb-515f-abf7-9c2500906429 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - AS/NZS 3725, AS/NZS 3500.3
label | 0a46ddc1-e147-5a31-8c94-08a28b97da90 |  | note | Conformance Criteria - Crushing Resistance not less than 100kN. Maximum percentage of weight passing 0.075mm sieve shall not exceed 10%
label | 118331d8-8a9a-5b88-a371-3e48473c7740 |  | note | Records - Test report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Pipes and Precast Units
label | d33772ff-6482-5f3f-9aa0-a85da90b98e8 |  | note | ACTION (Hold, Monitor, Witness) - M
label | bc6c4942-3cc1-522e-88f8-0e80786f2aaa |  | note | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | 277f9d4f-a939-5f6e-9b11-d2bdebaeceec |  | note | Frequency - Delivery to site
label | c498f391-f90e-52ec-9da3-c079c0934b5f |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 46c4c061-1c9f-5b5e-9344-d270bb25c52f |  | note | Conformance Criteria - Pipe - Diameter & Class, Manholes, Catchpits as per SW CoP and AS/NZS 3725
label | 85abe99f-eac1-5913-ba08-e0a185211b60 |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 8 - Trenching and Excavation
label | e186bfed-7927-5494-bfc6-de5087b3bc42 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 53c84240-4c6e-574b-97f6-61d7127e1614 |  | note | Detail - Inspect trench profile and ensure it is correct to lines and levels to design
label | c60527c7-b371-5e08-8545-5b3b6bf24422 |  | note | Frequency - Daily
label | 648f4d4c-ef61-5fcb-9742-15ceef6daf7d |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection
label | 306d0647-fb43-569a-86af-db604d065b59 |  | note | Conformance Criteria - Line and level is correct
label | f070f8e5-2b83-59dd-9ced-e5c16331861c |  | note | Records - Checksheet
checkpoint-status |  |  | checkpoint | 8 - Trenching and Excavation (2)
label | 0aed77cd-19f1-5c71-87d0-2fffbc6ea6c4 |  | note | ACTION (Hold, Monitor, Witness) - M
label | e15bbb78-d7e0-5b81-81e1-ae2c51f19868 |  | note | Detail - Ensure trench width is sufficient as per AS/NZS 3725 namely 3x Diameter of Pipe
label | c1fa2a7a-e7df-51a8-ba72-063c43868dba |  | note | Frequency - Daily
label | eaa71966-ed55-56bf-8e8f-ddf95c81d2fc |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 86e64940-ec15-5e83-b566-d7e30bb03664 |  | note | Conformance Criteria - As per AS/NZS 3725
label | 79d64fcb-2506-53ee-bdf0-a8caf5589984 |  | note | Records - Checksheet
checkpoint-status |  |  | checkpoint | 9 - Foundation Compliance
label | 99d880ae-db55-5f50-abe4-0785a6a48d56 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c5ed77ae-f337-5fc0-9feb-c7c45702e880 |  | note | Detail - As per specification, Shear Vane <50 KPa 2%<CBR<3% Undercut 150mm, CBR<2% Seek Design Engineer's advice
label | ae198050-27be-5760-91ff-33727c2d58e5 |  | note | Frequency - 1 Test every 20m
label | e1a9ee19-9932-54d9-8973-16021fb8bea3 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
label | 21798ea5-ac50-57ce-9250-19b72d2da5a3 |  | note | Conformance Criteria - Shear Vane >50 Kpa, CBR > 3%
label | 3df92bd4-befa-5301-8f4e-f3f36977f874 |  | note | Records - QA Sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Undercut Backfill Material Compliance Testing
label | 1c61b839-eda5-5c98-bb1e-3c45ef4958f8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 752a161e-5374-53d4-8cda-8ab6c4f5aa4b |  | note | Detail - Undercut If subgrade fails testing requirements and replace with copmpacted GAP40 for depth of undercut
label | 57e1f221-aaf7-50e8-b8c6-91147583d1fd |  | note | Frequency - 1 Test every 20m
label | 240b3e64-2ae7-5320-81d4-6b665a23370a |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
label | 6aec1e21-9e6f-50b4-a789-fcc85d9a7759 |  | note | Conformance Criteria - CIV> 15
label | ae9f617f-4e73-50ee-a5ed-c86483ba55b0 |  | note | Records - QA Sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Pipe and Structure Bedding
label | da803391-8d18-5abe-8063-c133c0c0982a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3bc39311-0a0d-58b3-b956-4567c9db2dbb |  | note | Detail - Specified Bedding Construction Material
label | 6736174f-e90d-5bc6-b30e-d96171833c2a |  | note | • Pipe Diameter<300mm bedding, side and haunch zones to be 100mm
label | 944d0532-ae38-5b8d-b049-5448515614ba |  | note | • Pipe Diameter >300mm bedding, side and Haunch zones to be 150mm
label | 58817efa-5763-51c5-af59-3c33a850366a |  | note | • Stucture Bedding to comprise of a 75-100mm levelling course GAP20
label | 6b0f43b8-f901-5e7b-b39b-caa56df657eb |  | note | Frequency - 1 Test every 20m
label | d43c5ac7-000d-5944-8f86-763ab59a4ef4 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
label | a306334b-9a84-5bb6-96d2-4b5200438ba9 |  | note | Conformance Criteria - As per AS/NZS 3725 Minimum Bedding, Side and Haunch Zone CIV > 15
label | c5646731-c832-58b3-8021-27a777a1bf3b |  | note | Records - Checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Structure and Pipe Backfill
label | 302740f7-b5de-504f-8190-0eb09d9dd0f2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 469742c0-7288-5e6c-8471-bc3ee95b6aab |  | note | Detail - Backfill zone compacted in GAP40 layers no greater than 200mm .
label | b5505faa-d93a-5727-ba2c-af4f2bb43775 |  | note | Frequency - Test Per Structure
label | 58accbe1-f6f9-53ce-9c69-d5e1108eb466 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 11868c7b-0db6-590f-8917-29b724ed1390 |  | note | Conformance Criteria - Compliance with requirements from Specifications and SW CoP.
label | 54be1ad9-de52-5651-a93b-0b8c3a9dd6dd |  | note | ○ Under Carraigeway
label | 1b36226a-82cc-5980-bcdc-9d974a766ac5 |  | note | • CIV >=32
label | a816191a-acf8-5286-b50b-b4758b7543c3 |  | note | ○ Under Footpath and Berm
label | b9f30c3e-a2f2-5a8a-a121-974bcc2ea2af |  | note | • CIV >=25
label | 7c4f2eaf-16f3-5982-80ca-0c4d5d9053ad |  | note | Records - Checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - Pipe Laying
label | 58ba8f54-d8cf-568f-b168-9a7c785b7252 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 438fa695-f0dc-5494-a78d-44992e8b9570 |  | note | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place and sealed.
label | efc0fa92-c20a-55a7-b384-bb6f70cdd23c |  | note | • Ensure Pipes do not exceed ±25 mm from design levels for any five metres of pipe
label | 868b2ba5-5193-5532-8e60-9bb5843408e2 |  | note | Frequency - Prior to backfilling
label | 509d6285-e8e0-597c-81f9-e0b754884c6c |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection
label | 1be76ef1-bb2f-5b26-b280-0485379c6fcd |  | note | Conformance Criteria - No defects/ gaps / pipes are aligned correctly. Compliance with the Stormwater Contract specification
label | 1e88b06a-af70-59c0-8ad6-77a5caf697f9 |  | note | Records - Photos, Checksheet
checkpoint-status |  |  | checkpoint | 13 - Pipe Laying (2)
label | 61a37e10-47f8-5b61-9c86-dd0e5109dd54 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 36f28837-0dc9-5f71-9b3e-39851e599527 |  | note | Detail - As-built survey of pipes installed
label | dd82a445-5300-5c62-a106-a125634904a8 |  | note | Frequency - Once line is completed between 2 structures
label | b2dc19e7-0340-55a0-b423-fb669c69bb80 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
label | d1f11e1b-54f1-51d9-8572-87a8435ec49f |  | note | Conformance Criteria - Survey Receipts
label | 34fc100a-fcf5-5082-87c7-93cc431bd984 |  | note | Records - Checksheet
checkpoint-status |  |  | checkpoint | 14 - Trench Overlay Zone
label | 64a84133-95fa-5dd8-85fd-8f881940b57a |  | note | ACTION (Hold, Monitor, Witness) - M
label | d4d6ebd1-d558-536b-96c0-84898eda3191 |  | note | Detail - Ensure correct thickness of compacted overlay zone - 150mm overlay above top of pipe for Pipe Diameter between 300 and 1500mm
label | 0075abd9-7e43-5c51-8e3e-1ecda5b0ce0a |  | note | Frequency - During Backflling
label | d5d5b995-0d15-540d-8014-f3ecc087b4b1 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | c434e2af-9399-544b-8455-caa5bc1fefd2 |  | note | Conformance Criteria - Compliance with the drawings . 150mm overlay above top of pipe. Refer to AS/NZS 3725
label | a77b9ef5-f635-59bb-b9b8-9f59bc835286 |  | note | Records - Checksheet
checkpoint-status |  |  | checkpoint | 15 - Pipe Backfill Compliance
label | 290a7d41-3a4c-5819-aabc-d8245296a839 |  | note | ACTION (Hold, Monitor, Witness) - M
label | da9d896b-e311-5c25-b99e-1e4b16ac5c1d |  | note | Detail - Backfill zone compacted in GAP40 layers no greater than 200mm . Requirements based on pipe location. Minimum cover 1200mm from top of pipe in carraigeway and 800mm in berm. If Cover cannot be achieveded seek advice from design engineer
label | 67a1916f-01bb-54a0-860f-f1004fec7cd5 |  | note | Frequency - 1 Test every 20m
label | b0c27732-233c-5223-9b8d-7eceb0241279 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review & Testing
label | dc6fa5cb-7354-5c77-a198-1659b5eebeb3 |  | note | Conformance Criteria - Compliance with requirements from Specifications and SW CoP.
label | 3cda05d3-e554-52ed-b106-b4aec41640dd |  | note | ○ Under Carraigeway
label | f91dc94a-6d37-5246-a629-c287a6131054 |  | note | • >=95% Compaction and CIV >=32
label | 1601107c-9a65-5b30-be7f-50b80864b38a |  | note | ○ Under Footpath and Berm
label | 7eeb8c22-973d-5f17-997d-16c6fc80ffb8 |  | note | • >=85% Compaction and CIV >=25
label | bc13c6e9-90d7-5ef3-a964-f79eb7a83495 |  | note | Records - Checksheet, Lab Report, QA Sheets
checkpoint-status |  |  | checkpoint | 16 - Structure installation (Manhole, Catchpit)
label | a4526281-5ddf-5fb4-a0b3-6f5f58edaf9c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 35715d0f-186f-55b5-8c25-d7cb7ea1727c |  | note | Detail - Galvanised Step irons required in chambers over 1500mm deep
label | f5598ee4-9636-5781-bef9-490a249fa801 |  | note | Frequency - As required
label | fd74dadf-09e3-5c19-a7ee-183c5c912f6a |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection
label | 39a8aa61-9e3a-5957-a843-6bfdc3f5c755 |  | note | Conformance Criteria - Maximum 600mm from manhole frame to first rung. Maximum 300mm between rungs. As Per ATCoP
label | 0552e1cc-8b49-5612-ad71-ba89e943acc4 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 16 - Structure installation (Manhole, Catchpit) (2)
label | 292beeaa-763e-50e7-a31d-23ea0e6c8f92 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4a678761-9448-592a-a82c-fcb374885abd |  | note | Detail - Structures to be installed to the design survey location and level
label | b9947eb6-3e46-505a-8bf6-233b80a684f2 |  | note | Frequency - During structure construction
label | e8e072f2-802f-55a6-a2f1-f46c5984d3b5 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection
label | 13ee374d-dc8d-5a5b-a3c7-2c45e95e3f22 |  | note | Conformance Criteria - Survey markouts for centre of structure and insatllment to be from centre of structure
label | dda8b98a-0f42-5ff5-958e-9801e7b5b6b1 |  | note | Records - Checksheet
checkpoint-status |  |  | checkpoint | 16 - Structure installation (Manhole, Catchpit) (3)
label | c9ca57a4-4dd9-5edd-bb24-941a2df5b6ae |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8164eb88-d49f-591c-b79e-4c398800de08 |  | note | Detail - All joints are to be sealed including rungs and lids
label | cb414c0c-ed0a-5ad9-9601-09263b51faff |  | note | Frequency - During structure construction
label | d8c266a5-c406-58a2-ab98-2400d918c16b |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection
label | 3fc30eca-cb3b-5c37-b82f-382f91bec6cb |  | note | Conformance Criteria - 25 MPa concrete to be used for throat haunching and cradle around inlets an outlets
label | 5b139abf-2550-542e-916c-cd8adc122b5d |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 16 - Structure installation (Manhole, Catchpit) (4)
label | 5a7f6bdd-68c2-573c-9227-00c3f14a4c29 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a139d73a-748d-5fb8-ac3f-3d7662f1276c |  | note | Detail - Adjustment rings to ensure correct level and fall to cover
label | ebd23ceb-02c4-5933-9258-6b10103b9ca1 |  | note | Frequency - During structure construction
label | 0e4e3bc2-9605-5a68-93d0-b7c1ab0956b1 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection
label | d91ac48a-4a01-57d3-aed5-722f94317205 |  | note | Conformance Criteria - Maximum throat depth on manholes to be 450mm. Miminimum riser usage is required and minimum riser height to be 300mm. All Joints between risers must be epoxied
label | 09ba41da-2d8a-5612-b97d-f2b371a87b83 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 16 - Structure installation (Manhole, Catchpit) (5)
label | 5c248908-94c4-5ca7-9ff4-eec821c76e87 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2648f60c-710a-5150-b0e9-17d9f086d815 |  | note | Detail - Concrete benching
label | 4f29a29a-f30a-5f7c-8d97-1840060d9076 |  | note | Frequency - During structure construction
label | 7700eed1-3820-5f6e-9bb0-f57b41005a67 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection
label | 8df839b4-b7e0-5bd9-8311-9be68525d305 |  | note | Conformance Criteria - Benching at base of Manhole shall be formed with 25 Mpa concrete.
label | b05e8268-76f3-5f15-a83d-791612088d40 |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 16 - Structure installation (Manhole, Catchpit) (6)
label | d5d1058b-3994-53ed-9f14-6e9626a8d7e3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3028937c-3797-54ab-b995-267a6f180945 |  | note | Detail - Manhole covers & frames set to correct level
label | 80d6ccb7-aea9-5091-8ff0-c779841b22c6 |  | note | Frequency - During structure construction
label | 19bd8857-7694-5214-93ae-6a3e7cf7c900 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection/ Check
label | 8dc16677-1e9c-58f4-843f-ee9784d42404 |  | note | Conformance Criteria - Heavy Duty Class E manhole covers required in trafficable areas as per AS 3996 400 KN rating
label | 5ba306f8-8631-5abf-8409-ebfb61a96a89 |  | note | Records - Checksheet, Delivery Dockets, SW CoP
checkpoint-status |  |  | checkpoint | 16 - Structure installation (Manhole, Catchpit) (7)
label | 22cca6a2-36ba-5e16-8a0c-550c03099e7a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2a537e3f-89df-560a-94da-8d404347e6e5 |  | note | Detail - Catchpit sump depth
label | 92994a78-169d-5333-adff-8a2e8fb625cf |  | note | Frequency - During structure construction
label | 74f1feea-bb5a-5699-b14a-83c1ddccf47f |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
label | d2f8b409-221e-5657-86e5-63644bb437c8 |  | note | Conformance Criteria - Minimum sump depth to 450mm as per AT CoP
label | 9235ddd9-3853-533b-933b-1cbddc54af2e |  | note | Records - ATCOP
checkpoint-status |  |  | checkpoint | 16 - Structure installation (Manhole, Catchpit) (8)
label | 892a4937-85bd-582c-94e1-c70ddeb3323f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 39a5c023-a429-5a4f-8a47-4a9dbb922eb0 |  | note | Detail - Catchpit grate levels are set to correct level
label | 380ba071-a1f7-59d5-99e5-548b436f241a |  | note | Frequency - During structure construction
label | c4136fd1-3888-51e3-b81c-26320833f27b |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection/ Check
label | cb5ae1bf-8db7-5714-b70d-44bc77400ac8 |  | note | Conformance Criteria - Measure on site and must be Cycle friendly Class D lids as per AS/ 3996 rating 210 KN
label | 2e4a26a9-b582-523f-a76f-da4c6e11cf5d |  | note | Records - Checksheet, Delivery Dockets, SW CoP
checkpoint-status |  |  | checkpoint | 17 - CCTV
label | 013d6f61-7cd1-54e3-b06d-1e6529d4407f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 56f9adde-5b53-5326-bc92-9002fe555db5 |  | note | Detail - CCTV record at completion of trench backfill and prior to final surfacing
label | 283a3411-a2b7-57ef-a748-50017ba9b8cb |  | note | Frequency - At completion of the works
label | b0dad5a1-bdaf-5e8a-ba20-5e82d601177c |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection/ CCTV inspection
label | d72790f0-2dc0-5434-8d12-2662e3d49604 |  | note | Conformance Criteria - No Defects
label | 7777035e-62ae-51b8-a971-5639ccf4b5f4 |  | note | Records - Inspection Report CCTV
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 18 - As-builts
label | 676cb2b0-b61b-51a3-8185-c76a3f7780f7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c26332da-21f6-56aa-b391-93c03a944065 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | ac679274-a20e-513b-a807-5572d1f8f9e3 |  | note | Frequency - At the completion of the Lot of work
label | 9173295f-a55c-5b37-9c35-e7d152fae3ed |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings
label | 8513c80b-e85a-5293-b87a-6ab5447d4d0e |  | note | Records - Asbuilt Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Ducting and Traffic Signals | itp |  |  |  | Yes | Triangle/Mokora - Ducting and Traffic Signals | b3c2130e-9f1d-4366-b99e-506a112601c8
checkpoint-group |  |  | section | Ducting
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 53b2afc1-acb2-586a-8571-a49eea0c611b |  | note | Inspection / Test Point - Permits
label | 27032a19-e659-5ff9-9298-77aca02897b9 |  | note | ACTION - H
label | 42f13e09-0ade-514d-b0f1-a0e38214747b |  | note | Detail - Obtain Permits
label | 8c4e987e-3e56-5535-afc2-7374dc74dbe2 |  | note | Frequency - As required
label | d2d315b8-0ee7-5561-abdc-9ab715d5fc78 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | ef264d2a-23e3-50ef-90dc-7f7b45fc8e79 |  | note | Conformance Criteria - Authorisation to work, dig permit and first gas permit obtained
label | 96e422b0-d724-55ba-801b-df0b27dca77d |  | note | Records - This ITP signed
label | 86514a1e-a924-5bd5-a1af-d2337cba11ba |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 2 - Design
label | c02560ae-fcd2-59fa-9157-4ef01b73e1b0 |  | note | Inspection / Test Point - Design
label | 16be970f-c364-5af2-91dc-7a9f7c4106bc |  | note | ACTION - H
label | 281a2c6d-cedc-5d5a-acbf-1e106d73c880 |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | 4b7debbc-31c1-53b9-8be8-466487abc5ab |  | note | Frequency - Prior to commencement
label | b56042f4-2c79-5a73-b08b-c2a4d2cf51e8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 6eec18cd-fc51-5d33-8b01-d72c817fdae6 |  | note | Records - Check Drawing Register
label | 8df0694c-fce7-5626-98dd-e5c0471f3567 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Survey set out
label | c079b95a-09b2-5707-9b6e-e5fc800b9d93 |  | note | Inspection / Test Point - Survey set out
label | f0b8b5bf-d839-5376-b160-ef311ae4d2ee |  | note | ACTION - H
label | 1262a144-88a8-5daf-b355-a48e2d1ab3a5 |  | note | Detail - set out ducting alignment and EOS FL depths. set out and mark all known services along the cable corridor.
label | 4d75dc16-19c5-5e1f-89a2-7c6d9ac18320 |  | note | Frequency - Prior to commencement
label | b082723b-36d5-5351-9f0d-84ff31499389 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 982a56f1-6bef-5997-ad54-99cadbed28b1 |  | note | Conformance Criteria - Consistency with Drawings and Specifications
label | d53432f1-8ff8-52dc-bbbd-4ec83d7fccfb |  | note | Records - Survey Records
label | a465725c-6c0a-5372-8a3c-e06e1c4a3ac6 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1 - Survey set out
label | 7efc82cb-49c8-54c4-b6fc-9e938ca1206b |  | note | ACTION - H
label | 493c628c-4cc1-5e10-ac5a-28ee1bde0343 |  | note | Detail - Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
label | 0245a2c0-c98d-5163-9e19-d2e166358a40 |  | note | Frequency - Prior to commencement
label | d620ce6f-a5c0-5ee0-bc7e-fc23aeb594e1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b664973e-5778-5886-89e0-a81910ca3baa |  | note | Conformance Criteria - Consistency with Drawings and Specifications
label | 3074b02c-f637-5db6-b31a-f5ae71c08d37 |  | note | Records - Photos / Engineers approval documentation
label | 1fa5f70a-b366-5260-aec7-52ad1a7d2955 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Locate existing services by hand digging/ hydrovac
label | 6c92a8cd-cf76-566e-aa8e-496d3fcd96c3 |  | note | Inspection / Test Point - Locate existing services by hand digging/ hydrovac
label | 769fa145-c025-5d4a-b7d4-8b323d892863 |  | note | ACTION - W
label | 7560d5f1-0f10-5928-b7e1-0b195f3895ab |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
label | 12a9894e-25fd-5fc5-83f2-822440e58bb5 |  | note | Frequency - Prior to Installation
label | 4106413a-20a4-5c72-9090-797ed2273555 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | bcd9e38b-05a2-5ade-a345-20432fd9092f |  | note | Conformance Criteria - All conflicts have been located and survey as built recorded
label | 81087485-4ed2-544e-8518-01280fae6130 |  | note | Records - Digging/Excavating Control Checklist
label | 4ebf0403-ba09-5574-9174-7caa292c33c5 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Material Compliance
label | a9e61cc5-f137-537c-9f9e-71d3d94270b0 |  | note | Inspection / Test Point - Material Compliance
label | 1a7bdcf1-aa37-5c02-ac88-64df113265c8 |  | note | ACTION - H
label | 005224a5-6262-534c-8882-7103d01b4456 |  | note | Detail - Ensure duct pipes and poles are as per drawings and specification
label | 52c532e4-75ad-5ba9-b0d9-d2cf59d8e546 |  | note | Frequency - Upon delivery to site
label | d06abdf9-ee02-5661-ade1-b4a1bae49692 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials
label | 83242b78-99c7-578d-aedd-009f8b3e9d8b |  | note | Records - Delivery Docket
label | c50d31fd-0cf6-538a-8bb9-a346a11758bf |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Trenching
label | e5f2d25d-38a3-5887-aa89-cf5d6e4625e1 |  | note | Inspection / Test Point - Trenching
label | 61f9d35b-8be3-5225-8396-167f9d81b646 |  | note | ACTION - H
label | 8df9515a-030d-5ba7-bccf-804868095f5c |  | note | Detail - Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm (900mm cover when under road crossing)
label | 3550e339-9b88-5062-97ab-3a4f35d211cf |  | note | Frequency - 10m Intervals
label | e9956d82-2610-5ed9-b717-67e271575978 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 5f7795f6-e1b3-5f9f-a64d-3aeda3ccdf53 |  | note | Conformance Criteria - Consistency with Drawings and Specifications
label | 00937cb7-382e-5ad9-89df-4b16e77c3e39 |  | note | Records - Photos
label | b2f86b6c-afb3-52f6-bf96-e496ebc88abc |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.1 -
label | cf6ecbe2-284f-5f77-b6b4-d9cca9868007 |  | note | Inspection / Test Point -
label | bb6d3611-6d4e-54cd-97dc-14679dcd4712 |  | note | ACTION - H
label | 0e528504-fb0e-5fa4-8c0b-404fc014d4f5 |  | note | Detail - Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
label | d97d23a5-7cf1-5f58-9463-0b89cf7ad053 |  | note | Frequency - 10m Intervals
label | cbc1471c-a27b-56b7-a763-02259a22bbb9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | d052d515-ea10-5e89-9072-4a48215300c1 |  | note | Conformance Criteria - Ensure trench alignment and levels match the design drawings
label | 18fac6c7-bafc-5b3e-971b-0059fc361dd0 |  | note | Records - Dipsheet & Photos
label | bcf6bbaf-2aac-5810-8c5b-d53741fb01cf |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Duct Installation
label | bc8ae8ce-8fc9-5607-8709-adc5aedaf6c7 |  | note | Inspection / Test Point - Duct Installation
label | 5cb6ec98-461a-53d9-9cfe-b0060188d9ec |  | note | ACTION - W
label | ab3431d8-952c-5508-bc8c-11f9008d6a57 |  | note | Detail - Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
label | 3ec326b5-e566-5526-b719-53d05a9166d5 |  | note | Frequency - Prior to Installation
label | 1121f70b-0f12-54dd-8757-0efd37c73eb0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | aa8f4dbc-7109-52db-804e-3249a040e55f |  | note | Conformance Criteria - Consistency with Drawings and Specifications
label | 65226926-304b-5bc8-a616-14e82100bada |  | note | Records - Photos
label | e4e44f17-c344-511a-9645-5d2cdaf60619 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 7.1 -
label | 8fce1be5-6d0b-5aec-a22b-80e3444386b7 |  | note | Inspection / Test Point -
label | 750829ed-8501-5c97-8353-f6284ef90a83 |  | note | ACTION - H
label | f1e4cd5c-5fbe-5dbc-b193-0b90d45da2b6 |  | note | Detail - Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
label | 7edfce79-6205-50d1-96b2-8bbb86e1c06d |  | note | Frequency - 10m Intervals
label | a02f995b-241b-5d47-b7da-983e7b253096 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | a9a598b8-9bf6-502e-98e3-f133b98b8db9 |  | note | Conformance Criteria - Consistency with Drawings and Specifications
label | 6de345a9-1fa7-591e-be9a-a1f29a0d920a |  | note | Records - Photos
label | bc73b671-b632-5949-b13d-d52f879b30d9 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 -
label | be0d88b7-131f-554d-a60f-533bfabdc65f |  | note | Inspection / Test Point -
label | 84f14dc7-1d8a-50e6-9708-13d87573b0fd |  | note | ACTION - H
label | 30f0d793-b730-5d03-8ebd-0c3060d3995f |  | note | Detail - Asbuilt Survey
label | 144b2fa2-72e0-519f-9758-7ea1d0de01df |  | note | Frequency - 20m Intervals
label | 71435f5b-456e-54fb-a949-0d2ade028464 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | b6d7e403-52d5-5c0e-ac1a-fb5b1ea8dae4 |  | note | Conformance Criteria - Consistency with Drawings and Specifications
label | de5bf9b7-281d-5125-a01b-b5eceb81b860 |  | note | Records - Survey Records
label | b9fb9620-f1af-59f9-a01d-dc648632df01 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Bedding
label | 3faa6602-9016-5e42-8a67-4a98f1c8bd28 |  | note | Inspection / Test Point - Bedding
label | 5311bf78-3228-5b8f-a93a-a81c625c2d7e |  | note | ACTION - H
label | 7c48b95c-a50f-5d11-8db4-e0e857b8c36d |  | note | Detail - Lay min. 150mm gap20 or finer for bedding and haunching
label | 80f5f053-f105-5a70-9ed5-0b9c06d80ae8 |  | note | Frequency - 10m Intervals
label | c8dc7356-e151-515c-88c1-d5c5786b38b9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 296cca00-7431-55f4-b11f-f44af477e57f |  | note | Conformance Criteria - Consistency with Drawings and Specifications
label | b91eff43-0716-5921-b9e0-ed4b60a01a8b |  | note | Records - Photos
label | a5237a77-c7ed-53d4-b26a-1133383bf05c |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Warning Tape
label | fe88d8f1-4a01-5673-9715-6655a121791e |  | note | Inspection / Test Point - Warning Tape
label | f62c2bd1-9abd-548a-b6e9-97f65a1d9768 |  | note | ACTION - H
label | 3c0dc7c5-2645-529f-9039-74bedc53a9d1 |  | note | Detail - Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
label | aa6e97fc-278e-515b-b0de-68aa68f9cb56 |  | note | Frequency - 10m Intervals
label | 7bce4963-863c-5f54-bdcc-287f4785e85f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | b08bc8ad-d98c-5100-9c7b-3274cc39e761 |  | note | Conformance Criteria - Consistency with Drawings and Specifications
label | 2389f1bc-6cc8-5e5c-9e56-5b4ee74a9dc2 |  | note | Records - Photos
label | 791d2d5c-92d9-5ee4-aea2-5152f9ab296f |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Traffic signal pole erection
label | 6dc48d30-2745-5d8d-97d5-178773da85ff |  | note | Inspection / Test Point - Traffic signal pole erection
label | d0f82e00-2637-5ef3-bf8d-6a48bb3eeb80 |  | note | ACTION - H
label | 362449a6-12fa-5fcb-a7ca-d07a7e693a77 |  | note | Detail - Ensure Design engineer as inspected pole locations prior to proceeding
label | 2adba43c-8a77-5af9-81e9-d0db99db1117 |  | note | Frequency - Per pole
label | 2fbedb18-435c-5099-b28f-01d67cf055ae |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | cb1ea257-edb3-5008-a100-b0470302a9ae |  | note | Conformance Criteria - Sign off by design engineer
label | f7896853-772c-5d66-837a-74447b18e130 |  | note | Records - Engineer sign off
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1 -
label | 870c77cc-e7f4-5774-9c47-19e86721bf37 |  | note | Inspection / Test Point -
label | 6a45e845-5708-5c34-bead-2e7d06d1423b |  | note | ACTION - H
label | ec659785-3bef-5a83-8ae4-74e068d8b40c |  | note | Detail - Ensure Pot hole is as per design with required depths and widths
label | ab88dd10-0511-5c09-b565-2af632930747 |  | note | Frequency - Per pole
label | e00553a0-bf23-5717-a588-4e5bf8932d02 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 6255f427-dada-5d44-bb6d-c8e2d083c046 |  | note | Conformance Criteria - Consistency with Drawings and Specifications
label | 55849a49-bfc1-5228-a1e6-d70a5c49d31a |  | note | Records - Dipsheet & Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.2 -
label | 287a3adc-d44a-5986-8db0-dd90e8fde8d1 |  | note | Inspection / Test Point -
label | 67806246-0301-5668-8c21-8dd9e2f6c97c |  | note | ACTION - H
label | 2cd44903-07d8-55a6-b5a0-14bc8313dbc8 |  | note | Detail - Ensure Poles are plumb and within design tolerances
label | bc5c7eb3-8498-51c7-96fc-27321b6e0858 |  | note | Frequency - Per pole
label | 0e722b62-0ce6-5f38-b2af-d60d4bf3e43e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 86b002d4-dca6-59bd-998e-d676decb5835 |  | note | Conformance Criteria - Consistency with Drawings and Specifications
label | 00fbf1d0-a45f-5c3c-8053-25d4e52c758e |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - As-builts
label | 9364e6c3-f12e-5694-a1c7-5af5b7f90378 |  | note | Inspection / Test Point - As-builts
label | c0b75a5f-f311-512b-937d-2d24bea5693f |  | note | ACTION - H
label | ace2f23d-10f0-5bed-b158-1532e151875e |  | note | Detail - Red pen mark up drawings to be included in QA file
label | a78e2fcf-f4b2-5629-a28f-49983e9101ac |  | note | Frequency - At the completion of the Lot of work
label | cf560b8e-9355-5427-b2b9-2bad1fd4f157 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | fb7286e4-c43c-5fb1-b059-c43958478cf1 |  | note | Records - Asbuilt Drawing
label | 7ffd2356-c42e-5c61-8255-25841b5c5921 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | Pavement Construction | itp |  |  |  | Yes | ITP - Griffen Park / Hillsborough Rd - Pavement Construction | b6aae83f-309d-4f90-a1eb-c1b43d19bc87
checkpoint-group |  |  | section | Precom
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | 62e9973d-2985-52e5-8fd3-ca26d5cf0154 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5d0e4bf9-9527-5947-ab77-9c33fe9dfb2c |  | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | b5f7d7b8-dcc0-54ff-a987-f1480610f3a9 |  | note | Frequency - Prior to any construction commencing
label | 4d9937b9-ff35-5e72-9191-0aa49282da91 |  | note | Inspection / Test Method - Document Review
label | 0419ed67-41bd-5b2d-9853-026f608de7b5 |  | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | 34a417ec-8853-5e73-8e55-18e6635957a1 |  | note | Records - Permit attached or permit number noted.
label | 28596e92-587c-5b02-9919-2bd156748883 |  | note | FH Initials - Site Engineer
label | 619d35b7-45ad-5328-aac0-e2185c34101b |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | a6fa1bcb-b095-5963-901d-4a9aaf28678d |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1 - Permits & Services
label | 08e11552-d49a-57e3-b947-62e77bf4b8b5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7f08386a-5ab7-5b83-80a1-b2d648e395e1 |  | note | Detail - Locate and mark out all existing services
label | 7334d9be-1a65-54c3-a76c-8520b68914d7 |  | note | Frequency - Prior to any construction commencing
label | b55fd00c-8349-57a0-81e1-6cc0d312eb1e |  | note | Conformance Criteria - B4u dig procedure - follow utility protocols
label | 6d7238b4-0658-5b61-8b18-db5ef17d8d5f |  | note | Records - B4u dig plans
label | 5b559521-d19c-5ba3-9c62-c55b4b7feddb |  | note | FH Initials - Site Engineer
label | bb856e89-5355-5d00-a05d-3d04a1033979 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 8a8bdd00-cbe6-536e-a914-d72d364bfdaa |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Permits & Services
label | db6b4c36-ebfc-59a8-980e-8498bd04dfdd |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2cdcb174-a35a-5438-96ce-f99a748148da |  | note | Detail - Approved TMP
label | 7dbd59cf-ad94-5f02-b10b-9adacdaa0061 |  | note | Frequency - Prior to any construction commencing
label | 92928bf1-dc10-5ab9-90a2-4b881ba8dd23 |  | note | Conformance Criteria - Approved TMP and WAP onsite before establishing traffic management
label | 3fa7ba7e-c0a2-5c04-a99a-7f4dbb994513 |  | note | Records - TMP Plans
label | feb5b156-a39b-58d5-881e-9a520c69df1c |  | note | FH Initials - Site Engineer
label | 8e766ea6-f3c3-5fe5-80ce-9479538b7906 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 6e7c5e90-d6fb-597c-bcc5-b8a543da04c3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | cfcd0342-b448-54f2-ab73-9b0459077e09 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 27e0d633-aa76-5c2b-b021-c56264880693 |  | note | Detail - Sub-Contract and Supplier Agreements
label | 54fb54be-9512-5b43-ba97-a354d2640fcd |  | note | Frequency - Prior to commencement.
label | 09c419e5-5edd-5000-853f-7505195cf9a6 |  | note | Inspection / Test Method - Document Review
label | dd265cf7-634c-568f-8039-1e8c5816738b |  | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | 6b7ee0d8-a284-533c-8ab1-6a32307ebd2f |  | note | Records - Subcontract and Supplier Agreements
label | e4783062-ce5c-5837-9e07-0c8bd737b3b8 |  | note | FH Initials - Site Engineer
label | 2f116d7f-3701-5ea0-bb10-4ceddd1a2f18 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 6af2bc42-7efc-5c88-8aea-796b61a5a150 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | d6cd7bfa-37ef-5e81-b201-6ba113ffe3ba |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3be2259e-5dca-5745-9dae-4b14d4151871 |  | note | Detail - Design is approved and Drawings are of the latest revision.
label | 9aee4f63-cee9-5716-9d02-8bc2e0771f9a |  | note | Frequency - Prior to commencement.
label | ea583c1f-1fa5-5524-a416-cd26b5392c1d |  | note | Inspection / Test Method - Document Review
label | fdcde257-310a-5b68-bffb-00260c47d876 |  | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | c9ff9232-4af1-5290-bd54-3a2bac63637f |  | note | Records - Drawing Register.
label | 0b1113ea-e101-50e8-a409-e7370171592f |  | note | FH Initials - Site Engineer
label | d497e045-3cb1-54ad-9d90-fb9d587fda7a |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Engineers Rep.
text | ce68d538-b3fe-56ae-97a0-cf484ea27e85 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | SAC Pavement & Surfacing
checkpoint-status |  |  | checkpoint | 4 - Bitumen
label | 429347cf-d5f3-553b-9a2b-fd96022fa33a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2781e25b-f19d-5e2e-9147-a88639f5dad8 |  | note | Detail - NZTA M/1
label | 16f2a62d-ea3f-589a-a598-69139f3b88b1 |  | note | Frequency - Passing all tests listed in Table 1 of NZTA M/1
label | c908ae02-dcfb-5dfd-ac3c-51e1b02d6e4c |  | note | Inspection / Test Method - Testing
label | 9a0fdfe2-416d-5c99-9603-c82d87897930 |  | note | Conformance Criteria - Passing all tests listed in Table 1 of NZTA M/1
label | c2ae3dee-e55a-5821-96a5-9ecfaef97c58 |  | note | Records - IANZ Lab results
label | 611535d9-dc35-5766-84bf-e58e44ff36bb |  | note | FH Initials - Site Engineer
label | da06984a-f3bf-5c27-8040-a729c9022cd8 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | acd83318-13fe-55f3-97ce-3a59012a4cd5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Asphalt Mix Design
label | 6f6280e5-9bfa-5cb9-a878-0eded63ff960 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ed2e50ac-aed9-5d82-8a16-6d05dc4e4678 |  | note | Detail - JMF approved
label | 53bffc8e-be36-5954-9e3c-4fdb797eee88 |  | note | Inspection / Test Method - Review
label | d3fe68b5-7d6a-50a7-87bb-6ea4f55bb884 |  | note | Conformance Criteria - AUSTROADS
label | 80a96a9c-1c33-5322-938c-0c74c4fb0a45 |  | note | FH Initials - Site Engineer
label | 2b8eb1c7-f5d6-52d0-acd2-ec1abffb05bc |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 382b27d6-06d3-5372-875b-be6ee983efe2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Production Tests
label | b626332f-5b71-5fec-b846-5675a4d01a71 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 8ab83956-0a65-5547-aa2c-05b5b7776a89 |  | note | Detail - NAS 2004 & TNZ sup to NAS 2006 TNZ P/9P (M/10 Table 5.1)/
label | 36f99a93-a83d-5fb1-87db-032abd082739 |  | note | Frequency - 1 set every 300t
label | 1170b6b3-7899-5b96-b5b3-bf883f0cf1fb |  | note | Inspection / Test Method - Review
label | ed2dd645-1dd5-591b-bd8d-60edc214645d |  | note | Conformance Criteria - NAS 2004 & TNZ sup to NAS 2006 TNZ P/9P or NZTA M/10 - Grading, Binder content, Max Density, Temperature
label | 1e03b675-d1cb-55d7-96eb-5865313f0c27 |  | note | Records - IANZ Lab results
label | dcab5ae3-5897-5c49-86d9-37cfcd6d99d0 |  | note | FH Initials - Site Engineer
label | 9d9a5560-33b7-5c40-9edb-c3720b81babb |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | e106788d-5ac3-5718-8674-6f6990b0f9c0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Check Weather Reports
label | 1fd64a46-2df3-5c17-a385-cfdd4ee9ce17 |  | note | ACTION (Hold, Monitor, Witness) - W
label | adb096e4-c008-5c55-9f6d-5303c4bd3b3f |  | note | Detail - No fog, rain or wet surface. Base temp greater or equal to 7 degree celcius
label | 9627214b-308f-5f58-b592-7701bc47ab46 |  | note | Frequency - Weather call the day before
label | b06013e1-e74a-5372-b5ff-987d5fd5c4c0 |  | note | Inspection / Test Method - Visual
label | 261246ab-0820-5e22-868d-2591706b79fc |  | note | Conformance Criteria - Forecast and thermometer
label | 54be454d-455d-5495-8ecb-5b77b92f3b13 |  | note | Records - Radar and Asphalt QA
label | a332f882-6058-5b97-b71b-49b36d43801a |  | note | FH Initials - Site Engineer
label | 6e91370b-a5fb-54eb-a0c4-79dc2f7decbc |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
text | f23790eb-022f-59d2-876e-0f1b50bb2eb5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8 - Pre-Seal Inspection
label | b432d070-ba6c-56c8-a245-297d8965141f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9d810e9a-42c7-538e-8626-dacbf651befa |  | note | Detail - Surface finish
label | e6d6e0ce-f8db-5d29-93dd-8c430ba4ea5f |  | note | Frequency - Continuous
label | 4713723d-d27a-5fee-bf93-9a414786cdee |  | note | Inspection / Test Method - Visual
label | a9c35315-900e-5d6f-a920-045871524926 |  | note | Conformance Criteria - The surface must be clear of deleterious material and not choked with fines. The basecourse surface must present a stone mosaic surface with larger aggregates protruding and not appear damp
label | 4286fcd7-acfe-506c-a92b-747d6d7abe4b |  | note | Records - Sealing QA
label | d754f4bd-7f76-5ecd-8334-1ecace206a15 |  | note | FH Initials - Site Engineer
label | 9544ff27-61de-5dbd-ada1-204372bf2414 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 06fcb880-bf0e-53d2-b78e-24ccd720be32 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Tack Coat
label | 348fe02d-0d0a-5953-928a-e28955ce4006 |  | note | ACTION (Hold, Monitor, Witness) - M
label | c90352fa-eac4-5414-a7d3-1f19a16d1b32 |  | note | Detail - Minimum residual binder application of 0.3l/m2
label | 16bf9594-906c-5f36-a6ed-24b657c664ff |  | note | Frequency - Each Run
label | bb34cf32-90de-5de3-9cab-f8df6abc6d14 |  | note | Inspection / Test Method - Testing & Visual
label | 3a148a16-dbdf-5ac9-92f2-50f789827f5d |  | note | Conformance Criteria - Each spray of bitumen
label | 972aa670-195c-5432-aa51-7581d90e3171 |  | note | Records - Asphalt QA
label | 06af291c-45d3-5629-83de-3c0f8df6177c |  | note | FH Initials - Site Engineer
label | ed999465-ddd5-589d-8daf-41826f928829 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 83ce7160-443b-5223-a114-f62883391626 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10 - Construct 200mm AC14
label | c2bb42a1-5a8b-51c3-9fbc-c7aeb660686f |  | note | ACTION (Hold, Monitor, Witness) - M
label | a0223181-e810-53f0-8ae4-9463c7a36358 |  | note | Detail - NZTA M/10 NDM and Stringline
label | 95d8cb58-f2ad-5e16-928b-92290731150b |  | note | Frequency - Each Run
label | 488dfbc2-3e93-53bc-998d-295c83fa83e0 |  | note | Inspection / Test Method - Visual
label | a91f098e-b44b-5c80-81ef-6975f361fdda |  | note | Conformance Criteria - Construct 200mm AC14 in 4 layers
label | ef18f913-cf3b-5e54-818a-e05fc085b632 |  | note | Records - Asphalt QA
label | dd320178-354a-50e6-91af-53d6536c8116 |  | note | FH Initials - Site Engineer
label | 753517e4-72e3-5a29-a352-8c2ba41a7d46 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 630311d2-af89-5e9a-b309-53431d99407a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 11 - Construct 135mm AC14
label | 0c399d57-7df4-5fa8-8115-7dd064376cfb |  | note | ACTION (Hold, Monitor, Witness) - M
label | 864bdfc4-9572-5369-ad60-d0dbd285951a |  | note | Detail - NZTA M/10 NDM and Stringline
label | 3976ec94-5be4-549f-b239-04c959152463 |  | note | Frequency - Each Run
label | a7db12a0-e2aa-5e96-85f4-e6ceac8e9a0b |  | note | Inspection / Test Method - Visual
label | 64b80b23-c00f-598b-933d-e0b9c9d85490 |  | note | Conformance Criteria - Construct 135mm AC14 (75mm bottom and 60mm top)
label | c4328220-26a4-5536-98ac-8670a37496de |  | note | Records - Asphalt QA
label | ed751680-9288-5d74-827b-4ec002ada401 |  | note | FH Initials - Site Engineer
label | 80c486dd-80b9-5ffa-81fa-80f0a5c9e5f9 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 40d10487-6bed-55ca-a7c4-11e513b4fdae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 12 - Two coat Grade 3/5 racked -in seal Grade 4 Membrane
label | 4fa95990-acc7-51a4-9cd8-8923ba02c28f |  | note | ACTION (Hold, Monitor, Witness) - M
label | e2d18a0b-42a6-500f-bc71-6f8dd5bd157e |  | note | Detail - Construct a two-coat Grade 3/5 racked in seal or G4 membrane (min residual bitumen application rate of 1l/m2)
label | 15828872-e20b-5496-bc34-39ecfcd3d953 |  | note | Frequency - Continuous
label | 9d41d0a5-794b-552e-9996-e0483e78c968 |  | note | Inspection / Test Method - Testing & Visual
label | 51875954-4a2d-5be0-93ca-a4fafa890f9b |  | note | Conformance Criteria - Tank dip tests before and after application to confirm application rate. Additional PTR rolling to imbed the aggregates into the bitumen
label | 5c516500-f7e4-5242-8cbc-a940335b97f1 |  | note | Records - Chipseal QA Photos
label | 28a5bbb5-4b79-5112-96a8-efe1efb5f5a7 |  | note | FH Initials - Site Engineer
label | 44a94569-4045-5834-8e63-d047323bc444 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | ad4b66de-c995-57ba-bb67-22e00bcab5a4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 16 - Construct 40mm SMA 10
label | d47e389e-3c23-58d1-a3a5-8c62eaa35d5c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 00e20e68-3bcb-5ef9-b3d9-e44b9e5b1344 |  | note | Detail - NZTA M/10 NDM and Stringline
label | b19a3f63-9dff-587c-9439-2b02763b8fcf |  | note | Frequency - Each Run
label | ce9e4326-ae0d-5780-9a96-469761fd4962 |  | note | Inspection / Test Method - Testing & Visual
label | b6007f04-b757-5040-8c55-921b3b7f5d6a |  | note | Conformance Criteria - Construct 40mm SMA10. - Design air voids 4% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
label | 5105e4e2-ad44-50a5-8880-d879d191956f |  | note | Records - Asphalt QA
label | 87d532b0-192a-577c-ac12-7ef5855b33bf |  | note | FH Initials - Site Engineer
label | 765ccc82-cf67-5651-bf4e-c077478dfc37 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 63a3e579-65ea-54ee-9191-13f87840b7e3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 17 - Surface Finish
label | 83401896-2264-5311-813e-3199fb955892 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5f29f441-fe54-5bf9-a48f-b8d9c3da26e2 |  | note | Detail - TNZ P/9P
label | a42267c8-2f35-5c72-95fc-0b77338671f5 |  | note | Frequency - Each Lot
label | 1f42c0fb-a205-542d-a095-dd3b234be638 |  | note | Inspection / Test Method - Visual
label | 48fa1917-4a75-5a39-b30f-276f8c242263 |  | note | Conformance Criteria - Inspection: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate
label | 1603aa22-60ac-53b4-a0f5-2e5b16c33666 |  | note | Records - Photos
label | b676c852-4338-51a0-b93b-923cf60bf03c |  | note | FH Initials - Site Engineer
label | e11ce0cb-05a6-5474-bdd2-6f82e61cfe63 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 6918319f-02ba-5cef-92b1-df876da9dcd9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 18 - Reinstatement of Line Marking and RRPM's
label | 22c08cc3-059a-5ff3-bae6-7f1612d19eb8 |  | note | ACTION (Hold, Monitor, Witness) - M
label | a71ce275-6bd4-5dac-b031-7b38b443ec08 |  | note | Detail - NZTA M7 approved (Class B or C as required for anticipated traffic level)
label | c56baa27-8df9-5561-8d76-d6873331aa1f |  | note | Frequency - Every site
label | 51fa94da-e2e5-545f-a297-027642a052c4 |  | note | Inspection / Test Method - Visual
label | d8be3409-69fd-5a61-8df5-9257724756f2 |  | note | Conformance Criteria - *Carried out within 12 hours of each shift completed and as per the existing markings * Suitable Traffic Control to remain in place until pavement markings have been reinstated
label | 275b96c4-1d47-5737-84fc-ecb4f5527172 |  | note | Records - Photos
label | 03443722-84a0-51fa-81af-6b7ca4469afe |  | note | FH Initials - Site Engineer
label | 02b4dc73-acfa-5ccc-bbc8-dff36e72dd8d |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 920766ce-0978-568b-8674-42623f51410b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | d37828da-8ce1-573d-8ba4-676da562c458 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | dc20f5ea-9fa1-59c9-944f-fac4c939c7ac |  | textbox | Print Name:
text | c2be89c4-fd59-537f-9c00-508557019143 |  | textbox | Position:
text | 53df3eae-668c-55de-9fa2-3bc499e15ab6 |  | textbox | Date:
checklist-flat |  |  | checklist | ITP - Raised Pedestrian Crossing | itp |  |  |  | Yes | Portland Road - ITP - Raised Pedestrian Crossing | b6ad0ece-275a-4bd3-8ac3-557e7df6c52e
checkpoint-status |  |  | checkpoint | 1 Permits
label | f56bf502-9539-43da-af99-240cedc8574b |  | note | ACTION (Hold, Monitor, Witness): H
label | 8c8cae44-7b04-4760-b242-28e78b1e91af |  | note | Detail: Obtain Permits
label | 5cca4860-d4b2-473f-84ba-4dcb2cf17d37 |  | note | Frequency: As required
label | a70ebf2e-226f-4cc4-bc05-9c7a75f6a0a1 |  | note | Inspection / Test Method: Document Review
label | 98d3c58c-fe02-48ed-98d1-382009002904 |  | note | Conformance Criteria: Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 0d1e2c00-a658-445a-9944-98d933edf619 |  | note | Records: Permit attached or permit number noted
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 Pre-construction sign offs
label | 63e1c69b-5dff-4f3a-b80c-8e6b6d022cda |  | note | ACTION (Hold, Monitor, Witness): H
label | 846d8f18-7be1-4b4b-a12d-05f3c8d35b01 |  | note | Detail: Ensure that Sub-Contract and Supplier Agreements are signed
label | bc049f9e-9edc-4d55-a27a-1c1d8d76c21b |  | note | Frequency: Prior to commencement
label | 43b964ac-2843-45ad-aaa5-3ebba8767cec |  | note | Inspection / Test Method: Document Review
label | 2dcad666-a16d-4eb2-a6c9-03654bf3fb3f |  | note | Conformance Criteria: Signed Subcontractor and Supplier Agreements
label | feda9ed1-ef13-407c-9507-2495ae1b2f8a |  | note | Records: Subcontract and Supplier Agreements
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.1 Pre-construction sign offs
label | c2d8b032-697f-4c8b-8f92-7fc97f5861a6 |  | note | ACTION (Hold, Monitor, Witness): H
label | 3b48c016-bc45-4e08-b531-ff83ed894f99 |  | note | Detail: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | 7e59723c-5785-4f32-9a98-d0d4fc557391 |  | note | Frequency: Prior to commencement
label | 266a1d60-8f88-47af-882c-bea0b6666682 |  | note | Inspection / Test Method: Document Review
label | 53fa9b9f-dcae-47e1-a339-6908f7207ec3 |  | note | Conformance Criteria: TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | 6c0fa734-97eb-4124-a859-c8ccc846e342 |  | note | Records: TMP on MyWorksites/On Site
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 Pre-construction sign offs
label | 2f394cef-d478-40e4-8999-07a5d69378f1 |  | note | ACTION (Hold, Monitor, Witness): H
label | d5216ee6-4d21-429e-9bba-3e274b17764b |  | note | Detail: Ensure all Sub-Contractors and Suppliers go through FH induction
label | 3747555d-333e-4770-bf72-a71d58938bda |  | note | Frequency: On site daily
label | 0a0fe2b6-fe75-4438-bd51-4958634dc09a |  | note | Inspection / Test Method: Induction
label | 01bfb892-6bc0-41cb-a63a-4439b2bc6a0b |  | note | Conformance Criteria: Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | a99e23fd-3b34-4b3c-b1de-ab851626f95a |  | note | Records: Hazard ID and Pre-starts to safety team
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 Design
label | 4179b8e7-d8b1-4164-91bf-60bf65910e20 |  | note | ACTION (Hold, Monitor, Witness): H
label | c91b510f-24f7-4866-8f63-9749eae62a85 |  | note | Detail: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 0e0f64ed-4282-4621-b7a5-6e810af0181f |  | note | Frequency: Prior to commencement
label | 49cc0497-fa7a-41b8-a4ae-bf968e01ce47 |  | note | Inspection / Test Method: Document Review
label | 227e9ebf-5499-43b9-afb4-1c57778f6b47 |  | note | Conformance Criteria: IFC drawings have been received by Contractor
label | 49be4b99-81e4-4f2e-9f0d-22ff0976bd8d |  | note | Records: Check Drawing Register
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4 Installation of Erosion and Sediment Controls
label | 41eacb28-836f-48e4-880e-b86e651abcdc |  | note | ACTION (Hold, Monitor, Witness): H
label | 0a724ba1-c386-4ce4-91a7-ade5f7dce03b |  | note | Detail: Ensure that Erosion & Sediment Control in place
label | b7e8f025-7514-41b4-addc-cea782daa1af |  | note | Frequency: Prior to commencement
label | c8731ebf-d732-452f-999f-0b3aff412fd3 |  | note | Inspection / Test Method: Visual Inspection
label | 0f37c1e2-051f-45bd-b5f0-368486522016 |  | note | Conformance Criteria: Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | b1917bf5-47aa-4393-a1d2-58f6366f1643 |  | note | Records: Environmental Controls Audit
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5 Survey Setout
label | 30eb8f63-f0a4-4785-8ade-74a9902eab44 |  | note | ACTION (Hold, Monitor, Witness): H
label | d35da8f5-25b7-4eac-ae6f-9d3560726b6c |  | note | Detail: Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | b7efc5a7-a4ea-4671-a1ea-93118d2cbf68 |  | note | Frequency: Prior to commencement
label | 9f7091ff-5b51-4744-8d61-ea776ec21c1f |  | note | Inspection / Test Method: Survey + Smart Level
label | 2b173680-e92d-4917-935a-2069c5d7d1c1 |  | note | Conformance Criteria: Consistency with Construction Drawing
label | 6a381b4d-667c-48dc-89f0-e5fae3224665 |  | note | Records: Site Photos post surveying
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6 Locate Existing Services by Hand Digging
label | a432a95f-9f45-4a0d-8ad8-a9d503260c2c |  | note | ACTION (Hold, Monitor, Witness): H
label | d3e57843-347a-4dae-b71b-4d991a749317 |  | note | Detail: Ensure all services conflicting with the line of trench has been exposed by hand digging
label | 84dc2db5-4e5d-4a9b-b308-0e756803db05 |  | note | Frequency: Prior to commencement
label | eb5ed185-6256-4f19-8882-409342504eed |  | note | Inspection / Test Method: Potholing
label | 2c687a65-1e09-4b2a-8145-a0d149d853f8 |  | note | Conformance Criteria: All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | a80908e6-d06d-440a-b590-c1834455a790 |  | note | Records: Digging and excavation checklist, service planes, As-Built Drawings Doc. Review
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7 Material Compliance
label | 9dd79b85-75d2-42e4-ad59-d7085aaa5ca2 |  | note | ACTION (Hold, Monitor, Witness): H
label | e0ac73be-884e-4d09-8007-308961d46ae3 |  | note | Detail: LESA dowels to be used at all construction joints
label | bacdcc39-077e-46e3-8b85-0a9bd49dd2ca |  | note | Frequency: Prior to pouring concrete
label | b0e634a9-0de5-448a-922f-debce8e2e816 |  | note | Inspection / Test Method: Document Review
label | eeabc891-14b1-4260-a31a-e23b2b158028 |  | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
label | fef0c3a2-30d7-4cf3-b210-02e765404eb1 |  | note | Records: Delivery Dockets / Photos
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.1 Material Compliance
label | 41372d2a-0a2d-4411-aca6-98d99f974c1e |  | note | ACTION (Hold, Monitor, Witness): H
label | e32e00ba-7337-4643-bd12-12682bfbf191 |  | note | Detail: 0.25mm polythene layer placed across all surface area at bottom of raised table
label | 1cc8a188-0887-47bd-9136-784f4650a572 |  | note | Frequency: Prior to pouring concrete
label | bfd97af3-6e1f-4dd7-8ac4-3bd70d5d03fe |  | note | Inspection / Test Method: Visual Inspection, Document Review
label | c8d54b2f-2d9d-4f7e-a5e3-7cde4ac2a585 |  | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
label | 4e859543-5ef4-40d9-8be0-4ae5b3091aea |  | note | Records: Delivery Dockets / Photos
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.2 Material Compliance
label | 44cfe1e0-3710-452e-9341-053faa14b103 |  | note | ACTION (Hold, Monitor, Witness): H
label | b6c26eef-eaf1-4f25-8536-f37029f7d934 |  | note | Detail: 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | 7459797f-2301-4702-a88d-371486ca0a56 |  | note | Frequency: Prior to pouring concrete
label | f4692c39-50f8-4733-963e-33ae9f6459c8 |  | note | Inspection / Test Method: Visual Inspection
label | e7c60162-49a6-4b14-92c9-548e9854ee0b |  | note | Conformance Criteria: CIV >15
label | cbf29821-ee45-454d-b144-746239a36f29 |  | note | Records: Delivery Dockets
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.3 Material Compliance
label | 0c3d736c-6522-40bd-af4d-0ea0f302e5a3 |  | note | ACTION (Hold, Monitor, Witness): H
label | effb3675-8a0f-497c-b57c-847a6991995f |  | note | Detail: All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder and 13mm aggregate chip size
label | 49932543-1d07-473e-860c-5d742691d5cb |  | note | Frequency: Prior to pouring concrete
label | 0b901848-68f1-491a-8371-e6cfc7f64044 |  | note | Inspection / Test Method: Concrete Delivery Dockets
label | 9e54f103-affb-45c6-91d8-2a46a67923a5 |  | note | Conformance Criteria: Delivery Docket added to QA folder
label | dcce77ec-87f0-4a2b-8a38-fc3abb2be56e |  | note | Records: Concrete Delivery Dockets
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.3.1 Material Compliance
label | 1022789c-4fa2-4d4b-bd73-fc2ae9464396 |  | note | ACTION (Hold, Monitor, Witness): H
label | b1699f0e-eeae-4154-a937-2d6cd070a662 |  | note | Detail: Two layers of 663 steel mesh to be placed in the speed table with 50mm plastic chairs separating them.
label | c64f84ed-333d-48ab-b45f-8e606f2dc0e0 |  | note | Frequency: Prior to pouring concrete
label | 1ff750a3-97f6-4585-94c7-64f0b11d857c |  | note | Inspection / Test Method: Visual Inspection
label | cf705f1d-7ad3-4abf-9158-c026e2595f4b |  | note | Conformance Criteria: Delivery Docket added to QA folder
label | 1aa01731-7268-4fd7-867b-554494ae7784 |  | note | Records: Site photos
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 8 Temporary Works (Formwork)
label | fe430fd1-7e14-4350-86d1-544149bf4c7e |  | note | ACTION (Hold, Monitor, Witness): W
label | 251bb264-8ad2-410c-bbb0-d3691d814290 |  | note | Detail: Formwork to be set to correct line and level
label | 4dd3e3bd-01be-4036-b280-5d655be7f08e |  | note | Frequency: Prior to pouring concrete
label | 060f3c38-5966-46e7-a72b-ac9d7cf31c78 |  | note | Inspection / Test Method: Visual inspection
label | a37df524-7434-4d23-afa4-ea4d30e2efc3 |  | note | Conformance Criteria: Concrete Inspection Record
label | 4ab35f2e-51b9-4041-a705-cda3df9b6410 |  | note | Records: Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 8.1 Temporary Works (Formwork)
label | 201dee91-857e-4195-b737-f843e3d967ff |  | note | ACTION (Hold, Monitor, Witness): H
label | 0f9128df-ee75-48d6-9322-9ac2f03c00b8 |  | note | Detail: Raised table formwork to be 100mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
label | 1e27f38c-6ad6-459b-84fc-f83c98a7e85b |  | note | Frequency: Prior to pouring concrete
label | ea9ad903-0407-400c-bf63-ce78a28a5749 |  | note | Inspection / Test Method: Measurement
label | b9f59c01-ad72-4568-bf97-b9bfbe48ace9 |  | note | Conformance Criteria: Designer to inspect formation level
label | 1e8ce9eb-1e89-4c6e-b8e5-637570a714b6 |  | note | Records: Site photos
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 8.2 Temporary Works (Formwork)
label | 767f2a4d-ec18-4d25-9b2c-c44d85d87543 |  | note | ACTION (Hold, Monitor, Witness): H
label | ea734fbc-a760-4a72-9903-a422cefef5c8 |  | note | Detail: Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
label | a2821ce0-d9eb-42c0-90a1-84d917bed137 |  | note | Frequency: Prior to pouring concrete
label | 93defb24-6e36-4d4e-9fa5-af70bbf115cc |  | note | Inspection / Test Method: Measurement
label | d80a41c2-73ac-4668-b0aa-5554d41cebd5 |  | note | Conformance Criteria: Designer to inspect formation level
label | c2146b10-f582-4a48-86e0-967e85de32d2 |  | note | Records: Site photos
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 8.3 Temporary Works (Formwork)
label | 36f41995-74f9-4414-b20c-8631d4b529a2 |  | note | ACTION (Hold, Monitor, Witness): H
label | 5f38a159-9fc5-491d-a50d-a40fe96a8144 |  | note | Detail: Raised Table ramps to be 1m across for entry and 1m for departure ramp. Toe to be 1m across for both entry and departure.
label | 747a9554-3f61-47c2-8d78-6acb5fc18d96 |  | note | Frequency: Prior to pouring concrete
label | bae7a742-4497-4772-8eb4-44912cc3beea |  | note | Inspection / Test Method: Measurement
label | a6b765f6-1d43-4c08-8104-c4731f73f321 |  | note | Conformance Criteria: Designer to inspect formation level
label | f1716038-284a-4c27-a661-e633767ca5cc |  | note | Records: Site photos
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 8.4 Temporary Works (Formwork)
label | b035d067-0d54-4eda-9e91-2eef8e585357 |  | note | ACTION (Hold, Monitor, Witness): H
label | b826856b-0444-4418-bfd6-70f181c8b634 |  | note | Detail: Raised Table ramps to be 1:10 gradient for ramps, with 2 layers of 663 mesh.
label | 3c9f0291-6fcf-4db8-85d4-15cc3dbd6a31 |  | note | Frequency: Prior to pouring concrete
label | 31fab920-624f-4851-9f64-29e55a6590f8 |  | note | Inspection / Test Method: Measurement
label | f7addfbd-80dc-4744-9ee6-12d788264204 |  | note | Conformance Criteria: Designer to inspect gradient level
label | 998e5e88-098b-45ca-8aa4-a5ce9c928587 |  | note | Records: Site photos / Concrete Formwork Checklist
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 8.5 Temporary Works (Formwork)
label | b3b82123-b6f4-499d-94be-5c81400e750b |  | note | ACTION (Hold, Monitor, Witness): H
label | f3a8060c-a195-4d97-8361-27be3751bcad |  | note | Detail: The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | 7442c626-8877-482c-9249-045459373cba |  | note | Frequency: Prior to concrete pour
label | 20016f50-1d4c-4a15-9bc0-79cc30eeeaed |  | note | Inspection / Test Method: Visual inspection
label | 4d080c3f-b33b-4c7e-a899-42c75bfcdf1b |  | note | Conformance Criteria: Concrete Inspection Record
label | 115bcc5a-9e9f-4cb1-b96e-56b5db214212 |  | note | Records: Concrete Formwork Checklist
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 9 Reinforcing
label | e5654b62-6b80-4be1-94bc-443759a953a3 |  | note | ACTION (Hold, Monitor, Witness): H
label | f5c770be-1e59-49da-ba43-c2e6686139e3 |  | note | Detail: All construction joints are to contain 2 rows of LESA dowels or similar approved dowels . Speed basket system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
label | 8e7156a9-907d-496f-809b-e99270d17c6c |  | note | Frequency: Prior to pouring concrete
label | 9be5db5e-beb5-4d6c-9585-9e044f721f89 |  | note | Inspection / Test Method: Measurement
label | bdca7882-7498-4cdc-9c64-5c7f022433c2 |  | note | Conformance Criteria: Concrete Inspection Record
label | bb07d310-8fa8-43bf-80c0-fbd960310b6d |  | note | Records: Site photos/Concrete Formwork Checklist
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 10 Concreting
label | b85302da-5165-40ea-8058-5434bf362cc7 |  | note | ACTION (Hold, Monitor, Witness): H
label | 5c7778d9-ae39-42c7-a73b-da48b531a027 |  | note | Detail: The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | f5055c91-f968-4257-8fb4-1abebffa02bc |  | note | Frequency: Prior to concrete pour
label | c6d6ece4-3331-484e-8747-b4f04629d27f |  | note | Inspection / Test Method: Visual inspection
label | 298678c2-880f-4fbd-a965-84c2cf98f534 |  | note | Conformance Criteria: Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | 04feae9c-1de3-441a-9014-57cdc50ffd77 |  | note | Records: Email / SMS
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 10.1 Concreting
label | d7e69b08-ad9b-4bcb-8da8-fe35aafb43b4 |  | note | ACTION (Hold, Monitor, Witness): W
label | 5ccdeeb8-35c9-4c5e-86e1-9e44c21e7e82 |  | note | Detail: Vibrator to be used throughout concrete pour
label | a77c287e-0028-4c39-b907-d783be6e4fc5 |  | note | Frequency: When pouring concrete
label | 3c9365d3-3c07-4b41-a2a5-000759509644 |  | note | Inspection / Test Method: Visual Inspection
label | 2b9f7f28-fa20-4c6f-bf23-0e89e71f34bd |  | note | Conformance Criteria: Concrete Inspection Record
label | a2a52200-478d-4f85-9a98-687760bd14f1 |  | note | Records: Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 10.2 Concreting
label | e3262b93-b302-4fbf-a395-4b234898aa65 |  | note | ACTION (Hold, Monitor, Witness): H
label | 3129c15e-ae3f-4f46-b496-55f36c628c4b |  | note | Detail: Concrete surfaces on ramps shall be U5 broomed finish and speed table top to be exposed.
label | 3f7f87ef-7b94-436a-8d6f-2d6aa624b4b0 |  | note | Frequency: At completion of pour
label | f70e81b1-96ce-4fa4-ae3c-50e5dc532557 |  | note | Inspection / Test Method: Visual inspection
label | aef894e4-5324-49ee-a415-f4bb5b0a2b3b |  | note | Conformance Criteria: Concrete Inspection Record
label | 70e104f4-92c0-4779-94bf-e492c40e0dd8 |  | note | Records: Concrete Formwork Checklist
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 11 Curing
label | def74f70-98c8-4b8e-b507-9b27939880a5 |  | note | ACTION (Hold, Monitor, Witness): M
label | e4a245ce-c1bb-4b15-80ea-e6e9e310b6fb |  | note | Detail: Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | 1f0b0cac-6411-4857-b2df-fc3bd05e4a0d |  | note | Frequency: Post Pour
label | 4bc577a4-a44d-46ce-849d-a275b59a2c05 |  | note | Inspection / Test Method: Monitoring the time allowed for curing
label | 00a8cf94-3468-4e9e-b71b-13b1f1257a13 |  | note | Conformance Criteria: 48 hours minimum have passed
label | 19cf7064-0b90-4d30-a351-7036fc4c3325 |  | note | Records: Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 12 Remove formwork
label | c80cffc2-19c5-4eb5-9a70-87336dba40a8 |  | note | ACTION (Hold, Monitor, Witness): W
label | 4b367bd1-a46d-41fa-8e46-8e89f338a859 |  | note | Detail: Remove formwork after 48 hours
label | 9160683f-c760-466e-924f-a457c0f96d8a |  | note | Frequency: Post Curing
label | caf4bf72-8636-485e-a125-4d33be178de2 |  | note | Inspection / Test Method: Visual inspection
label | fa795ffd-e07d-4859-803f-8e1d26f22cc3 |  | note | Conformance Criteria: Concrete Inspection Record
label | bffb310b-e8d2-45ef-a849-1c2c73201576 |  | note | Records: Concrete Formwork Checklist
checkpoint-status |  |  | checkpoint | 13 Asphalt- Concrete extension slab/ Toe
label | f3f9dbd1-2e51-4c77-8bab-da88888c22f2 |  | note | ACTION (Hold, Monitor, Witness): H
label | 47b35a2c-0e57-4978-b247-0cff52f67e1b |  | note | Detail: One row of Lesa diamond placed mid depth @400 C/C along construction joint as per TDM TC003
label | 47cf3f2a-1945-4a6e-95c7-e581bdcae3ae |  | note | Frequency: Prior to pouring concrete
label | 28a13716-b8e5-4453-a1d0-cacdb54d3272 |  | note | Inspection / Test Method: Measurement
label | 27ed45a9-b531-49b8-811c-5ebbde781798 |  | note | Conformance Criteria: Pre pour Inspection Checklist, Concrete Inspection records
label | 666ba1d8-450c-469c-82da-d6c675e3b709 |  | note | Records: Site photos, delivery dockets
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 13.1 Asphalt- Concrete extension slab/ Toe
label | 28453789-3d7e-49e0-927d-48c574fbea50 |  | note | ACTION (Hold, Monitor, Witness): H
label | d01f1aed-af62-4989-87a5-96b6928b9889 |  | note | Detail: 150mm thick 40Mpa Concrete with two layers of 663 mesh
label | 6d5fdb82-6f47-4159-b973-5c7de4eabcb5 |  | note | Frequency: Prior to pouring concrete
label | f723a0e4-ca0c-4979-891d-9ba1225b9beb |  | note | Inspection / Test Method: Measurement
label | 50bed6e0-752e-4a27-a3b8-36c92fc9b304 |  | note | Conformance Criteria: Pre pour Inspection Checklist, Concrete Inspection records
label | 92abd2a4-4d4f-4f79-adeb-8dab485389dd |  | note | Records: Site photos, delivery dockets
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 13.1 Asphalt- Concrete extension slab/ Toe
label | 3c2aa981-0720-4efd-9a7b-bff6f958465a |  | note | ACTION (Hold, Monitor, Witness): W
label | 6049aa86-766d-43d9-a47f-8bd856a634da |  | note | Detail: Tack Coat between AC14 and Concrete slab
label | 729fe008-e918-4635-b22d-e8a1eb2e988d |  | note | Frequency: Post Curing
label | 1bde3535-cf2d-4b69-8200-6336b62aaf33 |  | note | Inspection / Test Method: Visual inspection
label | 3706bc0b-f2f9-4beb-8935-f1162c3d08bf |  | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
label | cb29131a-1578-4b8a-b533-dd8df1c48ace |  | note | Records: Site photos
checkpoint-status |  |  | checkpoint | 13.2 Asphalt- Concrete extension slab/ Toe
label | d8c507c8-0b5d-4b48-b5bf-36f850ec1c6b |  | note | ACTION (Hold, Monitor, Witness): W
label | 3d3572a8-5e74-421b-b59e-987209855737 |  | note | Detail: Tack Coat between AC14 and Concrete slab
label | aabb8ae7-23a1-4449-b6ae-c0eda7936ecf |  | note | Frequency: Post Curing
label | 4462193a-b23d-4013-a88f-3cdcfa20106b |  | note | Inspection / Test Method: Visual inspection
label | 9bc10efc-8497-452d-9ed9-a42d71437a7f |  | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
label | e57d7c03-315c-46eb-a95c-d7f62f50912b |  | note | Records: Site photos
checkpoint-status |  |  | checkpoint | 13.3 Asphalt- Concrete extension slab/ Toe
label | 54b43e21-64e5-43e2-af9a-f585c5de769b |  | note | ACTION (Hold, Monitor, Witness): W
label | 13d5e5a4-1534-4b9f-b05b-e2884c53e591 |  | note | Detail: 50mm thick AC14
label | a15af5c9-224c-406e-a579-c660aa33d03d |  | note | Frequency: Post Curing
label | b49e9db7-fd0c-49c1-a8cc-6ece5df86cab |  | note | Inspection / Test Method: Measurement
label | 8f9aa266-4fb8-41b8-85b6-a5e939680a12 |  | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
label | e5d9f024-f507-4bb7-8582-92047875778e |  | note | Records: Site photos, delivery dockets
checkpoint-status |  |  | checkpoint | 14 Lot Number QA File
label | 363cffe8-3fc7-400d-9cd0-bdc30d131922 |  | note | ACTION (Hold, Monitor, Witness): W
label | 417f20dd-9085-43d5-a234-237df66854bb |  | note | Detail: Ensure all QA Records, site photos and incident cases (OFIs) are closed and included within QA file
label | e8d1f1be-2656-4500-bf88-46ef4d6a4fdd |  | note | Frequency: At completion of Lot
label | dd6e03af-830c-455a-b82e-d884b2b6f93c |  | note | Inspection / Test Method: Document Review
label | 15e876ea-1ceb-4710-a28a-7fe0a755d1fb |  | note | Conformance Criteria: All QA files compiled and submitted to client
label | ef70740f-9079-45f6-9ab4-39253935ecc0 |  | note | Records: QA records
checkpoint-status |  |  | checkpoint | 14.1 Lot Number QA File
label | 5de1c3f0-ff92-4f2b-9369-e9e235bfbea2 |  | note | ACTION (Hold, Monitor, Witness): W
label | 4c633804-3e62-4a98-8c7d-a3061e9b8612 |  | note | Detail: Delivery Dockets to be included in QA file
label | 4a475358-7073-4af5-b8b8-4cc7d40993cd |  | note | Frequency: At completion of Lot
label | 85a5fcd6-59a4-4076-a6cf-6743feed3068 |  | note | Inspection / Test Method: Document Review
label | 2068eea2-bb6d-4b93-b6cb-b51c28f5b911 |  | note | Conformance Criteria: Delivery Dockets to be included in QA file
label | 654c45cc-bc14-46a7-b38d-0322c1b2bf9e |  | note | Records: QA records
checkpoint-status |  |  | checkpoint | 15 As-builts
label | 156b2c61-85be-4d45-8c7f-1ad046c65ecc |  | note | ACTION (Hold, Monitor, Witness): H
label | 81615d11-d426-4cd0-badc-bf04b9ef4821 |  | note | Detail: Red pen mark up drawings to be included in QA file
label | 661fa224-04b5-477f-a0a5-0332c993c94b |  | note | Frequency: At the completion of the Lot of work
label | 97a1cd4e-6014-4a3a-be7b-5c0a94ff9aa1 |  | note | Inspection / Test Method: Drawings
label | bfc8153a-de96-4df5-88ec-4713e348fa6a |  | note | Conformance Criteria:
label | 451d9bf6-a748-4220-b154-a1ef7ed7c5d5 |  | note | Records: Asbuilt Drawing
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | ITP Completion
text | 53888654-1392-46a6-a780-cd3f25a76094 |  | textbox | IFC Drawings used for Construction incl. Rev numbers:
text | 7ed63d06-c5ef-4951-a4a9-6f552795f6b1 |  | textbox | Reference Documentation (Notices/OFIs etc.):
text | 73ba3f5d-d6bb-4244-8c05-e799d7ca7df5 |  | textbox | QA Compiled By :
text | b4a70f36-e41e-43d0-9c1d-ddcdb8402df7 |  | textbox | QA checked By Discipline Manager:
text | e247471a-2360-4e00-9e71-a9e48d74d621 |  | textbox | QA checked By Quality Manager:
text | 993bd705-f7b3-4d77-b81b-ba5f6631ba9f |  | textbox | Accepted By Design Engineer:
checklist-flat |  |  | checklist | Footpath Construction |  |  |  |  | Yes | Ponsonby - ITP - Footpath Construction | b6ed7067-2f1c-4438-a6bc-692caf2b97f2
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 0e5e4114-f77a-5340-a3d2-bc834619232e |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5e55b5ae-6a7a-5bd2-8206-129f19aeb630 |  | note | Detail - Obtain Permits
label | b99db9f8-1043-5e3b-a4a1-a82dc7f96f63 |  | note | Frequency - As required
label | f3372cf5-4ab4-556a-a6fd-132c2509bd4f |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 8761135e-19a6-5303-a248-07ed631c803c |  | note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 3fec396c-71a5-5026-808b-20df80e05afc |  | note | Records - Permit attached or permit number noted
checkpoint-status |  |  | checkpoint | 2 - Traffic Management
label | 5cddd236-4827-5d26-bdf2-47df66053f6f |  | note | ACTION (Hold, Monitor, Witness) - W
label | f77d0210-893e-5d7d-bd2b-ef04bb944559 |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | 6636b103-ff55-5fd5-8234-97a8d1b8da92 |  | note | Frequency - Prior to commencement
label | a4b1e451-7d0b-5de7-aa31-985fb0ba116f |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 81d6b8c1-4bec-55b9-9da5-785340edfd14 |  | note | Conformance Criteria - TMP is approved by AT for the site and works are completed within the approved dates
label | 0f5ffd83-23fa-57d3-a66b-13ca0d7b3231 |  | note | Records - TMP on MyWorksites
checkpoint-status |  |  | checkpoint | 3 - Pre-construction sign offs
label | 638133d5-137f-5c74-9a6b-500e14f5fb23 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 196c4253-486d-5052-b4e1-f255e6cf5297 |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site
label | ed083a39-6d10-51e3-8079-ed7873696d21 |  | note | Frequency - Prior to commencement
label | 8fb7599c-c8c9-59b9-8f6a-ed66b9e661ed |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 7d9eb675-53ce-5d1b-acd2-a8a5519c74f6 |  | note | Conformance Criteria - Signed Subcontract and Supplier Agreements and Induction Register updated
label | 41dd2dc0-dc33-5499-941a-2f36462a28cc |  | note | Records - Subcontract and Supplier Agreements, & Updated Induction Register
checkpoint-status |  |  | checkpoint | 4 - Design
label | e7cebae2-b2a0-531d-a646-0d38d463adf0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6cd3fee2-81b1-5b15-adf8-43b84db9eb05 |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | 4d04c102-2793-5cb8-9787-6621b0633737 |  | note | Frequency - Prior to commencement
label | b7caaf6a-e204-5a43-b881-ef723d36b0d7 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | d64cb15b-994a-5a65-9ac0-915bf863a53a |  | note | Conformance Criteria - IFC Label on drawings
label | c29b95eb-7e8b-525f-b33f-b9084b4c7003 |  | note | Records - Check Drawing Reegister
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | e12ed889-d3fe-5cb2-97bf-69d4c4eee536 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 203aec93-4233-5ff6-a2ae-daae5ce13350 |  | note | Detail - Set out pegs installed every 10m of the footpath showing the FL & giving indication of line, extra pegs required on curves or special features
label | 29a94fd6-68a5-5d92-997b-ad2e753d68e8 |  | note | Frequency - Prior to commencement
label | 2c5dc183-2877-5ac2-b7e3-c3234f42953d |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
label | dcbda7df-924c-5af7-8abb-ea4bf52359b4 |  | note | Records - Visual Inspection
checkpoint-status |  |  | checkpoint | 6 - Material Compliance
label | f509bd83-109b-5d4d-99f3-d3c585a7efed |  | note | ACTION (Hold, Monitor, Witness) - H
label | b23ffd78-9a62-5138-a02d-901447634b6b |  | note | Detail - GAP40 - Basecourse
label | 15e672da-8c6b-52a9-9f32-407c59b56171 |  | note | Frequency - Prior to commencement
label | 286f4d9b-9eb3-511a-9311-0f3e4c03657f |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab Testing
label | 7f573dc9-c757-5afb-9125-7b4264ad39d8 |  | note | Conformance Criteria - Grading test only
label | 8662cc24-35f5-5635-ad7d-70ab4f5783fc |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Material Compliance (2)
label | 50340e53-2e28-5737-8fb0-058a82ea01eb |  | note | ACTION (Hold, Monitor, Witness) - H
label | f47f8e6b-b25f-5818-affa-dce7219e1f07 |  | note | Detail - Concrete Mix Design at 20 Mpa in accordance with ATCoP
label | bff3bbb7-4208-535e-b3f7-e9d8018f306c |  | note | Frequency - Prior to commencement
label | a754b901-856f-544a-bfb3-a322b6960ef0 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 457107a8-4f24-5ef4-99b4-81fa85f57051 |  | note | Conformance Criteria - Mix Design is approved prior to any concrete being delivered to site by Design Engineer
label | 437cc26e-2cc1-54ea-967b-f458c3396efd |  | note | Records - Mix Design Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Subgrade Compliance
label | e2b34986-f02d-5c67-a866-329e0d736898 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 05dabe9a-c85c-5326-a954-490dcefcf7f7 |  | note | Detail - If Existing Subgrade CBR<3% or CIV<7 (if granular), Base layer thickness can be increased by 100mm at Design Engineer's discretion
label | e2e2d744-2ee6-5868-9b65-cac2bf87f534 |  | note | Frequency - One test per 10 linear metres
label | 427f83f8-d02d-50f5-a164-48bd22704a8e |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Design Engineer Inspection and Correspondence
label | 17d857f8-bd58-568d-9104-370cfa58cb9e |  | note | Conformance Criteria - CBR> 3% or CIV>=7
label | 7c5cd335-88c4-535c-84fb-9780db513259 |  | note | Records - QA Sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Basecourse - GAP40
label | 875ef245-e53e-52bf-9249-fd448a442b5b |  | note | ACTION (Hold, Monitor, Witness) - H
label | ca7be100-d1c7-55c6-b93d-a3880570a1ab |  | note | Detail - Compaction of GAP 40 with minimun 100mm thickness
label | 169d7f93-93b2-5e66-9350-f9df176e9ce8 |  | note | Frequency - Upon Completion
label | 2c1922cd-8270-5ea3-a84a-8364fefa056e |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Clegg Test
label | 02262ea2-b476-5274-ad7d-04dc4afc36b2 |  | note | Conformance Criteria - ClV >= 12
label | 783b357e-0b6d-58a3-8510-8e102354b7c0 |  | note | Records - QA Sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Concreting
label | b4bd46f2-1abf-5405-a9b4-6606f38f8e0d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2a4062ae-8f5f-57b7-885a-e89e064e5ef4 |  | note | Detail - Before any concrete is poured a prepour inspection to be carried out
label | 5adf0c27-b97a-5d9e-b3fb-47af394603d8 |  | note | Frequency - Pre-Pour
label | 5d3766f3-f95a-5283-9be9-f51cb973c1ae |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | 70ce195d-91ce-5818-89cd-341be4b015e3 |  | note | Conformance Criteria - Concrete pre-pour checksheet
label | f37e89cf-b116-5d21-9f3a-2bc30379ae78 |  | note | Records - Checksheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Concreting (2)
label | ea977ed7-cfe4-5cd7-97ac-98580ae68ec6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2550ee62-6ede-5b1e-8838-2e84691eede1 |  | note | Detail - Ensure concrete type and finish is as per specifications & drawings. Concrete panels should be no longer than 3m.
label | 3cdfb57c-a835-522f-8ad9-519e646eeffe |  | note | Frequency - Pre-Pour
label | 163dd34e-bbc6-5f4d-8c4b-4895c124ce45 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | 5400a180-0573-5049-a37b-4f7abaa9c8de |  | note | Conformance Criteria - U5 Broom Finish
label | 1f8d1d42-b5bb-5065-a7ec-d6ab3ee0309f |  | note | Records - Concrete docket/ Photos
checkpoint-status |  |  | checkpoint | 9 - Concreting (3)
label | 2b97c00e-386e-50c2-9503-af99f1769ecc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 02506c10-c9f9-515e-81c8-88f5813ad2fd |  | note | Detail - Vehicle crossing basecourse to be of a minimum 100mm thickness of compacted GAP40
label | 7e6d15e6-7b78-582a-88c5-3e1301e8b1f5 |  | note | Frequency - Pre-Pour
label | b4b90215-8d0c-54cf-9dda-bfbfaa7ca087 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Clegg Test
label | d00866ae-950d-5b3b-baf6-48df0814d4a2 |  | note | Conformance Criteria - CIV >= 25 as per ATCoP drawings
label | 3d584a31-947b-5390-8f03-4c34d8838278 |  | note | Records - QA Sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Concreting (4)
label | 5dd7ec35-837d-545d-90a4-42c05ea7e735 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2ae0abde-c65b-5073-9b62-6ace6aad0574 |  | note | Detail - Bus Shelter Foundation Prep
label | 869539eb-a0db-578c-9de7-a32dffcf419a |  | note | • Concrete thickness to be 2oomm
label | 57b79189-f084-5293-91e2-0835f534f526 |  | note | • 100mm GAP40 Basecourse.
label | 0c5b0364-8d5b-56df-b505-c2b6527ba6ee |  | note | • 2 layers of 665 mesh
label | f7fbeaf4-d424-5f96-85ed-80dbf464021b |  | note | Frequency - Pre-Pour
label | 8fb9f7be-fbb8-5cbb-9445-019c3badccba |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Clegg Test
label | 1530a748-c96b-586e-a6f2-35a30172b19f |  | note | Conformance Criteria - CIV >= 25 as per ATCoP drawings
label | 2f198c14-6045-5685-b319-350abf699e6b |  | note | Records - QA Sheets/ Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Concreting (5)
label | 29263ea1-5a8d-59b9-bca9-556e643288cc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 707043b9-ad05-5771-8d99-6a62663f83a6 |  | note | Detail - Tactile pavers are installed per drawings & specifications
label | 83d16a0d-b38d-5820-a6fb-55ec077a1982 |  | note | Frequency - Pre-Pour
label | b0996d1d-1bc9-5646-a2c1-74b9b7ff1b81 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | 3759e57f-27b3-5ff8-9759-d95939dd9325 |  | note | Conformance Criteria - As per drawing
label | 7f3ca029-f9c5-54da-9192-54e55535b125 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Signage
label | 800c266a-370a-5568-9544-4a04e8134c36 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1c06e215-df35-5108-be47-85a8b30a7a86 |  | note | Detail - Signage sockets and signs are installed as per drawings and specification
label | e3e2e1bb-35d8-58ec-ada4-86ca02242886 |  | note | Frequency - Upon Completion
label | c855db46-8fa7-5c5d-8653-096c59996703 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | e61758c9-000c-52da-9989-4b523fdf8c0d |  | note | Conformance Criteria - As per drawings
label | 7846f176-0a47-5823-a32e-34ad119bbfae |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 11 - As-builts
label | e0d4ba0a-f459-5bec-872e-1495edb47faf |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0f785c88-d743-57c2-a44b-d23ca6e23029 |  | note | Detail - Red pen mark up drawings and RAMM to be included in QA file
label | 52d45d93-dbab-5fd1-a1b4-311b2626c410 |  | note | Frequency - At the completion of the Lot of work
label | 47e39675-3690-5d5f-81af-c383c6affe16 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings
label | 13837915-81c3-5a70-8c0a-3327e888198d |  | note | Records - Asbuilt Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | Enabling Works - Footpath, Kerb and Channel |  |  |  |  | Yes | Sheehan Ave - ITP - Enabling Works - Footpath, Kerb and Channel | b774ed50-7042-4632-8cd2-faff797647b8
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | f6a0b195-fff7-53b6-8529-0d23ba59fa71 |  | note | VERIFICATION ACTIVITY - Surveyor
label | 467d2f42-2ffa-58c9-8072-ff6288c704da |  | note | METHODS OR REFERENCE - Surveyor
label | 7b56260d-11e8-5acb-9a68-3a30f5a69e79 |  | note | FREQUENCY - Every site
label | ecba7cbd-433a-58a2-9bf0-49099c5dc28f |  | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | 5e725552-888b-5f5f-8451-3424499e52d5 |  | note | Hold Point - Mandatory HOLD POINT -
label | f33b377b-ff40-5f88-9817-871bda2e97f7 |  | note | Records - Onsite records/photos
label | 7528a18a-dc9b-5660-a4b2-d0cd6ebdbd5a |  | note | Onsite Responsibility - Site Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Kerb & Channel
label | e16bb5b0-835c-5745-a023-738e07858b32 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 80c3b7ad-2d91-5fe0-80b5-a45664a726c5 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | 6f1019e9-a8b3-5df5-ae3a-b674bb977c4a |  | note | FREQUENCY - Every site
label | 5d455783-8a66-5fe4-952f-9316ae87ad22 |  | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
label | 5dbf06ef-ca78-5a10-b17d-b036367b37a4 |  | note | Hold Point - In process Inspection
label | be432a6d-377e-52e5-831c-23b1dea39288 |  | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
label | 043f99f2-5678-5140-8726-0f68f3c4d58e |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Channel Level
label | d7e29910-2b5c-5b0f-b29e-5523b9a09d57 |  | note | VERIFICATION ACTIVITY - QA FORM
label | ed929b60-ca80-52a9-b37f-885fc2b053aa |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | 85c72ae5-7d79-5e56-99fb-4ae70eb26caa |  | note | FREQUENCY - Every site
label | 40615e96-c936-5f62-817b-28c91e650c49 |  | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | 707a86d9-8a91-504f-96c0-0e5b386d705c |  | note | Hold Point - In Process Inspection
label | 61c5d0d9-3852-5764-b111-eef8edf13b98 |  | note | Records - FH concrete QA sheet
label | 27b734a8-471d-5ad8-a781-0e583be51c13 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | CIVIL WORKS
checkpoint-status |  |  | checkpoint | 4 - Concrete Footpaths
label | 03eb33ba-27ac-53fa-bfdd-3ce0a8bb2e02 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 65a10c4e-07f9-579a-9e75-4433af76d227 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
label | b6837531-20e7-5c3f-a152-003914a120c1 |  | note | FREQUENCY - 10m Intervals
label | ccd216a3-d574-507a-9f6a-359117680258 |  | note | ACCEPTANCE CRITERIA - Basecourse - 100mm min. thickness GAP40. Clegg CIV > 12. Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish.
label | 8d925024-2657-5e87-a6ae-b365973cdcad |  | note | Hold Point - Inprocess Inspection
label | 90ebdbd5-4489-5849-81e1-ec5bac1055b1 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | 29b84b63-9656-529a-a8d2-71f06530de4c |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Tactiles
label | d546fec8-b0e6-5de6-b788-7ea1bea57062 |  | note | VERIFICATION ACTIVITY - Visual
label | ff8f90c5-e1fc-500f-ab88-7d68a9d85dc4 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
label | 84e157d7-6d79-549f-b535-97596f7180be |  | note | FREQUENCY - Each PX
label | 3292f323-d66f-5278-8265-a211c2a8a001 |  | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
label | ee2153d3-9308-5dc5-8bc5-196bbc0f3ec4 |  | note | Hold Point - Inprocess Inspection, Measurement
label | 071f064f-8186-5ac5-8af8-c56bfd772a15 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | 7a245c54-c797-5a48-8282-8e75db4ed2e2 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5.1 - Tactiles
label | 893ae7ea-e31f-5eee-a6f4-839d4379639b |  | note | VERIFICATION ACTIVITY - Visual
label | 53b5365d-666f-56bd-b255-35ebb8106954 |  | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians. AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY.
label | 4c801836-3390-5eb0-8e2d-3085d96ffe6c |  | note | FREQUENCY - Every site
label | a2047e7e-d36c-51fe-86b0-bc95e73b06d0 |  | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | 798e3cfa-3d83-55de-9e62-1e9c2fec4e5a |  | note | Hold Point - In process Inspection
label | 730f4df3-474b-5590-9e91-48e874bc244c |  | note | Records - Photos
label | 7690dc5a-419b-5c4b-ae5a-9863a4639e58 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5.2 - Tactiles
label | c95fe916-1d8f-5850-a9b7-674cf7adf28d |  | note | VERIFICATION ACTIVITY - Visual
label | 03aba92e-aeca-58b0-b22b-84bb752fd4d8 |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 2ec13563-542e-5d6a-bcf7-e24b6e7fa1ba |  | note | FREQUENCY - Every site
label | 3e26842d-f364-5a7d-9ae2-32f254bbe8f9 |  | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | 3d077907-e443-57af-b29b-1026862c360f |  | note | Hold Point - In process Inspection
label | afa8416e-0e2a-598f-936a-b4d614fd04c9 |  | note | Records - Photos
label | f81070b6-a103-59f0-8b8e-a1ab908f1ce4 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5.3 - Tactiles
label | 7a88d972-4a0a-5a5a-ba21-a011089cfd07 |  | note | VERIFICATION ACTIVITY - Visual
label | 35de5e26-9d47-5bae-8657-f1fc78cc403a |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 93084d2c-69e1-56c9-94c8-de3f7a32e225 |  | note | FREQUENCY - Every site
label | 879934af-516c-5315-b37d-8fc55c10546c |  | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | c058f463-b45c-5e6f-bc5a-454c56f7e0de |  | note | Hold Point - In process Inspection
label | 3d37c479-475d-5f34-9527-f2c4f03fea4b |  | note | Records - Photos
label | 659798b9-a736-5c0f-9836-c4c1f915f06f |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | RAMM DATA
checkpoint-status |  |  | checkpoint | 6 - As built information
label | d7d60908-e0d6-5aa4-b66c-4be0807c3f26 |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | 4f10629b-a734-592b-9f8a-eaaa5f6945f6 |  | note | FREQUENCY - Every Site
label | 641911cc-b938-5f80-ba3a-7f73f492627c |  | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
label | 76021637-66fe-58f4-bbe3-23e52563ae83 |  | note | Hold Point - In Process Inspection
label | 74eabbcd-bfad-56be-a2a2-fba5ae52b8b6 |  | note | Records - As built records
label | fcc7b30b-b613-5502-b3ef-c42f271ada5f |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-sectioned |  |  | checklist | ITP - Enabling Works - Footpath, Kerb and channel | itp |  |  |  | Yes | New North Road and Sandringham Road - ITP - Enabling Works - Footpath, Kerb and channel | b7e4fcd9-920a-46fd-a835-28e4212af8be
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | 2fe52a0e-5782-5ecf-ad33-e4399c4168a7 |  | note | Verification Activity: Surveyor
label | 5bb0d8c4-4409-5ed7-8c17-2d46a6d229b3 |  | note | Methods or Reference: Surveyor
label | bc0b38cc-b4af-5139-b458-2653709d26ac |  | note | Frequency: Everysite
label | b6e5efa5-a7a5-5f7c-89d5-69118eb9a354 |  | note | Acceptance Criteria: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | 8f5a390b-aba9-5c26-a31f-c9f2dec6a3b7 |  | note | Hold Point: Mandatory HOLD POINT -
label | bef4c8fb-53d2-5e4f-96a9-df56aa4e8545 |  | note | Records: Onsite records/photos
label | 31024100-45b3-552b-9964-f568ac2244b6 |  | note | Onsite Responsibility: Site Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Kerb & Channel
label | 078fa6b1-3159-5502-8da8-5a5646d1c14f |  | note | Verification Activity: QA FORM
label | 228f584d-ee29-5b4d-8816-f6b841367cf8 |  | note | Methods or Reference: TDM Technical Standards - KC0001
label | 2a085a6c-28de-514a-8172-8f3b855d8c95 |  | note | Frequency: Everysite
label | cbdbbb48-919d-5dbf-be71-d85fdad0a37c |  | note | Acceptance Criteria: Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
label | b24288a8-bfef-527b-81b0-fc015d6845fb |  | note | Hold Point: Inprocess Inspection
label | 32a715c2-43f6-5f05-82fc-ce65ccb96ec8 |  | note | Records: FH concrete QA sheet, photos. Concrete Plant Docket
label | 460930f5-fb46-56f4-b02d-3417e7d036a1 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Channel Level
label | 681d30b3-936b-5ceb-b9f3-14f7de0e351a |  | note | Verification Activity: QA FORM
label | 13c42c4d-2497-567e-9397-b6df03b8cbab |  | note | Methods or Reference: TDM Technical Standards - KC0001
label | 157c7e24-5e01-5ad1-b564-e00b21a3fb8f |  | note | Frequency: Everysite
label | 79609dbb-8a55-510a-9609-b5f43edc2460 |  | note | Acceptance Criteria: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | 1a6557ae-dba4-558a-80d3-72467ee717f0 |  | note | Hold Point: Inprocess Inspection
label | ff900087-afad-5790-bae9-4d1690581c61 |  | note | Records: FH concrete QA sheet
label | fb0bb90b-e4e4-515c-9c24-510379b067bb |  | note | Onsite Responsibility: Site Engineer
checkpoint-group |  |  | section | Civil Works
checkpoint-status |  |  | checkpoint | 4 - AC Footpath
label | 383c73d4-9211-5eba-ae42-d228625b5d06 |  | note | Verification Activity: QA FORM
label | f6179225-d4c7-5fcc-9333-c62e2abbbc67 |  | note | Methods or Reference: TDM Technical Standards - FP0001
label | 2fddae70-cb30-5901-90cc-40b7fa2888c4 |  | note | Frequency: 10m Intervals
label | 1d4daf77-a529-519e-8818-24c509d79c65 |  | note | Acceptance Criteria: Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 13 DG7/ fine quality asphalt Mix used
label | 42dc7d35-76c1-54de-867e-ec88c9e3a3cc |  | note | Hold Point: Inprocess Inspection
label | 3ced6c52-a10f-5a18-ad5e-33e2257fdee0 |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 6b8664a0-ea65-5711-b2c5-716442cdb03b |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 5
label | 5ea8268d-ef66-54f6-b6a0-0101e631c22d |  | note | Methods or Reference: TDM Technical Standards - FP0010
label | a51db3b0-4255-56bc-b3a3-ce69f2dba6d7 |  | note | Frequency: Each PX
label | 6a01c3dd-590f-5ffa-b429-ba5f2c702a36 |  | note | Acceptance Criteria: Warning TGSI tiles should have 100mm concrete slab underneath
label | 952c1e9a-67c2-5ee5-9d3f-0f04a1de6dbc |  | note | Hold Point: Inprocess Inspection, Measurement
label | a4310b26-8a2e-5941-b436-9d0157c98f6a |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 22afbe54-d29f-5fb2-b300-0fe646b002da |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6 - Tactiles
label | 5c1742fe-fdf1-5de6-a3ff-94f123696143 |  | note | Verification Activity: Visual
label | ecb78ade-dd87-59fa-89d4-1708cc3204d0 |  | note | Methods or Reference: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 5f501c64-7adf-5c06-a8f6-62f30d043311 |  | note | Frequency: Everysite
label | 6c99a6be-120e-5aa1-99fc-196f85807a23 |  | note | Acceptance Criteria: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | 8682c26b-16de-5421-ad80-3d00e2e10589 |  | note | Hold Point: Inprocess Inspection
label | ce483a10-69c9-5c00-add6-ec545c8989e7 |  | note | Records: Photos
label | 07ed37d7-9876-522c-a768-a58fb0860c55 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6.1
label | 2f7edb57-0c1e-597f-a8f9-106e64be7172 |  | note | Methods or Reference: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 3fc0a4be-58ec-5e4f-af6a-85264be55f60 |  | note | Frequency: Everysite
label | 0103229a-cc78-562f-8aad-74ec801bdd5f |  | note | Acceptance Criteria: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | c04f5129-d843-5587-b942-f3ac0125dc38 |  | note | Hold Point: Inprocess Inspection
label | fbb92aec-70aa-563a-9633-6dfe5bd0ce75 |  | note | Records: Photos
label | 2ebbb0f4-512f-5bcb-b3fa-3a720a927da8 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6.2
label | 9f83f315-a193-5771-943d-bd23cad6f00b |  | note | Methods or Reference: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 3fca48e3-ee2c-5d90-839d-dc6bd6ff9b3c |  | note | Frequency: Everysite
label | 118b6a75-887d-5377-b317-4971bca41e0a |  | note | Acceptance Criteria: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | 2d6f708a-015a-5654-a0a8-785ae3817e79 |  | note | Hold Point: Inprocess Inspection
label | 82420e0a-e1a0-57bb-bce9-9dc0842a3477 |  | note | Records: Photos
label | c08c5d7a-d40f-5873-9477-07e354e61201 |  | note | Onsite Responsibility: Site Engineer
checkpoint-group |  |  | section | RAMM Data
checkpoint-status |  |  | checkpoint | 7 - As built information
label | fd1e7b4d-facd-5407-be2a-8a5ee3b593e1 |  | note | Verification Activity: RAMM DATA SHEET
label | 183be541-0f75-5b94-85b0-40b0be07a1ee |  | note | Methods or Reference:
label | 01d52a67-9acd-5523-aef6-f1d93d5a2ef1 |  | note | Frequency: Every Site
label | c1bbc5ee-ea4d-5e7d-a023-9be6022ff567 |  | note | Acceptance Criteria: As built drawings and Ramm Sheets Completed
label | c4af4338-a2f9-51ee-9c7d-bb5fd7b06dbf |  | note | Hold Point: In Process Inspection
label | 93cc5618-9c93-56ca-98db-e16ca2cf7f2c |  | note | Records: Asbuilt records
label | bb7e8046-ace2-5d9a-803b-1255210933f6 |  | note | Onsite Responsibility: Supervisor and Engineer
checkpoint-no-status |  |  | checkpoint | ITP Approval
label | 3bab6200-149e-5bf3-a523-b81df739c91e |  | note | Prepared by: Cimyona Vinbi (21/02/22)
label | 32ea78b5-5037-5f8d-a407-3bee8c842876 |  | note | Approving Delegate: Daniel Tat (15/03/22)
checklist-flat |  |  | checklist | Kerbs & Channel |  |  |  |  | Yes | Ponsonby - ITP - Kerbs & Channel | bae55c6d-caf7-4f40-a26c-9a818cca6c92
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 62e20d89-4479-5940-827a-6736dd6ee661 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 36403740-8a7a-5e5a-94e0-b2d1966ee4a4 |  | note | Detail - Obtain Permits
label | b86fe1c4-9814-5c8a-aa5e-2475975473c5 |  | note | Frequency - As required
label | 7f4aaec4-6890-573e-bf5a-3c021b454b50 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | f2482cd8-5914-53cc-a6f3-55cb4f5f5811 |  | note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services).
label | 98cbc3c9-f101-5286-945b-bc6b21f293f3 |  | note | • Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | b9756b96-c191-5236-9d66-a0b95879cbda |  | note | Records - Permit number noted
checkpoint-status |  |  | checkpoint | 2 - Traffic Management
label | 5954f96f-bec2-5e46-bad0-71b73c821ff8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a8de58a6-1f6a-555a-bb64-41fd340d359e |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | 5828343d-8f7d-5011-8a86-008f90fb831d |  | note | Frequency - Prior to commencement
label | fa8acb75-f229-5f47-8eb3-50e6c56e1c35 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | b1a0d9d2-f8cb-5e5b-8b06-18f672019a4a |  | note | Conformance Criteria - TMP is approved by AT for the site and works are only completed within the approved dates
label | 2800da23-c52c-5acd-94e2-bf5982474db2 |  | note | Records - TMP on MyWorksites/OnSite
checkpoint-status |  |  | checkpoint | 3 - Pre-construction sign offs
label | 4dc2c4de-06c9-520f-bd64-d5b741ba8f7a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9570df9b-4058-5410-94a3-18e83ce18281 |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site
label | 283d34be-cff7-59b3-ae68-c5d7609717eb |  | note | Frequency - Prior to commencement
label | 4d430236-1e1c-542a-a1ab-65b737fe73e8 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 6e13620a-8786-5fe3-a6b2-c09dda948bbc |  | note | Conformance Criteria - Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated
label | 1284fa02-2a3d-5351-b1bc-b3d622d792df |  | note | Records - Subcontract and Supplier Agreements, A & Updated Induction Register
checkpoint-status |  |  | checkpoint | 4 - Design
label | 82f7cda9-c75c-5bbc-a865-d30f216fbb89 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6c5d2ff3-b5e4-59e8-b258-f73189c979b7 |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | f6919c83-fc72-548f-aada-2d63f91a6310 |  | note | Frequency - Prior to commencement
label | c4472227-fc70-521d-8c64-67443ad62f76 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | c43a3b0d-5714-598b-88ec-1cad87a5e3a0 |  | note | Conformance Criteria - IFC Label on drawings
label | 773b7ad9-9f65-518f-8206-5d121fc83281 |  | note | Records - Check Drawing Register
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | 24f3b716-9e2e-51f3-8fb5-7f2b10835fc8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 543ca950-9978-5c9b-8b86-e764721c7a2a |  | note | Detail - Check constructed Sub base is within level tolerance.
label | e55b72fa-76db-55fe-968e-cfc5b58f7da4 |  | note | Frequency - Prior to commencement
label | 2db4586b-b3cf-52a7-85bd-49906e11bb4e |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
label | 3b0d5dfe-4c11-5a62-b4c9-57b90ab9bf0c |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 5 - Survey Setout (2)
label | 470024d7-aef4-59db-bec6-ac2ebdfd1b76 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ea15472a-075b-5a98-8f1b-0bf922bca9b1 |  | note | Detail - Set out Vehicle Crossing transition points and Pedestrian Drop Downs.
label | 0e231dd7-0836-5acd-818b-09b2fd03ecca |  | note | Frequency - Prior to commencement
label | 83343ddc-8394-55ca-80fb-140448f4c535 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey, Measurement and Visual inspection
label | 74cf5508-a82d-553d-b20b-a462202e9f6b |  | note | Conformance Criteria - Kerbing Specification and Geometrics Drawing
checkpoint-status |  |  | checkpoint | 6 - Material Compliance
label | 1ff9d53c-edc9-53b8-9f61-47d7f6c01455 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4c11ae5d-4df8-5ba5-a91a-8499ab6ae769 |  | note | Detail - Mortar consist of two parts fine, sharp sand to one part of cement.
label | 2d55d1b9-e7e1-5e62-ae6b-1ea247db145b |  | note | Frequency - Prior to commencement
label | 95a0e50d-f5e5-5d45-a9fc-730eea20795f |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Delivery Docket
label | 0e625ea0-f299-5ff7-a3ad-39743738ca3f |  | note | Conformance Criteria - Must be discarded if not used within 30mins of mixing
label | f93c2616-70e4-5873-ae27-8971b0f4e96a |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 6 - Material Compliance (2)
label | 8edc2d4f-d1e2-5b49-8013-96296cc80eb1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7938ed94-2d11-5d33-94e6-82b301b4446c |  | note | Detail - Precast work shall be 20MPa concrete Concrete haunching to also be 20MPa in accordance with ATCoP
label | 1e1b327a-fcfd-52b3-879a-8a160a751d72 |  | note | Frequency - Prior to commencement
label | df65d031-ea48-5c87-b553-2403a17a726b |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Delivery Docket
label | f158e992-9497-5e0f-8376-dadddcd37f38 |  | note | Conformance Criteria - Check product & dockets upon arrival onsite
label | e9acdbf3-4357-5e60-8212-1c6383729f0a |  | note | • Mix Design is approved prior to any concrete being delivered to site by Design Engineer
label | 24bbbdd9-b5a3-53f6-9b5a-70f5893aa5d5 |  | note | Records - Delivery Dockets, Mix Design report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Material Compliance (3)
label | a30d3d51-ea4c-5000-ad5f-a9cc8669e208 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2cda4c3a-8988-55ff-96da-d0260a59fb98 |  | note | Detail - GAP40 and GAP65 - Basecourse
label | 0da70a3d-e22c-5668-abf8-eb54e346f2b6 |  | note | Frequency - Prior to commencement
label | 6ddccac2-bb47-52f3-ad3c-c20121285de2 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab Testing
label | 672dd558-c770-5c67-b68f-772b28d8a963 |  | note | Conformance Criteria - Grading test only
label | a8d0b009-c367-59ca-a61b-f352179f9a51 |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Subsoils
label | 5429b1fa-fd74-5a7b-a94e-ee9759ff687d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 50907c94-5c8d-5250-ac9f-22cf9060957f |  | note | Detail - Preforated filter sleeve Drain Pipe to be placed minimium 375mm below subgrade bedded and covered with F/2 sand
label | b26269e6-52d4-5417-84cb-649960826460 |  | note | Frequency - 10m
label | 2f814d6f-97e7-5cc5-b423-7be65c7caeff |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Site Check
label | 2e7578aa-491e-57f7-8b87-b931c01d5a76 |  | note | Conformance Criteria - As per TDM Technical standards RD0100
label | f1890775-fd25-5600-bc00-3b3ba552fb24 |  | note | Records - QA Sheets
checkpoint-status |  |  | checkpoint | 8 - Precast kerb and channel
label | f52381ad-21b4-5dfb-a034-1466aff8bead |  | note | ACTION (Hold, Monitor, Witness) - M
label | f010f1e9-894b-5f2a-b20e-5827ffb7501e |  | note | Detail - All chamfer to be 20mm, kerb joints to be 10mm min cement mortared
label | 2ff7112d-2c5e-565b-b556-f1647a0959cf |  | note | Frequency - Prior installation
label | 9b90d289-ff95-5c0d-8941-3647b0a29103 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection and Measurement
label | 960c9daf-9577-5a39-ae5a-288f302c63cb |  | note | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
label | 4a318350-5eff-57b2-8864-309240764431 |  | note | Records - ATCOP, Photos
checkpoint-status |  |  | checkpoint | 9 - Kerb and channel foundation
label | 9c86595a-9641-516f-853b-71bb0d610965 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 497e1097-2414-5409-aac4-d303be38a727 |  | note | Detail - If Existing Subgrade <3% or CIV<7 (if granular), undercut required and bakcfilled with appropriate material and at depth for Design Engineer to specify.
label | 763db92d-0f5e-54b3-9b16-6f943e57a89f |  | note | Frequency - 10m
label | 4d326a86-544d-5f7e-bf21-a09443230f65 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
label | 58f8a288-0881-5e81-bd92-6ac95fe95172 |  | note | Conformance Criteria - Subgrade material >3%or CIV =>7
label | 300c2699-068f-52e2-a62d-97aae737e7a9 |  | note | Records - QA Sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Kerb and channel foundation (2)
label | 18bbf39f-f266-5a09-9d0e-cf147e2d818d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5b7c499a-60ba-547b-967c-7a79ba00fce2 |  | note | Detail - Kerbing must be laid on 300mm min GAP 65 subbase in Road and 100mm GAP 40 on Footpaths.
label | ccaa38e4-3270-5717-89c7-dc14d8f63ddf |  | note | • The subbase for the K&C must be Clegg Tested with no CIV<30
label | b9d19e00-2bd2-5ca7-b839-41cd5485444c |  | note | • Concrete haunching must be done as per drawings.
label | ba2ab687-3cd9-5931-b629-3d30a8201c95 |  | note | Frequency - 10m
label | 165f4544-a129-5ac7-8fea-1d95bfddcf48 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
label | ced54f99-fb7c-5693-b237-f29bee6daf75 |  | note | Conformance Criteria - Pavement depth and type under the kerb varies depending on location. CIV for foundations >=30
label | 0f1ecd67-36f1-547f-bd82-438f96fa328f |  | note | Records - QA Sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Kassel Kerbs Foundation
label | 85ad72bc-a6c5-5156-a77b-8c0ae8dad424 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0bc5bfd2-57c8-59b7-82ce-384b75261f4b |  | note | Detail - If the existing Subgrade material <3% CBR or CIV<7 if granular, Undercut 300mm and backfill with Granular GAP 40. Design Engineer to Specify Depth.
label | 0fe94b71-31ba-57e7-8faa-684595c16013 |  | note | Frequency - 10m
label | 57e88f6a-baa4-5577-a6c7-2699fc4fabc5 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
label | 330679f3-041c-5477-9f2f-a96ac5459b3b |  | note | Conformance Criteria - Subgrade material =>3%or CIV =>7
label | a01a92ba-8e79-5e2d-a184-0580a6d8cf8b |  | note | Records - QA Sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Kassel Kerbs Foundation (2)
label | 40de9cc1-8131-56bb-ae3f-353e42f49f31 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 49b4fa27-30b6-59eb-99a0-dd5f53cf396e |  | note | Detail - The Kassel Kerbs must be laid on minimum 15 MPa Concrete at correct 200mm thickness on GAP65 subbase CIV >15
label | c75564a0-97e1-5706-8a3a-8e8b8a77ab8d |  | note | Frequency - 10m
label | 923a80ae-79a0-5ad6-961f-afa486780dfe |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Test/Site Check
label | 076c5766-a9de-53c5-8e2e-44e17b0802a6 |  | note | Conformance Criteria - As per Drawing: 2019-AT-017_G502
label | d4d6b132-c138-56f6-90d0-5561238e8697 |  | note | Records - QA Sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Island Infill
label | 426a58e9-8059-5b60-8a3d-dbde2c5402f2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ebb79eb8-2522-56c4-9756-4bad5f36889f |  | note | Detail - If the existing Subgrade material <CBR 3% or CIV <7 (if granular), Increase base thickness by upto 100mm at the discretion of Design Engineer
label | 681179e4-30e9-50ff-a7e8-b7daa5606e4b |  | note | Frequency - 10m
label | 38995f6e-6b98-5b2c-8326-56761b2d67b6 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab/test
label | 5cbe0241-d431-50fe-b297-3e295c567fdf |  | note | Conformance Criteria - Subgrade material >3% or CIV>= 7
label | 45e82655-c398-567f-b5ed-b71eea3d5b68 |  | note | Records - QA Sheets, Design Engineer Correspondence
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Island Infill (2)
label | 467a3505-fd85-5413-b572-f625cc574911 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c5dc3c5a-0525-56ee-b902-3727c7508df9 |  | note | Detail - The sub-base must be GAP40 and must be clegg tested at every 10m intervals
label | f92ed24e-c8a9-58d5-ae5e-f081c0902dcf |  | note | Frequency - 10m
label | ab59ee90-fff3-59fb-8026-bf201f9570e1 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab/test
label | 73100581-ae30-5156-b6c8-1f25c6d2b01b |  | note | Conformance Criteria - CIV >=30
label | 824d6a4c-0e6b-5d66-9463-7257c696c6ea |  | note | Records - QA Sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Island Infill (3)
label | 62db5c81-9996-5c9b-99d0-b46060af6cfb |  | note | ACTION (Hold, Monitor, Witness) - W
label | a9c215b0-91b0-5832-8792-8b3d28cea0f2 |  | note | Detail - Concrete must be minimum of 20 Mpa and must be of correct 150mm thickness
label | 8d1173cd-dd8b-5c22-b78e-9a7d66d537b4 |  | note | Frequency - During Pour
label | 179ab947-3fc1-5bdc-8913-1a4f83d51882 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | b36a66a8-ab6f-52ff-a3a9-7ce765946318 |  | note | Conformance Criteria - Exposed finish compliant with NZS3104 and constructed accordance with NZS3109
label | 97deed65-4182-5902-a720-74b58bb29f87 |  | note | Records - Visual inspection
checkpoint-status |  |  | checkpoint | 12 - Stringing for All Kerb Type
label | fa710601-7287-5970-b765-7e283b3e0853 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 39a57d63-d6ae-5d52-88be-baa6204cde27 |  | note | Detail - Kerbs laid out accurately to lines, gradients & levels shown in drawings.
label | 87d7d37c-2a43-56ab-aeca-1da58ce18499 |  | note | Frequency - Prior to commencement
label | 7485dbc5-af77-5712-ae5c-5ef3276b99c2 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection and Measurement
label | 3f12473c-fb2c-5fa6-9206-ae1ae9121df5 |  | note | Conformance Criteria - Prior to laying, string lines or levels to be inspected by Engineers Rep.
label | 2d2c1f04-c632-5bcc-be92-78213ca6c0aa |  | note | • When a 3 m straight edge is laid parallel to any surface of a pre-cast or bluestone kerb and channel there shall be no more than 5 mm variation from the straight edge, except at change of grades or curves
label | 1753412d-7716-5970-a708-a438eed7020b |  | note | Records - ATCOP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - Dish Channels
label | 02a01078-3c1a-5c28-983f-5908fa9d5f53 |  | note | ACTION (Hold, Monitor, Witness) - M
label | f5721ed0-e8b1-5033-b146-2d867b810374 |  | note | Detail - Contraction joints at a maximum of 3m intervals.
label | 30373b0f-aa34-5ce6-8eff-cd885f94dbf9 |  | note | Frequency - During Slip forming
label | 364292d5-8b05-59e8-8a60-11eb83c8314c |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection and Measurement
label | 7c34bf72-ce13-5e42-8db9-3268ca411271 |  | note | Conformance Criteria - Kerbing Specification
label | c454c670-54cf-58f3-ab90-965200c952bf |  | note | Records - ATCOP
checkpoint-status |  |  | checkpoint | 13 - Dish Channels (2)
label | c94e55af-9e36-5e3f-a380-1084eafe77c5 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 4dd589fe-f004-558f-b4af-cdf410bd4128 |  | note | Detail - Top surface to channels to be finished smooth and even with a trowel.
label | a333c96c-1e4d-5f92-bfdc-69aab1be89cc |  | note | Frequency - Prior to commencement
label | 21415441-0a16-5a01-97ef-512e8e681c10 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | 5ab04c66-6d4f-5773-b275-23d9fdd5e1ec |  | note | Conformance Criteria - Shall not pond any water.
label | 8e5f92cf-1b58-5675-b72f-61ab749cbedb |  | note | Records - ATCOP
checkpoint-status |  |  | checkpoint | 14 - Tie-in with pre-cast components
label | 6371b36d-2417-5010-aa69-8c878303836c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 012374f6-af52-56ea-97b7-25f4a9f83636 |  | note | Detail - Ensure Kerb & channel to be cut and tied-in with pre-cast components by forming concrete aprons
label | 4afddd3c-d717-55c3-8343-2ffa8eec494f |  | note | Frequency - During works
label | 7e547f7b-6a55-529f-8e15-fd8066f33ac1 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | ea8bb5ed-ab6e-59be-bb8b-db0f82b95366 |  | note | Conformance Criteria - Consistency with Work Instruction
label | c46d5f47-eb74-55ff-a719-ffa0a84311ea |  | note | Records - ATCOP
checkpoint-status |  |  | checkpoint | 14 - Tie-in with pre-cast components (2)
label | 87143d53-5912-5dda-859b-4e8a8bf0894f |  | note | ACTION (Hold, Monitor, Witness) - M
label | d6901b3b-96d1-5716-b76d-72e69e247a74 |  | note | Detail - Channel joint material set flush with surfaces (ensure levels are within the tolerances).
label | 8adcaa00-d509-586f-877f-db0d9ffa4819 |  | note | Frequency - During works
label | b82bde5a-3599-5a3a-81d5-727ae1afeceb |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
label | 59125c42-5ba3-54d1-aa22-3071a4885971 |  | note | Conformance Criteria - Consistency with Channel Specifications
label | 5f3923c6-5dd1-551c-9596-009e8bbb384b |  | note | Records - ATCOP
checkpoint-status |  |  | checkpoint | 14 - Tie-in with pre-cast components (3)
label | 1584af3a-9c54-558b-a527-a71da10adab5 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 257323de-9243-5fcf-a695-ac2cef17ffd7 |  | note | Detail - Catchpit frame, grating and back entry kerb installed at correct level
label | c0ebef10-5ccf-52c5-a069-a79db7a295f0 |  | note | Frequency - During Works
label | c08c2aaf-8dd9-5674-b3f7-0f7669d7f2bb |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document review visual inspection
label | 75481d24-0b58-5a0a-9cfa-2dbc2ff547a9 |  | note | Conformance Criteria - Document review visual inspection
label | e373fe52-689b-5962-9805-1fec45543b2d |  | note | Records - ATCOP
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | ef8220e9-e076-5d37-8d46-f60350c45fba |  | note | ACTION (Hold, Monitor, Witness) - H
label | 35f16065-570e-5a42-a95f-f3d6f4689673 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | ce72d318-ab97-5067-b3d9-ed69c36aae1d |  | note | Frequency - At the completion of the Lot of work
label | 127c3beb-3dcd-5246-8093-2a0d791c396d |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings
label | 34a77d37-b828-5508-a646-f94567190ec4 |  | note | Records - Asbuilt Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | Traffic Islands |  |  |  |  | Yes | Sheehan Ave - ITP - Traffic Islands | bc8ce031-cf01-4852-b193-159b04364a66
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 1 - Mountable Kerb
label | 98be0f9b-ad3e-59c0-bdbe-42f8e38eb172 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 3b71cec9-21e2-5948-9e4f-d2148528a2de |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | 395771d7-9b05-5066-9e0a-962a18cc78a3 |  | note | FREQUENCY - Everysite
label | 203d768e-d99f-55e7-b6bd-a9f16db7ca2e |  | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
label | c690906c-00b1-59e9-952d-85534aa8f8b3 |  | note | Hold Point - Inprocess Inspection
label | f9c6db08-b2c5-5322-ac65-4677c142c984 |  | note | Records - FH concrete QA sheet, photos.
label | 0ad6fc16-18f1-572b-bb9f-4e0e3b792c50 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 3288d501-4e12-5b09-b20e-83c1eb54ffe9 |  | note | VERIFICATION ACTIVITY - Survey
label | 9890337d-9ea7-58e2-adbc-f567635a63f8 |  | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
label | fcf75e83-5683-5ec2-aa02-82ffb8aafacd |  | note | FREQUENCY - Prior to commencement.
label | c9e6d8f9-5724-5952-b8b1-e93ade194fbb |  | note | ACCEPTANCE CRITERIA - Survey
label | c310745f-7d24-532e-8b6d-3588766ed3bd |  | note | Hold Point - As per Construction Drawings
label | 1adcf586-c63a-52c0-a97f-8844becc47d6 |  | note | Records - Survey Receipt.
label | 7deafc1c-822c-59f5-8bc3-fa3eadd2845a |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Concrete Island
label | fc08e85d-66c1-5b53-9ec4-780336f80139 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 20ad9134-a4bc-54a9-9bd8-0f0f205c353c |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002, TDM Technical Standards - IS0001 & IS0003
label | 1f923be9-5909-59d8-a4c7-a404b27a2ce0 |  | note | FREQUENCY - Each Site
label | f5de6a3f-b90e-5ea3-9c3c-194dc668a8b9 |  | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete, Basecourse to be 150mm min thickness of GAP65
label | e0c00a9e-1953-5b11-be8d-fe31afe26422 |  | note | Hold Point - Inprocess Inspection
label | c7b990bd-cdfb-5925-8e4c-54b9d5b51fae |  | note | Records - Photos
label | 8f99278e-aae5-545b-b627-6c5e154a2f7d |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4 - Concrete Infil
label | 15153ff6-f572-558a-8f3e-40acba5aa89b |  | note | VERIFICATION ACTIVITY - QA FORM
label | 2b9af827-d8e1-5ff0-b0f8-96db4e71ae79 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | 3499d558-cffd-58ac-8f7d-9d212dd1473c |  | note | FREQUENCY - Each Site
label | ce82020b-79d4-52e7-a6fb-8152d8abaaf0 |  | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 red oxide, Cross Fall of 2% or max rise in centre of 180mm
label | 5c94ddc8-5ca4-5b20-940c-4c829ed1bf05 |  | note | Hold Point - Inprocess Inspection
label | c5637bb0-b95a-504d-96cb-ecd8d012af4c |  | note | Records - FH concrete QA sheet. Concrete delivery, Dockets kept as record
label | 26409d92-e71a-5a5f-9c4a-d9bba5df5e70 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 5 - As built information
label | d614c899-9bad-5d71-93d9-61393293e51c |  | note | VERIFICATION ACTIVITY - Drawings
label | 2494d6bb-4faa-5f8a-a846-3e858a3ea2a4 |  | note | FREQUENCY - Every Site
label | 74673376-e17b-5ea1-a55a-8e18b3b00c19 |  | note | ACCEPTANCE CRITERIA - As built drawings
label | 6ff4b6bb-238f-5789-9faf-f241ae60a1a3 |  | note | Hold Point - In Process Inspection
label | 55d397ae-a97e-5fce-87a1-8aa365462368 |  | note | Records - Asbuilt records
label | 77996391-ac9d-5f2b-9431-3b10a76b5830 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | 6 - RAMM DATA
label | 39205635-c29e-5e6a-9f55-4445fa94557d |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | 7e349841-9ed6-50e5-8022-4978aa051b75 |  | note | FREQUENCY - Every Site
label | 30214802-357b-56b2-b179-1b232997bc3a |  | note | ACCEPTANCE CRITERIA - RAMM SHEET
label | b92f940c-05f0-55bc-bb17-89cfdebac690 |  | note | Hold Point - In Process Inspection
label | 3c5e311b-6482-5fc8-9318-d78cb1f0a376 |  | note | Records - Asbuilt records
label | bc988a67-597c-59f5-afa8-e60f37e0b026 |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-sectioned |  |  | checklist | Drainage - Pipeline Installation - |  |  |  |  | Yes | Rogan Arunel - ITP - Roundabout Construction | c03ca805-3f48-41b0-bf35-c870cebcb437
checkpoint-group |  |  | section | Pre Start & Area Acceptance
checkpoint-status |  |  | checkpoint | Latest consented drawings available, checked and referenced
text | becbf563-65cf-4d00-b2a6-e5a2cf94db78 |  | textbox | Relevant drawings & revisions for reference:
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Work area acceptable & approval to start work
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-group |  |  | section | Pipeline Installation
checkpoint-status |  |  | checkpoint | Setout Completed checked and accurate
checkpoint-status |  |  | checkpoint | Excavation Accurate - Location & Depth
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status |  |  | checkpoint | Bedding depth and material correct
checkpoint-status |  |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
holdpoint |  |  | signoff | Connections to manholes complete and approved
checkpoint-status |  |  | checkpoint | Air Test Complete (Sewer Only)
checkpoint-status |  |  | checkpoint | All Pipe install elements completed - Install Completed
checkpoint-group |  |  | section | Review & Handover
checkpoint-status |  |  | checkpoint | All Pipe Install works completed, checked and reviewed as per specification
holdpoint |  |  | signoff | Raise Remedial / Request Review
checkpoint-status |  |  | checkpoint | Area left clean & tidy
holdpoint |  |  | signoff | Raise Remedial / Request Review
checklist-flat |  |  | checklist | ITP - Massey Road - Concrete Speedtable |  |  |  |  | Yes | ITP - Massey Road - Concrete Speedtable | c683d624-3111-4a62-a2ec-d73196c9aa76
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 0f4d6064-1620-51aa-bf55-ad93be71ed5f |  | note | H
label | 47027443-d8e2-526a-8840-c1a2d3f3fd1b |  | note | Detail - Obtain Permits
label | 7f6598d0-7a80-52d7-b0a2-39eb32ef0fba |  | note | Frequency - As required
label | 0ee197a6-64e8-527a-86f3-7e55fe6c00e5 |  | note | Inspection / Test Method - Document Review
label | 4ecbe8f0-136a-5f30-be19-fbda87600cec |  | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 35539426-54c0-55bc-992a-e9482824a43e |  | note | Records - Permit attached or permit number noted
label | 4b4d2b8b-1a48-55fe-bfc5-13b1e2902687 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-construction sign offs
label | ffce3f97-7c06-5547-aa12-9057aa51ab5d |  | note | H
label | 58ce06af-59ec-5978-8e1a-f2bb30a20015 |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
label | 00f61ceb-6d05-5094-abbc-5cfc936c9719 |  | note | Frequency - Prior to commencement
label | c0d8db66-fc7e-5ffc-a599-ac3959557064 |  | note | Inspection / Test Method - Document Review
label | 7f395d0e-84c1-5621-99bc-492a0148a93e |  | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
label | 8c124e0c-e6c7-5821-92d3-eec8af920cc1 |  | note | Records - Subcontract and Supplier Agreements
label | 7b1c6681-3d05-501e-8cd8-bcb0b9d02b72 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1 - Pre-construction sign offs
label | 6cd90d37-bfdb-508a-a553-c3169234e669 |  | note | H
label | 3c91dada-2d65-517a-886f-3fc9d314c9cd |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | cfcf895f-4bdc-55e7-a6b3-d3086e3f6aa9 |  | note | Frequency - Prior to commencement
label | fddcaf72-e911-572a-afda-342b322b7964 |  | note | Inspection / Test Method - Document Review
label | f1ac1315-7430-5cc8-a093-c114668d7376 |  | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | d58707cf-a3e9-5fd5-b8ca-f6bbac18bd39 |  | note | Records - TMP on MyWorksites/On Site
label | 90be97c4-ec5e-504e-9851-f1a4dbf63f59 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Pre-construction sign offs
label | 4fe36c84-677e-5618-a0ff-c4af521dafc7 |  | note | H
label | 05ca568c-96e3-5274-bae1-a590ca17317a |  | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
label | 5fa8114f-fac6-5a42-bc39-03dbf027b979 |  | note | Frequency - On site daily
label | 68fd3c0a-dd63-50db-a6d4-5945d9db8484 |  | note | Inspection / Test Method - Induction
label | d0c66501-c14b-50a6-bdd0-3fae06ef8e30 |  | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | 1613d336-4618-5a66-b479-68b61b9f7e1e |  | note | Records - Hazard ID and Pre-starts to safety team
label | 6b0e0903-a5ff-540a-81f3-3c0af7dd0c24 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 387c0396-e7bb-5b7d-899d-d33f41db257e |  | note | H
label | 7b11064f-ce46-5d01-bab4-7b4ffdbfef82 |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | eec7288f-0756-5ff2-9bc9-de79ce6c230b |  | note | Frequency - Prior to commencement
label | 799196d1-2273-5c4c-ac66-e8c01e48d0b4 |  | note | Inspection / Test Method - Document Review
label | feced328-22b5-5dd1-a628-0c38f2bfd011 |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | c262ebd3-ab97-5aba-a7b6-c503fc8cd69a |  | note | Records - Check Drawing Register
label | 912486fe-5c2f-5983-9700-39bbf490f3b8 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Installation of Erosion and Sediment Controls
label | c16a3d2c-66d3-53b4-9296-811888617760 |  | note | H
label | 3769329e-dd4d-56b1-9c2d-73e65ecfde62 |  | note | Detail - Ensure that Erosion & Sediment Control in place
label | a66b0bcb-9e2a-5e30-8a0c-156c79181afe |  | note | Frequency - Prior to commencement
label | a447b4aa-f32c-5fc6-bc0e-fdb41040db19 |  | note | Inspection / Test Method - Visual Inspection
label | f4f03a57-abee-5cf0-86aa-91b1dd458583 |  | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | 9ee8cafc-cdd3-5e7a-a6a9-631be8a69493 |  | note | Records - Environmental Controls Audit
label | 41d95662-04c7-5bd1-9712-21e61c219cc5 |  | note | FH Initials - Environmental Manager/Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | 499a3ecb-fb65-5751-8c23-f65749069d2e |  | note | H
label | 85895ce8-7384-5c15-9df2-4f54e924db0d |  | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | 234cd4ab-2086-5f29-bbf0-e810c1305214 |  | note | Frequency - Prior to commencement
label | 74e4adef-b619-58e6-a8aa-c5a01968df0b |  | note | Inspection / Test Method - Survey + Smart Level
label | e4f4fb33-acb8-5383-beee-19578a9ed4a6 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | b59a900e-1239-5349-a4bb-4282d3f6d237 |  | note | Records - Site Photos post surveying
label | 44a1198c-aaa8-58a7-8c49-c4cc6f75eca2 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging
label | 990567fc-0000-5ca6-8049-cbe0b10dc257 |  | note | H
label | 029f7459-61da-585b-9d07-547a4dec6886 |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | eecc81ea-62ba-5de9-8d0d-05a1930ee2a0 |  | note | Frequency - Prior to commencement
label | 80dea0c3-a11b-56d8-9340-761890dcee86 |  | note | Inspection / Test Method - Potholing
label | 00006604-a559-5bda-8f00-bf6c7281466f |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | 1356178b-4ad9-57b5-9f35-f80ec22e1bbd |  | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
label | eded3ebc-0136-5711-a562-440328e789d5 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Material Compliance
label | ad774b40-8edd-54f1-bb43-737e10ce0e32 |  | note | H
label | 10f70683-c825-5179-acf1-4fbaeadde4ab |  | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
label | 1bc4b32d-3258-58bd-9386-7be0fc6ee84d |  | note | Frequency - Prior to pouring concrete
label | f2607b06-b70a-5125-a7ae-2ec50a788a78 |  | note | Inspection / Test Method - Document Review
label | 215093c6-c408-5a29-b839-89dd4da69d25 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | aca146bb-2524-5e70-9737-3727e64eaa4c |  | note | Records - Delivery Dockets / Photos
label | 6b20e2bc-1173-5b84-be83-137ff0b37e1a |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1 - Material Compliance
label | c54beaac-0ad9-55db-bbe3-e454d8baaaf0 |  | note | H
label | 5299856b-c399-520a-a9cd-7b2dc5b42dbe |  | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
label | f165bd20-9cf2-508f-93c6-6999210007a6 |  | note | Frequency - Prior to pouring concrete
label | f30e8b75-a657-5c36-abec-55a9471d37ce |  | note | Inspection / Test Method - Visual Inspection, Document Review
label | aa4ef2a9-f1d2-552c-892f-a7f51f466614 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 43de80e7-996d-5b58-b46f-ae82ffdf4e44 |  | note | Records - Delivery Dockets / Photos
label | 2f748119-0023-5138-bda5-919bbb14f3c5 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 - Material Compliance
label | 5f789206-f37b-5089-bd72-cd5777b39c8c |  | note | H
label | 69d3228e-083a-5e08-8520-0501150d4486 |  | note | Detail - 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | 0d9922e2-e881-55cd-9217-5ae53a2c187c |  | note | Frequency - Prior to pouring concrete
label | 9446104e-f66a-5537-8cf1-ad6872041c78 |  | note | Inspection / Test Method - Visual Inspection
label | 38469cb4-3d32-5ac6-8de6-64d443f28470 |  | note | Conformance Criteria - CIV >15
label | 41d1bd30-2112-5491-a468-6a58d48746d8 |  | note | Records - Delivery Dockets
label | e16f8bce-4c13-5640-af8d-a00183e20802 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 - Material Compliance
label | 4818dadf-2988-549c-9b40-343f3c874d0d |  | note | H
label | 9ab047e8-6e0c-533e-82ed-00e97a431883 |  | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.4 - Material Compliance
label | b552c48b-39d1-51e0-81d6-ffaa6a894b3f |  | note | H
label | ee8f0140-1a16-581d-a6cb-c851e10fea7a |  | note | Detail - All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
label | fbad5aac-2378-5e7f-8f15-db72cd51e60d |  | note | Frequency - Prior to pouring concrete
label | 33469e0b-d663-572a-ad07-86ade5bb3b31 |  | note | Inspection / Test Method - Concrete Delivery Dockets
label | cc77c5cd-a561-50ca-a997-a63b0d35fc30 |  | note | Conformance Criteria - Delivery Docket added to QA folder
label | 61e60dc6-f265-51ca-bf7d-b7ed94aebce5 |  | note | Records - Concrete Delivery Dockets
label | 8e455699-faae-58b8-b9b8-9ca9b721ca4e |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Temporary Works (Formwork)
label | b95fb1e4-f50b-5e13-8948-d87bfeefc766 |  | note | W
label | 5ded7b26-7f79-5d51-bcb6-d212ff2120d2 |  | note | Detail - Formwork to be set to correct line and level
label | 47fdc6d1-a306-5edd-a48c-d1e32d754c57 |  | note | Frequency - Prior to pouring concrete
label | 7dec3bac-63f6-5a63-9939-758855bcdb3f |  | note | Inspection / Test Method - Visual inspection
label | 41edbbee-427b-53f2-8cf4-e980aa82105b |  | note | Conformance Criteria - Concrete Inspection Record
label | 926f99b9-2805-57d8-a552-7e31c6de57d5 |  | note | Records - Concrete Formwork Checklist
label | e37a48e1-8aa7-556c-a6dd-0dbbabd6df23 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 8.1 - Temporary Works (Formwork)
label | f76b1282-532c-529a-bd3d-528c7948665f |  | note | H
label | 68e83ad2-eee8-578f-b223-63823e96e836 |  | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:40)
label | 2089a776-6244-58ee-8ea9-06cf3654cd2c |  | note | Frequency - Prior to pouring concrete
label | fccc4f4e-97ac-5bec-9c8e-4e72b49400c0 |  | note | Inspection / Test Method - Measurement
label | c385d31b-de73-5b15-8a88-8178e1b3fd18 |  | note | Conformance Criteria - Designer to inspect formation level
label | 08d6ae13-d853-58a4-bbbe-3502248290a0 |  | note | Records - Site photos
label | 149c43d5-a28a-5e96-80ef-7d2b61a0a17b |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2 - Temporary Works (Formwork)
label | 78feef78-a58c-5e1e-a978-721237d8f2bf |  | note | H
label | beac5227-1ada-50f1-8342-8ae138d5046f |  | note | Detail - Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table
label | f2517eb8-ffaf-5811-9416-a5d5a8662460 |  | note | Frequency - Prior to pouring concrete
label | 0f3e3991-5086-58f6-ada5-601690cb3691 |  | note | Inspection / Test Method - Measurement
label | f9400cbf-7306-527f-beda-4131c796b09c |  | note | Conformance Criteria - Designer to inspect formation level
label | 9658c7c4-60a5-50ee-a26f-d37431e8066d |  | note | Records - Site photos
label | 37a0331a-1713-5015-bfe4-74a2fc318ce9 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.3 - Temporary Works (Formwork)
label | 55f8cca9-6269-5037-b295-20e7ed3c7159 |  | note | H
label | 19179e9a-e789-531c-a1d1-478b0f778526 |  | note | Detail - Raised Table ramps to be 1.125m across for entry and 3m for departure ramp.Toe to be 0.5 to 1m across for both entry and departure with 50mm asphaltic wearing course
label | 8bd07545-790f-5a60-84a1-406a229b155e |  | note | Frequency - Prior to pouring concrete
label | 57cdafbb-caab-53ce-8fa0-fc320e33aa3a |  | note | Inspection / Test Method - Measurement
label | 080e16fe-01a7-57c9-a275-937a5ab50f76 |  | note | Conformance Criteria - Designer to inspect formation level
label | fd19f098-e1ac-59d7-a09a-23681785afb6 |  | note | Records - Site photos
label | 98b28352-405a-5570-aa59-968495017e54 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4 - Temporary Works (Formwork)
label | 2c68fcc8-4469-50d4-a7d6-bdf1277e19cf |  | note | H
label | 0bbfd7ef-633b-5724-9c13-af89fc8360c2 |  | note | Detail - Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:40 relative to the road
label | f28ebe09-8876-5309-a2c9-e4749f1890bf |  | note | Frequency - Prior to pouring concrete
label | 81e112b7-ba11-5c34-9dc6-ed9e8d6ab203 |  | note | Inspection / Test Method - Measurement
label | 17eca3c2-32e2-5b5b-9d71-667d81c033bf |  | note | Conformance Criteria - Designer to inspect gradient level
label | c78be967-02f2-59c9-bacd-4e6e3f2dcb23 |  | note | Records - Site photos / Concrete Formwork Checklist
label | 3288e6b2-b2c6-555f-a841-14bb42c2e65c |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5 - Temporary Works (Formwork)
label | 48218fa4-b097-536f-91de-26a527497872 |  | note | H
label | a3f00042-eb48-5d2f-9acb-d810f9a9fbcd |  | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | d38874b4-c0e6-56a9-a709-a1925a3cf4e2 |  | note | Frequency - Prior to concrete pour
label | 73f2f102-f3a1-5046-a6d4-e6d52ddb6c51 |  | note | Inspection / Test Method - Visual inspection
label | a91e1374-791d-58ce-b9c4-a7831bfef6a6 |  | note | Conformance Criteria - Concrete Inspection Record
label | 8dbd82ea-402c-567c-9784-73b040d38afc |  | note | Records - Concrete Formwork Checklist
label | 2e7755a7-d37f-55d6-9a8b-2dea1ce9b4aa |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Reinforcing
label | 2840ba86-f67e-528b-a06d-2902f3649ba7 |  | note | H
label | eaa9d176-b8b0-5bfe-aadf-ece31bba38a9 |  | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
label | f299b4f1-3ebf-59b9-81d1-4ad43592e741 |  | note | Frequency - Prior to pouring concrete
label | 5bd6f5e0-241c-58f5-90b8-3f85b380059e |  | note | Inspection / Test Method - Measurement
label | 8c1cd58c-e49d-554f-87b7-9df5906eb0fb |  | note | Conformance Criteria - Concrete Inspection Record
label | 11a058f0-3838-5722-9f60-8e6fab8657ae |  | note | Records - Site photos/Concrete Formwork Checklist
label | 631ca45d-86c0-5019-9042-6264c89769a0 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Concreting
label | 117dc37e-51a7-50ff-85b5-35c60dc7d688 |  | note | H
label | 69018828-cdd9-57f6-b352-4e245105c7a3 |  | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | 2ed95d1b-c428-52ad-ab85-d4432bc6f619 |  | note | Frequency - Prior to concrete pour
label | f5108f52-11aa-5d5a-9ad1-e4ca419b19ae |  | note | Inspection / Test Method - Visual inspection
label | e6ce21d7-83e9-587a-914e-dd4dfbc171e1 |  | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | dfef2d05-0f1a-5e89-aa1c-fa07f4531f5d |  | note | Records - Email / SMS
label | f122a913-2e33-5bb3-a067-9f260e7ccbed |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1 - Concreting
label | 34be1a9a-a917-5f48-a62f-79b6c4fab4c9 |  | note | W
label | bc58a866-d889-5284-9a82-c3bd46788329 |  | note | Detail - Vibrator to be used throughout concrete pour
label | cf52789a-f377-534e-b60b-23de42381468 |  | note | Frequency - When pouring concrete
label | 260f281f-4b22-5426-a5fd-29bfe9bf78e0 |  | note | Inspection / Test Method - Visual Inspection
label | 28883e40-f2c1-54e2-8656-562e0cecf13b |  | note | Conformance Criteria - Concrete Inspection Record
label | 80e5bcfa-25da-5593-99b1-51ed94e957c5 |  | note | Records - Concrete Formwork Checklist
label | 6d12907d-bfe6-5814-8ca9-d0005fc178f5 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 10.2 - Concreting
label | f7d2df1b-a8a8-59a1-a772-a17db52e0049 |  | note | H
label | 45c73e1a-6619-5db2-bb77-f25fdacd6b67 |  | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
label | bddb1747-4a88-5580-b98b-c9e2f3d827a4 |  | note | Frequency - At completion of pour
label | 5de21843-a826-50e9-a344-195f8d3bf3bd |  | note | Inspection / Test Method - Visual inspection
label | ec1d3784-a6c6-5e3d-9f5c-01da6669016a |  | note | Conformance Criteria - Concrete Inspection Record
label | 6c920759-c721-561d-8697-d757f55965ec |  | note | Records - Concrete Formwork Checklist
label | f9b5bd9d-302f-540c-8ad0-1a0fbac94f51 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Curing
label | 7af45420-4d31-5561-9a3b-198d8e3eb605 |  | note | M
label | 1bc11787-46e0-5da2-819a-220bef1c7338 |  | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | cce22517-65b5-597f-8d84-08a78a3c5de1 |  | note | Frequency - Post Pour
label | 32d2015a-9c0d-52ef-8644-576e87aab836 |  | note | Inspection / Test Method - Monitoring the time allowed for curing
label | 594b4a3f-dab6-5637-b551-9eb183fabf15 |  | note | Conformance Criteria - 48 hours minimum have passed
label | 23e3fcf3-2f44-5633-9cb4-cd782e7e9c21 |  | note | Records - Concrete Formwork Checklist
label | 71b6bb6e-3dab-5ef4-88d2-cd00559e69cf |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 12 - Remove formwork
label | fa01c4b1-2f3c-5c31-998e-b5b797852773 |  | note | W
label | 343a09ac-cf9a-57d0-b371-13ddffc9892d |  | note | Detail - Remove formwork after 48 hours
label | 78696a15-4037-527c-b05e-17133764d97a |  | note | Frequency - Post Curing
label | 2c6014dc-4c2c-5551-b3b9-3be9dd92b866 |  | note | Inspection / Test Method - Visual inspection
label | ebd734e3-f7af-5c5a-bf77-feb5db5619f4 |  | note | Conformance Criteria - Concrete Inspection Record
label | efd21a9c-a633-5f37-8e96-6f746bd8bdca |  | note | Records - Concrete Formwork Checklist
label | fc97511b-0b74-5520-928a-42ee66284224 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
label | 1718446f-5885-5108-a6b5-36459b135fe5 |  | note | H
label | 862698ab-7128-50b1-9fa1-a2df69cff95a |  | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
label | 8b48170f-42fb-598b-80b8-fd45c20a2e50 |  | note | Frequency - Prior to pouring concrete
label | f47c8879-c242-5881-95b9-79474ef14b2b |  | note | Inspection / Test Method - Measurement
label | f5148ed9-3400-590b-b5fc-dcc942f7492a |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | a632ef94-7c25-5b22-b660-aceed8888408 |  | note | Records - Site photos,delivery dockets
label | c2b0ae29-2f58-5d4a-b8a0-ae1c8ad15a57 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.1 - Asphalt- Concrete extension slab/ Toe
label | 5573c8bd-4092-5ea5-aa8d-dad41a95173e |  | note | H
label | 213a958c-317f-52f4-819a-96d919c40c00 |  | note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
label | 08d9e0bd-5c52-50bb-aaae-37336611bb39 |  | note | Frequency - Prior to pouring concrete
label | d7a6095b-3b56-5518-a333-064caf99c5af |  | note | Inspection / Test Method - Measurement
label | a21e0186-a353-593c-927f-62fe93a8235a |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | e9552771-19e4-50bc-b5d4-5c603587af85 |  | note | Records - Site photos,delivery dockets
label | f5851840-ff4c-5da0-bcc3-eb4de4ba49d7 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.2 - Asphalt- Concrete extension slab/ Toe
label | c3272865-fa17-5a09-8611-2dc77eb71aec |  | note | W
label | b4c35e9e-8a77-5d41-8d9d-caeff69384a4 |  | note | Detail - Tack Coat between AC and Concrete slab
label | 3f851fbf-9a97-50e9-8e09-47dc32b5a64a |  | note | Frequency - Post Curing
label | f9063739-8d2d-5109-85ae-02534e1220e2 |  | note | Inspection / Test Method - Visual inspection
label | 5db1dca2-b438-5457-b0cf-c55b73566e44 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 80b55f22-9f89-5970-91e3-ccb2301c6051 |  | note | Records - Site photos
label | 8a882f0f-2d26-52f6-8f2f-5ee9ea45b861 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 13.3 - Asphalt- Concrete extension slab/ Toe
label | 637ee4ad-cad5-5dff-a310-1b4a1f611551 |  | note | W
label | a423ccd9-f12f-53e6-8c0b-f4529ef6f067 |  | note | Detail - 50mm thick DG10 / Mix 7
label | a4436f06-c33c-5f96-a3bb-dd2f45379caa |  | note | Frequency - Post Curing
label | 34c886c8-c55a-5561-bfe2-08b279a3e1d9 |  | note | Inspection / Test Method - Measurement
label | b377205d-3b62-5f8d-b405-e2435fbffe89 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 9b3e6a67-a1d2-51c2-a520-2a1bba5e9758 |  | note | Records - Site photos,delivery dockets
label | 3efbd145-8ba5-5b22-8628-c69cd50e3100 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 14 - Lot Number QA File
label | bdcb2868-da6a-556c-b4b6-6a7eb0a4276b |  | note | W
label | 679d987e-d33c-5f7b-97ec-e2edbd3633c8 |  | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | 6e1d9664-76a2-54d5-b4aa-3900bf7d41eb |  | note | Frequency - At completion of Lot
label | e092abbd-5ac8-5339-9119-3850afa32f2b |  | note | Inspection / Test Method - Document Review
label | 0cc05428-edc2-5949-87da-abb689913190 |  | note | Conformance Criteria - All QA files compiled and sumbitted to client
label | b6a7522f-f120-51a6-9431-b508b5906dd2 |  | note | Records - QA records
label | 23ac1799-a1c3-5052-8ad0-ef0fc8d696e2 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 14.1 - Lot Number QA File
label | 47f9a892-46da-5c2d-81f2-a169d7e5fbf5 |  | note | W
label | 78c71332-c880-5931-a817-3b3f603ab7a3 |  | note | Detail - Delivery Dockets to be included in QA file
label | 94849429-7261-502f-ae9c-4e088d74d36e |  | note | Frequency - At completion of Lot
label | 38b26994-f2f6-517b-b2a5-0cbe29068ff1 |  | note | Inspection / Test Method - Document Review
label | d2d98d1a-de4d-54cd-a260-16c4b0b012f9 |  | note | Conformance Criteria - Delivery Dockets to be included in QA file
label | e5524f37-1b54-5d6f-89a3-d8fc002ac2cb |  | note | Records - QA records
label | 8faa7480-976d-59de-8f12-381024e40bd1 |  | note | FH Initials - Site Engineer
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | de83c686-dde8-51ce-907d-b993402fb4c2 |  | note | H
label | d51f0e5f-234a-5ea8-bc11-af14c55b6531 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | a546573a-2e86-594f-9805-e26533113004 |  | note | Frequency - At the completion of the Lot of work
label | 90e38ad5-a4cb-55cd-861f-31d949b6689f |  | note | Inspection / Test Method - Drawings
label | 44c7f70a-7fee-574e-901f-63a2a63a41cd |  | note | Records - Asbuilt Drawing
label | 5e7a36e7-5dc4-52fb-8974-d23bdb9aa2d2 |  | note | FH Initials - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Mckenzie Road - Istands | itp |  |  |  | Yes | ITP - Mckenzie Road - Istands | c893bfa6-3050-4922-803b-1267c55783a3
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 1 - Mountable Kerb
label | b5b29231-6dbd-5f2a-a6e8-362c7dc22159 |  | note | VERIFICATION ACTIVITY - QA FORM
label | ecbf6ae6-bd11-5b41-b94e-15c714787622 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | 59545849-38c3-53d8-bf1a-1474cf6c1df9 |  | note | Frequency - Everysite
label | e3481414-55ed-590e-9f0d-59a841c72ffc |  | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
label | e99e213b-fa15-5e77-a9bb-e3d25e9def41 |  | note | Inprocess Inspection
label | 19abb039-a9c8-5ca1-b05c-fa7cad8ef99e |  | note | Records - FH concrete QA sheet, photos.
label | 5dd78786-4cb7-55b7-b004-7090d79aa702 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 0a5c58e4-10be-52f3-9540-7af022a2cec3 |  | note | VERIFICATION ACTIVITY - Survey
label | cfce74f1-1328-55ef-9148-c3d5a7d6b836 |  | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
label | 239d0a59-52a1-560e-8de6-06cc70950f35 |  | note | Frequency - Prior to commencement.
label | b0fa0657-b135-50f6-8de7-3b6dc13c70d7 |  | note | ACCEPTANCE CRITERIA - Survey
label | 4b50244a-88be-5498-8f5d-e8647c2e2b51 |  | note | As per Construction Drawings
label | 7a841d36-a2ca-5348-8c72-e4b478af8f84 |  | note | Records - Survey Receipt.
label | 86ccae4e-3657-5abb-b7a2-a1b93f6ca539 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Concrete Island
label | 4a74169c-ebbb-52a0-8141-fc4fb3e79b64 |  | note | VERIFICATION ACTIVITY - QA FORM
label | fbb090f6-6ae3-52b1-adde-99ae865a9b70 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | 315ea323-337d-51a5-8407-554c2a1d11d2 |  | note | Frequency - Each Site
label | d0320fa8-4620-561a-9f0c-a273ff63faad |  | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete
label | dcb15982-1e2f-5573-93c5-8261d48fe7b2 |  | note | Inprocess Inspection
label | 4f4fea3b-7f83-5fa0-b2b8-1f13ce358722 |  | note | Records - Photos
label | 298f4900-53f4-5223-b249-bfcfe6d1ace4 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3.1 - Concrete Island
label | e0ae9b25-73fc-5b8d-918d-87cd670676eb |  | note | VERIFICATION ACTIVITY - QA FORM
label | 28c83f0e-7165-58e8-9c90-55d4c8bc6df7 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0003
label | eda69262-cd49-5d44-958e-df1bfd1d264f |  | note | Frequency - Each Site
label | c636587c-5b01-5a00-814e-0190b3454327 |  | note | ACCEPTANCE CRITERIA - Basecourse to be 150mm min thickness of GAP65
label | 122a3ce4-60e7-564d-8e28-377d4e25e697 |  | note | Inprocess Inspection
label | 79654a07-8837-5f0c-bad6-23170986e0b4 |  | note | Records - Photos
label | 5352c20d-4a3e-5f8c-a3f6-212d55069d88 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4 - Concrete Infil
label | 3318be48-2ef8-5887-b6e0-00454711bc67 |  | note | VERIFICATION ACTIVITY - QA FORM
label | fb8b9f11-7cbc-50a3-bb8c-eb118d8ebb7d |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
label | 897736fd-2410-527f-80cc-de5da7d759a6 |  | note | Frequency - Each Site
label | ba8906fd-ff48-5543-bfc2-6d0cbf4fb1e1 |  | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 black oxide Cross Fall of 2% or max rise in centre of 180mm
label | a0803486-6431-52c3-a5ee-9aee9afca9c9 |  | note | Inprocess Inspection
label | 126bb5c9-acaa-54fc-9618-99e8e201b529 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 2f132c15-ea38-5f3e-bf74-cd4fde0e23ac |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 5 - As built information
label | c8dd1ba8-975a-54cf-b1ed-a1c22ac7883d |  | note | VERIFICATION ACTIVITY - Drawings
label | 9e4170b7-e428-5c6e-87c8-ea5713ba3f50 |  | note | Frequency - Every Site
label | d7b44af1-e174-50ff-ae43-9a45ef43c851 |  | note | ACCEPTANCE CRITERIA - As built drawings
label | 7dd495bc-dc07-5baa-8039-1068addd84e7 |  | note | In Process Inspection
label | 0ebbc3fb-fc32-5ca7-bba6-ca85bbe9f03f |  | note | Records - Asbuilt records
label | fc2239ab-ee3b-5f3e-b77d-4dd166958db0 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | 6 - RAMM DATA
label | 9cb46067-41b5-5f6d-ab4b-756bffb8374d |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | c627eae4-3992-5601-b243-8fc6be1837b1 |  | note | Frequency - Every Site
label | 5f7b3300-29e1-590c-a9cb-bfb565d6bb5b |  | note | ACCEPTANCE CRITERIA - RAMM SHEET
label | d0d4d1de-3c96-5463-8195-4eba3cfea856 |  | note | In Process Inspection
label | 8e9b7c88-5631-580e-b278-18a8aef89ddd |  | note | Records - Asbuilt records
label | 33e9f869-7c48-58da-a354-dda3a0c82384 |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-sectioned |  |  | checklist | ITP - Mckenzie Road - Enabling Works | itp |  |  |  | Yes | ITP - Mckenzie Road - Enabling Works | c9f0fcf8-5059-4b99-b6b8-0836fc7fe957
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | 439422f2-2c65-58e4-82f9-d707ee6f717a |  | note | VERIFICATION ACTIVITY - Surveyor
label | 74253c76-5cb4-59b3-aa0b-cda5769e4c35 |  | note | METHODS OR REFERENCE - Surveyor
label | 7a39e8e9-2b14-5cc1-b42b-6dc106657636 |  | note | Frequency - Everysite
label | 6833c819-3c7e-50a7-a315-2042a706ea86 |  | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
label | f0f0b2b3-da17-565e-9a14-68dcecfa3afa |  | note | Mandatory HOLD POINT -
label | 83e04af4-81d1-50da-a302-beda8fcbd470 |  | note | Records - Onsite records/photos
label | b3233770-065e-5c02-bed3-f127b70ee55a |  | note | Onsite Responsibility - Site Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Kerb & Channel
label | c5743425-7d8e-59ae-b212-ca2bf2e0c7ab |  | note | VERIFICATION ACTIVITY - QA FORM
label | a96d3300-262b-5c58-b24e-7403c24008e9 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | 6092a0c1-7c4b-5c3c-9371-391ab7a26a7c |  | note | Frequency - Everysite
label | 8a8b924b-4f38-544f-b101-00392ed216f3 |  | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
label | e196b0b6-6bc7-527e-9f37-44b6cb660c14 |  | note | Inprocess Inspection
label | ff5619e0-83fc-5dfa-95f6-6cbe08703c97 |  | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
label | 2f91bef5-b2ba-55db-84c0-af489b1dd3ab |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Channel Level
label | 09ab135e-af17-5501-b3b3-6c26b8445398 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 829cac3e-09af-567a-b1cf-fc1f3c28e4ed |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | c2ab4cae-ffd0-5d1e-ab6d-8c64bebadaf8 |  | note | Frequency - Everysite
label | 75e97bf6-04f9-5865-8abd-3009d119b570 |  | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | bda627e4-899d-5215-a8b6-619c2114fda8 |  | note | Inprocess Inspection
label | 549d1dcb-eeca-5aa8-a3dc-a0ab226ba548 |  | note | Records - FH concrete QA sheet
label | df1bf82e-4d25-5fb9-94a5-a66bb448dc1e |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | CIVIL WORKS
checkpoint-status |  |  | checkpoint | 4 - Concrete Footpaths
label | cfb4ccbd-254d-539f-aafd-7a745f405324 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 1654db99-b2a0-58f0-af3d-32e58b4b2862 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
label | 574d5174-04f6-582a-9c69-7a25801f615f |  | note | Frequency - 10m Intervals
label | b7754a23-9ba2-54bc-916b-de79c07221f1 |  | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
label | 6522b40f-d64b-59dd-941d-ec333f895f20 |  | note | Inprocess Inspection
label | 474da51e-632c-5151-985a-a8ca5d4aa53b |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 714aed54-a5ac-54c7-9427-240ef32b4a6a |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Concrete Footpaths
label | 45800dca-e5fd-564c-ba68-e3867f609c88 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
label | 23ff0886-3367-5f3c-81d9-334b1e840b69 |  | note | Frequency - Each PX
label | 1e4ea2da-a3c6-5001-b1dc-09e00df219e5 |  | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
label | d8578279-7668-528e-bbb7-93fd00d24070 |  | note | Inprocess Inspection, Measurement
label | dc7ae81d-29ff-5c4b-a277-3f9bf2042ca7 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 6ec6c717-c885-5929-9abc-484c033d4a0d |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6 - Tactiles
label | b41fcf97-3426-5beb-81c5-4f52f5588ef7 |  | note | VERIFICATION ACTIVITY - Visual
label | 87efeafb-35ae-5633-816b-2c9f75ce2408 |  | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 701b4689-b6b9-5883-ac05-8f404bac611c |  | note | Frequency - Everysite
label | a9718bb5-35ec-5a01-99b9-d1fefeeaf218 |  | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | 09cb9a96-6b04-5402-94c1-3bdc3ac19489 |  | note | Inprocess Inspection
label | 8c3b0e8e-7e6c-57ab-845f-32449b49f50a |  | note | Records - Photos
label | 04789e70-9f7f-56e8-9965-d74b639cc3da |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6.1 - Tactiles
label | 9b367b77-378b-57d4-be85-23222e30578d |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 38509ada-5593-52be-9c7d-30413cbc30b4 |  | note | Frequency - Everysite
label | afe9e313-2c71-5a9d-9f7d-dc1643d171d8 |  | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | fbfcbe44-6ecc-5dd1-8d2b-d9166d3c379b |  | note | Inprocess Inspection
label | 9f667a29-7e6e-514d-a258-42666b1dd89e |  | note | Records - Photos
label | 4010b5ad-1fac-5a0d-8266-df92c96ea2dd |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6.2 - Tactiles
label | 9c36eea6-6a47-58c8-8d52-267128a0bcfd |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 93f3b718-fda0-5281-8bf8-0992de6f56ce |  | note | Frequency - Everysite
label | ec3e83a0-0e0b-5a04-9baa-1f52eb166111 |  | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | 48139960-530b-5a53-a3f7-f0fde34ef3b0 |  | note | Inprocess Inspection
label | 888b36f2-756c-5571-9a14-609b73280956 |  | note | Records - Photos
label | e8a96466-e202-5175-8fb6-9d9fb9c85988 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | RAMM DATA
checkpoint-status |  |  | checkpoint | 7 - As built information
label | 8d793f95-8342-5e5d-9925-768d10f0579d |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | f2c76af5-4137-598d-88de-4e058d945a74 |  | note | Frequency - Every Site
label | d0b881b1-54f2-5e77-98fe-90c424c920c1 |  | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
label | 4b755307-fbc7-5cae-8680-e0028cdf13aa |  | note | In Process Inspection
label | a8953299-5066-503b-8cac-05c2a7dbeecb |  | note | Records - Asbuilt records
label | 3f265431-cfad-5bf0-b22a-287068e9d41f |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-sectioned |  |  | checklist | Enabling Works - Footpath, Kerb and Channel |  |  |  |  | Yes | Tui Rd - ITP - Enabling Works - Footpath, Kerb and Channel | d128af73-4d51-4c5f-a6fb-2740c74ad43d
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | b3a70e77-027b-5067-9797-c99e3ad76b1d |  | note | VERIFICATION ACTIVITY - Surveyor
label | 3f56bf33-4668-5d49-85f1-015b209f89c9 |  | note | METHODS OR REFERENCE - Surveyor
label | 87315cfb-95a1-5a5f-9548-d705f00ad218 |  | note | FREQUENCY - Every Site
label | e7eb2c4f-7f46-50f1-a7e5-ab729804a3a7 |  | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | fe0823db-f60e-5def-bf6f-0982c19a477e |  | note | Hold Point - Mandatory HOLD POINT -
label | 9b248af1-672b-5c69-ade7-dca23870892a |  | note | Records - Onsite records/photos
label | 3e5b8ace-d656-5b9b-9a27-844a8ad9cbef |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Kerb & Channel
label | cc21a109-f5d8-59dc-a8d8-ccb0fa719e9a |  | note | VERIFICATION ACTIVITY - QA FORM
label | 68efa75e-0683-52de-836e-acc48fc78302 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | 0da0e14f-fc29-5366-84a7-f3009be5c572 |  | note | FREQUENCY - Every Site
label | c7ff5a11-ceb5-5c8d-8756-c60a215acd73 |  | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40
label | 6916098d-ca06-5ee0-abac-2f868b9b43a7 |  | note | Hold Point - In Process Inspection
label | e20fdf9b-07d6-5852-8196-bfa70184b394 |  | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
label | 27152a28-930c-57b5-96d2-e9e653b43b3d |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Channel Level
label | 80fb4431-347e-5fc9-a390-80d2363e2fbc |  | note | VERIFICATION ACTIVITY - QA FORM
label | adbb8108-2646-5c80-b145-604ccdb19d19 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | b0e086f7-8085-54b8-adb0-f8151be47c89 |  | note | FREQUENCY - Every Site
label | 2359dd18-04cc-5fb9-979a-0d0807063a44 |  | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | 88ffd02c-781d-5c9b-b776-059804f44728 |  | note | Hold Point - In Process Inspection
label | 85b99411-f60c-562d-9170-3d17a7d61d28 |  | note | Records - FH concrete QA sheet, Photos
label | 2e84f918-e5ad-55df-98fa-765269aa6b86 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Civil Works
checkpoint-status |  |  | checkpoint | 4 - Concrete Footpaths
label | fb5de875-3277-5c1d-be8a-38991ec5ab37 |  | note | VERIFICATION ACTIVITY - QA FORM
label | c518ef1a-3e84-5f84-ae55-9971d1cf54bd |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
label | ca34de8c-09b6-51c3-853d-6cc2bddd3f90 |  | note | FREQUENCY - 10m Intervals
label | 6c0ca541-b8e3-5b4b-a115-a77b853a3b34 |  | note | ACCEPTANCE CRITERIA - Basecourse - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
label | 87b50fe1-fc55-5b0b-83bd-353dbf8effd4 |  | note | Hold Point - In Process Inspection
label | 8a153b91-0625-58d2-b649-6cbf79dfc0a7 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | 12bee3bb-6d14-5eb1-8392-c22d7b7e8373 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Tactiles
label | 0525e1a9-82bb-5a87-b902-c881a86b1b0d |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
label | f3ed2490-8d03-5ddf-99ab-64d6b72238db |  | note | FREQUENCY - Each PX
label | c4d769a1-00b1-55fd-8d2b-b5522fc18538 |  | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 150mm concrete slab underneath
label | eabc50a9-3774-567d-b460-c1133a69dd2c |  | note | Hold Point - In Process Inspection, Measurement
label | c29d65cc-4a8f-590d-83a0-ce9bb12ab667 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | b59a52ba-d959-5a4e-927b-02c2b592d062 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5.1
label | 4f70dcdc-8b93-5768-893b-5e6f6a77f097 |  | note | VERIFICATION ACTIVITY - Visual
label | 9b83a32f-20ad-5e95-af66-5b89e3d61942 |  | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 8c16db9b-5b3b-5919-ba9a-d4695c6d4f1a |  | note | FREQUENCY - Every Site
label | 2aa3cf13-0503-5d3b-bd50-d9d9d643c947 |  | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | 460c7b5a-1fee-50c5-8759-7dfef181f16b |  | note | Hold Point - In Process Inspection
label | 8202732a-569e-511d-86cf-7b9ffd188a12 |  | note | Records - Photos
label | 74267c85-a489-501d-b5cd-201dfa641df9 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5.2
label | 1986d75f-0988-559d-ae30-14e8963f3095 |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | dd3cd2ea-f63a-5704-9e80-f2eed6eb8c26 |  | note | FREQUENCY - Every Site
label | 32eed9e8-68e1-5810-9cb3-25af3cd7a90e |  | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane.
label | cb922aec-89b2-5406-9d32-d71ebc39804c |  | note | Hold Point - In Process Inspection
label | 0e524f9a-f2d5-57eb-bb9f-e3d8bb71da16 |  | note | Records - Photos
label | 99a962f5-7266-5fe6-a722-32cfde72b75f |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5.3
label | 2d01a0cf-f00e-55f4-a9de-6728e500348b |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | d383a4bf-35d4-503a-b65c-7e49abc2b3f2 |  | note | FREQUENCY - Every Site
label | 7bce9772-5d80-51c0-af1b-b30ab283bca4 |  | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | ee32891e-ee3d-5bbd-aa22-a59b08c66ae8 |  | note | Hold Point - In Process Inspection
label | 14f1fd15-686f-547e-9b9d-a90fbddf1aec |  | note | Records - Materials Dockets
label | d0a8c4db-804d-5119-a31a-c0edc6ed22b5 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | 6
checkpoint-status |  |  | checkpoint | 7 - As built information
label | 54aa5161-1743-5e4a-8cff-14bd9ecab42d |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | be6b6115-c6aa-5bae-b0f0-16e83ec6ebf9 |  | note | FREQUENCY - Every Site
label | bb427496-579d-5081-8569-1e414afd80cb |  | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
label | ea721030-d852-5e8a-9a22-c3494caed59a |  | note | Hold Point - In Process Inspection
label | 7a35a218-bd56-57cd-b916-239c8298aaa9 |  | note | Records - Asbuilt records
label | 2a722b40-e81b-54a4-9a0d-37cb0554ea83 |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-sectioned |  |  | checklist | ITP - St Lukes Road/Morningside Drive intersection - Signage |  |  |  |  | Yes | ITP - St Lukes Road/Morningside Drive intersection - Signage | d23c3f41-5ebf-4e92-bdcf-0cfbd2cbcb58
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | 6c30b96f-cc76-519f-939e-65b0f3e5c4cd |  | note | VERIFICATION ACTIVITY - Surveyor
label | 9b419a34-fba2-5517-9907-219ca93c82d5 |  | note | METHODS OR REFERENCE - Surveyor
label | e42cb435-a1c6-5350-83ac-6fb6f0ad65c8 |  | note | FREQUENCY - Everysite
label | 47ad77de-9b70-5d3a-b658-18efd2884a3a |  | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like
label | 6211c931-97fe-5441-bfaf-5c1b4f077a32 |  | note | Hold Point - Mandatory HOLD POINT -
label | 002256ce-4831-54fb-b1dd-2c9da066d919 |  | note | Records - Survey Receipt
label | c8d7f9d8-518c-5ffc-9a43-cbdbf125f219 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Signs/Belisha Disk
label | 8cdd2313-0161-59fe-8093-052cb1f5301b |  | note | VERIFICATION ACTIVITY - QA FORM
label | c4d84a2e-15fb-54af-96db-7c1833ed6265 |  | note | METHODS OR REFERENCE - TDM Technical Standards
label | 37345873-2bc6-59a7-9035-907fa0413645 |  | note | FREQUENCY - Every site
label | 0521424b-fb14-5431-9e1a-1152938aef17 |  | note | ACCEPTANCE CRITERIA - All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
label | 83748288-3989-5fa1-9833-c04d82a14bd4 |  | note | Hold Point - Inprocess Inspection
label | 42e796ce-dcac-528c-a7ae-e3a1b33be1b9 |  | note | Records - Dockets/Photos
label | 29acf428-061c-5156-858f-c6de95849ec0 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Pole, Impact recovery post and Ground Socket
label | 296976d6-d5e8-595d-b5b2-50dc4ffee59d |  | note | VERIFICATION ACTIVITY - QA FORM
label | 8d6137a6-185b-5522-90b1-9d740df4acef |  | note | METHODS OR REFERENCE - TDM Technical Standards
label | 1e728bde-734e-5710-b930-078fe7bef29a |  | note | FREQUENCY - Every site
label | e3871b77-d62a-5d88-bc18-b4eecb2fbd73 |  | note | ACCEPTANCE CRITERIA - Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
label | 3447d9bb-043b-5e28-ba49-617582a2cf01 |  | note | Hold Point - Inprocess Inspection
label | 7ad56af7-7ec7-551e-b0f8-302e60ead007 |  | note | Records - Dockets/Photos
label | c700c196-3d59-5e66-b19d-76d5f1a8eadf |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 4a - Ground Socket
label | 0f6392cf-8473-5e9f-b5d8-af6217ccbc09 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 510b353f-bdbc-531f-a96f-e8235d22b0af |  | note | METHODS OR REFERENCE - TDM Technical Standards
label | 4798ef22-c4b9-5401-965b-d64985b2e237 |  | note | FREQUENCY - Each Socket
label | 983488b5-4601-5662-88d7-6e4fd9b69540 |  | note | ACCEPTANCE CRITERIA - The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
label | b7c63dba-23fa-552c-84fb-8fd9628a1ae6 |  | note | Hold Point - Inprocess Inspection
label | 84a50fb8-bc2a-520c-8634-3ccc1a92b795 |  | note | Records - Dockets/Photos with tape measurement
label | 1e4e988f-b75d-581c-a865-2ededf737d06 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4b - Pole and Impact recovery post
label | 20aeae10-a04e-5e10-b7f3-8107e26de1d6 |  | note | VERIFICATION ACTIVITY - QA FORM
label | b9e329cc-5f86-563d-92d2-afa297d06b34 |  | note | METHODS OR REFERENCE - TDM Technical Standards
label | f93094dd-b717-5876-b0b6-5247a5bfbc8c |  | note | FREQUENCY - Each Post or pole
label | f47116f7-d0cb-5020-a94a-bb16a528f1c3 |  | note | ACCEPTANCE CRITERIA - All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent thr pole rotation. The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
label | 9de63f0b-21f4-58c8-9c65-1cc2c6283a2e |  | note | Hold Point - Inprocess Inspection
label | 049bb299-122d-5d4f-ab4a-e72a958499f8 |  | note | Records - Dockets/Photos
label | 926f7564-5b2c-5121-889a-43f1bfac7dca |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Signs/Belisha Disk
label | b7d83355-5457-53f3-8c1d-2bdbf85d9f5e |  | note | VERIFICATION ACTIVITY - QA FORM
label | ba49d362-fa68-5c4f-b490-69e62068626b |  | note | METHODS OR REFERENCE - TDM Technical Standards
label | 0e6081a6-2ba4-560f-8509-0b50b7d8c90b |  | note | FREQUENCY - Each Sign
label | d56be1eb-edab-58a5-b197-ab34849ca520 |  | note | ACCEPTANCE CRITERIA - All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
label | 603fa05e-bd93-502c-8827-857da99065be |  | note | Hold Point - Inprocess Inspection
label | a9e43cdd-8af0-5735-a2c5-15c16b55eb9d |  | note | Records - Dockets/Photos
label | 5add1126-f2fc-5e15-a157-0fc0f2742caf |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 6 - As built information
label | 99a91e13-8947-5a23-b685-0c676da900d3 |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | fa120b3c-bf78-5142-a3bb-ca4abf97d1dd |  | note | FREQUENCY - Every Site
label | ade2b428-fa03-5ffe-a873-8e2f73ed2d8e |  | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
label | 9d1982a3-8173-5079-a968-b305c1b1fe4f |  | note | Hold Point - In Process Inspection
label | 4421d5e1-b755-5c41-9c17-9996a259cca1 |  | note | Records - Asbuilt records
label | bc715876-077a-5c0e-99f4-657ed47aff0d |  | note | Onsite Responsibility - Supervisor and Engineer
checklist-flat |  |  | checklist | ITP - Stormwater Drainage | itp |  |  |  | Yes | Portland Road - ITP - Stormwater Drainage | d4312cd7-8b9f-4547-bc46-b4502ec27505
checkpoint-status |  |  | checkpoint | 1 Permits & Services
label | c2885d90-a291-4ed8-bc40-0501071d0479 |  | note | ACTION (Hold, Monitor, Witness): H
label | 1ff1e0bd-0b4f-444d-a771-504b9a760227 |  | note | Detail: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | eed78585-ac25-498b-a6f5-dc08748992dc |  | note | Frequency: Prior to any construction commencing
label | 752960d6-41c6-4aa3-b575-080b7165061e |  | note | Inspection / Test Method: Document Review
label | f9da23f5-37c7-42df-b9ed-6baca7aa2300 |  | note | Conformance Criteria: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | 504e7e93-5920-4853-aae2-133a91cef0d1 |  | note | Records: Permit attached or permit number noted.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1 Permits & Services
label | 4c10b021-7685-4631-ade9-d77e84d9639c |  | note | ACTION (Hold, Monitor, Witness): H
label | 75d33cfe-0af3-4fdb-9ff5-53e46c9506e4 |  | note | Detail: Locate and mark out all existing services
label | 3e9fb62a-10f7-4918-a27a-d15089cc2a56 |  | note | Frequency: Prior to any construction commencing
label | 4b69bcc5-5df6-45e7-bdb5-229182cdad68 |  | note | Conformance Criteria: B4u dig procedure - follow utility protocols
label | ccf664cb-eb11-40ed-af95-83e7022ea107 |  | note | Records: B4u dig plans & GPR report attached
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 Pre-Construction Sign Offs
label | 7b000c77-4390-46d9-bf60-62082c074aae |  | note | ACTION (Hold, Monitor, Witness): H
label | 74cea165-b7f0-4745-ad08-40112cd659e0 |  | note | Detail: Sub-Contract and Supplier Agreements
label | d4f8959d-9a6b-49ac-918e-e923222ec3e7 |  | note | Frequency: Prior to commencement.
label | f807329f-413f-4cfb-9076-c4a1b256deeb |  | note | Inspection / Test Method: Document Review
label | 65c12716-4de2-4871-83c6-b63f656b3892 |  | note | Conformance Criteria: Sub-Contract and Supplier Agreements to be agreed and signed
label | d364de73-dfa1-4072-bff1-9982da820def |  | note | Records: Subcontract and Supplier Agreements
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 Design
label | 0c26d9a5-ccf6-4755-ac01-ac89144d6879 |  | note | ACTION (Hold, Monitor, Witness): H
label | 4fdbbe36-0aef-4e97-97c2-66e49175ea98 |  | note | Detail: Design is approved and Drawings are of the latest revision.
label | ce200f98-ea1a-447d-9fb8-79e3bf64b512 |  | note | Frequency: Prior to commencement.
label | efb555f9-2217-40b1-adb0-507f56fdc7af |  | note | Inspection / Test Method: Document Review
label | 49c0ad5f-e0a5-4f7f-9c4d-dbc0fb9dcbdf |  | note | Conformance Criteria: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 9859f3c5-9d7f-492f-afc5-fabfa98360c4 |  | note | Records: Drawing Register.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4 Survey Setout
label | 5ef567b7-05c4-4072-b795-b9d3d878a766 |  | note | ACTION (Hold, Monitor, Witness): H
label | 80869c21-4056-47b2-8e78-1bdf1fcaf1d3 |  | note | Detail: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | ab0a0f6f-fdc6-4623-acbd-ce5f75ddb53e |  | note | Frequency: Prior to commencement.
label | 7f5f4023-efac-4fe1-b4c0-cdbc8e14edf5 |  | note | Inspection / Test Method: Survey
label | eee59466-462c-4959-9c14-68dc7d602cee |  | note | Conformance Criteria: As per Stellar Consulting Engineering Drawings: 2789-C3060 and/or Setout files
label | 2b9a34d5-a211-4343-9c54-4d8ded1f2e3c |  | note | Records: Survey Receipt.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5 Pipe and Manhole Material Compliance
label | d00519aa-7b94-4597-999b-bbcd9fbd0ab4 |  | note | ACTION (Hold, Monitor, Witness): H
label | 10646e4c-1685-4e3b-abf2-0741362d9e94 |  | note | Detail: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | 37bd7cc1-9405-4585-998e-7058b1ec2d3b |  | note | Frequency: Prior to commencement.
label | 9c765384-69d7-48cf-bd28-758bfed6b9ea |  | note | Inspection / Test Method: Document Review, Visual Inspection
label | f182d5f3-8bb9-4321-af56-d7def8ac885d |  | note | Conformance Criteria: Pipe shall be Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | 627766d3-7c57-4964-a80a-4934555dab68 |  | note | Records: Manufacturers Data Sheets, Delivery Dockets
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6 Locate Existing Services by Hand Digging / Hydro Vac
label | 64ba33aa-e928-4ff0-b2c7-f439a3552a8d |  | note | ACTION (Hold, Monitor, Witness): H
label | fc6d371b-76fa-4443-86ae-653bb0081dcb |  | note | Detail: Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | 5ada89b3-0b90-4337-a51f-44446b438923 |  | note | Frequency: Prior to commencement.
label | 4824ee37-6b11-40f2-9502-e0146814d21a |  | note | Inspection / Test Method: Potholing / Survey
label | e791beb7-1d74-42fc-8b20-96d379f82104 |  | note | Conformance Criteria: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | e51a9da6-1e59-4c67-a6b5-6b81becddf47 |  | note | Records: As-built Drawings. Doc. Review
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7 Trenching & Excavation
label | e117d45b-9ab3-4a4f-bc55-8b083784024f |  | note | ACTION (Hold, Monitor, Witness): H
label | 61c5ea18-bb74-45f1-8e5d-09f5590fff0e |  | note | Detail: Excavation methodology
label | 3c80169a-af0c-44ba-a992-995b00f30a94 |  | note | Frequency: Daily
label | 303ca3e1-d78c-4025-80e7-5a4e61650d71 |  | note | Inspection / Test Method: Prestart review
label | 5b8633f8-ff71-427a-8768-4843cdfdfd4f |  | note | Conformance Criteria: The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | 996c164e-563c-4cd4-a6e1-0b7df26bd31e |  | note | Records: Prestart RCP
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.1 Trenching & Excavation
label | cb1fb5af-932f-4383-b65f-82ee828c85d8 |  | note | ACTION (Hold, Monitor, Witness): M
label | 61926801-8edc-42e4-a0cb-aa14935a1a44 |  | note | Detail: Trench Profile - Width
label | b3cfb3bd-9894-494f-a7f7-b879f5cca780 |  | note | Frequency: Daily / as trenching takes place. Different depth methodology
label | dd0a26b1-3db1-4517-b9de-74cec24bf6c1 |  | note | Inspection / Test Method: Visual Inspection, Excavation methodology
label | c1b596e8-b0b3-4341-a379-d0eb54ddc253 |  | note | Conformance Criteria: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | 95de32d8-cc8f-4988-9c7c-bcb6421c7658 |  | note | Records: Construction Photos
checkpoint-status |  |  | checkpoint | 7.2 Trenching & Excavation
label | 2db21365-c18a-4ef8-8787-45c98fd363f1 |  | note | ACTION (Hold, Monitor, Witness): W
label | 8c224eab-db92-4249-b1eb-00baf326438b |  | note | Detail: Trench Profile - Depth
label | 971dd20f-991e-4956-838e-5902ea126f9d |  | note | Frequency: Daily / as trenching takes place.
label | 12ac1402-0a15-4389-a503-e7971b664bb7 |  | note | Inspection / Test Method: Visual Inspection, Measurement
label | f3136228-f32a-44ae-9594-ea5b9ef5c59c |  | note | Conformance Criteria: Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | fb7457ce-9488-495f-be08-8dba93cd3080 |  | note | Records: FH Drainage Line Record / Construction Photos
checkpoint-status |  |  | checkpoint | 8 Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | 401f6e88-98ec-4b83-b98a-36776ad8654c |  | note | ACTION (Hold, Monitor, Witness): W
label | e01446e4-c773-45f7-b9b5-d64a3531b011 |  | note | Detail: Placing and compaction of Bedding Material.
label | 144feafe-345a-492f-8a16-e7816e44e193 |  | note | Frequency: Inspected continuously during placing and compaction of Bedding Material.
label | ac6a6834-b2b2-498f-b280-25fabc0f6f98 |  | note | Inspection / Test Method: Visual Inspection
label | 393291df-a25b-4639-ba85-5b1f5309f2b0 |  | note | Conformance Criteria: Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | e5216534-5924-4500-bbba-c5d64dc5e171 |  | note | Records: FH Drainage Line Record / Construction Photos
checkpoint-status |  |  | checkpoint | 9 Pipe Position Tolerance
label | ce19ce58-9d8e-45c9-88c3-159be2684391 |  | note | ACTION (Hold, Monitor, Witness): M
label | 0716ece8-22cb-424b-853f-192e8cf0e3d9 |  | note | Frequency: At any point of pipe
label | 69825e5c-a4bb-4f3f-b023-12fc6add586a |  | note | Conformance Criteria: Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
label | b82ff2fa-18a3-40eb-9e4a-b0510b87d18b |  | note | Records: FH Drainage Line Record, Survey Data.
checkpoint-status |  |  | checkpoint | 10 Trench Backfill - Placing & Compacting
label | 8c35da22-4bc5-45ff-b12c-cd86abd53ef8 |  | note | ACTION (Hold, Monitor, Witness): M
label | 375db5b8-41dc-40d6-aead-1ccd835a4153 |  | note | Detail: Placing and compacting of Trench Backfill Material
label | 5e188385-0073-47c0-bcc0-da68bfd713e9 |  | note | Frequency: Throughout Trench Backfilling operation.
label | 836bd108-2f21-46b3-8ce6-7217bb7a8dc2 |  | note | Inspection / Test Method: Visual Inspection
label | 4809184b-908c-475d-958f-5cdae77c70d3 |  | note | Conformance Criteria: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | 992e92b1-9212-4056-9f50-b0166319a656 |  | note | Records: Construction Photos
checkpoint-status |  |  | checkpoint | 11 As-Built Drawings
label | a5cc2192-9d03-42c9-b6e2-31e7e2b43c91 |  | note | ACTION (Hold, Monitor, Witness): W
label | 744a17ef-64ee-49bd-b5ac-fcfe8cd2e6a2 |  | note | Detail: Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
label | 5d944afd-f522-43b1-a5fd-02c11ff39c46 |  | note | Frequency: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | a026919c-966a-42b6-863b-ec7062c3dc71 |  | note | Inspection / Test Method: Drawings / Visual Inspection
label | fe16844d-a82e-4644-9884-3ad7f0ebd311 |  | note | Conformance Criteria: As Built and GIS Data
label | db8f1524-6235-4117-90da-099fc5cba40c |  | note | Records: Redline As-Built Drawings, scanned as .pdf files.
checkpoint-status |  |  | checkpoint | ITP Completion
text | 9ef11f3f-3931-4817-a0df-2adf354929c9 |  | textbox | QA checked By Quality Manager:
text | 6d394280-5c5b-4c4a-9354-4afef2eb2f77 |  | textbox | Accepted By Engineers Rep:
checklist-flat |  |  | checklist | ITP - Stormwater Drainage | itp |  |  |  | Yes | Graeme Ave - ITP - Stormwater Drainage | d4aa4c14-fcdc-4ab6-852a-267c01f23c45
checkpoint-status |  |  | checkpoint | 1 Permits & Services
label | b7ec7a87-3953-4188-a75c-6c0f2e119de6 |  | note | ACTION (Hold, Monitor, Witness): H
label | ad5f1e43-52c7-44e1-9061-651cf401c3d7 |  | note | Detail: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | 925aa715-6553-493f-81ee-e4ec332149e6 |  | note | Frequency: Prior to any construction commencing
label | c55dad23-de86-46d7-8560-14474d013142 |  | note | Inspection / Test Method: Document Review
label | 6b4610b1-7d70-4d0c-9de2-731cfde4e143 |  | note | Conformance Criteria: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | 93d9f389-dd39-4921-90e6-5d70d5c032cf |  | note | Records: Permit attached or permit number noted.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.1 Permits & Services
label | d8fe82ab-864b-47bf-a9d6-7bc7e1be8c0f |  | note | ACTION (Hold, Monitor, Witness): H
label | 116ae0cc-d56c-4cef-b276-f9e4992a0644 |  | note | Detail: Locate and mark out all existing services
label | be23b614-687f-4316-9b78-2c459195683e |  | note | Frequency: Prior to any construction commencing
label | aa7a04c4-37df-441c-986e-924f2698cd66 |  | note | Conformance Criteria: B4u dig procedure - follow utility protocols
label | 2d7db214-9f55-4989-9de8-2063ad6c83c9 |  | note | Records: B4u dig plans & GPR report attached
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 Pre-Construction Sign Offs
label | 66945c5b-93bb-432e-aba3-a8fa39445b6e |  | note | ACTION (Hold, Monitor, Witness): H
label | 6dd3afae-5fdc-40e0-addd-755a9366d752 |  | note | Detail: Sub-Contract and Supplier Agreements
label | ea47f085-5bd7-4f22-9d79-f9547b74ddb1 |  | note | Frequency: Prior to commencement.
label | a85c61bb-4146-4305-823c-e516dacee613 |  | note | Inspection / Test Method: Document Review
label | 554a05b6-86d0-49e1-928a-882a306830ec |  | note | Conformance Criteria: Sub-Contract and Supplier Agreements to be agreed and signed
label | 160cdefa-2fd6-4dd8-9df7-46df06d1decb |  | note | Records: Subcontract and Supplier Agreements
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 Design
label | d5c72e03-034a-41e1-8ffe-65a463fdd064 |  | note | ACTION (Hold, Monitor, Witness): H
label | dc683c62-0ea5-426c-a727-dc6ce2dd0f46 |  | note | Detail: Design is approved and Drawings are of the latest revision.
label | 6d59f248-9640-405f-860e-5fe7fc441ef0 |  | note | Frequency: Prior to commencement.
label | e841c7ed-b7e6-4ab3-beb6-f064ba2e39bf |  | note | Inspection / Test Method: Document Review
label | e0ccad98-e930-4311-8708-b25827c0595b |  | note | Conformance Criteria: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 0a9aeb7c-3aeb-4c1e-b7d2-afd5d41f5de5 |  | note | Records: Drawing Register.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4 Survey Setout
label | 3a8209d7-3065-4acf-8afe-6b1dc718189f |  | note | ACTION (Hold, Monitor, Witness): H
label | 1e4e0175-50f1-4836-8797-60a914e590f4 |  | note | Detail: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | bab53349-2b0e-41b2-aaf6-d0883defec6b |  | note | Frequency: Prior to commencement.
label | 2ec43d8c-a143-450f-a13a-419d5f0cbe5d |  | note | Inspection / Test Method: Survey
label | 573b55e1-a528-435c-a1da-1590277ea2bf |  | note | Conformance Criteria: As per Blue Barn Consulting Engineering Drawings: 02188-T-400 & Setout files
label | c2758e35-c837-4883-9739-2f927f3deb8f |  | note | Records: Survey Receipt.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5 Pipe and Manhole Material Compliance
label | 5e57cc77-cb04-48ee-80a2-9bb90e087c9f |  | note | ACTION (Hold, Monitor, Witness): H
label | 1b951c79-7e83-40bc-b01b-83230cbbf37a |  | note | Detail: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | b86b784b-ff59-451b-9112-69e7eabe7cfd |  | note | Frequency: Prior to commencement.
label | f38d79be-7970-40b5-9c95-b0f197391be9 |  | note | Inspection / Test Method: Document Review, Visual Inspection
label | 69f2354d-d35a-4979-8d61-50372e9f69be |  | note | Conformance Criteria: Pipe shall be Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | f62d0ff4-d2d3-4fcd-a490-eef89723d455 |  | note | Records: Manufacturers Data Sheets, Delivery Dockets
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6 Locate Existing Services by Hand Digging / Hydro Vac
label | 05c12c8e-2691-4b4c-9000-e7e3714cc7b4 |  | note | ACTION (Hold, Monitor, Witness): H
label | 807cee40-0fd7-41d0-aae6-085b32a67138 |  | note | Detail: Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | 9dff6fef-83e7-4460-9043-c749f20f74a1 |  | note | Frequency: Prior to commencement.
label | ea282c22-4f4c-46ae-81ee-09e0c404a403 |  | note | Inspection / Test Method: Potholing / Survey
label | 4c7f2d95-1866-479a-81dc-b10e334f469f |  | note | Conformance Criteria: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | 3bf0b62e-288a-4dd8-8f0c-c7713fd3f66d |  | note | Records: As-built Drawings. Doc. Review
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.1 Trenching & Excavation
label | 3c4f85f8-accf-4f7e-9d6b-7ddb8584588c |  | note | ACTION (Hold, Monitor, Witness): H
label | 2bdfadb7-a312-4306-a130-c04743827681 |  | note | Detail: Excavation methodology
label | a900b1e3-664c-4667-b447-3b5cc62ad5d9 |  | note | Frequency: Daily
label | a7727bba-dd6f-4567-bf4e-788a60a9919c |  | note | Inspection / Test Method: Prestart review
label | 788f8e63-886d-4172-bf33-f8c12d611eb3 |  | note | Conformance Criteria: The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | 4cd09fb3-8cac-4c16-b52e-1783bed95435 |  | note | Records: Prestart RCP
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.2 Trenching & Excavation
label | 0a231706-9abf-462e-95ca-6495862f9c9c |  | note | ACTION (Hold, Monitor, Witness): M
label | 5ed268ba-f0b2-4d72-94ac-a42dd657a34d |  | note | Detail: Trench Profile - Width
label | 0fa29df7-fcc3-44e0-8cb9-ce31de8f77c2 |  | note | Frequency: Daily / as trenching takes place. Different depth methodology
label | eab6a6d9-c90d-4184-9b76-86b0cdc54980 |  | note | Inspection / Test Method: Visual Inspection, Excavation methodology
label | 8951f026-3f3d-4c16-bed4-d8038a3d78af |  | note | Conformance Criteria: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | 0ad97960-d1ec-419e-be02-b484e8e795c2 |  | note | Records: Construction Photos
checkpoint-status |  |  | checkpoint | 7.3 Trenching & Excavation
label | 639ed2d1-2f4f-460e-b0f6-299f559bbc73 |  | note | ACTION (Hold, Monitor, Witness): W
label | 8ae5f038-715d-48a6-b95d-9e019d66faf8 |  | note | Detail: Trench Profile - Depth
label | a980c10b-e150-46f0-a334-ca3977825d0f |  | note | Frequency: Daily / as trenching takes place.
label | c4aa66fd-f57c-4914-a6fe-23e805bf6820 |  | note | Inspection / Test Method: Visual Inspection, Measurement
label | 3503bbb5-333f-4265-882b-ef6f478e9337 |  | note | Conformance Criteria: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | 6e5168a0-01b1-44a7-8d97-6b96f6c0067a |  | note | Records: FH Drainage Line Record / Construction Photos
checkpoint-status |  |  | checkpoint | 8 Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | 6df61f31-ab55-41c7-af26-25a339ab3737 |  | note | ACTION (Hold, Monitor, Witness): W
label | a04e9e6e-6afd-4cdc-b401-61d60b453389 |  | note | Detail: Placing and compaction of Bedding Material.
label | a8069920-80ac-4df1-a222-60026049c7db |  | note | Frequency: Inspected continuously during placing and compaction of Bedding Material.
label | 42970406-2f5f-4dd1-96bd-5737a0543f0e |  | note | Inspection / Test Method: Visual Inspection
label | 0cdaf7cd-a658-47ad-85d2-c96f232dcc0d |  | note | Conformance Criteria: Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | 2b437bd1-f274-4007-be92-46b83744b29b |  | note | Records: FH Drainage Line Record / Construction Photos
checkpoint-status |  |  | checkpoint | 9 Pipe Position Tolerance
label | d8da1ffe-bc30-4cea-b4c8-55f0b9ed94d6 |  | note | ACTION (Hold, Monitor, Witness): M
label | fc129e97-340c-4a49-a199-fa89e5ce8a9e |  | note | Frequency: At any point of pipe
label | da07c6ae-c50b-41c1-9bae-d574c0354a8b |  | note | Conformance Criteria: Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
label | d018aec5-a833-4a52-8a15-f00389a25291 |  | note | Records: FH Drainage Line Record, Survey Data.
checkpoint-status |  |  | checkpoint | 10 Trench Backfill - Placing & Compacting
label | 56e8b10d-7b1f-44b7-9f1a-1a5bc23373d5 |  | note | ACTION (Hold, Monitor, Witness): M
label | 499bae44-505c-410a-9e0f-dd822013cad5 |  | note | Detail: Placing and compacting of Trench Backfill Material
label | ed4d79e3-8883-4dd6-9629-8b76e9270752 |  | note | Frequency: Throughout Trench Backfilling operation.
label | 965c6718-b497-435f-8ae4-2586d5e145e2 |  | note | Inspection / Test Method: Visual Inspection
label | ffc18123-f027-4e2f-9bfb-7347a7dc948c |  | note | Conformance Criteria: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | 9835e08a-0d74-4103-845c-1bd50870adc3 |  | note | Records: Construction Photos
checkpoint-status |  |  | checkpoint | 11 As-Built Drawings
label | 9a480ad1-8dfc-4395-b769-a5276929ece8 |  | note | ACTION (Hold, Monitor, Witness): W
label | a17a6e2c-bcc5-44aa-9f15-349d67aab1a8 |  | note | Detail: Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
label | 595fb929-4b5a-4a08-b716-d265df471db0 |  | note | Frequency: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | df8ef794-01ee-46e6-ab7a-a44a29f5455d |  | note | Inspection / Test Method: Drawings / Visual Inspection
label | 03a11c25-22d5-4284-bb6e-e6027474ce77 |  | note | Conformance Criteria: As Built and GIS Data
label | 97f9d110-b94c-4672-8f08-59bef070f3b0 |  | note | Records: Redline As-Built Drawings, scanned as .pdf files.
checkpoint-status |  |  | checkpoint | ITP Completion
text | d5030a00-ac11-4f4b-a79c-114988f29b54 |  | textbox | QA checked By Quality Manager:
text | fe763a8f-dc87-412c-9251-64a35a6f6594 |  | textbox | Accepted By Engineers Rep:
checklist-flat |  |  | checklist | ITP - Stormwater Drainage | itp |  |  |  | Yes | White Swan Road - ITP - Stormwater Drainage | d563898b-cc0c-4315-b092-5351ed7ff32b
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | 31475d75-f06a-5fbc-b369-bcafcd8ad77f |  | note | ACTION (Hold, Monitor, Witness): H
label | d5706de0-c40c-5724-83a7-63d777480637 |  | note | Detail: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | 9ac1b4a8-cf72-5798-a0de-b0f08d2de4d5 |  | note | Frequency: Prior to any construction commencing
label | 828b603a-f7a4-5eec-99e2-6f10a3d1c440 |  | note | Inspection / Test Method: Document Review
label | 3344f3dd-8b35-536d-95c2-e02ddc272e96 |  | note | Conformance Criteria: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | 13b1f17f-8211-5dea-8171-e49d5faaed89 |  | note | Records: Permit attached or permit number noted.
text | d39ef3d6-50b9-5fcd-acff-9d9ddf770283 |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD
checkpoint-status |  |  | checkpoint | 1.1 - Permits & Services
label | c925a7b0-456e-5430-b812-92352e94875b |  | note | ACTION (Hold, Monitor, Witness): H
label | 9aeb9fd4-0c2c-5365-93cd-0d820b7b4629 |  | note | Detail: Locate and mark out all existing services
label | 75abd92f-5fae-56f3-88f0-345df82ba1b7 |  | note | Frequency: Prior to any construction commencing
label | 9b733c25-da1f-575c-a3b3-4581f6fc143d |  | note | Conformance Criteria: B4u dig procedure - follow utility protocols
label | 05f6d7b7-448c-5fbf-aaf7-6ead68059bb4 |  | note | Records: B4u dig plans & GPR report attached
text | 8e824f3c-0ebf-55a9-bb90-286c1029f3fd |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | 74f42b61-2bd3-58a4-b7f3-afdeca997b96 |  | note | ACTION (Hold, Monitor, Witness): H
label | 067ecccb-be46-5471-ae33-50902d8e7e05 |  | note | Detail: Sub-Contract and Supplier Agreements
label | 25a1c5cb-3df4-5b1b-9f6f-d38490f96149 |  | note | Frequency: Prior to commencement.
label | aa4c9920-32d5-5c13-aca4-2e10070ebaef |  | note | Inspection / Test Method: Document Review
label | 1f9aa577-996f-5ee4-9a1d-548df7d46332 |  | note | Conformance Criteria: Sub-Contract and Supplier Agreements to be agreed and signed
label | 5cf47b41-47ab-5302-a8fc-0f192bf6dad8 |  | note | Records: Subcontract and Supplier Agreements
text | ebe035a4-9fbe-5014-944f-9f9feae28401 |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD
checkpoint-status |  |  | checkpoint | 3 - Design
label | 2bcb0abf-8fa2-56f9-b4c6-2a3347c45046 |  | note | ACTION (Hold, Monitor, Witness): H
label | 7fa06da5-d2c4-518f-94fa-d4641229db86 |  | note | Detail: Design is approved and Drawings are of the latest revision.
label | 0d3dac44-637d-5141-98b3-06f59d36848c |  | note | Frequency: Prior to commencement.
label | aa4cef3a-ad8a-5550-9cd1-0b4cb3c2db3b |  | note | Inspection / Test Method: Document Review
label | 2343def0-f067-5c5c-a3a6-8a4f5eea8726 |  | note | Conformance Criteria: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | c3a2faa7-b4ca-5047-9da4-3f3a80cf1b37 |  | note | Records: Drawing Register.
text | c08ba414-52ab-5a98-a115-beb7a29e56ec |  | textbox | FH Initials - Site Engineer:
text | d1249327-e888-5850-9db9-48c8649a2c24 |  | textbox | FH Initials - Design Engineer's Rep:
holdpoint |  |  | signoff | HOLD
checkpoint-status |  |  | checkpoint | 4 - Survey Setout
label | 60ff7e38-934d-5eb6-87a6-cfb26d6440eb |  | note | ACTION (Hold, Monitor, Witness): H
label | f927d707-6475-5939-bbc3-5bc478752855 |  | note | Detail: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | 64b11fb1-44d9-5451-a57b-032adf3bf042 |  | note | Frequency: Prior to commencement.
label | 0e19af56-10ac-5016-988d-1cd71866130d |  | note | Inspection / Test Method: Survey
label | 1ae80683-4542-567c-b30f-8550647254cb |  | note | Conformance Criteria: As per Blue Barn Consulting Engineering Drawings: 02188-T-400 & Setout files
label | 2b8063f9-ec97-598d-8fb1-cea10a020096 |  | note | Records: Survey Receipt.
text | 5d399fcd-f879-5857-a997-3152ba189cc2 |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD
checkpoint-status |  |  | checkpoint | 5 - Pipe and Manhole Material Compliance
label | 5195f64e-1034-52d7-ae42-9b8752150b2a |  | note | ACTION (Hold, Monitor, Witness): H
label | b55bd1c9-07a8-50a5-a066-6df6198ff554 |  | note | Detail: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | 24933ea3-9df1-549d-989c-31135a63cf1e |  | note | Frequency: Prior to commencement.
label | 17b615c3-ea64-5f12-8052-717bbe3c802a |  | note | Inspection / Test Method: Document Review, Visual Inspection
label | cfbc177a-21cb-5e56-9b9d-09f7f9ba8777 |  | note | Conformance Criteria: Pipe shall be Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | 481b1646-f7f5-5caa-862b-553fe9239164 |  | note | Records: Manufacturers Data Sheets, Delivery Dockets
text | 64b5c1cc-9eb3-512f-9423-380a91b8de95 |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | 90e322c0-35c2-5266-87cf-8301cdcc8576 |  | note | ACTION (Hold, Monitor, Witness): H
label | 3cfe7cc2-b9cc-5e07-bba6-bd5cb84db475 |  | note | Detail: Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | eeb752b3-eca4-52fb-b052-26aab83165fa |  | note | Frequency: Prior to commencement.
label | 0631ac1d-24a2-5ac8-888d-d595766e2ec7 |  | note | Inspection / Test Method: Potholing / Survey
label | 351fa7d3-95a9-58ca-9e9e-12c072f9a186 |  | note | Conformance Criteria: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | d58c8838-842d-5910-a182-87eeb6936e3a |  | note | Records: As-built Drawings. Doc. Review
text | 07d1a4cf-fe67-5528-925e-6794bcb40275 |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | 14eeb07c-5096-5f83-9d55-4355d44868ea |  | note | ACTION (Hold, Monitor, Witness): H
label | ee89d0d0-4a31-5577-a0e7-cd732f3611ab |  | note | Detail: Excavation methodology
label | c110c911-6a5f-5afa-81ca-064aae206534 |  | note | Frequency: Daily
label | 882fcdc4-6106-5ea3-9e75-a5bea91e6f13 |  | note | Inspection / Test Method: Prestart review
label | 4ede7f38-1b33-5939-9760-80cc4a0e2c67 |  | note | Conformance Criteria: The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | 5ce786de-1246-5c00-a3d6-30fef0fc7106 |  | note | Records: Prestart RCP
text | fdd71b9d-1014-5fbb-a1e3-b30c7f237bdd |  | textbox | FH Initials - Site Engineer:
holdpoint |  |  | signoff | HOLD
checkpoint-status |  |  | checkpoint | 7.1 - Trenching & Excavation
label | 2bf08752-75fc-53f8-86c1-793027b4eda3 |  | note | ACTION (Hold, Monitor, Witness): M
label | 7fc597df-9071-5caa-9507-390c712b44fb |  | note | Detail: Trench Profile - Width
label | deb288c5-328d-5967-9af3-3467d7c99a1a |  | note | Frequency: Daily / as trenching takes place. Different depth methodology
label | 9dffdfd8-282b-59cf-b9cc-68986350fb1d |  | note | Inspection / Test Method: Visual Inspection, Excavation methodology
label | e05c3e89-0f27-52b7-968e-32ad2cac9328 |  | note | Conformance Criteria: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | b8696e72-27ad-500e-a091-ac3f6bb26d2e |  | note | Records: Construction Photos
text | 866d15f0-ab38-5b6a-8ffd-f59af68acd9b |  | textbox | FH Initials - Site Engineer:
checkpoint-status |  |  | checkpoint | 7.2 - Trenching & Excavation
label | 2881868d-770e-52f8-a4c9-c8284603724d |  | note | ACTION (Hold, Monitor, Witness): W
label | 82b76a0d-1aeb-5dc9-8236-035b8aaeddca |  | note | Detail: Trench Profile - Depth
label | 3badf86e-3a49-59b7-b4e6-3f18540a9267 |  | note | Frequency: Daily / as trenching takes place.
label | 481a363f-07dc-5bde-be42-90659028a0af |  | note | Inspection / Test Method: Visual Inspection, Measurement
label | 2e730f69-5af1-5c23-887e-359cb219fe30 |  | note | Conformance Criteria: Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | 087b4da6-406d-5f6b-b008-ef71b6db8112 |  | note | Records: FH Drainage Line Record / Construction Photos
text | 57f47e4e-d3c3-5118-a635-8fbf7cb2605c |  | textbox | FH Initials - Site Engineer:
checkpoint-status |  |  | checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | 3e8fade3-3af5-5566-a6f7-3008d0457884 |  | note | ACTION (Hold, Monitor, Witness): W
label | 866be954-f01f-5c55-90f5-42c584444bd5 |  | note | Detail: Placing and compaction of Bedding Material.
label | 05cda5fb-002d-51a6-8d8c-a394184dfb2c |  | note | Frequency: Inspected continuously during placing and compaction of Bedding Material.
label | 135b9055-6432-555a-871f-967e568da482 |  | note | Inspection / Test Method: Visual Inspection
label | 0e985ce1-b439-5a1a-85f9-043bd23b394d |  | note | Conformance Criteria: Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | 9bfeedad-64ab-5fa9-8041-2439715fcdd9 |  | note | Records: FH Drainage Line Record / Construction Photos
text | 0b473c68-3584-5850-8fbd-5a6eef0363ea |  | textbox | FH Initials - Site Engineer:
checkpoint-status |  |  | checkpoint | 9 - Pipe Position Tolerance
label | d42d7cad-e39d-5c55-a2d1-518388b59aaf |  | note | ACTION (Hold, Monitor, Witness): M
label | 59883d93-8b9a-58b6-b45e-64afb1aa16f6 |  | note | Frequency: At any point of pipe
label | 022de414-f903-5404-96a9-f7871608f68e |  | note | Conformance Criteria: Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
label | 51656817-e55b-5e68-b75b-4ffa2d7f8203 |  | note | Records: FH Drainage Line Record, Survey Data.
text | ac941886-6da3-5ea4-9286-4441452e1f9e |  | textbox | FH Initials - Site Engineer:
checkpoint-status |  |  | checkpoint | 10 - Trench Backfill - Placing & Compacting
label | 366354f2-d94e-592e-925b-77541e094c1b |  | note | ACTION (Hold, Monitor, Witness): M
label | db9580ed-89fa-530e-ac6b-e97c289f95d9 |  | note | Detail: Placing and compacting of Trench Backfill Material
label | fd900b3b-58c4-517b-8d6e-650139d7c14e |  | note | Frequency: Throughout Trench Backfilling operation.
label | 73dd78b3-4fe6-5a8c-b9c5-eded80d9aaca |  | note | Inspection / Test Method: Visual Inspection
label | f873e0a1-03b0-5b0a-9acf-c9c4f0cbe092 |  | note | Conformance Criteria: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | c6bdf922-5a1c-582d-99a1-7bb0568c67bd |  | note | Records: Construction Photos
text | dc18ad46-4508-549d-94b3-d28d7785c6d6 |  | textbox | FH Initials - Site Engineer:
checkpoint-status |  |  | checkpoint | 10 - Trench Backfill - Placing & Compacting
label | a99d6a43-49df-537c-a631-9aa1349d3ca3 |  | note | ACTION (Hold, Monitor, Witness): M
label | 6731abcc-ff73-5f3f-a967-a51ddee1678d |  | note | Detail: Placing and compacting of Trench Backfill Material
label | 9d6737d5-5ed6-50eb-a576-553dffed253a |  | note | Frequency: Throughout Trench Backfilling operation.
label | c5b3880d-72af-565b-98e3-c1f4e547993b |  | note | Inspection / Test Method: Visual Inspection
label | 692f4bc7-1409-5846-a977-5097b1063be2 |  | note | Conformance Criteria: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | 2352a394-9ebe-57d9-94e1-1a2fdb977aa8 |  | note | Records: Construction Photos
text | b9c26345-44d5-5d3b-9fb7-574eef88ae71 |  | textbox | FH Initials - Site Engineer:
text | eeaeb32a-5f04-5d70-837a-51b0c0352dd5 |  | textbox | FH Initials - Design Engineer's Rep:
checkpoint-status |  |  | checkpoint | ITP Completion - QA checked By Quality Manager:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | ITP Completion - Accepted By Design Engineer's Rep:
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | ITP - Stormwater Drainage | itp |  |  |  | Yes | Triangle/Mokora - Stormwater Drainage | ea5b5dee-f826-4d50-b0c1-5bf6de289a4b
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | edf59c30-ffed-5a56-ab74-abfde34b804b |  | note | Inspection / Test Point - Permits & Services
label | 68b6e067-97e9-5c02-accd-9754bc4ef53f |  | note | ACTION - H
label | bd0db75a-05bc-5df3-850f-bfb305935466 |  | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | b36abbd8-90b6-537d-bc7e-d90d19ed40a3 |  | note | Frequency - Prior to any construction commencing
label | 5d5a7563-1c51-56cf-a344-e9864099a4d5 |  | note | Inspection / Test Method - Document Review
label | 05a3b03e-f04b-56fc-8893-6091143881d0 |  | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | 0df16b94-1a6b-582b-b730-dcef6d700412 |  | note | Records - Permit attached or permit number noted.
label | 5dccd84a-2573-551f-8d85-6e6c06929a07 |  | note | FH Initials - Site Engineer
label | 70f81cc2-0930-53be-be96-13507289d246 |  | note | Design Engineer Initials
label | 77af23bf-f560-5a93-98ca-7068fdb0a75e |  | note | Designers comment - Workover from Watercare obtained?
label | a2acd53c-d55d-528f-889b-2ec7a15d966e |  | note | FH Comment - Has been lodged with Mohammed
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1 - Permits & Services
label | aad78433-2a87-5880-91d2-10ce0a4a65e7 |  | note | Inspection / Test Point -
label | b43fb145-b42e-55b5-9f46-fbb1821dcec7 |  | note | ACTION - H
label | 20f0a791-5806-5b0e-97de-99ea616b2b66 |  | note | Detail - Locate and mark out all existing services
label | 6d23a396-7c05-5c1f-aab2-b4708d49ad57 |  | note | Frequency - Prior to any construction commencing
label | 8dd059e5-32e2-5231-aed2-4584e78a14d8 |  | note | Conformance Criteria - B4u dig procedure - follow utility protocols and GPR Report provided by Aerial Smith
label | 6f12e89f-d679-53cf-86bd-c94008e1fd54 |  | note | Records - B4u dig plans & GPR report attached
label | 1155552d-4950-5ef3-af52-61839ee26232 |  | note | FH Initials - Site Engineer
label | ea07e2d8-0bca-55d4-b52d-73953068ca3a |  | note | Design Engineer Initials
label | d899668b-709f-5993-96a7-e515b00f0912 |  | note | Designers comment - by BECA? Are they helping with GPR?
label | 98cbceb9-7a16-53fb-aa9b-e35a9324ae33 |  | note | FH Comment - Has been revised to Aerial Smith
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | 1a11938d-0f80-5c79-9bfd-0ceb9d92b0c7 |  | note | Inspection / Test Point - Pre-Construction Sign Offs
label | 64bbfda6-6261-5837-88c9-47cb991ff622 |  | note | ACTION - H
label | 9cb696e2-8212-52a5-b3f0-2894221b8605 |  | note | Detail - Sub-Contract and Supplier Agreements
label | c4f10637-de0d-534a-ba85-4ac78b9f6ec3 |  | note | Frequency - Prior to commencement.
label | ca972219-5c1f-51fb-a762-7ff951461d87 |  | note | Inspection / Test Method - Document Review
label | c0b2ddf9-7c1f-5f43-b57d-1f92b4d64972 |  | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | 4a660fe5-3b0e-553b-a522-8087885e5bea |  | note | Records - Subcontract and Supplier Agreements
label | cdba1a11-ede6-50bc-b796-3393c30fbc02 |  | note | FH Initials - Site Engineer
label | cb987693-2958-54e2-8cc5-88d8ffeb9a1e |  | note | Design Engineer Initials
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 40ea2643-5b45-5ccb-a35e-d638a88c2593 |  | note | Inspection / Test Point - Design
label | b4e75724-c865-5d6a-8c0b-127321b57353 |  | note | ACTION - H
label | 6850a3aa-6863-53f7-8748-784bf913662b |  | note | Detail - Design is approved and Drawings are of the latest revision.
label | 080986b2-7e31-54c3-800b-2da0c88cd3a6 |  | note | Frequency - Prior to commencement.
label | f2e6c519-28e3-576e-8b06-52323ce7acb3 |  | note | Inspection / Test Method - Document Review
label | b8d4ddc2-def8-55fd-b30b-eb543abedfdd |  | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 2c8ad1dd-020d-5710-81da-a6825eea0d0e |  | note | Records - Drawing Register.
label | 8f85bd20-5f79-5869-8c49-8f7fc78b948c |  | note | FH Initials - Site Engineer
label | 3d731fd4-f752-5e33-b10f-b805ec1cbda5 |  | note | Design Engineer Initials
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Survey set out
label | 9d39bb1a-e55c-57e7-afbd-0f0bd466d1f0 |  | note | Inspection / Test Point - Survey set out
label | 5bd44bac-6411-554c-841e-98857476fbce |  | note | ACTION - H
label | f6000557-9988-5dfb-9092-a2192aebab73 |  | note | Detail - set out Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | a77017d6-5e84-502a-a166-f1edf6f77505 |  | note | Frequency - Prior to commencement.
label | fd180bd9-dcfc-5edc-b8df-006bca6fee58 |  | note | Inspection / Test Method - Survey
label | 9caf16e9-6029-5ad3-9b80-58f8c2c054e3 |  | note | Conformance Criteria - As per eliga Drawings: 2020-AT-04_G060 REV2 & set out files
label | 05c256c9-ecc8-5d46-90f6-2c2930d24759 |  | note | Records - Survey Receipt.
label | 9fed3ae3-c947-5fc1-aa86-cea53937b913 |  | note | FH Initials - Site Engineer
label | 30cdee89-beb0-5e7e-8d41-9f618238b4c1 |  | note | Design Engineer Initials
label | a2f22cfc-4250-580b-bfb3-cb99be9d811c |  | note | Designers comment - Please allow AT representative to review set out locations prior to catchpit installation. IFC drawing number incorrect, it refers to drainage plan prepared for Bucklands Beach RAB project.
label | ba05f955-938e-5a81-bd5f-f57b237c4be1 |  | note | FH Comment - Noted and allowed in Design Engineer initials
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Pipe and Manhole Material Compliance
label | 43993f04-1813-553e-b76f-d9c648ff9f9a |  | note | Inspection / Test Point - Pipe and Manhole Material Compliance
label | 72670a1f-ef78-56cc-9ef8-86691da1027c |  | note | ACTION - H
label | 0d5692ae-2099-5671-b453-a110de8794bc |  | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | ad1cb477-7055-5270-a7ed-6f0d7e17fda0 |  | note | Frequency - Prior to commencement.
label | c77c3a0d-f5e1-501c-9c40-180e18f9b6f8 |  | note | Inspection / Test Method - Document Review, Visual Inspection
label | a143787a-3cd7-57a7-90a5-d8a2033b367b |  | note | Conformance Criteria - Pipe shall be Check for freshly formed pipes and return if required 1) DN300 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | 4b76cf6f-2e4a-5073-a3eb-dd9f18b99dbd |  | note | Records - Manufacturers Data Sheets, Delivery Dockets
label | 21ad2bfa-c3b2-5097-a1ed-58b2e30883a7 |  | note | FH Initials - Site Engineer
label | 0c765f03-6497-502a-ab35-c2c0e799a8ac |  | note | Design Engineer Initials
label | 49e2f641-92b5-50e0-92e3-38fc13cfed8f |  | note | Designers comment - Please specify pipe class. Manholes are AC assets and should comply with AC COP
label | 40c22cd5-74bd-5cb2-b46a-32bef2790d5b |  | note | FH Comment - Class 4 has been specified
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | 59a023e1-e665-535c-9ac8-baca3b10b0d3 |  | note | Inspection / Test Point - Locate Existing Services by Hand Digging / Hydro Vac
label | 39a8ea13-8d2a-55a0-90dd-9b0f9090ef03 |  | note | ACTION - H
label | 264496d8-06f8-5598-9afc-8874c8f2106e |  | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | 85ae82d7-6a1f-5c69-8653-cef8518f854b |  | note | Frequency - Prior to commencement.
label | a78d6a4b-97da-5a89-9ab8-d7f24894ea51 |  | note | Inspection / Test Method - Potholing / Survey
label | ee6548ac-2c8f-5760-aeb3-3df91c7bad73 |  | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager. As-built all services.
label | 95e01594-b9aa-5b36-9327-12659fa24ab7 |  | note | Records - As-built Drawings. Doc. Review
label | 26e2e09f-c031-58b0-a726-7655b1db9cbe |  | note | FH Initials - Site Engineer
label | 990cd89c-a6e6-58d1-8a78-264c9341b514 |  | note | Design Engineer Initials
label | 0ed3baea-29ed-5ad1-a1ba-837ac1d233ed |  | note | Designers comment - Please ensure asst. to engineers reps is on site during hydro so that they can immediately inform designer for design changes minimising delay to the program
label | 855b3fe1-5f9d-5cee-9dc0-8623b8227a89 |  | note | FH Comment - Noted. This can be revised if conflict persists
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | 0f3345dc-d5ce-5d12-9394-0838ec05361a |  | note | Inspection / Test Point - Trenching & Excavation
label | c4920f42-e44a-594c-9a85-d5a186494535 |  | note | ACTION - H
label | 1387ddd3-80e5-5304-8123-ff2efa1ed359 |  | note | Detail - Excavation methodology
label | b9d1b422-cc51-5540-9d3c-dd12e40e3a10 |  | note | Frequency - Daily
label | f33049e6-c9dd-5d05-ac55-053a8d0bfb72 |  | note | Inspection / Test Method - Pre Start review
label | 652daaba-bd0a-5550-bee6-0e71747a1661 |  | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | 6f35d215-a09b-58fe-aa54-83385f11cb2d |  | note | Records - Pre Start RCP
label | 125eecf7-4d62-51be-a905-b93d8f87b91b |  | note | Design Engineer Initials
checkpoint-status |  |  | checkpoint | 7.1 - Trenching & Excavation
label | 49348c0c-6e09-5be2-b19e-bbfd10355ff8 |  | note | Inspection / Test Point -
label | 3a81347a-3e9a-534c-894d-aed51725a8d5 |  | note | ACTION - M
label | 4e1135f0-2747-5316-bec2-b9e2d3e8f389 |  | note | Detail - Trench Profile - Width
label | 555e5376-b3fb-5f1f-8d92-ce7a435cbe38 |  | note | Frequency - Daily / as trenching takes place. Different depth methodology
label | 44a19888-8222-5c07-842c-abba8c3fe1b1 |  | note | Inspection / Test Method - Visual Inspection, Excavation methodology
label | be65350c-7beb-58cf-b3c5-987df1ca5e82 |  | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | 49c2e00c-ba8e-5f38-9635-29a2f77d862b |  | note | Records - Construction Photos
label | c8b93c87-131d-55d3-8642-b073f0d97712 |  | note | FH Initials - Site Engineer
label | ea93d692-77c3-5858-b30b-b9f1705331bb |  | note | Design Engineer Initials
checkpoint-status |  |  | checkpoint | 7.2 - Trenching & Excavation
label | 625f266e-2b59-5842-a48e-067987952dac |  | note | Inspection / Test Point -
label | 127305b0-096e-532e-9a0a-7d5eaedeef9c |  | note | ACTION - W
label | fe6598e8-dabb-5dda-932f-28901a0ae053 |  | note | Detail - Trench Profile - Depth
label | 97a33852-4981-5696-b785-c5c587ae80a4 |  | note | Frequency - Daily / as trenching takes place.
label | da6834f2-995f-5e30-bffa-a3dc2f5ae7e5 |  | note | Inspection / Test Method - Visual Inspection, Measurement
label | 24e7bd94-f926-5c51-a288-2c7aefe9f1eb |  | note | Conformance Criteria - Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | 9e689216-8ab7-5be1-82ed-7968227b4874 |  | note | Records - FH Drainage Line Record / Construction Photos
label | 6267ef00-a897-53c5-894d-9687ccc502d4 |  | note | FH Initials - Site Engineer
label | 1d01185a-0da4-589a-9cc1-a1635cc54904 |  | note | Design Engineer Initials
checkpoint-status |  |  | checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | 85d4dbf3-c9fe-5838-b535-72ef84f229e7 |  | note | Inspection / Test Point - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | 31bf2f8e-8c08-5121-864f-2f7c2f9a0fca |  | note | ACTION - W
label | 8ffd74e0-37b9-546a-8325-6770c7613a10 |  | note | Detail - Placing and compaction of Bedding Material.
label | 08e44cfc-4b0b-56e5-9547-61202d588370 |  | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
label | 9b09a3b1-8b67-503f-bdff-361d2f1f3536 |  | note | Inspection / Test Method - Visual Inspection
label | 6edf25d8-98ca-51b0-90cb-25ff14eac341 |  | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | f0d00c88-6abe-5989-9be8-833bfa0c15a5 |  | note | Records - FH Drainage Line Record / Construction Photos
label | d080559c-43c6-5599-8d75-9411811b994b |  | note | FH Initials - Site Engineer
label | 343cea56-5e93-5c36-bafd-f41c65077b34 |  | note | Design Engineer Initials
checkpoint-status |  |  | checkpoint | 9 - Pipe Position Tolerance
label | 0d2530e6-f896-5e3b-a877-76958a60017c |  | note | ACTION - M
label | 11d5e9ae-4c9f-5035-8efb-46ea3ed330e3 |  | note | Frequency - At any point of pipe
label | bd3089d1-de16-5890-9c49-729b156e6afc |  | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±5 mm from the specified design.Any tolerance required more than +/- 10mm will require design engineers approval.
label | 52e5767a-e4d2-5527-ba7d-17d802902d06 |  | note | Records - FH Drainage Line Record, Survey Data.
label | b149089a-c1fa-561e-8366-6a64c79d8417 |  | note | FH Initials - Site Engineer
label | eab6e415-163b-543c-b095-9fadc0f8891c |  | note | Designers comment - Min length of proposed SW pipe is less 2.0m, +/-30mm tolerance for short length is excessive. Can we you please include any tolerance required more than +/- 10mm will require design engineers approval.
label | ed5f7fa6-de87-5073-bbd3-86583bb04b74 |  | note | FH Comment - Noted. Has been added in conformance criteria
checkpoint-status |  |  | checkpoint | 10 - Trench Backfill - Placing & Compacting
label | ef9569b3-11f3-5ae5-a9d9-d6037a7bb18d |  | note | Inspection / Test Point - Trench Backfill - Placing & Compacting
label | 63d87dd5-04b1-55d3-b867-1c763d6bc938 |  | note | ACTION - M
label | e1ee7a57-f064-5a59-9549-c434a2db4d09 |  | note | Detail - Placing and compacting of Trench Backfill Material
label | da92b851-feef-575d-80ef-0d4e27c40fff |  | note | Frequency - Throughout Trench Backfilling operation.
label | 85dcd1aa-ea9e-52d5-804f-c3564fad5c3f |  | note | Inspection / Test Method - Visual Inspection
label | d0a3f584-2780-5609-92ce-19da5f69eeeb |  | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm MR9 AP40 for Sub Base/basecourse. AP20 for bedding
label | ce169e35-7d01-5866-bb19-a755fa4dcd0d |  | note | Records - Construction Photos
label | b7226d78-26c4-5f96-9476-fdc838962beb |  | note | FH Initials - Site Engineer
label | 10546664-f4f7-54c5-88d1-cdafdd66851e |  | note | Design Engineer Initials
label | 1f1da6d8-0a21-52ec-9038-11b8b31dab59 |  | note | Designers comment - Provide compacted backfill specs to check against. Compaction? Backfill to match existing or use AP20 .
label | 0afae7eb-f613-5eb4-a181-6c8fd9b097b9 |  | note | FH Comment - Noted. Has been added in conformance criteria
checkpoint-status |  |  | checkpoint | 13 - Subsoil Material Compliance
label | c767991c-a034-53ea-a143-0a4fa242f5ee |  | note | Inspection / Test Point - Subsoil Material Compliance
label | 8ebc3520-4d17-51e1-a9f7-9e93a404ac13 |  | note | ACTION - H
label | f1d7dd71-9bc7-5b20-b159-947b03083915 |  | note | Detail - Ensure Subsoil Drainage pipe complies with TDM RD010
label | 7cdaf9dc-a46b-5ca6-b9ff-11a3a43b4a35 |  | note | Frequency - Upon delivery to site
label | 80697313-f85e-5abd-a8c7-1381f384d8de |  | note | Inspection / Test Method - Ensure delivery docket matches materials delivered
label | 484c37b9-28bc-5cfa-803c-d2c93b13487a |  | note | Conformance Criteria - 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock
label | d36d68a3-e23a-5bb5-af85-7579d0088a17 |  | note | Records - Delivery docket
label | e1de9540-229e-56c3-9c5c-b3ee723cdc74 |  | note | FH Initials - Site Engineer
label | 180210a2-0272-58b0-8f3b-68a2cbc9cced |  | note | Design Engineer Initials
label | 19c22924-bbe9-5901-a527-87d93a08107a |  | note | Designers comment - Change to ATCOP reference to TDM RD010. backfill material AP20? Specify spes for AP20.
label | 97c2938d-fd9f-54a2-b2f1-86a03d3fba4e |  | note | FH Comment - Note that we have not allowed for fully wrapped subsoil trench
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.1 - Subsoil Material Compliance
label | 7b3424a9-c168-59b4-b994-a94d32e0b040 |  | note | Inspection / Test Point -
label | 7da366e1-1158-511a-8cca-3c3c4d74cad2 |  | note | ACTION - H
label | a68ed5c1-0935-59d7-8d49-ed7502cbc311 |  | note | Detail - Ensure Material for Bedding, Side support and backfill F6 filter sand drainage aggregate
label | 7474637e-1089-5774-acae-683ea61dd3bd |  | note | Frequency -
label | 94baea35-948f-5fd3-ad63-241bed7f0f29 |  | note | Inspection / Test Method - Visual Inspection
label | ca548565-a7a4-5d5d-be2e-14ff08699408 |  | note | Conformance Criteria - Ensure clean drainage aggregate - F2 Sand or scoria
label | 0d18ae92-90d4-5906-96dc-c2b2f58e2170 |  | note | Records - Delivery docket
label | 22c9a005-8d43-581c-8700-1c1d926330da |  | note | FH Initials - Site Engineer
label | f062dcdd-2f85-5840-a999-5eb282309ef7 |  | note | Design Engineer Initials
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Trenching
label | 24e1783e-33c3-579c-8506-6ad7b7884d65 |  | note | Inspection / Test Point - Trenching
label | d7191ab9-c608-537f-a59e-906386476d29 |  | note | ACTION - H
label | 4937c1ac-b3c3-5dc8-839c-5a2b8cea467a |  | note | Detail - Inspect trench profile and ensure it is 0.300m wide and 1.000m below Edge of Seal level.
label | 589f8d1a-5e7f-5460-aebb-789cebd66721 |  | note | Frequency - 10m intervals
label | 4faa461b-766d-5d37-8532-1f1c72c2246b |  | note | Inspection / Test Method - Visual inspection and measurement
label | 620650ee-66ff-526e-a428-28d5298af2fd |  | note | Conformance Criteria - Record levels of base of trench on dip sheet. If the same trench is used to combine utility ducts than photos of warning tape to be recorded
label | 3dfd6e9b-c5c5-5224-8579-8894f12bc1dd |  | note | Records - Photo / subsoil log
label | a637f1ba-89ce-5034-a9f5-c81c0bdbae8e |  | note | FH Initials - Site Engineer
label | b63d9363-8d65-5393-b0a3-7b36f411167b |  | note | Design Engineer Initials
label | c1f3b685-124b-5eb2-a1d8-b748d4333cec |  | note | Designers comment - Please capture evidence of installation of electrical warning tape and magslab where electrical cable is installed
label | 702eeacc-b9df-5c15-a36b-dda94ae79566 |  | note | FH Comment - Noted. Has been added in conformance criteria
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14.1 - Trenching
label | 0947e2df-8fcf-5fa0-b25f-6da58651f156 |  | note | Inspection / Test Point -
label | 8e469b71-a8f0-5d9f-af6d-08489edd60bc |  | note | ACTION - H
label | dce805b6-9a27-5450-b547-dc7a3c4570cc |  | note | Detail - Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
label | 618d304b-d7a8-5d15-bedd-a98e1b489bc5 |  | note | Frequency - 10m intervals
label | 970d9a62-8273-5123-b30c-e94e2f4bb3c4 |  | note | Inspection / Test Method- Visual inspection and measurement
label | 7c798be8-06d2-5803-97d9-db9d2e2435d9 |  | note | Conformance Criteria - Ensure trench line and levels match the design drawings
label | fc6b851e-0f20-5181-b4b0-a7e5e4834d6d |  | note | Records - Photo / subsoil log
label | 43a5fd02-34dc-5429-b63f-97a4f1ecf795 |  | note | FH Initials - Site Engineer
label | 136bdc8f-64a6-5cb1-b27a-59971a5cb43c |  | note | Design Engineer Initials
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 15 - Bedding, pipe installation and Backfill.
label | b99818b9-ee6e-5858-9a29-1886083011f4 |  | note | Inspection / Test Point - Bedding, pipe installation and Backfill.
label | 348c1368-b7ee-50e2-ac4e-2612a38da08c |  | note | ACTION - W
label | 180745af-aecb-5d1e-8024-e7e65c56e368 |  | note | Detail - Ensure 100mm thick F2 or scoria Drainage aggregate bedding is placed in base of trench.
label | 6cca7344-2068-5513-b1f4-8a1809ba9c06 |  | note | Frequency - 10m intervals
label | 88eca7ed-609f-5824-97f1-698e0fbdaf37 |  | note | Inspection / Test Method - Visual Inspection
label | 5b0a323b-e727-5c55-9cd8-93c0d48a3aee |  | note | Conformance Criteria - Record levels of top of bedding on dip sheet
label | 22e1f031-7d2b-5484-b3e0-ae2fedfa7a83 |  | note | Records - Photo / subsoil log
label | 3098f757-9cf7-5a02-b660-8b9db599b7ae |  | note | FH Initials - Site Engineer
label | 357ad296-3ea4-540c-ae21-f92965f35c0e |  | note | Design Engineer Initials
checkpoint-status |  |  | checkpoint | 15.1 - Bedding, pipe installation and Backfill.
label | 797cc6b9-97d4-5ec6-a7b8-fa11b86943af |  | note | Inspection / Test Point -
label | f654bbd3-7ca9-52d3-8f52-515bb9e1dedc |  | note | ACTION - W
label | fdc76545-69fe-5d76-9f46-3060d9268d57 |  | note | Detail - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | 4328bc8c-fe56-50f8-8b5d-2cd2cb9e3f81 |  | note | Frequency - 10m intervals
label | 7069c34f-081b-54c1-921c-248ddb89bcca |  | note | Inspection / Test Method - Visual Inspection
label | 7b5bdbbb-a6ab-554e-a707-bfaf61a0896a |  | note | Conformance Criteria - Consistency with Subsoil Details
label | ca47566c-d7e5-5c35-be82-6f8b0cb4a6b9 |  | note | Records - Photos
label | a7ca7cfe-1c68-5b5e-83d9-c5b9e2a5bacd |  | note | FH Initials - Site Engineer
label | be986429-d6a4-5a86-8df8-b994db7c1c12 |  | note | Design Engineer Initials
checkpoint-status |  |  | checkpoint | 15.2 - Bedding, pipe installation and Backfill.
label | 3d4d7386-af47-504f-960d-c5228747a8b9 |  | note | Inspection / Test Point -
label | e4bf838a-5668-54b3-9bff-a8c15a65bdb0 |  | note | ACTION - W
label | 46599443-cd30-52da-ab18-f345704422ad |  | note | Detail - Backfill by tipping AP20 as bedding & AP 40as pavement structure into the trench
label | 3cb5c006-e0ed-530a-b315-29c44fa54218 |  | note | Frequency - -
label | 9d8a9558-ba40-5f77-93fb-5ebbfabf208e |  | note | Inspection / Test Method - Visual Inspection
label | a108f067-427b-529f-bc3e-08e6a7ee9cf1 |  | note | Conformance Criteria - Ensure good coverage
label | c2261608-1a9f-5847-953a-259cf59eb4da |  | note | Records - Photos
label | 3c40fa05-28c0-5c1a-93e0-69d0007cc5d6 |  | note | FH Initials - Site Engineer
label | 68a7eb99-3091-515d-a356-1a380eb0b29b |  | note | Design Engineer Initials
label | fc91f8b9-00ae-59d9-b60f-ec7ef523bd52 |  | note | Designers comment - TDM specifies AP20 as backfill material.
label | e34f31f2-983d-5f32-896d-ab147299c965 |  | note | FH Comment - Sub Base & basecourse AP 40 and bedding AP 20
checkpoint-status |  |  | checkpoint | 16 - Catchpit Connection
label | 31356826-59b9-5674-8a1f-5a78169543f6 |  | note | Inspection / Test Point - Catchpit Connection
label | a1b0d190-4ccb-58c1-b8c2-22ad1dfc627c |  | note | ACTION - W
label | 9708f1d5-c29d-544a-867b-f0c60e6817af |  | note | Detail - Ensure minimum entry point 150mm above soffit of outlet stormwater pipe
label | 092d7a17-08ba-569c-871c-388f5ab8df3c |  | note | Frequency - As required
label | 6044f460-a357-52a7-820a-479dde4a072f |  | note | Inspection / Test Method - Visual Inspection
label | 5a8fa0cf-4256-5977-a0cc-aa68b2cc06d9 |  | note | Conformance Criteria - Consistency with Subsoil Details
label | a6f9cb1d-6dca-533d-8767-3fa562d913d3 |  | note | Records - Photo / FHIMS-CS-4001
label | ef936003-be22-5151-a12c-e2a0cb4025da |  | note | FH Initials - Site Engineer
label | 05b3c399-47c0-509a-bef3-ca393ca7f74d |  | note | Design Engineer Initials
checkpoint-status |  |  | checkpoint | 16.1 - Catchpit Connection
label | b43dfea0-3157-5bf5-8a54-a97597b0ec4b |  | note | Inspection / Test Point - Catchpit Connection
label | 2c73a5a4-85d5-51cf-86e6-7835f425a83a |  | note | ACTION - W
label | cba62b0f-6d52-5315-921b-58018c0cd626 |  | note | Detail - Perforate Catchpit and epoxy grout pipe from inside to completely seal connection.
label | c4a0e0ed-7e12-5c8b-ab79-9dc569aef320 |  | note | Frequency - As required
label | 7da0f3f1-150a-5cf2-ac10-1ed1d853ce66 |  | note | Inspection / Test Method - Visual Inspection
label | 7f68c318-a592-5bf6-bbf0-5016ef6aee2c |  | note | Conformance Criteria - Consistency with Subsoil Details
label | b97c4590-5f05-51ee-9f1b-6342bf654619 |  | note | Records - Photos
label | d07a6b7b-4adb-5b0f-bc4c-1af847525b7c |  | note | FH Initials - Site Engineer
label | a13b47f7-e613-532d-bd22-1b27074ce9b9 |  | note | Design Engineer Initials
checkpoint-status |  |  | checkpoint | 17 - As-Built Drawings
label | a13a8670-4e69-5375-8812-d1a34c620edc |  | note | Inspection / Test Point - As-Built Drawings
label | c7d9402a-62e5-550b-97a3-ae862be8c368 |  | note | ACTION - W
label | fc3f854f-f68a-5512-800c-2aa3684f7bf0 |  | note | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT /Eliga drawings
label | 8bfffb33-a4dc-5697-a04e-ae5d99dd391c |  | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | c8f81027-f9bf-545f-8e19-8449d76aca19 |  | note | Inspection / Test Method - Drawings / Visual Inspection
label | 24383d0f-9986-5694-ac11-04203545a499 |  | note | Conformance Criteria - As Built and GIS Data
label | 76056740-4870-5174-966c-f4ce52e00fd5 |  | note | Records - Redline As-Built Drawings, scanned as .pdf files.
label | 6852d022-2284-56e5-b1a5-f20b5f3e53cf |  | note | FH Initials - Site Engineer
label | 4597242d-62be-56ee-ae23-6ad0ddce3bab |  | note | Design Engineer Initials
checklist-flat |  |  | checklist | ITP - Rockfield Road - Enabling Works - Stormwater Drainage | itp |  |  |  | Yes | ITP - Rockfield Road - Enabling Works - Stormwater Drainage | eb4aed92-0783-4eaa-bafd-282432715c0f
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 00ab1127-64db-53f1-b06a-8386d2091f76 |  | note | Inspection / Test Point - Permits
label | 183207a2-c4a2-5b25-ba31-e077240507ae |  | note | H
label | 45d42828-a59e-56c4-bd1c-6039f7ab7f84 |  | note | Detail - Obtain Permits
label | 4d0e3c67-a4b5-5bab-97c0-4e51d121709d |  | note | Frequency - As required
label | 4f8dd11f-9a7e-51d7-bf8e-7f9183854783 |  | note | Inspection / Test Method - Document Review
label | e54ae6b7-2ad4-5420-81e2-abd82bf75d53 |  | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | 6f5c365c-704b-59b8-b5ce-c8d5a774a56b |  | note | Records - Permit attached or permit number noted
label | 90fff355-5441-5cb6-be89-b25c2ea169e8 |  | note | FH Initials - Site Engineer
label | 3b4af23a-f2db-537c-baea-dfe6f79e478f |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | e2917f26-2837-53a7-8c00-622204662221 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 1 - Permits
label | d9eff987-140c-5f9b-ab2a-fb5a4af01f92 |  | note | Inspection / Test Point - H
label | a7182667-5948-5d12-9dfb-e14f8c826df3 |  | note | Locate and mark out all existing services
label | cd6c20fb-1d52-51c1-85ed-49bd21cbeaf0 |  | note | Detail - Prior to any construction commencing
label | 2e50eda7-7f52-5979-9bb7-b3146ba52154 |  | note | Frequency -
label | a3976806-c072-5351-849c-34a05c140275 |  | note | Inspection / Test Method - B4u dig procedure - follow utility protocols
label | c358754a-530b-582f-80d0-aadb18266120 |  | note | Conformance Criteria - B4u dig plans & GPR report attached
label | ac5871c8-41fd-5217-88dc-615ea0d46952 |  | note | Records - Site Engineer
label | 10306186-907b-576c-9cda-6c516b2e4d99 |  | note | FH Initials -
label | 1f796ce9-2d26-58da-a964-fe082d2e19ae |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 60c55d7f-956c-5047-a0a7-610bc8b35c77 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | 2cfd2342-9352-5445-93d6-63b02827b67a |  | note | Inspection / Test Point - Pre-Construction Sign Offs
label | f45c78b1-8457-5854-b2c4-bfda7bea61e5 |  | note | H
label | f590fd14-26b6-593a-acf9-6ef0906dfac0 |  | note | Detail - Sub-Contract and Supplier Agreements
label | 380f2010-6243-5f3a-b712-8c4e2a7af689 |  | note | Frequency - Prior to commencement.
label | 4da38d81-c6a9-5d39-9843-44db4841bef8 |  | note | Inspection / Test Method - Document Review
label | 5a720d2a-4756-5f28-aebe-cd3e07830813 |  | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | 4dcbfc85-d9ff-5cab-83ab-5ba7c252debe |  | note | Records - Subcontract and Supplier Agreements
label | 79b8a1c4-812f-5475-a39f-397bf841747d |  | note | FH Initials - Site Engineer
label | 6a312967-7841-584e-89a6-f21deafd659e |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 096219ae-df0b-5948-a7a7-dfbdb717eb97 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | ef055e25-107f-5eb7-9df9-520d29fa57b1 |  | note | Inspection / Test Point - Design
label | 776d2937-a836-5bd2-89b1-f525d3dc55f4 |  | note | H
label | b22adb27-a549-5052-bb15-045c00f26f40 |  | note | Detail - Design is approved and Drawings are of the latest revision.
label | 54d7e38e-d7da-5207-8431-94b6138f2e16 |  | note | Frequency - Prior to commencement.
label | bc54c608-5e06-5b31-adfb-67bc7ca89b0b |  | note | Inspection / Test Method - Document Review
label | 16a785b5-e32f-59ca-9c59-d517297b0c6d |  | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | a08330fb-d43a-5547-97b8-04132170623b |  | note | Records - Drawing Register.
label | 22641290-3009-568d-9baa-ecd45ae7f3ff |  | note | FH Initials - Site Engineer
label | dbe137ca-027c-5f3c-bf1e-a60babd58240 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Engineers Rep.
text | 705ec862-c821-5f74-a539-7a1dcf79f1dc |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Survey Setout
label | 5a77ffe0-31e1-579a-9094-fb239edda13b |  | note | Inspection / Test Point - Survey Setout
label | 20992feb-ed35-5d55-8c59-f42ccaede359 |  | note | H
label | eb7333cf-5809-594a-a8cd-ce568131b5da |  | note | Detail - Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | 7cbd2ce0-662e-5cee-bfac-f5d95b743ace |  | note | Frequency - Prior to commencement.
label | 515fb95d-a31c-545e-b9de-5208dce65968 |  | note | Inspection / Test Method - Survey
label | 9a478b80-4991-5749-9957-42e1d92f1d05 |  | note | Conformance Criteria - As per Stellar Consulting Engineering Drawings: 2789-C6060 & Setout files
label | 325c93a9-fd23-529f-a469-3b691a11cb67 |  | note | Records - Survey Receipt.
label | 8b3c9c1b-c16c-5877-ab0e-bbb1aa543a69 |  | note | FH Initials - Site Engineer
label | a9954120-aad9-5ab9-8dd8-37f1b94d5290 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | b6e5c9da-6954-58d4-92db-314f997bb3a2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Pipe and Manhole Material Compliance
label | bbc362a8-d0b6-5304-aac6-cdf923dd22fc |  | note | Inspection / Test Point - Pipe and Manhole Material Compliance
label | ba2244a6-f42b-5aa4-a9d1-121913f91d64 |  | note | H
label | 6aa1c130-a0dd-5879-9f17-cc880669f8d5 |  | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | 9b793455-7ff3-5cc8-9725-fe042711f90c |  | note | Frequency - Prior to commencement.
label | 24570b8d-2a52-5d16-be39-57410f4ab3a7 |  | note | Inspection / Test Method - Document Review, Visual Inspection
label | fd759d90-01df-55fe-bb0d-de23852c700d |  | note | Conformance Criteria - Pipe shall be Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | 4ef40135-8168-55f1-a07f-e5cb78b85bd1 |  | note | Records - Manufacturers Data Sheets, Delivery Dockets
label | 1e219da9-0e10-5352-88e9-06f4bf19afa4 |  | note | FH Initials - Site Engineer
label | b5087c28-09d4-58d4-b1b6-0514974e3f9f |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | b1bb2e5b-8c71-5cdf-bda2-3ea13f35fa95 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | ea978183-d339-52bf-8c91-fb379112a06d |  | note | Inspection / Test Point - Locate Existing Services by Hand Digging / Hydro Vac
label | ac0c34b9-d701-576a-9e05-c55743a8faec |  | note | H
label | e5dad906-e39f-5eb7-ac56-66d4e27f2b7c |  | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | 1d711993-f8cf-5bff-8009-e10b7059bdae |  | note | Frequency - Prior to commencement.
label | b3e6e46a-5d8c-5d26-964d-136bd6369b71 |  | note | Inspection / Test Method - Potholing / Survey
label | 02951b00-10a9-5ed6-9cf4-3dfa9b00127e |  | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | 12c2eed7-7b76-529a-a1eb-cd409f65eaff |  | note | Records - As-built Drawings. Doc. Review
label | 16eec84f-4812-544f-b363-94d7c879d9c6 |  | note | FH Initials - Site Engineer
label | 5f6bad4b-811e-5958-900e-6f64c4dd944e |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 45bea89f-ba16-5304-8af9-c722de8d3183 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | d8dc85b3-3c74-57e9-ac3c-f9e77123dcce |  | note | Inspection / Test Point - Trenching & Excavation
label | 3a88def5-a13a-5084-b783-4b30509e387f |  | note | H
label | fc1b353b-e1af-57b8-8a48-df842474dfee |  | note | Detail - Excavation methodology
label | b2cc4087-1c4e-5f39-bd59-438a1abb31d5 |  | note | Frequency - Daily
label | 61eaecb0-6f8a-5cf3-8e7f-60b97dd5db51 |  | note | Inspection / Test Method - Prestart review
label | 2374ff9e-74e0-55d0-9a00-e1998b65d1fd |  | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | 8f03f228-525b-5411-8f50-830570960dc7 |  | note | Records - Prestart RCP
label | 1eb07f1e-0d25-5b1b-b0f5-e83d236b9af2 |  | note | FH Initials - Site Engineer
label | cf093af4-5d81-5f54-aa1b-0612d4216e97 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 036cd03e-91df-57b1-8143-dcfde3b77e19 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | 48a1871c-12cd-57a2-a279-f34b8f4c4d24 |  | note | Inspection / Test Point - Trenching & Excavation
label | 7dd5df56-b64d-5291-9d82-1892a36f942a |  | note | M
label | eb95f2d7-eba3-5c05-8a66-2b9b2933ef36 |  | note | Detail - Trench Profile - Width
label | 3f260c86-cf98-5186-9a75-e9a1fc213813 |  | note | Frequency - Daily / as trenching takes place. Different depth methodology
label | bcb4453d-d9e6-526c-9842-fd99bd178ff8 |  | note | Inspection / Test Method - Visual Inspection, Excavation methodology
label | 8a380b5b-fa6d-507c-8895-70a8b2c58320 |  | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | 2918e044-6d34-552b-ab09-d087510c6280 |  | note | Records - Construction Photos
label | 526fab03-d78c-59b9-9d90-de38465eca52 |  | note | FH Initials - Site Engineer
label | d6cc68e9-d625-5a48-9c10-018bf465e685 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 8bb14a8b-26c8-5d58-801d-afcbcc9691c8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | 8c16cbc4-e2e1-5fae-b309-74d805cde984 |  | note | Inspection / Test Point - Trenching & Excavation
label | 834531f7-9502-5099-b474-ec19c6085652 |  | note | W
label | f473227f-ce6a-5615-a6b5-10cbb75b9e4f |  | note | Detail - Trench Profile - Depth
label | 5e5d12a0-da15-58b7-8a69-f6294ca43149 |  | note | Frequency - Daily / as trenching takes place.
label | b3405ea5-dd2b-556a-ae2b-d7e0941292ba |  | note | Inspection / Test Method - Visual Inspection, Measurement
label | b2a899f0-9d21-59f1-80a3-ba61bf3e2d14 |  | note | Conformance Criteria - Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | 206eb8b0-21b5-527d-8fb5-15d0111a5a62 |  | note | Records - FH Drainage Line Record / Construction Photos
label | 23355709-ead6-587d-b2ac-e311b9900da8 |  | note | FH Initials - Site Engineer
label | e0eb54b5-a2d6-54f9-ac28-22f3e6a3dccc |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | abeb11c7-aacf-5bf8-9d8a-e3dd0a9084dc |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | ff7153c1-3698-5401-a4d6-a72e8ebaff59 |  | note | Inspection / Test Point - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | 8ef0ca36-170f-500b-a1e8-4c00cc6dc213 |  | note | W
label | 382b3550-f106-516a-8ac8-5c4245380483 |  | note | Detail - Placing and compaction of Bedding Material.
label | e2d1cb8a-eaff-5bc6-b738-0add764cfe5f |  | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
label | 221d2a77-4e6d-53fa-8085-59affa61e555 |  | note | Inspection / Test Method - Visual Inspection
label | 3a9b15ae-1bb7-52fd-af11-c6172d74078c |  | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | f44c34df-0c47-53b2-92af-1c10db23ca06 |  | note | Records - FH Drainage Line Record / Construction Photos
label | 0e76d346-3e71-5b61-93b6-15872693d91a |  | note | FH Initials - Site Engineer
label | 0718b3e2-3ff8-5218-ade1-192cc4a97534 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | a2021d28-6633-5017-a05f-bf020bbcd2ce |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9 - Pipe Position Tolerance
label | 7bb8f8e1-320a-5a99-ae4e-46fb9a630498 |  | note | Inspection / Test Point - Pipe Position Tolerance
label | a381ebf8-0a09-5cd6-8222-4328d5943171 |  | note | M
label | 148760e5-c377-5973-8c35-155b247410d7 |  | note | Frequency - At any point of pipe
label | 55f15f5f-035b-532d-881c-a11a78d19f21 |  | note | Inspection / Test Method -
label | e4042748-7a8a-5e23-ba7d-8355036837f2 |  | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
label | 7645d288-060c-5f08-a122-281148f352af |  | note | Records - FH Drainage Line Record, Survey Data.
label | bf7c8cb1-2dd7-5ac6-b06d-9ef83265c6e6 |  | note | FH Initials - Site Engineer
label | 6d98a35f-4695-5bd7-98db-313774a4d35e |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 8c9a4c37-efc1-5a4c-93b1-390badef206c |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Trench Backfill - Placing & Compacting
label | 513b3ef0-aa39-5338-be2e-cd925b0111f9 |  | note | Inspection / Test Point - Trench Backfill - Placing & Compacting
label | 5c804624-1367-5ab1-acb2-63b858dc4ada |  | note | M
label | 4c9cd90f-e6d6-5111-84d3-e329d940e3a6 |  | note | Detail - Placing and compacting of Trench Backfill Material
label | 7dc12623-7022-59e0-af08-837e83951a78 |  | note | Frequency - Throughout Trench Backfilling operation.
label | 1fc567f5-1209-5a51-9c66-74adf845b92d |  | note | Inspection / Test Method - Visual Inspection
label | f9ef99c6-b55d-5089-8fe5-d594551aa8ee |  | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | 2258e5bf-4d0b-56dd-a661-2ec250346aaf |  | note | Records - Construction Photos
label | b942e9c1-75ab-59e2-bb5a-09fa7ccd237f |  | note | FH Initials - Site Engineer
label | 07f2b529-770b-589e-b88d-f7639b0cd6bb |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 7b114328-0ef3-5fbb-b345-f5d46cfc8423 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 11 - As-Built Drawings
label | f4efdd73-4070-5ea3-8a4c-693869ac793e |  | note | Inspection / Test Point - As-Built Drawings
label | 2cf6a1d0-0605-5276-9552-434f3543a960 |  | note | W
label | 362f7d48-d471-56e2-986c-12bbaf186392 |  | note | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
label | 386db64e-80ad-5c69-a562-20f1b1133c4f |  | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | c8193fca-db22-516a-9b13-1008517003f7 |  | note | Inspection / Test Method - Drawings / Visual Inspection
label | 93ea2e6c-0da2-59b0-9638-666fa747c9c6 |  | note | Conformance Criteria - As Built and GIS Data
label | 300c80a0-77ae-5dcc-bcda-ec6324397d00 |  | note | Records - Redline As-Built Drawings, scanned as .pdf files.
label | 74dbf3d8-5415-5495-8f36-57dae8e24fb3 |  | note | FH Initials - Site Engineer
label | 0d65d4f4-7aa6-5815-bace-0d824c2dfeb8 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Engineers Rep.
text | f377021a-5d3f-5e28-af0e-493ff298f606 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
text | 5b0dd77f-1059-515a-b705-725ea3d463a1 |  | textbox | QA checked By Quality Manager:
text | 02062df2-46f6-5328-84fd-3bddf0081edd |  | textbox | Accepted By Engineers Rep:
checklist-flat |  |  | checklist | ITP - Rockfield Road - Raised Pedestrian Crossing | itp |  |  |  | Yes | ITP - Rockfield Road - Raised Pedestrian Crossing | f01d1022-1eb8-4698-8faa-f19ddd078051
checkpoint-status |  |  | checkpoint | 1 - Permits
label | 05cbec80-0e79-5278-a9b8-27b99151278c |  | note | Inspection / Test Point - Permits
label | e0acf17d-d11a-55fd-9f3b-51774b04507f |  | note | H
label | 820bd8bf-ef4e-5e38-99e3-1551ba54b812 |  | note | Detail - Obtain Permits
label | beae4c90-cc33-5469-89d3-a39d65fbb2f3 |  | note | Frequency - As required
label | 2cacb85b-52bf-51a3-b684-a4d7da722da0 |  | note | Inspection / Test Method - Document Review
label | 55740fef-9b09-5f6d-9601-e20abe1921e5 |  | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | e944414f-42f1-5966-9d50-54eb281252b7 |  | note | Records - Permit attached or permit number noted
label | 0ffe3f4c-4caa-5602-b48d-5b3f8670a17a |  | note | FH Initials - Site Engineer
text | 44b7c84e-a64c-5896-a893-025ba7d70c26 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-construction sign offs
label | f6a59d11-ec34-58c2-8117-0a17c3784e58 |  | note | Inspection / Test Point - Pre-construction sign offs
label | 88aab39d-809e-5afd-a87f-c80b4229d69e |  | note | H
label | 83a2899f-a486-5c8f-a947-939575c3c10b |  | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
label | 6b219e0f-2399-5cab-8275-df2328f6b797 |  | note | Frequency - Prior to commencement
label | b84297ee-c7be-5075-bd09-780a69730909 |  | note | Inspection / Test Method - Document Review
label | 7c7393d5-44c4-5486-abec-d06d734f73cc |  | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
label | 873264c5-437f-5685-81f6-90e5b7586b41 |  | note | Records - Subcontract and Supplier Agreements
label | 374e328d-ff73-55f7-a973-e61e0dbc98dd |  | note | FH Initials - Site Engineer
text | 0c978cf7-adb7-5c4e-982e-7a3c61b1fe5b |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1 -
label | 3d51b5f1-a6a2-552f-8085-a36ba30b02fd |  | note | Inspection / Test Point -
label | 450296d5-d0b4-5570-8fc9-ec0342cfab6b |  | note | H
label | 66842f7f-82af-5041-b3a6-e94eed6264bc |  | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | 6e8ab7de-01c4-5903-b3a9-8d812040214a |  | note | Frequency - Prior to commencement
label | add673bc-ccc0-5508-9b14-29d3baba1582 |  | note | Inspection / Test Method - Document Review
label | c2037626-a474-5b37-ac29-923a429e8f8b |  | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | 16877900-9e46-55c2-aec5-c6aa470f337f |  | note | Records - TMP on MyWorksites/On Site
label | 9ef8750c-b3f2-54a6-a0ec-efd437f544ad |  | note | FH Initials - Site Engineer
text | 7ad330a0-c603-59a1-8dc9-4c6b41e82058 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 -
label | af3705bc-3285-582f-827a-85f956f49002 |  | note | Inspection / Test Point -
label | cd9659e8-ea34-5d1c-be3c-52447874804a |  | note | H
label | 2d38d2d6-db26-597f-9a09-68063998e881 |  | note | Detail - Ensure all Subcontractors and Suppliers go through FH induction
label | a1570447-19dd-5ea4-a4fb-6f8b2332893a |  | note | Frequency - On site daily
label | 68999fe1-221c-5b1a-9248-773d25bfffb7 |  | note | Inspection / Test Method - Induction
label | bb0b55b4-1789-5ec8-9f6b-494b0bd20846 |  | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | c1a31d49-33f7-56f2-b001-a3be07b42d4c |  | note | Records - Hazard ID and Pre-starts to safety team
label | 9ab58790-a056-5aa8-b1e5-e3ac305e5fe9 |  | note | FH Initials - Site Engineer
text | 6081fdb6-fb11-54a5-bcb6-c1f98f3c3ca1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 3c9d7258-8fcf-5943-90d9-389cb2449e37 |  | note | Inspection / Test Point - Design
label | edf74a9f-2d7a-59ac-bcff-04fd7e37eb5f |  | note | H
label | bc715568-e106-501a-a59d-bca1373b1a48 |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 3328e18e-f6a3-55e4-908e-b8dd7a14d53a |  | note | Frequency - Prior to commencement
label | d915f0d1-9d40-5f63-a720-4650cb4baf88 |  | note | Inspection / Test Method - Document Review
label | f858f55f-ef85-5be8-9e0f-ec8c58cf7c34 |  | note | Conformance Criteria - IFC drawings have been received by Contractor
label | 5507bc0d-2fc9-5b31-84b5-cd740801dac6 |  | note | Records - Check Drawing Register
label | b711aa63-8e66-557b-8342-5d8439937596 |  | note | FH Initials - Site Engineer
label | 6ca126e2-65a6-5096-a259-afd9c6d44780 |  | note | Design Engineer/MSQA Engineer Initials - Design Engineer
text | 7610a12b-e1e7-5091-a17b-a6c264c364e8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Installation of Erosion and Sediment Controls
label | b54d64da-a211-5327-8e14-2ec7c9e5354e |  | note | Inspection / Test Point - Installation of Erosion and Sediment Controls
label | 05dd4647-bef9-5a89-9a6d-271ed8297738 |  | note | H
label | ecd92957-8a36-5863-8a02-9df8b7292823 |  | note | Detail - Ensure that Erosion & Sediment Control in place
label | dbe11fb8-9b78-5d8d-9792-bec6685cca82 |  | note | Frequency - Prior to commencement
label | 692e41c9-4cff-5528-8e20-9240c8062a00 |  | note | Inspection / Test Method - Visual Inspection
label | ba7f1958-87c3-5e2d-86de-2d63305a85b3 |  | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | e73d306e-fada-545a-99c3-9d04a73ba238 |  | note | Records - Environmental Controls Audit
label | 9d286478-8eb4-5d0b-878b-18be120d99c2 |  | note | FH Initials - Environmental Manager/Site Engineer
text | e265a897-2e7b-5a1f-82e4-8f363abdb1fe |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | 7090de7c-7732-546f-80ac-41f57ceb3248 |  | note | Inspection / Test Point - Survey Setout
label | 588bdd70-1124-5f58-82cc-eb2b4ef0ae39 |  | note | H
label | 0d8459f4-2c52-552e-a87b-400738f3b57b |  | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | c45a35e0-d659-5bd3-90db-4d98d42dc3b3 |  | note | Frequency - Prior to commencement
label | 8594f82d-41bd-5685-92b1-9d226f3ef996 |  | note | Inspection / Test Method - Survey + Smart Level
label | de677f0a-a856-5016-bf23-9a4d37377fab |  | note | Conformance Criteria - Consistency with Construction Drawing
label | d7e5e77e-8ec6-5b87-bce6-24c546d77e53 |  | note | Records - Site Photos post surveying
label | 2deae77b-622e-5c74-be17-760582c104ba |  | note | FH Initials - Site Engineer
text | 58a16dc2-fbd9-5d52-84a3-89efc8608cdc |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging
label | ee5d5d08-ee62-588d-816b-674e0e8c88f5 |  | note | Inspection / Test Point - Locate Existing Services by Hand Digging
label | 70942ef1-9a1a-5ee5-ad7a-abc50ab14e17 |  | note | H
label | 31ab2c4a-c406-5384-8081-885c590cc249 |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
label | e7f2c366-6a45-5f5f-8ffd-4018da659e78 |  | note | Frequency - Prior to commencement
label | 1129c76a-4ce3-5e94-818d-39175258b004 |  | note | Inspection / Test Method - Potholing
label | 1e5a9a32-a739-570e-a768-a1f03c25b878 |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | f5ebdadd-1b77-514f-ba6f-19ff1152919a |  | note | Records - Digging and excavation checklist, service planes, As-Built Drawings Doc. Review
label | 4ac98b18-af9a-5086-b486-8e41dc6f330e |  | note | FH Initials - Site Engineer
text | 1f7693c9-3cae-5f92-a60c-6e82238227f8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Material Compliance
label | 725807d1-d5c5-50a0-a919-60765d38ae25 |  | note | Inspection / Test Point - Material Compliance
label | 35fa9cd5-becc-5adb-9a3c-2d030e0816ff |  | note | H
label | 35d1f776-52e7-52b3-a2a8-5ce12a611412 |  | note | Detail - LESA dowels to be used at all construction joints
label | 2c42273c-250f-594f-bc1f-9384bb2f3958 |  | note | Frequency - Prior to pouring concrete
label | 419e6323-037d-5d28-9f6a-6ab663086a1d |  | note | Inspection / Test Method - Document Review
label | c3eb137e-65c2-56d5-b81f-5ca06f88021f |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 3c36e38d-f7e3-5150-ac62-5969f1e9d055 |  | note | Records - Delivery Dockets / Photos
label | 3e380ad2-bfe2-5e88-aef5-5368aad5b397 |  | note | FH Initials - Site Engineer
text | 322532a2-fb21-5f3f-89aa-dcb1fc853789 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.1 -
label | 8f7e8deb-7876-5ad6-a881-d7fc66d1da56 |  | note | Inspection / Test Point -
label | fc2ce230-6e38-5c1b-84f7-d49845df89a5 |  | note | H
label | ea3cd11b-c2b1-5a37-912a-fe1986e0b5d4 |  | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
label | 1ddf18cd-e7f8-59d7-a23b-211aa60872c1 |  | note | Frequency - Prior to pouring concrete
label | 77860391-908c-5ad1-af05-9c60c0698f0e |  | note | Inspection / Test Method - Visual Inspection, Document Review
label | cbccec42-d6b3-50e1-8a3a-f5c0092b7bf1 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 7602b08f-fb11-5f6e-b4fa-174be874945c |  | note | Records - Delivery Dockets / Photos
label | a8b0f701-ff6a-5091-a266-5d8eb054d8e1 |  | note | FH Initials - Site Engineer
text | 249921a9-a37a-50ed-b065-37afe86753a1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.2 -
label | 2cb04413-514e-5eea-b75a-3cdaf5a9d681 |  | note | Inspection / Test Point -
label | 7fd493e3-9b90-573a-8110-81bd7e4b18b6 |  | note | H
label | 944e2271-b1d0-5d8e-af05-739cbfba04f4 |  | note | Detail - 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | 601182fa-4be7-5b27-b466-0f371367cb01 |  | note | Frequency - Prior to pouring concrete
label | 07ba3819-b2d8-5463-a688-abdf4d7e3e26 |  | note | Inspection / Test Method - Visual Inspection
label | 704c97d8-6cde-52bd-8466-c6c733544080 |  | note | Conformance Criteria - CIV >15
label | b8ef0332-e935-5f16-8dc7-e66b4dde96f3 |  | note | Records - Delivery Dockets
label | cd0da887-e456-5470-b323-607dfe49b212 |  | note | FH Initials - Site Engineer
text | 275b7b55-a0f5-5d19-b292-92ee4af87781 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.3 -
label | 95c9c422-d041-5811-9614-4888c96a6f4c |  | note | Inspection / Test Point -
label | 2916f9ca-f1cb-5401-bcc6-8d37de94940a |  | note | H
label | 9a505cde-6ea7-5a6d-9174-774fe16bd285 |  | note | Detail - Two layers of 663 mesh to be placed inside with plastic chairs separating.
label | a1c9c413-c842-5ae6-b558-13ae0aa00629 |  | note | Frequency - Prior to pouring concrete
label | c6106c54-b39e-56d6-9490-35ad36e3a146 |  | note | Inspection / Test Method - Visual inspection
label | 2c5ed789-bd26-57e1-b51f-a6bf7e4419ef |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | f68e0a3f-2d24-5caa-a5a7-f6df4c49668b |  | note | Records - Delivery Dockets / Photos
label | 72bd08ab-d71e-5e06-a3a0-767db0f9c1a7 |  | note | FH Initials - Site Engineer
text | c66107a3-ec68-5ca8-bb55-7439032f0021 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.4 -
label | 0d71ee37-22b0-57b6-870d-2f887facfcd4 |  | note | Inspection / Test Point -
label | b4ba1bc6-a2b7-5b0f-b062-2117d2db1fe3 |  | note | H
label | 5dc0f403-0732-543f-9d1d-f7fa2e481557 |  | note | Detail - All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder and 13mm aggregate chip size
label | 37d8b1d1-e726-5956-93ea-5813526ab5d0 |  | note | Frequency - Prior to pouring concrete
label | 4f74487f-5291-5fca-964d-127d1e32bc81 |  | note | Inspection / Test Method - Concrete Delivery Dockets
label | 651570f1-2fe9-506e-ba3d-a55369e3bf74 |  | note | Conformance Criteria - Delivery Docket added to QA folder
label | e34b61f8-081a-50ad-9b51-4974c544f6fa |  | note | Records - Concrete Delivery Dockets
label | 469d149e-1ce1-57c6-97b3-245e7a364923 |  | note | FH Initials - Site Engineer
text | d62df1dc-a46d-5a17-bd0d-46c8adb22441 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.5 -
label | 89a9b857-d4a3-56eb-9c8f-0d1a12390bd6 |  | note | Inspection / Test Point -
label | f537b313-40a1-5631-8051-373e625e20b3 |  | note | H
label | b950baf6-53ab-5c10-ac9d-98b750f5e7ba |  | note | Detail - Steel chequer plate cover powder coated skid resistant yellow connecting kerb to kerb bolted on
label | 3f3c35ca-0828-5d18-abe7-3414fc74622e |  | note | Frequency - Prior to pouring concrete
label | 384872a0-5e79-50e9-9fc3-f27d2f8a1659 |  | note | Inspection / Test Method - Visual inspection
label | 856f8d00-2b1a-5229-9567-a81dce416a23 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 1c0e11ab-7d64-5847-8627-1744341eef69 |  | note | Records - Delivery Dockets / Photos
label | 26d3a297-5480-5f3a-92e7-75763d0d46bd |  | note | FH Initials - Site Engineer
text | d96652df-27c8-54e3-9ca8-338e64511ed6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Temporary Works (Formwork)
label | 2e400c34-b05d-56dd-b3eb-1432731ad06a |  | note | Inspection / Test Point - Temporary Works (Formwork)
label | 0d768aa3-2368-59f5-8c7c-da3c0f4cd440 |  | note | W
label | cb4ebbed-c619-58d8-a14a-6c500f30890a |  | note | Detail - Formwork to be set to correct line and level
label | 4d618890-5115-59b0-a271-86a8812ea9bc |  | note | Frequency - Prior to pouring concrete
label | 623014ef-0269-54ba-a098-db4b44d1efb9 |  | note | Inspection / Test Method - Visual inspection
label | 1778ec95-a31b-53a4-bc99-c486c9d6e33b |  | note | Conformance Criteria - Concrete Inspection Record
label | 3169c781-8a2b-501d-94f9-d3019424cde0 |  | note | Records - Concrete Formwork Checklist
label | fde13eb7-0bf3-5618-b8e6-32d8b7e67944 |  | note | FH Initials - Site Engineer
label | 0f31d380-7352-509e-b204-279d75d692a3 |  | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
text | 9f7d0a19-c266-5b3c-bea0-298a8973873a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.1 -
label | 2e2f9cf7-1a5e-5726-b0a1-3ac911c41f73 |  | note | Inspection / Test Point -
label | 5c917d1a-38a0-5e26-8b7f-a3cf729f3e41 |  | note | H
label | 511c9b0d-98a5-50cf-9421-19804fc63f25 |  | note | Detail - Raised table formwork to be 100mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
label | dd7ba0f1-1c8a-53c7-83e3-95ccf105c104 |  | note | Frequency - Prior to pouring concrete
label | 90168591-b495-5e18-9068-2eb2b655a3fc |  | note | Inspection / Test Method - Measurement
label | a9f0c13b-ea05-577b-9049-ed5bcb38653b |  | note | Conformance Criteria - Designer to inspect formation level
label | 49248cf6-1ff0-5d9a-be0c-25e7fc986c85 |  | note | Records - Site photos
label | 26efac4b-0b8b-557f-8b7f-7d75a141f2e9 |  | note | FH Initials - Site Engineer
label | af388441-2658-5175-b26b-581d8d2d9176 |  | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
text | 7520e2c4-1cd2-5c7d-aa74-198fa9976d8e |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2 -
label | 817aec67-63de-58b9-a53e-99e691a2c383 |  | note | Inspection / Test Point -
label | 0e39bdaf-3557-5bec-99c1-df80226c66dc |  | note | H
label | b73e8d63-c299-5a5b-bbd8-9b018b1e987b |  | note | Detail - Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
label | 62b5c8e4-b860-587b-86b6-6dc9b5e33fe1 |  | note | Frequency - Prior to pouring concrete
label | a3b92258-d6b6-5346-89e3-2de4d1e8f9d0 |  | note | Inspection / Test Method - Measurement
label | 42c0896e-52cb-57d3-b177-5f891bcf8589 |  | note | Conformance Criteria - Designer to inspect formation level
label | 00cf9ce7-fae0-5d26-9d0c-a88f159fbb3d |  | note | Records - Site photos
label | 4f5f5d54-c2c5-5cc3-bc15-3a441c048742 |  | note | FH Initials - Site Engineer
label | dace20b0-f72d-57d8-9a77-06860e26a9a1 |  | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
text | 559695be-c4ce-5609-9626-1d70b4f3cdc6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.3 -
label | b9c5c145-9370-523e-8125-45b8a0949bf1 |  | note | Inspection / Test Point -
label | 75510f12-7aa2-578c-b248-e81555b2d0a4 |  | note | H
label | caf40323-ad83-5816-abac-7e44b432832e |  | note | Detail - Raised Table ramps to be 1m across for entry and 1m for departure ramp. Toe to be 1m across for both entry and departure with asphaltic wearing course
label | b47b0dd5-6c5c-5b58-81ce-cfe0554816da |  | note | Frequency - Prior to pouring concrete
label | 12334108-527e-54a5-aa0d-53379a7a1795 |  | note | Inspection / Test Method - Measurement
label | b1d2c378-f9a9-5247-88b2-c00adbe83ed4 |  | note | Conformance Criteria - Designer to inspect formation level
label | a22d485f-4d78-5bda-9374-9920cb6edc88 |  | note | Records - Site photos
label | ea15c6bc-8895-52ed-a609-561d4245ba9e |  | note | FH Initials - Site Engineer
label | 07232781-b115-52ca-a7b3-b549d75b3a65 |  | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
text | 7ca9b55d-3e30-571f-9ae4-3b0eccb59833 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.4 -
label | c8034f61-e52b-5a5f-82cb-6b0eebe923db |  | note | Inspection / Test Point -
label | 3994f072-0b04-522a-acf7-1d3feb138ca1 |  | note | H
label | 718e6eba-f98f-592a-acef-994ba948c4a2 |  | note | Detail - Raised Table ramps to be 1:10 gradient for ramps
label | 38311fe5-5209-5701-b961-66c5d2feedf0 |  | note | Frequency - Prior to pouring concrete
label | b43405fc-487c-5c70-a3f9-8244e14cbe49 |  | note | Inspection / Test Method - Measurement
label | 3c8c01f8-b069-5e4b-a06f-7d361627d7d8 |  | note | Conformance Criteria - Designer to inspect gradient level
label | fcb1ea13-2a55-52d8-9e89-4487701dd7fe |  | note | Records - Site photos / Concrete Formwork Checklist
label | ba30032d-2f08-5d04-a0c7-639af18ca3bd |  | note | FH Initials - Site Engineer
label | 82039416-27c3-57a7-b1c9-5a54a8636b18 |  | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
text | ea7f7fe4-24ff-5349-ad2e-78c96a8f4a39 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.5 -
label | ec8c8d55-f144-575b-84cb-e9f80a7c0e49 |  | note | Inspection / Test Point -
label | 46455d9c-2a8c-5754-bcdb-4522f73537b7 |  | note | H
label | 4076ca26-5b08-5e6d-b549-14fcbeaa46d2 |  | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | 32da3cea-0a7c-5469-902f-0e2dcbdc9891 |  | note | Frequency - Prior to concrete pour
label | 53434348-0009-55f8-99e3-9f5c8001d5e6 |  | note | Inspection / Test Method - Visual inspection
label | 45af18bd-521b-5be0-9f59-71b684faf1fa |  | note | Conformance Criteria - Concrete Inspection Record
label | 993970b3-34df-575f-8aec-0738da14c7d9 |  | note | Records - Concrete Formwork Checklist
label | c122dd8f-14b5-506b-89ce-1e5aa8933446 |  | note | FH Initials - Site Engineer
label | edf67f0d-b97a-5538-980a-3937679ad618 |  | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
text | 361af112-825c-52c6-b0e0-baeef8c78be4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Reinforcing
label | 2caf267d-4898-59c6-a18b-1b6a0a8e511a |  | note | Inspection / Test Point - Reinforcing
label | 7cf9e9da-0f8a-5980-b964-ff611bbea450 |  | note | H
label | 349a6ea8-555d-57e3-b77f-c3d5a0126183 |  | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels . Speed basket system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
label | 9b498cc7-89d2-5987-8865-b6918031d17c |  | note | Frequency - Prior to pouring concrete
label | e5335527-afc7-5c2a-a4c0-7abc8148ced7 |  | note | Inspection / Test Method - Measurement
label | 7dd6396c-d0fe-5855-aa70-cbf8bf5c57ac |  | note | Conformance Criteria - Concrete Inspection Record
label | a2a19c69-1086-5762-af10-99839fe185ce |  | note | Records - Site photos/Concrete Formwork Checklist
label | 00b09ec9-b9eb-5339-a3bd-4405d4d96318 |  | note | FH Initials - Site Engineer
label | ddf07baf-5743-5cc3-8292-1e68a803aee3 |  | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
text | beee2acf-9497-5eba-8181-5ce812847419 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Concreting
label | 632436b2-c02d-553f-8dc2-fd079228d00e |  | note | Inspection / Test Point - Concreting
label | c948e372-bafa-5714-b640-094a435f463d |  | note | H
label | 1c1540ad-e769-5461-b250-64abb96aab5a |  | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | 963cfaff-c9ab-530c-a8e2-82000115958e |  | note | Frequency - Prior to concrete pour
label | edcacaf8-c057-5489-807f-1b8b3695c64a |  | note | Inspection / Test Method - Visual inspection
label | 0e83e389-6295-57f2-821b-2b578f31aae9 |  | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | 22c8ef53-7418-5f4a-99e6-a13127694fe9 |  | note | Records - Email / SMS
label | aceec6f9-e27c-5223-ab4d-263861b96619 |  | note | FH Initials - Site Engineer
text | 42262de0-6ea7-50ef-aded-d8ad20033422 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.1 -
label | 2c56ea6a-2fb6-5ac0-844a-b8e47ccbddcf |  | note | Inspection / Test Point -
label | 20286f18-db82-52a7-8e2b-58a0595b9ab8 |  | note | W
label | bace855d-3ffc-524c-afbb-789a6a8bb874 |  | note | Detail - Vibrator to be used throughout concrete pour
label | 04186972-2adc-527c-820a-a0bfb8ec0175 |  | note | Frequency - When pouring concrete
label | 3ae7e579-b665-5350-bad9-96269c028d20 |  | note | Inspection / Test Method - Visual Inspection
label | 24394b2b-4e02-5040-9693-9437f4feb4b6 |  | note | Conformance Criteria - Concrete Inspection Record
label | a5520cf9-62f6-5b99-a64b-1ef51844f9b8 |  | note | Records - Concrete Formwork Checklist
label | 6c7522c3-c4ba-5015-b7d6-1b1469f345cd |  | note | FH Initials - Site Engineer
text | f82cb3f5-db9e-560d-9246-e4e96623caf5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10.2 -
label | bccfd351-21a7-575e-a947-246a5c035348 |  | note | Inspection / Test Point -
label | e48ce5f5-439d-5642-bf89-ac1cdce1beca |  | note | H
label | be633215-234d-5d91-9c56-38ba448c32a0 |  | note | Detail - Concrete surfaces shall be U5 broom finish for ramps, and exposed aggregate finish for table top.
label | b3e4cabf-e7a5-5219-b968-4b5506a2b075 |  | note | Frequency - At completion of pour
label | 650fa4b8-e748-5929-87b5-94ceb7692936 |  | note | Inspection / Test Method - Visual inspection
label | 5502497a-0832-5442-9b69-390b8d5edaa3 |  | note | Conformance Criteria - Concrete Inspection Record
label | 22ec5c40-619c-5dde-a87a-ef69780f1fe2 |  | note | Records - Concrete Formwork Checklist
label | 6404d0bd-2561-5b6e-9a6e-dcb661853b13 |  | note | FH Initials - Site Engineer
label | 8afaa1fc-81ab-5ec4-8700-a4034a90257b |  | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
text | 61b54244-69b1-51d0-949c-f0e0fec87305 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Curing
label | 93c5ffb0-7412-5491-9e91-938a880e6fec |  | note | Inspection / Test Point - Curing
label | a3f3896e-a51e-521c-9bf5-58d4d1f4cbf0 |  | note | M
label | 4e7adff6-6e27-5cdf-8b81-f9ff702ae6f2 |  | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | ec1b5aa6-8f6f-5033-af9f-c1f2c901bf1b |  | note | Frequency - Post Pour
label | faa49a7b-864a-56b5-a497-9c777993a765 |  | note | Inspection / Test Method - Monitoring the time allowed for curing
label | 44887ec4-94e9-5530-8318-69f34991ae31 |  | note | Conformance Criteria - 48 hours minimum have passed
label | a3d8a987-3682-5fbe-a0ab-06b416f65e6a |  | note | Records - Concrete Formwork Checklist
label | 2e4905f2-a99c-583a-aeb5-575223eed83b |  | note | FH Initials - Site Engineer
text | dd4949ef-31e0-5f06-89d9-a68668a10eef |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 12 - Remove formwork
label | 19400316-74ee-5874-9f96-b918b64e4aa8 |  | note | Inspection / Test Point - Remove formwork
label | c97af875-16a7-55d6-abf7-e7da1d145269 |  | note | W
label | 6c594a86-bd83-5538-9b4b-8f30b5bb6479 |  | note | Detail - Remove formwork after 48 hours
label | 74e90f37-113e-54f5-a69a-6b334652b873 |  | note | Frequency - Post Curing
label | cee20364-5503-5421-975d-3075f6760eca |  | note | Inspection / Test Method - Visual inspection
label | adea6d84-71ad-5790-a38b-59e23cb0f843 |  | note | Conformance Criteria - Concrete Inspection Record
label | 5b9782d5-e748-574d-8397-5e59a6f2bf9d |  | note | Records - Concrete Formwork Checklist
label | 38d6b186-f90c-507a-b57f-c0f317e9c7ff |  | note | FH Initials - Site Engineer
text | a2c4dd0f-ca1d-5813-b069-94c6ff7bd1cd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
label | 4b04f28e-659b-56a3-8268-f47178c68e15 |  | note | Inspection / Test Point - Asphalt- Concrete extension slab/ Toe
label | e8b7dedd-3f51-52c3-8b07-10cc8858f7f3 |  | note | H
label | 6659e328-71c4-5557-9990-056088e19ea1 |  | note | Detail - Two rows of Lesa diamond placed mid depth @400 C/C along construction joint as per 2789-C6500
label | 159decb3-9784-5e54-b485-d61e3f93a845 |  | note | Frequency - Prior to pouring concrete
label | eea4bb89-2e82-5f18-a488-c9497d5407c7 |  | note | Inspection / Test Method - Measurement
label | 13b7029d-956f-541a-9577-40333664e919 |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 8050366c-b834-546f-8084-b03cd6e1412a |  | note | Records - Site photos, delivery dockets
label | ae3f41b2-3fa9-5ed4-a333-a5e24471dec6 |  | note | FH Initials - Site Engineer
text | dddb5520-17e5-5e29-8608-e0e52d2d44dd |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.1 -
label | 868d8cdf-bb0a-58de-a036-098c8d74f13c |  | note | Inspection / Test Point -
label | 370847f7-031b-59ff-9c96-4e4a3db1dcaa |  | note | H
label | 87ac80a2-dc16-5a34-bc76-d75dc64bce33 |  | note | Detail - 150mm thick 40MPa Concrete with two layers of 663 mesh
label | 51763886-8c4c-556d-9347-7616435ec232 |  | note | Frequency - Prior to pouring concrete
label | 9a2e1a76-005f-54b3-9575-6c8791435be3 |  | note | Inspection / Test Method - Measurement
label | e083d65d-6b4d-571b-b2b7-9ae6ba746249 |  | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
label | 2035b63d-ff97-59e4-8a03-aa05041063a5 |  | note | Records - Site photos, delivery dockets
label | 91c367b8-0bd2-53cd-bdb1-1f61953dcbe8 |  | note | FH Initials - Site Engineer
text | a7c08cbb-135a-570c-ac33-f2cd20db6495 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.2 -
label | 328e5297-9ab8-5172-96b1-9a66f1b61b8a |  | note | Inspection / Test Point -
label | e365e014-e8a9-5823-90a4-c4223340b11b |  | note | W
label | 6d459a30-bb2e-5744-b198-9d3a6c74e118 |  | note | Detail - Tack Coat between AC and Concrete slab
label | 1c67a132-d2c6-53a2-b934-9e13acc83216 |  | note | Frequency - Post Curing
label | 5b030bdf-9782-5c23-9e3a-7904a1bf742a |  | note | Inspection / Test Method - Visual inspection
label | 53a4bfae-2978-5c7b-b353-8c5f3b3d7fad |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 25572adb-ace6-5f65-a26d-04fc79e79ef3 |  | note | Records - Site photos
label | ef4dea5c-d31f-5076-820c-d9f66c4e7ad0 |  | note | FH Initials - Site Engineer
text | 86dbda62-616c-5045-a0f2-dd630d119d49 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 13.3 -
label | 6bed3770-4b66-53ac-a8c9-864165eca01e |  | note | Inspection / Test Point -
label | cbfcd288-152a-5998-ab64-65896ab5121e |  | note | W
label | 06e0a4ed-ff08-5704-9912-6123ed6a6230 |  | note | Detail - 50mm thick DG10/Mix 7
label | 73ce9a89-5deb-5c42-8105-7869c9933c95 |  | note | Frequency - Post Curing
label | c6f599e0-80b5-54a7-ab56-fbcdb176e6ae |  | note | Inspection / Test Method - Measurement
label | 8ee57864-aee9-5a4f-924a-3e4fa098d577 |  | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
label | 12ace640-3442-58c4-bb4f-e257036e2cf1 |  | note | Records - Site photos, delivery dockets
label | e4b16ab2-d06d-5b3f-b608-f2520e85c838 |  | note | FH Initials - Site Engineer
text | d3a4e18c-5de7-5e36-b53d-6d03c4acbe1c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 14 - Lot Number QA File
label | bd2b47aa-a80e-5c54-b123-240d0c9608a7 |  | note | Inspection / Test Point - Lot Number QA File
label | 6c8591b7-9628-57ad-8b16-adc7a06ab7db |  | note | W
label | 397a3720-b65d-5d4d-96d0-3561e22194e3 |  | note | Detail - Ensure all QA Records, site photos and incident cases (OFIs) are closed and included within QA file
label | 7210877a-1748-5ce7-9f3a-d3029a9c7e59 |  | note | Frequency - At completion of Lot
label | df51271b-0637-5fcb-beda-658d1c84b923 |  | note | Inspection / Test Method - Document Review
label | ae415392-6b8b-5a83-97e1-c45ebbcf4481 |  | note | Conformance Criteria - All QA files compiled and submitted to client
label | 65af2ce3-1125-512a-9f68-b0778cb62e0e |  | note | Records - QA records
label | 48c9ccb2-1b8a-575c-840e-01dc27607cac |  | note | FH Initials - Site Engineer
text | 2f75e48a-7b4e-596c-b63d-eb81f99b31b7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 14.1 -
label | 38ddffc4-6ad0-5174-b8c4-2ecd127a14ec |  | note | Inspection / Test Point -
label | f981d0e1-ec05-5933-8b15-184f91bbbf2f |  | note | W
label | 2d505d36-a0a5-560b-bb25-eca2f31b6fc6 |  | note | Detail - Delivery Dockets to be included in QA file
label | cc82254a-7a9f-51b3-824d-62ce55ab28ee |  | note | Frequency - At completion of Lot
label | b7e579b0-a29e-55da-8c48-4b5718831486 |  | note | Inspection / Test Method - Document Review
label | 862838fb-0568-5bf5-9914-69e36ec1b175 |  | note | Conformance Criteria - Delivery Dockets to be included in QA file
label | 6f221d5a-1771-56b2-932f-0b64a4e0535e |  | note | Records - QA records
label | a705f408-6ebf-5b50-944c-8204f9876a00 |  | note | FH Initials - Site Engineer
text | 5844dc61-a36a-5784-9806-25f253e4b55a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | ae680f74-b222-5a0a-80a0-41fb21c2be54 |  | note | Inspection / Test Point - As-builts
label | a1517fce-eb7b-5b8e-bb8d-6b5f9c6a1f18 |  | note | H
label | e093927a-549c-5dba-92d5-9ff8b15fc888 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 8445d1af-357c-5deb-9686-01ddcb7f0203 |  | note | Frequency - At the completion of the Lot of work
label | 7328d362-b87c-561e-bfff-77c972a1c681 |  | note | Inspection / Test Method - Drawings
label | 485f43ab-8756-5f12-bf71-c4def112c5aa |  | note | Conformance Criteria -
label | 9ae87ba0-7401-56a9-add8-ea43cc7c8047 |  | note | Records - Asbuilt Drawing
label | 1931cb71-8ffc-50c2-acd3-a46b07fbab10 |  | note | FH Initials - Site Engineer
text | 7cd667b3-3e9b-5244-bbe8-0cfdf68c943e |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
text | 42675938-bf9f-58dd-9ea8-4c0de3756ee2 |  | textbox | Comments:
text | cdfb682a-67af-5d0a-8f0c-d14183aa06fd |  | textbox | IFC Drawings used for Construction incl. Rev numbers:
text | 9b3121f1-079c-59ab-8139-9016a7fde799 |  | textbox | Reference Documentation (Notices/OFIs etc.):
text | 88c6352c-529d-58c2-acac-e8f3e4b78f17 |  | textbox | QA Compiled By :
text | 5e6faef5-9b97-55ce-b1bd-c4016f6dcbe9 |  | textbox | QA checked By Discipline Manager:
text | 6953f4d2-489f-5e3a-a51b-9e2531068a13 |  | textbox | QA checked By Quality Manager:
text | fd076df9-63f6-52cc-99e5-15d4e88976a6 |  | textbox | Accepted By Design Engineer:
checklist-sectioned |  |  | checklist | ITP - Rockfield Road - Enabling Works - Footpath, Kerb and channel | itp |  |  |  | Yes | ITP - Rockfield Road - Enabling Works - Footpath, Kerb and channel | fb655810-416c-4e57-8417-79c43865c027
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 - Site Set out
label | 07ecd051-4d0a-584b-a15e-609d51d224c2 |  | note | VERIFICATION ACTIVITY - Surveyor
label | fdf7d0d7-4a7b-53be-b546-4c396bee803a |  | note | METHODS OR REFERENCE - Surveyor
label | 8e167f3e-f89d-5aab-8cc1-21c28ade0b30 |  | note | FREQUENCY - Every site
label | 56d8a5a0-da62-536d-98ea-edb654e1135f |  | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | 0aa25e34-ef58-588e-a2cf-4072d1d7ab69 |  | note | Mandatory HOLD POINT -
label | 10f67d2e-6381-556b-b23d-1f5fd6146282 |  | note | Records - Onsite records/photos
label | 11ceba2f-ac5d-545c-92c0-7868a1d83b25 |  | note | Onsite Responsibility - Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2 - Kerb & Channel
label | ad13f4aa-4830-5cf3-ac4e-3d45a6be39ea |  | note | VERIFICATION ACTIVITY - QA FORM
label | 12102165-c59c-57e2-9b58-8cfc3b833ae3 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | d99599a6-b2f7-5e3c-a9e0-ffbf24dd0f27 |  | note | FREQUENCY - Every site
label | 96d4a49b-bf7a-5360-ac4b-8c01be1cf8d1 |  | note | ACCEPTANCE CRITERIA - Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min GAP65 sub-base in roads and 100mm GAP40 in footpaths (CBR>5).Concrete 20MPa @28 Days
label | 60430459-dbb8-5036-b3de-df9b9561f7f0 |  | note | In Process Inspection
label | 212ffff4-7808-5102-9c89-ef6dc6d4b16a |  | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
label | c41e0cfe-c387-54ae-8933-b14c6184731c |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Channel Level
label | 1226f12b-0f68-57c1-921c-c603e64489e8 |  | note | VERIFICATION ACTIVITY - QA FORM
label | 0d9f097e-449c-5d96-97ca-5e6590616687 |  | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
label | ad39818b-7bd0-5211-9337-0aa65113d288 |  | note | FREQUENCY - Every site
label | 1e3c3bb4-7175-5f74-a44d-21e19a30d14a |  | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | bec9ae8f-240c-5f63-8428-d57efdf9a3c1 |  | note | In Process Inspection
label | 2f99a405-169a-5799-9ad9-1cbb7bfbb7a3 |  | note | Records - FH concrete QA sheet
label | 549a3264-c9ef-5467-b36a-2e9a8aac5ded |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4 - Concrete Footpaths
label | 1c1977e7-e4fd-586c-950b-f86502d81ac9 |  | note | VERIFICATION ACTIVITY - QA FORM
label | d2063b68-6577-5cee-9393-a47e96fb9b26 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
label | 8f49be11-cc9c-53e0-a4b0-1fb604935020 |  | note | FREQUENCY - 10m Intervals
label | c8d02b63-fbfd-5111-830c-3b7b6ac76467 |  | note | ACCEPTANCE CRITERIA - Subgrade - (CBR > 3) Basecourse - 100mm min. GAP40 thickness Clegg CIV > 15 Surfacing - Concrete 150mm and 20 Map @ 28 days. 4kg/m3 black oxide with broom finish Concrete surface finish must comply with 3114 and S/NZ 4663 Slip resistance of pedestrian surface
label | 2fadb520-3e96-5a4e-a94f-fb380275f28a |  | note | In Process Inspection
label | 2f7a0af6-d5d8-53ef-8bd4-a02a8bcec8f3 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | fd633a63-c488-5d43-92fb-32df404746b7 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4 - Concrete Footpaths
label | 76d320f0-62f5-5928-a05a-b4eff835176a |  | note | VERIFICATION ACTIVITY - QA FORM
label | 496b584a-8761-51ab-ad18-bb9997768e54 |  | note | METHODS OR REFERENCE - TDM Technical Standards - FP0006
label | 55dff54e-da03-5d61-ae2c-56c275c3233c |  | note | FREQUENCY - Each PX
label | 2646c073-04d9-5d73-95f8-7fd5f2e18110 |  | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
label | 18383a18-d505-5024-af67-19ea89f7fcbd |  | note | In Process Inspection
label | 462016da-a4f5-57fc-b34b-a3a4a485e7ea |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 7142c647-e078-5ec5-b481-2c1ac4fec461 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 5 - Side Islands
label | 3561c5a2-2988-5dea-810d-21c5676b7c6c |  | note | VERIFICATION ACTIVITY - QA FORM
label | 347a9a84-5c6d-5618-adef-d112c5c74f67 |  | note | METHODS OR REFERENCE - TDM Technical Standards - IS0003 A
label | 5de4643c-aeaf-5d9c-afb4-72d18acdf2ee |  | note | FREQUENCY - Each site
label | 94973d1d-8d8f-51e4-8a6e-667f87d80838 |  | note | ACCEPTANCE CRITERIA - Tapered Edge line with 1:10, 180mm thick 20 MPa Unreinforced Re-chip and -YUK concrete with 4kg/m3 Black Oxide and Exposed aggregate finish , base course to be 150mm min GAP65
label | 4ae4b976-9e48-544a-849f-f4636e52f706 |  | note | In Process Inspection
label | 2f901828-7b58-5c40-a7ac-3b212b779202 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | b049a821-0983-5d0c-99b4-fade2e8ad81b |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6 - Tactiles
label | 00477da1-6e1a-5d7f-b5f8-8f2db720b88d |  | note | VERIFICATION ACTIVITY - Visual
label | a2e1afa5-e3a4-54f0-ab77-85f0f269aa74 |  | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | ed064f6b-fe74-52a4-b9fc-53887c99505d |  | note | FREQUENCY - Every site
label | 87eefd18-a4bb-551e-9d35-807275f1a0d5 |  | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | 223631f6-9eeb-5fe3-b0f3-ba1670729357 |  | note | In Process Inspection
label | 66569026-79da-5e80-9d27-c9a2c5eb636c |  | note | Records - Photos
label | 4ba15f9b-53d1-59b4-982e-d700de38b22a |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6.1
label | b5f44351-08a9-5399-b2bf-256bac251439 |  | note | VERIFICATION ACTIVITY - Visual
label | bc4c8807-ae7e-526a-8e51-e9eb51807cc5 |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 437cb9cc-fd13-5da2-8de7-715303ae6f03 |  | note | FREQUENCY - Every site
label | 7cc92249-babc-55a4-bee1-c9573a2e1717 |  | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | 3f0a6a92-c36b-57b1-a9b9-262e0afbaec0 |  | note | In Process Inspection
label | c8b076e9-77c4-5275-afb3-81141028d26f |  | note | Records - Photos
label | 47d56cef-d94d-5c8d-ae30-dacaea5df74c |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 6.2
label | 2b3dc35d-d3a8-5db8-a747-703e64ae4c8a |  | note | VERIFICATION ACTIVITY - Visual
label | aab0bed5-a300-5f0d-a713-31ade6878e7d |  | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 9195fa0d-db1e-580f-be0e-51e25421aec4 |  | note | FREQUENCY - Everysite
label | 9764f275-9f2a-57c6-9fdf-8f8debf6c1a0 |  | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | 2ba7e5d2-ecb0-5f8f-acda-564ebd53c771 |  | note | In Process Inspection
label | 3b5c0f90-7894-58e6-b2dd-74ed9f1f25b6 |  | note | Records - Photos
label | f5ff9c58-8d1d-505f-a899-4f9f1a33f9ec |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 7 - As built information
label | a137bde0-3ccd-5003-8d14-7c8655203034 |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | ee7d6b39-0f92-56a9-9322-0f5d33fd1280 |  | note | METHODS OR REFERENCE -
label | 4c00058f-21ce-52ca-8e1e-708cc24a452d |  | note | FREQUENCY - Every Site
label | 0543586b-39a4-5c1f-b3bc-c8d5812eae7c |  | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
label | e2a378a1-5510-5da1-8c06-61f088ccb9f4 |  | note | In Process Inspection
label | 168ac0cd-0bf9-5a47-9754-85413dae4d25 |  | note | Records - Asbuilt records
label | 86fd4aa3-205c-5e0f-be54-d2879cb6de42 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | d6d39d37-a63d-54b1-924b-fe7cff086935 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 0c029be1-5391-5d0b-8e3d-90c3fa0ec8b8 |  | textbox | Print Name:
text | 73f4fac0-218a-509b-b1b2-3e91bdb9da1a |  | textbox | Position:
text | 49d0c257-5eeb-5a68-bb2a-155e78ad798a |  | textbox | Date:
checklist-flat |  |  | checklist | Stormwater Drainage |  |  |  |  | Yes | Halsey/Maich RAB - ITP - Stormwater Drainage | fba3b7be-026c-400a-bc02-9de4791e11b3
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | 82d38025-9b2a-590c-a404-94c0cecbc760 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5f6d9de9-7516-52db-9128-a99e8cd6fdc1 |  | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | a474e32a-14da-5f4c-91bf-378527c9b1fd |  | note | Frequency - Prior to any construction commencing
label | f6ec15ea-22b6-57ed-b9b9-0e23e557b0ec |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | f1d1ef3d-7dad-51ad-8488-0f3ec4a72905 |  | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | d0def003-2149-59a1-9d8a-1ee093728327 |  | note | Records - Permit attached or permit number noted.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1 - Permits & Services (2)
label | 7cd5b1e9-c36c-547f-a3fa-dc3fec06553a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 11423f8e-39da-5773-bd2c-9dd8504a75d1 |  | note | Detail - Locate and mark out all existing services
label | e06cf240-a595-51d5-8239-42848edfa82c |  | note | Frequency - Prior to any construction commencing
label | 22b257c6-9f8a-559e-af02-e7c8f74ca6f0 |  | note | Conformance Criteria - B4u dig procedure - follow utility protocols
label | e62a868f-5874-5b51-9d06-54d774151995 |  | note | Records - B4u dig plans & GPR report attached
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | 9a8ba019-eb5b-51bf-adf5-5b4817d5d0b4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 591aba36-4846-5522-8f01-7a8d66970108 |  | note | Detail - Sub-Contract and Supplier Agreements
label | 18b4a46a-42dc-5b31-ad35-6f24da7eb33b |  | note | Frequency - Prior to commencement.
label | 8e46aae8-8a38-5809-8126-3790d2245274 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 50d159f8-f4f8-57dd-b2c6-a2a313338169 |  | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | 436b3f9a-8071-586c-9518-c23d71b8f424 |  | note | Records - Subcontract and Supplier Agreements
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 4d814cf0-9c57-586f-8cc5-f3690ffe9e6b |  | note | ACTION (Hold, Monitor, Witness) - H
label | ec4be3d7-a54b-5b06-939d-737d6ac04136 |  | note | Detail - Design is approved and Drawings are of the latest revision.
label | 1857180d-696a-5414-82e5-90a7bb088df8 |  | note | Frequency - Prior to commencement.
label | 1c23c984-1f11-5065-8713-a8552db3c08f |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
label | 5ecf5e44-f50b-5de2-8deb-310c907e222c |  | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision.
label | b2c9aa87-15dd-522a-b5f3-37edf5c3d5e1 |  | note | • Drawings to be 'ISSUED FOR CONSTRUCTION' status.
label | cea50518-1c48-5758-8054-93b22874158e |  | note | • HOLD POINT of not issued to IFC.
label | 8f63773b-4a49-52ad-889a-09e4a318d029 |  | note | Records - Drawing Register.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Survey Set out
label | c87a080f-e09f-51ee-ada0-d4d806532dfb |  | note | ACTION (Hold, Monitor, Witness) - H
label | 620ffd51-7466-50ad-9a81-967ac1330a14 |  | note | Detail - Set out Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | 021e4a18-dcd4-527d-bfbb-eff6250257a7 |  | note | Frequency - Prior to commencement.
label | d2ef42eb-5980-55de-87fa-2cff63ff59a6 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
label | 27e8e321-90ba-5d69-9927-2bff79a2fee7 |  | note | Conformance Criteria - As per BlueBarn Engineering Drawings: 02237.17-T-400 & Set out files
label | e006f6c7-9597-5cce-bc1c-bb7f528c52ee |  | note | Records - Survey Receipt.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Pipe and Manhole Material Compliance
label | 2d130bbe-b3f5-5a34-8d92-19e591514178 |  | note | ACTION (Hold, Monitor, Witness) - H
label | da6b54d5-9400-5995-ad3a-6f0b34adfdf2 |  | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | 81ed7602-30aa-5750-b01e-ae6721629dd8 |  | note | Frequency - Prior to commencement.
label | 3191564a-0e3b-5130-a09e-d174a30a2ebf |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review, Visual Inspection
label | 54244494-ee7a-566c-967e-0368d0284ae1 |  | note | Conformance Criteria - Pipe shall be
label | 972dbc5d-f0c6-5099-8808-75a700f3433d |  | note | • Check for freshly formed pipes and return if required
label | 45e00685-7134-5ff4-9437-086077b9bc97 |  | note | 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058
label | 5b9c7d58-2de6-56d6-a72e-4c27ed4b260f |  | note | 2). All Concrete RCRRJ pipes to be fitted with Rubber rings
label | 88b563db-1b60-5a01-8392-fcf0f377ec7c |  | note | 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
label | 97a9680f-7f7a-5a02-a90d-d7a340e4f218 |  | note | Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | 4e8cca62-f77a-5092-ae45-3e960f53d1aa |  | note | Records - Manufacturers Data Sheets, Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | aac41f62-f32a-52d1-941d-1bb991731847 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 97167f8f-6914-55f2-88ee-620ff933ee07 |  | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | 7b5bfb12-b0fb-5db0-a40c-3e10e37f10d1 |  | note | Frequency - Prior to commencement.
label | 077413eb-8617-5567-83ce-ec2559f7e7af |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Potholing / Survey
label | fc0144e0-ad34-5d67-a0bf-a803ed01d150 |  | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | 0a08eef6-0f56-5871-bfbb-a5ec84133a49 |  | note | Records - As-built Drawings. Doc. Review
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | 122ba340-9748-55e9-990f-c13099f45122 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f5b32caa-848e-5070-9aa8-367e1b2ee380 |  | note | Detail - Excavation methodology
label | 607e265e-c6b2-5b90-9696-491980a263a0 |  | note | Frequency - Daily
label | 8d780982-d8c3-5c9f-89c3-265d02f4b6d4 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Prestart review
label | 979b9c0c-60f7-5aea-b3b8-9a470f06dfd7 |  | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | 16c388c9-ee52-573b-b9f5-24d97c8dedcf |  | note | Records - Prestart RCP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation (2)
label | 9c12ded6-63fe-5c01-8869-6f098a12b55c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 34ae6c6d-0894-5384-b6e9-1700cda1f9a5 |  | note | Detail - Trench Profile - Width
label | 9bf6d40d-3f67-5623-bf9c-e7ff09880105 |  | note | Frequency - Daily / as trenching takes place. Different depth methodology
label | 86531590-629f-54c0-a2d3-784fed82eb37 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Excavation methodology
label | 8d0a468c-1b64-5f96-a2f6-68ee2483224f |  | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | dac30131-b0ff-5d98-bb4a-708f6e687a8d |  | note | Records - Construction Photos
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation (3)
label | ce1df771-04fb-59d5-8ae3-be9897d8ba9c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5a91fda8-df67-5be1-b6ad-b9588ae0a84c |  | note | Detail - Trench Profile - Depth
label | 0afb0c41-2f2f-51d8-88f0-a4a0a30e3083 |  | note | Frequency - Daily / as trenching takes place.
label | 4ade6378-3d57-5cfd-aa38-4b7e826b8097 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Measurement
label | 0e6a44bd-67cb-53a0-9018-a2016dce9596 |  | note | Conformance Criteria - Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | c2c9a6b0-d3ac-560f-8c0a-1a5b31a6b6a8 |  | note | Records - FH Drainage Line Record / Construction Photos
checkpoint-status |  |  | checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | 6aec941a-c42b-5f0d-b9e7-667839a42467 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 66c90076-1126-5dd0-8c1c-a1be97900974 |  | note | Detail - Placing and compaction of Bedding Material.
label | 96c0a495-0b68-5e4b-9d65-8b27d7ce9418 |  | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
label | 4dbcbfd2-9df9-5a9e-a93b-d460f064d129 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | e76a0a15-7b9c-5ad8-923f-584ead095ead |  | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | 7a60dea9-2744-52bc-9689-0c52b191e137 |  | note | Records - FH Drainage Line Record / Construction Photos
checkpoint-status |  |  | checkpoint | 9 - Pipe Position Tolerance
label | 54339542-6acf-52dd-ab0b-0339687ca06f |  | note | ACTION (Hold, Monitor, Witness) - M
label | d6e69034-509e-5787-9eb5-03f73e3f0ba8 |  | note | Frequency - At any point of pipe
label | 80201d0d-b6c0-59cb-8ba0-40ae97dce7b0 |  | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
label | 2a5f1f5a-1cd7-5c37-b206-fa8d88ff3eeb |  | note | Records - FH Drainage Line Record, Survey Data.
checkpoint-status |  |  | checkpoint | 10 - Trench Backfill - Placing & Compacting
label | 7230837d-eb03-5aaf-8c40-29ec79191f9c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 4a2fdd52-7426-5a4c-a349-5d06052e8341 |  | note | Detail - Placing and compacting of Trench Backfill Material
label | cdb0cccb-62bc-5225-9b3f-93e11b25b32e |  | note | Frequency - Throughout Trench Backfilling operation.
label | 5b28714a-b3ec-50bd-a531-4bc06dc58ee7 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
label | 909bb25a-b6e5-5c77-8bc4-d5598936875b |  | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | 993d5ba0-7aad-507b-982b-76b2a53cbdac |  | note | Records - Construction Photos
checkpoint-status |  |  | checkpoint | 11 - As-Built Drawings
label | e94ba7b0-e7ed-5ba6-99fb-f56e6f0d737a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 197616ef-4770-5cdb-a580-0812ac8bcbe4 |  | note | Detail - Red pen marked-up As-Built of every 'Issued for Construction' AT drawings
label | e1a502cf-f400-5493-8f00-b075d12d0491 |  | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | 8178030a-ab43-50af-b832-37ee8d806382 |  | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings / Visual Inspection
label | a5ccfc48-43ea-536b-a699-ade058443589 |  | note | Conformance Criteria - As Built and GIS Data
label | 52c6e871-460b-580b-a55e-1e8c7013c0d9 |  | note | Records - Redline As-Built Drawings, scanned as .pdf files.
checklist-sectioned |  |  | checklist | ITP - Enabling Works - Footpath, Kerb and Channel | itp |  |  |  | Yes | Portland Road - ITP - Enabling Works - Footpath, Kerb and Channel | fcdc189f-a663-487c-b749-ab79d0e983a3
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 Site Set out
label | 6ba67fd0-fcf0-43e3-bdcc-ac4ef83dc0da |  | note | VERIFICATION ACTIVITY: Surveyor
label | 1de5edcb-f93a-4490-9798-269251836005 |  | note | METHODS OR REFERENCE: Surveyor
label | 0a184a6a-d6e9-49ee-be8e-f1f8afa340ff |  | note | FREQUENCY: Everysite
label | 6d483f4f-7c63-49d8-83dc-eaf5cbf10da7 |  | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
label | c90f04c8-92d0-4ca7-bb56-50c5250d21f0 |  | note | Hold Point: Mandatory HOLD POINT -
label | e1bc6caf-bf93-464b-a570-95575463b298 |  | note | Records: Onsite records/photos
label | f3428d77-5b9a-4921-865d-b9b8c520ab9d |  | note | Onsite Responsibility: Site Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 1 Kerb & Channel
label | e8631064-92fd-4a6b-acaa-f885fc11f8b8 |  | note | VERIFICATION ACTIVITY: QA FORM
label | e3ec6c60-83bd-4b18-ac0a-a539ed188ed8 |  | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | 2a845afd-fbc3-4e46-befd-3a4215066a1c |  | note | FREQUENCY: Everysite
label | 23969383-05b9-478c-8d61-ca12e4be6e1a |  | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. . Kerbing laid on 300mm min Gap 65 subbase in roads and 100mm GAP 40 in footpaths (CBR>5).Concrete 20mpa @28 Days
label | 1a229d3a-9bd9-48ba-98c4-7b1186724fb9 |  | note | Hold Point: Inprocess Inspection
label | 74afbda9-9cc4-49dd-a6dc-9e3039ff61d4 |  | note | Records: FH concrete QA sheet, photos. Concrete Plant Docket
label | db00f418-7008-4882-8a2d-fd7f3d2a22d7 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 2 Channel Level
label | 32a1bd74-6845-44b4-ad5f-fc336e207cd3 |  | note | VERIFICATION ACTIVITY: QA FORM
label | e52a614c-f8ab-49b3-934c-59d387be3679 |  | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | 27e4280a-8897-4e8d-b18f-b823294f0db6 |  | note | FREQUENCY: Everysite
label | 16d28bc4-1a4e-4472-9b02-afa037a494af |  | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | 246a92b5-6d96-447f-94dc-0fb98611f771 |  | note | Hold Point: Inprocess Inspection
label | d14acd82-cdc5-422e-b06a-04dcde86d64d |  | note | Records: FH concrete QA sheet
label | 4d7d156f-c039-4060-81db-4dac1f4a50fe |  | note | Onsite Responsibility: Site Engineer
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 3 Asphaltic Footpaths
label | 24dded84-4a27-433d-a1b5-688e0fde4024 |  | note | VERIFICATION ACTIVITY: QA FORM
label | 091a2f99-f6b9-4f8a-a5e4-0b7b3d4f29e6 |  | note | METHODS OR REFERENCE: TDM Technical Standards - FP0003
label | 0928d2e6-a294-4285-b19b-1effaa7f3a89 |  | note | FREQUENCY: 10m Intervals
label | 0a85d0de-da51-4cdd-859c-14148ff40fac |  | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3) Basecourse - 150mmmin. thickness of GAP 40 Clegg CIV > 15 Surfacing - 25mm MIX 10 (TNZ-M/10 SPEC BLACK ASPHALTIC CONCRETE) . 2% to 3% max. fall to carriageway.
label | eee93390-f3e5-46cd-8a39-dfb05cfe6d60 |  | note | Hold Point: Inprocess Inspection
label | 9a662980-3254-41c2-b246-eaa5def7d9ef |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 3c7000e1-8057-4c52-b319-945619754bd9 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 4 Pram Crossings (PX)
label | b9bd9624-fa73-4eed-9a17-610550781a03 |  | note | VERIFICATION ACTIVITY: QA FORM
label | 3c4f5a57-13cd-4c54-b1a5-cdc856f40d57 |  | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006
label | 3627dc7b-53cb-4973-ada1-bee0f7027cdb |  | note | FREQUENCY: Each PX
label | 2acead64-00c0-4e6f-aa82-964c852a42a3 |  | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3) Basecourse - 150mmmin. thickness of GAP 40 Clegg CIV > 15 Surfacing - 25mm MIX 10 (TNZ-M/10 SPEC BLACK ASPHALTIC CONCRETE) . 2% to 3% max. fall to carriageway.
label | 8b40f33d-aa21-44a2-b73d-7b270d3bfa78 |  | note | Hold Point: Inprocess Inspection
label | a8eacb49-4e88-4431-9a17-8171f9bc348d |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 83e7bb98-fde9-483a-b2b5-e81c9a8daf6c |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 5 Grass Berms
label | dbd10f7f-782e-4693-89a9-ac511bad94c6 |  | note | VERIFICATION ACTIVITY: Visual
label | 91e99469-84b4-49fc-83b8-ffaca0411950 |  | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
label | ab1ac7d3-3c92-419d-ad86-049c2952849c |  | note | FREQUENCY: 10m Intervals
label | 0f7f4bf4-d3fa-47a7-b873-ae09682d7da2 |  | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | 13a7feff-1405-47ae-9e41-8ccf1e337970 |  | note | Hold Point: Inprocess Inspection
label | 41d93eae-647a-4395-aa57-9a1947c4eb5d |  | note | Records: Photos
label | c2bd0d00-2c30-44a3-90a9-636a84466e28 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6 Tactiles
label | a531284a-a145-4afb-88f8-6d3a0c07239b |  | note | VERIFICATION ACTIVITY: Visual
label | 1765b4f4-aa4e-4f73-9277-ee68ef7bd77b |  | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians; AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 8d5787d1-4ded-4ab0-b7f7-1909b6eeb3f1 |  | note | FREQUENCY: Everysite
label | 80684a7e-5421-4d7d-8183-99b521e79724 |  | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | 8c52c2cb-6b52-4ee9-8506-81a7cc901c99 |  | note | Hold Point: Inprocess Inspection
label | 13fca5cb-5164-4d1f-9058-d13865c122d4 |  | note | Records: Photos
label | c687bd6c-e374-420d-ab19-54ed6d343faa |  | note | Onsite Responsibility: Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 7 As built information
label | 35c3599d-ff5b-429c-97ef-6b5b927d2c33 |  | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | ec811bfb-ef07-46ba-984b-9f2eecd5824f |  | note | FREQUENCY: Every Site
label | 39da1f8e-0951-4cda-ab9f-5e63d4057190 |  | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | 7e627da2-7a5b-4566-ac21-6fb6568be03b |  | note | Hold Point: In Process Inspection
label | bd5215ab-23a6-4167-8cf3-1d96c42ac378 |  | note | Records: Asbuilt records
label | 85e891f2-7ed9-4b1b-9a47-f5b00e62bbec |  | note | Onsite Responsibility: Supervisor and Engineer
checklist-sectioned |  |  | checklist | Roundabout |  |  |  |  | Yes | Halsey/Maich RAB - ITP - Roundabout | fce87690-771a-4f22-ba9f-0c2c3fbef255
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | fb0e7618-0e7c-5957-9bd5-52231192561a |  | note | VERIFICATION ACTIVITY - Survey
label | 6a808e75-ff15-5e99-8d45-9c64caeaa1bd |  | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
label | 0008a52c-765b-5281-96da-9c59e7fc04a1 |  | note | FREQUENCY - Prior to commencement.
label | 27b5e7a5-995d-5e61-ada9-227c1c780be8 |  | note | ACCEPTANCE CRITERIA - Survey
label | 62a04765-95af-5511-994b-ae454acfcabf |  | note | Hold Point - As per Drawings
label | 5ebf8eab-edda-5424-b0c2-02f1df0cdc38 |  | note | Records - Survey Receipt.
label | b2dca72f-2555-56ac-8c85-1b6ec0e8b0c1 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 2 - Concrete Roundabout - Central Island
label | 5e76a7ba-c2c6-53dc-8665-a033f3389265 |  | note | VERIFICATION ACTIVITY - QA FORM/ Drawings
label | a111c3b4-897d-56b7-bc6f-9a3272ce4ecd |  | note | METHODS OR REFERENCE - Construction Drawings
label | b45f3b68-a473-5c1a-96c8-01ebe6cefa3e |  | note | FREQUENCY - Each Site
label | af730fb9-6a41-5c0a-9cc7-7f85d4e544b2 |  | note | ACCEPTANCE CRITERIA - Standard precast kerb to be hand-laid with 120mm reveal. Diameter to varies across with 2% cross fall.Kerbs to be sitted on 300mm Min AP40 Sub Basecourse, with CBR>5
label | a96e8f21-0a6b-51cc-a2c3-d14add6d7307 |  | note | • Central island to have 150mm GAP 65 Granular base course on removed pavement surface.
label | d10ca27c-6e9e-505f-8277-a120b460dee7 |  | note | Hold Point - Inprocess Inspection
label | 4527f6c7-8b50-5d99-a511-1f5b27c5f0e6 |  | note | Records - Photos
label | bea27791-3972-58c4-933b-7978220201f9 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 3 - Concrete Infill - Central Island
label | aee87e25-8e84-5448-83c4-6ca695fad09f |  | note | VERIFICATION ACTIVITY - QA FORM
label | 544edd09-b55e-5e32-baae-d0b3e15ca645 |  | note | METHODS OR REFERENCE - Construction Drawings
label | 48134a99-a430-5a44-9d22-cb4e06b05cf1 |  | note | FREQUENCY - Each Site
label | fab51903-afff-5266-85cf-051737fd6beb |  | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa Unreinforced Concrete with 3kg/m3 red oxide and Broom Finish
label | 56144e23-6785-5688-abd9-eb25b305bba0 |  | note | Hold Point - Inprocess Inspection
label | fd155c9f-bc21-513b-ba51-036ec0d014d5 |  | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 3a43ecaf-1155-5032-9c8d-5229d7f13996 |  | note | Onsite Responsibility - Site Engineer
checkpoint-status |  |  | checkpoint | 4 - Apron
label | 7950cc02-be0d-5c2c-b126-a79b0da7de2b |  | note | VERIFICATION ACTIVITY - QA FORM/ Drawings, Concrete Dockets
label | 2578ec58-4ad0-5c88-9df7-83ec1ff80509 |  | note | METHODS OR REFERENCE - Construction Drawings, TDM Technical Standards - IS0007
label | 25ef7c9f-7617-5a32-9cad-532c11d8b497 |  | note | FREQUENCY - Each Site
label | ad5a2140-f059-5bab-95da-121690853615 |  | note | ACCEPTANCE CRITERIA - Slip formed 25Mpa fibre reinforced concrete for roundabout edging
label | c252335b-2da7-5a1c-9695-962e5070e053 |  | note | • Kerbs to be sitted on 300mm Min AP40 Sub Basecourse, with CBR>5
label | 5f6ae2b5-2f02-5a78-b1d0-e412978f1956 |  | note | • Apron to have 2% min fall towards the road and 2 m wide throughout.
label | 75acfb11-b5c6-5744-979c-309d44ac2f6f |  | note | • Apron to have 50mm thick AC14 HF with 0.25mm Polythene layer on top below concrete
label | 6873123c-0f47-51b7-b24d-afd2d44ee9d1 |  | note | • 195mm depth of 40 Mpa concrete with 4kg/m3 Black oxide and Broom Finish
label | 2619e4c7-72d9-54c4-b460-101196e98985 |  | note | Hold Point - Inprocess Inspection
label | 78719144-3af2-57e3-ad57-668786c6bd64 |  | note | Records - Photos of smart level/ Asbuilts, FH concrete QA sheet. Concrete delivery Dockets kept as record
label | f07d34a8-d111-5c8b-82f0-437797912cb6 |  | note | Onsite Responsibility - Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 7 - As built information
label | 7c451498-a4f3-50fe-b462-a3298708ce48 |  | note | VERIFICATION ACTIVITY - Drawings
label | c092b679-93e3-55f7-b520-89b7cef67f26 |  | note | FREQUENCY - Every Site
label | 7c0f1602-9c87-5561-af4b-0986287bdf9f |  | note | ACCEPTANCE CRITERIA - As built drawings
label | cf3f2bf2-529a-58f8-8819-e3fbce9a6e33 |  | note | Hold Point - In Process Inspection
label | 9460e910-01b8-55d8-b768-53085a21b464 |  | note | Records - Asbuilt records
label | 575ccb70-5b86-553d-b89a-7359a8c836ff |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-status |  |  | checkpoint | 7 - RAMM DATA
label | 1e81e83a-dd8c-5fd5-9ba6-05443850a755 |  | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
label | 98d26b5b-f20f-5520-8c38-468db235c8d5 |  | note | FREQUENCY - Every Site
label | 303e1a7f-d0c7-5f9d-aee6-02b3d898c9f0 |  | note | ACCEPTANCE CRITERIA - RAMM SHEET
label | aabb14b1-90b5-5f88-96a1-826170b309f0 |  | note | Hold Point - In Process Inspection
label | 098c5713-7671-507b-8fbf-a6f09312139b |  | note | Records - Asbuilt records
label | dbf802a0-0ada-570d-a138-720ee409b3c9 |  | note | Onsite Responsibility - Supervisor and Engineer
checkpoint-group |  |  | section | ITP APPROVAL
checkpoint-no-status |  |  | checkpoint | ITP Approval
label | ee86fe3c-8f20-52d3-9996-e8037f3ae674 |  | note | Prepared by: Cimyona (4/02/2022)
label | 3f0abf8c-3dd2-551f-b22f-962da9981e16 |  | note | Approving Delegate: Daniel Tat (4/02/2022)
checklist-sectioned |  |  | checklist | ITP - Enabling Works - Footpath + Pram |  |  |  |  | Yes | Stancombe Road - ITP - Enabling Works - Footpath + Pram | fd266961-f4e5-455c-b9ed-41246d7afede
checkpoint-group |  |  | section | Site Set Out
checkpoint-status |  |  | checkpoint | 1 Site Set out
label | 1e4c7a14-897a-434e-9c71-20fb4d22f547 |  | note | VERIFICATION ACTIVITY: Surveyor
label | 4d8d0429-5f81-4700-af48-172db9507f85 |  | note | METHODS OR REFERENCE: Surveyor
label | 5c570415-51dd-4201-9f26-bdd0b2e3e290 |  | note | FREQUENCY: Every site
label | 14368743-6dda-4527-bf63-000cd6c5e5c8 |  | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | 4016eb69-5169-450a-a865-e9366d9fa180 |  | note | Hold Point: Mandatory HOLD POINT -
label | a75b5c4f-7cfe-41bc-821b-4e08372710c7 |  | note | Records: Onsite records/photos
label | c6456509-200b-4d96-a063-6629414d328e |  | note | Onsite Responsibility: Site Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 2 Concrete Footpaths
label | e16459ac-9503-47f9-916c-6c93334ca53f |  | note | VERIFICATION ACTIVITY: QA FORM
label | 57fafe55-a8eb-4e07-ba39-725bec2f9483 |  | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | 5074c38e-486d-4335-b700-f32e40b91340 |  | note | FREQUENCY: 10m Intervals
label | 37ed3d3b-3696-4c2e-9cd1-247ac09bc27f |  | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3.5); Subbase - 150mm min. thickness of GAP65. ; Basecourse - 100mm thick AP40; Clegg CIV > 15; Surfacing - Concrete 150mm and 20 Mpa @ 28 days. 4kg/m3 blackoxide with broom finish
label | d41d7e97-c286-4da4-9cac-b5be67578822 |  | note | Hold Point: Inprocess Inspection
label | 9d2bbd0c-4348-4144-b269-2b29231451f5 |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 511ce254-c572-4dfd-819d-fa2c91e89758 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.1
label | fe62006c-ae45-4b1d-98cb-1f70fc028fb4 |  | note | VERIFICATION ACTIVITY: Visual
label | 6f80c284-eea0-45a3-b382-28abb9255f26 |  | note | METHODS OR REFERENCE: Drawing No: 2020-AT-006-03_G035 - SECTION A -G020
label | 26164d12-8455-4a8b-a71a-1176cf2571c6 |  | note | ACCEPTANCE CRITERIA: Topsoil and grass on either side of the footpath section A - G020 with 1.5% gradient.
label | 9bf6d0b2-734a-4449-b372-14065b0386bd |  | note | Hold Point: Inprocess Inspection
label | c462bc1d-989f-4c71-aac8-d1384d13b2db |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 44e328ca-672b-45cc-a300-f556c94711b3 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 3.2
label | 90b67476-ec41-48d7-b550-890d5174e94a |  | note | VERIFICATION ACTIVITY: Visual
label | 1d00f7ff-5354-4837-b324-4215b767bd21 |  | note | METHODS OR REFERENCE: Drawing No: 2020-AT-006-03_G035 - SECTION B -G020
label | 97668250-00f2-4526-a326-0b97b2fd054b |  | note | ACCEPTANCE CRITERIA: 250mm mean diameter basalt rocks on either side of footpath under Section B - G020 with 1:2 gradient
label | 60fe3450-22be-43a1-af5a-85f4d65c577e |  | note | Hold Point: Inprocess Inspection
label | fdf4e0d9-432c-41ce-b734-537da79e88df |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 36512a32-3bcc-44cc-ab50-e03d4a666e20 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 4 Concrete Pram Crossings (PX)
label | aacbc74b-fd5f-409c-8473-01e50537e088 |  | note | VERIFICATION ACTIVITY: QA FORM
label | e8f08555-8ce5-4808-b3d1-de5207dcfb07 |  | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006
label | a2993241-a291-4c72-b8ef-b57b547324f7 |  | note | FREQUENCY: Each PX
label | 14f3c499-31e4-4cd7-98f2-861a96bbbb1f |  | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3); Basecourse - 100mm min. GAP40 thickness; Clegg CIV > 15; Surfacing - Concrete 150mm and 20 Mpa @ 28 days. 4kg/m3 blackoxide with broom finish
label | 49f61d85-4a51-4c8d-8307-d7bee29e0719 |  | note | Hold Point: Inprocess Inspection
label | 6c4895f6-b719-4f31-8ce1-946c0054d431 |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 43a2063e-4a27-4d63-a42a-fcb5bdb39940 |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 5
label | b9bd6769-9071-4fee-acc6-784fe47f6188 |  | note | VERIFICATION ACTIVITY: QA FORM
label | 36c24408-48b0-41d7-9d3e-121a07e514cd |  | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006
label | 6ed89e3e-6bae-4c47-b4cf-6cd66e8e2b8a |  | note | FREQUENCY: Each PX
label | 797dc9b8-9a20-4c33-ba24-0fc4bf5384cf |  | note | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 100mm concrete slab underneath
label | 09dfb963-c81f-4027-baf1-97db48909fca |  | note | Hold Point: Inprocess Inspection, Measurement
label | d1a2031b-b543-4be7-834b-e0575c7f5b6b |  | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | 99e906c4-4135-4176-a681-0d27c812eefa |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6 Tactiles
label | 8605d9d7-f4c3-43bf-b2e3-d17a2ef98f67 |  | note | VERIFICATION ACTIVITY: Visual
label | 51aa71cc-9b7e-4ed6-8aad-e8bfb3d54ffc |  | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians; AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | cfa6abd6-ccf9-437d-8962-515a593e192b |  | note | FREQUENCY: Everysite
label | ab55a1b1-e7b5-4fa3-a935-084c1b37c699 |  | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | 8e2357c8-b463-40b3-a6cf-3b2ad564b9bd |  | note | Hold Point: Inprocess Inspection
label | ff80715e-43e7-49d9-aeaf-9019ef60bed6 |  | note | Records: Photos
label | 88a3fb32-d059-452d-9960-fcb777024dbc |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6.1
label | 819757d4-083f-4f9f-b8a7-7fb78f451b7e |  | note | VERIFICATION ACTIVITY: Visual
label | b56fc4f0-8a44-4c1d-b2d9-62ae7971019b |  | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 2b4c4055-c3ed-45bb-b113-7a4927abc638 |  | note | FREQUENCY: Everysite
label | 23d25f60-f9d7-4346-99eb-15358ab9e91c |  | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | d438d1d1-c997-42ef-b86f-82a1efaf2c4d |  | note | Hold Point: Inprocess Inspection
label | 000eb175-2480-438c-ba08-16a3b1703fc7 |  | note | Records: Photos
label | 840c32e4-c731-4a8b-98b2-3f44a2f961bd |  | note | Onsite Responsibility: Site Engineer
checkpoint-status |  |  | checkpoint | 6.2
label | fa45484e-b77f-4fe6-96e3-77430e0a4d03 |  | note | VERIFICATION ACTIVITY: Visual
label | 7873e08e-28a3-42cb-84bd-a5a7a378e261 |  | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | 6381ba2c-5f91-4547-8294-c21a7d8ed570 |  | note | FREQUENCY: Everysite
label | fdd41caf-64c1-41c0-80fb-f3d0d74a9bda |  | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
label | 0fb4a6a7-62d3-4432-8341-3247354ed01d |  | note | Hold Point: Inprocess Inspection
label | 9efd92e0-aa78-455b-baad-1476b3923ff5 |  | note | Records: Delivery Dockets/Photos
label | c72dcc25-d4fd-4f4d-95d0-a33f1e24b8c1 |  | note | Onsite Responsibility: Site Engineer
checkpoint-group |  |  | section | Asbuilts
checkpoint-status |  |  | checkpoint | 7 As built information
label | cd1c9f24-9924-4987-9521-d1b345bc36c0 |  | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | 9a8e92d4-7a80-43cb-9821-3826d88fc333 |  | note | FREQUENCY: Every Site
label | b4acd19d-99b4-48e8-b872-5aa4bfe30945 |  | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | 9e6650b7-5407-4b68-a0e0-95c6f5be3850 |  | note | Hold Point: In Process Inspection
label | e7071eea-90b1-418b-af17-69e9547ca784 |  | note | Records: Asbuilt records
label | 3a9a001f-70e7-439f-a268-517681984966 |  | note | Onsite Responsibility: Supervisor and Engineer
checklist-flat |  |  | checklist | Stormwater Drainage | itp |  |  |  | Yes | ITP - Griffen Park / Hillsborough Rd - Stormwater Drainage | fde6d96f-8169-4528-81a7-d05a77d59960
checkpoint-status |  |  | checkpoint | 1 - Permits & Services
label | f6f3d7bb-cac7-5076-be67-68f956c83385 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 534fd5d6-69d0-554e-b910-b5c2b2c1f35a |  | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | e207af83-3236-5ce9-b123-cd3204629252 |  | note | Frequency - Prior to any construction commencing
label | 06e35948-cf86-5bbd-b6ac-90b0b662fad0 |  | note | Inspection / Test Method - Document Review
label | 569f6a3b-f70d-54f6-b238-7a2e6ce6dd11 |  | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
label | 1523d8d3-c7e6-58bc-b858-486c05080fc7 |  | note | Records - Permit attached or permit number noted.
label | 93d1d344-ccab-5906-9584-8b692726fd35 |  | note | FH Initials - Site Engineer
label | 2e396cfe-cee0-5c99-ab1c-f7802b51a48b |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 7c0fde4d-7fcc-5661-8a17-3209d513c5fa |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.1 - Permits & Services
label | 573ac577-f997-50b4-8ef9-cc63c1f64208 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8f0f3258-1670-5423-98a5-2751a678aa53 |  | note | Detail - Locate and mark out all existing services
label | 36a580e2-568b-5dbb-8199-3b4db282cf08 |  | note | Frequency - Prior to any construction commencing
label | 5d457417-65d5-53d4-b373-9bba10b2b60b |  | note | Conformance Criteria - B4u dig procedure - follow utility protocols
label | a7cd2493-1da9-5d7a-96f8-de41d30f34cd |  | note | Records - B4u dig plans & GPR report attached
label | a2008a79-919c-5096-b378-e6fd9f9add06 |  | note | FH Initials - Site Engineer
label | 07588169-732a-56e2-a30f-0675e4824e82 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | c4e8d32c-35b9-53ed-bc35-19b340bdb159 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pre-Construction Sign Offs
label | 32d78f6a-97c9-5c6d-b468-de7558c019aa |  | note | ACTION (Hold, Monitor, Witness) - H
label | 08db983c-1888-5e87-9523-808afd0f527f |  | note | Detail - Sub-Contract and Supplier Agreements
label | 6d8fb180-37c8-55ea-bbbe-d83f3ec085dc |  | note | Frequency - Prior to commencement.
label | 6f6f78d5-8880-5c89-94f0-d97abfc95a69 |  | note | Inspection / Test Method - Document Review
label | e8be5a7b-ddbd-5c64-a5eb-31ae5a79fa05 |  | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
label | 4c9a0faa-8b54-5958-b273-2e7ff88a218f |  | note | Records - Subcontract and Supplier Agreements
label | 3b4eafa9-7756-555f-8188-e4e9ca0fafb8 |  | note | FH Initials - Site Engineer
label | e3fda1d2-6a86-5199-9db4-cad566717398 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 917ce5b0-e2b5-5499-a04c-186d3b4f9c46 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Design
label | 4ad37f39-4b2b-5e0a-af27-0f758177aa92 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7db3fddd-30fe-5bc2-9c2e-bc320294f06c |  | note | Detail - Design is approved and Drawings are of the latest revision.
label | c3b15ff9-6a20-582e-bb65-2b4e1f1dc8a3 |  | note | Frequency - Prior to commencement.
label | 476256c7-3b46-5a39-827f-7cd132e99aba |  | note | Inspection / Test Method - Document Review
label | da39513a-01a7-5942-8da2-a0c3cc7f2a14 |  | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | 7bad854a-79db-5cf0-a6e6-cd03315a5284 |  | note | Records - Drawing Register.
label | acea18fc-7b7c-5f60-9d7d-9366f7b85105 |  | note | FH Initials - Site Engineer
label | 6f30af95-40a6-5043-bc2b-667b3622ceb2 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Engineers Rep.
text | b0934bc4-71ee-598f-af40-d70028cac3a5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Survey Setout
label | 4dd6f742-bc24-50d0-910c-6bc5d2a19b2c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 43a42e2d-16ed-5255-a60e-c816fcdc9af6 |  | note | Detail - Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | b7770e91-f670-5e0c-83a3-b3567534d59b |  | note | Frequency - Prior to commencement.
label | cc237a79-bf42-5006-a259-2deb9ce34b00 |  | note | Inspection / Test Method - Survey
label | 5812b88a-17f1-5cdd-806b-1137015ef340 |  | note | Conformance Criteria - As per Beca Engineering Drawings: Setout files
label | e8be8019-4799-54d5-b281-a807c5f9b421 |  | note | Records - Survey Receipt.
label | 2fd08296-db22-5caf-b501-40baa38aadce |  | note | FH Initials - Site Engineer
label | b65d8c1f-2101-5f68-a476-de4f2c5be225 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 91f99d6d-9934-521e-a05b-6320983ab6e2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Pipe and Manhole Material Compliance
label | 492b7202-4526-52ae-a458-9e4b7ad73fa0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 39fe7d61-5053-5b0b-a806-991d79c8a437 |  | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
label | 556fb5b3-3f68-5d8f-812f-5d97b0edc695 |  | note | Frequency - Prior to commencement.
label | 40b5fd14-50be-5366-b428-d664276085fe |  | note | Inspection / Test Method - Document Review, Visual Inspection
label | 16882568-b173-5ba8-8f3c-c0d7cccefdef |  | note | Conformance Criteria - Pipe shall be Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
label | 03ccc8b6-d69f-51af-b9b2-d00a81cbeb1b |  | note | Records - Manufacturers Data Sheets, Delivery Dockets
label | a13c221c-b22f-566c-9b20-55370572c78f |  | note | FH Initials - Site Engineer
label | 4577469a-d34a-5af5-8a99-b54e3c0ef544 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | c225aead-fad2-5612-8762-8f369065874c |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | f72b28b2-d963-51cf-9646-943ffe61d225 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a91648a3-e431-5911-be83-177cdf8a4b7b |  | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | 09243b8a-2482-5077-8b1f-f3b780789f4c |  | note | Frequency - Prior to commencement.
label | 94586221-1597-53df-ba5b-ddf2a8306c91 |  | note | Inspection / Test Method - Potholing / Survey
label | 178fa21b-ca79-5611-9538-aa171eb49c5f |  | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
label | c66ed31d-2b41-569e-ad2e-e4a74d460403 |  | note | Records - As-built Drawings. Doc. Review
label | fbf06b21-c28e-595a-a936-d30cdb984e6c |  | note | FH Initials - Site Engineer
label | 7f4a4ebc-f197-57de-b065-221a07ca5760 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | a0cfdcb6-509f-5f3c-961a-45b553cb408f |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | aa691113-1663-533d-b327-fb77fba8d19c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 82823301-bf3f-5233-a475-ca6dd2bb4542 |  | note | Detail - Excavation methodology
label | e312fa65-c96c-59d0-a71d-48d10903621b |  | note | Frequency - Daily
label | 3c065082-8abc-5a66-85cb-6267dda079e2 |  | note | Inspection / Test Method - Pre Start review
label | 968d0340-b4ec-5bbc-ab1d-a3a0a6fc0911 |  | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
label | 959e0175-a77f-55ac-8485-3e54aff69888 |  | note | Records - Pre Start RCP
label | 28af99d4-429e-5397-a4ac-fcbbcc1aec9f |  | note | FH Initials - Site Engineer
label | b5aad2e8-ba9d-54ea-acfa-20775e7aa00b |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 776d15a3-7a90-5224-8274-36dd06f75b51 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | 1bf85918-efcc-5d18-ab68-584eba68fce3 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 2a1c2112-5f09-56da-b129-63bd2d16316e |  | note | Detail - Trench Profile - Width
label | 43832bf7-9236-56d4-b306-2573f68672c9 |  | note | Frequency - Daily / as trenching takes place. Different depth methodology
label | 23b9fbff-03d5-5af7-b27b-78a7a69ef196 |  | note | Inspection / Test Method - Visual Inspection, Excavation methodology
label | 422523b5-dfe9-5a38-a184-22c0534d7949 |  | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | 8ee9fc43-dafc-572d-89e4-23e8523a0e8b |  | note | Records - Construction Photos
label | 1e36d163-f0be-5a33-b9a3-f1bd0246b5b6 |  | note | FH Initials - Site Engineer
label | 911576bc-d62b-5328-8ee6-813874fee6b9 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 78615c3b-cc7c-592e-9075-7d1b85ffeaa1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Trenching & Excavation
label | af795caa-c4ce-59db-902d-a03281d9e5b8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e0c4426b-8c3d-5b73-bebc-8607403a293f |  | note | Detail - Trench Profile - Depth
label | 24db5940-b95e-5110-8659-611d205208e1 |  | note | Frequency - Daily / as trenching takes place.
label | f943fb4f-0e0f-5989-8338-963a873339ee |  | note | Inspection / Test Method - Visual Inspection, Measurement
label | e9321a89-b4cd-5e9b-8e97-444453b39301 |  | note | Conformance Criteria - Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | 16d629df-5ed3-5626-8582-fd07d2232bfa |  | note | Records - FH Drainage Line Record / Construction Photos
label | 1ad7b30b-8b91-5b6c-af85-e08cab6e774f |  | note | FH Initials - Site Engineer
label | a2a5ed65-5b5d-566a-b23b-fe69bd755669 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 66b91866-b8d7-5361-a631-0c8a41496c51 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | 5d509f6d-9d98-58ba-98d3-cbf387d83fb0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8dbf8c72-4e2d-5f15-adf6-f117050c0b66 |  | note | Detail - Placing and compaction of Bedding Material.
label | db3ba749-ecd2-58df-ab48-0631077b8d96 |  | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
label | 050558c3-dc9c-53d4-91c4-b75c826526c4 |  | note | Inspection / Test Method - Visual Inspection
label | f08feebd-0095-5ad9-b4a9-d40229817233 |  | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
label | 3c75bcd7-25ab-5330-9d9b-f2982b55e79f |  | note | Records - FH Drainage Line Record / Construction Photos
label | b4508696-60d0-5109-8961-eef8356f8ca5 |  | note | FH Initials - Site Engineer
label | ef482a7e-986b-5f30-8aea-1dd113996441 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | e23ce1b4-7532-5679-81ed-679775b28985 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9 - Pipe Position Tolerance
label | 21aab0b4-ecdc-5979-8bd7-6d36214f8f90 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 7b247627-2056-5c93-9ad5-0e72603f9820 |  | note | Detail -
label | b446897c-9174-5e25-b5e2-690bcd4933b3 |  | note | Frequency - At any point of pipe
label | 548a8c36-3d7f-55ce-a350-bb0b88ff39a8 |  | note | Inspection / Test Method -
label | 7b6fd6a6-87e7-5b55-b9d7-e9057c04328d |  | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
label | 198c14c6-895d-5cc2-bbf8-8bc5d61cd46f |  | note | Records - FH Drainage Line Record, Survey Data.
label | 2e8fad5f-c02d-5996-8db1-848bc2b52e8f |  | note | FH Initials - Site Engineer
label | a2976253-0347-59e1-8305-59390f802cce |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | a30bf56b-0352-5994-a2f7-0387dc0b798e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10 - Trench Backfill - Placing & Compacting
label | d857dda6-0c89-5622-871b-d9835b4b7e83 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 830b8234-fe9b-5063-b7fa-a7c8ec453ab0 |  | note | Detail - Placing and compacting of Trench Backfill Material
label | 66719542-5fe3-5ebe-a37d-47d8eb2452a2 |  | note | Frequency - Throughout Trench Backfilling operation.
label | 23f44e5f-3a25-58cf-9e77-9c578dd74bfb |  | note | Inspection / Test Method - Visual Inspection
label | ba05e284-4a1f-56b7-8e78-7991d502fa72 |  | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | 7917b3a1-04a4-51ff-a24e-5a883e91ffd9 |  | note | Records - Construction Photos
label | 74a33021-ae9c-5d9b-be5c-5b6b6c4f945b |  | note | FH Initials - Site Engineer
label | 31854e68-e949-569c-adbc-782ed1a676c7 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
text | 0e14e433-22e3-54c4-b33b-837c200abc7a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 11 - As-Built Drawings
label | 30a553e0-9496-5671-827f-bc7c3b8dda2e |  | note | ACTION (Hold, Monitor, Witness) - W
label | 58c1af22-f92f-5d10-be6d-4bd82cd84247 |  | note | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
label | 7e0193ce-0dfa-5f0b-9d74-c04a603f730d |  | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | 2e6097b3-d02d-5c35-b71b-8a7726c94ec7 |  | note | Inspection / Test Method - Drawings / Visual Inspection
label | 558da3f4-3bd3-5a7e-af1b-93006a61d267 |  | note | Conformance Criteria - As Built and GIS Data
label | 32703fb6-db9c-56c6-ac7c-00f84ab854a2 |  | note | Records - Redline As-Built Drawings, scanned as .pdf files.
label | 5d45afd9-1c2a-5cef-b828-db39a03e2a8c |  | note | FH Initials - Site Engineer
label | 2de70484-c626-5906-be94-013552eb50a9 |  | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Engineers Rep.
text | 22c76171-6162-5d86-81de-5744632dc1f9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 9aab3715-b8d0-59ea-a4f5-deccc9e8aabc |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | a5e2cf1c-d4f1-5cad-bbbd-b0708f98f3c3 |  | textbox | Print Name:
text | ef500c46-a20b-5cdc-9b7d-5188ec878ae8 |  | textbox | Position:
text | b158c023-ee2d-5668-a470-1cc8ec8898b1 |  | textbox | Date: