## Civil Works
ITP - Raleigh Road Bus Lane
Civil Works
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Survey - Set out
1 | Site Set out | Surveyor | Surveyor | Everysite | Site Set out as per construction plan provided with GPS location and 2D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable. | Inprocess Inspection | Onsite records/photos | Site Engineer
Kerb and Channel
2 | Kerb & Channel | QA FORM | TDM Technical Standards - KC0001 | Everysite | Kerb & Channel to be laid using precast hand-laid on compacted minimum 300mm GAP65 sub base with CIV > 25. Concrete 20MPa @28 Days | Inprocess Inspection | Clegg Sheet, photos. Concrete Plant Docket | Site Engineer
3 | Channel Level | QA FORM | TDM Technical Standards - KC0001 | Everysite | Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set. Channel to be trowel finish. | Inprocess Inspection | FH channel QA sheet/photos | Site Engineer
Footpath & Pram Crossing
4 | Concrete Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m Intervals | Basecourse - 100mm Gap40 min. thickness Clegg CIV > 12 (frequency every 3m or minimum 4 spots per pour - excluding PX) Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish | Inprocess Inspection | Clegg Sheet, photos. Concrete Plant Docket | Site Engineer
5 | Pram Crossing | QA FORM | TDM Technical Standards - FP006 | Each Crossing | Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. Tactiles Directional & warning - 40mm; 600mm flares;width as per design; Slope no greater than 1:12 where practicably possible Clegg CIV > 12 | Inprocess Inspection | Photos | Site Engineer
6 | Service Covers and Street Furniture | Visual | AT Contract Specification 14000 | Everysite | Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works. | Inprocess Inspection | Nil | Site Engineer
Tactile indicators
7 | Tactiles | Visual | TDM Technical Standards - FP0010 | Each PX | Tile set out position to be agreed with ATOC and Engineer. Warning TGSI tiles should have 100mm concrete haunching underneath | Inprocess Inspection, Measurement | FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos | Site Engineer
8 |  | Visual | NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Everysite | Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. | Inprocess Inspection | Photos | Site Engineer
9 |  | Visual | AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Everysite | Edge of warning indicators to set back 300mm from the face of the kerb or lane. | Inprocess Inspection | Photos | Site Engineer
Bus Shelter Pads (Minor 1300 & Minor 1500)
10 | Bus Shelter Pads | Visual | "Plumb Consultants" drawings Sheet S01 & S03 as per WSP IFC drawings sheet C121 & C123 revision 1 | Everysite | 50-100mm basecourse. Clegg value acceptance criteria CIV>12. | Inprocess Inspection | Clegg Sheet, photos. Concrete Plant Docket | Site Engineer
11 |  |  |  |  | 200mm thick 20MPa concrete with 4kg/m3 black oxide & broom finish.
12 |  |  |  |  | Minor 1500 - 2 x layers of 665mesh Minor 1300 - 2 x layers of 663 mesh 50mm top cover. 75mm bottom cover.
Retaining Wall
13 | Timber Retaining Wall | Visual | TDM ST0004 - Version A Timber Retaining Wall Detail | Everysite | 125 x 125 H5 Timber Posts @ 1.5m centres installed with 20MPA concrete. Concrete footing to be 325mm diametre. 150 x 50 RS Tanalised H5 Timber Rails. Provide 5-10mm gap between rails Retaining wall slope to be 10:1 grade. Maximum height of wall = 1499mm. Minimum embedded depth of post to be same as exposed height unless less than 300mm, then depth = 300mm. | Inprocess Inspection | Photos Material Dockets Dimension checks | Site Engineer
Grass Berm
14 | Grass Berms | Visual | ATCOP Section 12 Footpaths and Pedestrian Facilities | Everysite | 100mm thick layer of compacted approved quality topsoil, free of weeds and stones and sowed with grass seeds. | Inprocess Inspection | Photos | Site Engineer
Asbuilts
15 | As built information | Drawings |  | Every Site | As built drawings | In Process Inspection | Asbuilt records | Site Engineer & PM
16 | RAMM DATA | RAMM DATA SHEET |  | Every Site | RAMM SHEET | In Process Inspection | RAMM Sheet | Site Engineer & PM
ITP APPROVAL
Prepared By |  | Joseph John | Initial | JJ |  | Date: | 2023-07-12
Approving Delegate |  | Denny Jeong | Initial | DJ |  | Date: | 2023-07-19

## Ducting and Traffic Signals
|  |  |  | ITP |  |  | Approved |  | Signature
|  |  |  | Contract Name: | Raleigh Road Bus Lane |  | FH Engineer |  | Joseph John
|  |  |  | Procedure: | Traffic signal ducting and Pole erection |  | FH Project Engineer |  | Erfan Farahani
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | Traffic signal installation |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
Ducting
1 | Permits | H | Obtain Permits | As required | Document Review | Authorisation to work, dig permit and service provider permits | This ITP signed | Site Engineer
2 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
3.1 | Survey Setout | H | Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor. | Prior to commencement | Survey | Consistency with Drawings and Specifiactions | Survey Records | Site Engineer
3.2 |  | H | Confirm with Engineer/ATOC on site the exact locations of poles/controller/tactiles indicators. | Prior to installation | Visual Inspection | Consistency with Drawings and Specifiactions & sign-off by Engineer/ATOC. | Photos / Engineers approval documentation | Site Engineer
4 | Locate existing services by hand digging/ hydrovac | W | Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation | Prior to Installation | Potholing | All conflicts have been located and survey as built recorded | Digging/Excavating Control Checklist | Site Engineer
5.1 | Material Compliance | H | Ensure duct pipes and poles are as per drawings and specification | Upon delivery to site | Ensure delivery docket matches materials |  | Delivery Docket | Site Engineer
5.2 |  | H | Ensure all concrete used is 20MPa mix for pole footings and concrete aprons around traffic assets. | Upon delivery to site | Ensure delivery docket matches materials |  | Delivery Docket | Site Engineer
6.1 | Trenching | H | Inspect trench profile to ensure walls vertical, widths is 600mm max (two ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm/FP and 900mm cover under carriageway. Concrete capping detail to be followed where reduced cover is required due to existing services. | 10m Intervals | Visual Inspection | Consistency with Drawings and Specifiactions. Concrete capping detail - WSP IFC Drawings Sheet C126. | Photos | Site Engineer
6.2 |  | H | Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs | 10m Intervals | Measure | Ensure trench alignment and levels match the design drawings | Dipsheet & Photos | Site Engineer
6.3 |  | H | The trench on the carriageway should be filled with Gap40 and compacted and on top reinstated with AC14 or similar & match existing asphalt thickness. The finished level to be match with existing road level | Eash Site | Visual Inspection | Reinstatement as per designer acceptance | Docket and photos | Site Engineer
7.1 | Duct Installation | W | Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct. | Prior to Installation | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
7.2 |  | H | Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
7.3 |  | H | Asbuilt Survey | 20m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Survey Records | Site Engineer
8 | Bedding | H | Lay min. 100mm gap20 or finer for bedding and haunching | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
9 | Warning Tape | H | Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines. | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
10.1 | Traffic signal pole erection | H | Ensure Design engineer & ATOC inspect pole locations prior to proceeding | Per pole | Visual Inspection | Sign off by design engineer | Engineer sign off
10.2 |  | H | Ensure foundation hole excavation is as per design with required depths and widths | Per pole | Measure | Consistency with Drawings and Specifiactions | Dipsheet & Photos
10.3 |  | H | Ensure Poles are plumb and within design tolerances | Per pole | Visual Inspection | Consistency with Drawings and Specifiactions | Photos
11 | As-builts & C&I Diagram | H | As-built as per ATOC requirements | At the completion of the Lot of work | Drawings | As-built as per ATOC requirements | Asbuilt Drawing | Site Engineer
Comments:
Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Project manager |  |  |  |  | Signature: |  |  | Date:
QA checked By Contract Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design/AT Engineer: |  |  |  |  | Signature: |  |  | Date: