## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Civil Works | itp |  |  |  | Yes | Raleigh Road Bus Lane - ITP - Civil Works
section | Survey - Set out
checkpoint | 1 - Site Set out
note | VERIFICATION ACTIVITY: Surveyor
note | METHODS OR REFERENCE: Surveyor
note | FREQUENCY: Everysite
note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 2D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
note | HOLD POINT: Inprocess Inspection
note | RECORDS: Onsite records/photos
note | ONSITE RESPONSIBILITY: Site Engineer
section | Kerb and Channel
checkpoint | 2 - Kerb & Channel
note | VERIFICATION ACTIVITY: QA FORM
note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
note | FREQUENCY: Everysite
note | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid on compacted minimum 300mm GAP65 sub base with CIV > 25. Concrete 20MPa @28 Days
note | HOLD POINT: Inprocess Inspection
note | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
note | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Channel Level
note | VERIFICATION ACTIVITY: QA FORM
note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
note | FREQUENCY: Everysite
note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set. Channel to be trowel finish.
note | HOLD POINT: Inprocess Inspection
note | RECORDS: FH channel QA sheet/photos
note | ONSITE RESPONSIBILITY: Site Engineer
section | Footpath & Pram Crossing
checkpoint | 4 - Concrete Footpaths
note | VERIFICATION ACTIVITY: QA FORM
note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
note | FREQUENCY: 10m Intervals
note | ACCEPTANCE CRITERIA: Basecourse - 100mm Gap40 min. thickness
note | ○ Clegg CIV > 12 (frequency every 3m or minimum 4 spots per pour - excluding PX)
note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish
note | HOLD POINT: Inprocess Inspection
note | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
note | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Pram Crossing
note | VERIFICATION ACTIVITY: QA FORM
note | METHODS OR REFERENCE: TDM Technical Standards - FP006
note | FREQUENCY: Each Crossing
note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
note | ○ Tactiles Directional & warning - 40mm; 600mm flares;width as per design;
note | ○ Slope no greater than 1:12 where practicably possible
note | ○ Clegg CIV > 12
note | HOLD POINT: Inprocess Inspection
note | RECORDS: Photos
note | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 6 - Service Covers and Street Furniture
note | VERIFICATION ACTIVITY: Visual
note | METHODS OR REFERENCE: AT Contract Specification 14000
note | FREQUENCY: Everysite
note | ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
note | HOLD POINT: Inprocess Inspection
note | RECORDS: Nil
note | ONSITE RESPONSIBILITY: Site Engineer
section | Tactile indicators
checkpoint | 7 - Tactiles
note | VERIFICATION ACTIVITY: Visual
note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
note | FREQUENCY: Each PX
note | ACCEPTANCE CRITERIA: Tile set out position to be agreed with ATOC and Engineer. Warning TGSI tiles should have 100mm concrete haunching underneath
note | HOLD POINT: Inprocess Inspection, Measurement
note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
note | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 8 - Tactiles
note | VERIFICATION ACTIVITY: Visual
note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
note | FREQUENCY: Everysite
note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
note | HOLD POINT: Inprocess Inspection
note | RECORDS: Photos
note | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 9 - Tactiles
note | VERIFICATION ACTIVITY: Visual
note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
note | FREQUENCY: Everysite
note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane.
note | HOLD POINT: Inprocess Inspection
note | RECORDS: Photos
note | ONSITE RESPONSIBILITY: Site Engineer
section | Bus Shelter Pads (Minor 1300 & Minor 1500)
checkpoint | 10 - Bus Shelter Pads
note | VERIFICATION ACTIVITY: Visual
note | METHODS OR REFERENCE: "Plumb Consultants" drawings Sheet S01 & S03 as per WSP IFC drawings sheet C121 & C123 revision 1
note | FREQUENCY: Everysite
note | ACCEPTANCE CRITERIA: 50-100mm basecourse. Clegg value acceptance criteria CIV>12.
note | HOLD POINT: Inprocess Inspection
note | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
note | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 11 - Bus Shelter Pads
note | VERIFICATION ACTIVITY: Visual
note | METHODS OR REFERENCE: "Plumb Consultants" drawings Sheet S01 & S03 as per WSP IFC drawings sheet C121 & C123 revision 1
note | FREQUENCY: Everysite
note | ACCEPTANCE CRITERIA: 200mm thick 20MPa concrete with 4kg/m3 black oxide & broom finish.
note | HOLD POINT: Inprocess Inspection
note | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
note | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 12 - Bus Shelter Pads
note | VERIFICATION ACTIVITY: Visual
note | METHODS OR REFERENCE: "Plumb Consultants" drawings Sheet S01 & S03 as per WSP IFC drawings sheet C121 & C123 revision 1
note | FREQUENCY: Everysite
note | ACCEPTANCE CRITERIA: Minor 1500 - 2 x layers of 665mesh
note | ○ Minor 1300 - 2 x layers of 663 mesh
note | ○ 50mm top cover.
note | ○ 75mm bottom cover.
note | HOLD POINT: Inprocess Inspection
note | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
note | ONSITE RESPONSIBILITY: Site Engineer
section | Retaining Wall
checkpoint | 13 - Timber Retaining Wall
note | VERIFICATION ACTIVITY: Visual
note | METHODS OR REFERENCE: TDM ST0004 - Version A Timber Retaining Wall Detail
note | FREQUENCY: Everysite
note | ACCEPTANCE CRITERIA: 125 x 125 H5 Timber Posts @ 1.5m centres installed with 20MPA concrete. Concrete footing to be 325mm diametre.
note | ○ 150 x 50 RS Tanalised H5 Timber Rails. Provide 5-10mm gap between rails
note | ○ Retaining wall slope to be 10:1 grade.
note | ○ Maximum height of wall = 1499mm.
note | ○ Minimum embedded depth of post to be same as exposed height unless less than 300mm, then depth = 300mm.
note | HOLD POINT: Inprocess Inspection
note | RECORDS: Photos, Material Dockets, Dimension checks
note | ONSITE RESPONSIBILITY: Site Engineer
section | Grass Berm
checkpoint | 14 - Grass Berms
note | VERIFICATION ACTIVITY: Visual
note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
note | FREQUENCY: Everysite
note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones and sowed with grass seeds.
note | HOLD POINT: Inprocess Inspection
note | RECORDS: Photos
note | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 15 - As built information
note | VERIFICATION ACTIVITY: Drawings
note | FREQUENCY: Every Site
note | ACCEPTANCE CRITERIA: As built drawings
note | HOLD POINT: In Process Inspection
note | RECORDS: Asbuilt records
note | ONSITE RESPONSIBILITY: Site Engineer & PM
checkpoint | 16 - RAMM DATA
note | VERIFICATION ACTIVITY: RAMM DATA SHEET
note | FREQUENCY: Every Site
note | ACCEPTANCE CRITERIA: RAMM SHEET
note | HOLD POINT: In Process Inspection
note | RECORDS: RAMM Sheet
note | ONSITE RESPONSIBILITY: Site Engineer & PM
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Joseph John
note | Approving Delegate: Denny Jeong
checklist-flat | ITP - Traffic Signal Ducting and Pole Erection | itp |  |  |  | Yes | Raleigh Road Bus Lane - ITP - Traffic Signal Ducting and Pole Erection
checkpoint | 1 - Permits
note | H
note | Detail - Obtain Permits
note | Frequency - As required
note | Inspection / Test Method - Document Review
note | Conformance Criteria - Authorisation to work, dig permit and service provider permits
note | Records - This ITP signed
note | FH Initials - Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Design
note | H
note | Detail - Ensure that Design is approved and Drawings are of the latest revision
note | Frequency - Prior to commencement
note | Inspection / Test Method - Document Review
note | Records - Check Drawing Register
note | FH Initials - Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1 - Survey Setout
note | H
note | Detail - Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
note | Frequency - Prior to commencement
note | Inspection / Test Method - Survey
note | Conformance Criteria - Consistency with Drawings and Specifiactions
note | Records - Survey Records
note | FH Initials - Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 -
note | H
note | Detail - Confirm with Engineer/ATOC on site the exact locations of poles/controller/tactiles indicators.
note | Frequency - Prior to installation
note | Inspection / Test Method - Visual Inspection
note | Conformance Criteria - Consistency with Drawings and Specifiactions & sign-off by Engineer/ATOC.
note | Records - Photos / Engineers approval documentation
note | FH Initials - Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Locate existing services by hand digging/ hydrovac
note | W
note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
note | Frequency - Prior to Installation
note | Inspection / Test Method - Potholing
note | Conformance Criteria - All conflicts have been located and survey as built recorded
note | Records - Digging/Excavating Control Checklist
note | FH Initials - Site Engineer
checkpoint | 5.1 - Material Compliance
note | H
note | Detail - Ensure duct pipes and poles are as per drawings and specification
note | Frequency - Upon delivery to site
note | Inspection / Test Method - Ensure delivery docket matches materials
note | Records - Delivery Docket
note | FH Initials - Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 -
note | H
note | Detail - Ensure all concrete used is 20MPa mix for pole footings and concrete aprons around traffic assets.
note | Frequency - Upon delivery to site
note | Inspection / Test Method - Ensure delivery docket matches materials
note | Records - Delivery Docket
note | FH Initials - Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1 - Trenching
note | H
note | Detail - Inspect trench profile to ensure walls vertical, widths is 600mm max (two ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm/FP and 900mm cover under carriageway. Concrete capping detail to be followed where reduced cover is required due to existing services.
note | Frequency - 10m Intervals
note | Inspection / Test Method - Visual Inspection
note | Conformance Criteria - Consistency with Drawings and Specifiactions. Concrete capping detail - WSP IFC Drawings Sheet C126.
note | Records - Photos
note | FH Initials - Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 -
note | H
note | Detail - Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
note | Frequency - 10m Intervals
note | Inspection / Test Method - Measure
note | Conformance Criteria - Ensure trench alignment and levels match the design drawings
note | Records - Dipsheet & Photos
note | FH Initials - Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 -
note | H
note | Detail - The trench on the carriageway should be filled with Gap40 and compacted and on top reinstated with AC14 or similar & match existing asphalt thickness. The finished level to be match with existing road level
note | Frequency - Each Site
note | Inspection / Test Method - Visual Inspection
note | Conformance Criteria - Reinstatement as per designer acceptance
note | Records - Docket and photos
note | FH Initials - Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.1 - Duct Installation
note | W
note | Detail - Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
note | Frequency - Prior to Installation
note | Inspection / Test Method - Visual inspection
note | Conformance Criteria - Consistency with Drawings and Specifiactions
note | Records - Photos
note | FH Initials - Site Engineer
checkpoint | 7.2 -
note | H
note | Detail - Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
note | Frequency - 10m Intervals
note | Inspection / Test Method - Visual inspection
note | Conformance Criteria - Consistency with Drawings and Specifiactions
note | Records - Photos
note | FH Initials - Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.3 -
note | H
note | Detail - Asbuilt Survey
note | Frequency - 20m Intervals
note | Inspection / Test Method - Visual inspection
note | Conformance Criteria - Consistency with Drawings and Specifiactions
note | Records - Survey Records
note | FH Initials - Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Bedding
note | H
note | Detail - Lay min. 100mm gap20 or finer for bedding and haunching
note | Frequency - 10m Intervals
note | Inspection / Test Method - Visual inspection
note | Conformance Criteria - Consistency with Drawings and Specifiactions
note | Records - Photos
note | FH Initials - Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Warning Tape
note | H
note | Detail - Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
note | Frequency - 10m Intervals
note | Inspection / Test Method - Visual inspection
note | Conformance Criteria - Consistency with Drawings and Specifiactions
note | Records - Photos
note | FH Initials - Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.1 - Traffic signal pole erection
note | H
note | Detail - Ensure Design engineer & ATOC inspect pole locations prior to proceeding
note | Frequency - Per pole
note | Inspection / Test Method - Visual Inspection
note | Conformance Criteria - Sign off by design engineer
note | Records - Engineer sign off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.2 -
note | H
note | Detail - Ensure foundation hole excavation is as per design with required depths and widths
note | Frequency - Per pole
note | Inspection / Test Method - Measure
note | Conformance Criteria - Consistency with Drawings and Specifiactions
note | Records - Dipsheet & Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.3 -
note | H
note | Detail - Ensure Poles are plumb and within design tolerances
note | Frequency - Per pole
note | Inspection / Test Method - Visual Inspection
note | Conformance Criteria - Consistency with Drawings and Specifiactions
note | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - As-builts & C&I Diagram
note | H
note | Detail - As-built as per ATOC requirements
note | Frequency - At the completion of the Lot of work
note | Inspection / Test Method - Drawings
note | Conformance Criteria - As-built as per ATOC requirements
note | Records - Asbuilt Drawing
note | FH Initials - Site Engineer
holdpoint | AUTHORITY HOLDPOINT