## ITP - Stormwater
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # CTN-ITP-019
[11 empty] | Revision : 01 |  | Date: 10/08/23
Client: Department of State Growth |  |  |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Midland Highway Campbell Town North |  |  |  | Tree Planting |  | Name: | Liam Dale | Name: |  |  | Name:
Contract No: |  | 3170 |  | Specifications: Section 719
|  |  |  | Structure / Component: Landscaping |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: North of Campbell Town (Campbell Town to Epping Forest) |  | Date : |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | QAV | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings - all drawings are the latest revision - Conflicting documents will be referenced to the hierarchy of documents listed in Section 175.03 | Drawings and drawing registers Section 720 | Visual inspection | This ITP Signed | HP* | Site Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP | OHSMP, EMP, TMS, SWMS, WP | Visual Inspection | This ITP Signed | HP* | Site Engineer | N/A |  | N/A
1.3 | Provide records |  | As required, Prior to commencement of relevant work | - evidence of origin of indigenous provenance plant material - details of suppliers - soil tests on topsoil - copies of fertiliser labels | 719.02 | Verify | Records, This ITP signed | WP | Site Engineer/ QAV | N/A
2 | Materials
2.1 | Topsoil, Fertiliser and Mulch |  | Prior to any planting for each lot | Utilise locally stripped topsoils only, Fertilisers shall be suitable for the establishment of plant types, sizes and species specified in the plant schedule and Site created Mulch shall be used where possible - imported mulch must meet requirements of Table719.071 | 719.05, 719.07, Table719.071 | Verify | This ITP Signed | IP | Site Engineer | N/A |  | N/A
2.2 | Plants |  | Prior to any planting for each lot | Plants to be as per planting schedule (drawing 4795): PMA replacement trees to be 45L white peppermint (Eucalyptus Pulchella) | Planting Schedule | Verify | This ITP Signed | IP | Site Engineer | N/A |  | N/A
3 | Site Preperation and Planting
3.1 | Soil Ripping |  | Each Lot | Soil ripped as per Table720.061; 1. 25m2 of min 400mm deep at 500mm max spacing 2. In disturbed areas; place 150mm topsoil (leave uncompacted) 3. cross rip min 300mm deep at 500mm max spacing | 719.06, Table719.061 | Visual inspection | This ITP Signed | HP* | Site Engineer | N/A |  | N/A
3.2 | Fertilising, Planting and Mulching |  | Each Lot | - Holes to be dug to correct size for root ball, Holes in heavy soils prepared to ensure adequate drainage, Holes not left smooth sided in Basalt or Plastic soils - Planting holes shall be backfilled with friable topsoil, free of debris, rocks and clods greater than 50mm in diameter - Fertiliser is to be applied to all disturbed surfaces and the contractor shall fertilise advanced trees - Mulch, no less than 1.5 diameter and 150mm depth, will be applied around all planted trees | 719.07 | Verify | This ITP Signed | HP* | Site Engineer | N/A |  | N/A
3.3 | Initial Watering |  | Each Lot | The Contractor shall saturate each plant within 8 hours after planting. Cells and tubes shall be irrigated with a minimum 3 litres of water per plant. Other container sizes shall be irrigated with a volume of water greater than the container size. | 719.07 | Visual inspection | This ITP Signed | HP* | Site Engineer | N/A |  | N/A
4 | Maintenance
4.1 | Performance requirements |  | Each Lot | Where tree planting areas do not achieve the performance requirements detailed in Table 719.092 (below) they shall be replaced annually to achieve 100% of the original specified planting numbers. PREVIOUS 12 MONTHS RAINFALL - ADVANCED TREES MIN GROW RATE more than 750mm - 300mm per annum 500 - 700mm - 200mm per annum Less than 500mm - 100mm per annum | 719.09, Table719.092 | Verify | Lot Map | HP* | Site Engineer | N/A |  | N/A
4.2 | Watering and Re-Mulching |  | Each Lot | The Contractor shall water all plants, including seeded areas, as necessary to ensure continued healthy and vigorous growth from time of planting or seeding. Maintenance of areas mulched shall begin from the first planting | 719.09, Table719.092 | Verify | Lot Map | HP* | Site Engineer | N/A |  | N/A
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Fulton Hogan | Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent