## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CTN-ITP-019 - Tree Planting | itp |  |  |  |  | CTN-ITP-019 - Tree Planting
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | – Conflicting documents will be referenced to the hierarchy of documents listed in Section 175.03
label | Reference Documents - Drawings and drawing registers Section 720
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | Reference Documents - OHSMP, EMP, TMS, SWMS, WP
label | Inspection / Test Method - Visual Inspection
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 1.3 - Provide records
label | Frequency - As required, Prior to commencement of relevant work
label | Acceptance Criteria - Evidence of origin of indigenous provenance plant material
label | – details of suppliers
label | – soil tests on topsoil
label | – copies of fertiliser labels
label | Reference Documents - 719.02
label | Inspection / Test Method - Verify
label | Record of conformity - Records, This ITP signed
label | WP
label | Responsibility - Site Engineer/ QAV
date | Date Completed:
checkpoint | 2.1 - Topsoil, Fertiliser and Mulch
label | Frequency - Prior to any planting for each lot
label | Acceptance Criteria - Utilise locally stripped topsoils only, Fertilisers shall be suitable for the establishment of plant types, sizes and species specified in the plant schedule and Site created Mulch shall be used where possible - imported mulch must meet requirements of Table 719.071
label | Reference Documents - 719.05, 719.07, Table 719.071
label | Inspection / Test Method - Verify
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 2.2 - Plants
label | Frequency - Prior to any planting for each lot
label | Acceptance Criteria - Plants to be as per planting schedule (drawing 4795): PMA replacement trees to be 45L white peppermint (Eucalyptus Pulchella)
label | Reference Documents - Planting Schedule
label | Inspection / Test Method - Verify
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 3.1 - Soil Ripping
label | Frequency - Each Lot
label | Acceptance Criteria - Soil ripped as per Table720.061;
label | 1. 25m2 of min 400mm deep at 500mm max spacing
label | 2. In disturbed areas; place 150mm topsoil (leave uncompacted)
label | 3. cross rip min 300mm deep at 500mm max spacing
label | Reference Documents - 719.06, Table 719.061
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 3.2 - Fertilising, Planting and Mulching
label | Frequency - Each Lot
label | Acceptance Criteria - Holes to be dug to correct size for root ball, Holes in heavy soils prepared to ensure adequate drainage, Holes not left smooth sided in Basalt or Plastic soils
label | – Planting holes shall be backfilled with friable topsoil, free of debris, rocks and clods greater than 50mm in diameter
label | – Fertiliser is to be applied to all disturbed surfaces and the contractor shall fertilise advanced trees
label | – Mulch, no less than 1.5 diameter and 150mm depth, will be applied around all planted trees
label | Reference Documents - 719.07
label | Inspection / Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 3.3 - Initial Watering
label | Frequency - Each Lot
label | Acceptance Criteria - The Contractor shall saturate each plant within 8 hours after planting. Cells and tubes shall be irrigated with a minimum 3 litres of water per plant. Other container sizes shall be irrigated with a volume of water greater than the container size.
label | Reference Documents - 719.07
label | Inspection / Test Method - Visual inspection
label | Record of conformity - This ITP Signed
label | HP*
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 4.1 - Performance requirements
label | Frequency - Each Lot
label | Acceptance Criteria - Where tree planting areas do not achieve the performance requirements detailed in Table 719.092 (below) they shall be replaced annually to achieve 100% of the original specified planting numbers.
label | PREVIOUS 12 MONTHS RAINFALL - ADVANCED TREES MIN GROW RATE
label | ○ more than 750mm - 300mm per annum
label | ○ 500 - 700mm - 200mm per annum
label | ○ Less than 500mm - 100mm per annum
label | Reference Documents - 719.09, Table 719.092
label | Inspection / Test Method - Verify
label | Record of conformity - Lot Map
label | HP*
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | 4.2 - Watering and Re-Mulching
label | Frequency - Each Lot
label | Acceptance Criteria - The Contractor shall water all plants, including seeded areas, as necessary to ensure continued healthy and vigorous growth from time of planting or seeding. Maintenance of areas mulched shall begin from the first planting
label | Reference Documents - 719.09, Table 719.092
label | Inspection / Test Method - Verify
label | Record of conformity - Lot Map
label | HP*
label | Responsibility - Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Work Completed On:
date | Date: